Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Jordan CSSF: Economic Sustainability Programme (ESP)
Country and Region:	Jordan, Middle East and North Africa
IATI Unique ID:	CSSF-06-4017
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO), HM Revenue & Customs (HMRC), Office for National Statistics (ONS), Department for Business, Energy and Industrial Strategy (BEIS), Department for Education (DFE), Department for International Trade (DIT)
Total Budget:	ODA: £3.1m			Non-ODA: £0
Total Spend:	ODA: £2.2m			Non-ODA: £0
Original Programme Start Date: April 2018		End Date: March 2019
Outputs					Score
Research on inclusion of refugee window within the National Aid Fund (NAF) system					B
Improved technical capacity of National Aid Fund systems					A
Analysis and assessment undertaken to improve the communication and outreach for the expansion project of the National Aid Fund					A
Better understanding of Jordanian private sector structure, particularly international aspects and opportunities for growth					B
HMG identifies novel opportunities for technical assistance and exchange of best practice between UK and Jordanian government departments					A
HMG relationships with different Jordanian government departments initiated and strengthened, and mechanisms for coordination between members of the international community encouraged and supported					A
Overall output score: A
Outcome Assessment: B The technical assistance to NAF achieved the desired results, although the completion of the research is behind schedule due to factors outside of the programme’s control. The implementation of the HMG Peer-to-Peer partnerships has been slower than anticipated.
Final Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	N/A	N/A	N/A	A	B
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	Medium
*output/outcome scores

What support did the UK provide?

The programme provided:
- £0.75m for World Bank (WB) technical support to guide the Government of Jordan (GoJ) in the expansion and modernisation of the cash assistance programme;
- £1m for United Nations International Children's Emergency Fund (UNICEF) technical support to the expansion of the cash assistance programme;
- £0.25m for a WB research report on coherence between systems for cash assistance to Jordanians and assistance to refugees;
- £0.22m for Kick-Start the Partnership Programme (KSTP), which supported seven phase one peer-to peer or technical assistance (TA) workstreams.

What results did the programme deliver? Will they be sustained?

- By the end of this programme 309,000 Jordanians had applied for the cash benefits using the new system, and the new poverty targeting formula had been applied to them.
- A successful pilot of digital payments methods was run, demonstrating significant results in terms of reduced waiting times and restoration of dignity for the beneficiaries.
- UNICEF successfully delivered the Management Information System (MIS) and ensured National Aid Fund (NAF) had all the tools and human resources to manage the expansion. The MIS replaces a manual system that only allowed NAF to process 10,000 applications annually. This represents at least a 30-fold increase in capacity.
- Three memorandums of cooperation had been signed between the UK Government and the GoJ, demonstrating a positive step towards strengthening the bilateral relationship.

The results of this programme are likely to be sustainable from a National Aid Fund perspective as: staff have been trained in using and maintaining the MIS; re-running the targeting formula across all beneficiaries every year ensures effective application of the scheme; and the move to digital payments will be permanent, leading to a permanent increase in dignity for beneficiaries and expected improvement in the social contract as a result. Early results from KSTP work will be sustained by the UK Government taking a long-term approach to capacity development and relationship building with the Government of Jordan.

What lessons have been learned?

Appropriate levels of staffing, expertise, and clarity of roles and responsibilities are required to design and deliver projects at scale, particularly pilot projects which respond to Ministerial demand such as the ESP.

The GoJ-led approach, which involved joined-up working between Government and development partners has been successful and should continue and be emulated elsewhere. Use of a Technical Working Group and design of the poverty targeting formula were good examples of this.

Attempts to influence Government policy through research work needs to be informed by the context, and ensuring sound understanding of the relevant politics.

Formal asset disposal plans to be provided, when applicable, at close of programmes.

Formal scrutiny of budgets and benchmarking of costs should be undertaken to ensure that all components of projects reflect value for money at the economy level.

A more extensive survey of the beneficiaries to provide insight into achievement of outcomes should be considered to understand how CSSF funding has changed perceptions of Jordanian citizens. The MENA Monitoring Evaluation and Learning (MEL) contract could be considered to support this activity.

Realistic programme level outcomes should be discussed with the team and implementing partners and agreed early in the programme design. Project level results frameworks should feed into this. Updates to the programme level results framework should be systematic and documented in the project delivery plan. A project delivery plan should be developed and used throughout the programme lifecycle.

Better communication between teams, and clarity of roles will help develop load bearing relationships and maximise results.

Greater clarity in the form of an inter-departmental MOU could provide the necessary clarity going forwards.

High quality research has been delivered due to Terms of Reference which were informed by the context and sound understanding of the relevant politics.

Various models of TA provision could be explored to increase the efficiency of the process of matching GoJ with relevant HMG-funded support. This would allow for a greater scale up of work, more local specific knowledge and better political economy analysis.

Strengthened overall tracking of the KSTP projects, including setting milestones and links to the Political Access and Influence (PAI) framework will help to describe how the projects are contributing to this outcome.
Feedback forms and monitoring methods will be helpful to understand how the GoJ technical capacity is being increased.