Annual Review - Summary Sheet

PROGRAMME TITLE: Jordan CSSF: Political Stability Programme
Country and Region:	Jordan, Middle East and North Africa
IATI Unique ID:	CSSF-06-000016
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: £10.1m			Non-ODA: £0
Budget this FY	ODA: £10.1m			Non-ODA: £0
Spend this FY	ODA: £9.7m			Non-ODA: £0
Original Programme Start Date: April 2018		Planned End Date: June 2021
Outputs					Score
Capability built for strategic government communications (Government Communications Services International (GCSI) Cabinet Office)					B
Systematic approach for scrutiny of legislation and its implications for citizens piloted (Global Partners Governance (GPC))					C
Municipal and governorate councils understand community needs and priorities (World Bank, Municipal Services & Social Resilience Project (MSSRP) and GPC)					A
Municipal and governorate councils technically and financially more capable of delivering services (World Bank, MSSRP and GPC)					A
Sustainable infrastructure in target locations meets the needs of the community (Mercy Corps)					B
Community leaders sustainably better at negotiation, in target locations (Mercy Corps)					A
Youth, women and refugees have more opportunities to engage politically (GPC and Mercy Corps)					B
Tensions and underlying drivers of conflict within Jordan are tracked and understood (Mercy Corps)					A
New interventions scoped, and research and lesson learning conducted (mainstreamed throughout programme)					B
Gender sensitivity and conflict sensitivity and sustainability considered and embedded in all programme activities (mainstreamed throughout programme)					A
Overall output score					A
Outcome Assessment: / The programme has elements of conflict reduction/prevention; developing trust in government, and supporting/communicating Government of Jordan existing policy. This represented a more diffuse mix of projects that limited the overall outcome level score and this translated into less overall impact. The review team assessed the MSSRP and Mercy corps programmes as being particularly successful.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	N/A	N/A	N/A	A	B
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	Medium
*output/outcome scores
How has the programme changed during this period? / This programme succeeds the Community Conflict Reduction Programme (FY15/16 to FY17/18), elements of which have been carried forward into this new programme, in particular MSSRP and the Mercy Corps project. The programme has absorbed legacy programmes since 2017. Focus has moved away from an emergency response Syrian-driven programme and towards addressing the structural drivers of instability in Jordan, working in geographical locations where grievances and complaints directed towards government are most evident.

What support did the UK provide in FY 18/19?

The World Bank executed Municipal Services and Social Resilience Programme (MSSRP) strengthened state capacity by making its most local level of government, Municipal Authorities, more capable and accountable in delivering services to all their residents, including supporting local job creation and encouraging Public Private Partnerships through the Innovation Fund (IF).
- Mercy Corps delivered conflict-prevention techniques & essential infrastructure to areas most at risk of directing tensions against the state, helping to cultivate more transparent, responsive and inclusive local government institutions
- Global Partners Governance strengthened decentralised governance providing technical assistance to governorate councils and supporting parliamentary reform.
- Technical assistance provided by GCSI to the Prime Ministry on strategic communications.

Key results for FY 18/19:

- Proven evidence for social cohesion at local community level e.g. 414 Community Leaders trained in basic conflict management skills; 267 Youth Leaders trained in life skills; and 356 community based activities to promote social cohesion implemented, benefiting 64,850 individuals. 86% of programme participants demonstrated an increase in knowledge of conflict resolution.
- The cross-Government of Jordan (GoJ) Department Communication Grid to ensure cohesion of key public communication has been adopted and is in use.
- Institutional change at municipal level through GoJ adopting the Innovation Fund and extending the reach beyond the programme focused areas has led to more socially relevant projects (such as employment creation and focus on women and youth).

Summary of progress and lessons learnt/actions taken since last review

The programme team have developed a compelling and open approach to lessons learning and have embedded the key lessons drawn from evaluations and wider discussions with the programmes. There is a lessons learning framework that tracks recommendations and action taken. There has not been a programme level Annual Review completed for FY17/18 however the main lessons drawn from the evaluations of the MSSRP and Mercy Corps programme have been accepted and enacted by the team.

Summary of recommendations for the next year

- Redesign the programme to ensure more focused and mutually supporting programmes that allow for better outcome and impact
- Integrate truly adaptive programming with a strong investment by the Embassy’s political team at the design stage to allow the programme to reflect the local political economy
- Build in a core Political Access and Influence component to capture and enhance a whole of mission stake in outcome level change. Consider how to capture the influence element more comprehensibly.
- Develop a Value for Money (VfM) strategy to guide the approach to delivery partners and ensure a more equitable use of targeted resources
- Build the new programme on a comprehensive evidence base and focused on how UK funding can influence change in the areas identified as being the most critical to Jordan’s political stability.
- A new Theory of Change (ToC) should be adopted and consideration given to challenging some of the underlining assumptions should be built in to the programme design.
- Results framework should have more qualitative indicators to demonstrate the change of behaviour at outcome level
- More Monitoring & Evaluation (M&E) advice and support needed to design adaptive programme and enable outcome harvesting and more outcome-orientated M&E
Establish a clear and consistent approach to contract management of implementing partners that allows for a baseline of common delivery standards with all Implementing Partner’s but allows nuances to reflect working relationships between UK Government colleagues.