 Annual Review - Summary Sheet

PROGRAMME TITLE: Lebanon CSSF: Community Stability Programme
Country and Region:	Lebanon, Middle East and North Africa
IATI Unique ID:	CSSF-06-000020
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget:	ODA: £38.1m			Non-ODA: £3.2m
Budget this FY:	ODA: £13.1m			Non-ODA: £0.1m
Spend this FY:	ODA: £13.1m			Non-ODA: £0.1m
Original Programme Start Date: April 2016		Planned End Date: March 2019
Outputs					Score
Reduction in tensions between/among communities and local government over Solid Waste Management and Recycling					A
Reduction in tensions between/among communities and local authorities, through increased provision of services and livelihood opportunities					A
Targeted at risk youth are involved in positive coping mechanisms, reducing the vulnerability to recruitment by violent extremist organisations (VEOs)					A+
To alleviate the loss of long-term livelihoods for farmers through the rehabilitation of fruit tree orchards and agricultural equipment					A
Overall Output Score					A
Outcome Assessment: Projects have individually delivered well in a turbulent year for social stability in Lebanon, meeting all project output targets. The programme has fallen marginally short of outcome targets, amidst challenges in the local and regional stability environment.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	A	A	A	B
Risk Rating - low/medium/high	High	Medium	High		High
*output/outcome scores
How has the programme changed during this period? / Over the course of the programme, it has incorporated a ‘Stabilisation Theme’, which focuses on swift responses to adapt to in-year developments, including rapid demining and livelihood support. One of the projects, Improved Network training and Jobs (INTAJ), has passed two of its three areas of support into DFID Lebanon’s Economic Development programming, demonstrating the catalytic nature of CSSF programming in Lebanon.

What support did the UK provide in FY 18/19?

The CSSF Lebanon Community Stability Programme focuses on building resilience and deterring conflict and violence in the most vulnerable communities in Lebanon by addressing tensions between and among Lebanese host communities and refugees. It operates in the most conflict-vulnerable areas across the country.

Key results for FY 18/19

- Over 390,000 direct beneficiaries from UK-supported community projects in Lebanese municipalities, driven by municipal-level decision-making bodies, which has driven over 20,000 households’ improved perception of local governments’ ability to meet to community needs.
- Over five million youths engaged through UK-funded social media projects (including against sexual violence); 75% of youths with grant-awarded projects refraining from engaging in violent or corrupt practices.
- Over 390,000 direct beneficiaries of completed municipal services projects, identified and implemented through local, inclusive governing bodies established by CSSF funding.
- 27 avoided casualties from demining in Arsal (Northern Lebanon), nearly 3,000m2 of land demined, and 65% farmers reporting improved potential to generate income through rehabilitated farms.

Summary of progress and lessons learnt/actions taken since last review

Progress has been made since last year’s review, including on communications, gender, monitoring and evaluation, and use of UK Government expertise.

Summary of recommendations for the next year

Strategy: The programme should ensure a consistent cross-portfolio narrative with coherent objectives to ensure greater impact. A clearer strategy on long-term CSSF programming, hand-over planning, and communication of this with other teams at the Embassy should also be produced.

Network, Coordination, and Outreach: The programme team should look to better coordinate – across a variety of stakeholders – their programmes, using networks and outreach opportunities to streamline operations and catalyse synergies.

Monitoring and Evaluation (M&E), and Theory of Change (ToC): The programme should use econometric techniques to track counterfactual perceptions in non-targeted communities, against which outcome targets should be set. Using central M&E resources may help further refine, test and adapt the ToC. In line with the ToC refresh, a new Logframe should be created that tracks outputs at a CSSF Stability portfolio level.

Adaptiveness and Programme Agility: Procedures could be further enhanced to ensure swiftness of UK Government response to emerging issues.

Conflict Sensitivity: A number of conflict sensitive reviews have been carried out on CSSF security programme, and, where applicable, the Stability programme team should learn from the review outcomes and incorporate learning/recommendations in future programming.

Gender: Implementation Partners should be encouraged to conduct gender research at scoping stage, and a gender analysis at project initiation stage, to identify and safeguard specific gender needs, and ensure these are addressed through project activity.