Annual Review - Summary Sheet

PROGRAMME TITLE: Lebanon CSSF: Security Programme
Country and Region:	Lebanon, Middle East and North Africa
IATI Unique ID:	CSSF-06-000005
HMG Partners	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £17.1m		Non-ODA: £28m
Budget this FY	ODA: £8.1m		Non-ODA: £7.6m
Spend this FY	ODA: £8.1m		Non-ODA: £7.5m
Original Programme Start Date: April 2016			Planned End Date: March 2019
Outputs				Score
Lebanese Armed Forces (LAF) company groups trained and able to better deliver internal security operations that are compliant with International Humanitarian Law and Law Of Armed Conflict				A+
LAF Land Border Regiments trained and able to plan and conduct proactive land border operations while improving community engagement and securing the trust of the local population				A+
Roll out Community Policing Model based on police-public partnerships mainstreamed at Police of Beirut (PoB) HQ and 1st Territorial Company including community policing training, Command and Control functions and consolidation of the links with Human Right standards				A
Vulnerable youth (including men, women, boys and girls) supported to be positive elements in their societies promoting diversity and coexistence, with a focus on Tripoli and Beirut				A+
Grow the religious discourse to promoting the values of democracy, citizenship and human rights among the youth and vulnerable communities				B
Overall output score				A
Outcome Assessment: / LAF able to effectively contribute to maintaining Lebanon's external security and management of its land border with Syria (A) / LAF and ISF better able to effectively contribute to maintaining Lebanon's internal security (A) / Vulnerable groups in flashpoint areas becoming more resilient to conflict and extremist thoughts and radical religious narratives (A)
Outcome Score: A		Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	A	B	A	A
Risk Rating	High	High	High		High
*output/outcome scores
How has the programme changed during this period?: N/A

What support did the UK provide in FY 18/19?

Through the CSSF Lebanon Security Programme, the UK has been addressing three key strands of security threats to Lebanon:
- External security by supporting the LAF to strengthen their presence and authority at the border;
- Internal security by building the capacity of the LAF and Internal Security Forces (ISF) to manage internal security threats, and;
- Violent extremism by supporting vulnerable, at-risk youth to become more resilient to extremism, including through engagement with religious leaders and religious journalists.

In FY 18/19, the programme also supported three pilot projects focussed on strengthening social cohesion, prisoner rehabilitation, and youth social services.

Key results for FY 18/19

The programme made important progress in its three strands over the last year:
- External security strand - the programme completed the establishment and training of the fourth LBR, including by installing its Protected Border Observation Posts (PBOPs) and Forward Operating Bases (FOBs). 208 LBR troops were trained in rural operations and 1,873 troops in specialist “deter, detect, deny, and disrupt” skills, and troops from all four LBRs were mentored in planning and conducting rural and border operations.
- Internal security strand - the programme supported the LAF to dispense its internal security role by training nearly 9,500 LAF troops in urban operations. The programme also continued to build the capacity of the ISF to deliver its 2018-2022 Strategic Plan, including the roll out of the community policing model; strengthening the PoB’s data analysis and planning capability; and supporting the Inspectorate General’s Human Rights Division to assess and publish regular human rights bulletins.
- Preventing Violent Extremism (PVE) strand - the programme project engaged 392 youth in Tripoli and Beirut from different confessional backgrounds to work together to promote reconciliation and inter-confessional trust. The programme also trained 23 religious leaders and 28 religious media journalists to better engage with their communities and audiences to deliver projects and messages of inter-religious tolerance and respect.

Summary of lessons learnt

- Due to the hierarchical nature of security institutions, efforts should be concentrated not just on developing processes and procedures at different levels of the organisation, but also on facilitating internal relationships and enabling partnerships between different levels.
- Participatory governance structures are essential to the delivery of projects for all stakeholders – Embassy, implementing partners, other donors, and beneficiaries.  These should be fit-for-purpose, tailored to each project, but across the board need to facilitate conversations around challenges, concerns and new opportunities.
- Attracting marginalised youth with work opportunities is essential to incentivising their participation in activities that would allow their reintegration in their communities. Psychosocial support is key combined with other activities (culture, sports, anger manager, interpersonal skills, exposure to other communities, etc.)
- Conflict sensitivity is embedded in the programme and well understood by implementing partners, but there are additional ways that conflict sensitivity can be strengthened going forward.

Summary of recommendations for the next year

The CSSF programme team should:
- With support from the Conflict Adviser and a Monitoring & Evaluation (M&E) Adviser, further strengthen the new 2019-2022 programme theory of change and, from that, produce a new programme-level results framework.
- Keep the momentum on the strategic review process launched key stakeholders at post and in London to agree the best way forward in how HMG supports the LAF.
- Ensure that any future training provided to the LAF is subject to robust quality control and quality assurance standards.
- Ensure that the next phase of support to the LAF builds on and deepens previous community engagement work, and strengthens linkages with the ISF.
- Translate the efforts to support the longer-term transition of internal security responsibilities from the LAF to the ISF into a strategy.
- Work closely with other ISF donors to coordinate policy for a more united international front for influencing Ministry of Interior and ISF leadership.
- Incentivise greater collaboration between the Countering Radicalisation through Art and Culture (CRAC) and Religious Leaders for Diversity and Coexistence (RLDC) projects, and engagement between both projects and security institutions, to maximise results.
- Develop a tracker to allow the team to track progress against the implementation of Annual Review recommendations.