Annual Review - Summary Sheet

PROGRAMME TITLE: Morocco CSSF Programme
Country and Region:	Morocco, Middle East and North Africa
IATI Unique ID:	CSSF-06-000007
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Home Office (HO), Ministry of Defence (MoD)
Total Budget:	ODA: £6.8m			Non-ODA: £0
Budget this FY	ODA: £3.9m			Non-ODA: £0
Spend this FY	ODA: £3.9m			Non-ODA: £0
Original Programme Start Date: April 2017		Planned End Date: March 2021
Outputs					Score
Young women and men in target groups supported to increase capacity for employment					B
Women and men, and their civil society organisations, supported to increase capacity to hold government to account with non-violent, evidence-based strategies/tactics.					A
Selected national and regional institutions (government and parliament) supported to increase service delivery capacity and responsiveness to citizens.					B
Government supported to identify, design and implement practical and policy penal reforms in line with Mandela Rules					A
Political access and influencing undertaken by the UK Government (including with and through implementing partners), delivering political engagement, strategic communication and lesson learning to evolve future programme adaptations					A
Overall output score					B
Outcome Assessment: A
Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2016/17	2017/18		2018/19
Programme Score	B	A	B	B	A
Risk Rating - low/medium/high	Medium	High		High

What support did the UK provide in FY 18/19?

- The CSSF provided £3.9m to support delivery of political and economic initiatives, to address the supply and demand drivers of stability at the local and national level in Morocco.
- The programme has projects to support better governance, provide better education and employment opportunities, meet the needs of underprivileged groups, to reduce vulnerabilities of citizens.

Key results for FY 18/19:

- Support to the Moroccan government reforms on implementing regionalisation through new systems and structures that enable citizens and power holders to formally engage with each other (strengthening the state-citizen contract). A tangible example of governance working at the regional level is the decision by the Regional Council of Tangier Tetouan and Al-Hoceima to take forward four economic proposals submitted by local Civil Society Organisations (CSOs).
- Marginalised youth are better integrated in the formal school system through the provision of tuition, pedagogical and psychological support as well as extra-curricular activities. Support to Education for All in the Atlas Mountains has contributed to raising the issue more widely of the importance of education for girls, resulting in 99% of targeted young women remaining in education. Through the International Organisation for Migration project 658 disadvantaged young people received vocational training/internships, and 2011 disadvantaged young people from Tanger-Tetouan-Al Hoceima (TTAH) received support for continued education.
- Work with Parliament and CSOs has contributed towards greater transparency, accountability and state-citizen engagement. Tangible examples include the implementation of Article 148 in the Morocco Constitution where the Court of Accounts assists the Parliament in the domains of control of the public finances; activities to promote Parliamentary communication outreach to citizens; and capacity building of CSOs to conduct research in order to influence policy making.

Summary of progress and lessons learnt/actions taken since last review

The programme has progressed well from FY17/18 with improved monitoring and evaluation systems that support an evidenced based approach. With improvements to the Theory of Change and Results Framework, and support through the North Africa Monitoring, Evaluation and Learning (NAMEL) contract, results are being analysed, both intended and unintended, and the programme team should feel confident to adapt programming as a result.

Support to further develop the approach to programme risk management, value for money and implementing partner management remains required. A gender audit and conflict sensitivity analysis have been completed and the next step is to ensure that the findings are integrated into programme delivery.

Summary of recommendations for the next year

To continue to build on programme and political synergies. To agree on governance structures, roles and responsibilities and plans that facilitate a joint effort to deliver the embassy vision for Morocco.

Ensure the level of ambition and risk appetite for the programme and its projects are understood and agreed between embassy staff, implementing partners and beneficiaries.

To improve value for money (VfM) with attention to sustainability, the multiplier effect, and ability to monitor the effectiveness, efficiency and equity of projects so that they can be adapted in a timely way as necessary.

To review training needs for programme staff, Embassy staff involved in CSSF work, and local implementing partners. To create a training plan (potentially cross-North Africa). Areas identified include; risk management, gender and conflict sensitivity, VfM and management of implementing partners (contract management).