Annual Review - Summary Sheet

PROGRAMME TITLE: North Africa Fund for Regional Cooperation (RCF)
Country and Region:	North Africa Regional, Middle East and North Africa
IATI Unique ID:	CSSF-06-000021
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Home Office (HO), Ministry of Defence (MoD)
Total Budget:	ODA: £4.1m			Non-ODA: £0
Budget this FY	ODA: £2.3m			Non-ODA: £0
Spend this FY	ODA: £2.3m			Non-ODA: £0
Original Programme Start Date: April 2018			Planned End Date: March 2021
Outputs					Score
Support for a diverse group of organisations (multilateral, regional and national) to bring together gender sensitive networks of (CSO, state actors, individuals) on regional issues.					A
Support for organisations and institutions to build capacity of staff to engage on regional issues in North Africa					A
Support for political access & influencing by UK Government (political engagement, strategic communication, lesson learning, programme incubation & adaptations)					B
Overall output score					A
Outcome Assessment: A		Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	C	A	B	A	A
Risk Rating - low/medium/high		Medium/High	Medium		Medium
*output/outcome scores
How has the programme changed during this period? / The programme has undergone substantial refinement over the review period. Following recommendations from the Annual Review conducted at the end of Financial Year 17/18 (AR 17/18), the programme team have revised their strategic approach, reviewing the underlying theory of change, and amending the project portfolio as a result. There have been two projects added to the programme: The North Africa Dialogue Series, in partnership with Chatham House; and the North Africa Cooperation on Smuggling and Trafficking project, in partnership with the UN Office for Drugs and Crime. The RCF has achieved the outcome milestones set for the FY.

What support did the UK provide in FY 18/19?

The CSSF provided £2.28m of financial support to deliver technical assistance, research, policy advocacy, capacity development, monitoring and evaluation support and network development to support greater regional cooperation and integration on key transnational threats and cross-regional opportunities.

Financial Support (£138,468) to Chatham House develop the North Africa Dialogue Series, building a high-level trusted network of stakeholders to identify opportunities and means for regional cooperation on key issues.

Financial support (£499,494) to the Carnegie Middle East Centre to implement the Civil Military Relations in Arab States (CMRAS), a project to improve the role civilians are able to play in defence affairs in two North African countries (and two non-North African Arab countries).

Financial Support to ITAD (£654,990) to implement the NAMEL a project to help CSSF programme teams across the region develop their MEL approaches and to provide case studies that help ‘tell the story’ behind bare results data.

Financial support (£975,849) to UN Women to implement the Gender Equality Violent Extremism in North Africa (GENEVA) research agenda, a research project to collect primary and secondary research data in Morocco, Tunisia and Libya on the gendered dimensions of drivers for joining violent extremist groups.

While not providing further funds within the review period, the programme team continued to monitor disbursements made in FY 17/18 to the World Bank and to the European Bank for Reconstruction and Development, advocating for the strengthening of each project.

Key results for FY 18/19:

- UN Women successfully convened two civil society and academic institution networks on the role of women in tackling extremism and radicalisation in North Africa.
- Carnegie Middle East Centre finalised data collection for the Global Defence Atlas and delivered capacity development training on gender and the military.
- Chatham House successfully convened two research dialogues on illicit trade, security and economic alternatives in Morocco and Tunisia. They established core working group membership of two members from each North African country, ensuring women are represented.
- UN Office for Drugs and Crime (UNODC) started to develop a network of judges, prosecutors and law enforcement officials for greater cooperation on tackling criminality linked to trafficking and people smuggling, delivering two training sessions.
- The World Bank has adopted an analysis based approach to its regional coordination pillar, restructuring the Multi Donor Trust Fund’s objectives and operations to make it better suited to meet regional needs and to better align with the revised World Bank MENA strategy.

Summary of progress and lessons learnt/actions taken since last review

The RCF conducted a strategic review of the fund, developing a new approach to North Africa regional programming in response to recommendations in of AR 17/18 and in order to create a better ‘fit’ with the wider North Africa portfolio. Consequently, FY 18/19 was a year of transition where new projects were added to the portfolio and greater efforts were made to acclimatise internal and external stakeholders to the new strategic approach.

- The programme’s strategic approach was revisited for this FY, reassessing strategic objectives and testing the underlying assumptions. A Theory of Change workshop was convened in Cairo and included representatives from political teams from Posts across the region.
- A detailed VfM proposition was developed in December 2018 for inclusion in FY 19/20 programme document.
- Each project has an internal advisory lead. On gender, conflict sensitivity and human rights, all partners ensure expertise is at a minimum mainstreamed.
- The RCF has developed new indicators to measure delivery at output level, and adjustments made to outcome indicators to help assess level of change. These were approved by the NAMEL team.
Summary of recommendations for the next year

- Use the upcoming Carnegie Middle East Centre internal review to consider streamlining or restructuring the project. The internal review will be an opportunity to revise objectives, focus on the most impactful elements of the project, and revisit expectations on reporting.
- Increase engagement with internal stakeholders across North Africa CSSF to better link up regional and bilateral programming.
- Clarify the relationship between programme level results framework and project results frameworks, ensuring project level frameworks are kept up to date where appropriate.
- Improve lessons capture and learning synthesis, with a view to contributing towards the evidence base for adopting a regional approach to national and trans-national issues.
- Work with conflict advisers in NAJU and at post to develop country and regional conflict indicators for the programme RF to formalise routine conflict and contextual analysis.
- Revise programme level risk register to include consolidated security and delivery. Identify triggers for programme risks and developing indicators for reporting on risk trajectory at the programme level.
- Translate assumptions into risks (i.e. ‘what happens if this assumption does not hold true’) and develop a set of indicators. The ToC workshop identified assumptions that underpin the RCF, these need to be more explicitly carried over into the risk register and indicators developed.
- Recommend the RCF review NAMEL VfM as part of their refined VfM proposition in FY 19/20. Particularly focusing on the VfM provided by the NAMEL support to bilateral CSSF country teams.