Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria CSSF: Support for the Southern Syria De-Escalation Area (DEA) Programme
Country and Region:	Syria, Middle East and North Africa
IATI Unique ID:	CSSF-06-000026
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MOD)
Total Budget:	ODA: £3.26m			Non-ODA: £3.5m
Total Spend:	ODA: £6.37m			Non-ODA: £3.5m
Original Programme Start Date: April 2018		End Date: November 2018
Outputs					Score
Emergency search and rescue and medical support capability					A
Quality learning opportunities available in formal and non-formal education spaces					A
Livelihoods opportunities maintained and developed					C
Increased capacity and ability of local councils to deliver services and increased engagement between communities and local councils					B
Basic community policing, security and justice services provided					C
Overall output score					B
Outcome Assessment: Programme outcomes were not consistently achieved – mainly because of the South’s rapid fall to the regime in June/July 2018. Nevertheless, the programme performed well in critically important and deliberately pursued areas. The programme served political purposes and occasioned close cooperation with the US and Jordan, and individual projects delivered critical humanitarian type and protection objectives when the regime offensive began.
Final Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19*
Programme Score	NA			B	A
Risk Rating	NA			High
*output/outcome scores
Some projects in this programme were extended from the 17/18 Syria Security and Cross Cutting programmes including those supporting community policing, emergency search and rescue and medical support capability.

What support did the UK provide?

The UK delivered three months of a planned 12 month £24.07mm programme intended to help sustain the De-escalation Area (DEA) in Southern Syria agreed between the Russians, US and Jordanians. The UK sought a resilient DEA that would give the region the best possible chance of securing a future in a political process, prevent growth of extremism, protect Jordanian and Israeli borders, and mitigate the worst effects of the conflict even in the event of military takeover. The programme was comprised of a package of support to civilian institutions and civil society in the sectors of policing, education, livelihoods, governance, medical services, civil defence, stabilisation and peacebuilding activities.

What results did the programme deliver? Will they be sustained?:

The programme made modest progress in the first quarter, but was curtailed in June/July 2018, with the regime offensive and rapid collapse of the DEA. Contingency plans were put into action, and some projects made a sharp pivot towards humanitarian type activities. The programme was therefore unable to deliver planned output level results but succeeded in strengthening resilience and reducing suffering of the population. This was achieved both through the effective provision of humanitarian type assistance during the military takeover, and supporting the DEA for as long as possible to influence a less violent military takeover.

Lasting and sustained benefits are yet to be determined but are likely to include the lives saved through reduced violence and the provision of assistance.

What lessons have been learned?

In any rapidly changing context, routine update and challenge of contingency plans is essential. A flexible approach can create options to adapt stabilisation and development activities to support humanitarian type objectives in crisis. This can be supported by actively preparing for different scenarios which may emerge, to identify triggers to understand the emerging changes, and how and where a project may be able to flex to provide new support.

While formal coordination between stabilisation and humanitarian activities may not be possible, in part for reasons of principle, communication often is possible. Information and data sharing can help humanitarian and stabilisation actors understand needs and respond accordingly.

Where long-term development programmes such as value-chains based sustainable livelihoods are implemented in contexts with uncertain and potentially quite short timelines, a deliberate approach is needed to adapt activities to deliver (some) effects quickly, while also pursuing longer-term outcomes.

Remote programming presents significant challenges and requires intensive management but can achieve impressive results. Clarity on risk ownership and appetite are particularly important given the significant risks involved.

The UK Government should improve articulation and tracking of political objectives. This would enable a more accurate assessment of this type of politically driven programme, particularly in a context in which they may have not delivered all of their on the ground outcomes. The programme developed an innovative influencing and access monitoring tool which was unfortunately not implemented before closure but which may provide a useful model for monitoring political outcomes in contexts where access is highly restricted.