Annual Review - Summary Sheet

PROGRAMME TITLE: Tunisia CSSF Programme
Country and Region:	Tunisia, Middle East and North Africa
IATI Unique ID:	CSSF-06-000028
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD) and Home Office (HO)
Total Budget:	ODA: £23.7m			Non-ODA: £0.3m
Budget this FY	ODA: £9.2m			Non-ODA: £0.3m
Spend this FY	ODA: £8.37m			Non-ODA: £0.27m
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
1: Young people in Tunisia supported with English, literacy, numeracy and soft skills to improve their ability to access employment opportunities.					A
2: Micro Small and Medium Enterprises (MSMEs) supported with technical and financial support to facilitate their growth.					B
3: Tunisian government civil servants supported to implement key economic reforms relating to a) public enterprise and b) state-owned enterprise.					A
4: Support for creating conditions required to boost Tunisian trade and investment with other states, including the UK.					Covered by Outputs 2, 3, 5 & 6
5: Support for improving government mechanisms to prevent corruption.					A+
6: Support for improving government strategic communications capability and coordination.					A
7: Support for strengthening Tunisian government strategic planning capability and building the capacity to counter violent extremism.					A
8: Support for the Tunisian authorities to strengthen their capability to manage and enforce border security.					A
Overall output score: A
Outcome Assessment: A
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16 **		2016/17 **		2017/18*				2018/19*
Programme Score	A	A	A	A	B	B	B	A	A	A
Risk Rating - low/medium/high	M (Both)	M (Both)	M (Both)	M (Both)	M (Security)		M (Economic & Governance)		M
*output/outcome scores
How has the programme changed during this period? / ** Two programmes merged to one FY18/19

What support did the UK provide in FY 18/19?
The Tunisia CSSF Programme followed a two-track approach to i) Support reformers and government institutions to address long term structural problems; and ii) Work at the local level to bring immediate benefits to the most vulnerable and marginalised citizens and to demonstrate that an improvement in lives is possible. Delivering against Her Majesty’s Government (HMG) North Africa Strategy, it comprised of 12 projects under four strands.

- Economy (three projects) to: Support implementation of key economic reforms and unblocking barriers to the development of strategic sectors, mainly finance, education, ICT/entrepreneurship, agriculture and healthcare; help Tunisia liberalise and diversify its economy, create sustainable employment opportunities, and improve the business environment to boost Tunisia’s prosperity and UK trade and investment opportunities; create access to jobs, promote entrepreneurship with a focus on women, expand support to small and medium enterprises (SMEs), and their access to finance.
- Governance (two projects) to: Support Tunisia improve capability to strategically communicate with its citizen on key issues (such as economic reforms); identify and manage corruption risks; and deliver change to those in marginalised regions and help address grievances.
- Education (two projects) to: Support development of a system to reduce the number of school drop outs and give an opportunity for those that have dropped out to re-enter the education system, supporting employability; modernise English language education for employability; tackle inequality in education between the regions and genders.
- Security (five projects) to: Increase responsiveness, accountability and effectiveness of the Tunisian security and justice sector, including on human rights; reduce the likelihood of terrorism and violent extremism; and strengthen Tunisia’s border capability.

Key results for FY 18/19:
- Security: Refurbishment of six new National Police and Guard stations, bringing total to 14; six new Local Security Committees formed give sustainability to partnership fostering with citizens through civil society organisations; six capacity development interventions supporting Tunisian personnel security and justice system to plan and implement responses to key security threats; four documents delivered by strategic planning bodies to address key security threats; four interventions supported the development and roll-out of a Training Quality Manual for the Centre of Excellence for Explosive Ordnance Disposal Training.
- Education: 2000+ teachers across all 24 regions of Tunisia registered for online training with 504 (68% female, 32% male) so far completed; 10 Teacher Educators (eight female, two male) obtained accreditation in Professional Award in Teacher Education at NILE UK, with further 42 working towards accreditation in Professional Award in Teacher Education; ministerial visit to UK for bilateral talks, school visits, and sharing best practice; five workshops/conferences/national meetings/training events for key stakeholders from all regions of Tunisia; three technical committees set up and working on key issues; language benchmarking exercise (for 50% of teacher educators).
- Governance: 124 officials trained in audit reports (70 women), 127 in risk management (54 women), and 164 in citizen charters (63 women); launch of a strategy and a series of good practice tools for integrating risk management across public processes and activities; 73 officials (48 female) trained in strategic communications and coordination across target ministries involved in the different strands of strategic communication campaigns; two national communications campaigns (one in economic reform, one in entrepreneurship); three scans carried out to review steps in public service delivery (health, tax and waste management).
- Economy: 111 entrepreneurs selected to receive financial support (91 of their projects created as business enterprises and 30 so far fully received grants); 115 jobs have been created (77 permanent, 28 temporary and 10 internships - with women represented at 43%); 14 inter-ministerial collaborative workshops; three inter-ministerial awareness raising events; seven coaching sessions.

Summary of progress and lessons learnt/actions taken since last review
The programme has come a long way since Financial Year (FY) 17/18 following the consolidation of two programmes into one, with a sound action plan addressing the last Reviews’ recommendations, and supporting an integrated approach across the Embassy. The significant work on Monitoring & Evaluation (M&E) tools Gender, Conflict Sensitivity, Risk and use of the central Technical Assistance Fund has underpinned the performance of the programme, which has entered into better concrete delivery. Cross-Embassy/Donor mechanisms have enhanced decision-making and programme design. There is overall good progress within the constraints of this readjustment year, and the institutional barriers and other issues faced. However, the majority of benefits and results of effort will not come to fruition until FY19/20.

Summary of recommendations for the next year
- The Reviewers endorse the programme’s direction on graduating from a direct ‘Preventing/Countering Violent Extremism’ focus for security projects (to rest with Counter-Terrorism Hub interventions) to that of ‘Local/community level conflict prevention and peacebuilding’ and ‘Security Sector Reform’ (with a good governance angle). But working closely with other teams, the Programme Team should continue to oversee progress towards Outcomes of transferred and/or closing projects. Project Completion Reports should be undertaken on those closing.
- To strengthen M&E further, the Programme Team should, without delay, do further work with the North Africa Monitoring, Evaluation and Learning (NAMEL) contract assistance to a) Review indicators, milestones and targets in the FY19/20 Results Framework to enhance measurability and ensure they aid the necessary indication of impact; b) Commission evaluations on more established projects; and c) establish further evidence gathering methods and more robust metrics to assess Outcome progress at both project and programme level.
- Establish a methodology to measure Value for Money (VfM) better, whether via a VfM Framework or integrating VfM indicators into Results Framework. And in line with the above M&E recommendation, when a figure is used as a milestone e.g. x workshops/y trained, define and record the goal/skills etc. to be achieved at outset of each activity and track ongoing impact of these.
- Whilst there is a clear willingness of Government of Tunisia to engage and act on Conflict, Stability and Security Fund (CSSF) projects, the Programme Team should ensure robust mitigation measures against reversal of this, potential bureaucratic processes and ministerial conflicts and rivalries.