Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria CSSF: Whole of Syria Support to a Political Process Programme
Country and Region:	Syria, Middle East and North Africa
IATI Unique ID:	CSSF-06-000027
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £9.14m			Non-ODA: £0
Total Spend:	ODA: £5.35m			Non-ODA: £0
Original Programme Start Date: April 2018		End Date: March 2019
Outputs					Score
1: Support to the political process and dialogue amongst influential Syrians (Track I/II)					A
2: Rights and Accountability					A
3: Women’s Empowerment					A
Overall output score:					A
Outcome Assessment: B
Final Outcome Score:			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score: / Syria cross-cutting Strand	B	A	A	A	N/A	N/A
Programme Score: / Political process and moderate voices strand	B	B	A	A	N/A	N/A
Programme: Whole of Syria	NA	NA	NA	NA	A	B
Risk Rating - low/medium/high	High/Medium	High	High		High
*output/outcome scores
The Whole of Syria programme was a new concept in FY 18/19. While elements have been adopted from a range of previous UK programmes in Syria, principally Syria CSSF FY 17/18’s Political and Cross Cutting programmes, like for like comparisons are not possible to make in all areas.

What support did the UK provide in FY 18/19?

Under the Whole of Syria programme, the UK worked to support progress towards a political settlement through the UN-led Geneva peace process while improving dialogue amongst civil society and minorities and their ability to contribute to the UN-led process. The programme continued to contribute towards the empowerment of Syrian women and the promotion and defence of human rights including by supporting processes to hold violators of human rights to account.

What results did the programme deliver? Will they be sustained?:

The main results achieved by the programme included:

- Civil society and other influential Syrian voices that were not directly involved in Track I peace negotiations able to contribute credibly to the UN-led process.
- Documentation of human rights violations shared with relevant international accountability mechanisms enhanced prospects for future transitional justice and accountability. This builds evidentiary support of violations of international law, human rights and other abuses to be used by justice and accountability organisations in future.
- Training provided to first responders improved the ability to support survivors of sexual violence (men, women, boys and girls).
- Support to grass root Syrian feminist civil society organisations helped to empower these organisations to deliver on their objectives. Funding contributed to invaluable networking and advocacy opportunities building institutional capability to assist the most vulnerable, including children.
- Support to outreach and coordination between NGOs and international accountability mechanisms improved the ability for women to feed into holistic, gender sensitive transitional justice strategies.

What lessons have been learned?

Governance and Accountability

We have taken measures to strengthen the governance structure and accountability chain for the Syria CSSF’s political and civil society programming in FY18/19, repeatedly testing country board appetite for the project and programme level approaches, aiming to avoid the difficulties associated with shifts in board appetite or changes in policy direction.

Programme Level Theory of Change

Policy uncertainty and flux, as well as the broad spectrum of programming made it challenging in FY18/19 to develop a relevant, meaningful and integrated programme level theory of change. Investment in robust and measurable theories of change, underpinned by similarly robust monitoring and evaluation frameworks, has been a priority for the team in FY19/20.

Continuing to make the most of the UK’s convening power

In FY18/19, policy uncertainty, Syria’s conflict trajectory and in-year changes to the programme, meant the programme team did not convene the donor community and implementing partners at the same frequency as previously (although thematic multi-donor and implementing partner meetings were held regularly, e.g. the UK-led justice and accountability workshops delivered jointly with the Dutch. The programme team will aim to continue to make the most of the UK and the CSSF programme’s convening power to shape and catalyse broader donor efforts.