Annual Review - Summary Sheet

PROGRAMME TITLE: Yemen CSSF Programme
Country and Region:	Yemen, Middle East and North Africa
IATI Unique ID:	CSSF-06-000013
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Budget :	ODA: £13.2m			Non-ODA: £0.9m
Budget this FY	ODA: £5.9m			Non-ODA: £0.2m
Spend this FY	ODA: £5.9m			Non-ODA: £0.1m
Original Programme Start Date: April 2015		Planned End Date: April 2019
Outputs					Score
Office of the Special Envoy of the Secretary General for Yemen’s (OSESGY) ability to support progress towards a durable cessation of hostilities in Yemen increases					B
Local level peace building in targeted areas lead to localised conflict resolution and community stabilisation					A
Political Access and Influence of UK Government secondees and advisers leads to beneficial changes in strategies and approaches					A
UK Government (and where possible, partner) policy responses and programme design is better informed and based on evidence					A
Overall output score					A
Outcome Assessment: Overall there is evidence of programme activities contributing to outcome level change. The most significant barrier to achieving intended changes at the outcome level remains the absence of a fully-fledged Track I process. This does not invalidate the Theory of Change, or the importance of preparedness of both the OSESGY and different groups to participate in a peace process. It does however limit the extent of possible progress on inclusion of different groups in this space.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	B	B	A	B
Risk Rating - low/medium/high	High	High	High		High
*output/outcome scores
How has the programme changed during this period?:

What support did the UK provide in FY 18/19?

The programme represents the third full year of programming since the Embassy’s evacuation from Yemen in early 2015. In 2017/18 the programme sought to diversify from a previous focus on the political process, which has continued in 2018/19. The 2018/19 Yemen CSSF Programme aims to contribute to the following outcomes:

- Make Track I processes inclusive of key conflict stakeholders with national and international support;
- Ensure Track II processes have cross-group support and are capable of engaging with and influencing Track I processes;
- Build knowledge on the effects and results of Track III peace processes in targeted areas in Yemen.

Key results for FY18/19:
- Good progress in implementation of local peacebuilding and stabilisation pilots, including establishment of six Conflict Resolution Committees that generated 32 community-led initiatives. High levels of community perception that conflict dialogue processes were effective, with lessons generated to inform the UK’s stabilisation approach.
- Support to the Office of the Special Envoy of the Secretary General for Yemen (OSESGY) has continued to add the strategic benefit of maintaining the UK’s access and influence with the OSESGY. Key areas for support have been identified, including on inclusion and gender, and plans put in place for 19/20 to engage on these.
- CSSF has been able to build consensus on key governorate-level issues amongst diverse local actors across in Marib and Hadhramaut and designed a platform for their constituents to feed into the transition process, when it comes, with a more unified and coherent voice.
- Links have been strengthened between grassroots women peacebuilders at the Track III level and women leaders at the Track I/II level through an inclusive CSSF-funded conference hosted by UN Women, enhancing the legitimacy of those advocating at the top and amplifying the voice of those operating on the ground.

Summary of progress and lessons learnt/actions taken since last review

Despite the ongoing challenging operating environment, in 2018/19 the CSSF team was able to consolidate work to date and lay the foundations for a more focused and coherent programme.

Revision of the Theory of Change – the programme underwent a significant revision of the Theory of Change (ToC) and Results Framework (RF). Both now better reflect the changes the programme, and associated projects, are seeking to contribute to.

Analysis & evidence – A key strength of the programme has been the emphasis placed on underpinning programme and policy responses with commissioned analysis and evidence, responding to opportunities and gaps where needed.

The most significant barrier to achieving intended changes at the outcome level remains the absence of a fully-fledged Track I process. This does not invalidate the ToC, or the importance of preparedness of both the OSESGY and different groups to participate in a peace process. It does however highlight the importance of a continued focus on Track II strategy and coordination, and local level peacebuilding and stabilisation efforts.

Summary of recommendations for the next year

Continue to prioritise Track II coordination and strategy development. The programme has identified a clear need for coordination of efforts in this space and commissioned analysis to support UN and UK Government plans. The UN is best placed as a neutral party to lead in this coordination, however it may be necessary for the UK Government to take a more prominent role if this engagement stalls. The programme demonstrates both the importance and potential value of Track II initiatives at the governorate, and not only national level.

Actively engage with UN Women and the new OSESGY Gender Adviser to shift the focus away from only Track I. Supporting 30% women’s participation in official peace process delegations remains important. It does not however negate the need to consider wider incorporation of gender perspectives. This includes strategies for; a) how to ensure (diverse) women’s concerns are fed into Track I negotiation, even if 30% representation is not possible, b) wider engagement with national and governorate level Track II plans, and c) linking Track II and III (including strengthened links with the CARE-implemented project under output 2). The development of an overarching gender strategy, which incorporates both programme and political work, would support this.

Ensure learning from the stabilisation pilot is incorporated into the design of future CSSF supported stabilisation work. Priority for 19/20 will be consolidating learning to inform the design of future scaled up stabilisation work, in coordination with other donors. The Third-Party Monitoring, and project level learning, challenge several of the assumptions underpinning the ToC of service delivery in support of stabilisation objectives. This learning, alongside wider evidence on service delivery for stabilisation, needs to be actively considered in plans for scale up. This should include ongoing engagement with UK Government Humanitarian Advisers to ensure de-confliction with humanitarian response.

Prioritise consolidating an approach to Monitoring & Evaluation (M&E) of Political Access and Influence (PAI). The CSSF programme has begun using the PAI tool with the Stabilisation Adviser and Maritime Security Adviser, and has plans to use it with the UK seconded expert to the OSESGY and FCO political staff. The approach has the potential to not only capture evidence of successful influencing, but encourage ongoing reflection on achievement of influencing objectives. Recognising that M&E of PAI can be time intensive, the programme should focus on developing a practical and sustainable M&E approach.

Use the development of the Maritime Security Strategy as an opportunity to consider the strategic objectives and focus of the Maritime Security Adviser (MSA) role. In addition to ongoing support to achieving humanitarian objectives this should include a consideration of how the role may evolve as the peace process progresses. As noted in previous Annual Reviews, the review team recommends that the position should be transitioned to a minimum of 12 months, given the importance of relationship building in this area.