CSSF 2018/19 Annual Review Synthesis

1. Introduction

All Conflict, Stability and Security Fund (CSSF) programmes must undergo an Annual Review (AR) or Programme Completion Review (PRC) during the first quarter of the new financial year. Annual Reviews assess the effectiveness of how a programme is delivered and consider how teams have assessed risk and changing contexts. The review team must have at least one external reviewer, and the process of the review provides teams an opportunity to reflect on whether the results their programmes are delivering are in line with current HMG strategic objectives. This report summarises the trends, findings and lessons from the 2018/19 CSSF Annual Reviews as part of the Fund’s commitment to improving transparency of and learning in the Fund.
This year’s synthesis has been led by the Joint Funds Unit (JFU) and the learnings and evidence from it have been used to inform programming across financial year 2019/20 (FY2019/20). The synthesis process produced a series of timely internal evidence and learning products tailored to decision makers’ needs:
- In August 20119, a short report that provided a fund-level snapshot of the emerging findings from the ARs was fed into the 2020/21 CSSF budget allocation process. The Deputy National Security Adviser (DNSA), who is the Senior Responsible Officer for the CSSF, used evidence from the synthesis report to instruct an increase in the CSSF’s spend on Women, Peace and Security (WPS).
- In the autumn, a series of slide decks that summarised the trends and performance of CSSF portfolios were used by JFU staff to initiate a conversation with Portfolio Leads, who oversee programmes in particular regions or on thematic areas, about whether portfolios have the right programmes to meet HMG strategic objectives.
- In January 2020, the JFU facilitated two participatory workshops with Portfolio Leads to jointly analyse and reflect on change stories that were harvested from ARs. The first workshop was focused on conflict prevention and peacebuilding. The second was focused on WPS.
This report draws upon and summarises the data, analysis and reflection that was captured through these internal evidence products and processes. It provides a summary of performance and risk at fund level and then goes into more detail for two priority CSSF themes: conflict prevention and peacebuilding; and WPS. The final section summarises the key lessons learnt from the 2018/19 ARs.
Limitations
This document draws upon data from 76 Annual and Completion Reviews from 2018/19, representing 86% of CSSF programmes. ARs use a subjective scoring system and consistency of scoring can vary.

2. Performance
Figure 1 shows that CSSF’s performance at output level decreased in 2018/19 compared to the previous year (2017/18).

In response to recommendations from ICAI, in 2018/19 CSSF invested significant resources to improve results management processes. CSSF now puts more emphasis on measuring the quality of outputs rather than counting the number of people reached or the number of services/products delivered. For example, the AR of a CSSF strategic communications programme noted that in 2017/18 the programme was focused on monitoring reach data through social media (e.g. Facebook likes) but has now shifted to assessing changes in behaviour and quality of content through stories or case studies of behavioural change. The AR noted that a combination of more ambitious milestones/targets at output level focused on quality rather than quantity and the inability of the programme team to systematically collect stories of change across all of the projects, meant that many of the outputs were scored as a B (partially delivered).
This more meaningful and ambitious approach to monitoring, evaluation and learning (MEL) will take time to embed and needs to be properly resourced because it involves developing a Results Framework that is capable of synthesising more nuanced qualitative information and developing implementing partners M&E capacity so that they can systematically collect and reflect on stories of change. Looking across all CSSF ARs and results frameworks, the general trend is that milestones and targets at output level are more of a stretch compared to 2017/18. This may explain why performance at output level in 2018/19 decreased compared to the previous year.
Figure 2 shows that CSSF’s performance at outcome level improved in 2018/19 compared to the previous year (2017/18).

Strong performance at outcome level could be explained by an increased focus on monitoring outcomes. For example, in 2018 CSSF developed tools to capture intangible and hard to measure outcomes such as increasing political access influence (see box 1).
Box 1: Political Access and Influence

For CSSF, increasing political access and influence is essential to operating successfully in highly politicised, volatile and ambiguous environments where the way forward is uncertain. To better understand, measure and capture CSSF’s role in increasing political access and influence, in 2017/18 the CSSF East Africa team developed a Political Access and Influence (PAI) tool. The PAI tool enabled the East Africa team to develop a set of PAI case studies that represent a distilled and accessible record of the strategic CSSF Eastern African achievements and demonstrate the value of CSSF investments. They have also helped to inform and enhance reporting and learning across the region. Learning from East Africa, the 2018/19 Annual Reviews show that the PAI tool has also been adapted and used by CSSF North Africa, CSSF Caribbean, CSSF Middle East and the CSSF Eastern Europe and Central Asia.

CSSF has also put more focus on using complexity aware MEL methods that can capture both planned and unplanned results. For example, the ARs show that the CSSF’s implementing partner, Saferworld, has used outcome harvesting to capture and reflect on outcomes in Pakistan and Nepal: “Saferworld’s outcome harvesting tool has been used more effectively in the past year, with Saferworld’s downstream partners attending workshops to fully explore the attribution of activities to results” (CSSF Pakistan Regional Programme AR, 2018.19). Looking forward, CSSF will continue to strengthen its outcome monitoring system and will develop and scale the use of conflict sensitive M&E approaches that capture planned and unplanned results, both positive and negative.

3. Risk

From Somalia and northeast Nigeria in Africa to Yemen and Syria in the Middle East, CSSF works in some of the most fragile and unstable countries in the world. Moreover, CSSF works on highly complex and interrelated issues such as conflict prevention, preventing violent extremism, migration and tackling serious and organised crime. Tackling the root causes of conflict and instability requires a high tolerance for risk[1].
[1] For annual reviews, the programme Senior Reporting Officer and the review team are asked to review the key risks that affect the successful delivery of the expected results. The risk categories that are considered to determine the overall risk include: delivery, fiduciary, partner, political, reputational, and security/context, including conflict sensitivity and human rights.

Figure 3 above shows that CSSF has a bold risk appetite. For FY2018/19, 31% of CSSF programmes had a high overall risk rating. Only 7% of CSSF programmes were rated as low or low/medium risk.
A bold risk appetite requires strong risk management processes. One indicator of active risk management is the percentage of programmes where the risk rating for individual outputs has been changed during the 2018/19 programme cycle. Figure 4 shows that in 2018/19 programme teams changed the risk rating for 33% of individual outputs.
Figure 5 below shows that CSSF programmes rated as high overall risk rating, performed slightly better than programmes rated as low or medium risk at output level. Figure 6 shows that performance of high risk programmes was similar to the performance of low and medium risk programmes at outcome level. This demonstrates CSSF’s ability to manage programmes effectively in high risk conflict and fragile contexts. Looking forward, CSSF will continue to invest in its risk management processes and will look to develop more synergy between risk management, M&E and conflict sensitivity processes.

4. Conflict prevention and peacebuilding

Conflict prevention and peacebuilding is a priority theme for CSSF. For the purposes of the synthesis, JFU analysed all the ARs that had an output and/or outcomes relate to conflict prevention and peacebuilding. 26 programme ARs were included in the sample, covering the following portfolios: Middle East and North Africa (8 programmes); Africa (8); South Asia and Afghanistan (3); Eastern Europe and Central Asia (3); Multilateral Strategy (2); Western Balkans (1); Americas (1).
In 2018, the JFU worked with the Stabilisation Unit to analyse how the CSSF can best tackle conflict and instability; and support integrated delivery of broader national security priorities. The analysis highlighted that conflict occurs at multiple levels, at interstate level, nationally and sub-nationally, and that these levels intersect in conflict settings. For the synthesis, the JFU looked across the 26 sampled ARs and analysed what level of conflict CSSF interventions are operating (figure 7).

Figure 7 shows that 50% of programme outcomes are focused at the sub-national level; 32% of outcomes are contributing to national-level peace and reconciliation processes; 8% of outcomes make explicit the link between sub-national and national; 6% of outcomes are focused at the regional level; and 4% at the international level. During a workshop to analyse the emerging synthesis findings, the Head of the CSSF, Dr Christian Dennys noted:
“The balance [figure 7] seems accurate and reflects where we are now. In terms of where we need to get to, the link between local and national is important because this is where the contest over resources happens. Looking forward, the regional and international level is where CSSF needs to work hardest.”
For the synthesis, the JFU coded CSSF programme outputs and outcomes by (a) community-level conflict prevention (CP) and peacebuilding (PB); (b) national level CP and PB; (c) stabilisation; (d) de-mining; (e) multilateral capacity for PB. Figure 8 shows that CSSF programmatic performance is stronger at national-level compared to sub-national.

At output level, the trend was reversed: CSSF performed stronger at sub-national level (83% of outputs fully delivered, 17% partially delivered) compared to national-level (58% fully delivered, 38% partial, 4% not delivered). This perhaps suggests that CSSF is stronger at delivering products and services at the sub-national level but has more influence to bring about change at the national-level. However, it should be noted that this analysis is based on data from a single year and we need to be careful about drawing concrete conclusions at this stage. The JFU will monitor this trend over a longer time-period and will look to recalibrate CSSF programmes accordingly.
The JFU harvested 30 conflict prevention and peacebuilding change stories from the 2018/19 ARs. The change stories showed that CSSF is focused on changing the behaviour of multiple different actors. 11 of these stories were focused on changing government actors at different levels; ten of the stories focused on changes for people/groups affected by conflict at the community level; seven on changes of security and justice actors; one focused on change of civil society; and one on multilateral actors. Box 2 provides a summary of a change story that was harvested from the Colombia Peace Process AR. The story highlights how CSSF has provided catalytic support to develop seven Regional Development Programs in Colombia, which contributes to the Government of Colombia’s plans for broader rural development reform, which is a critical factor for building a process of sustainable peace and stability.
Box 2: Colombia Peace Process

Description of the change
The Colombia peace process refers to the peace process between the Colombian government and the Revolutionary Armed Forces of Colombia (FARC). During 2018/19, CSSF supported the construction of three Regional Development Programs (PDETs) that incorporated elements from the Colombia peace deal, creating an institutional framework for the next six years to help stabilise seven regions. This generated momentum and irreversible steps that lead to new funding for the final consultative stage of all the 16 PDETS and their inclusion in the National Development Plan. This sets the Government of Colombia's plan over the next four years including how it will dedicate policy efforts and economic resources to support the implementation of the peace process.
Significance
Because reparations to victims, reintegration of ex-fighters and combating illicit economies are closely tied to issues of land access and development of rural communities, the success of these efforts ultimately hinges on achieving broader rural reform. At the centre of the government’s plans for rural development are the PDETs. The PDETs will help to ensure that the perspectives of more than 200,000 people from the regions most affected by conflict are included in the National Development Plan, which ultimately could lead to a more sustainable process of building peace and security.
CSSF Contribution
The UK provided crucial bilateral support to finish the consultative phase of two PDETs before change of government. The UK provided three consultants to assist the incoming Presidential Counsellor for Stabilisation prepare the necessary legal documents to ensure the inclusion of PDETs in the national development plan. Without this support, it is not certain that the Counsellor would have met deadlines and built the political alliances necessary to include this key component of the peace deal in the national budget.

5. Women, Peace and Security
Women, Peace and Security (WPS) is a priority theme for CSSF. CSSF is an important delivery mechanism that contributes to the UK National Action Plan (NAP) on WPS.[2] The NAP is the UK government’s 5 year strategy for how the UK will meet its WPS commitments under United Nations Security Council Resolution 1325 to reduce the impact of conflict on women and girls, to promote their inclusion in conflict resolution, and to protect their human rights. It is part of wider efforts to ensure that the UK’s foreign policy consciously and consistently delivers for women and girls
[2] UK National Action Plan on Women, Peace and Security - https://www.gov.uk/government/publications/uk-national-action-plan-on-women-peace-and-security-2018-to-2022
.For the purposes of the synthesis, the JFU looked at all the ARs that had an output and/or outcomes that directly relate to WPS. 13programme ARs were included in the sample, covering the following CSSF portfolios: Middle East and North Africa (6); Eastern Europe and Central Asia (2); Africa (2); Multilateral Strategy (2); Commonwealth (1). The JFU analysed and coded WPS outputs and outcomes in terms of their contribution to NAP strategic outcomes.
43% of CSSF outcomes in the sample contribute to the NAP strategic outcome focused on decision-making. Indeed, nine of CSSF’s outcomes are focused on increasing the meaningful and representative participation of women in conflict prevention and peacebuilding processes at the community and national level. 66% of the decision-making outcomes were fully achieved and 33% were partially achieved. Figure 9 shows that 24% (five in total) of CSSF outcomes contribute to the NAP outcome on gender-based violence (GBV). Box 3 provides a case study on how CSSF’s programme in Ukraine has contributed to the development of a multi-sectoral response mechanism that responds to GBV.

Analysis of CCSF programme outcomes highlights that 10 CSSF WPS outputs are being delivered in priority NAP countries. Figure 10 to the right highlights which NAP priority countries CSSF is currently contributing to NAP strategic outcomes. It should be noted that the ARs for Myanmar and Afghanistan were not included in the synthesis and in both countries, CSSF programmes have WPS outcomes/outputs. Considering CSSF has a programmatic footprint in over 80 countries and the NAP is focused on nine priority countries, the synthesis shows that CSSF’s current WPS programming meeting priorities identified in the NAP as well as stretching delivery in to other important contexts where required.
The JFU recognises that CSSF needs to scale up its WPS programming activity. 21 outcomes focused on WPS is not sufficient relative to the strategic importance of WPS and the strength of evidence that suggests gender equality is critical to achieving our broader peace, security and stability objectives. The CSSF is committed to significantly increasing its programming activity and spend on WPS. Despite HMG policies on WPS being in place since 2010, and repeated political acknowledgements of the importance of gender equality and the scale of the challenge, funding has not kept pace with policy or evidence of need. Gender equality exists and manifests in all conflicts, and the JFU will support programme teams to meet this challenge.
The JFU harvested 19 WPS change stories from the 2018/19 ARs. Box 3 provides a summary of a change story that was harvested from the CSSF Ukraine AR. The story highlights how CSSF has provided catalytic support to support the government to develop a multi-sectoral response and a network of specialised services in response to GBV.
Box 3: CSSF Ukraine Gender-based Violence

Ukraine has made considerable progress in developing a system of response to gender-based violence (GBV). Ukraine has developed multi-sectoral response mechanisms and created a network of specialised services for survivors. In 2018/19, with CSSF funding and DFID co-funding, the programme achieved the following results:
(i) Built strong national (GoU) ownership over the existent GBV response mechanisms and frameworks in order to ensure sustainability
- Following adoption of the Law of Ukraine on Preventing and Combating Domestic Violence in December 2017, the project supported establishment of the national coordination body in GBV response and prevention.
- At the regional/municipal level, the project operates in 12 regions after extending to seven new regions over 2018-2019 (Odesa, Kherson, Mykolaiv, Vinnytsia, Poltava, Kyiv, Lviv regions).
- The programme has supported the establishment and capacity development of multi-sectoral coordination bodies in 12 municipalities and 11 regions.
(II) Ensured that in Ukraine majority of gender-based violence survivors seek and have access to good quality survivor centred services.
- Complex psychosocial assistance to 47,046 survivors of GBV across twelve regions of Ukraine.
- 24/7 All-Ukrainian Hotline for GBV survivors gave vital informational, psychological and legal consultations to 24,953 people (more than 36,600 calls received in 2018-2019).
- 45 Mobile police GBV response groups “POLINA” started operations in all regions of the country. Over 350 police officers received necessary equipment and training.
- In 2019, two new shelters and three new daycare crisis centres were opened for GBV survivors.
(III) Enhanced legal, institutional and social environment that will contribute to zero tolerance and eradication of violence against women in Ukraine
- The programme advanced the concept and advocacy strategy of the “Break the Circle” campaign aimed to call survivors to report their cases and seek help as well as to build zero tolerance to GBV among survivors.
- Over 36,000 people accessed crucial information about GBV and available services on the website of “Break the Circle” campaign (rozirvykolo.org).
- Over 132,000 people in rural areas (subscribers of Ukrainian national newspaper “Silski visti” Rural News) got a chance to sensitise themselves with the issue of GBV.
- Over 190,000 young people learnt how to recognise early signs of psychological violence through a series of videos “No Trivia in Relationship” that challenge negative stereotypes that perpetuate GBV.

Significance
Because both reparations to victims and reintegration of ex-fighters are closely tied to issues of land access and development of rural communities, the success of these efforts ultimately hinges on achieving broader rural reform. At the centre of the government’s plans for rural development are the PDET’s. The PDET’s will help to ensure that regional perspectives are included in the National Development Plan, which ultimately could lead to a more sustainable process of building peace and security.
CSSF Contribution
The UK provided crucial bilateral support to finish the consultative phase of three PDET’s when the previous Governance faced a funding crisis. This enabled the last President to approve two PDET’s raising the political cost of the new Government for abandoning this initiative from the peace deal. The UK provided three consultants to assist the incoming High Commissioner for Stabilisation prepare the necessary legal documents to ensure the inclusion of PDETs in the national development plan. Without this support it is not certain that the Commissioner would have met deadlines and overcome political resistance to include this key component of the peace deal in the national budget.

6. Lessons learnt
Using a sample of 31 ARs focused primarily on conflict prevention, peacebuilding and WPS, the JFU harvested, coded and analysed 92 lessons learnt and 190 recommendations. The lessons and recommendations were sorted into categories. Table 1 provides list of the top ten lessons that were most frequently included in the ARs and a selected lesson example for each category. This provides a flavour of the types of lessons that were included in the ARs.
Monitoring, evaluation and learning was the top category for both lessons (13) and recommendations (32). This is perhaps unsurprising because AR teams rely on MEL data to complete the AR. Programme management, including adaptive programming, was the second most frequently cited with 9 lessons and 11 recommendations. Programme design, including theories of change, was third with 5 lessons and 14 recommendations. This suggests that programme management continues to be a priority area of development for CSSF. Indeed, the Fund Management team is currently consulting the CSSF network to refresh the CSSF operating framework, which includes updating the guidance and rules on programme management. In 2019, the JFU launched the Global Monitoring, Evaluation and Learning contract, which will develop portfolio and fund-level MEL systems and processes.
Rank	Top ten lesson categories	No. of lessons	Selected lesson example from an Annual Review
1	Monitoring, evaluation and learning	13	Significant progress has been made on Monitoring, Evaluation and Learning (MEL) since the last review, including using an external consultancy to rework the results framework.
2	Thematic lessons on conflict prevention and peacebuilding	10	Elite deals do not buy peace. They buy time. Whether or not it is delivered through the R-ARCSS [peace process monitoring body], it will be a more inclusive political settlement that brings lasting and long-term peace to South Sudan. HMG should continuously reflect upon whether HMG actions contribute to this longer-term goal.
3	Programme management, inc. adaptive programming	9	In any rapidly changing context, routine update and challenge of contingency plans is essential. A flexible approach can create options to adapt stabilisation and development activities to support humanitarian type objectives in crisis. This can be supported by actively preparing for different scenarios which may emerge, to identify triggers to understand the emerging changes, and how and where a project may be able to flex to provide new support.
4	Volume, timing and scale	8	The pilot approach to stabilisation and peacebuilding has been important in laying the foundations for future cross-HMG work in Yemen. The programme recognised however that they ran the risk of implementing too many small projects, and have plans to consolidate work in 19/20.
5	Programme design, including theories of change	5	Programme Level Theory of Change: Policy uncertainty and flux, as well as the Whole of Syria strand’s broad spectrum of programming made it challenging in FY18/19 to develop a relevant, meaningful and integrated programme level theory of change. Investment in robust and measurable theories of change, underpinned by similarly robust monitoring and evaluation frameworks, has been a priority for the team in FY19/20.
=5	Working in partnership	5	The programme [Jordan] has operated in a space that, as a result of sharing information does have a degree of alignment with other donors. Contact is maintained with other international partners including the US, EU, Dutch, Japanese and Canadians to share information on project progress and thus avoid any overlaps.
=5	Catalytic effect	5	Because of its close linkages with both the civilian administration and the military, the programme [Somalia Stabilisation] can play a catalytic role and bring together civilian and military actors in a dialogue with communities that have been excluded from the political settlement.
=5	Staffing	5	The programme consists of a significant number of projects and interventions, which has placed a considerable management burden on the programme team.
=5	Knowledge/lessons sharing	5	Guard against optimism bias. The team [Sri Lanka] should ensure regular lesson learning and be prepared to adapt programme quickly to adjust to a more uncertain political context than that in which the programme was set up.
10	Effectiveness	4	Embedding the legal advisor within the Ministry of Justice showed the most concrete results with regard to encouraging the passing of piracy legislation, training of Nigerian MoJ prosecutors and establishing a core maritime crime group.

Table 1: Top ten most citied lessons by CSSF AR teams, 2018/19