Business Case

Monitoring, Reporting, Evaluation and Learning in the Prosperity Fund

# Summary

In order to help promote economic growth in developing countries the government has created a new Prosperity Fund worth £1.3 billion over the next five years. Its priorities will include improving the business climate, competitiveness and operation of markets, energy and financial sector reform, and increasing the ability of governments to tackle corruption. These reforms will drive sustainable development and will aim to contribute to a reduction in poverty in developing countries. They will also create opportunities for international business, including UK companies.

Around two thirds of the world’s poor live in middle income countries. These countries are able to finance their own development, but face considerable challenges such as rapid urbanisation, climate change and high and persistent inequality which can lower long-term growth prospects. The Prosperity Fund will support the broad-based and inclusive growth needed for poverty reduction and to make development sustainable.

In order to develop a robust monitoring and evaluation framework the Fund has tendered three central contracts to deliver these products and services. This mirrors a similar contract model developed by the International Climate Fund to deliver monitoring, evaluation and learning (MEL) services and products across its funding streams.

HMT’s settlement letter ring-fences five per cent of Fund expenditure to be earmarked for monitoring and evaluation. This amounts to £65m.

The PF’s Monitoring, Reporting, Evaluation and Learning Programme will deliver:

## Fund level evaluations
- Midpoint process and contribution evaluation.
- Small Projects Fund evaluation
- Impact evaluations: formative in approach and feeding into design. These will follow a macro approach and focus on five major programmes and 1015 medium-sized programmes.
- UK benefit evaluation to report in time for next SR.
- Post funding cycle impact evaluation

## Programme/sector evaluations
 Up to 30 programme evaluations tailored to Department and Post needs and also feeding into Fund level evaluation.

## Monitoring & Reporting
- Technical Assistance to programme teams to review programme ambitions and support monitoring and reporting activities
- Monitor and report on programme and Fund level primary and secondary benefit indicators
- Monitor and report on financial expenditure versus budget
- Quality assure data entered into the monitoring and reporting system
- Monitor and report on financial expenditure versus budget
- Delivery of an online monitoring and reporting IT tool for internal and external use

## Learning
- Lessons from programmes and thematic/sector strands
- Operational Research and collaboration with IFIs to support and challenge Fund and programme theories of change and to develop metrics where appropriate.

Strategic Case

Global experience has shown the importance of good quality monitoring and evaluation of development programmes and aid instruments. For example, the OECD DAC Principles for Evaluation of Development Assistance emphasise that “aid evaluation plays an essential role in the efforts to enhance the quality of development cooperation.”
DFID’s evaluation strategy for 2014 to 2019 situates evaluation as part of an overall agenda to strengthen the evidence underpinning policies and programmes to ensure development results, impact and value for money. DFID’s evaluation policy recognises, “evaluation has a key role in generating evidence and learning about what is working in development and what is not; it can identify better ways of doing things; allow for course corrections of programmes to improve effectiveness; ensure that lessons are learned during the development process and resources shifted to where they are most effective; and improve the ability to respond to change.” The Fund’s settlement letter from HMT sets out the need for robust monitoring and evaluation to ensure impact measurement from Fund expenditure.
“The Prosperity Fund Department should build robust impact evaluations, in line with the Principles of Managing Public Money, into your programme delivery that can provide pragmatic findings on the effectiveness and impact of programmes over this Parliament.”
“Five per cent of the total Prosperity Fund will be ring-fenced for monitoring and evaluation activities, with a Framework to be agreed by Treasury and by the Ministerial Board.” HMT Settlement letter 11 February 2016

The Ministerial Board approved the initial conceptual framework in March 2016 and approved the business case to go through to assurance and tender in July 2016. As required by the settlement letter the CST also gave HMT approval to proceed.
Being clear about Prosperity Fund results will help ensure a focus on key objectives from the start. This focus, through monitoring and evaluation (M&E), will help maximise impact and value for money and help manage risk. It will generate an evidence base to inform decision making on how and where we can effectively use resources, for example through identification of which reforms matter the most for partner growth and UK benefit. This evidence and lessons generated in turn will make the delivery of programmes more effective. M&E also provides a key tool to inform our public and Parliamentary communications on Fund impacts.

What do we need to monitor and evaluate?

Aims: the aim of the Fund is primarily to support growth and economic development in aid-eligible countries, with secondary benefit for international business including UK companies.

The Fund’s monitoring and evaluation framework follows the theory of change for the Fund (see Annex A) – i.e. how we expect fund activity to deliver stated objectives. This sets out how inputs, activities and outputs are expected to contribute to changes in intermediate and ultimate outcomes. In particular, it shows how the Fund is expected to contribute to producing its primary and secondary benefits. It also identifies key underlying assumptions regarding the successful operation of the Fund.

The M&E approach will look at how the Fund has an impact on the primary objectives of economic development in partner countries. The intermediate objectives for the Fund draw on consultations with DFID and on the findings of the World Bank’s Commission on Growth and Development (May 2008). They are shown as purple circles in the Fund’s theory of change (Annex A).
- Improving investment in infrastructure
- Increasing investment in human capital, innovation and knowledge
transfer,
- Supporting positive trade growth and openness
- Supporting financial and economic reform
- Improving the business environment
Secondary benefit for international business including UK companies should arise from UK businesses successfully competing for contracts in the short-run and from more effective markets and partner growth in the longer-run. Estimates of the returns to the UK will include measures of direct commercial benefits (exports and inward foreign direct investment); wider economic benefits (imports, returns from outward FDI), and; any benefits to the UK from tackling global public goods or challenges such as global corruption, financial stability, health or climate change. The Fund will work closely with DIT as its own metrics on UK export benefits and critical sectors develop.

The M&E framework is structured around the Fund’s theory of change. Evidence gathered through monitoring and evaluation will be used to inform a process of contribution analysis, i.e. assessing the extent to which:

- Particular activities or outputs have occurred;
- Expected outcomes have occurred;
- The Fund’s activities and outputs have contributed to expected outcomes; and/or
- Other contributory factors have been involved.

Based on this evidence and analytical approach, the theory of change will be periodically reviewed and revised. The existing evidence base is strong that the Fund’s activities and outputs would be likely to contribute to the primary benefits and intermediate outcomes. However, the evidence base for secondary benefit for international business including UK companies is less well-established. Contributing to the evidence base in this area is likely to make a major contribution to wider FCO work on the value of diplomacy and further building the case for the position in the UK Aid Strategy that ‘prosperity abroad is good for prosperity at home’.

The M&E activities within the Fund will be underpinned by: the country level analysis that will form economic growth diagnostics; the overarching analysis that will inform selection and prioritisation; the indicators that will be developed, and; the partnerships that will be forged with international institutions and other interested governments and agencies to deepen our understanding of pathways to prosperity through programme funding of this nature. Analysis and the learning that comes from evaluations will be used to inform programme design and its delivery.

The M&E strategic framework:

The Prosperity Fund has developed an overall strategic framework for monitoring; reporting; evaluation and learning (MREL). This identifies a number of principles on which the Fund’s MREL will be based.
- MREL will be based on the Fund’s theory of change.
- This has been revised for use as a monitoring and evaluation (M&E) framework and will be further revised as needed based on experience and M&E evidence.
- Monitoring systems will report on critical indicators on a quarterly basis.
- Evaluation will focus on learning to be used during planning and implementation (a formative approach) based on the information needs of stakeholders (utilisation-focused approach).
- Communicating evaluation findings and lessons learned will be a key focus.
- M&E will use a contribution analysis approach: collecting evidence of what the Fund has done; the extent to which expected outcomes have occurred; and the extent to which Fund actions/other mechanisms have contributed to change.
- MREL will take place at both Fund and, especially, at project and programme level.
- Evaluations of large projects or programmes within the Fund will be bespoke/tailored to individual situations and contexts.
- Evaluations will be conducted at appropriate times to feed into key decision timelines of the Fund. In order to assess programme impacts, it is proposed to conduct a post-cycle evaluation three to five years after the end of the programme.
The scope of the MREL strategic framework covers monitoring, reporting, evaluation, learning and operational research. The framework is based on the Fund’s theory of change. It seeks to identify ways to assess elements in the framework and the links between them. This will involve quantifiable indicators to be measured on an ongoing basis and questions to be answered during evaluations or reviews.

## Monitoring and Reporting
What will we measure, what will we report and what tools will we need?
The Fund theory of change provides the backbone to the monitoring and reporting strategy. Monitoring will focus on capturing the inputs (resources), the outputs (what has been done), and the intermediate outcomes (what happened as a result in the avenues identified). The Fund level theory of change has been amended to better capture activities and outputs so as to enable better mapping against intermediate outcomes. Indicators are being developed for the intermediate outcomes and for the output level to allow programmes to channel their results through these, which will aid in synthesis across the Fund.
### Primary benefit
Monitoring and reporting will be focused on the main development benefits (intermediate outcomes) of the Prosperity Fund as measured through agreed outcome and output indicators derived from the Fund’s theory of change.
All projects and programmes will be expected to report quarterly/annually on relevant outputs and intermediate outcomes using agreed core indicators. Projects and programmes will also be expected to answer qualitative questions relating to contribution to intermediate outcomes during annual reviews.
These requirements will apply in particular to large country and thematic programmes but small projects will be expected to report contribution to at least one core output indicator and one intermediate outcome. Small projects will be treated as a fund and year one will be evaluated in year 2 to determine the effectiveness of this type of spending.
### Secondary Benefit /strengthened partnerships
One of the expected outcomes of the Prosperity Fund is that partnerships are strengthened in terms of mutually beneficial economic relationships and are developed in sectors where the UK has a comparative advantage.
Monitoring and reporting will seek to identify these benefits to business, including the UK, in three spaces:
- Direct commercial benefits: short-term commercial benefits derived from programme activity – measured by posts/DIT;
- Indirect economic benefits: longer term economic reforms bringing longer term economic benefits to the UK, (measured through economic modelling) and;
- Benefits arising from global goods: trade policy reforms, anti-corruption and security reforms, environmental reforms (measured through economic modelling).

The latter two elements of UK benefits should in time produce direct commercial benefits but it will be important to model the expected benefits and then validate these when the longer-term post-cycle evaluation takes place.

Reporting of UK benefits will fall in the main to departments and posts through the quarterly impact reporting requirement. Where contracts are identified the commercial benefits of the export win will be recorded. Where the benefits are accruing from policy changes (economic and public good benefits) values will be estimated by FCO economists drawing where necessary on external, contracted expertise. The Fund is in the process of recruiting an economist to sit with Economics Unit and who will have a focus on deriving, allocating and reporting UK benefits arising from programming.
### Value for Money
A third key element for monitoring and reporting (alongside primary and secondary benefit for international business including UK companies) will be value for money. It is proposed that an early operational research study be carried out to identify ways in which the Fund’s value for money might be best monitored and evaluated. This study would be expected to influence how value for money is measured within the Fund, particularly in terms of evaluation.
In terms of monitoring and reporting, it is expected that Departments and Posts will report financial expenditure, including unit costs where possible and appropriate. In addition, it is expected that during annual reviews, Departments and Posts will take stock of their performance on value for money including assessing economy, efficiency, effectiveness and equity and giving themselves an overall rating.
### Reporting
In order to meet the HMT requirement for quarterly impact reporting, the Fund will develop a set of key indicators which will allow Ministers to critically analyse Fund activity. These will show:

- Spending by country and sector programme
- Spending by theme/sector
- Spending by department
- Value for money
- Primary benefits
- Secondary benefit for international business including UK companies (as above – direct commercial, indirect economic and global public good) 	Portfolio/fund management quality covering spend, return and risk
- Risk reporting.

A dashboard will be developed that will capture these reporting needs and will form the core of the quarterly report, supplemented with specific analyses when available and with information to support effective external communications.

Monitoring and reporting will also deliver information on programme activities, spending and benefits that can be used to provide communications material to inform the public, Parliament and HMG’s international partners on the activities of the
Fund. While much of this at the outset will be based on inputs and outputs, as the Fund matures more information will become available on the impacts that are generated.
How will we do it?
In addition to the financial information gathered through the Fund’s financial management system, departments, posts and their implementers will be required to coordinate with the central MREL team to determine which indicators of success will be most appropriate for their strands of work. In addition to reporting on core central indicators, programmes will develop their own indicators through the use of individual theories of change and logframes devised during business case development. For year one, where these are not available, reporting will be collated through the MREL team working directly with posts to deliver quarterly reports and annual reviews. For years two to five, it is proposed that a contracted firm will be responsible for the collection, synthesis and analysis of the information and will provide succinct reports to the MREL team ahead of quarterly reporting deadlines. The contractor will liaise closely with the MREL team in the Fund and with departments and posts who are implementing programmes. Financial information will be collected through the central financial management system of the FCO and other programming departments and will be reported to HMT monthly as well as forming part of the quarterly reports to Ministers.

Some reporting burden will fall on programme implementers, including departments and posts. Currently FCO posts do submit monthly financial reports and quarterly narrative reports but there have been challenges in reporting on impact. There is little experience of reporting against quantitative indicators.
The Fund will need to ensure that reporting systems are:
- Not burdensome
- Based on user-friendly templates that work
- Road tested in a number of posts as this helps credibility
- Supported with a range of explanations and trainings 	Built on what is currently being used 	In clear, simple language.
- Targeted to appropriate people
- Focused on reporting main changes and not all activities
- Designed to avoid multiple levels of reporting
The main elements of the Fund’s monitoring and reporting will be monthly financial reporting, quarterly reporting of results and annual reviews.
## Evaluation and Learning

What will we evaluate?
As the Fund is in start-up phase and there is a clear need to establish what is working best and where, the overarching approach to evaluation will be formative. Evaluation will focus on the need for information ahead of programme completion to assist teams in further developing theories of change for the Fund and its programmes. This approach embeds the need to provide the Fund with learning about what is working best to achieve Fund objectives and where activities are having most success. The impact on the Fund’s primary objective will be assessed through contribution evaluations, where development impacts will be delivered in the medium term after the current Fund cycle is complete.

To fit with the decision-making cycle, an impact evaluation on secondary (UK) benefit will be carried out ahead of the next spending round window in autumn 2021. This impact evaluation will examine the direct, indirect and public good aspects of the Fund’s work. Direct impacts will be through contracts delivering exports, ODA and FDI, indirect impacts will be through the structural reforms that the Fund will support and that will deliver more effective economic structures and environments that will lead to increased trade, and impact on public goods will be through the trade, security, anti-corruption and environmental benefits that the Fund will support.
### Fund or programme evaluations
Evaluations will be carried out at both Fund and programme level. At the Fund level, evaluations should assess the extent to which Fund activity is contributing to the sustainable, inclusive growth of the target country and that these activities are also contributing, and delivering secondary benefit for international business including UK companies. Evaluation of the Fund overall will be done through a combination of synthesising findings from programme evaluations and cross-Fund evaluations, e.g. of particular themes.
In addition, there will be specific project/programme evaluations. These may be handled directly by the Fund evaluators or may be conducted through a central contract established specifically to deliver programme-level evaluations. Whichever approach is taken, they will be led by programme managers. Given the new nature of the programme areas, it will be important to test theories of change and establish, while the programmes are running, whether they are delivering the outputs and outcomes that will likely lead to impact. These programme level evaluations will provide essential information to support the Fund level evaluation. Performance evaluations on 5 major and 10-15 medium sized projects will be carried out towards the end of the Fund cycle.

### Strategic evaluation questions
The Fund’s overarching evaluation question will be “To what extent, is the Prosperity Fund contributing to sustainable economic growth and development of partner countries, and in doing so is generating direct and indirect benefit for the UK?” There will be three categories of questions (see Table 1 for more detail):

- What has been, or is likely to be achieved, as a result of the Fund?
- Why is this? What factors have contributed, or not, to what has taken place and been accomplished?
- What does this mean? What can be learned from how well implementation is taking place to aid in improvement of ongoing activities and to inform future directions?
Table 1 also shows the extent to which different evaluation questions map to the OECD DAC evaluation criteria of relevance, effectiveness, efficiency, impact and sustainability.
## Table 1: Strategic evaluation questions for the Prosperity Fund

OECD DAC criteria / Relevance / Effectiveness / Efficiency / Impact / Sustainability
Overarching question: To what extent, is the Prosperity Fund contributing to sustainable economic growth and development of partner countries, and in doing so is generating direct and indirect benefit for the UK?
What has been or seems likely to be achieved as a result of the Fund?
1. Which types of interventions, in which sectors / types of country settings, have been most successful in leading to outcomes in the areas of investment; innovation and knowledge transfer; Trade, financial and economic reform; policy and regulatory capacity, and ease of doing business?
2. In the short-to-medium term, what evidence is there that the Fund has been or is likely to contribute to intended outputs and intermediate outcomes as suggested in the

	OECD DAC criteria / Relevance / Effectiveness / Efficiency / Impact / Sustainability
Fund’s Theory of Change, as well as unintended or unexpected effects at any level?
3. What are the characteristics of programmes and interventions that have led to strengthened partnerships that show evidence of likely contributing to improved economic growth and development and to UK benefit?
4. To what extent does Prosperity Fund funding represent value for money? Which approaches have provided the best value for money (VfM)?
5. What lessons can be learned from the experiences of individual programmes as well as that of the Prosperity Fund overall for improving ongoing and future efforts at supporting innovation and increasing inclusive economic growth and in a way that also can lead to UK benefit?
6. Who benefits the most, directly and indirectly, through programmes supported by the Fund? Which types of initiative, and under which set of circumstances, are most likely to lead to growth and development that benefits the poor and cross-cutting themes, such as gender equality, human rights and respect for minority populations, reductions in corruption, respect for the environment?
What factors are associated with how well the Fund works?
7. What factors have contributed to certain programme approaches in having an impact at any level? In which types of situations/contexts are given approaches most appropriate or not?
8. Are there certain types of settings or contexts where support through the Prosperity Fund are most likely to be appropriate and to have the greatest chance of contributing to the Fund’s objectives without undesired side effects?
9. How valid are the assumptions in the theory of change (ToC)? Are there refinements or changes that should be made, based upon early experiences with programmes and activities supported through the Fund?
10. What good practices can be identified from experiences of Prosperity Fund programmes that might be considered in other settings?
11. How can the Fund best work in combination with other partners, including with other initiatives also attempting to
	OECD DAC criteria / Relevance / Effectiveness / Efficiency / Impact / Sustainability
support economic growth and prosperity, and/or with themes (for example, education) of the Fund?
12. Which funding modalities work best in contributing to the Funds aims?
What are the implications of Fund experiences for future directions?
13. What can be learned from initial experiences of the Fund overall, as well as of supported ongoing programmes, in order to make adjustments so that the intervention will be more likely to succeed?
14. Which types of programmes and approaches represent better value for money?
15. Are there optional approaches or strategies that might be more appropriate or more effective?
16. What are the implications of the experiences of the Prosperity Fund for the UK to considering continuing with a similar approach in the future?

### Value for money
Value for money assessment will form part of evaluations conducted within the Fund. Our basis for value for money rests with the three E methodology: efficiency, effectiveness and economy. We will require programme teams to self-report on value for money through an annual report system in line with DFID practice.
### Learning
Learning forms an essential and integral aspect of the MREL strategy. There will be need for a detailed learning plan to be delivered by the evaluation and learning provider. While learning will occur from how monitoring and evaluation is carried out, there will also be a need for a dedicated learning team, and for dedicated learning products. An initial learning plan will be requested in proposals, and further developed and refined during the inception phase). The contract will provide for learning at different levels and for different stakeholders, such as: different departments within HMG, partners (countries, cooperating businesses, agencies etc.) The learning plan will also identify what learning will be needed, and for what purposes.
How will we do it?
Evaluation and learning reporting will form part of the contracts tendered by the central MREL team. The Fund level contractor will be required to plan integrated evaluations following the principles laid out above to develop a timetable for reporting so as to best enable the Fund’s management to make timely decisions on Fund direction and activities. In line with contracting practice in this area, the contractor will be asked to refine the strategic questions and approach to ensure that the objectives of the evaluation are fully met.
Departments and posts operating programmes over £10m will be asked to build evaluations into their business cases and tender these at the same time as wider implementation contracts. In line with the evaluation strategy these should be formative in design and focus on examining pathways through the programme theories of change and delivering learning on what works best to the wider Fund. The wider Fund level evaluation will sample from these programme evaluations as part of its synthesis.
## Gender Act Compliance
The OECD shows that women’s empowerment, specifically as entrepreneurs with access to growth markets, is a major contributor to pro-poor growth within a nation’s economy[i]. Similarly, the World Bank finds that greater gender equality could increase labour productivity by as much as 25 per cent in some countries [ii].Women are more likely to work in the informal sector and are typically disadvantaged by prevailing laws, regulations and customs. Laws, regulations, and customs restricting women’s ability to manage and own property and land, access finance and conduct business are crucial binding constraints to growth. Even where laws and regulations are gender-neutral in theory, they may still result in gender biased outcomes.

In line with Gender Equality Act compliance, good practice development and smart economics, these contracts will meaningfully consider how programming has contributed to reducing gender equality and support women’s economic empowerment. The MREL framework will assess programme aims to contribute to unlocking inclusive growth and efficiency by considering programme progress on:
1. Systematically assessing the gender impact of current practices and proposed interventions (benefits and losses on women and men and impact on the gender relationship between them);
2. Tackling gender-specific barriers to business and supporting gender sensitive business environment reforms, including: legal and regulatory reform of discriminatory laws, formal and informal rules, regulations and business practices, and their implementation;
3. Targeting sectors and linkages with the most potential to impact women’s employment, entrepreneurship and socio-economic situation;
4. Disaggregating the collection, tracking, and measurement of data, results and impact.
5. Ensuring interventions do no harm and do not worsen gender inequality and discrimination

In practice this means that
1. Gender and inclusion is integrated across programme diagnostics, design and implementation
2. Senior leadership and the programme team will ensure programme management incentives, systems and processes are robust and in place to support gender and inclusion mainstreaming
3. There is the required social development and gender technical expertise of sufficient quality and seniority to support the team in quality delivery and institutional mainstreaming
4. Team capability and institutional capacity is sufficient to support gender & inclusion
5. Procurement processes include gender and inclusion components and downstream partners are help to account for gender and inclusion capability and delivery
6. Risk management processes monitor gender equality act compliance and identify, monitor and mitigate potential risks and unintended consequences of programme interventions
7. A communications strategy to ensure all stakeholders are familiar with the requirements, that they understand their role and contribution to these and gender and inclusion dimensions of business environment reform are included in policy dialogue and programme results’ reporting.

# Appraisal Case
We considered a number of options for delivering the monitoring, reporting, evaluation and learning (MREL) services that the Prosperity Fund requires. These revolve around two main issues. The first is the extent to which the secretariat provides MREL services or contracts them out. The second is the extent to which contracting is centralised or decentralised, i.e. to programme and project level.
Four main options are considered here:
## Option 1
Would be for these services to be delivered “in house”, i.e. through the Prosperity Fund secretariat.
Options 2 to 4 would involve contracting out the majority of the MREL services. Under options 2 to 3, the secretariat will be responsible for managing the contractors, interfacing with broader management and governance structures and ensuring the quality of monitoring and evaluation products. In addition, departments and posts that will be implementing Prosperity Fund activities will be required to conduct the majority of monitoring and reporting activities including carrying out annual reviews.
Option 2
Would involve contracting out all MREL services in a single central contract.
## Option 3
Would involve subdividing the contracts for MREL services into three sub-lots - one lot focused on technical support to monitoring and reporting, one focused on evaluation and learning at the Fund level and one focused on programme evaluations. Option 3 might involve sub-divisions into further lots, e.g. one for operational research and another for measuring/modelling UK benefit.
## Option 4
Would involve projects and programmes managing and contracting their own monitoring and evaluation. This approach has been taken by other similar funds, e.g.
the International Climate Fund (ICF) but difficulties have been encountered in ensuring cross-Fund lesson learning and that adequate M&E capacity is available. Under this approach, the central evaluation contractor would carry out little, if any, primary evaluation work but would largely synthesise work done by others.
## Option 5
Create cross-government monitoring & evaluation function for cross-Whitehall ODA funds (e.g. CSSF, Empowerment Fund)
In assessing the five main options a number of criteria have been considered including expertise, independence, transaction costs and risk. These are presented in tabular form with each of the four options scored on a range from 1 (low) to 5 (high) (See over the page)
	Options
	1 2		3	4	5
The option is feasible given M&E capacities and expertise available to the secretariat	1	4	5	5	3
Evaluations will be independent of programme implementation and management	1	5	5	5	5
Transactions costs for the secretariat are likely to be low/manageable	1	5	5	1	2
Risks are low	1	2	3	2	3
Total	4	16	18	13	13

On balance, it is not going to be feasible to deliver all MREL services in house (option 1). The secretariat does not have the expertise and the challenge in sourcing and developing skills costs would be high. Furthermore, for evaluation to be externally credible it needs to be independent of the organisation disbursing funds. Similarly, Option 5 would require significant time to establish given the lack of available expertise across Whitehall, and would require a separate process from this business case due to the nature of cross-Whitehall authorities and responsibilities. Due to the importance and HMT requirement to establish rigorous MREL processes on the Prosperity Fund, particularly as programmes begin implementation, Option 5 is not desirable.
The options (2 and 3) of contracting out MREL services are likely to be preferable and there are some advantages of dividing this contract into sub-lots (option 3).
There may also be smaller lots on operational research and modelling UK benefit.
This tendering of MREL is common practice in development financing organisations. Learning from funds such as CSSF have identified coherence issues when programmes run their own M&E, which is a particular problem when performing portfolio management addressing Fund performance, making Option 4 less desirable.
On balance, and drawing on the experiences of DFID and DECC in their Girls Education Fund and International Climate Fund, the preferred option was to contract out MREL services in three lots (one lot focused on technical support to monitoring and reporting, one focused on evaluation and learning at the Fund level and one focused on programme evaluations) and requiring the central contractor to conduct evaluations of large country programmes, thematic programmes and the small projects fund.

# Commercial Case
## Procurement Strategy
A number of sourcing options were considered for delivering the monitoring, reporting, evaluation and learning (MREL) services that the Prosperity Fund required. These included Open, Restricted and Negotiated procedures, as well as use of existing frameworks. To determine the best route, an assessment was made with support from the market on the compliant procurement route that offered value for money in a timely manner.
The Programme team assessed the viability of the Global Evaluation Framework Agreement (GEFA) tendered by DFID on behalf of all Central Government. The tender process for this framework commenced in early 2016 and was awarded in August 2016, with the agreement commencing in September 2016.
Tendering of three contracts was undertaken for the following contracts:
1. Fund Level Monitoring and Reporting (forecast value=£13m)
2. Fund Level Evaluation and Learning (forecast value=£16m, plus)
3. Programme Level Evaluation and Learning (forecast value = £15m)

## Fund Level Evaluation and Learning Services & Programme Evaluations
### Market Engagement
GEFA had a launch event on the 13th October 2016 in East Kilbride, which was attended by the FCO Procurement representatives. DFID outlined supplier expectations, evaluation department expectations, reporting and system information.
### Procurement Approach
The GEFA which has 18 suppliers provided a procurement route on Lot 2 Performance Evaluation, for the Fund and Programme level evaluations requirements.
All communication with bidders was undertaken through the FCO’s Bravo Solutions e-Sourcing portal service to ensure full audit trail of bidder communications, including receipt and response to Bidder Clarification Questions.
A total of 19 suppliers accessed the Invitation to Tender (ITT) for the Fund and Programme Level Evaluations with three bids finally submitted on the due date.
The evaluation criterion used was Most Economically Advantageous Tender (MEAT) in line with GEFA set criteria, 60 marks (60%) technical and 40 marks (40%) commercial.
The qualitative Technical evaluation comprised of five (5) weighted categories. Each category was split into a number of criteria and the weightings divided across those criteria to give weighted criteria. Each criterion contained a number of separate questions, but evaluation scoring was conducted at the criterion level with experts used to review and report on individual questions and to provide input to the overall score for the criterion where applicable.
## Fund and Programme Evaluation Sectional Weightings
Question Number	Description	Sub-Weighting %
TECHNICAL (60%)
1.	Resource	12%
2.	Methodology	26%
3.	Co-operative Working	6%
4.	Delivery	12%
5.	Comms Media	4%
	TOTAL CRITERIA WEIGHTING – TECHNICAL	60%

### Value for Money
The Commercial evaluation was based on Whole Life costs across the planned four years of the contract.
The pricing model placed an emphasis on Bidders to propose a competitive daily rate fee based on Staff costs inclusive of all indirect labour costs, Operational Costs and Expenses and Management fee/ profit % to only be applied to total labour costs as opposed to operational and costs and expenses.
To fully understand the commercial offerings, each supplier was presented with an opportunity to clarify their pricing in one-to-one meetings with the Commercial team to provide a summary of additional benefits that could be achieved by awarding both contracts to one bidder.

## Monitoring and Reporting Services
### Market Engagement
An FCO market consultation event was held on the 4th November 2016, with organisations who were considering participating in the competition. The event hosted 12 potential providers and provided additional background to the requirements whilst also providing an opportunity for FCO to address any technical clarification raised from the Terms of Reference. Procurement Approach
GEFA does not have an appropriate lot for the Monitoring and Reporting Services requirement, this was advertised via open competition to the market.
The Monitoring Reporting Services tender was let via the Official Journal of the European Union (OJEU) Open Procedure Route. Two suppliers submitted proposals.
A total of 42 suppliers downloaded the ITT from the e-Sourcing Portal and two (2) suppliers submitted a proposal prior to the deadline of 2nd December 2016.
The evaluation of tender was based upon the split of 70 marks (70%) technical and 30 marks (30%) commercial on a MEAT basis (Most Economically Advantageous Tender).
ITT Responses had to achieve an overall minimum score of 35 marks (50%) in the Technical evaluation in order to move to the Commercial Evaluation stage.

The qualitative Technical evaluation comprised of Five (5) weighted categories. Each category was split into a number of criteria and the weightings divided across those criteria to give weighted criteria: / TECHNICAL (70%)
1.	Resource	14%
2.	Methodology	30%
3.	Cooperative Working	7%
4.	Delivery	12%
5.	Comms Media	7%
	TOTAL CRITERIA WEIGHTING – TECHNICAL	70%

## Value for Money
The Commercial evaluation was based on Whole Life costs across the planned four years of the contract on a time and materials basis using the Suppliers standard day rates per staff grade.
Value for Money will be accessed throughout the life of the contracts via yet to be agreed Key Performance Indicators and contract management processes. SMART indicators will ensure effectiveness, efficiency and a partnership approach to the delivery of the services
The pricing model placed an emphasis on Bidders to propose a competitive daily rate fee based on Staff costs inclusive of all indirect labour costs, operational costs and expenses and management fee/ profit % to only be applied to total labour costs as opposed to operational and costs and expenses.
## Contract and Performance Management
The main contract will contain regular review points and break clauses at key stages to ensure a competitive element is maintained and to reduce the risks of poor performance. Indicators will be agreed and developed during the implementation stage.
Overall performance will be monitored and managed in a number of ways, including:
- Measurement of key attributes of performance through performance reviews, management information and reporting.
- Quarterly performance meetings with procurement and stakeholder involvement
- Audit of compliance with obligations set out in the contract
- A specific contract manager to be appointed within the secretariat to monitor contractual responsibilities
- An expert advisory group to monitor supplier performance
- Notices of material breach of terms with a period for cure of the alleged nonperformance
- monitoring progress against Key Performance Indicators and Payment by
Results mechanisms such as milestone payments
- managing contract variations
- maintaining contract documentation
- risk and benefit management
- contract reviews including cost review
- escalation, issue resolution and conflict management
- mobilisation and exit management
## Comment on commercial outcomes
Evaluation and Learning:
Through market engagement we knew that there would be a small number of technically specialist bids that would come in through the tender. Using the DFID framework for evaluation meant we were targeting specialist companies. We further made it clear to all MREL bidders that in order to maintain independence of evaluation we would not allow companies working on evaluation to bid for programme implementation contracts.
Monitoring and Reporting:
As we went through open competition for this contract we expected a wider range of bids than we received. In the end the bid met technical quality criteria was awarded the contract” and remove the entire last two statements.
# Financial Case

As set out in the strategic case, the Fund has earmarked 5% of its total funding for monitoring and evaluation activities and products. This requires the Fund to spend ~£65million over the funding cycle to 2021 on M&E related activities. Following the tender process we have the envelope of costs that suppliers will charge to carry out this work.
As we have engaged with suppliers and reviewed their work plans the most sensible approach to payments will be a hybrid fee-based and output-based approach. Where central, ongoing costs and most fixed costs are identified we will set up a fee-based payment schedule. Where the costs are directly associated with outputs (evaluations, analysis etc.) we will look to pay on an output basis.
There will be significant costs associated with the inception phase and we will look to have a significant payment point at the end of successful inception. This inception phase will also identify the deliverables that we expect to see emerge through the implementation of the contracts and this will allow the MREL team to establish a clear payment forecast for the years 2-5 process.
Inception phase is expected to run for six months from the contract inception date. We will make it clear to the successful contractors ahead of contracting that we expect to revisit the costs of the programme at the end of the inception phase and will use the unit costs identified in the tender process to build a cost and associated payment schedule for the implementation phase. We will continue to drive for value for money in the negotiations around contracting and at the end of the inception.
## Cost Variation
There is potential for cost variation in the contracts, particularly for EL. The services under the MR contract should be stable and predictable, following the reporting requirements of the fund for monthly financial reports, quarterly result reports and analysis and inputs into the annual report for the fund. But there will be some research that needs to be commissioned within years, that is not foreseeable but this will be a small item within the total costs.
The EL contract costs however are heavily output based. At the start of this process, we anticipated up to 55 programmes that would need evaluation support. We now believe that this number will be less than thirty (although we will only know for sure when business cases are approved). One of the key outputs from the inception phase will be clarity on the number of evaluations that will be needed, the methods that will be used and the costs that these will incur. On the basis of that information we will adapt our financial profile. While the likelihood is that the costs will be lower, the MREL budget, identified by HMT as 5% of Fund expenditure, has sufficient headroom to cope with some cost increases. We have set the envelope for these services at £48million, and will not breach that limit.

## MREL management costs
These comprise the costs of the team and the FCO platform to deliver the management of MREL. We have consulted with HR, and at present the vision is for
1xD7 (SRO), 1xC4 (Assistant Economist) 1xC5 (contract manager / operations officer).
We will make a judgement on the shape and size of this team as we move through inception and it is possible that we will need to add a D6 evaluation adviser to the team. This staffing plan has been agreed by Fund management and will be fully financed through the 5% of Fund expenditure admin overhead identified in the HMT settlement letter for the Fund.
Financial Profile for MREL:
		Total forecast spend
Inception (FY17_18)		£ 3,874,209.00
Year 2 (FY17-18))		£ 7,207,029.00
Year 3 (FY18-19)		£ 8,816,196.00
Year 4 (FY 19-20)		£ 9,426,028.00
Year 5 (FY 20-21)		£ 9,055,690.00
		£ 38,379,152.00

In line with Cabinet Office recommendations we will negotiate clear exit and extension arrangements before signing contracts.

# Management Case
The contract will be managed out of the Fund Secretariat with the SRO being the head of monitoring and evaluation. An advisory panel, with a diverse range of specialities and experience, has been appointed to provide challenge and support. At the start of inception the MREL team will gather the contractors to deliver an MOU for effective joint working between the contracts. The head of M&E within the secretariat will meet with the lead suppliers at least once per week through inception to drive the work plan. During implementation this meeting rhythm will slow to every two weeks and will be reviewed to ensure close and active contractor management. A governing board with external advisors has been established and will meet quarterly to discuss performance under the contract and provide challenge to the suppliers and offer technical advice to the MREL team. A project board will be chaired by the SRO and will be comprised of senior cross-Whitehall staff with contract management experience.
Infrastructure Projects Authority (IPA) review in January 2017 made important recommendations around the management of these contracts. A clear project plan is in place for the contracts inception period in line with these recommendations, which will allow the team to ensure delivery stays on track.
The implementation phase delivery plan will be developed with the contractors during the inception phase. This phase is crucial due to the uncertainty on the number, and characteristics, of Prosperity programmes: business cases are currently being reviewed and approved internally. The inception phase will allow us to gain greater specificity on what precisely will be delivered by suppliers to approved programmes. On the basis of the delivery plan the financial case will be reworked and presented as part of the inception report for each contract and will provide the basis for financial planning for years 2-5.
In line with IPA recommendations a contract manager will be appointed to support the MREL team and to ensure that what we have agreed as outputs for delivery are actually delivered and that they are appropriately paid for in line with the commercial case.
The staffing model will consist more broadly of a Project Director supported by a C4 (economist) project lead for MR and EL alongside the contract manager detailed above. Active management of these contracts, particularly during inception but also through implementation will be key to ensuring the quality and effectiveness of the outputs through the life of the contracts. The advisory board will assist in quality assurance and the external experts that will sit on this board will have the capacity to conduct short reviews at the request of the board to ensure that feedback to the contractors is expertly evidenced.
There is potential for disputes between the contractors that are appointed and more broadly between them and the PF project implementers. While every effort will be made to minimise this risk, the advisory board will be expected to consider the causes of any disputes and, in line with the contractor MOUs and the TORs for the PF project implementer, propose possible solutions.
The main risks for the project strands are outlined in the project risk matrices in Annex C. In line with IPA review recommendations we are building a comprehensive risk register which combines the different strands.

Contract Provisions – Termination for Default:
Whilst accepted that the GEFA provisions for termination are ‘light touch’, the PMFO does have the scope to either suspend or terminate the Call-off agreement where the services are not provided to its satisfaction. In doing so, the PMFO, will communicate the action required by the Supplier to remedy the dissatisfaction and the time within it must be completed.
In the event that the Supplier fails to remedy the satisfaction, then the PMFO could immediately terminate the Call-off.
For Monitoring and Reporting, PMFO could terminate the contract by written notice to the Supplier if the default is not remedied within 25 working days. There is also a break provision that permits PMFO to terminate the provision of all or any part of the services by giving three months written notice.
Both the Call-off and M&R contract will include robust business continuity provisions to ensure that there are contingency plans in place to ensure that the services are maintained in the event of disruption. Wording will be incorporated into the Agreements to allow the PMFO to inspect and to practically test the plans at any reasonable time.
The PMFO is committed to having a continuous improvement plan to manage each contract so that Suppliers adhere to their agreed contractual obligations along with negotiating any future changes that take place. This will be implemented during the Inception period.

August 2017

[i] OECD (2006) Promoting Pro-Poor Growth: Private Sector Development