Annual Review - Summary Sheet
Title: Monitoring, reporting, evaluation and learning in the Prosperity Fund
Programme Value: £37m for the two MREL contracts in place which run to Nov 2021		Review Date: Dec 2019
Programme Code: N/A	Start Date: September 2017	End Date: Mar 2023

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2022/23
Programme Score	N/A	B
Risk Rating	N/A	Major

Summary of progress and lessons learnt since last review
The overarching objective of Monitoring, Reporting, Evaluation and Learning in the Prosperity Fund (MREL), as documented in the business case, is to provide insight and intelligence to drive innovation and improvement, to support the effective delivery of high-impact programmes and a high-impact Fund.
The delivery of the MREL programme was split into two contracts. A consortium led by PA Consulting were selected to deliver Monitoring and Reporting (M&R) and consortium led by WYG were selected to deliver Evaluation and Learning (E&L) services. The contracts are managed by the Joint Funds Unit (JFU) MREL team and overseen by a Senior Responsible Owner (SRO), Joelle Jenny, the Head of the JFU. This is the first Annual Review of the PF’s MREL programme, covering the period from when the MREL contracts were established (September 2017) to date (December 2019).
Overall the review has found that the decision to set up a centralised MREL system early on for the PF has proved to be wise, in supporting the Fund’s credibility (as recognised by ICAI), ensuring a greater level of consistency and providing necessary preparation to establish the beginnings of a common MREL culture.
The MREL system is currently assessed to be comprehensive and broadly follows good practice, and in some areas is providing thought-leadership (on assessing the contribution of a diverse portfolio of programmes to broad Fund-level outcomes) and innovation (piloting a centralised, online monitoring and reporting IT tool and learning platform).
The MREL system is also currently assessed to be delivering against its core requirements. All programmes are developing or have developed theories of change and logframes, demonstrating contribution to the Fund level Theory of Change. Evaluations conducted to date have generally been found to be high-quality (as measured by the EQUALS quality assurance process) and to be useful (as reported by the PF programme teams). The Prospero online results system is being used increasingly often and the Prospero dashboard to report to the PF board. There have been some good examples of sharing learning via communities of practice on the PF learning platform.
The MREL contracts are also being effectively managed by a small team to ensure Value for Money, and on-going adjustments and adaptations have been made to ensure continued strategic relevance.
However, there remain a number of practical and operational challenges hindering the delivery of more efficient and effective MREL service:
The MREL system was never designed to support programme level MREL design and monitoring activities rather only capturing programme results via Prospero. PF HMG departments, in particular the FCO, need to consider how to fill programming and sector specialist capacity and capability gaps which has been temporarily filled by the M&R service. While the service provided by M&R has been seen as useful and responsive, there is a need for a systematic process for quality assuring the technical assistance provided, and it is not deemed to be a viable long-term solution to filling departmental capacity and capability gaps.
The reporting infrastructure of Prospero has been established and tailored to accommodate evolving needs. It has been significantly delayed in demonstrating its effectiveness due to the lack of logframe data across programme teams. There is still work required to make the reporting more useful to target audiences and to address some data quality issues.
The evaluation products thus far have broadly been deemed to be useful and independently verified as high-quality. However, due to delays in PF programmes, there have been fewer evaluations conducted to date than was originally anticipated. The key area where improvement is needed is make evaluation findings and products more accessible, digestible and sharable to relevant audiences, and to make recommendations clearer and more actionable.
The learning platform has been launched and has a strong membership. The platform has created a space for online peer to peer discussions, is facilitating active communities of interest globally (for example on secondary benefits, and Gender and Inclusion) and is being used as a document repository for guidance and policies. However, the platform is not currently used effectively to share and disseminate learning from the programmatic and thematic evaluations completed to date, in part because the evaluations that have been done to date have only recently been completed.
MREL has a ring-fenced budget of 5% of the overall Fund. Due to significant programme delays, JFU have been paying for central infrastructure (including Prospero) which cannot currently be used to its full potential, as it was designed to service a portfolio in full delivery, which raises some VFM concerns. Taking into account significant programme delays which has reduced the total value of the fund because budgets were not rolled over to future years, coupled with a provisional extension of the Fund until 2023, the MREL budget now has to be spread more thinly over a longer period with a changed profile of demand and viable activity.
However, if these operational and VfM challenges (some beyond direct control of the JFU team MREL) can be overcome in the course of the next year, and the following recommendations addressed, the programme should be on course to get an improved score in the next review.
List of recommendations for the next year
Number	Topic	Recommendation	Who
1	PF MREL logframe	A logframe, based on a theory of change, should be created for the MREL programme to assess progress in future Annual Reviews by the JFU MREL team in conjunction with MR and EL suppliers.	JFU MREL team in conjunction with MR and EL suppliers.
2	PF MREL delivery model	Within the next six months, the JFU MREL team should consider options for future MREL delivery models to cover the period 2021 to 2023.	JFU MREL team
3	PF MREL delivery model	JFU MREL team to clarify MREL roles and responsibilities between all key actors.	JFU MREL team
4	PF MREL delivery model	PF HMG departments, in particular the FCO, need to consider how to fill programming and sector specialist capacity/capability gaps.	FCO
5	PF MREL delivery model	JFU MREL team to consider if the technical assistance provided by the MR supplier (through the MR Operations team) is best way to reduce some programme team capacity gaps. In the meantime, two improvements to the current model: / JFU MR Operations team should build a stronger internal quality assurance process. JFU should also consider how MR Operations work can be externally quality assured. / JFU MREL team to look at the feasibility of having MR Operations team to spend more time with programme teams, in particular FCO programme teams, in FCO London office.	JFU MREL team and MR Operations team
6	PF fund-level indicators	The JFU MREL team needs to monitor to what extent Fund level ‘Portfolio KPIs’ are being used, whether and they will be able to be reported, and whether they need to be refined at all, now the JFU has a better understanding of final intervention designs	JFU MREL team
7	PF evaluations	E&L supplier, JFU MREL team and JFU Points of Contact to further communicate with HMG programme teams on purpose and use of evaluation.	E&L supplier, JFU MREL team and JFU Points of Contact
8	PF evaluations	In relation Annual Reviews and Annual Evaluations, we recommend: / The JFU MREL team, JFU Points of Contact and the E&L supplier should continue to highlight the intended differences between Annual Evaluations and Annual Reviews to programme teams. / JFU MREL team to continue to monitor how the Annual Evaluation and Annual Review process are working together to ensure they are indeed complimentary and not duplicative. If the two processes are found to be duplicative, then the JFU should consider how the processes can be combined. / JFU MREL team to work with programme teams to ensure Annual Evaluations come before Annual Reviews. / JFU MREL team to consider the feasibility of Programme Evaluation Leads working on Annual Reviews in future years.	JFU MREL team, JFU Points of Contact and the E&L supplier
9	PF evaluations	The E&L supplier need to take a more proactive and individualised approach to sharing findings. E&L supplier to make a stakeholder engagement plan for each evaluation and conduct targeted dissemination of findings using a range of products and approaches.	E&L supplier
10	PF evaluations	The JFU MREL team to clarify the process for deciding the scope, method and timing for all types of evaluation (programme, family, thematic, and Fund evaluations).	JFU MREL team
11	G&I	E&L supplier to update the G&I scorecard, in consultation with JFU, and the G&I ref group	E&L supplier
12	PF Learning	The JFU MREL team should carefully prioritise and set clear scope to maintain optimal efficiency of the learning resource (platform and EL supplier’s learning team). Consideration should be given as to how to align with JFUs capability strategy to be complimentary.	The JFU MREL team

Summary response by the Programme Senior Responsible Owner (SRO) (Joelle Jenny – Director, Joint Funds Unit)
I agree with this overall assessment. I strongly support the judgement that “MREL services continue to represent the best insurance policy for the wider PF to ensure effective portfolio and SRO decision-making and accountability” and that “The cost and effort to design and setup MR and EL services in advance of delivery (recognised best practice) is largely justified as it prepares the PF portfolio and individual SROs to be able to effectively measure and communicate progress towards impact”. The decision to put in place ambitious MREL services from the onset, which pre-dates my time, has helped make MREL a central component of the PF, albeit not without some difficulties as outlined in the AR. The recommendations will support the journey to adapt the MREL services to obtain maximum value-for-money and to achieve the overall objective of making the PF more effective. Going forward, it will be particularly important to have a constructive dialogue with FCO colleagues in order to identify the most efficient solutions to capability concerns highlighted by the Review. Other important actions include further clarifying roles and responsibilities, identifying options for MREL services over the extended period of the PF to 2023, and better communicating and sharing the emerging learning generated by the EL services. I agree that this will require making evaluation findings and products more accessible and digestible, and to make recommendations clearly actionable and not too broad or general.

List of Acronyms and definitions
Delivery partners = implementing partners (private companies, multilateral organisations or NGOs) hired by programme teams to implement PF programmes
EL (or E&L) = Evaluation and Learning contract
GPST = FCO Global Programme Support Team
JFU = Joint Funds Unit
JFU Points of Contact = the individual contact person in the JFU. Each programme has one point of contact.
MR (or M&R) = Monitoring and Reporting contract
ODA = Official Development Assistance
PF = Prosperity Fund
PFDU = FCO Prosperity Fund Delivery Unit
Programme Evaluation Leads (PELs) = The E&L supplier has a Programme Evaluation Lead for each programme.
Programme team = HMG government department teams (in FCO, DFID, BEIS, DIT, HMT, or DCMS) that lead on individual PF programme
ToC = Theory of change
SoR = Statement of requirements

A. Introduction and Context (1 page)
Link to Business Case:	https://www.gov.uk/government/publications/prosperity-fund-monitoring-reporting-evaluation-and-learning
Link to Log frame:	The MREL programme does not have a logframe (recommendation below to create one)

Outline of the programme
As part of its commitment to ensure the Prosperity Fund (PF) delivers good impact and value for money across the Portfolio, the Joint Funds Unit (JFU) manage a system to support, coordinate and partially deliver Monitoring, Reporting, Evaluation and Learning across the Portfolio. The overarching objective of MREL is to provide insight and intelligence to drive innovation and improvement and to support the delivery of high-impact programmes. One of the earliest design decisions on the PF was to ensure effective portfolio level MREL processes and structures were in place as Official Development Assistance (ODA) programming moved into delivery.
This MREL system is not a replacement for programme level monitoring functions but looks to provide a range of portfolio and programme level services. These services are designed to support management and accountability by enabling all three levels of the Fund (Portfolio, Departments and Programmes) to access results, progress dashboards and independent assessment of contribution to outcomes. These services are also designed to improve practice across the PF network by surfacing, documenting and sharing the evidence-base and learning underpinning the design and delivery of what is a large scale and innovative fund to support adaptation, course corrections and future design.
The PF portfolio level MREL capability is split and outsourced into two synergistic components:
Component 1: Monitoring and Reporting (M&R)
Monitoring and Reporting (M&R) is delivered through a 4-year £13m contract (Sept 2017 – Nov 2021) with a consortium led by PA Consulting.
Programme Theories of Change and logframes are central to measuring results and adapting to achieve high impact. These are a programme responsibility. The M&R technical assistance work delivers demand-led support to assist programmes in refining theories of change and developing logframes for their programmes to ensure they are able to link into the Prosperity Fund level Theory of Change.
The M&R supplier is also tasked to capture reporting from across the Portfolio and ensure it can be utilised at a project, programme and fund level to inform decisions. This is delivered through an internet-based platform called Prospero.
Component 2: Evaluation and Learning (E&L)
Evaluation and Learning (E&L) is delivered through a circa 4 year £24m contract (Sept 2017 – Nov 2021) with a WYG-led consortium.
E&L are important functions to help ensure a focus on key objectives, maximise impact and value for money, and manage risk.
While supporting accountability, this is not the primary purposes of E&L; instead, learning activities should generate an evidence base (on primary purpose and secondary benefits), help improve the efficiency of PF programmes, and support communication of PF impact. E&L should also address the needs of different stakeholders:
- At Fund level it should assess the extent to which PF is contributing to inclusive economic growth and inform thinking on future, similar Funds through synthesising lessons from programmes and cross Fund evaluation of particular themes;
- At programme level it should test Theories of Change and establish, while the programmes are running, whether they are delivering the outputs and outcomes that will likely lead to impact. Useful and usable learning will contribute to identifying programmes and projects not performing optimally and allowing corrective measure.

The overarching approach to evaluation will be formative (identifying what is working best and where activities are having most success) and utilisation-focused (based on the information needs of stakeholders). Impact of primary benefits should be assessed through contribution evaluations, and a system able to capture and share good practices should be put in place.
An annual E&L cycle will provide the basis for an evidence-based review of progress on what has been achieved, how and why, while enabling the sharing and use of evidence from evaluations to support decision making at project, programme and Fund levels. In turn, a cohesive picture of the programmes, families of projects / programmes that target an intermediate outcome, cross-cutting themes and the Fund itself will be generated over time.
Introduction to this Annual Review
This is the first Annual Review of the PF’s Monitoring, Reporting, Evaluation and Learning (MREL) work and covers the period from September 2017 (start of MREL inception) to December 2019.
The annual review represents a key strategic opportunity to monitor the performance of the MREL contracts and consider whether the activities and outputs are of sufficient quality, timeliness and continued relevance – directly contributing to the effective delivery of the desired MREL objectives for which the suppliers are contracted. It also provides an opportunity for the SRO to consider whether funding, scope or timeframes should be amended to deliver optimal Value for Money in light of changing needs and strategic priorities. In addition, the Annual Review offers an opportunity to reflect on the appropriateness of decisions made in the design of the MREL services, and to make changes were necessary. The Annual Review will also allow help identify areas for improvement in the continued management of MREL services.
The review is led by the JFU’s recently appointed Head of MREL and largely undertaken by MREL staff, plus one team member from the FCO’s PFDU. Thus the review is largely a self-assessment and provides the team that oversees the PF MREL system a chance to reflect and make adjustments where needed. The review was quality assured by an independent evaluation expert.
The key audiences for the review are as follows and shown in the table below and the full list of people interviewed are shown in Annex 1.
Audience for Annual Review	Reasoning
PF MREL SRO	Owns the process, commissions and approves the review. The results of the Annual Review will help the SRO make decisions on whether the programme or its components should be adjusted.
JFU MREL team	Leading on undertaking the review. Also leads on the development and implementation of the strategic vision for MREL and management of the MREL contracts to ensure support continues to meet needs.
JFU team	To demonstrate programme money is being well spent across the portfolio and for accountability and transparency purposes – when giving evidence to the public, civil society, parliamentary scrutiny bodies such as ICAI, IDC, NAO on MREL spend and activities.
PF Portfolio Board	To inform Portfolio Board decisions about programme change, funding, risk management.
PF Departments (FCO, BEIS, DFID, HMT, DIT, DCMS)	To provide an opportunity to hear from users of the MREL service.
Monitoring and Reporting supplier (PA consulting and the Economist’s Intelligence Unit), & Evaluation and Learning supplier (WYG, Integrity and LTS)	To understand areas of good performance, and where adjustments and improvements are required

## B: PERFORMANCE AND CONCLUSIONS

In the absence of a logframe from the MREL programme, in this annual review we will assess the MREL programme against the ambitions set up in the Business Case, which are still widely thought to be the right goals.
Broadly, the goal of the PF MREL systems, as outlined in the Business Case, is to make PF programmes and the PF as a whole more effective (higher impact, better value for money and better managed). This is expected to come about because the MREL system is expected to generate evidence and learning about what is working and what is not, and this evidence and learning is expected to be used to inform decision making on how and where to effectively use resources. There is overall broad agreement that this aim continues to be strategically relevant.
The decision to set up a centralised MREL system for the PF when the Fund began has provided to be effective in supporting the Fund’s credibility, ensuring greater consistency and establishing the beginnings of a common MREL culture. A robust MREL system is key for the PF because the Fund is innovative and testing frontiers of UK aid delivery, and therefore has a responsibility to ensure that it learns as it goes about what is working and what is not, and to share the learning. The MREL system adds to the overall credibility of the Fund as demonstrated by positive feedback from ICAI. It is good that the MREL system was set up centrally by the JFU because FCO and OGDs programme teams would not have had capacity to commission MREL themselves. Moreover, the centralised model allows for greater consistency in measurement approaches, methodologies and tools and the potential to aggregate results at the portfolio fund level. It also gives the possibility for learning between programmes. A benefit of having the MREL system set up from the beginning of the Fund is to create of culture of using MREL and to build it into ways of working. The MREL system is comprehensive and broadly follows good practice – for example all programmes (and projects within programmes) are developing theories of change and logframes for their programmes.
Programmes have been delayed which has created challenges for the MREL suppliers in implementing the services outlined in the inception report from March 2017. Slower than anticipated progress into implementation hinder the ability of programmes to demonstrate results, and MREL to document and evaluate which programmes are working and why within the lifetime of the Fund. Therefore, it is still very early to make a judgement about the achievement of MREL objectives but there are early positive signs and some challenges which we summarise here (and discuss in more detail in the next section).
The delays to programmes mean that the MR and EL contract timelines are now no longer in sync. Some programmes are at present expected to run until 2023, subject to HMG Spending Reviews. However, the MR and EL contracts are due to end in November 2021. This may limit the achievement of longer MREL objectives. Therefore, we are recommending that within the next six months, the JFU MREL team should consider options for future MREL delivery models to cover the period 2021 to 2023. As part of this process, the team can consider:
1. Are the current approaches to MREL still appropriate?
2. Are there other ways that MREL might be able to contribute more to the Fund?
3. What can be done to enhance greater appreciation and use of evaluation amount PF programmes?
This would be an appropriate time to re-engage the Technical Advisory Group, an independent group that was convened to provide strategic advice on the design of PF MREL system.
The JFU MREL team had prepared for 6-9-month delays in programme delivery timescales, however even this forecast was over optimistic with some programmes starting nearly 2 years later than anticipated. The MREL design, infrastructure and technical systems were mostly developed by the end of the MREL inception phase in April 2018, and since then much of the MREL work has focussed on designing programme evaluation approach papers, some upgrades to the Prospero system, and providing technical advice on indicators and logframes. However, the time lag between MREL inception phase and conducting evaluations has led to retention problems for evaluators. It has also meant JFU have been paying for central infrastructure / management costs which can’t be used to its full potential, as it was designed to service a portfolio in full delivery, which has raised some VFM concerns.
There are positive early signs that the MREL system will make PF programmes and the PF as a whole are more effective. These are:
- All programmes (and projects within programmes) are developing or have developed theories of change and logframes;
- The evaluations conducted to date have generally been found to be high-quality (as measured by the EQUALS quality assurance process) and to be useful (as reported by the PF programme teams);
- The Prospero online results system is being used increasingly often and enables reporting at the PF portfolio level to the PF board, amongst other users;
- There have been some good examples of sharing learning using the PF learning platform.
There are also a number of risk and challenges that prevent the MREL system from being as effective as it could be. These are outlined in detail in the sections below.
Recommendations:
- Within the next six months, the JFU MREL team should consider options for future MREL delivery models to cover the period 2021 to 2023.
- A logframe, based on a theory of change, should be created for the MREL programme to assess progress in future Annual Reviews by the JFU MREL team in conjunction with MR and EL suppliers.

## C: DETAILED OUTPUT SCORING

In the absence of a logframe for the MREL programme, in this annual review we will assess the MREL programme against the following key outputs of the MREL programme (which were selected by the Annual Review team based on the Business Case and stakeholder interviews):
1. Teams are supported on reporting on core indicators, developing their own indicators and logframes, based on their theories of change;
2. Departments report on programme level output, outcome and impact indicators quarterly through a centralised, online monitoring and reporting IT tool (Prospero), covering primary and secondary benefits;
3. Programme/sector/Fund evaluations provide pragmatic findings on the effectiveness and impact of programmes and the fund and identify better ways of doing things;
4. Lessons from programmes and thematic/sector evaluations are available, understood and used to adapt programmes and refine their theories of change;

Output Title	Output 1: Teams are supported on reporting on core indicators, developing their own indicators and logframes, based on their theories of change
Output number per LF		1	Output Score	B
Risk:		Major	Impact weighting (%):	N/A
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of programme/project logframes on Prospero	N/A	25 (out of 121 potential)
Number of technical support sessions	N/A	109 (in 2019)

The PF MREL business case and the design of the MREL system was based on the assumption that programmes would develop their own programme theories of change and logframe as part of the process of designing their programmes. However, in practice, some programme teams, in particular some in the FCO, have not had sufficient programming expertise (including background knowledge on the concepts and purposes of logframe and theories of change) and relevant sector specialists to do this without support. Programme managers cannot lead on the technical design of the programme through outsourcing – in house skills are needed to interpret and quality assure outputs that come from consultants and suppliers. In order to produce a theory of change and a logframe, teams need a deep understanding of the context, sector and a clear programme design, and as well as knowledge of theories of change and logframes, and some experience in measurement and the selection of indicators. The FCO programme teams have indicated the reason for these capacity/capability gaps are because many programme teams have been staffed from within the pool of people who are already FCO staff (who have historically not done this type of ODA programming work and hence may not have the relevant experience). The FCO has invested in two MREL positions who are working to upskill programme team with the concepts and purposes of logframe and theories of change. However the FCO carries a significant portion of the Fund, and with only two MREL advisors the capacity is stretched. In addition, these roles are unable to fill gaps in relevant sector expertise across the range of PF sectors.
HMG Programme teams need expertise in their team to do the following:
1. Develop/draft and owns the design of their programme including the theory of change and logframe (led by a person(s) with relevant sector, social development, and M&E experience) and revise over lifetime of programme as required
2. Write MREL requirements for suppliers / delivery partners and ensure they are conducting quality monitoring (collecting good quality data on the right indicators);
3. Develop a reporting plan with suppliers / delivery partners identifying what information programme teams need, and when
4. Input into the evaluation approach, including prioritising evaluation questions (requires consultation with E&L supplier and wider programme team), engaging in the evaluation process, reviewing evaluation products and using the evaluation findings to improve programme delivery.
5. Writing management responses to programme evaluations and prepare the annual review and evaluations for publication on gov.uk
6. Use evaluation findings to improve programmes and refine their theory of change
7. Use their logframe throughout implementation to monitor programme performance and to support effective programme delivery (monitoring progress against project and programme logframes, based on supplier reporting, and reporting results on Prospero)
8. Lead (design and deliver) programme annual reviews

In response to the capacity/capability gap in programme teams, the JFU adapted the MR contract to try and partially fill this capacity/capability gap even though the contracts were not initially intended to be used this way. However, the MREL contract will never be able to fully meet the capacity/capability gaps and FCO need to further consider and take action to ensure their programme teams have the relevant skills and experience.
PA Consulting were asked to set up “MR Technical Operations team” to provide technical support to programme teams on articulating their theory of change and developing logframes. This was set up as a “demand-driven” service where programmes teams could request support as and when they needed it and should demand exceed supply the MR Operations team would prioritise requests following guidance from the JFU MREL team. The MR Technical Operations team consists of 6 full-time advisors who support the whole PF portfolio. During 2019 they have delivered 109 support sessions, including 8 in-country visits to offer focussed support on specific programmes for a week on average. On the whole, programme teams have been very positive about the responsiveness and helpfulness of the MR Operations team and there is some evidence that the MR Operations team has built some MREL capability in programme teams.
However, there have been a number of challenges with the support provided by the MR Technical Operations team. Firstly, there has been significant confusion regarding roles and responsibilities, and in some cases this continues to date. There was an initial misconception amongst some programme teams that the MREL contracts would many of the tasks listed above which are in fact the responsibility of programme team. This confusion often leads to frustrations and confusion on all sides and a passing of the buck when things are not done on time or not done well. JFU MREL team has not had the time to engage frequently with each programme team to ensure roles and responsibilities are clear, which can be particularly challenging when programme teams are spread across the globe and there are over 130 key programme team contacts working in PF countries and an additional 100 UK based HMG PF programme stakeholders.
The lack of capacity/capability in programme teams has also meant that having a “demand-led” service has not worked very well because programmes teams have not always known what support or ask for, have asked for it at the wrong time or have been unsure what they could ask for support with. The MR Operations team responded by offering their services. However, this was sometimes offered at the wrong time, and in some cases programme teams thought that engaging with MR Operations was a requirement of JFU and did not feel able to push back. This has led to situations such as logframes being developed before programmes were clear on their programme design or theory of change, or MR Operations setting up workshops on logframes or theories of change which programmes teams were not adequately prepared for.
There have also been some challenges in delivering sector-specific technical support to programme teams. The MR Operations team are made up of six analysts, who cover all 27 programmes in the PF portfolio. They have generalist M&E skills to help programmes meet PF requirements in the design of MR tools, but were never intended to offer detailed sector technical support expertise for all PF programmes. There have been isolated incidences of the MR Operations individuals being too junior/inexperienced to provide quality expert support and facilitation. These issues have been identified on an ad hoc basis but the JFU does not have a systematic process for quality assuring the work of the MR Operations teams.
Additionally, the support provided through the MR Operations team is not necessarily sufficient to meet the demand from programme teams. For example, the FCO teams would like help reviewing the project level logframes (which sit under the programme level logframes) by March 2020 and, unless they pivot their work plan significantly, MR Operations team will not have enough time to do this.
In hindsight, it may have been better to use EL contract to provide this technical assistance because the Programme Evaluation Leads (PELs) (who are part of the E&L supplier’s team) are generally more experienced and stronger technically in M&E, have better sector knowledge than the MR Operations team and because many of the PELs are based in PF countries so could more easily build working relationships with programme teams[1]. The reason that the EL contractors were not selected for this work was because a distinction was not made between designing a programme and articulating a theory of change. At the time the technical assistance was being procured, the E&L supplier said they could not be involved in developing theories of change because then when they did the evaluation, they would be “marking their own homework”. However, it is normal good practice for evaluation team to write down the programme’s theory of change based on what the programme teams communicate as the design of the programme.
[1] Although the different delivery models and objectives of the MR technical operations team and PEL support mean that this is not necessarily a like-for-like comparison.
Another alternative option would have been to embed M&E consultants in the programmes teams requiring capacity/capability support. A challenge around this would be working out where the consultants should be based given that most PF spend is in 26 countries. A benefit of this option would be that the person providing the support would be able to build closer relationships with the programme team and thus provide more targeted support. Some programmes teams have commented that the relationship with the MR Operations team is necessarily formalised (e.g. programme team must send requests, set up intro calls etc.) which is quite different to be co-located and feeling part of the same team.
A challenge with all these options (use MR to provide support, use EL to provide support, hire consultants to be embedded in programme teams) is that they are short-term solutions. Moreover, none of these options solve the problem of the shortage of sector expertise in programme team to lead on the design of the programme. Ultimately, programme teams need to take ownership of developing their own theories of change and logframes, and to staff their programme teams with the necessary capacity.
Recommendations
- JFU MREL team to clarify MREL roles and responsibilities between all key actors.
- PF HMG departments, in particular the FCO, need to consider how to fill programming and sector specialist capacity/capability gaps.
- JFU MREL team to consider if the technical assistance provided by the MR supplier (through the MR Operations team) is best way to reduce some programme team capacity gaps. In the meantime, two improvements to the current model:
  - JFU MR Operations team should build a stronger internal quality assurance process. JFU should also consider how MR Operations work can be externally quality assured.
  - JFU MREL team to look at the feasibility of having MR Operations team to spend more time with programme teams, in particular FCO programme teams, in FCO London office

Output Title	Output 2: Departments report on programme level relevant logframe indicators quarterly through a centralised, online monitoring and reporting IT tool (Prospero), covering primary and secondary benefits
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	N/A
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Portfolio Board receive useful reporting through the MR system	Monthly Portfolio Board Dashboard produced through Prospero	Achieved in July 2019
Programme reporting to JFU using the MR system	Programme Quarterly Reports delivered via Prospero	Achieved for Q2 2019/20

A cross-departmental portfolio information management system, called Prospero, was created as part of the MR contract. It is designed to collect different sets of data from across departmental systems and programmes, and present a single source for all this information. This enables better portfolio management by having easy and ready access to the Fund’s data.
Prospero is a useful tool for oversight of the whole PF portfolio. It is especially good that the PF has invested in this system given that PF is a cross-government Fund and historically it has been challenging to get IT systems to work across departments. All departments in the UK can log in to the Prospero system without problems. There have been isolated incidents of posts overseas not being able to login due to internet speeds.
The Prospero system is most useful to the JFU to monitor the PF portfolio as a whole. It enables the JFU to report to PF Board of Directors, Ministers and other stakeholders such as HMT and ICAI. The system has only recently started to be used given programme teams have been focused on designing programmes and procuring delivery partners. In the past few months programme teams have begun engaging with the Prospero system more now that their quarterly reports to JFU are pre-populated with data from Prospero. The MR supplier are continually building in new functionality on a regular basis based on stakeholder feedback and JFU vision.
Some programme teams initially thought Prospero was going to be a programme management tool and were frustrated when they discovered it was not. As the Fund operates across six departments, it is not appropriate for JFU to build departmental operating systems – this could be significantly more costly, and duplicative of what is already in place in the majority of the departments, with the exception of the FCO.
The JFU Strategy & Advisory team and the MR supplier worked together to identify the Fund level ‘Portfolio KPIs’. These cover the key sectors that the Fund is operating in and help aggregate outcomes. The MR supplier created methodology guidance notes to help programmes collect KPI data. These Fund level ‘Portfolio KPIs’ were developed early to ensure they were embedded into programme M&E systems.
There are currently 253 user accounts for Prospero, covering almost everyone who works in the Prosperity Fund. 218 of these users have been provided with in-person training (or over video-teleconference for those abroad). The Prospero system draws data from back-office systems where feasible to minimise the burden on programme teams, such as staffing and finance data. JFU have tried to get access to DFID finance systems due to repeated data quality and timeliness problems experienced with the off-line reporting from programme teams, but have been unable to get access yet. This causes delays for the rest of the PF portfolio, as the whole dataset is required before it can be uploaded for a number of reasons (e.g. programmes being implemented by multiple departments).
Data quality will likely remain a risk that the MREL team monitor, because the reporting systems can only be as good as the quality of the data inputted. This could be a persistent risk due to the low levels of programming capabilities in programme teams.
Prospero has recently been upgraded to have a ‘Good News Stories’ to capture the narrative achievements of programmes which may not be as accessible through quantitative data. There are a number of different communication channels (e.g. Twitter, Diplomatic Telegrams) and the JFU MREL team will need to ensure that Prospero complements these systems, rather than create confusion.
After broad engagement across the network to design a new Quarterly Reporting template, the first use of Prospero to facilitate the Quarterly Reporting process was achieved for Q2 2019/20. The new process significantly reduces the amount of narrative reporting required by pre-populating the report with data, and subsequently the administrative burden on programme teams. A survey was conducted to seek feedback, and the MR supplier are using these insights to improve the report for Q3 2019/20.
While the reporting processes of Prospero have been achieved, it was significantly delayed due to the lack of logframe data across programme teams. There is still work ongoing to make the reporting more useful to target audiences. Reporting is also slower than desired, and still has some data quality issues, both of which are being driven by late and inaccurate finance reporting from non-FCO departments, primarily DFID. As a result, this output has been scored a B. However, the improvements to the reporting system looks to be very achievable in the months immediately following this Annual Review, so the programme is likely to get an improved score in the next review.
Recommendations:
The JFU MREL team needs to monitor to what extent Fund level ‘Portfolio KPIs’ are being used, whether and they will be able to be reported, and whether they need to be refined at all, now the JFU has a better understanding of final intervention designs

Output Title	Output 3: Programme/sector/fund evaluations provide pragmatic findings on the effectiveness and impact of programmes and the fund and identify better ways of doing things
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	NA
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Proportion of evaluation products which are rated ‘fair’ or above by EQUALS	90%	93%
Proportion of evaluation products which are rated ‘good’ or above by EQUALS	60%	79%
Quarterly Feedback Report findings	Stakeholders find evaluations insightful and useful	While the evaluation products are deemed rigorous by EQUALS, and the majority of evaluations have been viewed as useful, the communications and dissemination of key implications require improvement

The evaluations produced to date have been to a high standard, as measured by EQUALS quality assurance. However original assumptions within EL work plans were overly ambitious about the speed of delivery and when programmes would be sufficiently advanced to usefully engage with evaluation. The evaluation offer was also probably overly complex given the maturity of the Fund and the target audience. Far fewer programme evaluations have been completed to date than originally planned. Upward synthesis into thematic, family and fund evaluations has also been limited due to the dependence on programme evaluations. JFU and the EL supplier have recently taken positive steps to slow down activity and to better tailor EL services to Fund maturity in order to protect VfM. With hindsight intervention to re-scope and delay some evaluation activity could have happened more quickly. On that basis this output scores B.
To date the E&L supplier has completed 7 Programme evaluations, 4 programme readiness reports, 5 thematic evaluations (G&I, VfM, Secondary Benefits, Anti-corruption, and SR evidence) and 1 Fund evaluation. In addition, a further 6 programmes and 9 ‘families’ have completed approach papers.
During the inception phase the JFU evaluation advisor and the independent Technical Advisory Group raised concerns about the quality of the supplier’s team and the proposed methodological approaches. However, more recent feedback from relevant stakeholders on the evaluations done to date has largely been positive. Many programme teams have noted to the quality of the Programme Evaluation Leads (PELs) both in terms of technical evaluation and sector expertise and engagement with teams. The JFU evaluation advisor post has been vacant for most of 2019 and will be filled from early 2020. It should be a priority of this person to review the quality of the evaluation outputs, seek views from the Technical Advisory Group and develop a strategy for ongoing support of quality, noting that the usefulness of evaluations is a key component of quality.
The evaluations were set up to be formative (i.e. to provide early learning and insight to improve programme implementation) and user-focused. Most programme teams interviewed reported that it has indeed been participatory process with teams being able to input into the evaluation questions being considered and being able to closely engage with critical friends independently generating and brokering evidence to support course-correction. However, the evaluation team has noted that some programme teams do not appreciate the value of regular evaluations and that is intended to lead to adaptive programme management. Some programme teams also do not fully appreciate that the evaluation team also need to use programme level data collection process to collect information to inform Fund-level evaluations and therefore not everything that the evaluation team does will be immediately useful to them. These issues are most prevalent for programme teams that are yet to have an evaluation. In most cases once programme teams have had an evaluation, the value becomes clearer.
Some programme teams are still unsure of the key differences between Annual Reviews and Annual Evaluations and why the PF has both. From interviews with stakeholders who designed the MREL system, it is clear that the two process are meant to be complementary rather than duplicative.
- Annual Reviews were intended to be an internally led process reviewing work over the previous 12 months, focusing on processes and outputs. They were intended to provide programmes with time set aside to reflect and make changes where needed.
- The Annual Evaluations (originally called Annual Learning Reports) were intended to be independent and externally implemented reviews of the programme, done by experts in the field, focusing on the plausibility of the theory of change. The evaluation will initially focus on assessing processes and outputs but will focus more on contribution to outcomes over time (therefore over time the two processes are expected to be more distinct and different).
- The Annual Evaluations are planned to take place a few months before the Annual Reviews and are intended to collect evidence and generate recommendations that can then be used by the Annual Review team, and so were expected to make the Annual Review process quicker. In addition to providing findings for the programme teams, programme evaluations also collect information that can be used to answer questions about the Fund as a whole.

Due to uncertainty around the Annual Review dates at the start of the Fund (which arose because of uncertainty about when some final business cases would be signed off) some evaluations happened after the annual review (e.g. Brazil) and one at the same time (China).
Some programme teams have raised concerns about using too much of their stakeholders’ time with two sets of interviews (one for the Annual Reviews and Annual Evaluations). Where this will be an issue, given the large of number stakeholders on each programme, it should be possible for the Annual Review team to not interview the same people as the evaluation team. For Financial Year 2019/20 the JFU have also provided each programme team with 10 days of their PELs time, which can be used flexibly including having the PELs work directly on the Annual Review. This ensures that any relevant information collected as part of the Annual Evaluation that is missing from the evaluation report can feed into the Annual Review. Programme teams have reported this support has been beneficial.
The JFU MREL team manage the scope, timing and approval of evaluation activities and products, using DFID’s EQUALS evaluation quality assurance process. Both programme teams and the evaluators have given positive feedback for the QA function being provided by EQUALS (although some questions raised on the consistency of feedback).
PF evaluations are performing above EQUALS average compared to benchmark across all HMG. 79% of all PF evaluation products submitted to EQUALS scored good and above, and 93 % scored fair or above. The remaining 7% of unsatisfactory products (2) were rejected by JFU, improved and resubmitted. Comparatively the HMG benchmark is 60% of products are good or above and 84% fair or above. PF evaluations are technically robust and externally credible.
There has been some confusion regarding who makes decisions regarding the timing and scope of evaluations, in particular what programme teams and other stakeholders can influence and what has already been decided.
Recommendations:
E&L supplier, JFU MREL team and JFU Points of Contact to further communicate with programme teams on purpose and use of evaluation.

In relation Annual Reviews and Annual Evaluations, we recommend:
  - The JFU MREL team, JFU Points of Contact and the E&L supplier should continue to highlight the intended differences between Annual Evaluations and Annual Reviews to programme teams.
  - JFU MREL team to continue to monitor how the Annual Evaluation and Annual Review process are working together to ensure they are indeed complimentary and not duplicative. If the two processes are found to be duplicative, then the JFU should consider how the processes can be combined.
  - JFU MREL team to work with programme teams to ensure Annual Evaluations come before Annual Reviews.
  - JFU MREL team to consider the feasibility of Programme Evaluation Leads working on Annual Reviews in future years.

The JFU MREL team to clarify the process for deciding the scope, method and timing for all types of evaluation (programme, family, thematic, and fund evaluations).

Output Title	Output 4: Lessons from programmes and thematic/sector evaluations are available, understood and used
Output number per LF		4	Output Score	B
Risk:		Major	Impact weighting (%):	NA
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Number of ‘Communities of Practice’ and peer networks on PFLearning	N/A	There are 16 peer networks on PFLearning, facilitating learning on a range of topics
Number of users on PFLearning	N/A	587

Original expectations around wider learning have not been met. This is mainly due to factors outside the control of the MREL programme team and suppliers. Original assumptions about speed of implementation and capability within the network were, with hindsight, overly ambitious and are no longer valid. Whilst very positive progress has been made to pivot and flex evaluation and learning activity to be timelier, fill key gaps, and be more relevant more still needs to be done to better align EL services with the programmes and wider Funds’ actual maturity. In future EL need to further simplify evaluation products and interactions, and target lessons to a less advanced audience. On that basis this output scores a B.
As discussed, only a few programme evaluations (7) have been conducted to date because some were delayed due to delays in programming. The teams that have been evaluated have generally been very positive in terms of the usefulness of the finings (e.g. China, Better Health, and Mexico) and have said that they think the evaluation will lead to more effective programming. The Gender and Inclusion thematic evaluation triggered programme teams to think more carefully about how they are designing interventions to meaningful consider Gender and Inclusion, and documenting alignment to the Fund level G&I policy, and this process has led to Gender and Inclusion action plans (e.g. for the Anti-Corruption programme). The VfM scorecard used in the VfM thematic evaluation has also been supporting more robust and systematic assessments of VfM (VfM scorecards were used as inputs for VfM sections of annual reviews).
The key area where improvement is needed is make evaluation findings and products more accessible and digestible, and to make recommendations clearly actionable and not too broad or general. Long detailed approach papers and reports are needed for those very close to what is being evaluated and to meet the EQUALS requirement, but very few stakeholders will have the time to read long reports in full. The PF needs a wider variety of dissemination tools to be used (e.g. briefing notes, summaries, presentations, webinars, and meetings to discuss the results) targeted appropriately to the needs to stakeholders.
The EL supplier need to take a more proactive and individualised approach to sharing findings. The evaluation process was designed to have seven “learning touchpoints” built into each evaluation process (covering the following areas: validate evaluation questions and plans; evaluation stocktake during the design of the programme; contribute evidence know-how as part of the evaluation data collection; validate findings and develop recommendations; making sense of the evaluation findings; plan follow up actions; wider learning and enquiry) but it is not clear the extent to which these are being implemented. We found some evidence of these processes taking place for some programme evaluations but there were also some evaluations where it does not seem these processes were all implemented (e.g. the first PF fund level evaluation or the G&I thematic evaluation).
To share lessons the PF commission the EL supplier to develop an online site, the PF Learning Platform, which went live in October 2018. The platform is primarily intended to share learning from the evaluations and create communities of interest and a space for online peer to peer discussions globally. The platform was commended by ICAI as “as a strong example of using technology to enhance learning, at a time when legacy technical systems are standing in the way of effective sharing of information and knowledge”.
To date, the EL supplier’s learning team have been flexible and supported a range of initiatives to support common gaps in individual capability. For example, it has been used well to share learning on commercial skills, secondary benefits, and Gender and Inclusion. Additionally PF learning has been particularly useful as single source of information (e.g. guidance on ARs and G&I) in such a large Fund with many stakeholders.
Moving forward, as more evaluations are completed, the EL supplier needs to use PF learning more to share evaluation findings. For example, we think that the ASEAN ER, China, Colombia, Mexico programme level evaluations all contain very valuable findings and learning that would be of use to other programmes now.
JFU has explored opportunities to join up individual and organisational learning strands through a single platform. From April 2018 there was a six-month pilot of on-line training courses developed by Red R that were hosted on the PF learning platform. Feedback has been positive and this will inform options appraisal during the development of the JFU capability plan currently underway.
Recommendations
The E&L supplier need to take a more proactive and individualised approach to sharing findings. E&L supplier to make a stakeholder engagement plan for each evaluation and conduct targeted dissemination of findings using a range of products and approaches.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Economy: Whether the programme is getting the best value inputs by making good judgments about cost, quality and timeliness.
- PF Portfolio MREL services are delivered through 2, fixed value, time and material contracts. There is limited scope to reduce rate card unit costs agreed at contract award. JFU has managed economy through close monitoring and challenge of use of resources towards activities. A recent EL re-scope reduced planned activities by circa £2m in the current FY to reflect the maturity of the PF portfolio (i.e. programmes are less far along in implementation that originally estimated).
- JFU negotiated an additional discount on the EL contract rate card.
- JFU successfully challenged the MR provider to transition to ‘business as usual’ operating model. This removed the use of full-time consultants on the contract. This represented good economy but there has been challenge around some quality control of BAU staff. (This would likely still have been the case with consultants given the range of expertise required)
- JFU team have created commissioning processes to check and sign off call down work requests. This process provides a sound foundation to make evidence-based judgements about cost, timeliness, and quality of proposals. However further improvement is required with suppliers to drive a stronger understanding and challenge around additional value to the Fund from some activities.
- JFU team have defined processes to check and approve the CVs and day rate of any staff to be utilised on the MREL contracts. The team need to work with the EL supplier to be able to take a more holistic view of these appointments. Individual appointments have resulted in a highly skilled and experienced team. However, there has been a greater weighting towards more experienced staff than originally planned and budgeted for in inception. The MREL team should review whether this shift has had any effect on value vs cost judgements of contract economy.
Efficiency: How well the programme is converting inputs into outputs? How streamlined is implementation processes and activities?
- Programmes have been delayed which has created challenges for the MREL suppliers in implementing the services outlined in the inception report from March 2018.
- The MR supplier has adapted and pivoted services from Prospero and reporting activity to technical assistance to support development of theories of change and results frameworks. This has improved use of MR resources to tailor support to where it was most needed. Prospero reporting has taken steps forward with the creation of automated dashboards and quarterly reports. This will increase the likelihood of programmes using the tool for other purposes and create further efficiencies in reporting.
- The EL supplier has delivered fewer evaluations thus far than planned at inception. This is mainly due to delays to programme timelines meaning programmes were not ready to be evaluated. JFU and the supplier have recently re-scoped the work plan. This has delayed or simplified evaluation activity and reduced the amount of resources required in the current financial year whilst tailoring outputs more closely to stakeholders need. The quality of evaluations is good and above the EQUALS benchmark across HMG. However more could be done in future to better understand the relationship between evaluation resourcing and both the; number and quality of evaluation products, and their broader use across the Fund. This includes the better dissemination of products mentioned earlier within this report.
- The EL supplier’s learning team and platform is gaining users and traction with programme teams in the PF network. To date, the EL supplier’s learning team have been flexible and supported a range of initiatives to support common gaps in individual capability. However, in the longer term the platform is intended to support organisational learning using the evaluation findings, rather than provide individual skill development. This may be challenging if programme teams do not have the relevant technical skills or experience; if programme teams do not have the relevant knowledge about a particular subject area, sharing learning from an evaluation covering that particular subject area may require some individual skills development.
Effectiveness: To what extent programme outcomes justify the cost of delivery?
- MR and EL outcomes are heavily dependent on programmes progressing and delivering activities towards achieving their own outputs and outcomes. Programme delays have meant that only a few programmes are currently substantively in the implementation phase. This, and a limited understanding of what MREL is for within the wider network, has limited the effectiveness of the MREL services to date. There is some early evidence that MREL activities are supporting better programming outcomes.
- This is discussed in detail in the preceding sections of this report

Assessment of whether the programme continues to represent value for money
- MREL services continue to represent the best insurance policy for the wider PF to ensure effective portfolio and SRO decision-making and accountability. This should contribute towards the best possible impact from programming. Given the innovative nature of the Fund there is also a responsibility to share what has worked well and what has not with HMG and external bodies.
- The cost and effort to design and setup MR and EL services in advance of delivery (recognised best practice) is largely justified as it prepares the PF portfolio and individual SROs to be able to effectively measure and communicate progress towards impact. The early implementation of a centralised MREL approach has allowed a level of consistency and preparation across the fund than otherwise would have been achieved. The timelines for MREL services have needed to be adjusted to align with that of the PF programmes and with hindsight it would have been better to make this adjustment earlier. However, greater value from MREL is expected once more programmes start implementation and begin to collect and report on results, and once more evaluations are conducted are used.
Financial expenditure – to end of 2019/20
	17/18 Inception	18/19 Implementation	19/20 Implementation	Total to end of 19/20
Contract	Actual Spend (£m)	Actual Spend (£m)	Current Forecast (£m)	Current Forecast (£m)
Monitoring and Reporting	2.91	2.87	2.25	8.03
Evaluation and Learning	0.90	4.32	5.05	10.27
Total	3.81	7.19	7.30	18.30

Recommendations:
The JFU MREL team should carefully prioritise and set clear scope to maintain optimal efficiency of the learning resource (platform and EL supplier’s learning team). Consideration should be given as to how to align with JFUs capability strategy to be complimentary.

E: RISK
Risk register in place: Yes	Date of last review/update Nov 2019

Overall risk rating: Major
Rationale
The Prosperity Fund is large and complex. The portfolio covers a wide range of sectors and types of interventions. This combined with the more recent experience of some departments in delivering ODA programming has created a systemic capacity and capability challenge on a range of specialist skills – including MREL.
Ongoing programme delays continue to create issues for a centrally co-ordinated portfolio MREL system. There is still a lack of clarity over programme design, ToC, and log frames. This compromises the foundation on which programmes and the wider fund can use MREL to achieve better programming and impact. Slower than anticipated progress into implementation and longer delivery periods hinders the ability of MREL to demonstrate results and evaluate which programmes are working and why within the lifetime of the Fund.
Overview of programme risk
The three top risks areas for PF MREL are;
Capability and capacity within the PF network programme teams – As discussed in detail in Section C, some programme teams do not have sufficient programming expertise (including background knowledge on the concepts and purposes of logframe and theories of change) and relevant sector specialists to do develop clear theories of change and logframes for their programmes. This poses significant risk to the MREL system’s ability to provide evidence for effective adaptive programme management.
Programme Delays - Programmes have not progressed as quickly as expected on the PF. This has created significant challenges for a large central MREL service that was procured according to set of delivery timeline assumptions that are no longer valid. Pivoting services and delaying activity has partially mitigated. However, pace of delivery remains slow. The fund level MREL framework is dependent on implementing programmes to be able to provide evidence against the overall fund level ToC.
Budgetary pressure. MREL has a ring-fenced budget of 5% of the overall Fund. However this amount was originally intended for a five year period from 2016-2021. With a provisional no-cost extension of the Fund until 2023 this budget now has to be spread more thinly over a longer period. In addition the total value of the fund has reduced due to under-spend by some programme teams in initial years (the under-spend is not carried forward to future years). Hence the MREL budget may be challenged and face downward pressure.
F: WORKING IN PARTNERSHIPS / COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe.
The portfolio MREL service compromises of two central contracts. A £13m Monitoring and Reporting contract with PA consulting and a £24m Evaluation and Learning contract with a consortia of WYG, Integrity, and LTSI.
The two MR and EL contracts were awarded at the start of Sep 17 ready for a 6-month inception period. Implementation started from April 18 onwards. This was according to timetable. The planned implementation activity was dependent on programmes to progress according to delivery assumptions. This has not happened and JFU has had to work with delivery partners to adapt, pivot, and postpone planned activity to better meet the current needs of the portfolio. This re-scoping of activities has been reasonably successful but there have been some limitations as this was not the original purpose of the contracts.
Some underlying assumptions about anticipated timelines for the fund within the MREL inception design are unlikely to be still valid. Timeframes for fund level MR and EL objectives may need to be revised and expectations around results/evidence managed.
Performance of partnership(s)
JFU and the wider Funds relations with the delivery partners has been constructive and productive. Feedback from the review was largely positive about the behaviours and responsiveness of the suppliers to be flexible and support needs. The suppliers have sought feedback from a range of stakeholders through both regular and ad-hoc feedback mechanisms and have attempted to continuously improve their offer. However, as referenced earlier with this report, there has been some confusion over roles and responsibilities and how the suppliers will interact and complement each other that has hindered the delivery of ‘one’ MREL service.
The E&L offer in particular is complex with multiple dependent work strands and a large globally dispersed team (circa 70 individuals). JFU have previously formally expressed concerns about the capability of the supplier to centrally co-ordinate all this activity and to produce robust costed work plans. There has been improvement since but the JFU team should continue to closely monitor performance in this area.
The MREL service, including our suppliers, has been externally independently assessed by a number of reviews during the circa 2 year period in scope of this annual review. These are;
- EQUALS and Technical Advisory Group review of Inception documents. Apr 18 Score: Good
- IPA Gateway 4 review – Jan 18. Set up for success. Score: Amber / Green
- EQUALS assessment of evaluation products. Ongoing. 79% of products submitted scored good or above. (34 out of 43).
Changes in the Delivery Plan
There have been changes to the delivery plan. These are mainly due to delays in programmes progressing to implementation. The two main contractual changes have already been referenced earlier within this report,
- MR pivot towards providing substantially more technical assistance on logframes and theories of change.
- Re-scope of E&L activity to delay or simplify evaluations to reflect maturity of the fund portfolio.

WYG the E&L lead supplier was recently acquired by Tetratech Ltd. Tetratech also own Coffey – a supplier on the PF framework. WYG and Coffey are due to be merged in early 2020. This will have potential conflict of interest (CoI) implications around the independence of our E&L supplier. A robust review is planned for April 2020 to assess this risk and to ensure that WYG have adequate CoI procedures in place to manage HMGs exposure.

G: MONITORING & EVALUATION
This is the first Annual Review of the MREL programme. These should be done annually from now.
The suppliers report against KPIs but a logframe for the MREL programme should be made (see recommendation included in section B). However, the logframe should not be viewed as a comprehensive tool to assess progress. Additionally, it should be reviewed and adapted as needed. This is because by their nature logframes measure indicators that be specified in advance and measured (which may not be the most important), and are not good at assessing progress when programmes are adaptable and flexible. Many of the assumptions that the PF MREL system was built on (e.g. the capability of programme teams and the timing of programme implementation) have not held true. Favourably, the MREL programme has adapted in response to this. Further unexpected changes may indeed emerge.

H: CROSS CUTTING THEMATIC CONSIDERATIONS
Gender and inclusion (G & I)
Good practice on G & I in PF programmes is essential to meeting the primary purpose of the PF, to increase inclusive growth in partner countries. The business case states that, “in line with Gender Equality Act compliance, good practice development and smart economics, [the MR and EL contracts] will meaningfully consider how programming has contributed to reducing gender equality and support women’s economic empowerment.” This is important, especially given we need to ensure that programmes are compliant with the Gender Equality Act, but the PF’s G&I policy is broader than this, and covers other marginalised groups in addition to women, and following best practice, requires programmes to integrate a G&I perspective throughout the programme cycle. The EL supplier should be required to assess whether the programmes working in line with the broader PF G&I policy.
The MR and EL work on G&I covers three areas:
1. Assessment of alignment with PF G&I policy at the programme level as part of programme evaluations
2. Assessment of alignment with PF G&I policy at the Fund level as part of G&I thematic evaluation
3. MR Operations team technical assistance to programme teams on their logframes. Programmes should be including G&I relevant indicators and including appropriate data disaggregation (e.g. by age, gender, disability status) where possible. Given the demand led nature of this support, this does not provide a means of ensuring that programmes are aligned but rather supports programmes in how to include appropriate indicators and disaggregation where they request this support.

The MREL business case included a list of practices that the programmes should be following on G & I, and hence what the EL supplier should be checking that programmes are doing. This list has subsequently been updated as part of the creation of a G&I scorecard – which contains a list of criteria that programmes are scored against as part of the G&I stocktake (which is part of the G&I thematic evaluation). We have received feedback from JFU and FCO SDAs that this may require further updating, especially to ensure that the E&L supplier checks that programmes are analysing the likely “winners and losers” of programmes aimed at making economy wide reforms (e.g. trade reforms).
Recommendations:
E&L supplier to update the G&I scorecard, in consultation with JFU, and the G&I ref group