Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Global Infrastructure Programme
Programme Value: £25m		Review Date: 12 June 2019
Programme Code: GB-GOV-50-PF-14-INFRA (including GB-GOV-3-PF-INF-912; GB-GOV-3-PF-INF-922; GB-GOV-3-PF-INF-921; GB-GOV-3-PF-INF-913; GB-GOV-3-PF-INF-923; GB-GOV-3-PF-INF-911)	Start Date: SOBC approval – 4 October 2017	End Date: 31 March 2021

Summary of Programme Performance
Year	2019
Programme Score	A
Risk Rating	Moderate

Summary of progress and lessons learnt since last interim review
This is the first full Annual Review for the Global Infrastructure Programme (GIP), following a light-touch review covering transition funding in July 2018. Overall, the GIP has made good progress in the two years since it was launched, delivering a number of key outputs and establishing a firm foundation for the delivery of its overall objectives and primary and secondary benefits. Particular achievements include the strong relationships the GIP has built with key organisations in partner countries, and the delivery of capacity building initiatives in these, as well as in adapting UK methodologies for use in partner countries. The Programme has also worked with overseas stakeholders to identify the pilot projects that are the key to the successful delivery of Phase 3, to embed the UK methodologies in organisations in partner countries. The engagement of private sector suppliers (PwC and Mott MacDonald) has also provided greater delivery capacity and essential technical expertise.
The main risk to the GIP is that implementation of the pilot projects will be delayed or take longer than anticipated. The timetable for delivery is relatively short (2 years). This is also influenced by factors outside the control of the Programme Team, in particular the decision-making processes within institutions in partner countries. Mitigating this risk, and ensuring the programme remains flexible and agile enough to respond to new opportunities through an adaptive management approach, will be essential if it is to succeed. Other priorities for the programme will be to maintain a focus on the delivery of the primary and secondary benefits as projects are implemented in Phase 3. It will also be important to increase the level of private and third sector engagement in the UK and partner countries as the project moves into Phase 3. The Programme should also ensure gender and inclusion considerations are factored into programme design and delivery, addressing the recommendations of the G&I scorecard review. Finally, the annual review recommends the use of cost benchmarking to strengthen VfM processes around economy and efficiency and further improvements to its MREL framework to build on work to date.
List of recommendations for the next year
Programme Delivery
- Development of BIM Standards: It should be a priority to focus on the development of BIM standards aligned with UK and international best practice in partner countries during 2019, through using the additional capacity and technical expertise provided by Mott MacDonald as a means of driving this.
- Gender & Inclusion: Delivering the primary benefits will require the programme to ensure the documentation, training and support delivered during the pilot projects in partner countries fully embeds the principles of sustainability, inclusivity and equality. Whilst the focus on gender equality and female empowerment in the programme is strong, it will also be important to ensure there is a similar focus on other key areas including disability, age, community engagement and child safeguarding, and that these are embedded in all relevant aspects of the programme.

Value for Money and Financial Performance
- VFM (Economy): FCO GIP (contract manager) to implement cost benchmarking for the programme’s remaining activities where possible, to support assessment of the programme’s VfM in purchasing inputs.
- VFM (Effectiveness): Building on contacts already made, the Programme Team, IPA, CDBB and suppliers to review examples of past infrastructure or other major programmes, or development interventions across HMG (including those supported by the Prosperity Fund, DFID and other Departments) to embed new methodologies in planning processes (either in the UK or overseas) to identify any successful strategies for ensuring tools continue to be used post the programme.
- VFM (Equity) - G&I (Scorecard Recommendations): implement recommendations of G&I Scorecard assessment.
- VFM (Equity) - G&I (AR Recommendation): progress on G&I to be added as an agenda item at Operational Committees and Programme Board. This should be used to explain programme component design with respect to G&I, including: how G&I impacts is reflected in pathfinder project selection criteria; how GIP approach to Phase 2 training and capacity building in country will be inclusive; and what steps will be taken to embed G&I considerations in country institutions/planning processes via the tools.
- Financial Management: The GIP team should ensure that budget allocations for FY 2019/20 (and remaining programme years) for each of the programme line items (e.g. phases 1, 2 and 3 by delivery partner) are forecast as accurately as possible so that the source of any under or overspend at the aggregate level is easy to identify over the course of the year.
- Financial Management: The FCO GIP team should conduct regular checks of a sample of delivery partner invoices each year against individual receipts to assure fiduciary risk. IPA and CDBB should action the same for their respective suppliers (PWC and Mott Macdonald).

Risk
- Delivery Timetable: the Programme Team should undertake a strategic review of opportunities to extend and increase the scale of the programme, to enable it to achieve maximum impact in delivering the primary and secondary benefits, and to establish UK methodologies both in partner countries and more widely as internationally recognised best practice. (Summer 2019).
- Delivery Resources: the Programme Team should undertake a review of the personnel needed to deliver the programme within FCO, delivery partners and suppliers, assess whether these are sufficient, and if not recruit additional staff soon as possible to help manage and deliver the programme in an efficient manner.

Commercial Considerations
- Supplier Management: the Programme Team has experienced difficulties recruiting a contract manager; they should take forward the appointment process for a contract manager, using external resource if necessary, to oversee the contracts with the key suppliers to the programme, Mott MacDonald and PwC.
- Contractor Support: the Programme Team should evaluate the need for, and likely type of additional contractor support for the programme, in order to enable the Programme Board to take a decision as to whether to seek to procure this and start the procurement process as soon as possible.

Business Environment
- Stakeholder Engagement Strategy: Whilst the GIP has been successful in engaging public bodies in partner countries, further work is required in Phase 3 of the programme to develop a wider stakeholder engagement strategy in Tier 1 and 2 countries, encompassing the private sector (both clients and service providers), academia and media stakeholders. The GIP should also review whether there would be benefits to linking these stakeholders with similar groups in the UK, including the Knowledge Transfer Network and academic networks supported by the Transforming Construction Programme.
- Business Engagement: As part of its wider stakeholder engagement strategy, the Programme Team should work with the IPA, BEIS and DIT to identify UK firms that possess the capability to support the delivery of infrastructure projects in the partner countries, and when opportunities begin to emerge, to raise their awareness of the GIP and the potential opportunities this could generate.

Monitoring and Evaluation
- Theory of Change/Logframe: review of the Theory of Change/Logframe should be undertaken by the GIP Team and MREL partners to consider and address the points on Consolidation and Milestones (end September 2019)
- Output Indicators: Ensure all output indicators have associated milestones and implement reporting against these. This should include disaggregation by groups where appropriate e.g. reporting proportion of participants in training and capacity building activities by gender, disability status etc. (end July 2019)
- Strengthening MREL: Produce a review of the additional data requirements and methodologies needed to measure the Logframe’s intermediate outcomes, outcomes and impacts with the aim of implementing baseline data collection before the Programme’s activities are likely to effect change within country planning processes (end September 2019).

SRO Commentary
I welcome the conclusions and recommendations of this review, which reflects the positive progress made by the Global Infrastructure Programme over the last two years. The overall ‘A’ assessment reflects that the programme has delivered effectively over the past year and has outperformed expectations in some areas. The review highlights the excellent work carried out by our HMG partners the Infrastructure and Projects Authority and the Centre for Digital Built Britain; their expertise is invaluable.
This review provides a clear and coherent set of recommendations to improve, which I accept in full. We have identified key areas where the programme can do even better which will help drive continuous improvement and learning. The programme team will develop an action plan to ensure that these recommendations are acted on.
The next two years will be critical in realising the potential of the Global Infrastructure Programme to deliver its expected impact and value for money. This annual review demonstrates that the programme is well-placed to succeed. My thanks to all those involved for their hard work to date.
Sarah Cowley
SRO Global Infrastructure Programme
12 June 2019
JFU Note
“We welcome the conclusions of this review. It evidences the timely mobilisation of the Global Infrastructure programme and effective delivery over the past year. This reflects strength of programme management and technical expertise behind the programme. We note with appreciation the strength of partnerships cultivated with host governments and look forward to seeing these deepen as the programme progresses. We note the programme is entering an ambitious third phase and the review’s recommendation of maintaining close focus on delivery. We echo this and the need to ensure pilot projects are inclusive, eg through ensuring a strong focus on gender. As the programme progresses it should continue to consider opportunities for collaboration with other PF programmes working on improvements in the investment environment and ease of doing business to deepen mutual synergies. We look forward to hearing how the programme progresses in these and other areas and better drawing out learning from it over the next annual review”
Daniel Davis
Head of JFU
14 November 2019
List of Acronyms
5CM – 5 Case Model (Methodology)
BC – Business Case
BE Bogota – British Embassy, Bogota, Colombia
BE Jakarta – British Embassy, Jakarta, Indonesia
BE Hanoi – British Embassy, Hanoi, Vietnam
BEIS – Department for Business, Energy & Industrial Strategy
BIM – Building Information Modelling (Methodology)
CAF – Latin America Development Bank
CDBB – Centre for Digital Built Britain (BEIS delivery partner)
DFID – Department for International Development
DIT – Department for International Trade
FCO - Foreign and Commonwealth Office
G&I – Gender and Inclusion
IIOC – Investment, Infrastructure and Operations Committee
IPA – Infrastructure and Projects Authority
IUK – Innovate UK
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
L&D- Learning and Development
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
ODA – Official Development Assistance
PF – Prosperity Fund
PFDU – Prosperity Fund Delivery Unit
PIR – Project Initiation Routemap (Methodology)
PPP – Public Private Partnership
SRO – Senior Responsible Officer
ToC – Theory of Change
ToRs – Terms of Reference
VfM – Value for Money
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/global-infrastructure-programme
DevTracker Link to Log frame:	Not yet published

Prosperity Fund

The cross-Government Prosperity Fund was created in 2015 to promote economic growth in developing countries, and thereby increasing prosperity and reducing poverty, whilst also creating opportunities for international businesses, including UK companies. The Fund has a budget of £1.2 billion over the 5 years (2016-21) to provide technical assistance to partner countries to improve the business climate, reduce barriers to trade, investment and economic growth and support necessary reforms.

Global Infrastructure Programme

The Global Infrastructure Programme is a £25 million Prosperity Fund programme that aims to develop the capacity of partner middle income countries to bridge the current ‘infrastructure gap’, through training and embedding of proven UK methodologies in project planning, preparation and delivery. Thereby unlocking economic opportunities, increasing prosperity and reducing poverty, whilst also enhancing opportunities for international and UK business.

Following submission of a successful concept note, the Prosperity Fund Whitehall Ministerial Board approved the development of the business case on 25 October, 2016. The Programme received interim funding of £640,000 on 7 July 2017 to enable it to commence activities whilst developing a detailed programme of work. The Strategic Outline Business Case was approved by the FCO’s IIOC on 4 October 2017 and Outline Business Case approval by IIOC followed on 1 November 2017, with Ministerial approval received on 29 January 2018. The Letter of Delegation from the Cabinet Office authorising full funding of the programme was received on 12 April 2018. The Full Business Case was approved by IIOC on 12 December 2018, and an updated FBC was approved by the SRO on 11 March 2019.

A light-touch annual review for transition funding activities was published on 27 July 2018, when the programme received an overall score of ‘A’ with a programme delivery risk of Moderate.

Governance and Delivery Mechanisms

The GIP is managed by an internal team within the FCO, which works closely with the two main delivery partners, the Infrastructure and Projects Authority (IPA) and the Department for Business, Energy & Industrial Strategy (BEIS) which delivers through its partner, the Centre for Digital Built Britain (CDBB). The SRO is accountable to the PUS FCO as Accounting Officer for the financial management of the programme budget, and for the delivery of the programme to the Prosperity Fund SRO, the Joint Funds Unit and Ministerial Board for the Prosperity Fund. The key elements of the governance and delivery structure are:

- A Programme Board, chaired by the SRO, with representatives of the IPA, BEIS and BEIS (for CDBB), and DIT. DFID also attend as observers. This is responsible for strategic oversight of the programme, and ensuring that it is achieving milestones, as well as risk management. The Programme Board meets on a quarterly basis.
- An Operations Committee, which includes FCO, IPA and CDBB staff involved in the delivery of the programme. This is responsible for financial and operational management, including risks linked to this, and for co-ordinating activities across the programme. The Operations Committee meets on a fortnightly basis.
- The IPA is responsible for delivery of the internationalisation of the UK methodology for evaluating and delivering infrastructure projects, and for supporting capacity building activities in partner countries. This work is now being supported by PwC.
- The CDBB is responsible for delivering work in relation to Building Information Modelling technologies and capacity building in developing countries. This work is now being supported by Mott MacDonald.

Outside the formal governance mechanisms, there is regular contact between the team in FCO, the delivery partners and staff in posts; the latter are also able to participate in Programme Board and Operations Committee meetings remotely. The IPA and CDBB teams have been involved in the delivery of activities in-country, and there is a strong network across the programme that facilitates effective joint working.

Rationale for intervention and Expected Impact

Infrastructure is vital for any country’s economic growth and development. Infrastructure is the basic physical and organisational structures and facilities needed for the operation of a society: economic infrastructure networks such as transport, energy, water and telecoms provide the basis for businesses to grow and be productive, whilst social infrastructure investment in schools, hospitals and housing supports quality of life. Yet, despite the critical importance of infrastructure, a significant global investment shortfall or ‘infrastructure gap’ has been widely acknowledged in recent years. McKinsey assess this at $350 billion per year worldwide or $5.2 trillion over the next 14 years.[1] Today, as well as the need for finance, there is also a critical lack of properly developed projects that governments and financiers can invest in with confidence.[2]
[1] McKinsey Bridging Global Infrastructure Gaps – 2016
[2] Financing Change: How to mobilize private-sector financing for sustainable infrastructure, McKinsey, 2016)

The GIP can help address that problem through the adaptation of UK best practice methodologies in infrastructure project planning, preparation and delivery. The methodologies put forward, tried and tested in the UK, will be adapted for international use and promulgated internationally with the help of the private sector. In turn, this will increase the number of good infrastructure projects coming to market as investable propositions, helping to bridge the gap. This will assist developing countries to install the economic and social infrastructure they need to sustain inclusive economic growth, with particular benefits for the poorest in society, and attract investors and lenders to deliver critical projects and programmes (see Strategic Case for more detail).

The programme will deliver exemplar projects in four key pathfinder (Prosperity Fund priority) countries in the Latin America, ASEAN and African regions, also encompassing regions covered by China’s Belt and Road Initiative, whilst supporting a wider set of countries in these areas over time. Partner countries are selected on the basis of their ability to deliver inclusive growth and economic opportunities (including for the UK), their fit with the Prosperity Fund Theory of Change and Prosperity Fund priorities, and their ability to act as ‘beacons’ to demonstrate the benefits of the new methodologies.

The tier 1 pathfinder countries (covered in phases 2/3) are as follows:

- IPA: Indonesia, Colombia and South Africa (added in 2018); and
- CDBB: Indonesia, Colombia and Vietnam.

All these countries, following preparatory development work and intensive preliminary visits by the prospective team to the relevant public authorities involved, have expressed their interest in joining the programme. Exemplar projects in these target countries will act as a springboard to achieve wider regional change.

The tier 2 countries (covered in phase 2) are as follows:

- IPA: Vietnam, Peru, Mexico and Brazil; and
- CDBB: Peru, Mexico, Brazil and South Africa (under consideration).

Each will receive training and support from the programme on the three UK methodologies.

Cross-Government Programme with Multilateral and Private Sector Stakeholder Support

The multi-year funding offered by the Prosperity Fund offers a unique opportunity to address this problem strategically, through leveraging the collective expertise and resources of Government Departments through a co-ordinated multi-annual programme. The programme is a cross-Government initiative delivered by FCO, the Infrastructure and Projects Authority (IPA) and BEIS (via their BIM delivery partner the Centre for Digital Built Britain) in collaboration with DIT and DFID, drawing on the:

- global reach and local connections of the FCO overseas network;
- project management and fund management skills of the central FCO;
- infrastructure expertise and policy understanding of the IPA;
- digital construction and Building Information Modelling skills of BEIS (via CDBB);
- experience and expertise of DFID, in particular consulting on effective approaches to TA and engaging with their learning programme; and
- commercial knowledge and reach of DIT to exploit secondary benefit opportunities.

Additionality

The Programme will be complimentary to development assistance from Multilateral Institutions, and has broad support from the private sector. The World Bank view the proposed methodologies as filling a gap in the current support for development, and are supporting our methodologies with a view to placing them on their knowledge portal for use around the world. The Inter-American Development Bank (IADB) and UN Office for Project Services (UNOPS) are also supportive. There is further support in the private sector in the UK and partner countries, which recognise the potential of the Programme to facilitate infrastructure investment and the improved delivery of infrastructure projects.

Methodology, Roll out, Sustainability

At the heart of this Programme is the adaptation and dissemination of world-leading UK methodologies for international use and their adoption as a matter of policy by the partner countries for their infrastructure projects in order to produce sustainable and lasting change. The programme will deliver via the following activities:

- Support to partner countries for infrastructure planning, business case development including rolling out internationally-adapted models for pathfinder countries, based on the UK’s 5 Case Model and Project Initiation Routemap, and funding direct technical support for these pathfinder countries (in conjunction with private sector consultants); and
- Promoting the UK’s Building Information Modelling (BIM) methods and standards that optimise the design, build and operation of key infrastructure, by funding development of local models and training.

Benefits

The programme’s appraisal case estimated that it would deliver an estimated £1.18bn in primary benefits (aggregate uplift in programme country GDP) over the first 10 years. In addition, it estimated the programme would deliver £452m in UK exports (both through UK consultancy wins and increased exports in goods) over 10 years. The above figures are based on the impact in just the three pathfinder countries over a relatively short period - the actual overall impact could potentially be higher, since this programme is designed to produce permanent change and to have far-reaching, potentially global impact.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
Primary Purpose: the Programme is currently delivering effectively against its 9 key outputs, evidenced in the Logframe (see below). The Theory of Change shows how these outputs will flow forward into outcomes and impact, and achievement of its targets for poverty reduction, inclusive growth, gender equality and women’s economic empowerment. The GIP has worked closely with the Gender & Inclusion advisers from JFU and PFD; work to be done to ensure that G&I is properly embedded in the Programme’s approach and delivery
Finances: Key early steps were achieved during 2017/18 using the transition funding. Subsequently the GIP has been able to deliver broadly in line with plans through the first full delivery year (2018/19), but at lower than forecast cost, providing evidence the Programme is achieving VFM. Therefore, some budgeted funding was available to be repurposed to additional activities to support the programme in Colombia and Peru. A portion of the budget was also returned to JFU via the supplementary estimates process in November 2018. Towards the end of the year, the Programme has been able to accelerate activity (and spend) in order to compensate for challenges elsewhere in the FCO Prosperity Fund portfolio, ending with an accurately forecasted spend of 108% of adjusted budget.
Annual outcome assessment (Secondary Purpose)
A robust and credible secondary benefits plan is in place, produced in close cooperation with DIT. There has also been in-country engagement with business stakeholders, including Chambers of Commerce. A lower level of work has been undertaken in the UK, but this is because specific opportunities to bid for work in relation to projects have not yet emerged. This will be more important in Phase 3, as these opportunities are created. Further work is planned to update the plan as the route to the benefits becomes clearer with the identification and delivery of the pathfinder projects, including working with DIT infrastructure advisers funded through non-ODA budgets.

Overall output score and description
Each of the nine outputs is examined in the main body of the report. There are good overall indicators of success in a number of areas, with other areas still work in progress. Overall, the project is on track to deliver the outputs and outcomes expected by 2021.
Key lessons
The Programme has already benefitted from the flexibility of adopting an adaptive management approach towards projects and activities. This has enabled it to provide support to a project in Peru, and to reallocate resources between activities; and also to deliver a higher than planned level of activity and spending in the last financial year when requested to do so. As the Programme moves into Phase 3, it will be essential to continue this approach, and to undertake regular reviews of the portfolio of projects and activities in partner countries, and to be willing to reallocate resources between these, to support those likely to deliver the greatest impact, and to respond to opportunities that can emerge at short notice.

The importance of sufficient resources, primarily sufficient personnel, to deliver the Programme, particularly in posts, has been raised in relation to the projects and other activities in a number of partner countries. This is particularly the case where this responsibility sits within a wider portfolio of responsibilities in relation to Prosperity Fund, or other areas. To date, it has been possible to deploy resources relatively easily to support activities, but this is likely to become more difficult as the Programme moves into Phase 3 and pilot projects are launched. The level of resources dedicated to these pilot projects across posts, delivery partners and the contracted suppliers will need to be kept under ongoing review to ensure there are sufficient people to support the pilots.

There are also wider lessons for the management of the Prosperity Fund within the FCO that can be drawn from the GIP. Firstly, it is important to ensure that key roles within Prosperity Fund supported programmes both in London and in overseas posts are filled promptly, in order to build delivery capability and increase the resilience of teams. Secondly, it is importance to ensure there is sufficient capacity within the FCO GIP team and Commercial Function to support procurements of key suppliers, so these processes can be concluded as quickly as possible and not delay the delivery of projects and other activities.

Key actions
See list of recommendations.
Summary of changes to the Logframe since the last annual review
At the light-touch annual report done in July 2018, the Logframe was not reviewed. However, the Theory of Change and Logframe have been updated in 2019; in particular, the Logframe has further detail on Output milestones, related indicators, and progress against those indicators. There have also been updates to ensure a more comprehensive reflection of Gender & Inclusion aspects in the Logframe.
The process will be ongoing with further updates planned for the Theory of Change and Logframe in the light of experience gained in delivering the programme, including updating planned milestone delivery against indicators for future years.
Transition Funding Report: June 2018
The transition funding achieved its goal of building early momentum for programme delivery. It also succeeded in gaining significant preliminary interest and buy-in from key local stakeholders in planned partner countries. The work undertaken strengthened the business case assessment that the proposed Phase 3 countries were strong candidates to be the programme’s pathfinder countries, and saw agreements signed with each pathfinder country that set the framework for future collaboration. In particular, the reception and enthusiasm for the BIM and 5 Case Model offer exceeded expectations. Finally, good progress was made on the Phase 1 activity of preparing and finalising international versions of UK infrastructure design and development methodologies, preparatory to Phase 2 training activities.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Built and maintained relationships, mutual trust and commitment for long-term collaboration between the UK and the partner country
Output number per LF		1	Output Score	A+
Risk:		Major	Impact weighting (%):	15
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones by June 2019	Progress
Number of countries demonstrating evidence of willingness to partner with the UK over the long-term (e.g. signing of an MOU, or other form of senior sponsorship e.g. EFD - Economic & Financial Dialogue or Infrastructure Task Force Agreement)	3 MOU signings by June 2019 / 3 Inward delegations by June 19	MOUs signed: Vietnam - July 2018 Colombia - June 2018 Indonesia - July 2018 Hosted delegations: - Vietnam on 4th April 2019 - Latin America delegation (6 countries including x1 Tier 1, x2 Tier 2) Feb 2019 - DIT FCO Americas Network training Feb 2019 - Mexican delegation Feb '19 EFD/Infrastructure Taskforce - UK/Brazil Infrastructure and Capital Markets taskforce meeting (Date - tbc) - UK-Peru Infrastructure Taskforce meeting Feb '19
'Number of organisations with senior sponsor assigned	3 by June 19	IPA - Tier 1 - Indonesia, Bappenas Deputy Minister/Director - Colombia, FDN Vice President of Project Structuring IPA - Tier 2 - Mexico, MoF, Head of Investment Unit - Brazil, MoF, Head of Secretariat for Infrastructure Development CDBB - 6 (Indonesia, Colombia, Vietnam, Mexico, Brazil, Peru)
Number of workshops, public events held and country visits hosted by the country sponsor with relevant stakeholders (public sector) - e.g. workshops, and roundtable meetings	18: Minimum 2 meetings per Tier 1 country + 1 meeting per Tier 2 country, for IPA and CDBB	IPA: 11 National Strategy workshops, supplier events and MOU signing events all held in - Colombia - Indonesia Total = 6 events 5 Programme Introduction events: Tier 1 - Colombia - Indonesia - South Africa Tier 2 - Mexico - Brazil CDBB: 19 - Vietnam (5) Indonesia (2) Colombia (5), Brazil (2) Mexico (3) Peru (2)
'Stakeholder map and ownership grid populated jointly between UK and partner government team	2 CDBB stakeholder maps in progress	CDBB: Indonesia and Colombia (1 each)
'Number of country sponsors reporting good relationships through feedback mechanisms	NA	Not tracked this period – too early to reflect

Output Title	Country commitment to a national infrastructure transformation policy
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	10
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
'Number of public statements to implement a national BIM policy in the partner country, e.g. referencing "target BIM by year xxxx"	3	Vietnam (1) Indonesia (0) Colombia (0) / Mexico (1) / Brazil (1) / Peru (0):
'Number of plans developed to outline the high-level policy and programme level objectives (why BIM)	2	Vietnam (1) Indonesia (0) Colombia (0) / Mexico (1) / Brazil (0) / Peru (0)

Output Title	5 Case Business Case Model and PIR guidance & exams adapted for international use, incorporating concepts of inclusion and sustainability.
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
'5 Case Model & PIR locally & internationally adapted guidance, including concepts of inclusion and sustainable development.	Final draft 5CM and PIR Core phase 1 material completed and certified by international standards body (Better Business Case Standards Board)	Internal adaptation of materials 5CM and PIR Core phase 1 material completed, reviewed and certified by international standards body Indonesia - Pilot PIR exercise implemented, to develop learnings for adaptation Colombia - planning underway to implement Pilot PIR exercise, to develop learnings for adaptation Appointed delivery partner for peer reviewing international version of 5CM and PIR guidance and produce locally adapted versions for Colombia and Indonesia
'5 Case Model & PIR locally & internationally adapted foundation and practitioner training plan, exam & certification	Plain English version of material developed (PIR handbook) Development of exam based on new core training material Development of web-based training material	Internal adaptation of case study for 5CM and PIR Core phase 1 material completed, reviewed and certified by international standards body Indonesia - Pilot PIR exercise implemented, to develop learnings for level of socialisation and training required Colombia - planning underway to implement Pilot PIR exercise, to develop learnings for level of socialisation and training required Appointed delivery partner for peer reviewing international 5CM and PIR training materials, produce locally adapted versions for Colombia and Indonesia and consider development of web-based training.

Output Title	Plans developed for national BIM programme and framework development (aligned with UK/International)
Output number per LF		4	Output Score	B
Risk:		Major	Impact weighting (%):	10
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
'BIM national strategy and Implementation plans developed, aligned with principles of UK/International practice	3	Vietnam, Mexico and Brazil each have a BIM strategy
'Number of countries with a BIM legal and technical framework which has sufficient resource assigned and proposed to adapt from UK/International practice	3	Vietnam have BIM Steering Committee and Technical Group in place

Output Title	Capacity built of partner government central policy officials for implementing the UK programme methodologies
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
Number of male and female partner Government officials who have completed UK BIM policy training/workshops	CDBB (phase 2 training and adaptation) 1 training visit (Vietnam), 2 engagement visits (Colombia, Indonesia) (Follow up phase 2) 4 training visits (Mexico, Vietnam, Colombia, Brazil)	131: CDBB training visits to Vietnam (Sep18= 10, Mar19=7 Apr19=10), Colombia (Oct18=10 Mar19=10), Indonesia (Mar19=35), Brazil (Mar19=25), Mexico (Apr19 =20 ), Peru (Feb19 = 4) / Male/female split not yet available
'Number of male and female partner Government officials who have completed 5CM training and exams, delivered in Tier 1 & Tier 2 countries	IPA (Phase 2 Training and adaptation) 4 engagement and development visits (Indonesia, SA, Vietnam, Colombia)	Introductory training workshops Tier 1 - Colombia (JE/HN) - Indonesia (JE/HN), March 19 Tier 2 - Mexico - Latin America delegation - DIT FCO Americas Network
'Number of male and female partner Government officials who have completed PIR training, delivered in Tier 1 & Tier 2 countries	IPA (Phase 2 Training and adaptation) 4 engagement and development visits (Indonesia, SA, Vietnam, Colombia)	Introductory training workshops Tier 1 - Colombia (JE/HN) - Indonesia - Bappenas staff shadowed PIR Pilot process, for training on the PIR Tier 2 - Mexico - Latin America delegation - DIT FCO Americas Network

Output Title	Capacity increased across national public clients and demand grows for a national BIM standard approach
Output number per LF		6	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
'Number of pilot projects (social /economic infrastructure) identified across national public clients to implement elements of the UK methodologies	Number of BIM Country landscape reviews 3 consultant procurement processes successfully completed for BIM Phase 3 roll out One PIR pilot project identified in Indonesia	Vietnam currently have 3 pilot projects underway, Ministry of Health, Ministry of Agriculture and Ministry of Transport, using BIM guidelines which refer to PAS 1192 Indonesia: BAPPENAS pilot PIR project identified & implemented.
'Number of Industry events (e.g. conferences/training) held	Not defined	2 held in Colombia (see indicator 1C) 1 in Brazil in March 2019
'Number of publicity materials produced e.g. websites, press articles referencing BIM	Not defined	Tbc - to be collated via in country contacts
'Number of national / sub-national Public clients trained on BIM in procurement and projects (e.g. the lead champions for implementing BIM in projects)	Develop framework for phase 2 training and adaptation material Vietnam Mar18-Jan 19 Indonesia Jun18-Apr19 Colombia Aug18-Jun19 Adaptation of materials	Vietnam public clients identified

Output Title	Capacity built at scale across national public infrastructure clients, industry suppliers, donor organisations and academia.
Output number per LF		7	Output Score	A
Risk:		Major	Impact weighting (%):	15
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
'Number of countries with a BIM programme rollout plan produced by the partner government team	National strategy workshop for national BIM programme	Brazil Mexico Peru (Feb to Mar 19)
'Number of 5CM & PIR Pathfinder projects that have commenced	NA	NA
'% of infrastructure projects pipeline with BIM requirements (aligned with UK/International) by the "BIM target year"	Not reported this period	NA
'Number of university courses and training courses teaching BIM concepts and techniques	Not reported this period	NA
'Number of donor organisations demonstrating evidence of endorsement of UK methodologies	Endorsement of 5 case Model principles by one international/donor org	Endorsement by G20 01/07/2018 G20 Global Infrastructure Hub endorsement of 5CM and PIR

Output Title	National BIM legal & technical standards (aligned with UK/international practice) are developed
Output number per LF		8	Output Score	A
Risk:		Major	Impact weighting (%):	10
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
'Industry consultation on development of national standards and legal (procurement /contractual) definitions for BIM (e.g. meetings held with standards groups/industry/academia)	None planned	NA
'Legal and technical framework publicly available, e.g. media coverage, standards documents online	Not reported this period	NA
'Number of countries that have national standards and legal definitions for BIM, that aligns to international/UK practice	Training and standards localisation periodic review P2 delivery partner Vietnam 02/19 - 12/19 Indonesia 05/19-03/20 Colombia 07/19-05/20	Not reported this period

Output Title	An engaged and active participation in the national digital transformation change by industry suppliers, clients, academia and media
Output number per LF		9	Output Score	Not scored
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		NA – first AR	Impact weighting % revised since last AR?	NA –first AR

Indicator(s)	Milestones	Progress
'Number of conferences and workshops held by industry (including associations - e.g. Chamber of Construction)	To be defined	Not yet recorded – too early to quantify
'Number of media articles referring to BIM	To be defined	Not yet recorded – too early to quantify
'Number & membership of 'communities of practice' for BIM that are established	To be defined	Not yet recorded – too early to quantify

Output Summary
Key Points
Overall, good progress has been made across the majority of the 9 outputs, and the GIP is on track to deliver the planned outputs and outcomes by 2021. However, there is a moderate risk of delay to the realisation of the envisaged primary and secondary benefits within the anticipated period, due to the dependency on the commitment, institutions and processes in partner countries to take forward and embed approaches to infrastructure development based on UK approaches.
The GIP has successfully built and maintained relationships with public sector organisations in Tier 1 and 2 partner countries, and secured their commitment to the Programme. This is demonstrated by the MoUs that have been signed with Colombia, Vietnam and Indonesia, the identification of senior sponsors within key organisations, as well as the number of workshops that have been organised in partner countries, and inward visits by officials from key public bodies (Outputs 1 and 2).
The Programme has also been successful in building relationships with other institutions and initiatives, including securing the endorsement of the 5CM by the G20 Global Infrastructure Hub; and support of the Inter-American Development Bank for the BIM methodology through a proposed Memorandum of Understanding. Progress has also been made in developing expanding communities of practice, and in engaging academic and wider community interest in the digital transformation of infrastructure, and this is anticipated to increase and be monitored during the Phase 3 pilot projects (Output 9).
Key documentation, including the 5CM and PIR, has been adapted for use internationally, and been validated by the Better Business Case Standards Board, as the relevant international standards body. The use of the PIR documentation has been piloted in Indonesia, and a further pilot is being planned in Colombia. Further work is underway to adapt the approach and documentation for use in specific partner countries, taking account of the legal, institutional and policy frameworks that exist in these (Output 3).
There are also plans in place for the development of national BIM programmes and frameworks aligned with UK and international standards in Vietnam (where a BIM Steering Committee and Technical Group have also been established), Mexico and Brazil (Output 4).
A considerable amount of capacity building work has been delivered in Tier 1 and 2 partner countries, including workshops and a range of training events in Vietnam, Brazil and Indonesia. There has also been progress in identifying potential pilot projects in Vietnam and Peru, and work is underway to identify projects in other partner countries (Outputs 5 and 6).
Work is ongoing to deliver the alignment of BIM legal and technical standards in partner countries with UK and international best practice. The appointment of Mott MacDonald as suppliers to the programme will provide the necessary capacity and technical expertise to deliver this during Phase 3 of the programme (Output 8).
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
- Development of BIM Standards: It should be a priority to focus on the development of BIM standards aligned with UK and international best practice in partner countries during 2019, through using the additional capacity and technical expertise provided by Mott MacDonald as a means of driving this.
- G&I: Delivering the primary benefits will require the programme to ensure the documentation, training and support delivered during the pilot projects in partner countries fully embeds the principles of sustainability, inclusivity and equality. Whilst the focus on gender equality and female empowerment in the programme is strong, it will also be important to ensure there is a similar focus on other key areas including disability, age, community engagement and child safeguarding, and that these are embedded in all relevant aspects of the programme.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

1. Value For Money

Key cost drivers and performance

Overall, the programme has remained in line with its total budget to date with an underspend in 2017/18 and a (managed) overspend in 2018/19.

In FY 2017/18 (July-17–April-18) the programme spent £571,729 against a budget of £704,782 (Table 1). Administration expenditure (FCO Staff plus non-staff administration) accounted for £67,852 (11.9%) of total expenditure. Programme expenditure was focused on delivering Phase 1 activities: building relationships with partner countries; developing international versions; and raising awareness of 5CM, PIR and BIM. This succeeded in building country engagement and the programme made “good progress”[3] on developing the international versions of the tools, including securing World Bank endorsement and agreement to publish them on its website.
[3] GIP Transition Funding Report

Table 1: GIP Outturn Expenditure FY 2017/2018 and FY 2018/2019
	FY 2017/2018		FY 2018/2019
	Budget	Actual	Budget*	Actual
FCO Staff (UK Based and Posts)	£384,782	£54,100	£181,297	£136,710
FCO Non-Staff Administration	-	£13,752	£13,752	£62,633
FCO Platform Charge	-	£11,908	£155,645	£9,923
FCO Business Case Development	£320,000	-	-	-
Phase 1 – IPA Country Engagement	-	£74,267	-	£581,357
Phase 1 – CDBB Country Engagement	-	£36,202	£113,000	£306,298
Phase 1 – Developing International Versions of Tools	-	£381,500	-	£435,445
Phase 2 – IPA Training / Capacity Building	-	-	£949,795	£46,045
Phase 2 – CDBB Training / Capacity Building	-	-	£607,000	£367,500
Phase 3 – IPA Pathfinder Projects	-	-	£779,707	£0
Phase 3 – CDBB Pathfinder Projects	-	-	£779,804	£220,471
GIP Peru Post Project	-	-	-	£74,261
GIP Colombia Post Project	-	-	-	£269,262
Additional Training Visits	-	-	-	£41,961
Total	£704,782	£571,729	£3,580,000	£2,551,866

*Budget allocation as of June 2018

For FY 2018/19, the GIP budget was £3,580,000 (as of June 2018), though this was revised down to £2,366,000 in November 2018 in response to a forecast under-spend for the year. The original budget reflects a significant over-allocation of supplier budget due to incorrect projections of how quickly supplier support would need to be increased. In the event, the programme delivery remained largely on track without this supplier support. Actual spend for the year was £2,551,866; this reflects a managed overspend against the revised budget (108%) in order to balance under-spend elsewhere in the PF portfolio. The managed over-spend was achieved by scaling up activity in Colombia and Peru and some additional training visits.
Administrative spend at £199,343 was 7.8% of total spend. The Prosperity Fund has set a Fund-wide ceiling of 5% for administration costs and a benchmark of 3.5% for individual programmes over their lifetimes[4]. Taking the administrative spend for financial years 17/18 and 18/19 and forecast administrative spend over the remaining years, it is estimated that the GIP’s administrative spend will be 3.7% of total expenditure over the lifetime of the programme, assuming all programme budget is spent[5].
[4] The programme level ceiling is lower given that there are centralised costs of administering the Fund that need to be accommodated in managing to the 5% limit.
[5] The programme is forecast to spend a further ~£660k on staff and non-staff administration over 2019/20 and 2020/21 resulting in programme lifetime administration costs of ~£930k, which is 3.7% of £25m.
There was an under-spend on FCO staff versus budget, particularly at Posts; the reason for this was that infrastructure advisor roles in Colombia, Indonesia and Vietnam Posts were filled later than anticipated. This was offset to some extent by an overspend on non-staff administration costs; the original budget allocation was too low and there were additional training requirements for the team not envisaged at the start of the year.
Phase 1 activities continued and delivered against the following outputs; the signing of MOUs with the three Tier 1 countries, country commitments on national infrastructure transformation policies and completion and certification of international versions of the methodologies. The GIP also supported G20 recognition of the principles aligned with the UK’s 5CM methodologies as being ‘Gold Standard’.
Phase 2 and 3 activity commenced with 5CM/PIR/BIM workshops, the development of BIM national strategies and the identification/implementation of BIM and PIR pilot projects (see Output Scoring). Some activity was brought forward on the CDBB pathfinder projects.
The programme also initiated assistance with Peru’s National Infrastructure planning and training and dissemination of the tools in Colombia - as part of the managed overspend. The “additional training expenditure” item involved inward training visits to the UK by delegations from the Peruvian and Mexican governments and 10 Latin American country posts. These activities were not envisaged in the original budget allocation.
The budget allocation process at the beginning of the FY was conducted in a top-down way with limited information on and forecasting of the likely level of activity and associated costs under each of the programme phases. Aside from activities not envisaged at the start of the year; it is this that accounts for the significant variances between the budgets allocations for the different delivery Phases and actual spend against these items (Table 1). Whilst the team has managed actual spend to the overall budget, improved budget allocation to the different line items for FY 2019/20 must be addressed, drawing upon the actual expenditure data from 2018/19. Without this it is hard to see where in the programme spend is on track/above/below reasonable expectations.

VfM performance compared to the original VfM proposition in the business case and assessment of whether the programme continues to represent value for money

Economy and Efficiency
On economy (are inputs being purchased at good VfM?) and efficiency (does the conversion of inputs to outputs represent VfM?), programme expenditure has been managed successfully to budget over the first 18 months whilst delivering expected progress against its milestones, particularly for Phase 1 activities. The programme has also achieved wider recognition and influence with its work e.g. World Bank and G20 endorsement of the international methodologies and progress towards a regional BIM hub in South America.
The business case considered different delivery models and concluded that the use of the IPA and CDBB was needed for the Phase 1 and 2 activities, given their respective expertise in the tools. This has been borne out through the delivery of certified international versions of the tools and the credibility brought to country engagement. For Phase 3 (pathfinder projects) the business case preferred option was to deliver this through “in-house” management of consultants who would provide the necessary scale. This was preferred to other options with higher overhead costs.
In terms of how performance to date compares to this, the overhead cost (FCO staff costs + administration costs) of the preferred delivery option was estimated to be 4.6% over the life of the GIP (cf. 17% for one of the alternative options). To date these costs have amounted to 8.6% of expenditure (Table 1) though this should come down as delivery expenditure increases. Separately, the FCO’s procurement framework was used for the appointments of suppliers to support delivery of Phase 3 – this was a competitive process in which bids were assessed on cost, the quantity and quality of proposed deliverables and suppliers’ capability/capacity to deliver.
The experience and expertise of the FCO’s delivery partners has also helped promote economy and efficiency in the GIP work to date.
For example, CDBB supports countries in developing national digitalisation strategies outside of the GIP so are able to bring wider experience and sharing of common resources to the GIP. In the last year, CDBB have also developed online training to build scale and consistency of training, re-used previous BIM work and training BIM materials (e.g. in other languages) and, at low marginal cost, supported the development of a Latin American regional network to share BIM best practice, increasing reach. CDBB judge that the cost and effort they have expended so far to deliver their GIP outputs is consistent with their work outside of the programme.
On the IPA side, the development of the international version of the 5 Case Model drew upon IPA’s and HMT’s own extensive expertise in infrastructure project delivery in the UK and the concurrent revisions to the UK version. Use of a piloting approach for the adaptation of PIR (in Indonesia) has provided lessons for adapting the tool to other countries in the rest of the programme. The tools will also have further reach than just GIP work e.g. they are available for use in other PF programmes with infrastructure focused interventions.
In terms of areas for improvement on economy and efficiency, whilst the costs of GIP activities to date are judged commensurate with other similar activity by CDBB and IPA, there has been no formal benchmarking against similar activities/programmes[6] delivered by other organisations. This is recommended as an action to monitor the potential for additional cost economies and efficiencies against the wider market and to track efficiencies gained as the GIP activities are repeated. This will be particularly important as spend starts to increase in the remaining years of the programme (see below).
[6] Benchmarking involves comparing activity costs to those of similar activities from other (development) programmes as a guide to economy of inputs.

Effectiveness
The GIP is still at a relatively early stage of delivery, so effectiveness (whether outcomes/impacts delivered are VfM in relation to costs) is judged here in terms of whether the Programme’s performance to date provides new evidence that better informs the estimation of expected programme benefits in the business case.

Primary Benefits
The GIP business case estimated the Programme would deliver primary benefit NPV of ~£1,150m over the ten-year appraisal period 2017/18-2026/27. Primary benefits were calculated as the uplift in GDP for the three Tier 1 countries (Colombia, Indonesia and Vietnam) as a result of increased investment (gross fixed capital formation - GFCF) due to adoption and use of the tools. The Theory of Change here is that use of the tools will make proposed infrastructure projects in these countries more “investible” due to increased clarity of benefits and risks (5CM, PIR) and potential reductions in costs (BIM).

Evidence that programme is performing in line with or better than business case benefits estimation
A positive corroboration of the business case methodology is the high level of engagement and commitment shown to date by the three Tier 1 countries. Capacity building is planned for all three tools in all three countries and the tools will be embedded in pathfinder projects in all three countries, with the exception of 5CM/PIR in Vietnam. Secondly, the Programme has laid some foundations for future scaling of activity (e.g. the BIM Latin American hub) and responded to additional opportunities outside of core programming; these could potentially deliver benefits not envisaged in the original business case, though the team will need to ensure that appropriate focus remains on delivering the Phase 2 and Phase 3 activities.
A key assumption in the business case is that adoption of the tools will increase the growth rate of GFCF by 0.2-0.3 percentage points, though this is an assumption (judged conservatively small) rather than informed by evidence. Given projected country levels of GFCF, this translates into an increase of ~$200m-$1bn. per year. The Programme does not yet have any outturn data on increased investment with which to test this assumption; however, its arbitrary basis means it is even more important that the MREL framework is set up to measure this impact.
Finally, the business case assumed a 75% success rate for the programme and a 66% attribution rate[7]. There is no evidence to contradict these assumptions at this stage of the Programme, albeit that they are highly uncertain; the Tier 1 country engagement is good, and there is no evidence that other donors are encroaching on the GIP’s areas of activity. Ensuring the tools are sustained within country planning systems post the Programme’s current activities will be critical for success.
[7] The success rate is the likelihood that the programme tools are successfully adopted and utilised in country infrastructure planning and development. The attribution rate is the extent to which the primary benefits can be attributed to the programme’s activities given that other potential donor activity may deliver similar benefits.
Evidence/risks that benefits may not be as high as in business case benefits estimation
The primary benefits in the business case were assumed to start accruing from 2021/22 onwards. This original assumption looks optimistic: uptake of the methodologies has not yet been delivered (though is on track) and infrastructure build time would limit impact to projects such as small schools or hospitals, with multiple projects needed to deliver the uplift in annual GFCF envisaged above. Similarly, successfully embedding the tools within pathfinder projects within the remaining two years of the GIP will be challenging.
As such, it is likely that primary benefits would be realised on later timelines than envisaged in the appraisal analysis. However, the business case did also present a scenario in which the impact of the tools on GFCF was halved and benefits only start to be realised from 2024/25 onwards. This scenario still had a positive NPV of ~£250m for the 10-year appraisal period and it is likely that further benefits would continue to be delivered beyond that period.
In addition to timing, there is a sustainability risk. Benefits will only be realised if the adoption of tools, training and capacity building are sustained within country infrastructure processes once the Programme closes. The Programme Team should continue to consider how to address barriers to sustainability of impact as it progresses the Phase 2 and 3 activities. It is recommended that the team review past initiatives/development interventions to embed new methodologies in planning processes (in the UK or overseas), or in other domains, to identify successful strategies for ensuring sustained outcomes post programme activity.
Secondary benefits
The business case also estimated the Programme would deliver a secondary benefit NPV of ~£160m over the ten-year appraisal period. This focused on potential professional service consultancy opportunities arising from the additional infrastructure projects in the Tier 1 countries. Most assumptions made here cannot be tested with programme experience to date as it has not yet begun to influence actual infrastructure projects.
The exception here is the same timing point discussed under the primary benefits such that secondary benefits are likely to be realised later than envisaged (secondary benefits were assumed to start in 2021/22) or only with an initial ramp-up. Again though, this represents a delay to benefits rather than a reduction in them per se.
Equity
The GIP team has worked closely with Gender & Inclusion advisers from JFU, PFD and the Fund’s evaluation partner (WYG). The WYG G&I team assessed the GIP against the Fund’s Gender and Inclusion scorecard in May 2019, rating it Amber overall for insufficient evidence of alignment with the PF G&I policy[8]. Separately, the GIP’s Gender Equality Marker[9] rating was “0” (on a 0, 1, 2 scale), meaning the programme as currently designed does not target gender equality. Key recommendations from the EL scorecard assessment were:
[8] Scoring amber specifically on capability and incentives, and on financial resources
[9] The GEM is an OECD tool used by humanitarian and development agencies to monitor gender equality in programmes throughout the programme cycle (policy, design, implementation, monitoring and evaluation).
“suppliers need to undertake their own situational analysis of the differentiated impacts on women and men and gender equality at scoping and design stage with a proper implementation action plan on a project basis.” In order to fulfil the GEA Compliance measures stated in the GIP Business Case, “suppliers are required to undertake an evidence-based assessment of the differentiated impacts on women and men and gender equality at scoping and design stage with a proper implementation action plan”.

“the 5 Case model guidance document could be enhanced to fully embed G&I considerations throughout.” The team plan to address this by integrating G&I considerations into 5CM as a deliverable of the IPA Statement of Requirements. This will strengthen the GIP’s likelihood of positively impacting women and other excluded groups, provided such guidance is implemented effectively in partner countries. With this action, the EL team note the programme could reach a GEM score of 1 – a “significant contribution to gender equality”.

“future revisions of the programme Logframe indicators should incorporate and address the PF Global Social Development Advisor’s recommendations to cover both gender and disability considerations”. This reflects GEA compliance commitments that “Gender equality and women’s empowerment indicators will be built into the log-frame at outcome level and at output level” and that “Suppliers will also be required to report on differentiated impact as part of ongoing reporting with sex disaggregated data”.

There was evidence from this review that the GIP team is strengthening its G&I capability; delivery partner suppliers have G&I resource within their teams and the team has identified G&I “Champions”. That said, the GIP can do more to promote G&I progress within the Programme’s governance structures. We recommend G&I is a standing item at Operational Committees and Programme Board meetings and the team and its Social Development Advisor use these to update the SRO on development of the G&I Assessment and Action Plan and programme design. Recommended topics for discussion are the weighting of G&I impact within pathfinder project selection criteria; how training and capacity building approaches will target gender and wider inclusion and; what steps will be taken to embed G&I considerations in country institutions/planning processes via the tools.
To support this, the GIP team should draw on resources and lessons from major DFID infrastructure programmes and existing guidance on good practice on inclusive infrastructure. These include DFID’s Infrastructure and Cities for Economic Development (ICED) Helpdesk and Work and Opportunities for Women helpdesk.

Changes in staffing
The GIP staff includes the FCO’s GIP team (2 FTE), the IPA and CDBB delivery teams and their recently appointed supplier teams (PWC and Mott Macdonald) and Infrastructure Advisors supporting activities at FCO Posts (approximately 0.5 FTE in Colombia, 1 FTE in Indonesia and 0.25 FTE in Vietnam; other Posts provide support from existing staff).
As indicated in GIP quarterly reporting to JFU, staffing risk increased from Green to Red over FY 2018/2019, reflecting continued challenge in appointing a Contract Manager to the FCO GIP team and vacancies within the IPA team. The team is mitigating this in the short-term through temporary cover and increased supplier resource and is actively seeking to fill these vacancies permanently. Resolving this is key to avoiding any detrimental impact on delivery and VfM in the next year of the Programme.

Overall VfM Assessment
Overall, Programme performance on budget, milestones and progress towards outputs to date suggests it still represents value for money, albeit that it is still at a relatively early stage and reporting activity is confined only to outputs, rather than outcomes and impacts. Strong country engagement, particularly in the Tier 1 countries is a very positive sign, though it appears there is a risk to the timing of benefits realisation compared with the original cost-benefit analysis.

2. Financial Performance
The Programme’s outturn financial performance is discussed in the VfM section above.

Quality of financial management
The GIP has put financial management processes in place to set budgets, track expenditure and invoice expenditure but there is potential for improvement, particularly on the budget allocation process (see Key Cost Drivers and Performance section) and fiduciary risk.
Existing cost controls include the expenditure limits defined within the MOUs between the FCO and, respectively, IPA and BEIS (for CDBB)[10]. The Programme’s delivery partners, IPA and CDBB, have reported current and forecast spend against budget[11], project progress and project risks via monthly dashboards to the FCO GIP team since August 2018. These are discussed at Operations Committee meetings, including variances to forecasts, monthly under/overspends and exceptional costs. The Programme’s financial position is discussed at the Programme Board and is submitted to the PF’s Joint Funds Unit, both on a quarterly basis. There is evidence from Programme Board minutes that expenditure risks are actively managed e.g. a paper was circulated in November 2018 considering proposals to mitigate the forecast underspend for the Programme.
[10] The Prosperity Fund portfolio and ministerial boards and FCO’s Infrastructure, Investment and Operations Committee approved the £25m budget and proposed programme activities and countries through a concept note and business case assurance process. The IPA and CDBB’s experience of providing technical assistance internationally informed those documents.
[11] Disaggregated into: staff, consultants, travel and training costs
FCO GIP team have set up purchase orders for IPA and CDBB who submit invoices services provided to the Programme. The FCO Programme Manager checks these before being passed for payment. On the CDBB side, Mott MacDonald submit monthly invoices, with accompanying deliverables schedule, for payment against FCO Purchase Orders. Each invoice is scrutinised by CDBB for accuracy and authority is passed to FCO to arrange payment of the invoice. IPA similarly review draft invoices submitted by PWC against outputs before actual invoices are submitted and finally approved by the IPA programme manager; an audit trail of all approvals is kept.
In terms of room for improvement, it is recommended that the FCO GIP team implements cost benchmarking for the Programme’s remaining activities as it moves to spend larger sums in years 3 and 4. This will support assessment of the Programme’s VfM (Economy) and promote effective cost management. For example, given the Programme’s strong training component, the tracking of a “cost per trainee” metric and comparison with benchmarks from other (development) programmes delivering technical training would be sensible. This would assist with identifying potential cost efficiencies in the programme’s activities, though from a VfM perspective, cost savings need to be balanced against any implications for activities’ impacts.
It is also recommended that the FCO GIP team conduct checks of a sample of delivery partner invoices each year against individual receipts to assure fiduciary risk. IPA and CDBB should action the same for their respective suppliers.
An additional recommendation on budget allocation within the GIP has been made in the Key Cost Drivers and Performance section above.
Date of last narrative financial report	3 May 2019 (PST Programme Monthly Spend Final Year End 18/19)
Date of last audited annual statement	None

Summary of VFM and Financial Management Recommendations
- VFM (Economy): FCO GIP (contract manager) to implement cost benchmarking for the Programme’s remaining activities where possible, to support assessment of the programme’s VfM in purchasing inputs.
- VFM (Effectiveness): Building on contacts already made, the Programme Team, IPA, CDBB and suppliers to review examples of past infrastructure programmes or development interventions across HMG (including those supported by the Prosperity Fund, DFID and other Departments) to embed new methodologies in planning processes (either in the UK or overseas) to identify any successful strategies for ensuring tools continue to be used post the programme.
- VFM (Equity) - G&I (Scorecard Recommendations): implement recommendations of G&I Scorecard assessment.
- VFM (Equity) - G&I (AR Recommendation): progress on G&I to be added as an agenda item at Operational Committees and Programme Board. This should be used to explain Programme component design with respect to G&I, including: how G&I impacts is reflected in pathfinder project selection criteria; how GIP approach to Phase 2 training and capacity building in country will be inclusive; what steps will be taken to embed G&I considerations in country institutions/planning processes via the tools.
- Financial Management: The GIP Team should ensure that budget allocations for FY 2019/20 (and remaining programme years) for each of the programme line items (e.g. phases 1, 2 and 3 by delivery partner) are forecast as accurately as possible so that the source of any under or overspend at the aggregate level is easy to identify over the course of the year.
- Financial Management: The FCO GIP Team should conduct regular checks of a sample of delivery partner invoices each year against individual receipts to assure fiduciary risk. IPA and CDBB should action the same for their respective suppliers (PWC and Mott Macdonald).
E: RISK

Overall risk rating: Moderate
The Transition Funding annual report in July 2018 gave the GIP a delivery rating of A. Whilst risks remain, this is probably still a fair reflection of the progress made towards delivering the GIP.
Overview of programme risk
The programme risk register has around 40 risks of varying severity, and is reviewed on a monthly basis by the FCO Programme Team. It is then passed to the SRO before being submitted to JFU. The risk register is in line with JFU guidelines for the management of programme risk, including pre and post mitigation RAYG ratings, detailed mitigation details, proximity, impact, etc.
Project risk is managed by IPA and CDBB for each of their projects. They report back monthly on their top risks via the monthly dashboards submitted at the Operations Committees meetings. The risks are reviewed as part of the dashboard reviews and any changes in risks are discussed and mitigations agreed. Where projects risks are significant, they can be escalated to the programme risk register accordingly.
At this stage, the key risks to the Programme are:
a) Financial – the Programme spend profile that backloads spend towards the end of the programme risks underspending without careful management.
b) Resourcing – FCO, IPA and CDBB each have personnel resourcing challenges that are being managed but programme delivery remains at risk from the difficulty and delays in recruiting skilled staff.
c) Timeline/delivery - there is a potential need for an extension to the duration of the Programme given that some projects may go beyond the agreed timeline for delivery of 2021. It is not possible to fully mitigate this risk within the programme due to the dependency on decisions, actions and timetables for projects being made by public sector bodies in partner countries.
d) Relationship management - as work is to be carried out by Mott MacDonald and PwC, this will increase the scale and complexity of the Programme, and creates additional governance and management challenges that will need to be addressed to enable successful delivery.
e) Secondary benefits - the potential that the Programme doesn’t deliver on the secondary benefits as expected as there is competition between UK companies and other global companies.
f) Gender inclusion - the methodology of the Programme makes it hard to involve gender inclusion and concerns about how involved they are at posts.
Outstanding actions and recommendations from risk assessment
- Delivery Timetable: the Programme Team should undertake a strategic review of opportunities to extend and increase the scale of the programme, to enable it to achieve maximum impact in delivering the primary and secondary benefits and establishing UK methodologies in both partner countries and more widely as internationally recognised best practice. (Summer 2019).
- Delivery Resources: the Programme Team should undertake a review of the personnel needed to deliver the programme within FCO, delivery partners and suppliers, assess whether these are sufficient, and if not recruit additional staff as soon as possible to help manage and deliver the programme in an efficient manner.

F: COMMERCIAL CONSIDERATIONS (1 page)
Delivery against planned timeframe
The principal commercial activity within the Programme has been the recruitment of private sector contractors to support the IPA and CDBB deliver support to organisations within partner countries as part of Phases 2 and 3 of the Programme. Following procurement exercises undertaken in 2018-19, using the Prosperity Fund Frameworks, the two contractors appointed were:

- PwC (appointed March 2019) to support the adaptation of the UK methodologies for infrastructure programmes, and providing training and support to officials in partner countries, working with the IPA (£2,262,534); and
- Mott MacDonald (appointed December 2018) to provide technical support and training in relation to the use of Building information Modelling (BIM) techniques in relation to exemplar projects in partner countries, working with the CDBB (£2,563,093).

Performance of partnership(s)

Following their appointment, the contractors have been working closely with the FCO GIP team, the IPA and CDBB in the UK to plan the programme, and begun the process of establishing their teams and relevant resources in partner countries. This has included building relationships with staff in posts overseas and in key institutions within partner countries. As a result, programme delivery is broadly in line with the planned timeframe. Although this work is in the early stages, it is anticipated that the programme team and suppliers will be able to deliver the planned programme of activities, including supporting partner countries to apply UK methodologies on pathfinder projects, between 2019-21.

Changes in the Delivery Plan
However, the Programme is dependent on the engagement of public authorities in partner countries responsible for developing infrastructure; this means that it has been difficult to accurately plan activities and timescales, since the level of engagement and the ability of these institutions to adopt new approaches has varied. Consequently, some countries have proceeded faster than expected e.g. Vietnam, whereas others have been slower e.g. Indonesia. The uncertainties about the timing and level of resources required in partner countries may need additional support to be procured to support the delivery of the programme during 2019.

Recommendations
- Supplier Management: the Programme Team should take forward the recruitment process for a contract manager to oversee the contracts with the key suppliers to the programme, Mott MacDonald and PwC.
- Contractor Support: the Programme Team should evaluate the need for, and likely type of additional contractor support for the programme, in order to enable the Programme Board to take a decision as to whether to seek to procure this and if so, to start the procurement process as soon as possible.

Asset monitoring and control
The UK methodologies, and associated adaptations of these will continue to be owned by the UK Government. It is not anticipated that the new assets that are created (e.g. policies based on these or BIM models of specific built assets) would be owned by the relevant government organisation in the partner country.

G: Business Environment (½ page)

How has the business community and business environment responded to the programme?
Reaction from both the UK and overseas businesses has been positive, with a lot of interest in the Programme’s plans to increase the number of financed infrastructure projects, and to improve the way these are developed, procured and delivered in expanding markets in Asia, Africa and Latin America. There is also support for the alignment of the Programme with wider infrastructure initiatives, including funding from the multilateral institutions, the Inter-American Development Bank and through the Belt and Road Initiative.
The business community has been engaged through a range of events and other activities undertaken by the programme, both in the UK and in a number of the partner countries. A number of wider PF engagement events have been held in the UK, including one at which the GIP was formally launched in June 2018. During visits to partner countries, the team arranges meetings with the local business community e.g. via Mexico Chamber of Commerce. A number of UK firms have also been engaged in activities related to the programme in Peru. The work of the programme has also been promoted through local media and social media. As the GIP moves into Phase 3, it will be important to both intensify and extend the scope of these activities. It will also be important to engage UK firms with the capability to support the delivery of the pilot projects, to enable the realisation of the anticipated secondary benefits.
(Where relevant) What role has non-ODA spending played in promoting programme objectives?
There has been no non-ODA funding allocated to the Programme so far.
Recommendations
- Stakeholder Engagement Strategy: Whilst the GIP has been successful in engaging public bodies in partner countries, further work is required in Phase 3 of the Programme to develop a wider stakeholder engagement strategy in Tier 1 and 2 countries, encompassing the private sector (both clients and service providers), academia and media stakeholders. The Programme Team should also review whether there would be benefits to linking these stakeholders with similar groups in the UK, including the Knowledge Transfer Network and academic networks supported by the Transforming Construction Programme.
- Business Engagement: As part of its wider stakeholder engagement strategy, the Programme Team should work with the IPA, BEIS and DIT to identify UK firms that possess the capability to support the delivery of infrastructure projects in the partner countries and, when opportunities begin to emerge, to raise their awareness of the Global Infrastructure Programme and the potential opportunities this could generate.

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
The GIP has not been evaluated to date, though an annual evaluation by the PF’s Evaluation and Learning partner (WYG) is scheduled for September 2019.
Monitoring progress throughout the review period
The GIP team (FCO, IPA, CDBB) and monitoring partner (PA Consulting) made good progress in developing the programme Logframe in the first quarter of 2019. The current version of the Logframe has proposed indicators for outputs, intermediate outcomes, outcomes and impacts and follows the programme Theory of Change. It states where the team proposes to disaggregate metrics (e.g. by income, gender, age) and sets milestones (outputs) and assumptions made. The process has enabled the team to report progress against output milestones for this review, where expectations have been set for this year (see Output Scoring). The next step for Logframe development is to identify: data sources, costs of data collection and ownership and frequency of data collection/reporting and to get monitoring underway in full.
Observations for further development of the Logframe are:
Consolidation. Currently there are 9 outputs in the Theory of Change and 63 indicators in the Logframe, some of which are disaggregated further. Additional indicators/disaggregation has also been proposed to ensure G&I impact is measured effectively. This requires review to mitigate the risk that data collection becomes unmanageable for teams. A check that outputs and outcomes are appropriately classified is also suggested as part of this.
- Attribution. Some of the (Intermediate) Outcome and Impact indicators require careful thought about how the Programme’s impact can be measured in an attributable way and the data that will be required to achieve this. For example, to estimate the Programme’s NPV or its impact on country GDP, it will be necessary (at minimum) to collect data on the number of infrastructure projects in country that are and are not using the tools, which could require engagement with country agencies to develop infrastructure registers if these don’t already exist. For these indicators bespoke preparatory work will be required, potentially through the PF’s MREL partners.
- Milestones. Some outputs are currently missing milestones or are not currently being reported against (e.g. data on disaggregation of trainees by gender was not provided for this review)
- “Ways of working”. All parts of the GIP team have shown strong ownership and engagement in developing the Logframe, which is very positive. The need for consolidation however, is in part due to different teams engaging with the process at different times – to address consolidation and the other points above in a joined-up way, the team should ideally conduct a review with all areas participating simultaneously, potentially over a longer, more concentrated session.
- Move to Monitoring and Reporting implementation. Notwithstanding the points above, it is important that the GIP gets underway with data collection and indicator reporting quickly given that delivery activities will ramp up over this year. Where there is a need to baseline data to measure (intermediate) outcomes and impacts, this will need to be implemented soon. Adaptive management of the programme will also be dependent on getting data collection fully operational.

Recommendations
- Theory of Change/Logframe: review of the TOC/Logframe should be undertaken by the GIP team and MREL partners to consider and address the points on Consolidation and Milestones (end July 2019)
- Output Indicators: Ensure all output indicators have associated milestones and implement reporting against these (end July 2019).
- Strengthening MREL: Produce a review of the additional data requirements and methodologies needed to measure the Logframe’s intermediate outcomes, outcomes and impacts with the aim of implementing baseline data collection before the programmes activities are likely to effect change within country planning processes (end September 2019).