IRRP Annual Review 2019 - Summary

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Indonesia bilateral Regulatory Reform Programme (IRRP)
Programme Value: £1.5m		Review Date: completed 14/11/2019
Programme Code:	Start Date: 2017	End Date: 31/03/2023

Summary of Programme Performance
Year	2019	2020	2021	2022	2023
Programme Score	A
Risk Rating	moderate

Summary of review findings, progress and lessons learnt since last review
IRRP is off to a successful start having built a solid foundation from which it can deliver a set of small but important interventions. This programme represents Value-for-Money (VfM): its delivery model is efficient and effective; it’s gained good traction with the Government of Indonesia (GoI) due to the UK’s expertise and international reputation in this area; and it is focused on ensuring the sustainability of results achieved. The Regulatory Attaché role is a strong model for delivery. It maximises ongoing access to UK expertise in between visits by UK experts from Regulatory Delivery International (RDI) . The model demonstrates good VfM due to the background and skills of the incumbent. It also mitigates any risk to RDI resource availability associated with the UK leaving the European Union. Further consideration on Gender and Inclusion (G&I), the process to realise secondary benefits, and more effective governance processes will help improve this programme’s scoring.

This programme is demonstrating effective navigation of the challenging reform environment in Indonesia. It has carved out a niche area of support, where the focus of its delivery partner, Regulatory Delivery International (RDI) – a part of HMG’s Department for Business, Energy and Industrial Strategy - matches Government of Indonesia (GoI) priorities. Engagement with the GoI is generally good but it can be challenging as economy-wide programmes such as this can raise ideas for ancillary initiatives not directly aligned with the programme’s objectives. The programme is very aware of this and the risk to the programme’s focus.

IRRP receives a stream of requests from the GoI for additional activities. It maintains focus without adversely impacting relationships through strong relationship management. It has agreed a Memorandum of Understanding (MoU) and an agreed annual work-plan with GoI partners. Furthermore, it is using the work-strand on understanding and agreeing regulatory delivery reform priorities to develop a roadmap that should ensure focus on its delivery outcomes. This review recommends setting out explicit criteria for the Economic Reform Steering Group to use in assessing and approving inclusion of new activities suggested by the GoI. The programme should deploy a robust narrative, which fits into a wider Prosperity Fund (PF) in Indonesia narrative, as a way of keeping the programme bounded.

In addition, regulatory reform in Indonesia is a crowded space so there is a risk of overlap and duplication. This programme has mitigated this through clear and ongoing delineation with other partners, and constant alignment with often shifting GoI priorities. With regular engagement, it is now adaptively building synergies with other donors.

The programme team recognises it needs to do more work on G&I, including further research to scope G&I considerations specific to regulatory reform and incorporating G&I aspects into intervention selection. This review recommends conducting G&I impact assessments on interventions as they are designed.

The Theory of Change (ToC), its associated narrative and the LogFrame are progressing well, although further development and explanation is needed. As requested, support has been provided through this Annual Review. Revisions to these documents should be made within three months of this review.

Secondary Benefits (SB) should rise up the agenda as the programme develops and interventions become clearer. A plan should be developed for this programme and it needs to fit into a wider coherent plan for the realisation of SBs for all 11 PF programmes in Indonesia. The local DIT team will be under pressure to engage with all 11 programmes and those programmes that are cross-economy and non-sector specific will struggle unless work is done in a systematic cross-programme way. Supporting important regulatory reforms can serve as amplifiers for the realisation of SBs across the wider PF portfolio in Indonesia.

While governance structures have been created and are in use, including involvement of the GoI, the Embassy’s Economic Reform Steering Group and Programme Board would benefit from strengthening their governance function. The review recommends that Terms of Reference (ToRs) are created for both these Boards and an integrated governance structure developed to provide better complementarity. This would strengthen the Boards’ respective governance roles and help drive synergies across the Embassy’s PF portfolio.

I am grateful to the team for their thorough review of the establishment of this programme which represents a small but important part of our programme portfolio in Indonesia, and an important part of our work to improve the business environment more widely. The recommendations will help us continue to steer it effectively while being responsive to the GoI priority for regulatory reform.
Owen Jenkins
SROI and HM Ambassador to Indonesia and Timor Leste
Owen Jenkins
HM Ambassador to
Owen Jenkins
SRO and HM Ambassador to Indonesia and Timor Leste

List of recommendations for the next year
Governance
1.	ToRs should be prepared that allow the Economic Reform Steering Group and Post Programme Board to perform governance and oversight functions more fully. G&I, VfM and SB approaches should be regularly reviewed at these meetings, to ensure these thematic areas are fully embedded in programme delivery and to support synergies between the PF programmes. More consideration should be given to how the two boards interact. DIT should be represented on both Boards.	ACTION: SRO
2.	The ToC and logframe should be revised as planned, with the results presented to the Economic Reform Steering Group within the next three months. Programme indicators should be loaded onto Prospero.	ACTION: Regulatory Attaché/RDI
3.	Seek ways to promote best practice and share lessons learned with other Embassy PF programmes, including through structured PF Learning opportunities.	ACTION: Regulatory Attaché
4.	Consult with other donors to discuss the feasibility of establishing an economic reform donor coordination forum.	ACTION: Regulatory Attaché
Secondary Benefits
1.	Explore the possibility of tapping into non-ODA funds to help drive the realisation of SBs and the creation of synergies between PF programmes across Indonesia and the region.	ACTION: Regulatory Attaché
2.	Exploit opportunities to piggyback on the sectoral work of other PF programmes, ensuring that any regional events also deliver the key messages of this programme.	ACTION: Regulatory Attaché
3.	Carry out a SB mapping exercise and share the outcomes with interested parties. Identify relevant organisations such as trade associations, think tanks and other non-government actors, such as the UK Asia Business Council, that should be briefed regularly on programme activity.	ACTION: Regulatory Attaché/RDI
Cross-cutting
1.	This programme would benefit from having a cross-cutting PF function delivered at Post. This function would support synergies and learning across the PF portfolio, leading to embassy wide improvements in VfM, the development of a coherent PF in Indonesia narrative for communication with the GoI, and an increased focus on SB realisation.	ACTION: SRO

Engagement
1.	Renew stakeholder mapping following the appointment of new GoI ministers and develop a plan for engaging any new interlocutors, e.g. the President’s Office (KSP).	ACTION: Regulatory Attaché
2.	Use a cross portfolio narrative that emphasises the specific benefits of this programme but also sits it in within the wider context of PF in Indonesia in communication with the GoI. The aim would be to gain more traction for the programme and make it more bounded from the GoI perspective.	ACTION: Regulatory Attaché

Operational
1.	Prepare a checklist of criteria, including VfM and G&I aspects, for analysis and presentation to the Economic Reform Steering Group for agreement to any new GoI requests.
2.	Monitor closely the implications of UK exit from the EU on RDI resource.
3.	Secure RDI’s agreement to use timesheets for audit purposes.
4.	Consider ways to mitigate the lack of Indonesian resource in the delivery team.
5.	Commission the programme’s bespoke Indonesian G&I research within the next three months.
6.	The programme should undertake G&I impact assessments on the reforms it proposes.
7.	The risks recorded should be more explicit about VfM and sustainability, and their relevant mitigations.
8.	Revise the ToC and LogFrame, G&I plan and risk register based on the outcome of this review and present to the Economic Reform Steering Group within 3 months.
ACTION: Regulatory Attaché/RDI
List of Acronyms
BAPPENAS	Ministry of National Development Planning, GoI
BEIS	Department for Business Energy and Industrial Strategy, UK
CMEA/Kemenko	Co-ordinating Ministry of Economic Affairs, GoI
E&L	Evaluation and Learning team
EoDB	Ease of Doing Business – used as an intermediate outcome indicator for the Prosperity Fund
G&I	Gender and Inclusion
GBE	Global Business Environment Programme, financed by the Prosperity Fund
GoI	Government of the Republic of Indonesia
IRRP	Indonesia Regulatory Reform Programme
KSP	Kantor Staf Presiden (President’s Office)
LogFrame	Logical Framework
MoLHR	Ministry of Law and Human Rights, GoI
MoU	Memorandum of Understanding
MR	Monitoring and Reporting team
ODA	Official Development Assistance
PF	Prosperity Fund
PP	Primary Purpose
RDI/OPSS	Regulatory Delivery International, a function within the Office of Product Safety and Standards (OPSS) in BEIS
SB	Secondary Benefits
ToC	Theory of Change
ToR	Terms of Reference
VfM	Value for Money

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	https://www.gov.uk/government/publications/prosperity-fund-fco-programme-summaries-countries / NB FBC to be published soon following revision of benefits’ calculations / Update; FBC published at https://www.gov.uk/government/publications/indonesia-regulatory-reform-programme
DevTracker Link to Log frame:

The business case for IRRP was originally part of the business case for the Indonesia Renewable Energy and Regulatory Reform Bilateral Fund. A separate business case was subsequently developed and the full version was approved in November 2018. Programme implementation began in May 2019; the programme is being delivered by RDI which is part of HMG Department of BEIS which leads UK Government regulatory reform. A MoU with the GoI, setting out the initial workstreams, was signed in June 2019. The programme budget is £1.5 million and covers activities conducted between 2017 and March 2023.
Complex and inconsistent regulation and enforcement are widely agreed to be a significant barrier to business and further growth in Indonesia. The IRRP diagnostic work recommended a cross-cutting approach, focused on improving regulatory delivery strategy and systems, with potential benefits across the economy as a whole. Three workstreams have been developed:
1. Enhancing the strategic management and coordination of regulatory delivery reforms;
2. Improving the implementation and delivery of regulation by encouraging the professionalisation of regulators and building capacity of frontline regulatory officials; and
3. Strengthening formalised mechanisms for public consultation and ongoing business engagement
This programme fits clearly within the PF Business Environment Reform family, primarily contributing to the ‘Ease of Doing Business’ (EoDB) pillar and associated intermediate outcome of the PF. The programme’s reforms will increase incentives for domestic and international (including UK) firms to invest by reducing the uncertainty, risks and costs associated with doing business in Indonesia, contributing to a more level playing field for business. The impact on poverty is indirect; greater investment by firms leads to economic growth which is regarded as an essential pre-requisite for poverty reduction. . However, there are some important assumptions underpinning the link between economic growth, inclusive growth and poverty reduction, namely that reforms need to successfully reduce barriers to doing business for all, greater openness to business results in increased growth in practice and increased growth results in increased employment and economic opportunities for the poor.
There is however a direct impact of improved regulatory delivery on consumers, where they are protected from unsafe products or services. Improving the activity and behaviour of regulatory officials should also reduce the potential for corruption, although this will need to be assessed in relation to the specific interventions supported by the programme.
There is high potential for SBs for international and UK businesses from reforms in the ease of doing business area: the EU Business Confidence Index and feedback from British and local business leaders in Indonesia shows that regulation is consistently business’ highest concern.
The programme’s cost-benefit analysis has been reviewed due to concerns that the projected benefits were disproportionate to the rest of the PF portfolio. The conclusion was that the model used to calculate the benefits was the best available but a lower attribution rate would be more appropriate. The revision projections are for primary benefits of £79m and SBs of £21m.
The national and presidential elections in April 2019 have caused understandable delays in decision making, although we expect normality to resume following the re-inauguration of the President on 20 October and the appointment of ministers. For this programme, the Minister in charge of CMEA is likely to change as the incumbent is expected to retire. It will be important to ensure his successor’s commitment to this programme. Engagement has continued through the period and delivery has started but a new government should provide much needed impetus for the programme (and other wider economic reforms). In fact, the President emphasised the importance of continuing regulatory reform in his inauguration speech.
As the areas of work have been refined, the programme team has started to comprehensively map out other donors’ involvement. This is shaping the design and development of the programme’s activities. While the work areas are now reasonably well defined, the programmes flexibility is a strength and it should continue to adapt to the changing context.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
This programme sits within the EoDB pillar of the Prosperity Fund and its Theory of Change broadly reflects this and the business case narrative. The ToC and logframe are due to be revised following this review and should be treated as living documents.
At impact level the programme’s ambition is the creation of a more supportive business environment through improved delivery of regulation and better input of business into regulatory delivery. The programme has three outcomes:
- Improved compliance with business regulation and increased confidence in regulatory environment in Indonesia by domestic and international, including UK business;
- More effective and efficient post-border market surveillance rolled out in all post-border regions;
- Improvement in the ease of doing business in DKI (Jakarta) are through feedback from inclusive business engagement, particularly from women’s representatives.

The programme’s three workstreams, set out in section A, aim to make a contribution to these three outcomes. Outputs to be generated by the three workstreams are yet to be specified and will be set out in the logframe, which will be revised after this review. Interim outputs and associated indicators were defined to assess performance to date for the purposes of this Annual Review.
(outcome – impact)
The programme is at a very early stage in terms of implementation so at this point likelihood rather than achievements towards outcomes is assessed. Based on progress to date, interventions areas supported, and traction with GoI stakeholders it is It is considered likely that the programme outcomes can deliver better EoDB Better compliance and trust in regulatory implementation (for domestic and international businesses, including for UK companies for whom the rules- and risk-based approach will be familiar), reduce the risk and cost of doing business in Indonesia and improve outcomes for consumers (including the vulnerable and poor). These improved EoDB measures will support progress towards a more competitive economy, leading to more investment and jobs and consumer choices.
(output – outcome)
The programme is likely to contribute to better compliance and confidence. It is working with regulators to improve their behaviour to monitor and support compliance and businesses report that this gives them confidence. There is a strong likelihood of a contribution towards some parts of the regulatory system (not all regulators) through a staged approach of pilot, followed by rollout in a way that can be replicated. However, at this point it is too early to say whether GoI will drive the wider adoption of these improvements although efforts will be made towards that goal.
Authorities need to listen to business to understand how to make doing business easier. Licensing is a significant and important area for business. Improving the licensing processes – by listening to business about what the problems are and their requirements – is beneficial in itself and should set up the culture of engaging with business more widely. This will lead to a more attractive environment for business. Jakarta is the most significant business centre and the gateway for most foreign investors.
Reforming licensing is a high Presidential priority but the approach taken so far has focussed heavily on an IT tool, had insufficient engagement with regional and business stakeholders and has arguably not addressed the fundamental reform need. Although the workstream is highly likely to support local improved engagement with business, the probability of significant, widespread and sustainable reform is difficult to predict at this point.
G&I
Not all growth is inclusive: the programme must do its best to support opportunities to improve the situation for women and disadvantaged groups leading businesses. Economic growth is also a prerequisite for other, more directly poverty-targeted programmes ensuring that the poorest benefit from this growth.
Some work to embed G&I considerations into programme design has been done but not enough. However, work is underway to do more in this area. The programme is not focussed on gender-specific barriers to business and there is a dearth of evidence on the local barriers faced specifically by women in Indonesia. There is anecdotal evidence that reducing the number of times an entrepreneur has to go and deal face-to-face with a licensing official not only saves them time but also reduces the opportunity of abuse of power. In addition, female consumers are regarded as more vulnerable to unsafe goods in the market. An example of the kind of opportunity which may emerge, comes from a reform which DKI Jakarta has already made. To reduce the barriers to registration for very small businesses, DKI removed its regulation requiring businesses to have a separate premise, thus allowing them to register from a home address. This resulted in a wave of women registering their businesses, as they were disproportionately running small enterprise activity from home. The programme is preparing to commission research to identify specific issues within the areas of the programmes intervention, particularly important as consultation with relevant groups has not yet raised issues.
The review recommends that the programme carry out G&I impact assessment of its interventions.
The revision of the ToC and Logframe following this review needs to articulate all this more clearly.

Annual outcome assessment (Secondary Purpose)
The programme expects to make the market more attractive for international, including UK exports and ODI by making it easier and less risky to do business. UK businesses will be familiar with the rules and risk-based approach since this approach is applied in the UK.
The programme expects to see the benefits domestically first, followed by realisation of secondary benefits as the costs and risks to doing business in Indonesia for international, including UK, businesses are reduced.
This is a general business environment reform programme, not targeting any specific sector. The benefits of reduced risk and familiarity will not, in themselves, lead to new opportunities. They are an enabler of other opportunities, for example through sector-specific programmes. Therefore this programme has the potential to serve as an amplifier for the realisation of secondary benefits for other PF programmes in the portfolio and DIT priority sectors.
There are potential opportunities for international business, including UK companies, in Indonesia but it has been challenging to date for UK companies. Preparing a secondary benefit plan for this programme should be part of a more comprehensive look at secondary benefits across the whole Indonesian portfolio, including exploring options of accessing non-ODA funding might support this programme. The programme needs to actively pursue this area.
This is an area of high importance to the GoI and one in which GoI recognises UK expertise and leadership. They are open to UK influencing the adoption of good practice across the regulatory space and this is a great opportunity and basis for UK engagement.

Overall output score and description
The programme is assessed at A against the indicators of setup: delivery model, scoping & design, partnerships & collaborations; the very early stage of delivery; and governance and learning processes.
The programme has laid good foundations and is off to a successful start. It is a small but important intervention which represents VfM and builds on clear respect from GoI for the UK/RDI expertise in this area.
The programme was delayed in starting, but based on the assessment overall, the review feels a score of ‘A’ is justified:
- The world has moved on since the business case: the programme is nimbly taking on new areas of work and is ahead of delivery expectations for other outputs.
- The programme works in a collaborative way with the GoI so that it continues to reflect GoI needs and adapts interventions and even new areas of work (while staying aligned with the programme objectives).
- Some areas of work that have not been taken forward are in reflection of GoI needs (1.3) or coverage by GBE (3.5).
While the set of outputs that the programme is now delivering is not the specific set in the FBC nonetheless the programme is meeting expectations in terms of pace of delivery and progress at this point.

Key lessons
This Annual Review distilled a number of lessons, useful to inform learning for the IRRP as well as other PF programmes in Indonesia. These are set out below.
There are 11 Prosperity Fund programmes in Indonesia but synergies are not yet being completely realised. There would be many benefits from having an improved cross embassy approach, such as increased sharing of best practice, appearing more joined up with Indonesian stakeholders, and encouraging a more active learning culture across the embassy. The programme would be a beneficiary of these additional benefits if implemented.
- Staying narrow in focus should keep the GoI aligned with the programme and reduce the number of ancillary requests, thereby providing a greater likelihood of the delivery of the programme’s objectives.
- The programme should not underestimate the benefits of having a local resource, including on language and better understanding of cultural nuances. The programme should consider how this might be achieved.
- PF Programmes should not assume that secondary benefits will naturally materialise. There should be a concerted effort to ensure they are realised.
- G&I dimensions of PF intervention may warrant additional research which should be conducted early and be specifically focused on the intervention area and partner country.
- The embassy has a DfID presence so, where possible, they should be seen as a source of advice on delivering ODA. Consulting DfID colleagues in-country on issues such as G&I and how best to engage Indonesian stakeholders would be helpful.

Key actions
- Economic Reform Steering Group to review action implementation
- Share this report with relevant stakeholders

Summary of changes to the logframe since the last annual review
This is the first annual review of the programme. The Theory of Change and logframe will be revised following the review.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Outputs to be generated by the three workstreams are yet to be finalised and will be set out in the revised logframe. Interim outputs and associated indicators were defined to assess performance to date for the purposes of this Annual Review. The selected indicators reflect the early stage of programme implementation

The indicators at this early stage are classified into 3 groups:
1. those relating to the set-up processes;
2. the very early stages of delivery; and
3. governance and learning arrangements.

Output Title	Evidence that programme set-up processes are fit for purpose
Output number per LF			Output Score	A
Risk:		Moderate	Impact weighting (%):	n/a
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Delivery model: right expertise to deliver the interventions and value for money secured and in place	Delivery partner on board. / Regulatory Attaché in post	Both milestones achieved. / The delivery model strikes an appropriate balance between strategic line of sight and flexibility whilst maintaining key relationships. The model is a highly appropriate way to harness UK’s significant expertise in the regulatory reform space. The Regulatory Attaché has a skill set also that is a perfect fit for this programme and her role. Therefore the delivery model is assessed as exceeding expectations. / The programme would benefit from local involvement in the team for cultural, language and local capacity building. / A+
Scoping and design: mapping carried out of the regulatory reform needs against UK best practice and reflected in programme and intervention design	Scoping completed / Inception report approved / Alignment with GoI priorities / Approved ToC and logframe	All milestones achieved, except d. The ToC and logframe have good elements but need further work following this review. As a result, performance against this indicator is rated as moderately less than expectations. / IRRP has defined its niche. The GoI appreciate the UK leadership and expertise in this space and the reforms align well with Presidential priorities. Useful scoping work was conducted by RDI before the start of IRRP and the inception report was approved. Design will continue to adapt to the political economy of engagement in this space in Indonesia. / Programme design delayed by staffing issues, business case processes, election and local ancillary interests / B

Indicator(s)	Milestones	Progress
Partnerships: partnerships and collaborations and synergies formed and consolidated to support programme design and delivery	Key decision makers engaged / MoU signed / Workplan agreed / Range of stakeholders engaged: business, women and vulnerable groups, other donors / Synergies built with other PF Indonesia, other BER programmes, other donor programmes / Events used to build relationships	Performance meets expectations. All milestones were achieved, although some improvements are proposed concerning synergies with other programmes. / Bappenas, CMEA, MoLHR and other line ministries and regulatory agencies are effectively engaged. IRRP is planning wider engagement, following new Cabinet appointments - this will be important. / MoU signed on 12 June 2019. Workplan agreed at first Programme Management Committee (PMC) meeting under the MoU, August 2019. / Regular meetings with stakeholders and other donors. Programme is engaged with KADIN/APINDO, Indonesia Coalition for Women in Business, EuroCham and BritCham, HIPME and reaching out to individual businesses. / More thinking needs to be done on how the PF programmes can amplify each other, particularly to drive secondary benefits realisation. / Seamless coordination between Programme and BEIS through the Regulatory Reform Attaché and RDI. / A

Key Points
The delivery model has been very successful so far and represents good VfM. Having a subject matter expert as Regulatory Reform Attaché, able to combine programme management, engagement and delivery gives consistency and enables IRRP to get the most value out of the UK experts’ time.
In the context of multiple demands from CMEA, it allows the programme to have an ongoing point of contact to maintain relationships with key GoI stakeholders and ensures the programme stays aligned to its strategic line of sight.
The Programme is small but important: it has defined a niche matching GoI Presidential priorities and UK leadership. The GoI appreciate the UK expertise and engagement in this space. ToC and logframe have good elements but need further work following this review.

Recommendations
- ToC and logframe should be revised, as planned, and presented to the Economic Reform Steering Group within the next 3 months. The indicators should be loaded onto Prospero for reporting.
- Programme to consider how to get more local involvement, for cultural, language and capacity building purposes.
- More thinking needed about how the PF programmes can amplify each other, especially on realisation of secondary benefits.
- Consult with other donors to discuss the feasibility of establishing an economic reform donor coordination forum.
Output Title	Early progress with delivery
Output number per LF			Output Score	A+
Risk:			Impact weighting (%):	n/a
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Delivery: Is delivery on track	Delivery on track against workplan	IRRP has successfully launched delivery with all three workstreams underway. While the signing of the MoU was delayed through a combination of staffing issues at post and national elections, the programme is now progressing well. / The workplan was agreed with GoI at first Programme Management Committee meeting, during August 2019. This will be revised annually. However, in view of the ad hoc requests from GoI the workplan needs to be further embedded within GoI. / Workstream 1 / 1st mission, RDM training, planned for end November. Programme is supporting some additional work on use of RDM approach and good policy making thinking in new Guidelines for Public Sector Governance / Workstream 2 / 2 market surveillance missions have been completed. Mapping of market surveillance regime ongoing. / Workstream 3 / 2 licensing/engagement missions completed. Political landscape shifting depending on new Cabinet appointments October 2019. / The new Ministerial appointments are expected during October 2019 which presents opportunities and challenges for progress. The programme team has plans to engage the new stakeholders. / A+

Key Points
Good progress in the short time since the MoU was signed. IRRP events and support have been well received by GoI stakeholders and engagement so far bodes well for successful implementation going forward. The recent request for support concerning the wider use of the RDM approach in relation to the new Guidelines for Public Sector Governance has the potential to influence GoI public sector management more widely. A relationship will need to be built with the new ministerial appointees; the team is aware of this and are already defining steps in relation to this
Recommendations
- Renew GoI stakeholder mapping following new cabinet appointments. Develop a plan for engaging any new interlocutors, e.g. the President’s Office (KSP).
- Deliver the engagement plan using a cross-portfolio narrative that emphasises the specific benefits of this programme and its position in and linkages with wider context of PF in Indonesia. The aim being to gain traction for the programme and make it more bounded from the GoI perspective.

Output Title	Effective programme governance and learning processes
Output number per LF			Output Score	A
Risk:			Impact weighting (%):	n/a
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Leadership & governance: effective oversight mechanisms in place to manage and deliver the outputs and outcomes as set out in the business case	Embassy governance structures established / Management of delivery partner / Oversight structure with GoI / Proportionate monitoring, risk management and reporting mechanisms established / Building blocks in place such as G&I plan, SB plan, sustainability and VfM oversight	Meets expectations in terms of leadership and governance. / Embassy leadership and governance structures are established but could be strengthened and better integrated to drive synergies across PF portfolio. / Commendably the Programme Management Committee is established, involving representation of the GoI. / The following are reported monthly: risk, expenditure & variation against forecast, forecast, milestone delivery and impact on forecast. Quarterly reporting to and through SRO, receiving JFU feedback. However, many central level requirements do not take into account of the size of the programme. For efficiency, it is important for reporting to be proportionate to the size of the programme. / IRRP has started to address the building blocks for G&I and SB plan realisation, sustainability and VfM oversight. This is an opportune time to take this work forward as delivery gathers pace. / A
Learning orientation:	Processes in place to support lesson learning and improvement	IRRP meets expectations in terms of its learning orientation and learning processes in use. / The team is using the PFLearning platform and has reached out to the nascent UK Regulatory Diplomacy Network. / Sharing is underway with other PF programmes in Indonesia. / However there is more still to do on the technical and social (G&I) context in Indonesia and reflecting on these issues in intervention design and delivery. / A

Key Points
The programme has established leadership and governance structures with GoI, within the Embassy and with PFDU/JFU for monitoring and oversight.
Now the programme has moved into delivery, the Embassy structures could strengthen further their governance function and drive more integration across the PF portfolio in Indonesia.
Ongoing consideration by programme governance structures will be needed to drive G&I and SB realisation, sustainability and VfM.

Recommendations
- ToRs should be prepared that allow the Economic Reform Steering Group and Post Programme Board to perform governance and oversight functions more fully. G&I, VfM and SB approaches should be regularly reviewed at these meetings as a way to drive synergies between the PF programmes. More consideration should be given to how the two boards interact. DIT should be represented on both Boards.
- Use the G&I and SB communities, PF Learning and contact with other programme teams in the Business Environment Family to build and share learning
- Seek ways to promote best practice and share lessons learned with other Embassy PF programmes, including through structured PF learning opportunities

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Assessment of whether the programme continues to represent value for money
Although this programme is small, it represents Value-for-Money and this review finds that it is on track to deliver against expectations.
The VfM scorecard assessment (summary attached) rated the programme ‘Amber’ (Adequate evidence). The final business case was signed-off was by HM Ambassador, the SRO. The bespoke delivery model is highly appropriate to implement this programme. The locally based Regulatory Reform Attaché represents strong value-for-money, providing relationship management, continuity and intervention development between missions as well as programme oversight. The individual was able to accelerate (and enable) the signing of the MoU signing, engages in delivery between missions, which supports more effective use of the UK experts, and programme management the post is shared with Global Business Environment programme management, ensuring that synergies are driven between these closely related programmes and avoiding overlaps..
There are potential issues associated with the UK leaving the EU, specifically the availability of RDI staff, but these are being carefully considered and managed by the Attaché in consultation with RDI. As set out in risk mitigation, the RDI has access to a pool of UK experts who are well versed in the UK approach who now work as contractors and are considering how they can draw on the much larger network of local authority experts.
No commercial procurement process was required and this agile programme has been able to start delivery much more quickly than some others. The objectives are clear and the programme can adapt activities to meet government needs and emerging opportunities. Considerable care is being taken to avoid duplication across the PF portfolio and with other donors in this crowded technical space.
The programme has a VfM plan setting out the approach to economy, efficiency and effectiveness as covered below and referencing the G&I plan.
Recommendations
- The logframe and VfM plan will be revised following this review and performance tracked and reported at the Economic Reform Steering Board, thereby further strengthening the VfM oversight.
- The programme should set out selection criteria for new interventions, including VfM and G&I aspects.

Key cost drivers and performance
As a technical assistance programme, the main cost will be the staff time of RDI and the locally engaged Regulatory Reform Attaché.
To date the programme has largely been in set-up phase. Set-up costs included scoping research by local partners, a number of RDI missions to engage with the GoI and stakeholders, workshops to scope delivery areas and activities for the development of the business case. The costs also include the work by the FCO Prosperity Team in 2017-18 and 70% of the Regulatory Reform Attaché appointed from January 2019.
The programme did not have a separate budget/forecast line until April 2019 as it was incorporated within the consolidated Indonesia bilateral programme with the Renewable Energy programme. So we cannot assess previous expenditure against budget. The main difference from expectation was the period of vacancy in the local post. This first annual review has focussed on whether the programme is as well placed as possible to deliver. The next annual review will be able to look in more detail at forecasting and expenditure.
£		2017-18	2018-19
Admin salary cost (local Regulatory Reform post) and recruitment costs	a	346	9,196
Admin meetings and travel costs	b	1,162	936
Platform charge	c	10,002	9,763
Design & scoping: RDI and local partner research	d	41,938	60,535
% Admin in year / Note: The local regulatory Attaché is charged 70% to this programme as an administrative cost. However in practice the role was formulated as, and is, about 75% delivery.	(a+b)/ / (a+b+d)	3.5%	10.8%

Full delivery started in May 2019, just before the signature of the MoU. Expenditure has been largely to plan although some months delay in the MoU signing shifted spend later within the current year. The workplan agreed with GoI in August, sets out the expected number of missions to be conducted by UK staff, the major cost driver.
The staffing of the programme is as expected when the Full Business Case was prepared. The Regulatory Reform Attaché role (70% for this programme) is a combination of programme management/oversight and programme delivery, but the full costs are charged as ‘admin’. The programme expects this ‘admin’ cost to settle to approx. 5% of the full expenditure by the end of the programme.

VfM performance compared to the original VfM proposition in the business case

Economy (are we getting inputs at the right price?)
Different routes to market for the work were considered. The benefits of direct access to UK experts who have a world-leading expertise which is recognised and valued by GoI, and the time saved from not having to launch a commercial process, outweighed the possible benefits of commercial management. The approach also allows the programme to be more responsive to political changes and cuts out a commercial overhead/profit charge. These benefits are already being realised as the GoI is voicing its appreciation of the access to UK experts in this area and has been willing to work with the programme even through the difficult post-election/pre inauguration period.
Cost control is considered in the VFM plan for the programme. Cost containment is also important for team management. In terms of RDI missions, ToRs are prepared in advance of missions. The programme is so small that the programme manager can reasonably assess the RDI time spent on the programme against quarterly invoices. It is recommended that RDI use timesheets for recording and to make this assessment and audit easier.
There is potential for Brexit to affect RDI resource availability. Mitigation is in place but could have a small cost impact because of higher rates for associates who would be contracted to deliver. This is recognised in the risk register but is not forecast to be a significant issue.

Efficiency (how well are we converting inputs into outputs)
Once in country, the Regulatory Reform Attaché was able to accelerate (and enable) the signing of the MoU. The programme expects that it should also help to mitigate any future delay. The role is an efficient use of money, being a locally based role, sharing delivery supporting more effective use of the expert missions, and programme management inputs are shared with the Global Business Environment Programme. RDI have strong incentives to be efficient, and provide good value for money as a part of HMG.
The mode of delivery - meetings and regular contact for influence, supported by expert inputs - is considered an efficient approach and is used by many similar programmes. The programme plans to uses workshops to develop the approach in the local context, followed by piloting including training of trainers so that subsequent roll-out can be carried out by GoI, rather than requiring ongoing direct training by UK experts. This is a positive in terms of VfM
The programme is flexible and adaptive and can move funds between workstreams. This should be a positive in terms of VfM because of the relative ease of adapting and shifting activity towards more effective interventions. However, the governance structure should be strengthened to consider more consistent criteria in selecting activities/interventions, including VfM. It took more time to get to MoU signature than was expected which was inefficient.
There is relatively small exposure to currency fluctuation. The majority of costs are in £ sterling - RDI staff and platform costs. The review recommends that RDI use timesheets to facilitate the audit and verification of costs.

Recommendations

The programme should set out selection criteria for new interventions, including VfM and G&I aspects. Intervention proposals should be presented to the Economic Reform Steering Group for agreement.

Effectiveness (how well are our outputs delivering the desired outcomes?)
The expected primary and secondary financial benefits calculation has been revised since the FBC was signed in October 2018, reflecting a more realistic attribution rate given the small scale of the programme. It was decided that an attribution rate of 1% as opposed to a central attribution rate of 5% should be used.  This results in a projected primary benefits of £79m and secondary benefits of £21m, as opposed to primary benefits of £400m and secondary benefits of £112m. The revision has been approved by the FCO economist unit. The programme is still seen as representing good value for money if these benefits are achieved.
The ToC and logframe will be revised following this review, particularly to articulate better the pathways of change for G&I and secondary benefits. It is too early to fully assess effectiveness as results are not yet being reported. There are no reasons yet to suggest the expected outcome achievements are unrealistic. The assumptions that were identified as underlying the expected outcomes before delivery started still hold and the review has assessed the programme as ‘moderate risk’ overall. The position will become clearer once the new Cabinet is appointed and any structural changes to ministries made clear.
Costs are shared with GoI. The programme uses government rooms when possible, ministries have already sometimes paid for larger rooms for workshops and they pay GoI staff allowances. There is potential for future joint events with other programmes/countries.

Equity
The G&I scorecard assessment concluded that the programme was ‘Amber’ (insufficient evidence of alignment with PF G&I policy). The programme has taken some good steps concerning G&I considerations but further work is needed to mainstream G&I and identify potential opportunities for women and vulnerable groups within the specific activities.
PP and G&I need to be reflected on further in programme design and more consideration is needed in governance and management systems to robustly monitor and manage PP and G&I aims, risks and potential harm. The programme understands this and has already started taking this forward
The programme will commission Indonesia and programme-specific research to inform the development of the interventions to ensure that they are equitable and appropriately consider the impact on women and vulnerable groups. This will be increasingly reflected in the logframe as specific issues are identified.
The programme needs to continue seeking more appropriate consultative platforms to meet women and vulnerable groups. The programme should consider the conduct of impact assessments in terms of impacts on women and vulnerable groups from the different regulatory reforms being supported by the programme.
The VfM scorecard assessment summary is attached.
Recommendations
The programme should consider the conduct of impact assessments in terms of impacts on women and vulnerable groups from the different regulatory reforms being proposed.

Quality of financial management
The delivery partner is within the UK Department for Business Energy and Industrial Strategy (BEIS) and so subject to the full standards and controls of the British Government.
The programme was financially integrated with the Indonesia bilateral Renewable Energy Programme until 31/03/2019. The programme-specific costs have been identified from shared data but there was no separate forecast. The programme re-forecasts monthly and is on track to spend to forecast this year.

E: RISK (1 page)

Overall risk rating: Moderate

Overview of programme risk
The review rates the programme as moderate risk overall. The programme is considering the risks and maintains a comprehensive risk register that looks at both the long term and short term risks. The programme went through a turbulent period with changes in staff but is now much more stable.
The political environment in Indonesia has been febrile for much of this year due to an election in April; with the inauguration of the President later this week, stability should return to Indonesian politics although the appointment of new Ministers and other associated structural changes could present separate challenges. This also provides an impetus for the embassy to deliver a cross portfolio narrative that resonates with Indonesian interlocutors. At the moment, individual programmes present their own narrative but the whole portfolio has the potential to deliver more than the sum of its parts.
It has been difficult for the programme to secure a focussed response from government. The work to develop a better understanding of the scope of regulatory delivery and to encourage coordination of a roadmap for regulatory reform should help maintain the strategic focus of the programme. Meanwhile, the programme should set out its selection criteria for handling the incessant ad hoc requests. The programme is aware of the VfM risk of being drawn into other activities.
The programme has a number of layers of governance and as a whole, they perform adequately. There is a need to strengthen certain parts, notably Post’s Economic Reform Steering Group and Programme Board, so that oversight and scrutiny across the whole portfolio is improved and there is a coherent embassy approach to governance.
The programme also considers the risks emanating from the UK, including availability of RDI staff to engage in IRRP in the light of the UK’s departure from the EU. Plans are in place to mitigate any adverse impact. Within Indonesia, the risk of duplication in what is a crowded donor space has been carefully considered and mitigated through agreed co-ordination with relevant donors.
The uncertainty of GoI rolling out the approach to regulator reform beyond the two regulators directly targeted should be recognised as a VfM risk. The programme is mindful of potential G&I risks around its interventions and is going to commission research to understand the specific context better. This should be recorded in the register.
Secondary benefits have been considered and there is now a need to develop a cross embassy approach to how DIT and other actors can actively promote the realisation of secondary benefits. As all 11 PF programmes in Indonesia begin to focus on secondary benefits, this will put significant pressure on the local DIT team. As this programme has no sectoral focus, it will face an added challenge in engaging business attention. This will need to be managed. Another risk is the challenge to communicate this programme’s intended outcomes to business. The programme should begin promoting its intended outcomes with business as soon as possible. This can include piggybacking on other events.
The programme interventions could be somewhat compromised, or opportunity to be more effective missed, by the lack of Indonesian resource in the team meaning that cultural nuances are missed.

Recommendations from risk assessment
- VfM and sustainability should be more explicitly considered in the risk and mitigation descriptions.
- The programme team is actively considering G&I issues and the work needed to find out more. The risks of acting without better information should be registered.
- Programme should consider ways to get more local involvement to mitigate the risk of missing language and cultural nuances.

F: COMMERCIAL CONSIDERATIONS (1 page)

Delivery against planned timeframe
The annual workplan is agreed between RDI and GoI. Delay to signature of MoU, from staffing issues at Post and the national elections, delayed implementation but the workplan is now agreed and delivery is on track.

Performance of partnership(s)
The delivery model selected is highly appropriate for this programme and there are benefits from dealing with a government partner.
RDI’s presence in Indonesia before the programme start eased the process of scoping and transition to delivery as they already had an understanding of the local context. They are highly respected by the GoI.
The risks are around their resource availability as the UK leaves the EU but RDI has mitigation plans. This should be monitored closely.

Changes in the Delivery Plan
Since the business case, intervention areas have been further specified leading to specification and planning of activities for the year.
No current intention to alter the delivery plan

Asset monitoring and control
The programme is not purchasing any assets.

G: Business Environment (½ page)

How has the business community and business environment responded to the programme?
The programme has met the local Chamber of Commerce and Employers Organisations, a small business representative body, the Women in Business organisation, the UK and European Chambers of Commerce and several businesses. They welcome British support to address these issues. There is broad interest and agreement in the area and they also recognise the difficulty of overcoming vested interests and corruption. The programme intends to engage further as implementation proceeds.
The programme itself is also helping the GoI review its engagement with business and representative groups in the development of its evidence base, understanding of issues and the design of regulatory delivery reforms.

(Where relevant) What role has non-ODA spending played in promoting programme objectives?
None yet.
The review has identified the opportunity for the programme to explore non-ODA funding to help drive the realisation of secondary benefits.

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
Monitoring and Reporting
The programme team has worked closely with MR and E&L teams in the specification of initial versions of the programme logframe and ToC which will serve as programme monitoring tools. Further work is envisaged in the aftermath of this review to further refine both. It is planned to request support from E&L’s locally based team member to provide this input. The Regulatory Attaché has input programme related data onto Prospero and the new logframe indicators will be loaded onto the system once agreed.
Performance progress is discussed at the Economic Reform Steering Group and challenges and issues are raised. Additionally the Regulatory Attaché submits monthly reports to the PFDU and quarterly reports to PFDU and JFU ensuring London based stakeholders are informed of progress with programme implementation.

Evaluation & Learning
E&L support so far has focused on support in ToC and logframe development and input into the 2019 Annual Review for the programme. One member of the Review Team was an independent consultant drawn from E&L who also performs the role of Family Synthesis Lead for the Business Environment Reform family, thereby ensuring some of the results and lessons from the IRR programme can be fed into the family synthesis evaluation. E&L inputs into the 2019 Annual Review included conduct of a thematic workshop on G&I, SBs and VfM which included participation from other PF Indonesia Programme Teams. Additionally E&L supported the moderation of the G&I and VfM scorecards with the Regulatory Attaché. A follow up session with the Regulatory Attaché will be conducted on SB mapping. The specific inputs of E&L into these thematic assessments will be documented in a separate deliverable, which will be shared with the Programme Team and submitted to the JFU for approval.
The IRR programme is learning oriented and has already accessed PFLearning on many occasions. Going forward, it would be useful for the Regulatory Attaché to consult with E&L’s Learning Team in order to discuss learning needs and lesson sharing opportunities.
The evaluation and learning plans for Cycle 2 will be agreed with the Regulatory Attaché following the completion of the 2019 Annual Review.
Annex: VfM scorecard results summary

Key points
The VFM scorecard self-assessment was prepared by the IRRP Programme Team and reviewed by E&L VfM Lead and moderated during a session in Jakarta conducted by E&L and the Regulatory Attaché.
Quality of VfM evidence	Score
No	1
Little	2
Adequate	3
Good	4
Strong	5

Overall performance was rated as adequate in terms of VFM.
Two scorecard dimensions – approach to procurement and cost containment and strategies and measures adopted to enhance delivery and mitigate risk – were rated as green or level 4, indicating good VfM.

In terms of cost containment a number of positives were noted:
- Different routes to market for the work were considered.
- Benefits of direct access to UK experts outweighed benefit of commercial management.
- Approach allows the programme to be more responsive to political changes and cuts out a commercial overhead/profit charge.
- Cost control is considered in the VFM plan for the programme. Cost containment is also important for team management. In terms of RDI missions, ToRs are prepared in advance of missions. RDI’s delivery time is reported on quarterly invoices but should be recorded in timesheets and verified by the Attaché.
- Early evidence of VFM - comparing quotations, using government offices for events, not paying DSA, etc

In terms of strategies and measures to enhance delivery and mitigate risk, evidence reported the following positives in terms of VfM:
- FBC and regular reporting (QRs) considers risks and mitigation. The financial size of the programme means that approvals for the BC can be done by the British Ambassador to Indonesia. This means that the programme’s delivery can be more flexibly managed. There is however a need for more coverage of VfM issues in the risk register.
- There is early evidence of reflection on both opportunities and difficulties in terms of delivery from Economic Reform Steering Group minutes, and mechanisms to escalate as required.
- MoU with GoI signed in June 2019 and there is an annual work planning setting discussion at the Programme Management Committee with GoI representation. The workplan is a living document setting out activities and is updated quarterly, with formal agreement on an annual basis.

Key recommendations emerging from the assessment are presented in the table below.

Annex: G&I scorecard results summary

Programme name	Programme design	Internal capability/ institutional incentives	Financial resources	Accountability mechanisms	Partnerships	Overall score
Indonesia Regulatory Reform	2	2	3	2	2	2.2

Rating scale
1 Not aligned with PF G&I Policy	2 Insufficient evidence of alignment with PF G&I Policy	3 Minimum level of alignment with PF G&I Policy	4 Potential for women and girls’ economic empowerment (Level 3 +)	5 Potential for transformation (Level 3, 4 +)

Key points
- G&I self-assessment was conducted by the Programme Team, reviewed by E&L G&I team and moderated by E&L and the Regulatory Attaché during a mission to Jakarta as part of the Annual Review process. Scorecard results based on availability of evidence to demonstrate the different dimensions.
- The dimensions of the scorecard used for assessment are presented in the table overleaf.
- Some good steps taken by IRRP concerning G&I considerations but further work needed to mainstream G&I and identify the potential barriers and opportunities for women and vulnerable groups.
- PP and G&I need to be reflected on more in design and more consideration required in governance and management systems to robustly monitor and manage PP and G&I aims, risks, and potential harm.
Further work required across the different programming dimensions to bring the programme to minimum level of alignment with the PF G&I policy and guidance (in accordance with the ratings above). The rating of financial resources as pale green or level 3 is due to plan to draw funding for G&I activities from existing budgetary resources and the Programme Team have the flexibility and intention to do so. The team plan to commission G&I specific research on regulatory reforms focused on by the programme covering the Indonesia context and also plan to conduct G&I impact assessments on all interventions to be supported by the programme.