## SourceTable (hidden)
GMPP ID Number | Project Name | AR Year | Quarter | Department | MPA RAG (Departmental RAG used if MPA RAG missing) | Project - Start Date (Latest Approved Start Date) | Project - End Date (Latest Approved End Date) | FY Budget (£m) inc Non Gov | FY Forecast (£m) inc Non Gov | Budget Variance (£m) | Budget Variance (%) | TOTAL BUDGETED WHOLE LIFE COSTS including Non-Government Costs | Gov WLC | Non-Gov WLC | PROJECT CATEGORY | Project Length | Unique ID | Department Grouped | MPA RAG Grouped | Joiner | SRO | Description
BIS_0001_1112-Q1 | BIS Shared Services | AR 2013 | 1213-Q2 | BEIS | Amber | 2011-05-04 | 2013-04-30 | 11.26 | 11.41 |  |  | 15.54 |  |  |  | 1.9904 | BIS_0001_1112-Q1,1213-Q2 | BEIS | Amber | Joiner
BIS_0005_1112-Q1 | Further Education Fee Loans Programme | AR 2013 | 1213-Q2 | BEIS | Amber/Green | 2010-11-30 | 2016-04-01 | 5.452 | 5.452 |  |  | 576.593 |  |  |  | 5.3361 | BIS_0005_1112-Q1,1213-Q2 | BEIS | Amber/Green | Joiner
BIS_0008_1112-Q1 | Student Loans Monetisation Feasibility Study | AR 2013 | 1213-Q2 | BEIS | Amber/Red | 2010-03-01 | 2014-12-31 | 0.12 | 0.12 |  |  | 6.22 |  |  |  | 4.835 | BIS_0008_1112-Q1,1213-Q2 | BEIS | Amber/Red | Joiner
BIS_0009_1112-Q1 | The Francis Crick Institute (formerly UKCMRI) | AR 2013 | 1213-Q2 | BEIS | Amber/Green | 2006-10-01 | 2017-12-21 | 58 | 58 |  |  | 753 |  |  |  | 11.2225 | BIS_0009_1112-Q1,1213-Q2 | BEIS | Amber/Green | Joiner
BIS_0011_1213-Q1 | Core Systems Replacement | AR 2013 | 1213-Q2 | BEIS | Amber | 2012-03-01 | 2016-03-19 | 2.91 | 2.62 |  |  | 131.911 |  |  |  | 4.0493 | BIS_0011_1213-Q1,1213-Q2 | BEIS | Amber | Joiner
BIS_0002_1112-Q1 | Business Improvement Programme | AR 2013 | 1213-Q2 | BEIS | Green | 2010-08-01 | 2013-03-14 | 50.1 | 50.1 |  |  | 206 |  |  |  | 2.6174 | BIS_0002_1112-Q1,1213-Q2 | BEIS | Green | Joiner
BIS_0003_1112-Q1 | Technology and innovation centres | AR 2013 | 1213-Q2 | BEIS | Amber/Green | 2010-12-01 | 2013-04-01 | 60 | 60 |  |  | 476 |  |  |  | 2.3326 | BIS_0003_1112-Q1,1213-Q2 | BEIS | Amber/Green | Joiner
BIS_0004_1112-Q1 | FE Capital Investment Programme | AR 2013 | 1213-Q2 | BEIS | Amber/Green | 2010-05-31 | 2015-03-31 | 272.66 | 272.66 |  |  | 4578.42 |  |  |  | 4.8323 | BIS_0004_1112-Q1,1213-Q2 | BEIS | Amber/Green | Joiner
BIS_0006_1112-Q1 | Green Investment Bank | AR 2013 | 1213-Q2 | BEIS | Amber | 2010-06-01 | 2012-09-01 | 799 | 329 |  |  | 1857 |  |  |  | 2.2533 | BIS_0006_1112-Q1,1213-Q2 | BEIS | Amber | Joiner
BIS_0007_1112-Q1 | HE Reform Programme | AR 2013 | 1213-Q2 | BEIS | Amber | 2011-06-30 | 2015-12-31 | 370 | 370 |  |  | 4600 |  |  |  | 4.5038 | BIS_0007_1112-Q1,1213-Q2 | BEIS | Amber | Joiner
CO_0001_1112-Q1 | Electoral Registration Transformation Programme | AR 2013 | 1213-Q2 | CO | Amber | 2010-03-01 | 2016-01-01 | 5.9 | 5.9 |  |  | 218.227 |  |  |  | 5.8371 | CO_0001_1112-Q1,1213-Q2 | CO | Amber | Joiner
CO_0004_1112-Q1 | National Citizen Service | AR 2013 | 1213-Q2 | CO | Amber | 2011-10-01 | 2014-12-31 | 59.86 | 59.86 |  |  | 324.06 |  |  |  | 3.2498 | CO_0004_1112-Q1,1213-Q2 | CO | Amber | Joiner
CO_0005_1112-Q1 | National Cyber Security Programme | AR 2013 | 1213-Q2 | CO | Amber | 2011-04-01 | 2015-04-01 | 155 | 155 |  |  | 650 |  |  |  | 4 | CO_0005_1112-Q1,1213-Q2 | CO | Amber | Joiner
CO_0006_1112-Q2 | Public Services Network Programme | AR 2013 | 1213-Q2 | CO | Green | 2011-08-31 | 2015-01-30 | 1.05 | 1.05 |  |  | 24.958 |  |  |  | 3.4168 | CO_0006_1112-Q2,1213-Q2 | CO | Green | Joiner
CO_0002_1112-Q1 | G-Cloud Programme (covers Data Centre Consolidation and Application Store) | AR 2013 | 1213-Q2 | CO | Amber/Red | 2011-10-31 | 2015-06-30 | 0.58 | 0.58 |  |  | 0.58 |  |  |  | 3.6632 | CO_0002_1112-Q1,1213-Q2 | CO | Amber/Red | Joiner
DCLG_0005_1112-Q4 | ICTRelet Project (formerly entitled ICTDesktop Refresh) | AR 2013 | 1213-Q2 | DCLG | Amber/Red | 2011-11-16 | 2014-02-28 | 1.9 | 1.9 |  |  | 36.63 |  |  |  | 2.2861 | DCLG_0005_1112-Q4,1213-Q2 | DCLG | Amber/Red | Joiner
DCLG_0006_1112-Q4 | Enterprise Zones Programme | AR 2013 | 1213-Q2 | DCLG | Amber | 2011-03-23 | 2015-03-31 | 0 | 0 |  |  | 0 |  |  |  | 4.0219 | DCLG_0006_1112-Q4,1213-Q2 | DCLG | Amber | Joiner
DCLG_0004_1112-Q1 | Reform of the Audit Commission | AR 2013 | 1213-Q2 | DCLG | Amber | 2011-06-30 | 2012-11-01 | 24.99 | 0.05 |  |  | 53.08 |  |  |  | 1.3415 | DCLG_0004_1112-Q1,1213-Q2 | DCLG | Amber | Joiner
DCLG_0001_1112-Q1 | Housing Investment and Regulatory Reform Programme (HIRRP) | AR 2013 | 1213-Q2 | DCLG | Green | 2011-11-01 | 2012-03-31 | 6.9 | 6.9 |  |  | 25.5 |  |  |  | 0.41342 | DCLG_0001_1112-Q1,1213-Q2 | DCLG | Green | Joiner
DCMS_0001_1112-Q1 | Broadband Delivery Programme | AR 2013 | 1213-Q2 | DCMS | Amber/Red | 2011-05-01 | 2015-03-31 | 91 | 91 |  |  | 529 |  |  |  | 3.9151 | DCMS_0001_1112-Q1,1213-Q2 | DCMS | Amber/Red | Joiner
DCMS_0004_1112-Q1 | The Tate Modern Project | AR 2013 | 1213-Q2 | DCMS | Exempt | 2010-01-01 | 2015-05-01 | 5.3399 | 5.3399 |  |  | 214.997 |  |  |  | 5.3279 | DCMS_0004_1112-Q1,1213-Q2 | DCMS | Exempt | Joiner
DCMS_0005_1112-Q1 | World Conservation and Exhibitions Centre | AR 2013 | 1213-Q2 | DCMS | Amber/Green | 2008-03-31 | 2014-04-01 | 0 | 0 |  |  | 135 |  |  |  | 6.0014 | DCMS_0005_1112-Q1,1213-Q2 | DCMS | Amber/Green | Joiner
DCMS_0006_1112-Q4 | Mobile Infrastructure Project | AR 2013 | 1213-Q2 | DCMS | Amber | 2011-10-03 | 2015-03-31 | 12.5 | 4.5 |  |  | 154.5 |  |  |  | 3.4908 | DCMS_0006_1112-Q4,1213-Q2 | DCMS | Amber | Joiner
DCMS_0007_1112-Q4 | Urban Broadband Fund - Super-connected City Initiative | AR 2013 | 1213-Q2 | DCMS | Amber/Red | 2012-06-26 | 2015-03-31 | 10 | 0 |  |  | 150 |  |  |  | 2.7598 | DCMS_0007_1112-Q4,1213-Q2 | DCMS | Amber/Red | Joiner
DCMS_0003_1112-Q1 | Spectrum Clearance and Awards Programme | AR 2013 | 1213-Q2 | DCMS | Amber | 2011-06-22 | 2014-12-31 | 116.4 | 101.9923 |  |  | 281.2 |  |  |  | 3.5264 | DCMS_0003_1112-Q1,1213-Q2 | DCMS | Amber | Joiner
BIS_0010_1112-Q4 | Urenco Future Options | AR 2013 | 1213-Q2 | BEIS | Exempt | 2010-02-01 | 2013-12-23 | 2.5 | 2.5 |  |  | 11.98 |  |  |  | 3.8905 | BIS_0010_1112-Q4,1213-Q2 | BEIS | Exempt | Joiner
DECC_0003_1112-Q1 | Dounreay Parent Body Organisation (PBO) | AR 2013 | 1213-Q2 | BEIS | Green | 2009-09-21 | 2025-12-31 | 150 | 154.7 |  |  | 1578 |  |  |  | 16.2765 | DECC_0003_1112-Q1,1213-Q2 | BEIS | Green | Joiner
DECC_0004_1112-Q1 | Electricity Market Reform Programme | AR 2013 | 1213-Q2 | BEIS | Exempt | 2010-12-10 | 2030-12-31 | 10.2 | 10.2 |  |  | 40.1 |  |  |  | 20.0575 | DECC_0004_1112-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2013 | 1213-Q2 | BEIS | Exempt | 2011-06-30 | 2040-12-31 | 22 | 22.2 |  |  | 11626.2 |  |  |  | 29.5058 | DECC_0005_1112-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0009_1112-Q1 | Renewable Heat Incentive | AR 2013 | 1213-Q2 | BEIS | Exempt | 2008-11-30 | 2014-02-01 | 108 | 41 |  |  | 33149 |  |  |  | 5.1718 | DECC_0009_1112-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0010_1112-Q1 | Smart Meters Programme | AR 2013 | 1213-Q2 | BEIS | Exempt | 2009-12-02 | 2019-09-23 | 20.1485 | 20.1485 |  |  | 17171.9455 |  |  |  | 9.807 | DECC_0010_1112-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0011_1112-Q3 | Carbon Capture & Storage - Programme | AR 2013 | 1213-Q2 | BEIS | Exempt | 2011-10-25 | 2045-01-01 | 4.9 | 4.9 |  |  | exempt |  |  |  | 33.1882 | DECC_0011_1112-Q3,1213-Q2 | BEIS | Exempt | Joiner
DECC_0012_1213-Q1 | FID Enabling | AR 2013 | 1213-Q2 | BEIS | Exempt | 2011-09-01 | 2013-11-30 | 11.6 | 11 |  |  | 20.92 |  |  |  | 2.2478 | DECC_0012_1213-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | AR 2013 | 1213-Q2 | BEIS | Exempt | 2012-04-20 | 2028-06-30 | 740 | 740 |  |  | 7603 |  |  |  | 16.1944 | DECC_0013_1213-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0008_1112-Q1 | Plutonium Management | AR 2013 | 1213-Q2 | BEIS | Exempt | 2011-05-23 | 2110-03-31 | exempt | exempt |  |  | exempt |  |  |  | 98.8528 | DECC_0008_1112-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0007_1112-Q1 | New Nuclear Programme | AR 2013 | 1213-Q2 | BEIS | Exempt | 2008-01-31 | 2019-12-31 | 2 | 2 |  |  | 40.79 |  |  |  | 11.9151 | DECC_0007_1112-Q1,1213-Q2 | BEIS | Exempt | Joiner
DECC_0006_1112-Q1 | Green Deal | AR 2013 | 1213-Q2 | BEIS | Exempt | 2010-05-20 | 2030-12-31 | 66.5 | 66.5 |  |  | 10304.2 |  |  |  | 20.616 | DECC_0006_1112-Q1,1213-Q2 | BEIS | Exempt | Joiner
DEFRA_0001_1112-Q1 | CAP Delivery Programme (formerly the Future Options Programme) | AR 2013 | 1213-Q2 | DEFRA | Amber | 2011-01-01 | 2015-03-01 | 8.53 | 8.53 |  |  | 13.03 |  |  |  | 4.1615 | DEFRA_0001_1112-Q1,1213-Q2 | DEFRA | Amber | Joiner
DEFRA_0002_1112-Q1 | Covent Garden Market Authority (CGMA) Redevelopment - Project Chrysalis | AR 2013 | 1213-Q2 | DEFRA | Amber | 2008-09-29 | 2018-12-01 | 0 | 0 |  |  | 0 |  |  |  | 10.1711 | DEFRA_0002_1112-Q1,1213-Q2 | DEFRA | Amber | Joiner
DEFRA_0003_1112-Q1 | New Waterways Charity | AR 2013 | 1213-Q2 | DEFRA | Green | 2009-06-01 | 2012-08-31 | 39 | 39 |  |  | 873.72 |  |  |  | 3.2498 | DEFRA_0003_1112-Q1,1213-Q2 | DEFRA | Green | Joiner
DEFRA_0004_1112-Q1 | Thames Estuary 2100 (TE2100) Plan | AR 2013 | 1213-Q2 | DEFRA | Amber | 2010-04-01 | 2024-03-31 | 35 | 32 |  |  | 3082 |  |  |  | 13.9986 | DEFRA_0004_1112-Q1,1213-Q2 | DEFRA | Amber | Joiner
DFE_0003_1112-Q4 | Priority School Building Programme | AR 2013 | 1213-Q2 | DFE | Amber | 2011-07-19 | 2044-08-01 | 4.5 | 4.58 |  |  | 397 |  |  |  | 33.0376 | DFE_0003_1112-Q4,1213-Q2 | DFE | Amber | Joiner
DFE_0001_1112-Q1 | Building Schools for the Future (BSF) | AR 2013 | 1213-Q2 | DFE | Amber/Green | 2011-07-12 | 2017-07-02 | 677 | 677 |  |  | 6302 |  |  |  | 5.974 | DFE_0001_1112-Q1,1213-Q2 | DFE | Amber/Green | Joiner
DFID_0001_1112-Q1 | St Helena Airport | AR 2013 | 1213-Q2 | DFID | Amber/Green | 2005-03-15 | 2026-08-31 | 70.09 | 69.77 |  |  | 423.47 |  |  |  | 21.462 | DFID_0001_1112-Q1,1213-Q2 | DFID | Amber/Green | Joiner
DFT_0001_1112-Q1 | Crossrail | AR 2013 | 1213-Q2 | DFT | Amber/Green | 2008-07-22 | 2019-12-31 | 1206.5 | 1206.5 |  |  | 14510.98 |  |  |  | 11.4415 | DFT_0001_1112-Q1,1213-Q2 | DFT | Amber/Green | Joiner
DFT_0015_1112-Q1 | Shared Services Futures Project | AR 2013 | 1213-Q2 | DFT | Amber/Red | 2010-12-10 | 2014-12-31 | 0.5 | 0.5 |  |  | 3.2 |  |  |  | 4.0575 | DFT_0015_1112-Q1,1213-Q2 | DFT | Amber/Red | Joiner
DFT_0004_1112-Q1 | High Speed Rail Programme | AR 2013 | 1213-Q2 | DFT | Amber/Red | 2011-02-28 | 2033-12-31 | 306.8 | 209 |  |  | 1117.9 |  |  |  | 22.8392 | DFT_0004_1112-Q1,1213-Q2 | DFT | Amber/Red | Joiner
DFT_0006_1112-Q1 | M25 DBFO (Design, Build, Finance and Operate) | AR 2013 | 1213-Q2 | DFT | Green | 2009-05-31 | 2013-07-31 | 99.609 | 74.773 |  |  | 990.749 |  |  |  | 4.167 | DFT_0006_1112-Q1,1213-Q2 | DFT | Green | Joiner
DFT_0007_1112-Q1 | Managed Motorways | AR 2013 | 1213-Q2 | DFT | Amber/Green | 2011-10-31 | 2017-09-30 | 219.1876 | 245.449 |  |  | 1431.2672 |  |  |  | 5.9165 | DFT_0007_1112-Q1,1213-Q2 | DFT | Amber/Green | Joiner
DFT_0008_1112-Q1 | Olympics Transport Programme | AR 2013 | 1213-Q2 | DFT | Green | 2007-09-13 | 2012-12-31 | 24.607 | 24.862 |  |  | 34.488 |  |  |  | 5.3005 | DFT_0008_1112-Q1,1213-Q2 | DFT | Green | Joiner
DFT_0011_1112-Q1 | Rail ReFranchising Management Programme - GA Long | AR 2013 | 1213-Q2 | DFT | Amber/Green | 2012-07-19 | 2015-01-31 | 0 | 0 |  |  | 0 |  |  |  | 2.5352 | DFT_0011_1112-Q1,1213-Q2 | DFT | Amber/Green | Joiner
DFT_0012_1112-Q1 | Rail ReFranchising Management Programme - Greater Anglia Short | AR 2013 | 1213-Q2 | DFT | Green | 2010-06-01 | 2013-02-28 | -144.7 | -154.9 |  |  | -396.7769 |  |  |  | 2.7461 | DFT_0012_1112-Q1,1213-Q2 | DFT | Green | Joiner
DFT_0013_1112-Q1 | Rail ReFranchising Management Programme - West Coast | AR 2013 | 1213-Q2 | DFT | Red | 2010-09-22 | 2014-04-08 | 0 | 0 |  |  | 0 |  |  |  | 3.5428 | DFT_0013_1112-Q1,1213-Q2 | DFT | Red | Joiner
DFT_0017_1213-Q1 | Great Western refranchising | AR 2013 | 1213-Q2 | DFT | Amber | 2011-07-21 | 2015-01-16 | 0 | 0 |  |  | 0 |  |  |  | 3.4908 | DFT_0017_1213-Q1,1213-Q2 | DFT | Amber | Joiner
DFT_0018_1213-Q1 | Thameslink, Southern and Great Northern refranchising project | AR 2013 | 1213-Q2 | DFT | Amber/Red | 2011-10-30 | 2015-02-27 | 0 | 0 |  |  | 0 |  |  |  | 3.3292 | DFT_0018_1213-Q1,1213-Q2 | DFT | Amber/Red | Joiner
DFT_0010_1112-Q1 | Rail ReFranchising Management Programme - East Coast | AR 2013 | 1213-Q2 | DFT | Amber | 2009-07-20 | 2013-05-31 | 0 | 0 |  |  | 0 |  |  |  | 3.8631 | DFT_0010_1112-Q1,1213-Q2 | DFT | Amber | Joiner
DFT_0002_1112-Q1 | DVLA ICTContract Procurement | AR 2013 | 1213-Q2 | DFT | Amber | 2011-03-01 | 2015-09-30 | 6.96 | 3.463 |  |  | 102.06 |  |  |  | 4.5832 | DFT_0002_1112-Q1,1213-Q2 | DFT | Amber | Joiner
DFT_0005_1112-Q1 | Intercity Express Programme (IEP) | AR 2013 | 1213-Q2 | DFT | Amber/Green | 2005-06-01 | 2019-12-31 | 5.86 | 5.86 |  |  | 1288.68 |  |  |  | 14.5818 | DFT_0005_1112-Q1,1213-Q2 | DFT | Amber/Green | Joiner
DFT_0009_1112-Q1 | Periodic Review 2013 (HLOS) | AR 2013 | 1213-Q2 | DFT | Green | 2011-08-31 | 2012-07-31 | 0 | 0 |  |  | 18566.7877 |  |  |  | 0.91718 | DFT_0009_1112-Q1,1213-Q2 | DFT | Green | Joiner
DFT_0014_1112-Q1 | Search & Rescue Helicopters (SARH) | AR 2013 | 1213-Q2 | DFT | Amber | 2011-02-08 | 2017-09-08 | 37 | 37 |  |  | 3286 |  |  |  | 6.5818 | DFT_0014_1112-Q1,1213-Q2 | DFT | Amber | Joiner
DH_0008_1112-Q1 | Electronic Prescription Service (EPS) Release 2 | AR 2013 | 1213-Q2 | DH | Amber/Green | 2003-11-28 | 2014-03-31 | 8.85 | 10.26 |  |  | 36.38 |  |  |  | 10.3381 | DH_0008_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DFT_0016_1112-Q1 | Thameslink | AR 2013 | 1213-Q2 | DFT | Amber/Green | 2005-07-01 | 2018-12-01 | 28.826 | 26.827 |  |  | 5638.256 |  |  |  | 13.4182 | DFT_0016_1112-Q1,1213-Q2 | DFT | Amber/Green | Joiner
DH_0015_1112-Q1 | NME Programme for IT | AR 2013 | 1213-Q2 | DH | Amber | 2004-04-01 | 2016-07-31 | 273.0531 | 405.7482 |  |  | 5636.1923 |  |  |  | 12.3313 | DH_0015_1112-Q1,1213-Q2 | DH | Amber | Joiner
DH_0018_1112-Q1 | Pre-Pandemic Vaccine | AR 2013 | 1213-Q2 | DH | Amber/Green | 2011-10-01 | 2014-07-01 | 0 | 0 |  |  | 0 |  |  |  | 2.7488 | DH_0018_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0003_1112-Q1 | Brighton & Sussex University Hospitals NHS Trust (3Ts Programme - The development of a leading teaching, trauma and tertiary care centre) | AR 2013 | 1213-Q2 | DH | Amber/Green | 2012-05-31 | 2021-12-24 | 26.8 | 54.38 |  |  | 500.8 |  |  |  | 9.5661 | DH_0003_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0004_1112-Q1 | Broadmoor Redevelopment Programme | AR 2013 | 1213-Q2 | DH | Amber/Green | 2011-08-01 | 2018-11-01 | 16.219 | 16.219 |  |  | 256.246 |  |  |  | 7.2526 | DH_0004_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0022_1112-Q1 | Summary Care Record (SCR) | AR 2013 | 1213-Q2 | DH | Amber/Green | 2006-04-01 | 2016-03-31 | 24.87 | 24.17 |  |  | 51.1 |  |  |  | 9.9986 | DH_0022_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0023_1112-Q2 | London Programme for IT | AR 2013 | 1213-Q2 | DH | Amber/Red | 2003-12-18 | 2015-10-19 | 163.35 | 174.67 |  |  | 627.59 |  |  |  | 11.8357 | DH_0023_1112-Q2,1213-Q2 | DH | Amber/Red | Joiner
DH_0026_1112-Q2 | Southern Programme for IT | AR 2013 | 1213-Q2 | DH | Amber/Green | 2004-01-26 | 2015-10-31 | 102.39 | 78.95 |  |  | 634.06 |  |  |  | 11.7618 | DH_0026_1112-Q2,1213-Q2 | DH | Amber/Green | Joiner
DH_0014_1112-Q1 | NHSmail service refresh | AR 2013 | 1213-Q2 | DH | Amber/Green | 2004-10-31 | 2013-06-30 | 7.9 | 22.83 |  |  | 96.05 |  |  |  | 8.6626 | DH_0014_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0010_1112-Q1 | Health and Care Modernisation Transition Programme | AR 2013 | 1213-Q2 | DH | Amber/Red | 2011-10-01 | 2013-04-01 | 699.3 | 699.3 |  |  | 1563.9 |  |  |  | 1.5003 | DH_0010_1112-Q1,1213-Q2 | DH | Amber/Red | Joiner
DH_0012_1112-Q1 | IMS3 | AR 2013 | 1213-Q2 | DH | Green | 2011-05-16 | 2013-03-29 | 70.11 | 55.4 |  |  | 139.38 |  |  |  | 1.87 | DH_0012_1112-Q1,1213-Q2 | DH | Green | Joiner
DH_0005_1112-Q1 | CAB Variation | AR 2013 | 1213-Q2 | DH | Amber/Green | 2011-10-01 | 2013-12-15 | 30.09 | 29.0956 |  |  | 54.24 |  |  |  | 2.2067 | DH_0005_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0024_1112-Q2 | N3 Extension | AR 2013 | 1213-Q2 | DH | Amber | 2004-02-19 | 2014-03-31 | 114.314 | 120.34 |  |  | 371.89 |  |  |  | 10.1109 | DH_0024_1112-Q2,1213-Q2 | DH | Amber | Joiner
DH_0006_1112-Q1 | E &N Herts. NHS Trust - LIFT scheme - new QEII hospital in Welwyn Garden City | AR 2013 | 1213-Q2 | DH | Amber/Green | 2011-03-23 | 2014-04-01 | 0 | 0 |  |  | 70.25 |  |  |  | 3.0253 | DH_0006_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0016_1112-Q1 | Pandemic Vaccine Sleeping Contract | AR 2013 | 1213-Q2 | DH | Green | 2010-04-01 | 2012-06-01 | 0 | 0 |  |  | 0 |  |  |  | 2.1684 | DH_0016_1112-Q1,1213-Q2 | DH | Green | Joiner
DWP_0003_1112-Q1 | Child Maintenance Group Change | AR 2013 | 1213-Q2 | DWP | Amber/Red | 2009-08-01 | 2014-01-29 | 72.5 | 87.35 |  |  | 1203.39 |  |  |  | 4.4956 | DWP_0003_1112-Q1,1213-Q2 | DWP | Amber/Red | Joiner
DWP_0005_1112-Q1 | Enabling Retirement Savings Programme | AR 2013 | 1213-Q2 | DWP | Amber | 2007-05-18 | 2018-10-01 | 112 | 98.8 |  |  | 1004.3 |  |  |  | 11.373 | DWP_0005_1112-Q1,1213-Q2 | DWP | Amber | Joiner
DWP_0009_1112-Q1 | Universal Credit Programme | AR 2013 | 1213-Q2 | DWP | Amber/Red | 2011-11-17 | 2017-12-31 | 386.5 | 378.99 |  |  | 12845.38 |  |  |  | 6.1218 | DWP_0009_1112-Q1,1213-Q2 | DWP | Amber/Red | Joiner
DWP_0011_1112-Q2 | Personal Independence Payment Implementation | AR 2013 | 1213-Q2 | DWP | Amber/Red | 2011-10-31 | 2016-03-31 | 139.43 | 126.72 |  |  | 2771.379 |  |  |  | 4.4162 | DWP_0011_1112-Q2,1213-Q2 | DWP | Amber/Red | Joiner
DWP_0016_1213-Q2 | Fraud and Error Programme | AR 2013 | 1213-Q2 | DWP | Amber/Red | 2012-04-02 | 2015-03-01 | 156.3 | 128.65 |  |  | 770.3 |  |  |  | 2.9103 | DWP_0016_1213-Q2,1213-Q2 | DWP | Amber/Red | Joiner
DWP_0010_1112-Q1 | Work Programme | AR 2013 | 1213-Q2 | DWP | Amber | 2010-11-25 | 2011-10-18 | 735.7 | 777 |  |  | 5626.7 |  |  |  | 0.89528 | DWP_0010_1112-Q1,1213-Q2 | DWP | Amber | Joiner
DWP_0007_1112-Q1 | Incapacity Benefit Reassessment | AR 2013 | 1213-Q2 | DWP | Green | 2009-07-09 | 2012-03-23 | 143.6 | 140.99 |  |  | 891.8 |  |  |  | 2.705 | DWP_0007_1112-Q1,1213-Q2 | DWP | Green | Joiner
DWP_0002_1112-Q1 | Central Payment System | AR 2013 | 1213-Q2 | DWP | Green | 2008-09-01 | 2012-06-21 | 23.5 | 22.315 |  |  | 284.9 |  |  |  | 3.8029 | DWP_0002_1112-Q1,1213-Q2 | DWP | Green | Joiner
DWP_0012_1112-Q4 | Benefit Cap | AR 2013 | 1213-Q2 | DWP | Amber/Red | 2012-04-19 | 2013-07-31 | 28.53 | 27 |  |  | 49.03 |  |  |  | 1.2813 | DWP_0012_1112-Q4,1213-Q2 | DWP | Amber/Red | Joiner
DWP_0015_1112-Q4 | Youth Contract | AR 2013 | 1213-Q2 | DWP | Green | 2012-01-19 | 2012-06-21 | 139.97 | 182.04 |  |  | 741.93 |  |  |  | 0.42163 | DWP_0015_1112-Q4,1213-Q2 | DWP | Green | Joiner
DWP_0013_1112-Q4 | Specialist Disability Employment Programme | AR 2013 | 1213-Q2 | DWP | Amber | 2012-02-16 | 2014-07-31 | 33.52 | 35.63 |  |  | 202.98 |  |  |  | 2.4531 | DWP_0013_1112-Q4,1213-Q2 | DWP | Amber | Joiner
DWP_0014_1112-Q4 | State Pension Reform - Single Tier | AR 2013 | 1213-Q2 | DWP | Amber/Green | 2012-02-27 | 2017-10-31 | 2.7 | 1.12 |  |  | 114.16 |  |  |  | 5.6756 | DWP_0014_1112-Q4,1213-Q2 | DWP | Amber/Green | Joiner
DH_0007_1112-Q1 | E & N Herts NHS Trust - Lister Hospital ('Our Changing Hospitals' Phase 4 Programme) | AR 2013 | 1213-Q2 | DH | Amber/Red | 2011-08-04 | 2014-01-17 | 28.43 | 21.493 |  |  | 201.52 |  |  |  | 2.4559 | DH_0007_1112-Q1,1213-Q2 | DH | Amber/Red | Joiner
FCO_0004_1112-Q1 | Prism and Firecrest Re-procurement Programme | AR 2013 | 1213-Q2 | FCO | Amber | 2011-01-01 | 2013-11-30 | 0 | 0 |  |  | 0 |  |  |  | 2.9131 | FCO_0004_1112-Q1,1213-Q2 | FCO | Amber | Joiner
DH_0013_1112-Q1 | Mersey Care NHS LIFT scheme (TIME - To Improve Mental health Environments) | AR 2013 | 1213-Q2 | DH | Amber/Green | 2011-08-30 | 2015-01-20 | 0 | 0 |  |  | 208.8 |  |  |  | 3.3922 | DH_0013_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
FCO_0002_1112-Q1 | Echo | AR 2013 | 1213-Q2 | FCO | Amber/Green | 2009-06-09 | 2012-12-31 | 29.96 | 32.07 |  |  | 179.19 |  |  |  | 3.5619 | FCO_0002_1112-Q1,1213-Q2 | FCO | Amber/Green | Joiner
FCO_0003_1112-Q1 | JAKARTA: New Embassy | AR 2013 | 1213-Q2 | FCO | Amber/Green | 2004-04-01 | 2014-09-01 | 11.06 | 11.06 |  |  | 29.45 |  |  |  | 10.4175 | FCO_0003_1112-Q1,1213-Q2 | FCO | Amber/Green | Joiner
FCO_0005_1112-Q1 | TEL AVIV: Embassy Upgrade | AR 2013 | 1213-Q2 | FCO | Green | 2009-10-28 | 2013-11-01 | 3.82 | 2.62 |  |  | 21.5 |  |  |  | 4.011 | FCO_0005_1112-Q1,1213-Q2 | FCO | Green | Joiner
HMRC_0002_1112-Q1 | Debt Management & Banking (DMB) Staff Reinvestment | AR 2013 | 1213-Q2 | HMRC | Amber/Green | 2011-04-01 | 2015-04-01 | 11.257 | 11.27 |  |  | 56.414 |  |  |  | 4 | HMRC_0002_1112-Q1,1213-Q2 | HMRC | Amber/Green | Joiner
HMRC_0004_1112-Q1 | One Click | AR 2013 | 1213-Q2 | HMRC | Amber/Red | 2010-03-24 | 2013-04-10 | 10.014 | 26.04 |  |  | 113.18 |  |  |  | 3.0472 | HMRC_0004_1112-Q1,1213-Q2 | HMRC | Amber/Red | Joiner
HMRC_0006_1112-Q1 | Real Time Information (RTI) | AR 2013 | 1213-Q2 | HMRC | Amber | 2010-07-05 | 2014-10-31 | 28.32 | 28.32 |  |  | 241.1 |  |  |  | 4.3231 | HMRC_0006_1112-Q1,1213-Q2 | HMRC | Amber | Joiner
HMRC_0007_1112-Q2 | Expanding the use of Debt Collection Agencies | AR 2013 | 1213-Q2 | HMRC | Amber/Green | 2011-04-01 | 2015-03-31 | 20.145 | 18.695 |  |  | 70.678 |  |  |  | 3.9973 | HMRC_0007_1112-Q2,1213-Q2 | HMRC | Amber/Green | Joiner
HMRC_0008_1112-Q2 | Organised Crime | AR 2013 | 1213-Q2 | HMRC | Amber/Green | 2011-04-01 | 2012-07-02 | 25.42 | 25.21 |  |  | 82.73 |  |  |  | 1.2539 | HMRC_0008_1112-Q2,1213-Q2 | HMRC | Amber/Green | Joiner
HMRC_0009_1112-Q2 | Volume Crime | AR 2013 | 1213-Q2 | HMRC | Amber/Green | 2011-04-01 | 2013-03-31 | 11.201 | 11.08 |  |  | 42.038 |  |  |  | 1.9986 | HMRC_0009_1112-Q2,1213-Q2 | HMRC | Amber/Green | Joiner
HMRC_0003_1112-Q1 | Electronic Exchange of Social Security Information (EESSI) Programme | AR 2013 | 1213-Q2 | HMRC | Amber/Green | 2009-12-02 | 2014-05-31 | 0.12 | 0.12 |  |  | 5.288 |  |  |  | 4.4928 | HMRC_0003_1112-Q1,1213-Q2 | HMRC | Amber/Green | Joiner
HMRC_0010_1112-Q2 | Wider Coverage Project | AR 2013 | 1213-Q2 | HMRC | Amber | 2011-09-14 | 2015-06-30 | 104.738 | 103.7726 |  |  | 552.592 |  |  |  | 3.7919 | HMRC_0010_1112-Q2,1213-Q2 | HMRC | Amber | Joiner
HMRC_0005_1112-Q1 | Open Cases Programme | AR 2013 | 1213-Q2 | HMRC | Green | 2010-10-31 | 2012-10-31 | 19.43 | 19.43 |  |  | 57.28 |  |  |  | 2.0014 | HMRC_0005_1112-Q1,1213-Q2 | HMRC | Green | Joiner
HMT_0001_1112-Q1 | Equitable Life Payment Scheme | AR 2013 | 1213-Q2 | HMT | Amber/Red | 2010-05-01 | 2014-04-01 | 0 | 0 |  |  | 0 |  |  |  | 3.9179 | HMT_0001_1112-Q1,1213-Q2 | HMT | Amber/Red | Joiner
HMT_0002_1112-Q1 | Project OSCAR | AR 2013 | 1213-Q2 | HMT | Amber | 2011-08-24 | 2013-02-07 | 4.71 | 4.668 |  |  | 19.56 |  |  |  | 1.4593 | HMT_0002_1112-Q1,1213-Q2 | HMT | Amber | Joiner
HO_0007_1112-Q1 | SOCA Information Systems and Operating Technology (ISOT) Programme | AR 2013 | 1213-Q2 | HO | Amber/Red | 2008-04-01 | 2013-09-30 | 43.71 | 44.54 |  |  | 398.6 |  |  |  | 5.4976 | HO_0007_1112-Q1,1213-Q2 | HO | Amber/Red | Joiner
HO_0008_1112-Q1 | Schengen Information Systems (SIS) II Programme | AR 2013 | 1213-Q2 | HO | Amber | 2006-04-01 | 2015-03-31 | 11.855 | 14.48 |  |  | 168.165 |  |  |  | 8.9966 | HO_0008_1112-Q1,1213-Q2 | HO | Amber | Joiner
HO_0009_1112-Q1 | Transforming the Customer Experience (Formerly A&E) | AR 2013 | 1213-Q2 | HO | Red | 2007-05-14 | 2012-03-31 | 46.72 | 50.01 |  |  | 424.29 |  |  |  | 4.8816 | HO_0009_1112-Q1,1213-Q2 | HO | Red | Joiner
HO_0011_1112-Q2 | SIG Disclosure & Barring Service Programme (formerly Convergence Programme) | AR 2013 | 1213-Q2 | HO | Amber | 2010-12-29 | 2015-10-01 | 127.43 | 5.92 |  |  | 709.77 |  |  |  | 4.7556 | HO_0011_1112-Q2,1213-Q2 | HO | Amber | Joiner
HO_0012_1112-Q3 | Communications Capabilities Development programme | AR 2013 | 1213-Q2 | HO | Amber | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 | HO_0012_1112-Q3,1213-Q2 | HO | Amber | Joiner
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2013 | 1213-Q2 | HO | Exempt | 2011-06-01 | 2020-12-31 | 0 | 0 |  |  | 0 |  |  |  | 9.5852 | HO_0016_1213-Q1,1213-Q2 | HO | Exempt | Joiner
HO_0023_1213-Q1 | Next Generation Outsourced Visa Services Contract (P098) | AR 2013 | 1213-Q2 | HO | Amber/Green | 2011-12-09 | 2014-07-01 | 0 | 0 |  |  | 0 |  |  |  | 2.5599 | HO_0023_1213-Q1,1213-Q2 | HO | Amber/Green | Joiner
HO_0025_1213-Q2 | Harmondsworth and Colnbrook Retender (P110) | AR 2013 | 1213-Q2 | HO | Green | 2012-02-26 | 2014-08-31 | 0 | 0 |  |  | 0 |  |  |  | 2.5106 | HO_0025_1213-Q2,1213-Q2 | HO | Green | Joiner
HO_0004_1112-Q1 | Immigration and Asylum Biometric System (IABS) | AR 2013 | 1213-Q2 | HO | Amber/Green | 2006-10-01 | 2012-12-31 | 24.69 | 27.7 |  |  | 367.1489 |  |  |  | 6.2505 | HO_0004_1112-Q1,1213-Q2 | HO | Amber/Green | Joiner
HO_0019_1213-Q1 | IMPACT | AR 2013 | 1213-Q2 | HO | Amber | 2004-04-01 | 2012-03-31 | 5.93 | 5.93 |  |  | 184.84 |  |  |  | 7.9973 | HO_0019_1213-Q1,1213-Q2 | HO | Amber | Joiner
HO_0001_1112-Q1 | Commercial and Operating Managers Procuring Asylum Support Services (COMPASS) | AR 2013 | 1213-Q2 | HO | Amber/Green | 2009-07-01 | 2011-09-30 | 54.38 | 54.3541 |  |  | 686.7 |  |  |  | 2.2478 | HO_0001_1112-Q1,1213-Q2 | HO | Amber/Green | Joiner
HO_0026_1213-Q2 | National Crime Agency (NCA) | AR 2013 | 1213-Q2 | HO | Amber | 2011-06-08 | 2013-10-01 | 424.85 | 424.85 |  |  | 1687.29 |  |  |  | 2.3162 | HO_0026_1213-Q2,1213-Q2 | HO | Amber | Joiner
HO_0003_1112-Q1 | eBorders | AR 2013 | 1213-Q2 | HO | Amber | 2011-10-26 | 2014-08-01 | 0 | 0 |  |  | 0 |  |  |  | 2.7652 | HO_0003_1112-Q1,1213-Q2 | HO | Amber | Joiner
HO_0005_1112-Q1 | Immigration Case Work (ICW) | AR 2013 | 1213-Q2 | HO | Amber/Red | 2007-06-25 | 2013-07-30 | 59.9685 | 59.9685 |  |  | 374 |  |  |  | 6.0972 | HO_0005_1112-Q1,1213-Q2 | HO | Amber/Red | Joiner
HO_0014_1213-Q1 | SOCA Catalyst | AR 2013 | 1213-Q2 | HO | Amber/Green | 2010-06-01 | 2012-09-30 | 6.738 | 6.738 |  |  | 216.696 |  |  |  | 2.3326 | HO_0014_1213-Q1,1213-Q2 | HO | Amber/Green | Joiner
HO_0015_1213-Q1 | College of Policing project (formerly Police Professional Body Project) | AR 2013 | 1213-Q2 | HO | Amber | 2011-10-01 | 2012-12-30 | 56.1 | 56.1 |  |  | 202.8 |  |  |  | 1.2485 | HO_0015_1213-Q1,1213-Q2 | HO | Amber | Joiner
HO_0017_1213-Q1 | Escorting and Travel | AR 2013 | 1213-Q2 | HO | Green | 2008-07-01 | 2011-06-01 | 74.8844 | 79.17 |  |  | 283.5644 |  |  |  | 2.9158 | HO_0017_1213-Q1,1213-Q2 | HO | Green | Joiner
HO_0018_1213-Q1 | Extend and Blend | AR 2013 | 1213-Q2 | HO | Green | 2009-10-01 | 2012-04-30 | 69.98 | 66.23 |  |  | 503.3 |  |  |  | 2.5791 | HO_0018_1213-Q1,1213-Q2 | HO | Green | Joiner
HO_0022_1213-Q1 | New Passport Programme | AR 2013 | 1213-Q2 | HO | Green | 2008-03-01 | 2012-11-01 | 45.71 | 45.27 |  |  | 455.95 |  |  |  | 4.6708 | HO_0022_1213-Q1,1213-Q2 | HO | Green | Joiner
HO_0024_1213-Q1 | Police ICTCompany Programme | AR 2013 | 1213-Q2 | HO | Amber | 2011-09-01 | 2012-08-31 | 0 | 0 |  |  | 0 |  |  |  | 0.99932 | HO_0024_1213-Q1,1213-Q2 | HO | Amber | Joiner
MOD_0001_1112-Q1 | A400M | AR 2013 | 1213-Q2 | MOD | Amber | 2000-05-17 | 2046-12-31 | 189.77 | 189.77 |  |  | 0 |  |  |  | 46.6229 | MOD_0001_1112-Q1,1213-Q2 | MOD | Amber | Joiner
MOD_0004_1112-Q1 | Airseeker | AR 2013 | 1213-Q2 | MOD | Amber/Green | 2010-03-18 | 2018-04-01 | 110.492 | 128.878 |  |  | 1271.121 |  |  |  | 8.0383 | MOD_0004_1112-Q1,1213-Q2 | MOD | Amber/Green | Joiner
MOD_0009_1112-Q1 | BORONA | AR 2013 | 1213-Q2 | MOD | Amber | 2006-08-01 | 2019-03-01 | 31.17 | 30.39 |  |  | 1151.3 |  |  |  | 12.5804 | MOD_0009_1112-Q1,1213-Q2 | MOD | Amber | Joiner
MOD_0017_1112-Q1 | CROWSNEST | AR 2013 | 1213-Q2 | MOD | Exempt | 2013-03-31 | 2022-09-30 | 3.5 | 2 |  |  | 0 |  |  |  | 9.5003 | MOD_0017_1112-Q1,1213-Q2 | MOD | Exempt | Joiner
MOD_0019_1112-Q1 | Defence Information Infrastructure | AR 2013 | 1213-Q2 | MOD | Amber/Red | 2001-09-01 | 2015-03-31 | 850.24 | 831.4 |  |  | 7331.72 |  |  |  | 13.577 | MOD_0019_1112-Q1,1213-Q2 | MOD | Amber/Red | Joiner
MOD_0033_1112-Q1 | MARSHALL | AR 2013 | 1213-Q2 | MOD | Exempt | 2006-04-01 | 2035-03-31 | 2.019 | 1.13 |  |  | 0 |  |  |  | 28.9966 | MOD_0033_1112-Q1,1213-Q2 | MOD | Exempt | Joiner
MOD_0035_1112-Q1 | Merlin Capability Sustainment Programme (MCSP) | AR 2013 | 1213-Q2 | MOD | Green | 2003-06-01 | 2016-10-01 | 87.9 | 87.9 |  |  | 796.44 |  |  |  | 13.3361 | MOD_0035_1112-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0036_1112-Q1 | Military Afloat Reach and Sustainability | AR 2013 | 1213-Q2 | MOD | Green | 2005-07-25 | 2019-06-30 | 52.3 | 52.3 |  |  | 1860.203 |  |  |  | 13.9302 | MOD_0036_1112-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2013 | 1213-Q2 | MOD | Exempt | 2008-04-01 | 2025-04-30 | 906.277 | 907.611 |  |  | 12139.3 |  |  |  | 17.0787 | MOD_0038_1112-Q1,1213-Q2 | MOD | Exempt | Joiner
MOD_0040_1112-Q1 | Puma Helicopter Life Extension Programme | AR 2013 | 1213-Q2 | MOD | Amber | 2009-09-30 | 2014-10-31 | 97.82 | 89.8 |  |  | 279.279 |  |  |  | 5.0842 | MOD_0040_1112-Q1,1213-Q2 | MOD | Amber | Joiner
MOD_0042_1112-Q1 | QEC Aircraft Carriers | AR 2013 | 1213-Q2 | MOD | Red | 1998-12-01 | 2018-12-01 | 657.723 | 658.5 |  |  | 0 |  |  |  | 20 | MOD_0042_1112-Q1,1213-Q2 | MOD | Red | Joiner
MOD_0047_1112-Q1 | Spearfish Upgrade (SFU) | AR 2013 | 1213-Q2 | MOD | Exempt | 2010-04-30 | 2022-12-31 | 23 | 23 |  |  | 0 |  |  |  | 12.6708 | MOD_0047_1112-Q1,1213-Q2 | MOD | Exempt | Joiner
MOD_0055_1112-Q1 | Type 26 Global Combat Ship (T26 GCS) (P900005700) | AR 2013 | 1213-Q2 | MOD | Exempt | 2008-07-21 | 0 | 62.94 | 57.8 |  |  | 0 |  |  |  | -108.5558 | MOD_0055_1112-Q1,1213-Q2 | MOD | Exempt | Joiner
MOD_0057_1112-Q1 | Typhoon | AR 2013 | 1213-Q2 | MOD | Amber/Green | 2003-06-01 | 2018-04-10 | 827.793 | 863.68 |  |  | 18251.9759 |  |  |  | 14.8583 | MOD_0057_1112-Q1,1213-Q2 | MOD | Amber/Green | Joiner
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2013 | 1213-Q2 | MOD | Red | 1998-03-01 | 2040-12-31 | 91.375 | 59.159 |  |  | 1079.076 |  |  |  | 42.8364 | MOD_0061_1112-Q1,1213-Q2 | MOD | Red | Joiner
MOD_0062_1112-Q1 | Wildcat | AR 2013 | 1213-Q2 | MOD | Amber | 2001-12-01 | 2046-03-31 | 209.02 | 203.88 |  |  | 1661.368 |  |  |  | 44.3285 | MOD_0062_1112-Q1,1213-Q2 | MOD | Amber | Joiner
MOD_0065_1112-Q2 | Chinook (incl. project Julius) | AR 2013 | 1213-Q2 | MOD | Amber | 2008-04-01 | 2017-03-31 | 139.98 | 153 |  |  | 1185.51 |  |  |  | 8.9966 | MOD_0065_1112-Q2,1213-Q2 | MOD | Amber | Joiner
MOD_0067_1112-Q2 | Defence Core Network Services | AR 2013 | 1213-Q2 | MOD | Red | 2009-12-01 | 2020-03-01 | 18 | 13.79 |  |  | 5051.05 |  |  |  | 10.2478 | MOD_0067_1112-Q2,1213-Q2 | MOD | Red | Joiner
MOD_0069_1112-Q2 | Logistics Commodities Services Transformation | AR 2013 | 1213-Q2 | MOD | Amber | 2011-08-01 | 2018-02-01 | 8.36 | 8.36 |  |  | 2056.19 |  |  |  | 6.5051 | MOD_0069_1112-Q2,1213-Q2 | MOD | Amber | Joiner
MOD_0070_1112-Q2 | New Employment Model | AR 2013 | 1213-Q2 | MOD | Amber | 2011-05-03 | 2021-10-01 | 0 | 0 |  |  | 0 |  |  |  | 10.4148 | MOD_0070_1112-Q2,1213-Q2 | MOD | Amber | Joiner
MOD_0071_1112-Q2 | Submarine Enterprise Performance Programme | AR 2013 | 1213-Q2 | MOD | Amber | 2010-05-01 | 2014-03-01 | 0 | 0 |  |  | 0 |  |  |  | 3.833 | MOD_0071_1112-Q2,1213-Q2 | MOD | Amber | Joiner
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2013 | 1213-Q2 | MOD | Amber | 1997-03-17 | 2024-03-31 | 557.298 | 553.26 |  |  | 9947.224 |  |  |  | 27.039 | MOD_0076_1213-Q1,1213-Q2 | MOD | Amber | Joiner
MOD_0077_1213-Q1 | Complex Weapons | AR 2013 | 1213-Q2 | MOD | Amber | 2008-06-11 | 0 | 254.72 | 254.72 |  |  | 3624.05 |  |  |  | -108.4463 | MOD_0077_1213-Q1,1213-Q2 | MOD | Amber | Joiner
MOD_0078_1213-Q1 | Core Production Capability | AR 2013 | 1213-Q2 | MOD | Green | 2012-04-01 | 2023-03-19 | 115 | 75 |  |  | 0 |  |  |  | 10.9624 | MOD_0078_1213-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0079_1213-Q1 | Joint Combat Aircraft | AR 2013 | 1213-Q2 | MOD | Amber/Green | 2001-10-01 | 2050-03-31 | 192.497 | 163.302 |  |  | 15979.1603 |  |  |  | 48.4956 | MOD_0079_1213-Q1,1213-Q2 | MOD | Amber/Green | Joiner
MOD_0080_1213-Q1 | Successor SSBN 1, 2 & 3 | AR 2013 | 1213-Q2 | MOD | Exempt | 2011-04-14 | 0 | 410.28 | 413.283 |  |  | 0 |  |  |  | -111.2854 | MOD_0080_1213-Q1,1213-Q2 | MOD | Exempt | Joiner
MOD_0081_1213-Q2 | Future Reserves 2020 | AR 2013 | 1213-Q2 | MOD | Amber | 2011-09-01 | 2018-03-01 | 0 | 0 |  |  | 0 |  |  |  | 6.4969 | MOD_0081_1213-Q2,1213-Q2 | MOD | Amber | Joiner
MOD_0056_1112-Q1 | Type 45 Destroyers | AR 2013 | 1213-Q2 | MOD | Green | 2000-08-15 | 2014-07-31 | 252.2388 | 146.86 |  |  | 0 |  |  |  | 13.9576 | MOD_0056_1112-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0020_1112-Q1 | Defence Infrastructure Transformation Programme | AR 2013 | 1213-Q2 | MOD | Amber | 2011-01-11 | 2015-03-01 | 37.86 | 37.86 |  |  | 124.55 | GMPP ID Number |  |  | 4.1342 | MOD_0020_1112-Q1,1213-Q2 | MOD | Amber | Joiner
MOD_0016_1112-Q1 | Corporate Services Transformation Programme | AR 2013 | 1213-Q2 | MOD | Amber/Green | 2010-07-01 | 2016-12-01 | 7.4 | 9.01 |  |  | 38.4 |  |  |  | 6.4203 | MOD_0016_1112-Q1,1213-Q2 | MOD | Amber/Green | Joiner
MOD_0008_1112-Q1 | Beyond Visual Range Air-to-Air Missile (Meteor) | AR 2013 | 1213-Q2 | MOD | Green | 1995-10-20 | 2019-12-01 | 60.87 | 60.87 |  |  | 1185.34 |  |  |  | 24.115 | MOD_0008_1112-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0013_1112-Q1 | CIPHER | AR 2013 | 1213-Q2 | MOD | Exempt | 2007-07-10 | 2031-07-31 | 0 | 0 |  |  | 0 |  |  |  | 24.0575 | MOD_0013_1112-Q1,1213-Q2 | MOD | Exempt | Joiner
MOD_0023_1112-Q1 | Falcon - 02 (Increments A & C amalgamated at 1/4/11) | AR 2013 | 1213-Q2 | MOD | Green | 1998-01-01 | 2035-03-31 | 29.02 | 29.02 |  |  | 1467.044 |  |  |  | 37.243 | MOD_0023_1112-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0048_1112-Q1 | Specialist Vehicles - Recce Block 1 | AR 2013 | 1213-Q2 | MOD | Green | 2009-12-16 | 0 | 147.291 | 132.78 |  |  | 0 |  |  |  | -109.9603 | MOD_0048_1112-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0060_1112-Q1 | Warrior Capability Sustainment Programme | AR 2013 | 1213-Q2 | MOD | Green | 2011-10-31 | 2022-03-01 | 49.0072 | 66.51 |  |  | 1667.0416 |  |  |  | 10.3326 | MOD_0060_1112-Q1,1213-Q2 | MOD | Green | Joiner
MOD_0022_1112-Q1 | End Crypto Units (ECU) | AR 2013 | 1213-Q2 | MOD | Exempt | 2007-08-31 | 2040-08-31 | 0 | 0 |  |  | 0 |  |  |  | 33.0021 | MOD_0022_1112-Q1,1213-Q2 | MOD | Exempt | Joiner
MOJ_0002_1112-Q1 | Court Estates Reform | AR 2013 | 1213-Q2 | MOJ | Green | 2010-05-10 | 2014-09-30 | 9.56 | 14.26 |  |  | 45.44 |  |  |  | 4.3915 | MOJ_0002_1112-Q1,1213-Q2 | MOJ | Green | Joiner
MOJ_0003_1112-Q1 | Electronic Monitoring | AR 2013 | 1213-Q2 | MOJ | Amber | 2011-05-10 | 2013-09-30 | 0.99 | 0.99 |  |  | 891.96 |  |  |  | 2.3929 | MOJ_0003_1112-Q1,1213-Q2 | MOJ | Amber | Joiner
MOJ_0004_1112-Q1 | Future IT Sourcing Programme (FITS) | AR 2013 | 1213-Q2 | MOJ | Amber | 2011-03-01 | 2014-12-31 | 22.1 | 22.1 |  |  | 138.5 |  |  |  | 3.8357 | MOJ_0004_1112-Q1,1213-Q2 | MOJ | Amber | Joiner
MOJ_0005_1112-Q1 | Court Fines Compliance & Enforcement Project | AR 2013 | 1213-Q2 | MOJ | Amber | 2010-08-31 | 2014-02-01 | 4.5 | 2.5 |  |  | 8.6 |  |  |  | 3.4223 | MOJ_0005_1112-Q1,1213-Q2 | MOJ | Amber | Joiner
MOJ_0006_1112-Q1 | Integrated Delivery Programme | AR 2013 | 1213-Q2 | MOJ | Amber/Green | 2009-07-01 | 2013-10-30 | 13.59 | 13.59 |  |  | 73.89 |  |  |  | 4.3313 | MOJ_0006_1112-Q1,1213-Q2 | MOJ | Amber/Green | Joiner
MOJ_0007_1112-Q1 | Legal Aid Reform Implementation | AR 2013 | 1213-Q2 | MOJ | Amber/Green | 2011-04-01 | 2013-10-31 | 9.623 | 9.623 |  |  | 19.858 |  |  |  | 2.5845 | MOJ_0007_1112-Q1,1213-Q2 | MOJ | Amber/Green | Joiner
MOJ_0008_1112-Q1 | MoJ Shared Services | AR 2013 | 1213-Q2 | MOJ | Red | 2009-07-01 | 2013-06-07 | 42.94 | 58.94 |  |  | 127.09 |  |  |  | 3.9343 | MOJ_0008_1112-Q1,1213-Q2 | MOJ | Red | Joiner
MOJ_0015_1112-Q2 | Quantum Re-compete Project | AR 2013 | 1213-Q2 | MOJ | Amber | 2011-07-18 | 2012-11-30 | 103.73 | 103.73 |  |  | 156.97 |  |  |  | 1.3717 | MOJ_0015_1112-Q2,1213-Q2 | MOJ | Amber | Joiner
MOJ_0018_1112-Q2 | Prison Competitions Phase Two | AR 2013 | 1213-Q2 | MOJ | Amber | 2011-07-13 | 2014-01-31 | 4.31 | 4.31 |  |  | 2403.99 |  |  |  | 2.5544 | MOJ_0018_1112-Q2,1213-Q2 | MOJ | Amber | Joiner
MOJ_0021_1213-Q2 | NOMS Organisational Restructure Programme | AR 2013 | 1213-Q2 | MOJ | Green | 2010-11-01 | 2013-10-31 | 4.0313 | 4.0313 |  |  | 37.9816 |  |  |  | 2.9979 | MOJ_0021_1213-Q2,1213-Q2 | MOJ | Green | Joiner
MOJ_0020_1213-Q2 | National Offender Management Information Systems (NOMIS) Programme | AR 2013 | 1213-Q2 | MOJ | Amber | 2008-01-08 | 2013-10-31 | 8 | 40 |  |  | 444 |  |  |  | 5.8125 | MOJ_0020_1213-Q2,1213-Q2 | MOJ | Amber | Joiner
MOJ_0009_1112-Q1 | Prison Competitions Phase One | AR 2013 | 1213-Q2 | MOJ | Amber/Green | 2009-04-01 | 2012-05-31 | 59.63 | 59.63 |  |  | 878.705 |  |  |  | 3.165 | MOJ_0009_1112-Q1,1213-Q2 | MOJ | Amber/Green | Joiner
MOJ_0010_1112-Q1 | Prison Escort and Custody Services Re-competition | AR 2013 | 1213-Q2 | MOJ | Green | 2009-07-01 | 2012-02-28 | 136.7763 | 136.7763 |  |  | 1029.2069 |  |  |  | 2.6612 | MOJ_0010_1112-Q1,1213-Q2 | MOJ | Green | Joiner
MOJ_0011_1112-Q1 | Property Services and Works | AR 2013 | 1213-Q2 | MOJ | Amber/Green | 2010-02-01 | 2015-09-01 | 155 | 155 |  |  | 966 |  |  |  | 5.5797 | MOJ_0011_1112-Q1,1213-Q2 | MOJ | Amber/Green | Joiner
MOJ_0013_1112-Q2 | Capacity Management Portfolio (CMP) | AR 2013 | 1213-Q2 | MOJ | Amber/Green | 2011-07-01 | 2013-07-31 | 2.3129 | 3.24 |  |  | 15.0424 |  |  |  | 2.0835 | MOJ_0013_1112-Q2,1213-Q2 | MOJ | Amber/Green | Joiner
MOJ_0014_1112-Q2 | Community Payback | AR 2013 | 1213-Q2 | MOJ | Amber/Green | 2010-10-01 | 2012-12-31 | 6.85 | 6.85 |  |  | 43.2623 |  |  |  | 2.2505 | MOJ_0014_1112-Q2,1213-Q2 | MOJ | Amber/Green | Joiner
MOJ_0017_1112-Q2 | Payment by Results Pilot Programme | AR 2013 | 1213-Q2 | MOJ | Amber/Red | 2011-04-01 | 2015-12-31 | 7.63 | 7.63 |  |  | 119.03 |  |  |  | 4.7502 | MOJ_0017_1112-Q2,1213-Q2 | MOJ | Amber/Red | Joiner
MOJ_0019_1112-Q4 | STC Re-tendering Programme | AR 2013 | 1213-Q2 | MOJ | Amber | 2011-03-15 | 2015-07-13 | 0.55 | 0.55 |  |  | 336.16 |  |  |  | 4.3285 | MOJ_0019_1112-Q4,1213-Q2 | MOJ | Amber | Joiner
HMT_0003_1112-Q1 | Yoda Project (Outsourced Services Retender Project) | AR 2013 | 1213-Q2 | NS&I | Amber/Red | 2009-04-05 | 2014-04-01 | 2.501 | 2.501 |  |  | 0 |  |  |  | 4.9884 | HMT_0003_1112-Q1,1213-Q2 | NS&I | Amber/Red | Joiner
ONS_0001_1112-Q1 | 2011 Census | AR 2013 | 1213-Q2 | ONS | Amber/Green | 2002-09-01 | 2014-03-31 | 21.98 | 21.94 |  |  | 482.45 |  |  |  | 11.5784 | ONS_0001_1112-Q1,1213-Q2 | ONS | Amber/Green | Joiner
ONS_0002_1112-Q1 | Beyond 2011 Programme | AR 2013 | 1213-Q2 | ONS | Amber/Green | 2011-04-01 | 2015-03-31 | 5 | 5.75 |  |  | 25 |  |  |  | 3.9973 | ONS_0002_1112-Q1,1213-Q2 | ONS | Amber/Green | Joiner
ONS_0003_1112-Q4 | Web Data Access (WDA) Project | AR 2013 | 1213-Q2 | ONS | Red | 2011-04-01 | 2013-03-31 | 6.359 | 7.068 |  |  | 13.548 |  |  |  | 1.9986 | ONS_0003_1112-Q4,1213-Q2 | ONS | Red | Joiner
ONS_0004_1213-Q2 | Electronic Data Collection (EDC) | AR 2013 | 1213-Q2 | ONS | Amber/Green | 2012-04-02 | 2014-03-31 | 0 | 0 |  |  | 0 |  |  |  | 1.9932 | ONS_0004_1213-Q2,1213-Q2 | ONS | Amber/Green | Joiner
ONS_0005_1213-Q2 | European Systems of Accounting 2010 (ESA 10) | AR 2013 | 1213-Q2 | ONS | Red | 2011-02-05 | 2020-06-30 | 0 | 0 |  |  | 0 |  |  |  | 9.399 | ONS_0005_1213-Q2,1213-Q2 | ONS | Red | Joiner
DH_0017_1112-Q1 | HPA Chrysalis | AR 2013 | 1213-Q2 | DH | Amber | 2013-11-30 | 2019-05-17 | 91.02 | 5.9 |  |  | 6237.56 |  |  |  | 5.4593 | DH_0017_1112-Q1,1213-Q2 | DH | Amber | Joiner
DH_0019_1112-Q1 | PFI - Royal Liverpool and Broadgreen ('World Class Hospitals; World Class Services - Renewing the Royal Liverpool University Hospital') | AR 2013 | 1213-Q2 | DH | Amber/Green | 2010-06-01 | 2016-11-01 | 7.9 | 7.9 |  |  | 1117.7 |  |  |  | 6.4203 | DH_0019_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
DH_0020_1112-Q1 | Royal National Orthopaedic Hospital NHS Trust PFI Project | AR 2013 | 1213-Q2 | DH | Green | 2010-04-09 | 2016-11-28 | 0 | 0 |  |  | 309.93 |  |  |  | 6.6393 | DH_0020_1112-Q1,1213-Q2 | DH | Green | Joiner
DH_0021_1112-Q1 | Sandwell and West Birmingham Hospitals NHS Trust - The Midland Metropolitan Hospital Project | AR 2013 | 1213-Q2 | DH | Amber/Green | 2013-03-31 | 2019-04-01 | 0 | 0 |  |  | 1116 |  |  |  | 6.0014 | DH_0021_1112-Q1,1213-Q2 | DH | Amber/Green | Joiner
FCO_0001_1112-Q1 | ABUJA: New Office and Residence | AR 2013 | 1213-Q2 | FCO | Amber | 2010-12-01 | 2017-12-01 | 0.95 | 0.95 |  |  | 39 |  |  |  | 7.0007 | FCO_0001_1112-Q1,1213-Q2 | FCO | Amber | Joiner
FCO_0006_1213-Q2 | UKERP | AR 2013 | 1213-Q2 | FCO | Amber | 2011-06-01 | 2016-08-01 | 1.44 | 1.44 |  |  | 78.79 |  |  |  | 5.1691 | FCO_0006_1213-Q2,1213-Q2 | FCO | Amber | Joiner
BIS_0001_1112-Q1 | BIS Shared Services | AR 2014 | 1314-Q2 | BEIS | Amber | 2011-05-04 | 2014-04-01 | 3.785 | 3.785 | 0 | 0% | 19.27 |  |  | Government Transformation and Service Delivery | 2.9103 | BIS_0001_1112-Q1,1314-Q2 | BEIS | Amber | Not new
BIS_0005_1112-Q1 | Further Education 24+ Learning Loans Programme | AR 2014 | 1314-Q2 | BEIS | Amber/Red | 2010-11-30 | 2013-10-31 | 83.65 | 84.604 | 0.954 | 0.011405 | 572.291 |  |  | Government Transformation and Service Delivery | 2.9185 | BIS_0005_1112-Q1,1314-Q2 | BEIS | Amber/Red | Not new
BIS_0008_1112-Q1 | ICR Monetisation | AR 2014 | 1314-Q2 | DFE | Amber/Red | 2010-03-01 | 2018-12-31 | 5.5 | 5.5 | 0 | 0 | 28.61 |  |  | Government Transformation and Service Delivery | 8.835 | BIS_0008_1112-Q1,1314-Q2 | DFE | Amber/Red | Not new
BIS_0009_1112-Q1 | The Francis Crick Institute (formerly UKCMRI) | AR 2014 | 1314-Q2 | BEIS | Amber/Green | 2006-10-01 | 2017-12-21 | 112 | 112 | 0 | 0 | 753 |  |  | Infrastructure and Construction | 11.2225 | BIS_0009_1112-Q1,1314-Q2 | BEIS | Amber/Green | Not new
BIS_0011_1213-Q1 | SLC Transformation Programme | AR 2014 | 1314-Q2 | BEIS | Amber | 2012-03-01 | 2016-03-19 | 19.86 | 19.86 | 0 | 0 | 139.13 |  |  | Government Transformation and Service Delivery | 4.0493 | BIS_0011_1213-Q1,1314-Q2 | BEIS | Amber | Not new
BIS_0003_1112-Q1 | Catapult Centres | AR 2014 | 1314-Q2 | BEIS | Amber/Green | 2010-12-01 | 2013-04-01 | 127 | 127 | 0 | 0 | 757 |  |  | Infrastructure and Construction | 2.3326 | BIS_0003_1112-Q1,1314-Q2 | BEIS | Amber/Green | Not new
BIS_0004_1112-Q1 | FE Capital Investment Programme | AR 2014 | 1314-Q2 | BEIS | Amber/Green | 2010-05-31 | 2015-09-01 | 450.37 | 450.37 | 0 | 0 | 5609.46 |  |  |  | 5.2539 | BIS_0004_1112-Q1,1314-Q2 | BEIS | Amber/Green | Not new
BIS_0006_1112-Q1 | Green Investment Bank | AR 2014 | 1314-Q2 | BEIS | Green | 2010-06-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 278 |  |  | Government Transformation and Service Delivery | 2.2533 | BIS_0006_1112-Q1,1314-Q2 | BEIS | Green | Not new
BIS_0007_1112-Q1 | HE Reform Programme | AR 2014 | 1314-Q2 | BEIS | Amber/Green | 2011-06-30 | 2015-12-31 | 970 | 1180 | 210 | 0.21649 | 4600 |  |  | Government Transformation and Service Delivery | 4.5038 | BIS_0007_1112-Q1,1314-Q2 | BEIS | Amber/Green | Not new
CO_0001_1112-Q1 | Electoral Registration Transformation Programme | AR 2014 | 1314-Q2 | CO | Amber | 2010-02-01 | 2016-01-01 | 26.05 | 26.05 | 0 | 0 | 170.92 |  |  | Government Transformation and Service Delivery | 5.9138 | CO_0001_1112-Q1,1314-Q2 | CO | Amber | Not new
CO_0004_1112-Q1 | National Citizen Service | AR 2014 | 1314-Q2 | CO | Amber | 2011-10-01 | 2014-12-31 | 104.85 | 104.85 | 0 | 0 | 325.4 |  |  | Government Transformation and Service Delivery | 3.2498 | CO_0004_1112-Q1,1314-Q2 | CO | Amber | Not new
CO_0005_1112-Q1 | National Cyber Security Programme | AR 2014 | 1314-Q2 | CO | Amber/Green | 2011-04-01 | 2016-04-01 | 180 | 179.9 | -0.1 | -0.0006 | 860 |  |  | ICT | 5.0021 | CO_0005_1112-Q1,1314-Q2 | CO | Amber/Green | Not new
CO_0006_1112-Q2 | Public Services Network Programme | AR 2014 | 1314-Q2 | CO | Amber | 2012-08-16 | 2015-10-13 | 0 | 0 | 0 | 0 | 27.2851 |  |  | ICT | 3.1567 | CO_0006_1112-Q2,1314-Q2 | CO | Amber | Not new
CO_0002_1112-Q1 | G-Cloud Programme (covers Data Centre Consolidation and Application Store) | AR 2014 | 1314-Q2 | CO | Amber/Red |  |  | 1 | 0 | -1 | -1 | 6 |  |  |  | 0 | CO_0002_1112-Q1,1314-Q2 | CO | Amber/Red | Not new
DCLG_0005_1112-Q4 | CONNECT Project (formerly ICTRelet Project) | AR 2014 | 1314-Q2 | DCLG | Amber/Green | 2011-11-16 | 2014-02-28 | 4.83 | 4.83 | 0 | 0 | 24.6 |  |  | ICT | 2.2861 | DCLG_0005_1112-Q4,1314-Q2 | DCLG | Amber/Green | Not new
DCLG_0006_1112-Q4 | Enterprise Zones Programme | AR 2014 | 1314-Q2 | DCLG | Amber/Green | 2011-03-23 | 2038-03-31 | 111 | 0 | -111 | -1 | 211 |  |  | Government Transformation and Service Delivery | 27.0226 | DCLG_0006_1112-Q4,1314-Q2 | DCLG | Amber/Green | Not new
DCLG_0004_1112-Q1 | The Future of Local Audit | AR 2014 | 1314-Q2 | DCLG | Amber | 2011-06-30 | 2012-11-01 | 0 | 0 | 0 | 0 | 45.08 |  |  | Government Transformation and Service Delivery | 1.3415 | DCLG_0004_1112-Q1,1314-Q2 | DCLG | Amber | Not new
DCMS_0001_1112-Q1 | Broadband Delivery Programme | AR 2014 | 1314-Q2 | DCMS | Amber | 2010-12-06 | 2016-12-31 | 99.5 | 99.5 | 0 | 0 | 529 |  |  | Infrastructure and Construction | 6.0698 | DCMS_0001_1112-Q1,1314-Q2 | DCMS | Amber | Not new
DCMS_0004_1112-Q1 | The Tate Modern Project | AR 2014 | 1314-Q2 | DCMS | Amber/Red | 2010-01-01 | 2015-05-01 | -2.7 | -2.7 | 0 | 0 | 215 |  |  | Infrastructure and Construction | 5.3279 | DCMS_0004_1112-Q1,1314-Q2 | DCMS | Amber/Red | Not new
DCMS_0005_1112-Q1 | World Conservation and Exhibitions Centre | AR 2014 | 1314-Q2 | DCMS | Amber/Green | 2008-03-31 | 2014-04-01 | 0 | 0 | 0 | 0 | 135 |  |  | Infrastructure and Construction | 6.0014 | DCMS_0005_1112-Q1,1314-Q2 | DCMS | Amber/Green | Not new
DCMS_0006_1112-Q4 | Mobile Infrastructure Project | AR 2014 | 1314-Q2 | DCMS | Amber/Green | 2011-10-01 | 2015-03-31 | 71 | 14 | -57 | -0.80282 | 155 |  |  | ICT | 3.4962 | DCMS_0006_1112-Q4,1314-Q2 | DCMS | Amber/Green | Not new
DCMS_0007_1112-Q4 | Urban Broadband Fund - Super-connected City Initiative | AR 2014 | 1314-Q2 | DCMS | Amber/Red | 2012-12-05 | 2015-03-31 | 23 | 30 | 7 | 0.30435 | 150 |  |  | Infrastructure and Construction | 2.3162 | DCMS_0007_1112-Q4,1314-Q2 | DCMS | Amber/Red | Not new
DCMS_0003_1112-Q1 | Spectrum Clearance and Awards Programme | AR 2014 | 1314-Q2 | DCMS | Amber/Green | 2011-06-22 | 2014-12-31 | 86.16 | 55.03 | -31.13 | -0.3613 | 247.433 |  |  | ICT | 3.5264 | DCMS_0003_1112-Q1,1314-Q2 | DCMS | Amber/Green | Not new
BIS_0010_1112-Q4 | Urenco Future Options | AR 2014 | 1314-Q2 | BEIS | Exempt | 2010-02-01 | Data exempt under section 27 and section 43 of the Freedom of Information Act (2000) | 5.889 | 4.092 | -1.797 | -0.30515 | 18.416 |  |  |  | 0 | BIS_0010_1112-Q4,1314-Q2 | BEIS | Exempt | Not new
DECC_0003_1112-Q1 | Dounreay Parent Body Organisation (PBO) - Delivery Phase | AR 2014 | 1314-Q2 | BEIS | Green | 2009-09-21 | 2025-12-31 | 150 | 158.3 | 8.3 | 0.0553 | 1578 |  |  | Infrastructure and Construction | 16.2765 | DECC_0003_1112-Q1,1314-Q2 | BEIS | Green | Not new
DECC_0004_1112-Q1 | Electricity Market Reform Programme | AR 2014 | 1314-Q2 | BEIS | Exempt | 2010-12-10 | 2030-12-31 | 20.41 | 20.41 | 0 | 0 | 66.15 |  |  | Government Transformation and Service Delivery | 20.0575 | DECC_0004_1112-Q1,1314-Q2 | BEIS | Exempt | Not new
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2014 | 1314-Q2 | BEIS | Amber | 2008-06-30 | 2040-12-31 | 24 | 23.74 | -0.26 | -0.0108 | 11626.4 |  |  | Infrastructure and Construction | 32.5038 | DECC_0005_1112-Q1,1314-Q2 | BEIS | Amber | Not new
DECC_0009_1112-Q1 | Renewable Heat Incentive | AR 2014 | 1314-Q2 | BEIS | Amber | 2008-11-30 | 2014-09-10 | 219 | 80.1 | -138.9 | -0.6342 | 48261.8 |  |  | Government Transformation and Service Delivery | 5.7769 | DECC_0009_1112-Q1,1314-Q2 | BEIS | Amber | Not new
DECC_0010_1112-Q1 | Smart Meters Implementation Programme | AR 2014 | 1314-Q2 | BEIS | Amber | 2009-12-02 | 2020-09-30 | 15.609 | 18.609 | 3 | 0.1922 | 17184.647 |  |  | Government Transformation and Service Delivery | 10.8282 | DECC_0010_1112-Q1,1314-Q2 | BEIS | Amber | Not new
DECC_0011_1112-Q3 | Carbon Capture & Storage Commercialisation Programme | AR 2014 | 1314-Q2 | BEIS | Amber | 2011-10-25 | 2050-03-31 | 36.6 | 36.56 | -0.04 | -0.0011 | Data exempt under Section 43(2) of the Freedom of Information Act (2000) |  |  | Infrastructure and Construction | 38.4312 | DECC_0011_1112-Q3,1314-Q2 | BEIS | Amber | Not new
DECC_0012_1213-Q1 | FID Enabling for Hinkley Point C | AR 2014 | 1314-Q2 | BEIS | Exempt | 2011-09-01 | 2015-02-01 | 3.971 | 6.7278 | 2.7568 | 0.6942 | 13.6898 |  |  | Infrastructure and Construction | 3.4196 | DECC_0012_1213-Q1,1314-Q2 | BEIS | Exempt | Not new
DECC_0013_1213-Q1 | Magnox & Research Sites Restoration Ltd Parent Body Organisations Competition | AR 2014 | 1314-Q2 | BEIS | Amber/Green | 2012-04-03 | 2028-09-01 | 0 | 0 | 0 | 0 | 5716 |  |  |  | 16.4134 | DECC_0013_1213-Q1,1314-Q2 | BEIS | Amber/Green | Not new
DECC_0007_1112-Q1 | New Nuclear Programme | AR 2014 | 1314-Q2 | BEIS | Exempt | 2008-01-31 | 2019-03-31 | 1.38 | 1.38 | 0 | 0 | 31.292 |  |  |  | 11.1622 | DECC_0007_1112-Q1,1314-Q2 | BEIS | Exempt | Not new
DECC_0006_1112-Q1 | Green Deal | AR 2014 | 1314-Q2 | BEIS | Exempt | 2010-05-20 | 2030-12-31 | 200 | 200 | 0 | 0 | 10311.92 |  |  | Government Transformation and Service Delivery | 20.616 | DECC_0006_1112-Q1,1314-Q2 | DECC | Exempt | Not new
DEFRA_0001_1112-Q1 | CAP Delivery Programme (formerly the Future Options Programme) | AR 2014 | 1314-Q2 | DEFRA | Amber | 2011-01-01 | 2016-12-01 | 23 | 23 | 0 | 0 | 154.78 |  |  |  | 5.9165 | DEFRA_0001_1112-Q1,1314-Q2 | DEFRA | Amber | Not new
DECC_0014_1314-Q1 | FID Enabling for Renewables | AR 2014 | 1314-Q2 | BEIS | Exempt | 2012-12-17 | 2013-12-31 | 1.858 | 2.839 | 0.981 | 0.528 | 3.6919 |  |  | Infrastructure and Construction | 1.0376 | DECC_0014_1314-Q1,1314-Q2 | BEIS | Exempt | Joiner
DEFRA_0004_1112-Q1 | Thames Estuary Programme Phase 1 (TEP1) | AR 2014 | 1314-Q2 | DEFRA | Amber/Green | 2010-04-01 | 2025-12-31 | 2.04 | 2.3 | 0.26 | 0.1275 | 318.74 |  |  | Infrastructure and Construction | 15.7509 | DEFRA_0004_1112-Q1,1314-Q2 | DEFRA | Amber/Green | Not new
DFE_0003_1112-Q4 | Priority School Building Programme | AR 2014 | 1314-Q2 | DFE | Amber | 2011-07-19 | 2017-12-31 | 110.53 | 110.53 | 0 | 0 | 3889.76 |  |  | Infrastructure and Construction | 6.4531 | DFE_0003_1112-Q4,1314-Q2 | DFE | Amber | Not new
DEFRA_0005_1213-Q3 | Thames Tideway Tunnel | AR 2014 | 1314-Q2 | DEFRA | Amber/Red | 2010-09-07 | 2023-03-31 | 3.13 | 3.13 | 0 | 0 | 4217.88 |  |  | Infrastructure and Construction | 12.5613 | DEFRA_0005_1213-Q3,1314-Q2 | DEFRA | Amber/Red | Joiner
DFE_0001_1112-Q1 | Building Schools for the Future (BSF) | AR 2014 | 1314-Q2 | DFE | Amber/Green | 2004-04-01 | 2017-07-02 | 335 | 350 | 15 | 0.0448 | 6302 |  |  | Infrastructure and Construction | 13.2512 | DFE_0001_1112-Q1,1314-Q2 | DFE | Amber/Green | Not new
DFID_0001_1112-Q1 | St Helena Airport | AR 2014 | 1314-Q2 | DFID | Amber | 2005-03-15 | 2026-08-31 | 53.25 | 60.63 | 7.38 | 0.13859 | 445.11 |  |  | Infrastructure and Construction | 21.462 | DFID_0001_1112-Q1,1314-Q2 | DFID | Amber | Not new
DFT_0001_1112-Q1 | Crossrail | AR 2014 | 1314-Q2 | DFT | Amber/Green | 2008-07-22 | 2019-12-31 | 1200 | 1199.1 | -0.9 | -0.00075 | 14518.98 |  |  | Infrastructure and Construction | 11.4415 | DFT_0001_1112-Q1,1314-Q2 | DFT | Amber/Green | Not new
DFT_0015_1112-Q1 | Shared Services Implementation Programme | AR 2014 | 1314-Q2 | DFT | Amber | 2010-12-10 | 2015-06-01 | 35.4 | 31.22 | -4.18 | -0.11808 | 222.27 |  |  | ICT | 4.4736 | DFT_0015_1112-Q1,1314-Q2 | DFT | Amber | Not new
DFT_0004_1112-Q1 | High Speed Rail Programme | AR 2014 | 1314-Q2 | DFT | Amber/Red | 2011-02-28 | 2033-12-31 | 347.6 | 347.6 | 0 | 0 | 42600 |  |  | Infrastructure and Construction | 22.8392 | DFT_0004_1112-Q1,1314-Q2 | DFT | Amber/Red | Not new
DFT_0018_1213-Q1 | Thameslink, Southern, Great Northern Franchise Competition | AR 2014 | 1314-Q2 | DFT | Amber | 2013-03-26 | 2014-09-14 | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) |  |  |  | 1.4702 | DFT_0018_1213-Q1,1314-Q2 | DFT | Amber | Not new
DFT_0010_1112-Q1 | London, North East and Scotland Franchise Competition | AR 2014 | 1314-Q2 | DFT | Amber | 2013-03-26 | 2015-02-06 | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) |  |  |  | 1.8672 | DFT_0010_1112-Q1,1314-Q2 | DFT | Amber | Not new
DFT_0002_1112-Q1 | ICTContract Let Procurement Programme (CLPP) | AR 2014 | 1314-Q2 | DFT | Amber | 2011-03-01 | 2015-12-30 | 8.994 | 8.994 | 0 | 0 | 79.77 |  |  |  | 4.8323 | DFT_0002_1112-Q1,1314-Q2 | DFT | Amber | Not new
DFT_0005_1112-Q1 | Intercity Express Programme (IEP) | AR 2014 | 1314-Q2 | DFT | Amber/Green | 2005-06-01 | 2019-12-31 | 6 | 5.38 | -0.62 | -0.10333 | 1308.35 |  |  | Infrastructure and Construction | 14.5818 | DFT_0005_1112-Q1,1314-Q2 | DFT | Amber/Green | Not new
DFT_0009_1112-Q1 | Periodic Review 2013 (Rail Investment Strategy - HLOS & SOFA) | AR 2014 | 1314-Q2 | DFT | Amber/Green | 2011-08-31 | 2012-07-31 | 0 | 0 | 0 | 0 | 16840.61 |  |  | Infrastructure and Construction | 0.91718 | DFT_0009_1112-Q1,1314-Q2 | DFT | Amber/Green | Not new
DFT_0014_1112-Q1 | Search & Rescue Helicopters (SARH) | AR 2014 | 1314-Q2 | DFT | Amber/Green | 2011-02-08 | 2017-09-08 | 0 | 0 | 0 | 0 | 1923 |  |  | Infrastructure and Construction | 6.5818 | DFT_0014_1112-Q1,1314-Q2 | DFT | Amber/Green | Not new
DH_0008_1112-Q1 | Electronic Prescription Service (EPS) Release 2 | AR 2014 | 1314-Q2 | DH | Amber/Red | 2003-11-28 | 2014-03-31 | 5.86 | 5.8 | -0.06 | -0.0102 | 36.38 |  |  | Government Transformation and Service Delivery | 10.3381 | DH_0008_1112-Q1,1314-Q2 | DH | Amber/Red | Not new
DFT_0016_1112-Q1 | Thameslink | AR 2014 | 1314-Q2 | DFT | Amber/Green | 2005-07-01 | 2018-12-31 | 43.04 | 43.04 | 0 | 0 | 4796.04 |  |  | Infrastructure and Construction | 13.5003 | DFT_0016_1112-Q1,1314-Q2 | DFT | Amber/Green | Not new
DH_0015_1112-Q1 | NME Programme For IT | AR 2014 | 1314-Q2 | DH | Amber | 2004-04-01 | 2016-07-31 | 297.3503 | 224.6238 | -72.7266 | -0.2446 | 5636.1923 |  |  |  | 12.3313 | DH_0015_1112-Q1,1314-Q2 | DH | Amber | Not new
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | AR 2014 | 1314-Q2 | DFT | Amber | 2012-09-01 | 2020-03-12 | 5.878 | 5.878 | 0 | 0 | 1519.318 |  |  | Infrastructure and Construction | 7.5264 | DFT_0020_1314-Q2,1314-Q2 | DFT | Amber | Joiner
DH_0018_1112-Q1 | Pre-Pandemic Vaccine | AR 2014 | 1314-Q2 | DH | Green | 2011-10-01 | 2014-07-01 | Exempt under section 43 of the FoI Act (2000) | Exempt under section 43 of the FoI Act (2000) | Exempt under section 43 of the FoI Act (2000) | n/a | 259 |  |  | Government Transformation and Service Delivery | 2.7488 | DH_0018_1112-Q1,1314-Q2 | DH | Green | Not new
DH_0003_1112-Q1 | Brighton & Sussex University Hospitals NHS Trust (3Ts Programme - The development of a leading teaching, trauma and tertiary care centre) | AR 2014 | 1314-Q2 | DH | No DCA | 2012-01-27 | 2021-12-24 | 79.85 | 22.99 | -56.86 | -0.7121 | 500.8 |  |  | Infrastructure and Construction | 9.9083 | DH_0003_1112-Q1,1314-Q2 | DH | No DCA | Not new
DH_0004_1112-Q1 | Broadmoor Redevelopment Programme | AR 2014 | 1314-Q2 | DH | No DCA | 2010-03-01 | 2018-11-01 | 16.073 | 16.073 | 0 | 0 | 287.426 |  |  | Infrastructure and Construction | 8.6708 | DH_0004_1112-Q1,1314-Q2 | DH | No DCA | Not new
DH_0022_1112-Q1 | Summary Care Record (SCR) | AR 2014 | 1314-Q2 | DH | Amber/Green | 2006-04-01 | 2016-03-31 | 14.486 | 15.3489 | 0.86294 | 0.0596 | 51.1072 |  |  | ICT | 9.9986 | DH_0022_1112-Q1,1314-Q2 | DH | Amber/Green | Not new
DH_0023_1112-Q2 | London Programme for IT | AR 2014 | 1314-Q2 | DH | Amber/Green | 2003-12-18 | 2015-10-30 | 149.58 | 188.15 | 38.57 | 0.2579 | 628.2 |  |  |  | 11.8658 | DH_0023_1112-Q2,1314-Q2 | DH | Amber/Green | Not new
DH_0026_1112-Q2 | Southern Programme for IT | AR 2014 | 1314-Q2 | DH | Amber/Green | 2004-01-26 | 2015-10-31 | 75.98 | 47.47 | -28.51 | -0.3752 | 634.06 |  |  |  | 11.7618 | DH_0026_1112-Q2,1314-Q2 | DH | Amber/Green | Not new
DH_0014_1112-Q1 | NHSmail Service | AR 2014 | 1314-Q2 | DH | Green | 2004-10-31 | 2014-06-30 | 22.8 | 20.66 | -2.14 | -0.0939 | 235.45 |  |  | ICT | 9.6619 | DH_0014_1112-Q1,1314-Q2 | DH | Green | Not new
DH_0010_1112-Q1 | Health and Care Modernisation Transition Programme | AR 2014 | 1314-Q2 | DH | Amber/Red | 2011-10-01 | 2013-04-01 | 364.5 | 328.7 | -35.8 | -0.0982 | 1485.2 |  |  | Government Transformation and Service Delivery | 1.5003 | DH_0010_1112-Q1,1314-Q2 | DH | Amber/Red | Not new
DH_0012_1112-Q1 | IMS3 | AR 2014 | 1314-Q2 | DH | Amber/Green | 2011-05-16 | 2013-03-29 | 14.3 | 22.99 | 8.69 | 0.6077 | 139.38 |  |  | Government Transformation and Service Delivery | 1.87 | DH_0012_1112-Q1,1314-Q2 | DH | Amber/Green | Not new
DH_0005_1112-Q1 | CAB Variation | AR 2014 | 1314-Q2 | DH | Amber/Red | 2011-10-01 | 2013-12-15 | 15.75 | 16.13 | 0.38 | 0.0241 | 54.24 |  |  |  | 2.2067 | DH_0005_1112-Q1,1314-Q2 | DH | Amber/Red | Not new
DH_0024_1112-Q2 | N3 Extension | AR 2014 | 1314-Q2 | DH | Red | 2004-02-19 | 2014-03-31 | 125.33 | 99.23 | -26.1 | -0.2083 | 371.88 |  |  |  | 10.1109 | DH_0024_1112-Q2,1314-Q2 | DH | Red | Not new
DH_0006_1112-Q1 | E&N Herts NHS Trust - LIFT scheme - new QEII hospital in Welwyn Garden City | AR 2014 | 1314-Q2 | DH | No DCA | 2011-03-23 | 2014-04-01 | 0 | 0 | 0 | No departmental narrative | 67.44 |  |  | Infrastructure and Construction | 3.0253 | DH_0006_1112-Q1,1314-Q2 | DH | No DCA | Not new
DWP_0003_1112-Q1 | Child Maintenance Group Change | AR 2014 | 1314-Q2 | DWP | Amber/Green | 2009-08-01 | 2014-10-27 | 77.97 | 66.126 | -35.934 | -0.35209 | 1218.33 |  |  | Government Transformation and Service Delivery | 5.2375 | DWP_0003_1112-Q1,1314-Q2 | DWP | Amber/Green | Not new
DWP_0005_1112-Q1 | Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme) | AR 2014 | 1314-Q2 | DWP | Amber | 2007-05-01 | 2018-10-31 | 106 | 94.3 | -11.7 | -0.11038 | 995.4 |  |  | Government Transformation and Service Delivery | 11.5017 | DWP_0005_1112-Q1,1314-Q2 | DWP | Amber | Not new
DWP_0009_1112-Q1 | Universal Credit Programme | AR 2014 | 1314-Q2 | DWP | Reset | 2011-11-17 | Reset | 571.52 | 201.403 | -370.117 | -0.6476 | Reset |  |  | Government Transformation and Service Delivery | 0 | DWP_0009_1112-Q1,1314-Q2 | DWP | Reset | Not new
DWP_0011_1112-Q2 | Personal Independence Payment Implementation | AR 2014 | 1314-Q2 | DWP | Amber/Red | 2011-10-31 | 2016-03-31 | 191.21 | 179.45 | -11.76 | -0.061503 | 2518.57 |  |  | Government Transformation and Service Delivery | 4.4162 | DWP_0011_1112-Q2,1314-Q2 | DWP | Amber/Red | Not new
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | AR 2014 | 1314-Q2 | DWP | Amber/Red | 2012-04-02 | 2015-03-31 | 120.6 | 61.825 | -58.775 | -0.48735 | 770.3 |  |  | Government Transformation and Service Delivery | 2.9925 | DWP_0016_1213-Q2,1314-Q2 | DWP | Amber/Red | Not new
DWP_0010_1112-Q1 | Work Programme | AR 2014 | 1314-Q2 | DWP | Amber | 2010-11-25 | 2011-10-18 | 800.3 | 1002 | 201.7 | 0.25203 | 5626.7 |  |  |  | 0.89528 | DWP_0010_1112-Q1,1314-Q2 | DWP | Amber | Not new
DWP_0007_1112-Q1 | Incapacity Benefit Reassessment | AR 2014 | 1314-Q2 | DWP | Green | 2009-07-09 | 2012-03-23 | 142 | 142.79 | 0.79 | 0.0055634 | 891.8 |  |  |  | 2.705 | DWP_0007_1112-Q1,1314-Q2 | DWP | Green | Not new
DWP_0002_1112-Q1 | Central Payment System | AR 2014 | 1314-Q2 | DWP | Green | 2008-09-01 | 2012-06-21 | 17.5 | 17.6 | 0.1 | 0.0057143 | 284.9 |  |  |  | 3.8029 | DWP_0002_1112-Q1,1314-Q2 | DWP | Green | Not new
DWP_0012_1112-Q4 | Benefit Cap | AR 2014 | 1314-Q2 | DWP | Amber/Green | 2012-04-19 | 2013-12-19 | 25.407 | 14.63 | -10.777 | -0.42417 | 46.307 |  |  | Government Transformation and Service Delivery | 1.6674 | DWP_0012_1112-Q4,1314-Q2 | DWP | Amber/Green | Not new
DWP_0015_1112-Q4 | Youth Contract | AR 2014 | 1314-Q2 | DWP | Amber/Green | 2012-01-19 | 2012-06-21 | 259.4 | 250.61 | -8.79 | -0.033886 | 741.93 |  |  |  | 0.42163 | DWP_0015_1112-Q4,1314-Q2 | DWP | Amber/Green | Not new
DWP_0013_1112-Q4 | Specialist Disability Employment Programme | AR 2014 | 1314-Q2 | DWP | Amber | 2012-02-16 | 2014-07-31 | 32.14 | 7.13 | -25.01 | -0.77816 | 213.34 |  |  | Government Transformation and Service Delivery | 2.4531 | DWP_0013_1112-Q4,1314-Q2 | DWP | Amber | Not new
DWP_0014_1112-Q4 | State Pension Reform - Single Tier | AR 2014 | 1314-Q2 | DWP | Amber/Red | 2012-02-27 | 2017-10-31 | 14 | 8.87 | -5.13 | -0.36643 | 114.16 |  |  | Government Transformation and Service Delivery | 5.6756 | DWP_0014_1112-Q4,1314-Q2 | DWP | Amber/Red | Not new
DH_0007_1112-Q1 | E&N Herts NHS Trust - Lister Hospital ('Our Changing Hospitals' Phase 4 Programme) | AR 2014 | 1314-Q2 | DH | No DCA | 2011-08-04 | 2014-03-17 | 14.12 | 41.33 | 27.21 | 1.9271 | 212.03 |  |  | Infrastructure and Construction | 2.6174 | DH_0007_1112-Q1,1314-Q2 | DH | No DCA | Not new
FCO_0004_1112-Q1 | ICTRe-procurement | AR 2014 | 1314-Q2 | FCO | Amber | 2011-01-01 | 2013-11-30 | 43.7 | 45.2 | 1.5 | 0.034325 | 242.9 |  |  | ICT | 2.9131 | FCO_0004_1112-Q1,1314-Q2 | FCO | Amber | Not new
DH_0013_1112-Q1 | Mersey Care NHS LIFT scheme (TIME - To Improve Mental Health Environments) | AR 2014 | 1314-Q2 | DH | No DCA | 2011-08-30 | 2015-01-20 | 0 | 0 | 0 | No departmental narrative | 208.8 |  |  | Infrastructure and Construction | 3.3922 | DH_0013_1112-Q1,1314-Q2 | DH | No DCA | Not new
FCO_0002_1112-Q1 | Echo | AR 2014 | 1314-Q2 | FCO | Amber/Green | 2009-06-09 | 2012-12-31 | 22.82 | 22.82 | 0 | 0 | 182.85 |  |  | ICT | 3.5619 | FCO_0002_1112-Q1,1314-Q2 | FCO | Amber/Green | Not new
FCO_0003_1112-Q1 | JAKARTA: New Embassy | AR 2014 | 1314-Q2 | FCO | Amber/Green | 2004-04-01 | 2014-09-01 | 5.64 | 2.44 | -3.2 | -0.56738 | 29.45 |  |  | Infrastructure and Construction | 10.4175 | FCO_0003_1112-Q1,1314-Q2 | FCO | Amber/Green | Not new
HMRC_0002_1112-Q1 | Debt Staff Reinvestment | AR 2014 | 1314-Q2 | HMRC | Amber/Green | 2011-04-01 | 2015-04-01 | 16.89 | 16.89 | 0 | 0 | 56.418 |  |  | Government Transformation and Service Delivery | 4 | HMRC_0002_1112-Q1,1314-Q2 | HMRC | Amber/Green | Not new
HMRC_0004_1112-Q1 | One Click | AR 2014 | 1314-Q2 | HMRC | Amber/Green | 2010-03-24 | 2013-07-01 | 8.779 | 9.02 | 0.241 | 0.027452 | 111.062 |  |  | Government Transformation and Service Delivery | 3.2717 | HMRC_0004_1112-Q1,1314-Q2 | HMRC | Amber/Green | Not new
HMRC_0006_1112-Q1 | Real Time Information (RTI) | AR 2014 | 1314-Q2 | HMRC | Amber | 2010-07-05 | 2014-10-31 | 74.87 | 72.45 | -2.42 | -0.032323 | 333.02 |  |  | ICT | 4.3231 | HMRC_0006_1112-Q1,1314-Q2 | HMRC | Amber | Not new
HMRC_0007_1112-Q2 | Expanding the use of Debt Collection Agencies | AR 2014 | 1314-Q2 | HMRC | Amber/Green | 2011-04-01 | 2015-03-31 | 15.22 | 14.86 | -0.36 | -0.023653 | 70.683 |  |  | Government Transformation and Service Delivery | 3.9973 | HMRC_0007_1112-Q2,1314-Q2 | HMRC | Amber/Green | Not new
HMRC_0008_1112-Q2 | Organised Crime | AR 2014 | 1314-Q2 | HMRC | Amber | 2011-04-01 | 2013-10-31 | 25.3 | 25.51 | 0.21 | 0.0083004 | 82.708 |  |  | Government Transformation and Service Delivery | 2.5845 | HMRC_0008_1112-Q2,1314-Q2 | HMRC | Amber | Not new
HMRC_0009_1112-Q2 | Volume Crime | AR 2014 | 1314-Q2 | HMRC | Green | 2011-04-01 | 2013-05-29 | 11.13 | 11.37 | 0.24 | 0.021563 | 42.05 |  |  | Government Transformation and Service Delivery | 2.1602 | HMRC_0009_1112-Q2,1314-Q2 | HMRC | Green | Not new
HMRC_0010_1112-Q2 | Wider Coverage Project | AR 2014 | 1314-Q2 | HMRC | Amber/Green | 2011-09-14 | 2015-06-30 | 174.42 | 172.12 | -2.3 | -0.013187 | 552.254 |  |  | ICT | 3.7919 | HMRC_0010_1112-Q2,1314-Q2 | HMRC | Amber/Green | Not new
HMT_0001_1112-Q1 | Equitable Life Payment Scheme | AR 2014 | 1314-Q2 | HMT | Amber | 2010-05-01 | 2014-07-01 | 0 | 0 | 0 | 0 | 0 |  |  | Government Transformation and Service Delivery | 4.167 | HMT_0001_1112-Q1,1314-Q2 | HMT | Amber | Not new
HO_0007_1112-Q1 | ISOT Programme | AR 2014 | 1314-Q2 | NCA | Red | 2008-04-01 | 2013-09-30 | 41.97 | 38.11 | -3.86 | -0.09197 | 398.65 |  |  |  | 5.4976 | HO_0007_1112-Q1,1314-Q2 | NCA | Red | Not new
HO_0008_1112-Q1 | Schengen Information Systems (SIS) II Programme | AR 2014 | 1314-Q2 | HO | Amber | 2006-04-01 | 2015-03-31 | 13.98 | 14.67 | 0.69 | 0.049356 | 173.18 |  |  |  | 8.9966 | HO_0008_1112-Q1,1314-Q2 | HO | Amber | Not new
HO_0009_1112-Q1 | Transforming the Customer Experience (Formerly A&E) | AR 2014 | 1314-Q2 | HO | Amber | 2007-05-14 | 2014-11-01 | 11.3482 | 13.5604 | 2.2122 | 0.1949 | 202.0577 |  |  | ICT | 7.4689 | HO_0009_1112-Q1,1314-Q2 | HO | Amber | Not new
HO_0011_1112-Q2 | Disclosure & Barring Programme (formerly SIG Convergence Programme) | AR 2014 | 1314-Q2 | HO | Amber/Red | 2010-12-29 | 2015-10-01 | 130.57 | 161.5 | 30.93 | 0.23688 | 645.67 |  |  |  | 4.7556 | HO_0011_1112-Q2,1314-Q2 | HO | Amber/Red | Not new
HO_0012_1112-Q3 | Communications Capabilities Development programme | AR 2014 | 1314-Q2 | HO | Amber/Red | 2006-04-01 | 2020-04-01 | Exempt under Section 24 of the Freedom of Information Act (2000) | Exempt under Section 24 of the Freedom of Information Act (2000) | Exempt under Section 24 of the Freedom of Information Act (2000) | Exempt under Section 24 of the Freedom of Information Act (2000) | Exempt under Section 24 of the Freedom of Information Act (2000) |  |  | ICT | 14.0014 | HO_0012_1112-Q3,1314-Q2 | HO | Amber/Red | Not new
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2014 | 1314-Q2 | HO | Amber/Red | 2011-06-01 | 2020-12-31 | 6.82 | 10.24 | 3.42 | 0.50147 | 16.75 |  |  | ICT | 9.5852 | HO_0016_1213-Q1,1314-Q2 | HO | Amber/Red | Not new
HO_0023_1213-Q1 | Next Generation Outsourced Visa (NGOV) Services Contract | AR 2014 | 1314-Q2 | HO | Amber/Green | 2011-12-09 | 2014-07-01 | 1.54 | 1.54 | 0 | 0.00064977 | 595.69 |  |  |  | 2.5599 | HO_0023_1213-Q1,1314-Q2 | HO | Amber/Green | Not new
HO_0025_1213-Q2 | Harmondsworth and Colnbrook Retender | AR 2014 | 1314-Q2 | HO | Amber/Green | 2012-03-01 | 2014-08-31 | 0.04 | 0.04 | 0 | 0 | 183.52 |  |  |  | 2.4997 | HO_0025_1213-Q2,1314-Q2 | HO | Amber/Green | Not new
HO_0004_1112-Q1 | Immigration and Asylum Biometric System (IABS) | AR 2014 | 1314-Q2 | HO | Green | 2006-10-01 | 2012-12-31 | 20.89 | 21.61 | 0.72 | 0.034411 | 368.49 |  |  | ICT | 6.2505 | HO_0004_1112-Q1,1314-Q2 | HO | Green | Not new
HO_0019_1213-Q1 | PND (IMPACT) | AR 2014 | 1314-Q2 | HO | Amber/Red | 2004-04-01 | 2013-04-30 | 4.9 | 4.9 | 0 | 0 | 188.49 |  |  |  | 9.0787 | HO_0019_1213-Q1,1314-Q2 | HO | Amber/Red | Not new
HO_0001_1112-Q1 | Commercial and Operating Managers Procuring Asylum Support Services (COMPASS) | AR 2014 | 1314-Q2 | HO | Amber/Green | 2009-07-01 | 2012-09-30 | 94.92 | 97.8 | 2.88 | 0.030341 | 686.73 |  |  | Government Transformation and Service Delivery | 3.2498 | HO_0001_1112-Q1,1314-Q2 | HO | Amber/Green | Not new
HO_0026_1213-Q2 | National Crime Agency (NCA) | AR 2014 | 1314-Q2 | HO | Amber/Green | 2011-06-08 | 2014-03-31 | 417.7 | 417.7 | 0 | 0 | 1697.8 |  |  |  | 2.8118 | HO_0026_1213-Q2,1314-Q2 | HO | Amber/Green | Not new
HO_0024_1213-Q1 | Police ICTCompany Programme | AR 2014 | 1314-Q2 | HO | Exempt | 2011-09-01 | Data exempt under section 43 of the Freedom of Information Act (2000) | Data exempt under section 43 of the Freedom of Information Act (2000) | Data exempt under section 43 of the Freedom of Information Act (2000) | n/a | n/a | Data exempt under section 43 of the Freedom of Information Act (2000) |  |  |  | 0 | HO_0024_1213-Q1,1314-Q2 | HO | Exempt | Not new
MOD_0001_1112-Q1 | A400M | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2000-05-17 | 2022-03-31 | 149 | 149 | 0 | 0 | Exempt under Section 43 of the Freedom of Information Act (2000) |  |  | Military Capability | 21.87 | MOD_0001_1112-Q1,1314-Q2 | MOD | Amber/Green | Not new
MOD_0004_1112-Q1 | Airseeker | AR 2014 | 1314-Q2 | MOD | Amber | 2010-03-18 | 2018-04-01 | 141.57 | 150.19 | 8.62 | 0.060889 | 1219.4 |  |  | Military Capability | 8.0383 | MOD_0004_1112-Q1,1314-Q2 | MOD | Amber | Not new
MOD_0009_1112-Q1 | BORONA | AR 2014 | 1314-Q2 | MOD | Amber | 2006-08-31 | 2019-03-31 | 117.91 | 96.76 | -21.15 | -0.17937 | 1609.49 |  |  | Government Transformation and Service Delivery | 12.5804 | MOD_0009_1112-Q1,1314-Q2 | MOD | Amber | Not new
MOD_0017_1112-Q1 | CROWSNEST programme | AR 2014 | 1314-Q2 | MOD | Exempt | 2013-03-31 | 2022-09-30 | 2 | 3.51 | 1.51 | 0.755 | Exempt under Section 43 of the Freedom of Information Act (2000) |  |  | Military Capability | 9.5003 | MOD_0017_1112-Q1,1314-Q2 | MOD | Exempt | Not new
MOD_0019_1112-Q1 | Defence Information Infrastructure | AR 2014 | 1314-Q2 | MOD | Amber/Red | 2001-09-03 | 2015-03-21 | 777.49 | 794.8 | 17.31 | 0.022264 | 7349.97 |  |  | ICT | 13.5441 | MOD_0019_1112-Q1,1314-Q2 | MOD | Amber/Red | Not new
MOD_0033_1112-Q1 | MARSHALL | AR 2014 | 1314-Q2 | MOD | Exempt | 2006-04-03 | 2020-10-04 | 1.31 | 1.48 | 0.17 | 0.12977 | Exempt under Section 43 of the Freedom of Information Act (2000) |  |  | Military Capability | 14.5051 | MOD_0033_1112-Q1,1314-Q2 | MOD | Exempt | Not new
MOD_0035_1112-Q1 | Merlin Programme | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2003-06-01 | 2016-03-31 | 79.1 | 101.19 | 22.09 | 0.27927 | 755.44 |  |  | Military Capability | 12.8323 | MOD_0035_1112-Q1,1314-Q2 | MOD | Amber/Green | Not new
MOD_0036_1112-Q1 | Maritime Sustainment Programme | AR 2014 | 1314-Q2 | MOD | Green | 2005-07-25 | 2018-04-30 | 57.3 | 57.3 | 0 | 0 | 1664.03 |  |  | Military Capability | 12.7639 | MOD_0036_1112-Q1,1314-Q2 | MOD | Green | Not new
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2014 | 1314-Q2 | MOD | Exempt | 2008-04-01 | 2025-04-30 | 911.74 | 863.11 | -48.63 | -0.053338 | 21883.89 |  |  | Military Capability | 17.0787 | MOD_0038_1112-Q1,1314-Q2 | MOD | Exempt | Not new
MOD_0040_1112-Q1 | Puma Helicopter Life Extension Programme | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2007-02-01 | 2015-12-31 | 33.39 | 30.03 | -3.36 | -0.10063 | 265.66 |  |  | Military Capability | 8.9117 | MOD_0040_1112-Q1,1314-Q2 | MOD | Amber/Green | Not new
MOD_0042_1112-Q1 | Queen Elizabeth Programme | AR 2014 | 1314-Q2 | MOD | Red | 1998-12-01 | 2023-03-31 | 781 | 781 | 0 | 0 | 6221.35 |  |  | Military Capability | 24.3285 | MOD_0042_1112-Q1,1314-Q2 | MOD | Red | Not new
MOD_0047_1112-Q1 | Spearfish Upgrade (SFU) Programme | AR 2014 | 1314-Q2 | MOD | Exempt | 2008-04-01 | 2022-12-31 | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | 0 | 0 | Exempt under Section 43(2) of the Freedom of Information Act (2000) |  |  |  | 14.7488 | MOD_0047_1112-Q1,1314-Q2 | MOD | Exempt | Not new
MOD_0055_1112-Q1 | Type 26 Global Combat Ship (T26 GCS) | AR 2014 | 1314-Q2 | MOD | Exempt | 2008-07-21 | Exempt under Section 22 of the Freedom of Information Act (2000) | 87.35 | 82.42 | -4.93 | -0.05644 | Exempt under Section 43 of the Freedom of Information Act (2000) |  |  |  | 0 | MOD_0055_1112-Q1,1314-Q2 | MOD | Exempt | Not new
MOD_0057_1112-Q1 | Typhoon | AR 2014 | 1314-Q2 | MOD | Amber/Green | 1987-11-06 | 2024-03-30 | 1215.66 | 1215.57 | -0.09 | -7.4034e-05 | 20147.01 |  |  | Military Capability | 36.397 | MOD_0057_1112-Q1,1314-Q2 | MOD | Amber/Green | Not new
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2014 | 1314-Q2 | MOD | Amber/Red | 1998-03-01 | 2040-12-31 | 79.28 | 67.25 | -12.03 | -0.15174 | 1518.26 |  |  | Military Capability | 42.8364 | MOD_0061_1112-Q1,1314-Q2 | MOD | Amber/Red | Not new
MOD_0062_1112-Q1 | Wildcat | AR 2014 | 1314-Q2 | MOD | Amber/Red | 2001-12-01 | 2016-05-31 | 175.57 | 175.57 | 0 | 0 | 1661.36 |  |  | Military Capability | 14.4969 | MOD_0062_1112-Q1,1314-Q2 | MOD | Amber/Red | Not new
MOD_0065_1112-Q2 | CHINOOK (incl Project Julius) | AR 2014 | 1314-Q2 | MOD | Amber | 2008-04-01 | 2017-03-31 | 249.82 | 247.23 | -2.59 | -0.010367 | 1053.87 |  |  | Military Capability | 8.9966 | MOD_0065_1112-Q2,1314-Q2 | MOD | Amber | Not new
MOD_0067_1112-Q2 | Defence Core Network Services | AR 2014 | 1314-Q2 | MOD | Amber/Red | 2009-12-01 | 2020-03-02 | 33.51 | 29.62 | -3.89 | -0.11608 | 5632.58 |  |  | ICT | 10.2505 | MOD_0067_1112-Q2,1314-Q2 | MOD | Amber/Red | Not new
MOD_0069_1112-Q2 | Logistics Commodities Services Transformation | AR 2014 | 1314-Q2 | MOD | Exempt | 2011-08-01 | 2018-02-01 | 7.14 | 7.14 | 0 | 0 | Exempt under Section 43 of the Freedom of Information Act (2000) |  |  | Government Transformation and Service Delivery | 6.5051 | MOD_0069_1112-Q2,1314-Q2 | MOD | Exempt | Not new
MOD_0070_1112-Q2 | New Employment Model | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2011-05-02 | 2021-10-01 | 16.69 | 17.58 | 0.89 | 0.053325 | 85.82 |  |  | Government Transformation and Service Delivery | 10.4175 | MOD_0070_1112-Q2,1314-Q2 | MOD | Amber/Green | Not new
MOD_0071_1112-Q2 | Submarine Enterprise Performance Programme | AR 2014 | 1314-Q2 | MOD | Amber | 2010-05-31 | 2014-03-31 | 4.48 | 0.3 | -4.18 | -0.93304 | 12.42 |  |  | Government Transformation and Service Delivery | 3.833 | MOD_0071_1112-Q2,1314-Q2 | MOD | Amber | Not new
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2014 | 1314-Q2 | MOD | Amber | 1997-03-17 | 2024-03-31 | 549.02 | 534 | -15.02 | -0.027358 | 9867.58 |  |  | Military Capability | 27.039 | MOD_0076_1213-Q1,1314-Q2 | MOD | Amber | Not new
MOD_0077_1213-Q1 | Complex Weapons | AR 2014 | 1314-Q2 | MOD | Amber | 2008-03-31 | 0 | 450.09 | 389.59 | -60.5 | -0.13442 | 15948.67 |  |  | Military Capability | -108.2491 | MOD_0077_1213-Q1,1314-Q2 | MOD | Amber | Not new
MOD_0078_1213-Q1 | Core Production Capability | AR 2014 | 1314-Q2 | MOD | Green | 2012-04-01 | 2023-03-19 | 102.97 | 102.86 | -0.11 | -0.0010683 | 1232.35 |  |  | Military Capability | 10.9624 | MOD_0078_1213-Q1,1314-Q2 | MOD | Green | Not new
MOD_0079_1213-Q1 | Joint Combat Aircraft (Lightning) | AR 2014 | 1314-Q2 | MOD | Amber | 2001-10-01 | 2050-03-31 | 137.14 | 141.89 | 4.75 | 0.034636 | 15291.29 |  |  |  | 48.4956 | MOD_0079_1213-Q1,1314-Q2 | MOD | Amber | Not new
MOD_0080_1213-Q1 | Successor SSBN | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2011-04-14 | Exempt under Section 22 of the Freedom of Information Act (2000) | 472.46 | 507.4 | 34.94 | 0.073953 | Exempt under Section 43 of the Freedom of Information Act (2000) |  |  |  | 0 | MOD_0080_1213-Q1,1314-Q2 | MOD | Amber/Green | Not new
MOD_0081_1213-Q2 | Future Reserves 2020 | AR 2014 | 1314-Q2 | MOD | Amber/Red | 2011-09-30 | 2018-03-31 | 144.24 | 144.24 | 0 | 0 | 1810.26 |  |  | Government Transformation and Service Delivery | 6.4997 | MOD_0081_1213-Q2,1314-Q2 | MOD | Amber/Red | Not new
MOD_0056_1112-Q1 | Type 45 Destroyers | AR 2014 | 1314-Q2 | MOD | Green | 2000-08-15 | 2014-03-31 | 109.67 | 85.68 | -23.99 | -0.21875 | 5610.77 |  |  | Military Capability | 13.6235 | MOD_0056_1112-Q1,1314-Q2 | MOD | Green | Not new
MOD_0020_1112-Q1 | Defence Infrastructure Transformation Programme | AR 2014 | 1314-Q2 | MOD | Amber | 2011-01-03 | 2015-03-31 | 23.62 | 23.62 | 0 | 0 | 125.71 |  |  |  | 4.2382 | MOD_0020_1112-Q1,1314-Q2 | MOD | Amber | Not new
MOD_0016_1112-Q1 | Corporate Services Transformation Programme | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2010-07-02 | 2016-12-01 | 13.85 | 14.32 | 0.47 | 0.033935 | 41.46 |  |  | Government Transformation and Service Delivery | 6.4175 | MOD_0016_1112-Q1,1314-Q2 | MOD | Amber/Green | Not new
MOD_0022_1112-Q1 | End Crypto Units (ECU) | AR 2014 | 1314-Q2 | MOD | Exempt | 2007-08-31 | 2040-08-31 | 27.81 | 27.35 | -0.46 | -0.016541 | 188.43 |  |  |  | 33.0021 | MOD_0022_1112-Q1,1314-Q2 | MOD | Exempt | Not new
MOJ_0002_1112-Q1 | Court Estates Reform | AR 2014 | 1314-Q2 | MOJ | Green | 2010-05-10 | 2014-09-30 | 10.96 | 4.517 | -6.443 | -0.58786 | 45.44 |  |  | Government Transformation and Service Delivery | 4.3915 | MOJ_0002_1112-Q1,1314-Q2 | MOJ | Green | Not new
MOJ_0003_1112-Q1 | Electronic Monitoring | AR 2014 | 1314-Q2 | MOJ | Amber/Red | 2011-05-10 | 2013-09-30 | 100.541 | 33.421 | -67.12 | -0.66759 | 912.531 |  |  | Government Transformation and Service Delivery | 2.3929 | MOJ_0003_1112-Q1,1314-Q2 | MOJ | Amber/Red | Not new
MOJ_0004_1112-Q1 | Future IT Sourcing Programme (FITS) | AR 2014 | 1314-Q2 | MOJ | Amber | 2011-03-01 | 2016-04-01 | 31.3 | 31.3 | 0 | 0 | 1375.3 |  |  | ICT | 5.0869 | MOJ_0004_1112-Q1,1314-Q2 | MOJ | Amber | Not new
MOJ_0005_1112-Q1 | HMCTS Compliance & Enforcement Services Project | AR 2014 | 1314-Q2 | MOJ | Amber | 2010-08-31 | 2015-07-31 | 5.29 | 2.21 | -3.08 | -0.58223 | 12.19 |  |  | Government Transformation and Service Delivery | 4.9144 | MOJ_0005_1112-Q1,1314-Q2 | MOJ | Amber | Not new
MOJ_0006_1112-Q1 | Integrated Delivery Programme | AR 2014 | 1314-Q2 | MOJ | Amber | 2009-07-01 | 2014-03-01 | 10.814 | 10.814 | 0 | 0 | 68.798 |  |  | ICT | 4.6653 | MOJ_0006_1112-Q1,1314-Q2 | MOJ | Amber | Not new
MOJ_0007_1112-Q1 | Legal Aid Reform Implementation | AR 2014 | 1314-Q2 | MOJ | Green | 2011-04-01 | 2013-10-31 | 2.8029 | 2.8029 | 0 | 0 | 19.0598 |  |  | Government Transformation and Service Delivery | 2.5845 | MOJ_0007_1112-Q1,1314-Q2 | MOJ | Green | Not new
MOJ_0008_1112-Q1 | MoJ Shared Services | AR 2014 | 1314-Q2 | MOJ | Amber/Red | 2009-01-01 | 2015-07-07 | 31.3 | 14.236 | -17.064 | -0.54518 | 244.402 |  |  | ICT | 6.5106 | MOJ_0008_1112-Q1,1314-Q2 | MOJ | Amber/Red | Not new
MOJ_0015_1112-Q2 | NOMS ICTS Services (NIS) Programme (formally part of Quantum Re-compete Project) | AR 2014 | 1314-Q2 | MOJ | Amber | 2011-07-18 | 2014-11-30 | 88.7 | 88.7 | 0 | 0 | 248.82 |  |  | ICT | 3.3703 | MOJ_0015_1112-Q2,1314-Q2 | MOJ | Amber | Not new
MOJ_0018_1112-Q2 | Prison Competitions Phase 2 | AR 2014 | 1314-Q2 | MOJ | Amber | 2011-07-13 | 2014-01-31 | 39.6859 | 39.6859 | 0 | 0 | 786.6931 |  |  | Government Transformation and Service Delivery | 2.5544 | MOJ_0018_1112-Q2,1314-Q2 | MOJ | Amber | Not new
MOJ_0021_1213-Q2 | NOMS Organisational Restructure Programme | AR 2014 | 1314-Q2 | MOJ | Green | 2010-11-01 | 2013-10-30 | 0.61 | 0.45077 | -0.15923 | -0.26103 | 38.3744 |  |  |  | 2.9952 | MOJ_0021_1213-Q2,1314-Q2 | MOJ | Green | Not new
MOJ_0020_1213-Q2 | National Offender Management Information Systems (NOMIS) Programme | AR 2014 | 1314-Q2 | MOJ | Amber/Green | 2008-01-08 | 2013-10-31 | 20.93 | 17.9 | -3.03 | -0.14477 | 477.28 |  |  |  | 5.8125 | MOJ_0020_1213-Q2,1314-Q2 | MOJ | Amber/Green | Not new
HMT_0003_1112-Q1 | Yoda Project (Outsourced Services Retender Project) | AR 2014 | 1314-Q2 | NS&I | Green | 2009-04-05 | 2014-05-31 | 0.375 | 0.375 | 0 | 0 | 677.7103 |  |  | Government Transformation and Service Delivery | 5.1526 | HMT_0003_1112-Q1,1314-Q2 | NS&I | Green | Not new
ONS_0001_1112-Q1 | 2011 Census | AR 2014 | 1314-Q2 | ONS | Amber/Green | 2002-09-01 | 2014-03-31 | 10.1 | 10.1 | 0 | 0 | 481.632 |  |  | Government Transformation and Service Delivery | 11.5784 | ONS_0001_1112-Q1,1314-Q2 | ONS | Amber/Green | Not new
ONS_0002_1112-Q1 | Beyond 2011 Programme | AR 2014 | 1314-Q2 | ONS | Amber/Green | 2011-04-01 | 2015-03-31 | 8 | 7.52 | -0.48 | -0.06 | 25.1 |  |  | Government Transformation and Service Delivery | 3.9973 | ONS_0002_1112-Q1,1314-Q2 | ONS | Amber/Green | Not new
ONS_0003_1112-Q4 | Web Data Access (WDA) Project | AR 2014 | 1314-Q2 | ONS | Amber/Green | 2011-04-01 | 2013-12-31 | 3.36 | 3.36 | 0 | 0 | 16.108 |  |  | ICT | 2.7515 | ONS_0003_1112-Q4,1314-Q2 | ONS | Amber/Green | Not new
ONS_0004_1213-Q2 | Electronic Data Collection (EDC) | AR 2014 | 1314-Q2 | ONS | Amber/Red | 2012-04-02 | 2024-03-31 | 4.2283 | 4.2283 | 0 | 0 | 66.3501 |  |  | ICT | 11.9945 | ONS_0004_1213-Q2,1314-Q2 | ONS | Amber/Red | Not new
ONS_0005_1213-Q2 | ESA10/BPM6 Programme (European Systems of Accounting 2010) | AR 2014 | 1314-Q2 | ONS | Amber | 2011-02-05 | 2020-03-30 | 7.11 | 6.662 | -0.448 | -0.06301 | 57.847 |  |  | Government Transformation and Service Delivery | 9.1472 | ONS_0005_1213-Q2,1314-Q2 | ONS | Amber | Not new
BIS_0012_1213-Q4 | Business Bank Project | AR 2014 | 1314-Q2 | BEIS | Amber/Green | 2012-09-24 | 2014-11-15 | 237.92 | 185.569 | -52.351 | -0.22004 | 1567.45 |  |  | Government Transformation and Service Delivery | 2.141 | BIS_0012_1213-Q4,1314-Q2 | BEIS | Amber/Green | Joiner
CO_0008_1213-Q4 | Next Generation Shared Services | AR 2014 | 1314-Q2 | CO | Amber/Red | 2012-12-28 | 2015-04-30 | 8 | 8 | 0 | 0 | 11.6 |  |  | Government Transformation and Service Delivery | 2.3354 | CO_0008_1213-Q4,1314-Q2 | CO | Amber/Red | Joiner
CO_0009_1314-Q1 | New Civil Service 2015 Pension Scheme Implementation | AR 2014 | 1314-Q2 | CO | Amber | 2013-04-15 | 2016-06-30 | 0 | 0 | 0 | 0 | 0 |  |  | Government Transformation and Service Delivery | 3.2088 | CO_0009_1314-Q1,1314-Q2 | CO | Amber | Joiner
DH_0017_1112-Q1 | PHE Science Hub | AR 2014 | 1314-Q2 | DH | Amber/Red | 2013-06-28 | 2021-03-30 | 13 | 13.6 | 0.6 | 0.0462 | 6237.56 |  |  | Infrastructure and Construction | 7.7536 | DH_0017_1112-Q1,1314-Q2 | DH | Amber/Red | Not new
DH_0019_1112-Q1 | Royal Liverpool & Broadgreen ('World Class Hospitals; World Class Services - Renewing the Royal Liverpool University Hospital') | AR 2014 | 1314-Q2 | DH | No DCA | 2010-06-01 | 2016-11-01 | 7.5 | 7.5 | 0 | 0 | 837 |  |  | Infrastructure and Construction | 6.4203 | DH_0019_1112-Q1,1314-Q2 | DH | No DCA | Not new
DH_0020_1112-Q1 | Royal National Orthopaedic Hospital (RNOH) NHS Trust PFI Project | AR 2014 | 1314-Q2 | DH | No DCA | 2011-01-15 | 2016-11-28 | 0 | 0 | 0 | No departmental narrative | 208.79 |  |  | Infrastructure and Construction | 5.87 | DH_0020_1112-Q1,1314-Q2 | DH | No DCA | Not new
DH_0021_1112-Q1 | Sandwell and West Birmingham Hospitals NHS Trust - The Midland Metropolitan Hospital Project | AR 2014 | 1314-Q2 | DH | No DCA | 2008-10-01 | 2019-04-01 | 0 | 0 | 0 | No departmental narrative | 1116 |  |  | Infrastructure and Construction | 10.4969 | DH_0021_1112-Q1,1314-Q2 | DH | No DCA | Not new
DH_0027_1213-Q4 | South Acute Programme | AR 2014 | 1314-Q2 | DH | Amber | 2012-01-02 | 2017-06-27 | 40.4 | 42.69 | 2.29 | 0.0567 | 189.06 |  |  | ICT | 5.4839 | DH_0027_1213-Q4,1314-Q2 | DH | Amber | Joiner
DH_0028_1314-Q1 | General Practice System of Choice (GPSoC) Replacement | AR 2014 | 1314-Q2 | DH | Amber | 2012-01-26 | 2015-03-31 | 100.74 | 96.45 | -4.29 | -0.0426 | 319.03 |  |  | ICT | 3.1759 | DH_0028_1314-Q1,1314-Q2 | DH | Amber | Joiner
DH_0029_1314-Q1 | Liaison and Diversion Programme | AR 2014 | 1314-Q2 | DH | Amber/Red | 2011-04-01 | 2014-04-01 | 35 | 19.374 | -15.626 | -0.4465 | 59.474 |  |  | ICT | 3.0007 | DH_0029_1314-Q1,1314-Q2 | DH | Amber/Red | Joiner
DH_0030_1314-Q1 | National Pandemic Flu Service | AR 2014 | 1314-Q2 | DH | Amber | 2012-03-19 | 2015-12-01 | Exempt under section 43 of the FoI Act (2000) | Exempt under section 43 of the FoI Act (2000) | N/A | N/A | Exempt under section 43 of the FoI Act (2000) |  |  | Government Transformation and Service Delivery | 3.7016 | DH_0030_1314-Q1,1314-Q2 | DH | Amber | Joiner
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | AR 2014 | 1314-Q2 | DH | Amber/Red | 2012-01-01 | 2018-12-01 | 4.81 | 4.8688 | 0.058824 | 0.0122 | 1312.9441 |  |  | Infrastructure and Construction | 6.9158 | DH_0031_1314-Q1,1314-Q2 | DH | Amber/Red | Joiner
DH_0032_1314-Q1 | Rotavirus Immunisation Programme | AR 2014 | 1314-Q2 | DH | Green | 2009-03-05 | 2014-04-01 | 19.2 | 19.2 | 0 | 0 | 70.2 |  |  | Government Transformation and Service Delivery | 5.0732 | DH_0032_1314-Q1,1314-Q2 | DH | Green | Joiner
DH_0033_1314-Q1 | Seasonal Flu Extension to Children Programme | AR 2014 | 1314-Q2 | DH | Amber/Red | 2013-09-03 | 2017-09-01 | 34.2 | 34.2 | 0 | 0 | 719.5 |  |  |  | 3.9945 | DH_0033_1314-Q1,1314-Q2 | DH | Amber/Red | Joiner
DH_0035_1314-Q1 | Shingles Immunisation Programme | AR 2014 | 1314-Q2 | DH | Amber/Green | 2012-12-11 | 2013-11-01 | 51.3 | 51.3 | 0 | 0 | 171.53 |  |  | Government Transformation and Service Delivery | 0.8898 | DH_0035_1314-Q1,1314-Q2 | DH | Amber/Green | Joiner
DH_0036_1314-Q1 | Spine 2 | AR 2014 | 1314-Q2 | DH | Amber | 2010-05-10 | 2018-03-30 | 204 | 28.95 | -175.05 | -0.8581 | 857 |  |  | ICT | 7.8877 | DH_0036_1314-Q1,1314-Q2 | DH | Amber | Joiner
DH_0038_1314-Q2 | Health Visitor Programme | AR 2014 | 1314-Q2 | DH | Amber/Red | 2010-10-31 | 2015-06-30 | 123.8 | 123.8 | 0 | 0 | 335.8 |  |  | Government Transformation and Service Delivery | 4.6626 | DH_0038_1314-Q2,1314-Q2 | DH | Amber/Red | Joiner
DH_0039_1314-Q2 | NHS e-Referral Service | AR 2014 | 1314-Q2 | DH | Amber/Red | 2012-03-29 | 2018-03-31 | 12.43 | 12.43 | 0 | 0 | 212.03 |  |  | Government Transformation and Service Delivery | 6.0041 | DH_0039_1314-Q2,1314-Q2 | DH | Amber/Red | Joiner
DH_0041_1314-Q2 | Public Services Network for Health (PSNH) | AR 2014 | 1314-Q2 | DH | Red | 2012-03-29 | 2014-10-10 | 11.6 | 0.57 | -11.03 | -0.9509 | 748.16 |  |  | ICT | 2.5325 | DH_0041_1314-Q2,1314-Q2 | DH | Red | Joiner
FCO_0001_1112-Q1 | ABUJA: New Office and Residence | AR 2014 | 1314-Q2 | FCO | Amber | 2011-01-01 | 2017-12-01 | 0.66 | 0.66 | 0 | 0 | 39 |  |  | Infrastructure and Construction | 6.9158 | FCO_0001_1112-Q1,1314-Q2 | FCO | Amber | Not new
FCO_0006_1213-Q2 | UKERP | AR 2014 | 1314-Q2 | FCO | Amber | 2011-06-01 | 2016-08-01 | 4.43 | 4.43 | 0 | 0 | 82.425 |  |  | Infrastructure and Construction | 5.1691 | FCO_0006_1213-Q2,1314-Q2 | FCO | Amber | Not new
HMRC_0011_1314-Q1 | Digital Solutions Portfolio | AR 2014 | 1314-Q2 | HMRC | Amber | 2012-11-14 | 2015-04-05 | 37.76 | 32.03 | -5.73 | -0.15175 | 134.29 |  |  | Government Transformation and Service Delivery | 2.3874 | HMRC_0011_1314-Q1,1314-Q2 | HMRC | Amber | Joiner
MOD_0064_1112-Q2 | Carrier Enabled Power Projection (CEPP) | AR 2014 | 1314-Q2 | MOD | Amber/Red | 2011-01-31 | 2030-12-31 | 2.5 | 1.5 | -1 | -0.4 | 23.75 |  |  |  | 19.9151 | MOD_0064_1112-Q2,1314-Q2 | MOD | Amber/Red | Joiner
MOD_0066_1112-Q2 | Corporate Services Systems Convergence Programme | AR 2014 | 1314-Q2 | MOD | Amber | 2010-02-01 | 2020-02-28 | 9.32 | 9.78 | 0.46 | 0.049356 | 66.55 |  |  | Government Transformation and Service Delivery | 10.0726 | MOD_0066_1112-Q2,1314-Q2 | MOD | Amber | Joiner
MOD_0082_1213-Q3 | Next Generation Estates Contracts | AR 2014 | 1314-Q2 | MOD | Amber | 2009-03-02 | 2014-04-01 | 20.84 | 20.84 | 0 | 0 | 3328.79 |  |  | Government Transformation and Service Delivery | 5.0815 | MOD_0082_1213-Q3,1314-Q2 | MOD | Amber | Joiner
MOD_0083_1213-Q3 | Whole Fleet Management | AR 2014 | 1314-Q2 | MOD | Amber | 2001-01-31 | 2025-06-30 | 57.29 | 32.23 | -25.06 | -0.43742 | 1448.56 |  |  | Military Capability | 24.4107 | MOD_0083_1213-Q3,1314-Q2 | MOD | Amber | Joiner
MOD_0084_1213-Q4 | Army 2020 | AR 2014 | 1314-Q2 | MOD | Amber | 2011-08-31 | 2020-04-30 | 0 | 0 | 0 | 0 | 0 |  |  | Government Transformation and Service Delivery | 8.6653 | MOD_0084_1213-Q4,1314-Q2 | MOD | Amber | Joiner
MOD_0085_1314-Q2 | Army Basing Programme | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2013-05-22 | 2020-03-31 | 0 | 0 | 0 | 0 | 0 |  |  | Government Transformation and Service Delivery | 6.8583 | MOD_0085_1314-Q2,1314-Q2 | MOD | Amber/Green | Joiner
MOD_0086_1314-Q2 | Mounted Close Combat | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2010-03-16 | 2033-12-31 | 168.82 | 104.65 | -64.17 | -0.38011 | 9631.3 |  |  | Military Capability | 23.7947 | MOD_0086_1314-Q2,1314-Q2 | MOD | Amber/Green | Joiner
MOD_0087_1314-Q2 | The Material Strategy | AR 2014 | 1314-Q2 | MOD | Amber | 2011-05-02 | 2016-04-01 | 32.57 | 31.35 | -1.22 | -0.037458 | 66.15 |  |  |  | 4.9172 | MOD_0087_1314-Q2,1314-Q2 | MOD | Amber | Joiner
MOJ_0021_1314-Q1 | Common Platform | AR 2014 | 1314-Q2 | MOJ | Amber/Red | 2012-11-01 | 2017-01-31 | 0 | 0 | 0 | No departmental narrative | 0 |  |  | ICT | 4.2491 | MOJ_0021_1314-Q1,1314-Q2 | MOJ | Amber/Red | Joiner
MOJ_0022_1314-Q1 | Legal Aid Transformation | AR 2014 | 1314-Q2 | MOJ | Amber | 2012-12-04 | 2014-12-31 | 0 | 0 | 0 | No departmental narrative | 0 |  |  | Government Transformation and Service Delivery | 2.0726 | MOJ_0022_1314-Q1,1314-Q2 | MOJ | Amber | Joiner
MOJ_0023_1314-Q1 | New Prison -Wales | AR 2014 | 1314-Q2 | MOJ | Green | 2013-01-10 | 2018-05-31 | 0 | 0 | 0 | No departmental narrative | 252.3 |  |  | Infrastructure and Construction | 5.3854 | MOJ_0023_1314-Q1,1314-Q2 | MOJ | Green | Joiner
MOJ_0024_1314-Q1 | Prison Unit Cost Programme | AR 2014 | 1314-Q2 | MOJ | Amber/Green | 2012-11-20 | 2016-12-01 | 117.5 | 117.5 | 0 | 0 | 212 |  |  | Government Transformation and Service Delivery | 4.0301 | MOJ_0024_1314-Q1,1314-Q2 | MOJ | Amber/Green | Joiner
MOJ_0025_1314-Q1 | Rehabilitation Programme | AR 2014 | 1314-Q2 | MOJ | Exempt | 2012-11-05 | Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests) | Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests) | Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests) | Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests) | Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests) | Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests) |  |  | Government Transformation and Service Delivery | 0 | MOJ_0025_1314-Q1,1314-Q2 | MOJ | Exempt | Joiner
MOJ_0026_1314-Q1 | Transforming Youth Custody | AR 2014 | 1314-Q2 | MOJ | Amber | 2012-11-05 | 2018-07-15 | 0 | 0 | 0 | No departmental narrative | 0 |  |  | Government Transformation and Service Delivery | 5.6893 | MOJ_0026_1314-Q1,1314-Q2 | MOJ | Amber | Joiner
MOJ_0027_1314-Q2 | CJS Efficiency Programme Phase 2 | AR 2014 | 1314-Q2 | MOJ | Amber | 2013-04-30 | 2016-12-31 | 11.65 | 11.33 | -0.32 | -0.027468 | 102.85 |  |  | ICT | 3.6715 | MOJ_0027_1314-Q2,1314-Q2 | MOJ | Amber | Joiner
MOJ_0028_1314-Q2 | HMCTS Reform | AR 2014 | 1314-Q2 | MOJ | Amber/Red | 2013-03-21 | 2016-01-01 | 0 | 0 | 0 | No departmental narrative | 0 |  |  | Government Transformation and Service Delivery | 2.7817 | MOJ_0028_1314-Q2,1314-Q2 | MOJ | Amber/Red | Joiner
BIS_0013_1213-Q4 | Royal Mail Sale of Shares | AR 2014 | 1314-Q2 | BEIS | Amber | 2012-04-01 | 2013-10-17 | 380 | 350 | -30 | -0.078947 | 31.2 |  |  |  | 1.5441 | BIS_0013_1213-Q4,1314-Q2 | BEIS | Amber | Joiner
DH_0037_1314-Q1 | Spine Extension | AR 2014 | 1314-Q2 | DH | Amber/Green | 2011-06-28 | 2014-12-31 | 57.989 | 55.51 | -2.479 | -0.0427 | 104.5124 |  |  | ICT | 3.5099 | DH_0037_1314-Q1,1314-Q2 | DH | Amber/Green | Joiner
DH_0040_1314-Q2 | NHSmail2 | AR 2014 | 1314-Q2 | DH | Amber | 2012-03-29 | 2014-11-18 | 0.83 | 1.44 | 0.61 | 0.7349 | 157.38 |  |  | ICT | 2.6393 | DH_0040_1314-Q2,1314-Q2 | DH | Amber | Joiner
DFT_0019_1314-Q1 | Essex Thameside Franchise Competition | AR 2014 | 1314-Q2 | DFT | Amber/Red | 2013-03-26 | 2014-11-30 | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) | Exempt under Section 43(2) of the Freedom of Information Act (2000) |  |  |  | 1.681 | DFT_0019_1314-Q1,1314-Q2 | DFT | Amber/Red | Joiner
DH_0034_1314-Q1 | Shared Services Programme | AR 2014 | 1314-Q2 | DH | Amber | 2011-12-01 | 2015-03-31 | 3.97 | 3.97 | 0 | 0 | 72.19 |  |  | Government Transformation and Service Delivery | 3.3292 | DH_0034_1314-Q1,1314-Q2 | DH | Amber | Joiner
HO_0028_1314-Q2 | Tinsley House Immigration Removal Centre Expansion | AR 2014 | 1314-Q2 | HO | Amber/Green | 2013-01-01 | 2015-06-01 | 0.08 | 0.08 | 0 | 0 | 217.38 |  |  | Infrastructure and Construction | 2.412 | HO_0028_1314-Q2,1314-Q2 | HO | Amber/Green | Joiner
CO_0007_1213-Q4 | Civil Service Reform Programme | AR 2014 | 1314-Q2 | CO | Amber | 2012-06-19 | 2015-12-31 | 2.99 | 2.99 | 0 | 0 | 10.67 |  |  | Government Transformation and Service Delivery | 3.5318 | CO_0007_1213-Q4,1314-Q2 | CO | Amber | Joiner
MOD_0074_1112-Q3 | Defence Reform Programme | AR 2014 | 1314-Q2 | MOD | Amber/Green | 2011-07-01 | 2014-04-01 | 1.78 | 1.78 | 0 | 0 | 4.63 |  |  | Government Transformation and Service Delivery | 2.7515 | MOD_0074_1112-Q3,1314-Q2 | MOD | Amber/Green | Joiner
HO_0027_1314-Q2 | Border Systems Programme | AR 2014 | 1314-Q2 | HO | Amber/Red | 2013-04-29 | 2024-03-30 | 0 | 0 | 0 | 0 | 0 |  |  | ICT | 10.9185 | HO_0027_1314-Q2,1314-Q2 | HO | Amber/Red | Joiner
BIS_0001_1112-Q1 | BIS Shared Services | AR 2015 | 1415-Q2 | BEIS | Amber | 2011-05-04 | 2015-04-01 | 1.9 | 1.9 | 0 | 0 | 26.19 |  |  | Government Transformation and Service Delivery | 3.9097 | BIS_0001_1112-Q1,1415-Q2 | BEIS | Amber | Not new
BIS_0005_1112-Q1 | Further Education 24+ Learning Loans Programme | AR 2015 | 1415-Q2 | BEIS | Amber/Green | 2010-11-30 | 2013-10-31 | 242.66 | 122.55 | -120.11 | -0.49497 | 303 |  |  | Government Transformation and Service Delivery | 2.9185 | BIS_0005_1112-Q1,1415-Q2 | BEIS | Amber/Green | Not new
BIS_0008_1112-Q1 | ICR Monetisation | AR 2015 | 1415-Q2 | DFE | Amber | 2010-03-01 | 2018-12-31 | 6.96 | 3.88 | -3.08 | -0.44253 | 29.48 |  |  | Government Transformation and Service Delivery | 8.835 | BIS_0008_1112-Q1,1415-Q2 | DFE | Amber | Not new
BIS_0009_1112-Q1 | The Francis Crick Institute (formerly UKCMRI) | AR 2015 | 1415-Q2 | BEIS | Amber/Green | 2006-10-01 | 2017-12-21 | 18 | 18 | 0 | 0 | 753 |  | 469.42 | Infrastructure and Construction | 11.2225 | BIS_0009_1112-Q1,1415-Q2 | BEIS | Amber/Green | Not new
BIS_0011_1213-Q1 | SLC Transformation Programme | AR 2015 | 1415-Q2 | BEIS | Amber/Red | 2012-03-19 | 2017-03-31 | 46.29 | 46.46 | 0.17 | 0.0036725 | 139.13 |  |  | Government Transformation and Service Delivery | 5.0322 | BIS_0011_1213-Q1,1415-Q2 | BEIS | Amber/Red | Not new
CO_0001_1112-Q1 | Electoral Registration Transformation Programme | AR 2015 | 1415-Q2 | CO | Amber/Green | 2010-02-01 | 2016-03-31 | 65.5 | 65.5 | 0 | 0 | 173.65 | 173.65 |  | Government Transformation and Service Delivery | 6.1602 | CO_0001_1112-Q1,1415-Q2 | CO | Amber/Green | Not new
CO_0004_1112-Q1 | National Citizen Service | AR 2015 | 1415-Q2 | CO | Amber/Green | 2011-10-01 | 2015-03-01 | 140 | 140 | 0 | 0 | 437 | 225 |  | Government Transformation and Service Delivery | 3.4141 | CO_0004_1112-Q1,1415-Q2 | CO | Amber/Green | Not new
CO_0005_1112-Q1 | National Cyber Security Programme | AR 2015 | 1415-Q2 | CO | Green | 2011-04-01 | 2016-04-01 | 210 | 220 | 10 | 0.047619 | 860 | 860 |  | ICT | 5.0021 | CO_0005_1112-Q1,1415-Q2 | CO | Green | Not new
DCLG_0006_1112-Q4 | Enterprise Zones Programme | AR 2015 | 1415-Q2 | DCLG | Amber | 2011-03-23 | 2038-03-31 | 220.3 | 220.3 | 0 | 0 | 228.3 |  |  | Government Transformation and Service Delivery | 27.0226 | DCLG_0006_1112-Q4,1415-Q2 | DCLG | Amber | Not new
DCLG_0004_1112-Q1 | The Future of Local Audit | AR 2015 | 1415-Q2 | DCLG | Amber | 2011-06-30 | 2012-11-01 | 45.08 | 12.08 | -33 | -0.73203 | 45.08 |  |  | Government Transformation and Service Delivery | 1.3415 | DCLG_0004_1112-Q1,1415-Q2 | DCLG | Amber | Not new
DCMS_0001_1112-Q1 | Broadband Delivery Programme | AR 2015 | 1415-Q2 | DCMS | Amber/Green | 2010-12-06 | 2017-12-31 | 321.35 | 300.67 | -20.68 | -0.064354 | 792.36 |  | 0 | Infrastructure and Construction | 7.0691 | DCMS_0001_1112-Q1,1415-Q2 | DCMS | Amber/Green | Not new
DCMS_0004_1112-Q1 | The Tate Modern Project | AR 2015 | 1415-Q2 | DCMS | Amber/Red | 2010-01-01 | 2016-12-31 | 0 | 0 | 0 | 0% | 215 |  | 164.69 | Infrastructure and Construction | 6.9979 | DCMS_0004_1112-Q1,1415-Q2 | DCMS | Amber/Red | Not new
DCMS_0005_1112-Q1 | World Conservation and Exhibitions Centre | AR 2015 | 1415-Q2 | DCMS | Green | 2008-03-31 | 2014-04-01 | 0 | 0 | 0 | 0% | 135 |  | 112.45 | Infrastructure and Construction | 6.0014 | DCMS_0005_1112-Q1,1415-Q2 | DCMS | Green | Not new
DCMS_0006_1112-Q4 | Mobile Infrastructure Project | AR 2015 | 1415-Q2 | DCMS | Amber/Red | 2011-10-01 | 2016-03-31 | 71.54 | 25.59 | -45.95 | -0.6423 | 157.11 |  | 0 | ICT | 4.4983 | DCMS_0006_1112-Q4,1415-Q2 | DCMS | Amber/Red | Not new
DCMS_0007_1112-Q4 | Urban Broadband Fund - Super-Connected City Initiative | AR 2015 | 1415-Q2 | DCMS | Amber | 2012-12-05 | 2015-03-31 | 117.58 | 107.24 | -10.34 | -0.08794 | 152.08 |  | 0 | Infrastructure and Construction | 2.3162 | DCMS_0007_1112-Q4,1415-Q2 | DCMS | Amber | Not new
BIS_0010_1112-Q4 | Project Eagle (formerly Urenco Future Options) | AR 2015 | 1415-Q2 | BEIS | Amber/Red | 2010-02-01 | 2015-10-01 | 5.295 | 3.65 | -1.645 | -0.31067 | 23.725 |  |  | Government transformation and Service Delivery | 5.6619 | BIS_0010_1112-Q4,1415-Q2 | BEIS | Amber/Red | Not new
DECC_0003_1112-Q1 | Dounreay Parent Body Organisation (PBO) - Delivery Phase | AR 2015 | 1415-Q2 | BEIS | Green | 2009-09-21 | 2025-12-31 | 162.859 | 162.859 | 0 | 0 | 1678.2192 |  |  | Infrastructure and Construction | 16.2765 | DECC_0003_1112-Q1,1415-Q2 | BEIS | Green | Not new
DECC_0004_1112-Q1 | ELECTRICITY MARKET REFORM PROGRAMME | AR 2015 | 1415-Q2 | BEIS | Amber | 2010-12-16 | 2030-12-31 | 36.1 | 35.1 | -1 | -0.027701 | 47513.95 |  | 47226.29 | Government Transformation and Service Delivery | 20.0411 | DECC_0004_1112-Q1,1415-Q2 | BEIS | Amber | Not new
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2015 | 1415-Q2 | BEIS | Amber | 2008-06-12 | 2040-12-31 | 26.38 | 26.38 | 0 | 0 | 11252.48 |  |  | Infrastructure and Construction | 32.553 | DECC_0005_1112-Q1,1415-Q2 | BEIS | Amber | Not new
DECC_0009_1112-Q1 | Renewable Heat Incentive | AR 2015 | 1415-Q2 | BEIS | Amber | 2008-11-30 | 2014-12-01 | 231.79 | 233 | 1.21 | 0.0052202 | 43658.13 |  | 0 | Government Transformation and Service Delivery | 6.0014 | DECC_0009_1112-Q1,1415-Q2 | BEIS | Amber | Not new
DECC_0010_1112-Q1 | Smart Meters Implementation Programme | AR 2015 | 1415-Q2 | BEIS | Amber | 2009-12-02 | 2020-12-31 | 11.38 | 13.135 | 1.755 | 0.15422 | 19258 |  | 19026.5736 | Government Transformation and Service Delivery | 11.0801 | DECC_0010_1112-Q1,1415-Q2 | BEIS | Amber | Not new
DECC_0011_1112-Q3 | Carbon Capture & Storage Commercialisation Programme | AR 2015 | 1415-Q2 | BEIS | Amber | 2011-10-25 | 2050-03-31 | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) |  | exempt | Infrastructure and Construction | 38.4312 | DECC_0011_1112-Q3,1415-Q2 | BEIS | Amber | Not new
DECC_0012_1213-Q1 | FID Enabling for Hinkley Point C | AR 2015 | 1415-Q2 | BEIS | Exempt | 2011-09-01 | 2015-04-30 | 3.681 | 6.607 | 2.926 | 0.79489 | 14470.3337 |  | 14451.9327 | Infrastructure and Construction | 3.6605 | DECC_0012_1213-Q1,1415-Q2 | BEIS | Exempt | Not new
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | AR 2015 | 1415-Q2 | BEIS | Amber/Green | 2012-04-03 | 2028-09-01 | 428 | 390 | -38 | -0.088785 | 3860 |  |  | Infrastructure and Construction | 16.4134 | DECC_0013_1213-Q1,1415-Q2 | BEIS | Amber/Green | Not new
DEFRA_0001_1112-Q1 | CAP Delivery Programme | AR 2015 | 1415-Q2 | DEFRA | Amber/Red | 2011-01-01 | 2016-12-01 | 54.593 | 52.835 | -1.758 | -0.032202 | 154.789 |  |  | Government transformation and Service Delivery | 5.9165 | DEFRA_0001_1112-Q1,1415-Q2 | DEFRA | Amber/Red | Not new
DECC_0014_1314-Q1 | FID Enabling for Renewables | AR 2015 | 1415-Q2 | BEIS | Amber | 2012-12-17 | 2014-11-30 | 1.024 | 1.177 | 0.153 | 0.14941 | 22486.1985 |  | 22481.7245 | Infrastructure and Construction | 1.9521 | DECC_0014_1314-Q1,1415-Q2 | BEIS | Amber | Not new
DEFRA_0004_1112-Q1 | Thames Estuary Programme Phase 1 (TEP1) | AR 2015 | 1415-Q2 | DEFRA | Green | 2010-04-01 | 2025-12-31 | 1.37 | 2.15 | 0.78 | 0.56934 | 318.424 |  |  | Infrastructure and Construction | 15.7509 | DEFRA_0004_1112-Q1,1415-Q2 | DEFRA | Green | Not new
DEFRA_0005_1213-Q3 | Thames Tideway Tunnel | AR 2015 | 1415-Q2 | DEFRA | Amber/Red | 2010-09-07 | 2023-12-31 | 2.48 | 2.48 | 0 | 0 | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) |  | exempt | Infrastructure and Construction | 13.3142 | DEFRA_0005_1213-Q3,1415-Q2 | DEFRA | Amber/Red | Not new
DFE_0001_1112-Q1 | Building Schools for the Future (BSF) | AR 2015 | 1415-Q2 | DFE | Green | 2004-04-01 | 2017-07-02 | 95 | 95 | 0 | 0 | 6283 |  | 0 | Infrastructure and Construction | 13.2512 | DFE_0001_1112-Q1,1415-Q2 | DFE | Green | Not new
DFE_0004_1415-Q2 | Priority School Building Programme - Capital | AR 2015 | 1415-Q2 | DFE | Amber/Red | 2011-07-19 | 2019-01-01 | 607.3 | 358.4 | -248.9 | -0.40985 | 2023.34 |  |  | Infrastructure and Construction | 7.4552 | DFE_0004_1415-Q2,1415-Q2 | DFE | Amber/Red | Joiner
DFE_0005_1415-Q2 | Priority School Building Programme - Private Finance | AR 2015 | 1415-Q2 | DFE | Amber/Red | 2011-07-19 | 2017-07-31 | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept |  |  | Infrastructure and Construction | 6.0342 | DFE_0005_1415-Q2,1415-Q2 | DFE | Amber/Red | Joiner
DFID_0001_1112-Q1 | St Helena Airport | AR 2015 | 1415-Q2 | DFID | Amber/Green | 2005-03-15 | 2026-08-31 | 33.54 | 34.57 | 1.03 | 0.03071 | 445.17 |  | 159.62 | Infrastructure and Construction | 21.462 | DFID_0001_1112-Q1,1415-Q2 | DFID | Amber/Green | Not new
DFT_0001_1112-Q1 | Crossrail | AR 2015 | 1415-Q2 | DFT | Amber/Green | 2008-07-22 | 2019-12-31 | 1083.5 | 1083.5 | 0 | 0 | 14714.37 |  | 9478 | Infrastructure and Construction | 11.4415 | DFT_0001_1112-Q1,1415-Q2 | DFT | Amber/Green | Not new
DFT_0015_1112-Q1 | Shared Services Implementation Programme | AR 2015 | 1415-Q2 | DFT | Amber/Red | 2010-12-10 | 2015-10-01 | 21.7 | 23.91 | 2.21 | 0.10184 | 222.27 |  | 0 | ICT | 4.8077 | DFT_0015_1112-Q1,1415-Q2 | DFT | Amber/Red | Not new
DFT_0004_1112-Q1 | High Speed Rail Programme | AR 2015 | 1415-Q2 | DFT | Amber/Red | 2011-02-28 | 2033-12-31 | 380.01 | 483.01 | 103 | 0.27105 | 42559.51 |  | 0 | Infrastructure and Construction | 22.8392 | DFT_0004_1112-Q1,1415-Q2 | DFT | Amber/Red | Not new
DFT_0005_1112-Q1 | Intercity Express Programme (IEP) | AR 2015 | 1415-Q2 | DFT | Amber/Green | 2005-06-01 | 2020-02-06 | 4 | 5.01 | 1.01 | 0.2525 | 1308.35 |  | 1222 | Infrastructure and Construction | 14.6831 | DFT_0005_1112-Q1,1415-Q2 | DFT | Amber/Green | Not new
DFT_0009_1112-Q1 | Periodic Review 2013 (Rail Investment Strategy - HLOS & SOFA) | AR 2015 | 1415-Q2 | DFT | Green | 2011-08-17 | 2012-07-31 | 3164.93 | 2764.1 | -1083.03 | -0.28152 | 16840.61 |  | 0 | Infrastructure and Construction | 0.95551 | DFT_0009_1112-Q1,1415-Q2 | DFT | Green | Not new
DFT_0014_1112-Q1 | Search & Rescue Helicopters (SARH) | AR 2015 | 1415-Q2 | DFT | Amber/Green | 2011-02-08 | 2017-09-08 | 0 | 0 | 0 | 0% | 1923 |  | 0 | Infrastructure and Construction | 6.5818 | DFT_0014_1112-Q1,1415-Q2 | DFT | Amber/Green | Not new
DH_0003_1112-Q1 | Brighton & Sussex University Hospitals NHS Trust (3Ts Programme - The development of a leading teaching, trauma and tertiary care centre) | AR 2015 | 1415-Q2 | DH Capital | Amber/Green | 2012-01-27 | 2021-12-24 | 28.1257 | 33.75 | 5.6243 | 0.19997 | 445.7638 |  | 0 | Infrastructure and Construction | 9.9083 | DH_0003_1112-Q1,1415-Q2 | DH | Amber/Green | Not new
DFT_0016_1112-Q1 | Thameslink | AR 2015 | 1415-Q2 | DFT | Amber | 2005-07-01 | 2018-12-31 | 40.7 | 36.64 | -4.06 | -0.099754 | 4897.82 |  | 4547.25 | Infrastructure and Construction | 13.5003 | DFT_0016_1112-Q1,1415-Q2 | DFT | Amber | Not new
DH_0004_1112-Q1 | Broadmoor Redevelopment Programme | AR 2015 | 1415-Q2 | DH Capital | Green | 2012-07-10 | 2020-02-11 | 42.11 | 25.92 | -16.19 | -0.38447 | 287.42 |  | 0 | Infrastructure and Construction | 7.5893 | DH_0004_1112-Q1,1415-Q2 | DH | Green | Not new
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | AR 2015 | 1415-Q2 | DFT | Amber/Green | 2012-09-01 | 2021-09-30 | 23.5 | 17.49 | -6.01 | -0.25574 | 1519.32 |  | 0 | Infrastructure and Construction | 9.0787 | DFT_0020_1314-Q2,1415-Q2 | DFT | Amber/Green | Not new
DH_0007_1112-Q1 | E&N Herts NHS Trust - Lister Hospital ('Our Changing Hospitals' Phase 4 Programme) | AR 2015 | 1415-Q2 | DH Capital | Amber/Green | 2011-08-04 | 2014-03-17 | 0 | 21.561 | 21.561 |  | 212.03 |  |  | Infrastructure and Construction | 2.6174 | DH_0007_1112-Q1,1415-Q2 | DH | Amber/Green | Not new
DFT_0021_1314-Q3 | Rail Franchising Programme | AR 2015 | 1415-Q2 | DFT | Amber | 2013-03-26 | 2022-12-31 | -2.6 | 3.3 | 5.9 | -2.2692 | 134.2 |  | 0 | Infrastructure and Construction | 9.7659 | DFT_0021_1314-Q3,1415-Q2 | DFT | Amber | Joiner
DH_0008_1112-Q1 | Electronic Prescription Service (EPS) Release 2 | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2003-01-01 | 2016-12-31 | 4.2795 | 4.545 | 0.2655 | 0.06204 | 77.7446 |  | 0 | Government Transformation and Service Delivery | 13.9986 | DH_0008_1112-Q1,1415-Q2 | DH | Amber | Not new
DH_0013_1112-Q1 | Mersey Care NHS LIFT scheme (TIME - To Improve Mental Health Environments) | AR 2015 | 1415-Q2 | DH Capital | Amber/Green | 2011-09-16 | 2015-01-20 | 1.74 | 0.69 | -1.05 | -0.60345 | 208.8 |  | 0 | Infrastructure and Construction | 3.3457 | DH_0013_1112-Q1,1415-Q2 | DH | Amber/Green | Not new
DH_0015_1112-Q1 | CSC LSP Delivery Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2003-06-23 | 2016-07-31 | 213.76 | 134.11 | -79.65 | -0.37261 | 2294.07 |  |  | ICT | 13.1061 | DH_0015_1112-Q1,1415-Q2 | DH | Amber/Red | Not new
DWP_0003_1112-Q1 | Child Maintenance Group Change | AR 2015 | 1415-Q2 | DWP | Amber/Green | 2009-08-01 | 2015-12-31 | 86.66 | 69.179 | -17.481 | -0.20172 | 1218.33 |  |  | Government Transformation and Service Delivery | 6.4148 | DWP_0003_1112-Q1,1415-Q2 | DWP | Amber/Green | Not new
DWP_0005_1112-Q1 | Automatic Enrolment Programme | AR 2015 | 1415-Q2 | DWP | Amber | 2007-05-01 | 2018-11-30 | 117.5 | 120.209 | 2.709 | 0.023055 | 995.4 |  |  | Government Transformation and Service Delivery | 11.5838 | DWP_0005_1112-Q1,1415-Q2 | DWP | Amber | Not new
DWP_0009_1112-Q1 | Universal Credit | AR 2015 | 1415-Q2 | DWP | Amber/Red | 2011-11-17 | 2020-04-30 | 323.7996 | 323.7996 | 0 | 0 | 15844.0166 |  | 0 | Government Transformation and Service Delivery | 8.4517 | DWP_0009_1112-Q1,1415-Q2 | DWP | Amber/Red | Not new
DWP_0011_1112-Q2 | Personal Independence Payment Programme | AR 2015 | 1415-Q2 | DWP | Amber/Red | 2011-10-31 | 2016-03-31 | 231.48 | 303.611 | 72.131 | 0.31161 | 2525.94 |  |  | Government Transformation and Service Delivery | 4.4162 | DWP_0011_1112-Q2,1415-Q2 | DWP | Amber/Red | Not new
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | AR 2015 | 1415-Q2 | DWP | Amber | 2012-04-02 | 2017-03-31 | 111.3 | 98.81 | -12.49 | -0.11222 | 838.9 |  | 0 | Government Transformation and Service Delivery | 4.9938 | DWP_0016_1213-Q2,1415-Q2 | DWP | Amber | Not new
DH_0017_1112-Q1 | PHE Science Hub | AR 2015 | 1415-Q2 | DH Capital | Amber | 2013-08-09 | 2021-03-30 | 29.68 | 15.67 | -14.01 | -0.47204 | 10447.57 |  | 0 | Infrastructure and Construction | 7.6386 | DH_0017_1112-Q1,1415-Q2 | DH | Amber | Not new
FCO_0004_1112-Q1 | ICTRe-procurement | AR 2015 | 1415-Q2 | FCO | Amber/Red | 2011-01-01 | 2013-11-30 | 53.4 | 49.8 | -3.6 | -0.067416 | 242.1 |  |  | ICT | 2.9131 | FCO_0004_1112-Q1,1415-Q2 | FCO | Amber/Red | Not new
HMRC_0002_1112-Q1 | Debt Staff Reinvestment | AR 2015 | 1415-Q2 | HMRC | Green | 2011-04-01 | 2015-04-01 | 22.54 | 22.54 | 0 | 0 | 56.418 |  |  | Government Transformation and Service Delivery | 4 | HMRC_0002_1112-Q1,1415-Q2 | HMRC | Green | Not new
HMRC_0004_1112-Q1 | One Click | AR 2015 | 1415-Q2 | HMRC | Amber/Green | 2010-03-24 | 2013-10-16 | 8.65 | 8.73 | 0.08 | 0.0092486 | 111.06 |  |  | Government Transformation and Service Delivery | 3.5647 | HMRC_0004_1112-Q1,1415-Q2 | HMRC | Amber/Green | Not new
HMRC_0006_1112-Q1 | Real Time Information (RTI) | AR 2015 | 1415-Q2 | HMRC | Amber/Green | 2010-07-05 | 2015-06-30 | 45.87 | 45.701 | -0.169 | -0.0036843 | 333.02 |  |  | ICT | 4.9856 | HMRC_0006_1112-Q1,1415-Q2 | HMRC | Amber/Green | Not new
HMRC_0007_1112-Q2 | Expanding the use of Debt Collection Agencies | AR 2015 | 1415-Q2 | HMRC | Green | 2011-04-01 | 2015-03-31 | 14.49 | 14.123 | -0.367 | -0.025328 | 69.29 |  |  | Government Transformation and Service Delivery | 3.9973 | HMRC_0007_1112-Q2,1415-Q2 | HMRC | Green | Not new
HMRC_0008_1112-Q2 | Organised Crime | AR 2015 | 1415-Q2 | HMRC | Amber/Green | 2010-11-01 | 2014-06-30 | 22.039 | 21.73 | -0.309 | -0.014021 | 74.7 |  |  | Government Transformation and Service Delivery | 3.6605 | HMRC_0008_1112-Q2,1415-Q2 | HMRC | Amber/Green | Not new
HMRC_0009_1112-Q2 | Volume Crime | AR 2015 | 1415-Q2 | HMRC | Green | 2011-04-01 | 2013-05-29 | 11.05 | 11.02 | -0.03 | -0.0027149 | 42.05 |  |  | Government Transformation and Service Delivery | 2.1602 | HMRC_0009_1112-Q2,1415-Q2 | HMRC | Green | Not new
HMT_0001_1112-Q1 | Equitable Life Payment Scheme | AR 2015 | 1415-Q2 | HMT | Green | 2010-05-01 | 2015-12-31 | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept |  |  | Government Transformation and Service Delivery | 5.6674 | HMT_0001_1112-Q1,1415-Q2 | HMT | Green | Not new
HO_0007_1112-Q1 | NCA ICTModernisation Programme (was SOCA ISOT) | AR 2015 | 1415-Q2 | NCA | Amber/Red | 2008-04-01 | 2013-09-30 | 33.73 | 38.74 | 5.01 | 0.14853 | 398.65 |  |  | ICT | 5.4976 | HO_0007_1112-Q1,1415-Q2 | NCA | Amber/Red | Not new
HO_0008_1112-Q1 | Schengen Information System (SIS II) Programme | AR 2015 | 1415-Q2 | HO | Amber/Red | 2006-04-01 | 2015-03-31 | 14.25 | 16.66 | 2.41 | 0.16912 | 190.57 |  | 0 | ICT | 8.9966 | HO_0008_1112-Q1,1415-Q2 | HO | Amber/Red | Not new
HO_0009_1112-Q1 | Transforming the Customer Experience (Formerly A&E) | AR 2015 | 1415-Q2 | HO | Amber/Green | 2007-05-14 | 2014-11-01 | 11 | 11.26 | 0.26 | 0.023636 | 201.411 |  |  | ICT | 7.4689 | HO_0009_1112-Q1,1415-Q2 | HO | Amber/Green | Not new
HO_0011_1112-Q2 | Disclosure and Barring Service (DBS) Programme | AR 2015 | 1415-Q2 | HO | Amber | 2010-12-29 | 2015-07-31 | 136 | 136 | 0 | 0 | 741.625 |  |  | ICT | 4.5859 | HO_0011_1112-Q2,1415-Q2 | HO | Amber | Not new
HO_0012_1112-Q3 | Communications Capabilities Development Programme | AR 2015 | 1415-Q2 | HO | Amber | 2006-04-01 | 2020-04-01 | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) |  | exempt | ICT | 14.0014 | HO_0012_1112-Q3,1415-Q2 | HO | Amber | Not new
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2015 | 1415-Q2 | HO | Amber | 2011-06-01 | 2020-12-31 | 9.6 | 13.2 | 3.6 | 0.375 | 5367.08 |  |  | Government Transformation and Service Delivery | 9.5852 | HO_0016_1213-Q1,1415-Q2 | HO | Amber | Not new
HO_0023_1213-Q1 | Next Generation Outsourced Visa Services Contract | AR 2015 | 1415-Q2 | HO | Green | 2011-12-01 | 2014-07-01 | 85.007 | 83.9 | -1.107 | -0.013022 | 595.703 |  |  | ICT | 2.5818 | HO_0023_1213-Q1,1415-Q2 | HO | Green | Not new
HO_0025_1213-Q2 | Harmondsworth and Colnbrook Retender (P110) | AR 2015 | 1415-Q2 | HO | Green | 2012-03-01 | 2015-06-01 | 16.98 | 16.98 | 0 | 0 | 199.615 |  |  | ICT | 3.2498 | HO_0025_1213-Q2,1415-Q2 | HO | Green | Not new
MOD_0001_1112-Q1 | A400M | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 1997-07-01 | 2022-03-31 | 646.36 | 640.69 | -5.67 | -0.0087722 | 3833.15 |  |  | Military Capability | 24.7474 | MOD_0001_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0004_1112-Q1 | Airseeker | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 2010-03-18 | 2018-04-01 | 132.22 | 127.96 | -4.26 | -0.032219 | 753.11 |  |  | Military Capability | 8.0383 | MOD_0004_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0009_1112-Q1 | BORONA | AR 2015 | 1415-Q2 | MOD Transformation | Amber/Green | 2006-08-31 | 2019-03-31 | 161.1 | 147.01 | -14.09 | -0.087461 | 1557.1 |  |  | Government Transformation and Service Delivery | 12.5804 | MOD_0009_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0017_1112-Q1 | Crowsnest Programme | AR 2015 | 1415-Q2 | Military Capability | Green | 2013-03-26 | 2022-09-30 | 19.86 | 14.6 | -5.26 | -0.26485 | Data Exempt under Section 43 of the Freedom of Information Act (2000) |  | exempt | Military Capability | 9.514 | MOD_0017_1112-Q1,1415-Q2 | MOD | Green | Not new
MOD_0019_1112-Q1 | Defence Information Infrastructure | AR 2015 | 1415-Q2 | Military Capability | Amber/Red | 2001-09-03 | 2015-03-21 | 770.2 | 787.39 | 17.19 | 0.022319 | 7432.41 |  |  | ICT | 13.5441 | MOD_0019_1112-Q1,1415-Q2 | MOD | Amber/Red | Not new
MOD_0033_1112-Q1 | MARSHALL | AR 2015 | 1415-Q2 | Military Capability | Amber | 2006-04-03 | 2020-10-04 | 41.5 | 41.5 | 0 | 0 | 716.6 |  |  | Military Capability | 14.5051 | MOD_0033_1112-Q1,1415-Q2 | MOD | Amber | Not new
MOD_0035_1112-Q1 | Merlin Programme | AR 2015 | 1415-Q2 | Military Capability | Green | 2003-06-01 | 2016-03-31 | 90.5 | 25.67 | -64.83 | -0.71635 | 806.44 |  |  | Military Capability | 12.8323 | MOD_0035_1112-Q1,1415-Q2 | MOD | Green | Not new
MOD_0036_1112-Q1 | Maritime Sustainment Programme | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 2005-07-25 | 2018-04-30 | 68.71 | 75.73 | 7.02 | 0.10217 | 596.51 |  |  | Military Capability | 12.7639 | MOD_0036_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2015 | 1415-Q2 | Military Capability | Exempt | 2008-04-01 | 2025-04-30 | 1090.98 | 1064.55 | -26.43 | -0.024226 | 20957.16 |  |  | Military Capability | 17.0787 | MOD_0038_1112-Q1,1415-Q2 | MOD | Exempt | Not new
MOD_0040_1112-Q1 | Puma Helicopter Life Extension Programme | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 2007-02-01 | 2015-12-31 | 10.15 | 8.46 | -1.69 | -0.1665 | 377.79 |  |  | Military Capability | 8.9117 | MOD_0040_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0042_1112-Q1 | Queen Elizabeth Programme | AR 2015 | 1415-Q2 | Military Capability | Amber/Red | 1998-12-01 | 2023-03-31 | 844.81 | 810.06 | -34.75 | -0.041134 | 7209.06 |  |  | Military Capability | 24.3285 | MOD_0042_1112-Q1,1415-Q2 | MOD | Amber/Red | Not new
MOD_0047_1112-Q1 | Spearfish Upgrade Programme | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 2008-04-01 | 2022-12-31 | 21.65 | 23.55 | 1.9 | 0.08776 | 428.89 |  |  | Military Capability | 14.7488 | MOD_0047_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0055_1112-Q1 | Type 26 Global Combat Ship Programme | AR 2015 | 1415-Q2 | Military Capability | Exempt | 2008-07-21 | 2034-12-31 | 182 | 169.51 | -12.49 | -0.068626 | Data Exempt under Section 43 of the Freedom of Information Act (2000) |  | exempt | Military Capability | 26.4449 | MOD_0055_1112-Q1,1415-Q2 | MOD | Exempt | Not new
MOD_0057_1112-Q1 | Typhoon | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 1987-11-06 | 2024-03-30 | 1069.46 | 1023.39 | -46.07 | -0.043078 | 19210.68 |  |  | Military Capability | 36.397 | MOD_0057_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 1998-03-01 | 2040-12-31 | 63.37 | 68.04 | 4.67 | 0.073694 | 1167.56 |  |  | Military Capability | 42.8364 | MOD_0061_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0062_1112-Q1 | Wildcat | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 2001-12-01 | 2016-05-31 | 106.87 | 105.45 | -1.42 | -0.013287 | 1601.52 |  |  | Military Capability | 14.4969 | MOD_0062_1112-Q1,1415-Q2 | MOD | Amber/Green | Not new
MOD_0065_1112-Q2 | CHINOOK (incl Project Julius) | AR 2015 | 1415-Q2 | Military Capability | Amber/Green | 2008-04-01 | 2017-03-31 | 240.03 | 226.56 | -13.47 | -0.056118 | 1048.33 |  |  | Military Capability | 8.9966 | MOD_0065_1112-Q2,1415-Q2 | MOD | Amber/Green | Not new
MOD_0067_1112-Q2 | Defence Core Network Services | AR 2015 | 1415-Q2 | Military Capability | Amber/Red | 2009-12-01 | 2020-03-02 | 46.27 | 24.85 | -21.42 | -0.46293 | 6113.33 |  |  | ICT | 10.2505 | MOD_0067_1112-Q2,1415-Q2 | MOD | Amber/Red | Not new
MOD_0069_1112-Q2 | Logistics Commodities Services Transformation | AR 2015 | 1415-Q2 | MOD Transformation | Amber | 2011-08-01 | 2018-02-01 | 12.17 | 11.85 | -0.32 | -0.026294 | 803.73 |  |  | Government Transformation and Service Delivery | 6.5051 | MOD_0069_1112-Q2,1415-Q2 | MOD | Amber | Not new
MOD_0070_1112-Q2 | New Employment Model | AR 2015 | 1415-Q2 | MOD Transformation | Amber | 2011-05-02 | 2021-10-01 | 12.29 | 8.56 | -3.73 | -0.3035 | 66.72 |  |  | Government Transformation and Service Delivery | 10.4175 | MOD_0070_1112-Q2,1415-Q2 | MOD | Amber | Not new
MOD_0071_1112-Q2 | Submarine Enterprise Performance Programme | AR 2015 | 1415-Q2 | Military Capability | Amber | 2010-05-31 | 2014-03-31 | 0.28 | 0.23 | -0.05 | -0.17857 | 15.73 |  |  | Government Transformation and Service Delivery | 3.833 | MOD_0071_1112-Q2,1415-Q2 | MOD | Amber | Not new
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2015 | 1415-Q2 | Military Capability | Amber/Red | 1997-03-17 | 2024-03-31 | 558.1 | 645.59 | 87.49 | 0.15676 | 9860.64 |  |  | Military Capability | 27.039 | MOD_0076_1213-Q1,1415-Q2 | MOD | Amber/Red | Not new
MOD_0077_1213-Q1 | Complex Weapons | AR 2015 | 1415-Q2 | Military Capability | Amber | 2008-03-31 | 2032-04-01 | 508.61 | 527.7 | 19.09 | 0.037534 | 17490.6 |  |  | Military Capability | 24.0027 | MOD_0077_1213-Q1,1415-Q2 | MOD | Amber | Not new
MOD_0078_1213-Q1 | Core Production Capability | AR 2015 | 1415-Q2 | Military Capability | Amber | 2012-04-23 | 2024-08-23 | 144.15 | 144.23 | 0.08 | 0.00055498 | 1268.97 |  |  | Military Capability | 12.334 | MOD_0078_1213-Q1,1415-Q2 | MOD | Amber | Not new
MOD_0079_1213-Q1 | Lightning II Programme | AR 2015 | 1415-Q2 | Military Capability | Amber | 2001-10-01 | 2035-03-31 | 306.68 | 290.4 | -16.28 | -0.053085 | 13203.23 |  |  | Military Capability | 33.4949 | MOD_0079_1213-Q1,1415-Q2 | MOD | Amber | Not new
MOD_0080_1213-Q1 | Successor SSBN | AR 2015 | 1415-Q2 | Military Capability | Amber/Red | 2011-04-14 | Data Exempt under Section 35 of the Freedom of Information Act (2000) | 623.19 | 628.04 | 4.85 | 0.0077825 | Data Exempt under Section 43 of the Freedom of Information Act (2000) |  | exempt | Military Capability | 0 | MOD_0080_1213-Q1,1415-Q2 | MOD | Amber/Red | Not new
MOD_0081_1213-Q2 | Future Reserves 2020 | AR 2015 | 1415-Q2 | MOD Transformation | Red | 2011-09-30 | 2018-03-31 | 174 | 174 | 0 | 0 | 1819 |  |  | Government Transformation and Service Delivery | 6.4997 | MOD_0081_1213-Q2,1415-Q2 | MOD | Red | Not new
MOJ_0002_1112-Q1 | Court Estates Reform | AR 2015 | 1415-Q2 | MOJ | Green | 2010-05-10 | 2014-09-30 | 0.589 | 0.09 | -0.50422 | -0.85 | 45.439 |  | 0 | Government Transformation and Service Delivery | 4.3915 | MOJ_0002_1112-Q1,1415-Q2 | MOJ | Green | Not new
MOJ_0003_1112-Q1 | Electronic Monitoring | AR 2015 | 1415-Q2 | MOJ | Amber | 2011-05-10 | 2013-09-30 | 49.9 | 49.9 | 0 | 0 | 425.8346 |  |  | Government Transformation and Service Delivery | 2.3929 | MOJ_0003_1112-Q1,1415-Q2 | MOJ | Amber | Not new
MOJ_0004_1112-Q1 | Future IT Sourcing Programme (FITS) | AR 2015 | 1415-Q2 | MOJ | Amber | 2011-03-01 | 2016-09-01 | 77 | 77 | 0 | 0 | 1205 |  |  | ICT | 5.5058 | MOJ_0004_1112-Q1,1415-Q2 | MOJ | Amber | Not new
MOJ_0005_1112-Q1 | HMCTS Compliance & Enforcement Services Project | AR 2015 | 1415-Q2 | MOJ | Amber/Green | 2012-06-21 | 2015-07-31 | 47.67 | 52.286 | 4.616 | 0.096832 | 439.2 |  | 0 | Government Transformation and Service Delivery | 3.1075 | MOJ_0005_1112-Q1,1415-Q2 | MOJ | Amber/Green | Not new
MOJ_0006_1112-Q1 | Integrated Delivery Programme | AR 2015 | 1415-Q2 | MOJ | Amber | 2009-07-01 | 2014-09-01 | 3.9448 | 3.9687 | 0.023969 | 0.0060762 | 71.4898 |  | 0 | ICT | 5.1691 | MOJ_0006_1112-Q1,1415-Q2 | MOJ | Amber | Not new
MOJ_0007_1112-Q1 | Legal Aid Reform Implementation | AR 2015 | 1415-Q2 | MOJ | Green | 2011-04-01 | 2013-10-31 | 0 | 0 | 0 | 0% | 19.0598 |  |  | Government Transformation and Service Delivery | 2.5845 | MOJ_0007_1112-Q1,1415-Q2 | MOJ | Green | Not new
MOJ_0008_1112-Q1 | MoJ Shared Services | AR 2015 | 1415-Q2 | MOJ | Amber | 2009-10-04 | 2015-07-07 | 27.6 | 30.5 | 2.9 | 0.10507 | 357.3 |  | 0 | ICT | 5.755 | MOJ_0008_1112-Q1,1415-Q2 | MOJ | Amber | Not new
MOJ_0015_1112-Q2 | NOMS ICTS Services (NIS) Programme (formally part of Quantum Re-compete Project) | AR 2015 | 1415-Q2 | MOJ | Red | 2011-07-18 | 2014-11-30 | 89.4 | 95.8 | 6.4 | 0.071588 | 248.82 |  |  | ICT | 3.3703 | MOJ_0015_1112-Q2,1415-Q2 | MOJ | Red | Not new
MOJ_0018_1112-Q2 | Prison Competitions Phase 2 | AR 2015 | 1415-Q2 | MOJ | Green | 2011-07-13 | 2014-01-31 | 70.1268 | 32.61 | -37.5168 | -0.53498 | 786.7108 |  |  | Government Transformation and Service Delivery | 2.5544 | MOJ_0018_1112-Q2,1415-Q2 | MOJ | Green | Not new
HMT_0003_1112-Q1 | YODA Project (Outsourced Services Retender Project) | AR 2015 | 1415-Q2 | NS&I | Green | 2009-04-05 | 2014-05-31 | 184.1859 | 184.1859 | 0 | 0 | 722.3865 |  | 0 | Government Transformation and Service Delivery | 5.1526 | HMT_0003_1112-Q1,1415-Q2 | NS&I | Green | Not new
ONS_0001_1112-Q1 | 2011 Census | AR 2015 | 1415-Q2 | ONS | Green | 2002-09-01 | 2014-09-30 | 4.01 | 3.85 | -0.16 | -0.0399 | 482.09 |  | 0 | Government Transformation and Service Delivery | 12.0794 | ONS_0001_1112-Q1,1415-Q2 | ONS | Green | Not new
ONS_0002_1112-Q1 | Beyond 2011 | AR 2015 | 1415-Q2 | ONS | Amber/Green | 2011-04-01 | 2015-03-31 | 8 | 7.994 | -0.006 | -0.00075 | 25 |  |  | Government Transformation and Service Delivery | 3.9973 | ONS_0002_1112-Q1,1415-Q2 | ONS | Amber/Green | Not new
ONS_0003_1112-Q4 | Web Data Access (WDA) Project | AR 2015 | 1415-Q2 | ONS | Green | 2011-04-01 | 2013-12-31 | 0.6 | 1.01 | 0.41 | 0.68333 | 16.11 |  | 0 | ICT | 2.7515 | ONS_0003_1112-Q4,1415-Q2 | ONS | Green | Not new
ONS_0004_1213-Q2 | Electronic Data Collection | AR 2015 | 1415-Q2 | ONS | Amber | 2014-01-27 | 2019-11-01 | 6.6447 | 6.6447 | 0 | 0 | 40.0377 |  |  | ICT | 5.7604 | ONS_0004_1213-Q2,1415-Q2 | ONS | Amber | Not new
ONS_0005_1213-Q2 | ESA10/BPM6 Programme (European Systems of Accounting 2010) | AR 2015 | 1415-Q2 | ONS | Amber/Green | 2011-02-05 | 2020-03-30 | 11.163 | 9.363 | -1.8 | -0.16125 | 57.844 |  |  | Government Transformation and Service Delivery | 9.1472 | ONS_0005_1213-Q2,1415-Q2 | ONS | Amber/Green | Not new
BIS_0012_1213-Q4 | Business Bank Project | AR 2015 | 1415-Q2 | BEIS | Amber/Green | 2012-09-24 | 2014-11-01 | 312 | 322.4 | 10.4 | 0.033333 | 495.7 |  |  | Government Transformation and Service Delivery | 2.1027 | BIS_0012_1213-Q4,1415-Q2 | BEIS | Amber/Green | Not new
CO_0008_1213-Q4 | Next Generation Shared Services | AR 2015 | 1415-Q2 | CO | Amber/Red | 2012-12-28 | 2015-04-30 | 12 | 12 | 0 | 0 | 31.1 | 31.1 |  | Government Transformation and Service Delivery | 2.3354 | CO_0008_1213-Q4,1415-Q2 | CO | Amber/Red | Not new
CO_0009_1314-Q1 | New Civil Service 2015 Pension Scheme Implementation | AR 2015 | 1415-Q2 | CO | Amber | 2013-04-15 | 2016-06-30 | 11.7 | 11.4 | -0.3 | -0.025641 | 13.4 |  |  | Government Transformation and Service Delivery | 3.2088 | CO_0009_1314-Q1,1415-Q2 | CO | Amber | Not new
CPS_0001_1314-Q4 | ICTProcurement Programme | AR 2015 | 1415-Q2 | CPS | Amber | 2013-10-01 | 2016-03-31 | 3 | 3 | 0 | 0 | 183.98 |  |  | ICT | 2.4969 | CPS_0001_1314-Q4,1415-Q2 | CPS | Amber | Joiner
DH_0018_1112-Q1 | Pre-Pandemic Vaccine | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2011-10-01 | 2014-07-01 | Data Exempt under section 43 (2) of the Freedom of Information Act 2000 | Data Exempt under section 43 (2) of the Freedom of Information Act 2001 | Data Exempt under section 43 (2) of the Freedom of Information Act 2002 | Data Exempt under section 43 (2) of the Freedom of Information Act 2003 | Data Exempt under section 43 (2) of the Freedom of Information Act 2004 |  | exempt | Government Transformation and Service Delivery | 2.7488 | DH_0018_1112-Q1,1415-Q2 | DH | Amber/Red | Not new
DECC_0015_1415-Q1 | Household Energy Efficiency | AR 2015 | 1415-Q2 | BEIS | Amber/Red | 2014-04-30 | 2015-05-31 | 164 | 164 | 0 | 0 | 4723.61 |  | 4068.2231 | Government Transformation and Service Delivery | 1.0842 | DECC_0015_1415-Q1,1415-Q2 | BEIS | Amber/Red | Joiner
DH_0019_1112-Q1 | Royal Liverpool & Broadgreen ('World Class Hospitals; World Class Services - Renewing the Royal Liverpool University Hospital') | AR 2015 | 1415-Q2 | DH Capital | Green | 2010-06-01 | 2016-11-01 | 19.5 | 19.5 | 0 | 0 | 828 |  | 7.5 | Infrastructure and Construction | 6.4203 | DH_0019_1112-Q1,1415-Q2 | DH | Green | Not new
DH_0020_1112-Q1 | Royal National Orthopaedic Hospital (RNOH) NHS Trust PFI Project | AR 2015 | 1415-Q2 | DH Capital | Green | 2011-01-15 | 2016-11-28 | 0 | 0 | 0 | 0% | 53.539 |  |  | Infrastructure and Construction | 5.87 | DH_0020_1112-Q1,1415-Q2 | DH | Green | Not new
DH_0021_1112-Q1 | Sandwell and West Birmingham Hospitals NHS Trust - The Midland Metropolitan Hospital Project | AR 2015 | 1415-Q2 | DH Capital | Amber/Green | 2008-10-01 | 2018-10-15 | 0 | 0 | 0 | 0% | 1036.3 |  |  | Infrastructure and Construction | 10.037 | DH_0021_1112-Q1,1415-Q2 | DH | Amber/Green | Not new
DH_0022_1112-Q1 | Summary Care Record (SCR) | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2006-04-01 | 2016-03-31 | 7.765 | 10.95 | 3.185 | 0.41017 | 51.101 |  |  | ICT | 9.9986 | DH_0022_1112-Q1,1415-Q2 | DH | Amber | Not new
DH_0023_1112-Q2 | BT LSP (London) | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2003-12-18 | 2015-10-30 | 97.5 | 121.0015 | 23.5015 | 0.24104 | 1108.97 |  |  | ICT | 11.8658 | DH_0023_1112-Q2,1415-Q2 | DH | Amber/Red | Not new
DH_0026_1112-Q2 | BT LSP (South) | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2004-01-26 | 2015-10-31 | 40.11 | 68.7662 | 28.6562 | 0.71444 | 634.06 |  |  | ICT | 11.7618 | DH_0026_1112-Q2,1415-Q2 | DH | Amber/Red | Not new
DH_0027_1213-Q4 | South Acute Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Green | 2011-11-01 | 2017-06-27 | 40.914 | 11.05 | -29.864 | -0.72992 | 189.055 |  | 0 | ICT | 5.6537 | DH_0027_1213-Q4,1415-Q2 | DH | Amber/Green | Not new
DH_0028_1314-Q1 | General Practice System of Choice (GPSoC) Replacement | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2012-01-26 | 2015-03-31 | 79.645 | 90.3426 | 10.6977 | 0.13432 | 309.424 |  |  | ICT | 3.1759 | DH_0028_1314-Q1,1415-Q2 | DH | Amber | Not new
DH_0029_1314-Q1 | Liaison and Diversion Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2011-04-01 | 2014-04-01 | 50 | 25.4 | -24.6 | -0.492 | 213.17 |  |  | ICT | 3.0007 | DH_0029_1314-Q1,1415-Q2 | DH | Amber | Not new
DH_0030_1314-Q1 | National Pandemic Flu Service | AR 2015 | 1415-Q2 | DH Non Capital | Red | 2012-03-19 | 2015-12-01 | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) |  | exempt | Government Transformation and Service Delivery | 3.7016 | DH_0030_1314-Q1,1415-Q2 | DH | Red | Not new
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2012-01-01 | 2018-12-31 | 9.4 | 9.4 | 0 | 0 | 1295.53 |  | 34.8 | Infrastructure and Construction | 6.9979 | DH_0031_1314-Q1,1415-Q2 | DH | Amber | Not new
DH_0032_1314-Q1 | Rotavirus Immunisation Programme | AR 2015 | 1415-Q2 | DH Non Capital | Green | 2009-03-05 | 2014-04-01 | 25.5 | 25.5 | 0 | 0 | 70.2 |  | 0 | Government Transformation and Service Delivery | 5.0732 | DH_0032_1314-Q1,1415-Q2 | DH | Green | Not new
DH_0033_1314-Q1 | Childhood Flu Immunisation Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2013-09-16 | 2018-09-01 | 59.83 | 59.83 | 0 | 0 | 436.09 |  |  | Government transformation and Service Delivery | 4.9582 | DH_0033_1314-Q1,1415-Q2 | DH | Amber | Not new
DH_0035_1314-Q1 | Shingles Immunisation Programme | AR 2015 | 1415-Q2 | DH Non Capital | Green | 2012-12-11 | 2013-11-01 | 67.34 | 67.34 | 0 | 0 | 171.53 |  | 0 | Government Transformation and Service Delivery | 0.8898 | DH_0035_1314-Q1,1415-Q2 | DH | Green | Not new
DH_0036_1314-Q1 | Spine 2 | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2010-05-10 | 2018-03-30 | 65.86 | 73.6774 | 7.8174 | 0.1187 | 205.71 |  |  | ICT | 7.8877 | DH_0036_1314-Q1,1415-Q2 | DH | Amber | Not new
DH_0038_1314-Q2 | Health Visitor Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2010-10-31 | 2015-12-31 | 242.05 | 242.05 | 0 | 0 | 653.15 |  | 0 | Government Transformation and Service Delivery | 5.1663 | DH_0038_1314-Q2,1415-Q2 | DH | Amber | Not new
DH_0039_1314-Q2 | NHS e-Referral Service | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2012-07-26 | 2018-03-31 | 35.4102 | 33.9752 | -1.435 | -0.040526 | 131.1637 |  | 0 | Government Transformation and Service Delivery | 5.6783 | DH_0039_1314-Q2,1415-Q2 | DH | Amber | Not new
DH_0040_1314-Q2 | NHSmail2 | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2012-03-29 | 2016-06-30 | 27.39 | 19.09 | -8.3 | -0.30303 | 168.09 |  |  | ICT | 4.2546 | DH_0040_1314-Q2,1415-Q2 | DH | Amber | Not new
FCO_0001_1112-Q1 | ABUJA: New Office and Residence | AR 2015 | 1415-Q2 | FCO | Amber/Green | 2011-01-01 | 2017-12-01 | 19.89 | 19.89 | 0 | 0 | 46 |  |  | Infrastructure and Construction | 6.9158 | FCO_0001_1112-Q1,1415-Q2 | FCO | Amber/Green | Not new
DH_0041_1314-Q2 | Health and Social Care Network (Formerly Public Services Network for Health (PSNH)) | AR 2015 | 1415-Q2 | DH Non Capital | Red | 2012-03-29 | 2014-10-10 | 177.46 | 1.89 | -175.57 | -0.98935 | 748.16 |  |  | ICT | 2.5325 | DH_0041_1314-Q2,1415-Q2 | DH | Red | Not new
FCO_0006_1213-Q2 | UKERP | AR 2015 | 1415-Q2 | FCO | Amber/Green | 2011-06-01 | 2016-08-01 | 22.04 | 22.04 | 0 | 0 | 64.95 |  |  | Infrastructure and Construction | 5.1691 | FCO_0006_1213-Q2,1415-Q2 | FCO | Amber/Green | Not new
DH_0042_1314-Q3 | NHS Electronic Staff Record Reprocurement Project | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Green | 2013-06-10 | 2015-11-30 | 7.75 | 12.8 | 5.05 | 0.65161 | 425.38 |  | 0 | ICT | 2.4723 | DH_0042_1314-Q3,1415-Q2 | DH | Amber/Green | Joiner
DWP_0017_1314-Q3 | Estates Programme | AR 2015 | 1415-Q2 | DWP | Amber/Green | 2012-02-16 | 2018-03-31 | 23.57 | 18.719 | -4.851 | -0.20581 | 173.314 |  | 0 | Government transformation and Service Delivery | 6.1191 | DWP_0017_1314-Q3,1415-Q2 | DWP | Amber/Green | Joiner
DWP_0018_1314-Q3 | Fit for Work (previously called Health and Work Service) | AR 2015 | 1415-Q2 | DWP | Amber | 2013-02-27 | 2015-03-31 | 28.992 | 18.967 | -10.025 | -0.34579 | 324.1066 |  | 0 | Government transformation and Service Delivery | 2.0862 | DWP_0018_1314-Q3,1415-Q2 | DWP | Amber | Joiner
DWP_0019_1314-Q3 | IT Transformation Programme | AR 2015 | 1415-Q2 | DWP | Amber/Red | 2013-04-01 | 2016-02-28 | 36.5 | 30.403 | -6.097 | -0.16704 | 165.5 |  | 0 | ICT | 2.9103 | DWP_0019_1314-Q3,1415-Q2 | DWP | Amber/Red | Joiner
DWP_0020_1314-Q4 | Help to Work Package | AR 2015 | 1415-Q2 | DWP | Amber | 2013-12-19 | 2015-04-23 | 127.25 | 130.964 | 3.714 | 0.029187 | 695.66 |  | 0 | Government transformation and Service Delivery | 1.3415 | DWP_0020_1314-Q4,1415-Q2 | DWP | Amber | Joiner
DWP_0021_1314-Q4 | Conditionality Package | AR 2015 | 1415-Q2 | DWP | Amber | 2013-12-19 | 2015-04-23 | 135.02 | 136.161 | 1.141 | 0.0084506 | 1902.28 |  | 0 | Government transformation and Service Delivery | 1.3415 | DWP_0021_1314-Q4,1415-Q2 | DWP | Amber | Joiner
DWP_0023_1415-Q2 | New State Pension Project | AR 2015 | 1415-Q2 | DWP | Amber | 2012-02-27 | 2017-10-31 | 19.87 | 19.87 | 0 | 0 | 168.159 |  | 0 | Government Transformation and Service Delivery | 5.6756 | DWP_0023_1415-Q2,1415-Q2 | DWP | Amber | Joiner
FCO_0007_1415-Q1 | Overseas Healthcare Provision | AR 2015 | 1415-Q2 | FCO | Amber/Green | 2013-09-26 | 2016-04-01 | 0.089 | 0.089 | 0 | 0 | 55.989 |  |  | Government Transformation and Service Delivery | 2.5133 | FCO_0007_1415-Q1,1415-Q2 | FCO | Amber/Green | Joiner
HMRC_0011_1314-Q1 | Digital Solutions Portfolio | AR 2015 | 1415-Q2 | HMRC | Amber | 2012-11-14 | 2015-04-05 | 33.41 | 28.86 | -4.55 | -0.13619 | 116.7 |  |  | Government Transformation and Service Delivery | 2.3874 | HMRC_0011_1314-Q1,1415-Q2 | HMRC | Amber | Not new
HMRC_0012_1415-Q1 | Tax-Free Childcare | AR 2015 | 1415-Q2 | HMRC | Amber/Red | 2013-08-01 | 2016-06-30 | 30.4 | 19.07 | 11.33 | 0.37 | 31.79 |  |  | ICT | 2.9131 | HMRC_0012_1415-Q1,1415-Q2 | HMRC | Amber/Red | Joiner
HO_0029_1314-Q4 | Immigration Platform Technologies (IPT) | AR 2015 | 1415-Q2 | HO | Amber | 2013-04-01 | 2017-03-31 | 77.644 | 54.85 | -22.794 | -0.29357 | 208.6634 |  |  | ICT | 3.9973 | HO_0029_1314-Q4,1415-Q2 | HO | Amber | Joiner
HO_0030_1415-Q1 | Adelphi Modernisation Project | AR 2015 | 1415-Q2 | HO | Amber | 2014-07-03 | 2016-03-31 | 0 | 0 | 0 | 0% | 25.6 |  |  | ICT | 1.744 | HO_0030_1415-Q1,1415-Q2 | HO | Amber | Joiner
HO_0031_1415-Q1 | Digital Services at the Border | AR 2015 | 1415-Q2 | HO | Amber | 2014-02-12 | 2019-03-31 | 16.2 | 16.03 | -0.17 | -0.010494 | 178.25 |  | 0 | ICT | 5.128 | HO_0031_1415-Q1,1415-Q2 | HO | Amber | Joiner
HO_0032_1415-Q1 | Technology Reset Programme (TRP) | AR 2015 | 1415-Q2 | HO | Amber/Red | 2014-02-01 | 2016-09-01 | 32 | 32 | 0 | 0 | 242 |  |  | ICT | 2.5818 | HO_0032_1415-Q1,1415-Q2 | HO | Amber/Red | Joiner
MOD_0064_1112-Q2 | CEPP | AR 2015 | 1415-Q2 | Military Capability | Amber/Red | 2011-01-31 | 2030-12-01 | 1.58 | 1.58 | 0 | 0 | 21.7 |  |  | Government Transformation and Service Delivery | 19.833 | MOD_0064_1112-Q2,1415-Q2 | MOD | Amber/Red | Not new
MOD_0066_1112-Q2 | Corporate Services Systems Convergence Programme | AR 2015 | 1415-Q2 | MOD Transformation | Amber | 2010-02-01 | 2020-02-28 | 27.02 | 14.33 | -12.69 | -0.46965 | 77.96 |  |  | Government Transformation and Service Delivery | 10.0726 | MOD_0066_1112-Q2,1415-Q2 | MOD | Amber | Not new
MOD_0082_1213-Q3 | Next Generation Estates Contracts | AR 2015 | 1415-Q2 | MOD Transformation | Amber/Green | 2009-03-02 | 2015-03-20 | 75.58 | 66.25 | -9.33 | -0.12345 | 2250.69 |  |  | Government Transformation and Service Delivery | 6.0479 | MOD_0082_1213-Q3,1415-Q2 | MOD | Amber/Green | Not new
MOD_0083_1213-Q3 | Whole Fleet Management | AR 2015 | 1415-Q2 | MOD Transformation | Amber | 2001-01-31 | 2025-06-30 | 22.76 | 19.9 | -2.86 | -0.12566 | 1295.46 |  |  | Military Capability | 24.4107 | MOD_0083_1213-Q3,1415-Q2 | MOD | Amber | Not new
MOD_0084_1213-Q4 | Army 2020 | AR 2015 | 1415-Q2 | MOD Transformation | Amber | 2011-08-31 | 2020-04-30 | 0 | 0 | 0 | 0 | 0 |  |  | Government Transformation and Service Delivery | 8.6653 | MOD_0084_1213-Q4,1415-Q2 | MOD | Amber | Not new
MOD_0085_1314-Q2 | Army Basing Programme | AR 2015 | 1415-Q2 | MOD Transformation | Red | 2013-05-22 | 2020-03-31 | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept |  |  | Government Transformation and Service Delivery | 6.8583 | MOD_0085_1314-Q2,1415-Q2 | MOD | Red | Not new
MOD_0086_1314-Q2 | Mounted Close Combat | AR 2015 | 1415-Q2 | Military Capability | Amber | 2010-03-16 | 2033-12-31 | 288.34 | 308.75 | 20.41 | 0.070784 | 17251.83 |  |  | Military Capability | 23.7947 | MOD_0086_1314-Q2,1415-Q2 | MOD | Amber | Not new
MOD_0087_1314-Q2 | The Materiel Strategy | AR 2015 | 1415-Q2 | Military Capability | Amber/Red | 2011-05-02 | 2017-05-31 | 23 | 42.03 | 19.03 | 0.82739 | 98.68 |  |  | Government transformation and Service Delivery | 6.0808 | MOD_0087_1314-Q2,1415-Q2 | MOD | Amber/Red | Not new
MOD_0088_1314-Q4 | Head Office and Customer Design | AR 2015 | 1415-Q2 | MOD Transformation | Amber | 2014-01-01 | 2015-07-31 | 11.16 | 10.12 | -1.04 | -0.09319 | 14.73 |  |  | Government transformation and Service Delivery | 1.577 | MOD_0088_1314-Q4,1415-Q2 | MOD | Amber | Joiner
MOD_0089_1314-Q4 | Strategic Business Partner Implementation Programme | AR 2015 | 1415-Q2 | MOD Transformation | Green | 2014-03-06 | 2016-12-30 | 26.11 | 26.11 | 0 | 0 | 205.7 |  |  | Government transformation and Service Delivery | 2.82 | MOD_0089_1314-Q4,1415-Q2 | MOD | Green | Joiner
MOD_0090_1415-Q1 | Operating Model Rollout | AR 2015 | 1415-Q2 | MOD Transformation | Amber/Green | 2013-11-06 | 2016-02-26 | 17.37 | 17.37 | 0 | 0 | 61.57 |  |  | Government Transformation and Service Delivery | 2.3053 | MOD_0090_1415-Q1,1415-Q2 | MOD | Amber/Green | Joiner
MOJ_0021_1314-Q1 | Common Platform | AR 2015 | 1415-Q2 | MOJ | Amber/Red | 2012-11-01 | 2017-01-31 | 38.3713 | 25.941 | -12.4303 | -0.32395 | 374.0669 |  |  | ICT | 4.2491 | MOJ_0021_1314-Q1,1415-Q2 | MOJ | Amber/Red | Not new
MOJ_0022_1314-Q1 | Legal Aid Transformation | AR 2015 | 1415-Q2 | MOJ | Amber | 2012-12-04 | 2015-08-01 | 4.9 | 3.8 | -1.1 | -0.22449 | 11.796 |  | 0 | Government Transformation and Service Delivery | 2.6557 | MOJ_0022_1314-Q1,1415-Q2 | MOJ | Amber | Not new
MOJ_0023_1314-Q1 | New Wales Prison | AR 2015 | 1415-Q2 | MOJ | Green | 2013-01-10 | 2018-03-31 | 14.24 | 15.24 | 1 | 0.070225 | 208.04 |  |  | Infrastructure and Construction | 5.2183 | MOJ_0023_1314-Q1,1415-Q2 | MOJ | Green | Not new
MOJ_0024_1314-Q1 | Prison Unit Cost Programme | AR 2015 | 1415-Q2 | MOJ | Amber | 2012-11-20 | 2016-12-01 | 85.2 | 23.2 | -62 | -0.7277 | 866.4024 |  |  | Government Transformation and Service Delivery | 4.0301 | MOJ_0024_1314-Q1,1415-Q2 | MOJ | Amber | Not new
MOJ_0025_1314-Q1 | Rehabilitation Programme | AR 2015 | 1415-Q2 | MOJ | Amber/Red | 2012-11-05 | 2015-03-31 | 437.9125 | 437.9125 | 0 | 0 | 9607.7425 |  | 0 | Government Transformation and Service Delivery | 2.3984 | MOJ_0025_1314-Q1,1415-Q2 | MOJ | Amber/Red | Not new
MOJ_0026_1314-Q1 | Transforming Youth Custody | AR 2015 | 1415-Q2 | MOJ | Amber | 2012-11-05 | 2018-07-15 | 17.6 | 17.6 | 0 | 0 | 3466.3 |  |  | Government Transformation and Service Delivery | 5.6893 | MOJ_0026_1314-Q1,1415-Q2 | MOJ | Amber | Not new
MOJ_0027_1314-Q2 | CJS Efficiency Programme Phase 2 | AR 2015 | 1415-Q2 | MOJ | Amber | 2013-04-30 | 2016-12-31 | 34.28 | 31.45 | -2.83 | -0.082555 | 141.19 |  |  | ICT | 3.6715 | MOJ_0027_1314-Q2,1415-Q2 | MOJ | Amber | Not new
MOJ_0028_1314-Q2 | HMCTS Reform | AR 2015 | 1415-Q2 | MOJ | Amber/Red | 2013-03-21 | No end date | 23.8 | 12.1 | -11.7 | -0.4916 | 619.75 |  |  | Government Transformation and Service Delivery | 0 | MOJ_0028_1314-Q2,1415-Q2 | MOJ | Amber/Red | Not new
MOJ_0029_1415-Q1 | Crime Change Programme | AR 2015 | 1415-Q2 | MOJ | Amber/Green | 2013-07-07 | 2015-07-31 | 10.3575 | 10.3575 | 0 | 0 | 28.8158 |  |  | ICT | 2.0643 | MOJ_0029_1415-Q1,1415-Q2 | MOJ | Amber/Green | Joiner
NCA_0001_1415-Q2 | Novo Programme | AR 2015 | 1415-Q2 | NCA | Amber | 2014-04-01 | 2019-03-31 | 56 | 56 | 0 | 0 | 296 |  | 0 | Government Transformation and Service Delivery | 4.9966 | NCA_0001_1415-Q2,1415-Q2 | NCA | Amber | Joiner
ONS_0006_1314-Q3 | Consumer and Retail Prices Indices (CPI/RPI) Re-engineering | AR 2015 | 1415-Q2 | ONS | Amber | 2011-01-01 | 2015-03-20 | 1.315 | 1.32 | 0.005 | 0.0038023 | 13.043 |  |  | ICT | 4.2136 | ONS_0006_1314-Q3,1415-Q2 | ONS | Amber | Joiner
MOD_0095_1415-Q2 | Cryptographic Enabling Services | AR 2015 | 1415-Q2 | Military Capability | Exempt | 2014-06-24 | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept |  |  | ICT | 0 | MOD_0095_1415-Q2,1415-Q2 | MOD | Exempt | Joiner
DH_0043_1314-Q3 | NHS Pension Re-let Project | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2013-07-05 | 2017-07-31 | 1.7 | 1.7 | 0 | 0 | 1.9 |  | 0 | ICT | 4.0712 | DH_0043_1314-Q3,1415-Q2 | DH | Amber/Red | Joiner
DH_0044_1314-Q4 | Care and Support Implementation Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2013-06-04 | 2016-12-01 | 62.9 | 0.4 | -62.5 | -0.99364 | 1682.4 |  | 0 | Government transformation and Service Delivery | 3.4935 | DH_0044_1314-Q4,1415-Q2 | DH | Amber/Red | Joiner
DH_0045_1415-Q1 | care.data | AR 2015 | 1415-Q2 | DH Non Capital | Red | 2012-09-01 | No end date | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept |  |  | ICT | 0 | DH_0045_1415-Q1,1415-Q2 | DH | Red | Joiner
DH_0046_1415-Q1 | Death Certification | AR 2015 | 1415-Q2 | DH Non Capital | Red | 2007-07-24 | No end date | 0 | 0 | 0 | 0% | 411.61 |  | 0 | Government Transformation and Service Delivery | 0 | DH_0046_1415-Q1,1415-Q2 | DH | Red | Joiner
DH_0047_1415-Q1 | Francis & Compassionate Care programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2013-03-01 | 2018-03-01 | 2.5 | 2.16 | -0.34 | -0.136 | 14.55 |  | 0 | Government Transformation and Service Delivery | 4.9993 | DH_0047_1415-Q1,1415-Q2 | DH | Amber/Red | Joiner
DH_0048_1415-Q1 | Genomics Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2013-04-10 | 2017-12-31 | 50 | 19.2 | -30.8 | -0.616 | 160 |  |  | Government Transformation and Service Delivery | 4.7255 | DH_0048_1415-Q1,1415-Q2 | DH | Amber | Joiner
DH_0049_1415-Q1 | NHS Choices | AR 2015 | 1415-Q2 | DH Non Capital | Red | 2013-09-02 | No end date | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept | Data not provided by dept |  |  | ICT | 0 | DH_0049_1415-Q1,1415-Q2 | DH | Red | Joiner
DH_0050_1415-Q1 | NHS Procurement Efficiency Programme | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2013-09-01 | 2016-03-31 | 21.76 | 7.76 | -14 | -0.64338 | 39.44 |  | 0 | Government Transformation and Service Delivery | 2.5791 | DH_0050_1415-Q1,1415-Q2 | DH | Amber/Red | Joiner
DH_0051_1415-Q1 | North Tees & Hartlepool Foundation Trust - New Hospital Development | AR 2015 | 1415-Q2 | DH Capital | Green | 2013-04-01 | 2017-06-30 | 0 | 0 | 0 | 0% | 975.83 |  | 0 | Infrastructure and Construction | 4.2464 | DH_0051_1415-Q1,1415-Q2 | DH | Green | Joiner
DH_0052_1415-Q1 | Nursing Technology Fund | AR 2015 | 1415-Q2 | DH Non Capital | Amber | 2013-11-01 | No end date | 70 | 70.35 | 0.35 | 0.005 | 100 |  | 0 | ICT | 0 | DH_0052_1415-Q1,1415-Q2 | DH | Amber | Joiner
DH_0053_1415-Q1 | Papworth Foundation Trust - New Papworth Hospital | AR 2015 | 1415-Q2 | DH Capital | Amber/Green | 2003-12-01 | 2017-11-01 | 18 | 18 | 0 | 0 | 697.497 |  |  | Infrastructure and Construction | 13.9192 | DH_0053_1415-Q1,1415-Q2 | DH | Amber/Green | Joiner
DH_0054_1415-Q1 | SUS Transition | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2013-08-20 | 2014-12-05 | 30.67 | 30.67 | 0 | 0 | 53.61 |  |  | ICT | 1.2923 | DH_0054_1415-Q1,1415-Q2 | DH | Amber/Red | Joiner
DH_0055_1415-Q2 | Better Care Fund | AR 2015 | 1415-Q2 | DH Non Capital | Amber/Red | 2014-07-07 | 2015-03-31 | 5.38 | 5.38 | 0 | 0 | 5.38 |  |  | Government Transformation and Service Delivery | 0.73101 | DH_0055_1415-Q2,1415-Q2 | DH | Amber/Red | Joiner
BIS_0010_1112-Q4 | Project Eagle (formerly Urenco Future Options) | AR 2016 | 1516-Q2 | BEIS | Amber/Red | 2010-02-01 | 2017-06-15 | 1.3 | 1.295 | -0.005 | -0.0038462 | 12.9 |  |  | Government Transformation and Service Delivery | 7.3676 | BIS_0010_1112-Q4,1516-Q2 | BEIS | Amber/Red | Not new
BIS_0008_1112-Q1 | ICR Monetisation | AR 2016 | 1516-Q2 | DFE | Amber/Red | 2010-03-01 | 2018-12-31 | 5.79 | 5.79 | 0 | 0 | 15.29 |  |  | Government Transformation and Service Delivery | 8.835 | BIS_0008_1112-Q1,1516-Q2 | DFE | Amber/Red | Not new
BIS_0015_1516-Q1 | Local Land Charges (LLC) Programme | AR 2016 | 1516-Q2 | BEIS | Amber/Red | 2014-03-01 | 2018-06-28 | 5.5 | 5.5 | 0 | 0 | 193.3 |  |  | ICT | 4.3258 | BIS_0015_1516-Q1,1516-Q2 | BEIS | Amber/Red | Joiner
BIS_0014_1415-Q3 | New Polar Research Vessel | AR 2016 | 1516-Q2 | BEIS | Amber/Green | 2014-05-01 | 2019-08-05 | 41 | 39.7 | -1.3 | -0.031707 | 1186 |  |  | Infrastructure and Construction | 5.2621 | BIS_0014_1415-Q3,1516-Q2 | BEIS | Amber/Green | Joiner
BIS_0009_1112-Q1 | The Francis Crick Institute (formerly UKCMRI) | AR 2016 | 1516-Q2 | BEIS | Amber/Green | 2006-10-01 | 2016-12-31 | 6.2 | 6.2 | 0 | 0 | 752.7 |  |  | Infrastructure and Construction | 10.2505 | BIS_0009_1112-Q1,1516-Q2 | BEIS | Amber/Green | Not new
CO_0014_1516-Q2 | Government Office Hubs Programme | AR 2016 | 1516-Q2 | CO | Amber/Red | 2015-05-01 | 2023-12-31 | 7 | 7 | 0 | 0 | 42 |  |  | Government Transformation and Service Delivery | 8.668 | CO_0014_1516-Q2,1516-Q2 | CO | Amber/Red | Joiner
CO_0010_1415-Q4 | ISSC1 | AR 2016 | 1516-Q2 | CO | Red | 2012-12-28 | 2016-06-01 | 1.4 | 1.2 | -0.2 | -0.14286 | 8.2 |  |  | Government Transformation and Service Delivery | 3.4251 | CO_0010_1415-Q4,1516-Q2 | CO | Red | Joiner
CO_0012_1415-Q4 | Commercial Capability Programme | AR 2016 | 1516-Q2 | CO | Amber/Red | 2015-01-01 | 2017-03-31 | 5.2 | 5.2 | 0 | 0 | 10.4 |  |  | Government Transformation and Service Delivery | 2.245 | CO_0012_1415-Q4,1516-Q2 | CO | Amber/Red | Joiner
CO_0001_1112-Q1 | Electoral Registration Transformation Programme | AR 2016 | 1516-Q2 | CO | Amber/Green | 2010-02-01 | 2016-03-31 | 37.41 | 37.41 | 0 | 0 | 129.4 |  |  | Government Transformation and Service Delivery | 6.1602 | CO_0001_1112-Q1,1516-Q2 | CO | Amber/Green | Not new
CO_0013_1516-Q2 | FOXHOUND Programme | AR 2016 | 1516-Q2 | CO | Amber | 2013-09-01 | 2018-07-01 | 18.801 | 18.801 | 0 | 0 | 187.8 |  |  | ICT | 4.8296 | CO_0013_1516-Q2,1516-Q2 | CO | Amber | Joiner
CO_0015_1516-Q2 | GOV.UK Verify | AR 2016 | 1516-Q2 | CO | Amber/Green | 2012-04-01 | 2020-04-01 | 30 | 30 | 0 | 0 | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) |  |  | ICT | 8 | CO_0015_1516-Q2,1516-Q2 | CO | Amber/Green | Joiner
CO_0011_1415-Q4 | ISSC2 | AR 2016 | 1516-Q2 | CO | Amber/Red | 2012-12-28 | 2015-04-30 | 5.7 | 4.7 | -1 | -0.17544 | 32.8 |  |  | Government Transformation and Service Delivery | 2.3354 | CO_0011_1415-Q4,1516-Q2 | CO | Amber/Red | Joiner
CO_0005_1112-Q1 | National Cyber Security Programme | AR 2016 | 1516-Q2 | CO | Green | 2011-04-01 | 2016-04-01 | 212 | 212 | 0 | 0 | 860 |  |  | ICT | 5.0021 | CO_0005_1112-Q1,1516-Q2 | CO | Green | Not new
CO_0009_1314-Q1 | New Civil Service 2015 Pension Scheme Implementation | AR 2016 | 1516-Q2 | CO | Amber/Red | 2013-04-15 | 2015-12-31 | 1.7 | 3.5 | 1.8 | 1.0588 | 14.9 |  |  | Government Transformation and Service Delivery | 2.7105 | CO_0009_1314-Q1,1516-Q2 | CO | Amber/Red | Not new
CPS_0001_1314-Q4 | ICTRestructure Programme | AR 2016 | 1516-Q2 | CPS | Amber | 2013-10-01 | 2016-05-01 | 27.57 | 27.8 | 0.23 | 0.0083424 | 144.3 |  |  | ICT | 2.5818 | CPS_0001_1314-Q4,1516-Q2 | CPS | Amber | Not new
DCMS_0007_1112-Q4 | Super-Connected City Programme | AR 2016 | 1516-Q2 | DCMS | Green | 2012-12-05 | 2016-03-31 | 42.27 | 61.67 | 19.4 | 0.45895 | 154.6 |  |  | Infrastructure and Construction | 3.3183 | DCMS_0007_1112-Q4,1516-Q2 | DCMS | Green | Not new
DCMS_0001_1112-Q1 | Broadband Delivery Programme | AR 2016 | 1516-Q2 | DCMS | Amber/Green | 2010-12-06 | 2017-12-31 | 250 | 164.06 | -85.94 | -0.34376 | 1910.11 |  |  | Infrastructure and Construction | 7.0691 | DCMS_0001_1112-Q1,1516-Q2 | DCMS | Amber/Green | Not new
DCMS_0006_1112-Q4 | Mobile Infrastructure Project | AR 2016 | 1516-Q2 | DCMS | Amber | 2011-10-01 | 2016-03-31 | 28.47 | 28.07 | -0.4 | -0.01405 | 43.97 |  |  | Infrastructure and Construction | 4.4983 | DCMS_0006_1112-Q4,1516-Q2 | DCMS | Amber | Not new
DCMS_0004_1112-Q1 | The Tate Modern Project | AR 2016 | 1516-Q2 | DCMS | Amber | 2010-01-01 | 2016-12-31 | 43.5 | 43.5 | 0 | 0 | 255.5 |  |  | Infrastructure and Construction | 6.9979 | DCMS_0004_1112-Q1,1516-Q2 | DCMS | Amber | Not new
DECC_0011_1112-Q3 | Carbon Capture & Storage Commercialisation Programme | AR 2016 | 1516-Q2 | BEIS | Amber | 2011-10-25 | 2016-12-31 | 40.27 | 29.23 | -11.04 | -0.27415 | Data Exempt under Section 43(2) of the Freedom of Information Act (2000) |  |  | Infrastructure and Construction | 5.1855 | DECC_0011_1112-Q3,1516-Q2 | BEIS | Amber | Not new
DECC_0012_1213-Q1 | FID Enabling for Hinkley Point C | AR 2016 | 1516-Q2 | BEIS | Exempt | 2011-09-01 | 2016-06-01 | 2.3 | 5.9 | 3.6 | 1.5652 | 36963.64 |  |  | Infrastructure and Construction | 4.7502 | DECC_0012_1213-Q1,1516-Q2 | BEIS | Exempt | Not new
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2016 | 1516-Q2 | BEIS | Amber | 2008-06-30 | 2040-12-31 | 25.58 | 25.83 | 0.25 | 0.0097733 | 11393 |  |  | Infrastructure and Construction | 32.5038 | DECC_0005_1112-Q1,1516-Q2 | BEIS | Amber | Not new
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | AR 2016 | 1516-Q2 | BEIS | Amber/Green | 2012-04-03 | 2028-09-01 | 674 | 549 | -125 | -0.18546 | 3860 |  |  | Infrastructure and Construction | 16.4134 | DECC_0013_1213-Q1,1516-Q2 | BEIS | Amber/Green | Not new
DECC_0017_1516-Q1 | Sellafield Model Change (SMC) | AR 2016 | 1516-Q2 | BEIS | Amber | 2015-01-13 | 2017-05-24 | 2217.247 | 2217.247 | 0 | 0 | 29975 |  |  | Government Transformation and Service Delivery | 2.36 | DECC_0017_1516-Q1,1516-Q2 | BEIS | Amber | Joiner
DECC_0010_1112-Q1 | Smart Meters Implementation Programme | AR 2016 | 1516-Q2 | BEIS | Amber | 2009-12-02 | 2020-12-31 | 12 | 12 | 0 | 0 | 19261.09 |  |  | Government Transformation and Service Delivery | 11.0801 | DECC_0010_1112-Q1,1516-Q2 | BEIS | Amber | Not new
DEFRA_0001_1112-Q1 | CAP Delivery Programme | AR 2016 | 1516-Q2 | DEFRA | Amber/Red | 2011-01-01 | 2016-03-31 | 25.29 | 60.6277 | 35.3377 | 1.3973 | 154.8 |  |  | Government Transformation and Service Delivery | 5.2457 | DEFRA_0001_1112-Q1,1516-Q2 | DEFRA | Amber/Red | Not new
DEFRA_0006_1516-Q1 | DEFRA UNITY PROGRAMME | AR 2016 | 1516-Q2 | DEFRA | Amber/Red | 2014-11-01 | 2018-06-01 | 291 | 291 | 0 | 0 | 1666 |  |  | ICT | 3.5811 | DEFRA_0006_1516-Q1,1516-Q2 | DEFRA | Amber/Red | Joiner
DEFRA_0004_1112-Q1 | Thames Estuary Asset Management Programme (TEAM2100) | AR 2016 | 1516-Q2 | DEFRA | Green | 2010-04-01 | 2025-12-31 | 7.35 | 12.3 | 4.95 | 0.67347 | 318.42 |  |  | Infrastructure and Construction | 15.7509 | DEFRA_0004_1112-Q1,1516-Q2 | DEFRA | Green | Not new
DEFRA_0005_1213-Q3 | Thames Tideway Tunnel | AR 2016 | 1516-Q2 | DEFRA | Amber/Green | 2010-09-07 | 2023-12-31 | 2.38 | 3 | 0.62 | 0.2605 | 4221.1 |  |  | Infrastructure and Construction | 13.3142 | DEFRA_0005_1213-Q3,1516-Q2 | DEFRA | Amber/Green | Not new
DFE_0004_1415-Q2 | Priority School Building Programme 1 (PSBP1) - Capital | AR 2016 | 1516-Q2 | DFE | Amber/Red | 2011-07-19 | 2019-01-01 | 693.44 | 801.8 | 108.36 | 0.15626 | 2023.3 |  |  | Infrastructure and Construction | 7.4552 | DFE_0004_1415-Q2,1516-Q2 | DFE | Amber/Red | Not new
DFE_0006_1415-Q3 | Priority School Building Programme 2 | AR 2016 | 1516-Q2 | DFE | Amber/Red | 2014-05-01 | 2021-03-31 | 38.5 | 10.3316 | -28.1684 | -0.73165 | 1580.791 |  |  | Infrastructure and Construction | 6.9158 | DFE_0006_1415-Q3,1516-Q2 | DFE | Amber/Red | Joiner
DFE_0005_1415-Q2 | Priority School Building Programme - Private Finance | AR 2016 | 1516-Q2 | DFE | Amber/Green | 2011-07-19 | 2018-02-01 | 221.4177 | 234.3512 | 12.9335 | 0.058412 | 2085.52 |  |  | Infrastructure and Construction | 6.5407 | DFE_0005_1415-Q2,1516-Q2 | DFE | Amber/Green | Not new
DFID_0001_1112-Q1 | St Helena Airport | AR 2016 | 1516-Q2 | DFID | Amber | 2005-03-15 | 2026-08-31 | 25.98 | 25.56 | -0.42 | -0.016166 | 445.17 |  |  | Infrastructure and Construction | 21.462 | DFID_0001_1112-Q1,1516-Q2 | DFID | Amber | Not new
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | AR 2016 | 1516-Q2 | DFT | Amber | 2012-09-01 | 2021-09-30 | 40.1 | 41.73 | 1.63 | 0.040648 | 1519.32 |  |  | Infrastructure and Construction | 9.0787 | DFT_0020_1314-Q2,1516-Q2 | DFT | Amber | Not new
DFT_0001_1112-Q1 | Crossrail Programme | AR 2016 | 1516-Q2 | DFT | Amber/Green | 2008-07-22 | 2019-12-31 | 1794.5 | 2068.9 | 274.4 | 0.15291 | 14768.87 |  |  | Infrastructure and Construction | 11.4415 | DFT_0001_1112-Q1,1516-Q2 | DFT | Amber/Green | Not new
DFT_0004_1112-Q1 | High Speed Rail Programme (HS2) | AR 2016 | 1516-Q2 | DFT | Amber/Red | 2011-02-28 | 2033-12-31 | 713 | 713 | 0 | 0 | 42559.5103 |  |  | Infrastructure and Construction | 22.8392 | DFT_0004_1112-Q1,1516-Q2 | DFT | Amber/Red | Not new
DFT_0005_1112-Q1 | InterCity Express Programme (IEP) | AR 2016 | 1516-Q2 | DFT | Amber | 2005-06-01 | 2020-02-06 | 98.75 | 98 | -0.75 | -0.0075949 | 6246.89 |  |  | Infrastructure and Construction | 14.6831 | DFT_0005_1112-Q1,1516-Q2 | DFT | Amber | Not new
DfT_0022_1415-Q4 | Lower Thames Crossing | AR 2016 | 1516-Q2 | DFT | Amber | 2014-05-30 | 2026-12-31 | 19.1 | 16.4 | -2.7 | -0.14136 | 199.1 |  |  | Infrastructure and Construction | 12.5886 | DfT_0022_1415-Q4,1516-Q2 | DFT | Amber | Joiner
DFT_0009_1112-Q1 | Periodic Review 2013 (Rail Investment Strategy - HLOS & SOFA) | AR 2016 | 1516-Q2 | DFT | Green | 2011-08-31 | 2012-07-31 | 3381.94 | 2577.4 | -804.54 | -0.23789 | 16840.6 |  |  | Infrastructure and Construction | 0.91718 | DFT_0009_1112-Q1,1516-Q2 | DFT | Green | Not new
DFT_0021_1314-Q3 | Rail Franchising Programme | AR 2016 | 1516-Q2 | DFT | Amber | 2013-03-26 | 2022-12-31 | 0 | 0 | 0 | 0 | 1036.3 |  |  | Infrastructure and Construction | 9.7659 | DFT_0021_1314-Q3,1516-Q2 | DFT | Amber | Not new
DFT_0014_1112-Q1 | Search and Rescue Helicopters | AR 2016 | 1516-Q2 | DFT | Amber/Green | 2011-02-08 | 2017-09-08 | 119 | 112.8 | -6.2 | -0.052101 | 1923 |  |  | Infrastructure and Construction | 6.5818 | DFT_0014_1112-Q1,1516-Q2 | DFT | Amber/Green | Not new
DFT_0015_1112-Q1 | Shared Services Implementation Programme | AR 2016 | 1516-Q2 | DFT | Red | 2010-12-10 | 2015-06-01 | 20.2 | 11.17 | -9.03 | -0.44703 | 222.3 |  |  | ICT | 4.4736 | DFT_0015_1112-Q1,1516-Q2 | DFT | Red | Not new
DFT_0016_1112-Q1 | Thameslink Programme | AR 2016 | 1516-Q2 | DFT | Amber | 2005-07-01 | 2018-12-31 | 29.582 | 29.58 | -0.002 | -6.7609e-05 | 6830.5 |  |  | Infrastructure and Construction | 13.5003 | DFT_0016_1112-Q1,1516-Q2 | DFT | Amber | Not new
DH_0029_1314-Q1 | Liaison and Diversion Programme | AR 2016 | 1516-Q2 | DH | Amber | 2011-04-01 | 2017-04-01 | 34.8 | 34.8 | 0 | 0 | 199.1 |  |  | Government Transformation and Service Delivery | 6.0014 | DH_0029_1314-Q1,1516-Q2 | DH | Amber | Not new
DH_0041_1314-Q2 | Health & Social Care Network | AR 2016 | 1516-Q2 | DH | Amber/Red | 2012-03-29 | 2020-04-01 | 166.95 | 87.38 | -79.57 | -0.47661 | 748.2 |  |  | ICT | 8.0082 | DH_0041_1314-Q2,1516-Q2 | DH | Amber/Red | Not new
DH_0008_1112-Q1 | Electronic Prescription Service (EPS) Release 2 | AR 2016 | 1516-Q2 | DH | Amber | 2003-01-01 | 2016-12-31 | 4.96 | 7.83 | 2.87 | 0.57863 | 77.73 |  |  | ICT | 13.9986 | DH_0008_1112-Q1,1516-Q2 | DH | Amber | Not new
DH_0015_1112-Q1 | CSC Local Service Provider (LSP) Delivery Programme | AR 2016 | 1516-Q2 | DH | Amber/Red | 2003-06-23 | 2023-03-31 | 237.73 | 115.7 | -122.03 | -0.51331 | 2294.07 |  |  | Government Transformation and Service Delivery | 19.77 | DH_0015_1112-Q1,1516-Q2 | DH | Amber/Red | Not new
DH_0017_1112-Q1 | PHE Science Hub | AR 2016 | 1516-Q2 | DH | Amber | 2013-06-28 | 2023-03-31 | 197.25 | 135.56 | -61.69 | -0.31275 | 10447.57 |  |  | Infrastructure and Construction | 9.755 | DH_0017_1112-Q1,1516-Q2 | DH | Amber | Not new
DH_0028_1314-Q1 | General Practice System of Choice (GPSoC) Replacement | AR 2016 | 1516-Q2 | DH | Amber/Green | 2012-01-26 | 2015-03-31 | 87.3154 | 82.1341 | -5.1813 | -0.05934 | 309.43 |  |  | ICT | 3.1759 | DH_0028_1314-Q1,1516-Q2 | DH | Amber/Green | Not new
DH_0030_1314-Q1 | National Pandemic Flu Service | AR 2016 | 1516-Q2 | DH | Amber/Red | 2012-03-19 | 2016-10-30 | Exempt under section 43 of the Freedom of Information Act (2000). | Exempt under section 43 of the Freedom of Information Act (2000). | 0 | 0 | Exempt under section 43 of the Freedom of Information Act (2000). |  |  | ICT | 4.616 | DH_0030_1314-Q1,1516-Q2 | DH | Amber/Red | Not new
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | AR 2016 | 1516-Q2 | DH | Amber/Green | 2012-01-01 | 2018-12-31 | 52.15 | 52.15 | 0 | 0 | 1247.26 |  |  | Government Transformation and Service Delivery | 6.9979 | DH_0031_1314-Q1,1516-Q2 | DH | Amber/Green | Not new
DH_0033_1314-Q1 | Childhood Flu Immunisation Programme | AR 2016 | 1516-Q2 | DH | Amber | 2013-09-03 | 2018-09-01 | 69.28 | 69.28 | 0 | 0 | 348 |  |  | Government Transformation and Service Delivery | 4.9938 | DH_0033_1314-Q1,1516-Q2 | DH | Amber | Not new
DH_0038_1314-Q2 | Health Visitor Programme | AR 2016 | 1516-Q2 | DH | Green | 2010-10-31 | 2015-12-31 | 0.409 | 0.409 | 0 | 0 | 654.309 |  |  | Government Transformation and Service Delivery | 5.1663 | DH_0038_1314-Q2,1516-Q2 | DH | Green | Not new
DH_0039_1314-Q2 | NHS e-Referral Service | AR 2016 | 1516-Q2 | DH | Amber | 2012-03-29 | 2018-03-31 | 26.9969 | 30.7711 | 3.7742 | 0.1398 | 131.16 |  |  | ICT | 6.0041 | DH_0039_1314-Q2,1516-Q2 | DH | Amber | Not new
DH_0040_1314-Q2 | NHSmail 2 | AR 2016 | 1516-Q2 | DH | Amber/Red | 2012-03-29 | 2020-06-01 | 29.32 | 28.4 | -0.92 | -0.031378 | 133.03 |  |  | ICT | 8.1752 | DH_0040_1314-Q2,1516-Q2 | DH | Amber/Red | Not new
DH_0042_1314-Q3 | NHS Electronic Staff Record Reprocurement Project | AR 2016 | 1516-Q2 | DH | Amber | 2013-06-10 | 2015-11-30 | 47.1 | 45.31 | -1.79 | -0.038004 | 267 |  |  | ICT | 2.4723 | DH_0042_1314-Q3,1516-Q2 | DH | Amber | Not new
DH_0043_1314-Q3 | NHS Pension Re-let | AR 2016 | 1516-Q2 | DH | Amber | 2013-07-05 | 2017-07-21 | 2.5 | 2.5 | 0 | 0 | 10.84 |  |  | Government Transformation and Service Delivery | 4.0438 | DH_0043_1314-Q3,1516-Q2 | DH | Amber | Not new
DH_0044_1314-Q4 | Care and Support Implementation Programme | AR 2016 | 1516-Q2 | DH | Amber/Green | 2013-06-04 | 2016-12-01 | 512.1 | 354.5 | -157.6 | -0.30775 | 18619.2 |  |  | Government Transformation and Service Delivery | 3.4935 | DH_0044_1314-Q4,1516-Q2 | DH | Amber/Green | Not new
DH_0045_1415-Q1 | care.data | AR 2016 | 1516-Q2 | DH | Amber/Red | 2012-09-01 | 2020-03-31 | 4.19 | 4.1 | -0.09 | -0.02148 | 0 |  |  | ICT | 7.5784 | DH_0045_1415-Q1,1516-Q2 | DH | Amber/Red | Not new
DH_0048_1415-Q1 | 100,000 Genomes Project | AR 2016 | 1516-Q2 | DH | Amber/Red | 2013-04-10 | 2017-12-31 | 50 | 27.4 | -22.6 | -0.452 | 160 |  |  | Government Transformation and Service Delivery | 4.7255 | DH_0048_1415-Q1,1516-Q2 | DH | Amber/Red | Not new
DH_0049_1415-Q1 | NHS Choices | AR 2016 | 1516-Q2 | DH | Amber/Red | 2015-08-03 | 2016-02-03 | 0 | 0 | 0 | 0 | 0 |  |  | ICT | 0.50376 | DH_0049_1415-Q1,1516-Q2 | DH | Amber/Red | Not new
DH_0050_1415-Q1 | NHS Procurement Efficiency Programme | AR 2016 | 1516-Q2 | DH | Red | 2013-09-01 | 2016-03-31 | 18.5 | 18.5 | 0 | 0 | 71.9 |  |  | Government Transformation and Service Delivery | 2.5791 | DH_0050_1415-Q1,1516-Q2 | DH | Red | Not new
DH_0056_1415-Q3 | Visitor and Migrant NHS Cost Recovery Programme | AR 2016 | 1516-Q2 | DH | Amber | 2013-09-01 | 2017-03-31 | 4 | 3 | -1 | -0.25 | 10.5 |  |  | Government Transformation and Service Delivery | 3.5784 | DH_0056_1415-Q3,1516-Q2 | DH | Amber | Joiner
DH_0057_1516-Q1 | BT LSP | AR 2016 | 1516-Q2 | DH | Amber | 2003-12-18 | 2015-10-31 | 59.89 | 82.77 | 22.88 | 0.38203 | 1743.03 |  |  | Government Transformation and Service Delivery | 11.8686 | DH_0057_1516-Q1,1516-Q2 | DH | Amber | Joiner
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | AR 2016 | 1516-Q2 | DWP | Amber/Green | 2012-04-02 | 2017-03-31 | 152 | 124.047 | -27.953 | -0.1839 | 834 |  |  | Government Transformation and Service Delivery | 4.9938 | DWP_0016_1213-Q2,1516-Q2 | DWP | Amber/Green | Not new
DWP_0005_1112-Q1 | Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme) | AR 2016 | 1516-Q2 | DWP | Amber | 2007-05-01 | 2018-11-30 | 117.5 | 100.96 | -16.54 | -0.14077 | 995.4 |  |  | Government Transformation and Service Delivery | 11.5838 | DWP_0005_1112-Q1,1516-Q2 | DWP | Amber | Not new
DWP_0003_1112-Q1 | Child Maintenance Group | AR 2016 | 1516-Q2 | DWP | Amber/Green | 2009-08-01 | 2016-12-31 | 122.2 | 122.2 | 0 | 0 | 955.84 |  |  | Government Transformation and Service Delivery | 7.4168 | DWP_0003_1112-Q1,1516-Q2 | DWP | Amber/Green | Not new
DWP_0018_1314-Q3 | Fit for Work (formally Health & Work Service) Programme | AR 2016 | 1516-Q2 | DWP | Amber | 2013-02-27 | 2015-03-31 | 15.6 | 14.0679 | -1.5321 | -0.098214 | 276.36 |  |  | Government Transformation and Service Delivery | 2.0862 | DWP_0018_1314-Q3,1516-Q2 | DWP | Amber | Not new
DWP_0023_1415-Q2 | New State Pension Project | AR 2016 | 1516-Q2 | DWP | Amber/Green | 2012-02-27 | 2016-06-30 | 44.82 | 30 | -14.82 | -0.33066 | 174.11 |  |  | Government Transformation and Service Delivery | 4.3395 | DWP_0023_1415-Q2,1516-Q2 | DWP | Amber/Green | Not new
DWP_0011_1112-Q2 | Personal Independence Payment | AR 2016 | 1516-Q2 | DWP | Amber/Red | 2011-10-31 | 2018-04-30 | 365.81 | 351.051 | -14.759 | -0.040346 | 3603.04 |  |  | Government Transformation and Service Delivery | 6.4969 | DWP_0011_1112-Q2,1516-Q2 | DWP | Amber/Red | Not new
DWP_0009_1112-Q1 | Universal Credit Programme | AR 2016 | 1516-Q2 | DWP | Amber | 2011-11-17 | 2020-04-30 | 585.492 | 429.328 | -156.164 | -0.26672 | 15844.02 |  |  | Government Transformation and Service Delivery | 8.4517 | DWP_0009_1112-Q1,1516-Q2 | DWP | Amber | Not new
FCO_0001_1112-Q1 | ABUJA New Office and Residence | AR 2016 | 1516-Q2 | FCO | Amber | 2011-01-01 | 2016-12-01 | 18.8 | 18.8 | 0 | 0 | 46 |  |  | Infrastructure and Construction | 5.9165 | FCO_0001_1112-Q1,1516-Q2 | FCO | Amber | Not new
FCO_0004_1112-Q1 | ICTRe-procurement | AR 2016 | 1516-Q2 | FCO | Amber/Green | 2011-01-01 | 2015-12-18 | 27.29 | 31.95 | 4.66 | 0.17076 | 161.1 |  |  | ICT | 4.961 | FCO_0004_1112-Q1,1516-Q2 | FCO | Amber/Green | Not new
FCO_0009_1516-Q2 | Movement of Personal Effects Contract | AR 2016 | 1516-Q2 | FCO | Amber | 2015-07-06 | 2016-09-30 | 0 | 0 | 0 | 0 | 42.5 |  |  | Government Transformation and Service Delivery | 1.2375 | FCO_0009_1516-Q2,1516-Q2 | FCO | Amber | Joiner
FCO_0008_1415-Q4 | Technology Overhaul | AR 2016 | 1516-Q2 | FCO | Amber | 2015-11-01 | 2018-03-01 | 25.56 | 13.4 | -12.16 | -0.47574 | 114.5 |  |  | ICT | 2.3299 | FCO_0008_1415-Q4,1516-Q2 | FCO | Amber | Joiner
FCO_0006_1213-Q2 | UKERP | AR 2016 | 1516-Q2 | FCO | Amber/Red | 2011-06-01 | 2016-08-01 | 31.26 | 31.26 | 0 | 0 | 64.9 |  |  | Infrastructure and Construction | 5.1691 | FCO_0006_1213-Q2,1516-Q2 | FCO | Amber/Red | Not new
HMRC_0012_1415-Q1 | Tax-Free Childcare | AR 2016 | 1516-Q2 | HMRC | Amber | 2013-09-10 | 2018-06-30 | 41.87 | 37.5058 | -4.3642 | -0.10423 | 241.83 |  |  | Government Transformation and Service Delivery | 4.8022 | HMRC_0012_1415-Q1,1516-Q2 | HMRC | Amber | Not new
HMRC_0013_1415-Q4 | Columbus (formerly Aspire Replacement Programme) | AR 2016 | 1516-Q2 | HMRC | Amber/Red | 2014-01-01 | 2021-12-31 | 88 | 88 | 0 | 0 | 600 |  |  | ICT | 7.9973 | HMRC_0013_1415-Q4,1516-Q2 | HMRC | Amber/Red | Joiner
HMRC_0014_1415-Q4 | CUSTOMS DECLARATION SERVICES (CDS) Programme | AR 2016 | 1516-Q2 | HMRC | Amber/Red | 2013-10-16 | 2018-12-31 | 21.94 | 18.975 | -2.965 | -0.13514 | 71.16 |  |  | ICT | 5.2074 | HMRC_0014_1415-Q4,1516-Q2 | HMRC | Amber/Red | Joiner
HO_0030_1415-Q1 | Adelphi Modernisation Programme | AR 2016 | 1516-Q2 | HO | Red | 2014-06-05 | 2016-03-31 | 32.42 | 26.824 | -5.596 | -0.17261 | 185.3 |  |  | ICT | 1.8207 | HO_0030_1415-Q1,1516-Q2 | HO | Red | Not new
HO_0012_1112-Q3 | Communications Capabilities Development Programme | AR 2016 | 1516-Q2 | HO | Amber | 2010-05-01 | 2020-04-01 | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) | Data Exempt under Section 24 of the Freedom of Information Act (2000) |  |  | ICT | 9.9192 | HO_0012_1112-Q3,1516-Q2 | HO | Amber | Not new
HO_0011_1112-Q2 | Disclosure and Barring Service (DBS) Programme | AR 2016 | 1516-Q2 | HO | Amber/Red | 2010-12-29 | 2015-07-31 | 123.56 | 147.5 | 23.94 | 0.19375 | 785.633 |  |  | Government Transformation and Service Delivery | 4.5859 | HO_0011_1112-Q2,1516-Q2 | HO | Amber/Red | Not new
HO_0031_1415-Q1 | Digital Services at the Border | AR 2016 | 1516-Q2 | HO | Amber/Red | 2014-02-12 | 2019-03-31 | 16.67 | 17.89 | 1.22 | 0.073185 | 307.93 |  |  | ICT | 5.128 | HO_0031_1415-Q1,1516-Q2 | HO | Amber/Red | Not new
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2016 | 1516-Q2 | HO | Amber | 2011-06-01 | 2020-12-31 | 34.13 | 34.13 | 0 | 0 | 5319.23 |  |  | ICT | 9.5852 | HO_0016_1213-Q1,1516-Q2 | HO | Amber | Not new
HO_0033_1415-Q3 | Home Office Biometrics Programme | AR 2016 | 1516-Q2 | HO | Amber | 2014-04-01 | 2019-11-30 | 63.7 | 63.7 | 0 | 0 | 640.3 |  |  | ICT | 5.6646 | HO_0033_1415-Q3,1516-Q2 | HO | Amber | Joiner
HO_0029_1314-Q4 | Immigration Platform Technologies (IPT) | AR 2016 | 1516-Q2 | HO | Amber/Red | 2013-04-01 | 2017-03-31 | 71.1 | 49 | -22.1 | -0.31083 | 208.8 |  |  | ICT | 3.9973 | HO_0029_1314-Q4,1516-Q2 | HO | Amber/Red | Not new
HO_0008_1112-Q1 | SIS II Programme | AR 2016 | 1516-Q2 | HO | Amber/Green | 2006-04-01 | 2015-06-30 | 9.5 | 9.5 | 0 | 0 | 195.1 |  |  | ICT | 9.2457 | HO_0008_1112-Q1,1516-Q2 | HO | Amber/Green | Not new
HO_0032_1415-Q1 | Technology Platforms for Tomorrow | AR 2016 | 1516-Q2 | HO | Amber/Red | 2014-02-01 | 2016-09-01 | 29 | 29 | 0 | 0 | 369.5 |  |  | ICT | 2.5818 | HO_0032_1415-Q1,1516-Q2 | HO | Amber/Red | Not new
MOD_0064_1112-Q2 | Carrier Enabled Power Projection | AR 2016 | 1516-Q2 | MOD | Amber | 2011-01-31 | 2026-12-01 | 1.44 | 1.44 | 0 | 0 | 21.688 |  |  | Government Transformation and Service Delivery | 15.833 | MOD_0064_1112-Q2,1516-Q2 | MOD | Amber | Not new
MOD_0065_1112-Q2 | CHINOOK (incl. Project Julius) | AR 2016 | 1516-Q2 | MOD | Green | 2008-04-01 | 2017-06-30 | 97.703 | 97.703 | 0 | 0 | 1009.17 |  |  | Military Capability | 9.2457 | MOD_0065_1112-Q2,1516-Q2 | MOD | Green | Not new
MOD_0078_1213-Q1 | Core Production Capability | AR 2016 | 1516-Q2 | MOD | Amber | 2012-04-23 | 2028-11-14 | 170.5 | 158.126 | -12.374 | -0.072575 | 1443.46 |  |  | Military Capability | 16.5613 | MOD_0078_1213-Q1,1516-Q2 | MOD | Amber | Not new
HO_0034_1516-Q2 | Cyclamen Project | AR 2016 | 1516-Q2 | HO | Exempt | 2014-04-01 | 2021-04-01 | Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000) | Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000) | Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000) | Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000) | Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000) |  |  | ICT | 7.0007 | HO_0034_1516-Q2,1516-Q2 | HO | Exempt | Joiner
MOD_0079_1213-Q1 | Lightning II Programme | AR 2016 | 1516-Q2 | MOD | Amber | 2001-10-01 | 2026-03-31 | 551.467 | 529.439 | -22.028 | -0.039944 | 12941.607 |  |  | Military Capability | 24.4956 | MOD_0079_1213-Q1,1516-Q2 | MOD | Amber | Not new
MOD_0033_1112-Q1 | MARSHALL | AR 2016 | 1516-Q2 | MOD | Amber/Green | 2006-04-03 | 2020-10-04 | 74.417 | 70.29 | -4.127 | -0.055458 | 1819.961 |  |  | Military Capability | 14.5051 | MOD_0033_1112-Q1,1516-Q2 | MOD | Amber/Green | Not new
MOD_0070_1112-Q2 | New Employment Model | AR 2016 | 1516-Q2 | MOD | Amber | 2011-05-02 | 2021-10-29 | 13.61 | 8.923 | -4.687 | -0.34438 | 202.879 |  |  | Government Transformation and Service Delivery | 10.4942 | MOD_0070_1112-Q2,1516-Q2 | MOD | Amber | Not new
MOD_0103_1516-Q1 | Operational Information Services | AR 2016 | 1516-Q2 | MOD | Red | 2019-04-01 | 2024-04-01 | 9.6 | 9.6 | 0 | 0 | 73.83 |  |  | Military Capability | 5.0021 | MOD_0103_1516-Q1,1516-Q2 | MOD | Red | Joiner
MOD_0040_1112-Q1 | PUMA | AR 2016 | 1516-Q2 | MOD | Green | 2007-02-01 | 2016-03-31 | 2.162 | 2.247 | 0.085 | 0.039315 | 374.932 |  |  | Military Capability | 9.1608 | MOD_0040_1112-Q1,1516-Q2 | MOD | Green | Not new
MOD_0047_1112-Q1 | Spearfish Upgrade Programme | AR 2016 | 1516-Q2 | MOD | Amber/Green | 2008-04-01 | 2024-03-31 | 37.397 | 37.085 | -0.312 | -0.0083429 | 415.97 |  |  | Military Capability | 15.9973 | MOD_0047_1112-Q1,1516-Q2 | MOD | Amber/Green | Not new
MOD_0087_1314-Q2 | The Materiel Strategy | AR 2016 | 1516-Q2 | MOD | Amber | 2011-05-02 | 2018-05-01 | 78 | 74.23 | -3.77 | -0.048333 | 379.066 |  |  | Government Transformation and Service Delivery | 6.9979 | MOD_0087_1314-Q2,1516-Q2 | MOD | Amber | Not new
MOD_0001_1112-Q1 | A400M | AR 2016 | 1516-Q2 | MOD | Amber/Green | 2000-05-17 | 2022-03-31 | 541.668 | 491.801 | -49.867 | -0.092062 | 3713.093 |  |  | Military Capability | 21.87 | MOD_0001_1112-Q1,1516-Q2 | MOD | Amber/Green | Not new
MOD_0004_1112-Q1 | Airseeker | AR 2016 | 1516-Q2 | MOD | Amber/Green | 2010-03-18 | 2018-04-01 | 134.586 | 132.064 | -2.522 | -0.018739 | 757.801 |  |  | Military Capability | 8.0383 | MOD_0004_1112-Q1,1516-Q2 | MOD | Amber/Green | Not new
MOD_0091_1415-Q3 | Armoured Cavalry 2025 | AR 2016 | 1516-Q2 | MOD | Amber | 2014-01-22 | 2025-04-30 | 245.921 | 237.061 | -8.86 | -0.036028 | 6831.533 |  |  | Military Capability | 11.269 | MOD_0091_1415-Q3,1516-Q2 | MOD | Amber | Joiner
MOD_0092_1415-Q3 | Armoured Infantry 2026 | AR 2016 | 1516-Q2 | MOD | Amber | 2014-12-04 | 2026-12-31 | 90.497 | 84.154 | -6.343 | -0.070091 | 2176.45 |  |  | Military Capability | 12.0739 | MOD_0092_1415-Q3,1516-Q2 | MOD | Amber | Joiner
MOD_0085_1314-Q2 | Army Basing Programme | AR 2016 | 1516-Q2 | MOD | Amber/Red | 2013-05-22 | 2020-03-31 | 345.738 | 146.742 | -198.996 | -0.57557 | 1972.112 |  |  | Government Transformation and Service Delivery | 6.8583 | MOD_0085_1314-Q2,1516-Q2 | MOD | Amber/Red | Not new
MOD_0093_1415-Q3 | Army Reserve Development Programme | AR 2016 | 1516-Q2 | MOD | Amber/Red | 2014-12-01 | 2017-01-01 | 168.837 | 162.606 | -6.231 | -0.036905 | 1998.394 |  |  | Military Capability | 2.0862 | MOD_0093_1415-Q3,1516-Q2 | MOD | Amber/Red | Joiner
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2016 | 1516-Q2 | MOD | Amber/Red | 1997-03-17 | 2024-03-31 | 638.646 | 641.665 | 3.019 | 0.0047272 | 9935.482 |  |  | Military Capability | 27.039 | MOD_0076_1213-Q1,1516-Q2 | MOD | Amber/Red | Not new
MOD_0077_1213-Q1 | Complex Weapons | AR 2016 | 1516-Q2 | MOD | Amber | 2008-03-31 | 2032-04-01 | 444.094 | 336.838 | -107.256 | -0.24152 | 18499.656 |  |  | Military Capability | 24.0027 | MOD_0077_1213-Q1,1516-Q2 | MOD | Amber | Not new
MOD_0094_1415-Q3 | Contracting, Purchasing and Finance | AR 2016 | 1516-Q2 | MOD | Amber/Red | 2011-12-01 | 2018-03-31 | 38.638 | 33.85 | -4.788 | -0.12392 | 159.732 |  |  | Government Transformation and Service Delivery | 6.3299 | MOD_0094_1415-Q3,1516-Q2 | MOD | Amber/Red | Joiner
MOD_0017_1112-Q1 | Crowsnest Programme | AR 2016 | 1516-Q2 | MOD | Amber/Green | 2013-03-26 | 2022-09-30 | 4.076 | 13.599 | 9.523 | 2.3364 | Exempt under section 43 of the Freedom of Information Act (2000). |  |  | Military Capability | 9.514 | MOD_0017_1112-Q1,1516-Q2 | MOD | Amber/Green | Not new
MOD_0099_1516-Q1 | EMPORIUM | AR 2016 | 1516-Q2 | MOD | Amber | 2011-10-21 | 2017-12-01 | 7.223 | 7.223 | 0 | 0 | 236.476 |  |  | Government Transformation and Service Delivery | 6.1136 | MOD_0099_1516-Q1,1516-Q2 | MOD | Amber | Joiner
MOD_0100_1516-Q1 | Future Beyond Line Of Sight | AR 2016 | 1516-Q2 | MOD | Amber | 2011-01-01 | 2040-08-31 | 9.84 | 4.37 | -5.47 |  | 7280.69 |  |  | Military Capability | 29.6646 | MOD_0100_1516-Q1,1516-Q2 | MOD | Amber | Joiner
MOD_0102_1516-Q1 | GRAPEVINE 2 | AR 2016 | 1516-Q2 | MOD | Amber | 2009-12-01 | 2020-06-22 | 110.031 | 131.121 | 21.09 | 0.19167 | 1334.766 |  |  | Government Transformation and Service Delivery | 10.5572 | MOD_0102_1516-Q1,1516-Q2 | MOD | Amber | Joiner
MOD_0069_1112-Q2 | Logistics Commodities Services Transformation | AR 2016 | 1516-Q2 | MOD | Amber | 2011-08-01 | 2018-02-01 | 113.516 | 119.288 | 5.772 | 0.050847 | 652.415 |  |  | Government Transformation and Service Delivery | 6.5051 | MOD_0069_1112-Q2,1516-Q2 | MOD | Amber | Not new
MOD_0036_1112-Q1 | Maritime Sustainment Programme | AR 2016 | 1516-Q2 | MOD | Amber/Green | 2005-07-25 | 2018-04-30 | 194.98 | 176.839 | -18.141 | -0.09304 | 596.499 |  |  | Military Capability | 12.7639 | MOD_0036_1112-Q1,1516-Q2 | MOD | Amber/Green | Not new
MOD_0035_1112-Q1 | Merlin Programme | AR 2016 | 1516-Q2 | MOD | Green | 2003-06-01 | 2016-03-31 | 1 | 0.55 | -0.45 | -0.45 | 718.168 |  |  | Military Capability | 12.8323 | MOD_0035_1112-Q1,1516-Q2 | MOD | Green | Not new
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2016 | 1516-Q2 | MOD | Exempt | 2008-04-01 | 2025-04-30 | 1085.433 | 1009.747 | -75.686 | -0.069729 | 21028.75 |  |  | Military Capability | 17.0787 | MOD_0038_1112-Q1,1516-Q2 | MOD | Exempt | Not new
MOD_0042_1112-Q1 | Queen Elizabeth Programme | AR 2016 | 1516-Q2 | MOD | Amber | 1998-12-01 | 2023-03-31 | 712.927 | 687.006 | -25.921 | -0.036359 | 7289.681 |  |  | Military Capability | 24.3285 | MOD_0042_1112-Q1,1516-Q2 | MOD | Amber | Not new
MOD_0055_1112-Q1 | Type 26 Global Combat Ship Programme | AR 2016 | 1516-Q2 | MOD | Exempt | 2008-07-21 | 2034-12-31 | 222.3 | 222 | -0.3 | -0.0013495 | Exempt under sections 36 and 43 of the Freedom of Information Act (2000) |  |  | Military Capability | 26.4449 | MOD_0055_1112-Q1,1516-Q2 | MOD | Exempt | Not new
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2016 | 1516-Q2 | MOD | Amber | 1998-03-01 | 2017-07-03 | 61.026 | 58.935 | -2.091 | -0.034264 | 1169.776 |  |  | Military Capability | 19.3402 | MOD_0061_1112-Q1,1516-Q2 | MOD | Amber | Not new
MOD_0062_1112-Q1 | Wildcat Programme | AR 2016 | 1516-Q2 | MOD | Amber/Green | 2001-12-01 | 2016-05-31 | 39.462 | 39.456 | -0.006 | -0.00015205 | 1610.836 |  |  | Military Capability | 14.4969 | MOD_0062_1112-Q1,1516-Q2 | MOD | Amber/Green | Not new
MOJ_0004_1112-Q1 | Future IT Sourcing Programme (FITS) | AR 2016 | 1516-Q2 | MOJ | Amber/Red | 2011-03-01 | 2017-11-30 | 457 | 457 | 0 | 0 | 1706 |  |  | ICT | 6.7515 | MOJ_0004_1112-Q1,1516-Q2 | MOJ | Amber/Red | Not new
MOJ_0023_1314-Q1 | North Wales Prison (NWP ) Programme | AR 2016 | 1516-Q2 | MOJ | Amber | 2013-01-10 | 2018-03-31 | 101 | 81.2 | -19.8 | -0.19604 | 2541 |  |  | Infrastructure and Construction | 5.2183 | MOJ_0023_1314-Q1,1516-Q2 | MOJ | Amber | Not new
MOJ_0021_1314-Q1 | Common Platform (CP) | AR 2016 | 1516-Q2 | MOJ | Amber/Red | 2012-11-01 | 2019-03-29 | 63.19 | 63.19 | 0 | 0 | 380.84 |  |  | ICT | 6.4038 | MOJ_0021_1314-Q1,1516-Q2 | MOJ | Amber/Red | Not new
MOJ_0027_1314-Q2 | CJS Efficiency Programme (CJS Efficiency) | AR 2016 | 1516-Q2 | MOJ | Amber/Green | 2013-04-30 | 2016-12-31 | 28.1 | 33.9 | 5.8 | 0.20641 | 85.1 |  |  | ICT | 3.6715 | MOJ_0027_1314-Q2,1516-Q2 | MOJ | Amber/Green | Not new
MOJ_0029_1415-Q1 | Legal Aid Crime Change (LACC) Programme | AR 2016 | 1516-Q2 | MOJ | Green | 2013-07-07 | 2016-02-29 | 4.35 | 5.6126 | 1.2626 | 0.29024 | 45.01 |  |  | ICT | 2.6475 | MOJ_0029_1415-Q1,1516-Q2 | MOJ | Green | Not new
MOJ_0003_1112-Q1 | Electronic Monitoring (EM) | AR 2016 | 1516-Q2 | MOJ | Red | 2011-05-10 | 2016-11-30 | 117.1 | 90.82 | -26.28 | -0.22442 | 411.6 |  |  | Government Transformation and Service Delivery | 5.5606 | MOJ_0003_1112-Q1,1516-Q2 | MOJ | Red | Not new
MOJ_0005_1112-Q1 | Her Majesty's Courts and Tribunals Services (HMCTS) Compliance & Enforcement Services Project (CESP) | AR 2016 | 1516-Q2 | MOJ | Amber/Red | 2012-06-21 | 2017-01-07 | 44.8 | 45.12 | 0.32 | 0.0071429 | 439.2 |  |  | Government Transformation and Service Delivery | 4.5476 | MOJ_0005_1112-Q1,1516-Q2 | MOJ | Amber/Red | Not new
MOJ_0006_1112-Q1 | Integrated Delivery Programme (IDP) | AR 2016 | 1516-Q2 | MOJ | Amber | 2009-07-01 | 2016-03-31 | 2.69 | 2.49 | -0.2 | -0.074349 | 71.48 |  |  | ICT | 6.7488 | MOJ_0006_1112-Q1,1516-Q2 | MOJ | Amber | Not new
MOJ_0028_1314-Q2 | Her Majesty's Courts and Tribunals Services (HMCTS) Reform Programme | AR 2016 | 1516-Q2 | MOJ | Amber/Red | 2013-03-21 | 2020-03-31 | 48.16 | 48.2 | 0.04 | 0.00083056 | 510.4 |  |  | Government Transformation and Service Delivery | 7.0281 | MOJ_0028_1314-Q2,1516-Q2 | MOJ | Amber/Red | Not new
MOJ_0022_1314-Q1 | Legal Aid Transformation Programme (LAT) | AR 2016 | 1516-Q2 | MOJ | Amber | 2012-12-04 | 2015-11-01 | 1.32 | 2.1127 | 0.79272 | 0.60054 | 6.1727 |  |  | Government Transformation and Service Delivery | 2.9076 | MOJ_0022_1314-Q1,1516-Q2 | MOJ | Amber | Not new
MOJ_0015_1112-Q2 | NOMS ICTS Services (NICTS) Programme (formally part of Quantum Re-compete Project) | AR 2016 | 1516-Q2 | MOJ | Amber | 2011-07-18 | 2016-03-29 | 0 | 14.425 | 14.425 | 0 | 41.75 |  |  | ICT | 4.6982 | MOJ_0015_1112-Q2,1516-Q2 | MOJ | Amber | Not new
MOJ_0024_1314-Q1 | Prison Unit Cost Programme (PUCP) | AR 2016 | 1516-Q2 | MOJ | Amber | 2012-11-20 | 2016-12-01 | 30.5 | 23.3 | -7.2 | -0.23607 | 119.5 |  |  | Government Transformation and Service Delivery | 4.0301 | MOJ_0024_1314-Q1,1516-Q2 | MOJ | Amber | Not new
MOJ_0025_1314-Q1 | Transforming Rehabilitation (TR) Programme | AR 2016 | 1516-Q2 | MOJ | Green | 2012-11-05 | 2015-03-31 | 932.93 | 932.95 | 0.02 | 2.1438e-05 | 9127.61 |  |  | Government Transformation and Service Delivery | 2.3984 | MOJ_0025_1314-Q1,1516-Q2 | MOJ | Green | Not new
MOJ_0008_1112-Q1 | MoJ Shared Services Evolve (SS Evolve) Programme | AR 2016 | 1516-Q2 | MOJ | Amber/Red | 2013-09-07 | 2015-11-05 | 93.91 | 82.05 | -11.86 | -0.12629 | 390.77 |  |  | ICT | 2.1602 | MOJ_0008_1112-Q1,1516-Q2 | MOJ | Amber/Red | Not new
MOJ_0030_1516-Q1 | Secure Training centre (STC) Retendering Project | AR 2016 | 1516-Q2 | MOJ | Amber/Green | 2012-11-05 | 2017-05-01 | 0.73 | 0.73 | 0 | 0 | 165.2046 |  |  | Government Transformation and Service Delivery | 4.4846 | MOJ_0030_1516-Q1,1516-Q2 | MOJ | Amber/Green | Joiner
MOJ_0031_1516-Q2 | Transforming Prisoner Telephony (TPT) | AR 2016 | 1516-Q2 | MOJ | Amber/Red | 2015-02-01 | 2020-03-31 | 0.9 | 0.9 | 0 | 0 | 39.3 |  |  | Government Transformation and Service Delivery | 5.1608 | MOJ_0031_1516-Q2,1516-Q2 | MOJ | Amber/Red | Joiner
NCA_0001_1415-Q2 | Novo (NCA Transformation) Programme | AR 2016 | 1516-Q2 | NCA | Amber | 2014-04-01 | 2019-03-31 | 44.8 | 38.7 | -6.1 | -0.13616 | 151.5 |  |  | Government Transformation and Service Delivery | 4.9966 | NCA_0001_1415-Q2,1516-Q2 | NCA | Amber | Not new
ONS_0002_1112-Q1 | Census Transformation Programme | AR 2016 | 1516-Q2 | ONS | Amber/Green | 2015-01-01 | 2025-03-31 | 19.93 | 19.9 | -0.03 | -0.0015053 | 981.32 |  |  | Government Transformation and Service Delivery | 10.245 | ONS_0002_1112-Q1,1516-Q2 | ONS | Amber/Green | Not new
ONS_0004_1213-Q2 | Electronic Data Collection (EDC) | AR 2016 | 1516-Q2 | ONS | Amber | 2014-01-27 | 2019-11-01 | 6.03 | 6.11 | 0.08 | 0.013267 | 23.7 |  |  | Government Transformation and Service Delivery | 5.7604 | ONS_0004_1213-Q2,1516-Q2 | ONS | Amber | Not new
ONS_0005_1213-Q2 | ESA10/BPM6 Programme (European Systems of Accounting 2010) | AR 2016 | 1516-Q2 | ONS | Amber/Green | 2011-02-05 | 2020-03-30 | 11.489 | 9.4467 | -2.0423 | -0.17776 | 57.846 |  |  | Government Transformation and Service Delivery | 9.1472 | ONS_0005_1213-Q2,1516-Q2 | ONS | Amber/Green | Not new
MOD_0080_1213-Q1 | Successor SSBN | AR 2016 | 1516-Q2 | MOD | Amber/Red | 2011-04-14 | Exempt under section 35 of the Freedom of Information Act (2000) | 770.405 | 739.342 | -31.063 | -0.04032 | Exempt under section 43 of the Freedom of Information Act (2000) |  |  | Military Capability | 0 | MOD_0080_1213-Q1,1516-Q2 | MOD | Amber/Red | Not new
MOD_0095_1415-Q2 | Cryptographic Enabling Services | AR 2016 | 1516-Q2 | MOD | Exempt | Exempt under section 26 of the Freedom of Information Act (2000) | Exempt under section 26 of the Freedom of Information Act (2000) | Exempt under section 26 of the Freedom of Information Act (2000) | Exempt under section 26 of the Freedom of Information Act (2000) | 0 | 0 | Exempt under section 26 of the Freedom of Information Act (2000) |  |  | Military Capability | 0 | MOD_0095_1415-Q2,1516-Q2 | MOD | Exempt | Not new
MOD_0101_1516-Q1 | GRAPEVINE 1 | AR 2016 | 1516-Q2 | MOD | Amber | 2015-04-01 | 2018-03-05 | Exempt under section 43 of the Freedom of Information Act (2000). | Exempt under section 43 of the Freedom of Information Act (2000). |  |  | Exempt under section 43 of the Freedom of Information Act (2000). |  |  | Government Transformation and Service Delivery | 2.9268 | MOD_0101_1516-Q1,1516-Q2 | MOD | Amber | Joiner
BEIS_0001_1617-Q2 | Heat Networks Investment Project | AR 2017 | 1617-Q2 | BEIS | Exempt | 2015-11-25 | 2021-03-31 | 36.6 | 36.6 | 0 | 0 | 352.7 | 352.7 | 0 | Infrastructure and Construction | 5.3507 | BEIS_0001_1617-Q2,1617-Q2 | BEIS | Exempt | Joiner
BIS_0009_1112-Q1 | The Francis Crick Institute | AR 2017 | 1617-Q2 | BEIS | Amber | 2006-10-01 | 2016-12-31 | 27.7 | 24 | -3.7 | -0.13357 | 752.7 | 283.7 | 469 | Infrastructure and Construction | 10.2575 | BIS_0009_1112-Q1,1617-Q2 | BEIS | Amber | Not new
BIS_0010_1112-Q4 | Project Eagle (formerly Urenco Future Options) | AR 2017 | 1617-Q2 | BEIS | Red | 2010-02-01 | 2013-04-30 | 1.7 | 1.7 | 0 | 0 | 32.6 | 32.6 | 0 | Government Transformation and Service Delivery | 3.2438 | BIS_0010_1112-Q4,1617-Q2 | BEIS | Red | Not new
BIS_0014_1415-Q3 | New Polar Research Vessel | AR 2017 | 1617-Q2 | BEIS | Amber/Green | 2014-05-01 | 2020-07-01 | 63 | 71.5 | 8.5 | 0.13492 | 1403 | 1403 | 0 | Infrastructure and Construction | 6.1726 | BIS_0014_1415-Q3,1617-Q2 | BEIS | Amber/Green | Not new
BIS_0015_1516-Q1 | Local Land Charges (LLC) Programme | AR 2017 | 1617-Q2 | BEIS | Amber | 2014-03-01 | 2023-11-17 | 12.2 | 9.9 | -2.3 | -0.18852 | 193.3 | 193.3 | 0 | ICT | 9.7205 | BIS_0015_1516-Q1,1617-Q2 | BEIS | Amber | Not new
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2017 | 1617-Q2 | BEIS | Amber | 2008-06-30 | 2040-12-31 | 28.47 | 28.53 | 0.06 | 0.0021075 | 11751.97 | 11751.97 | 0 | Infrastructure and Construction | 32.526 | DECC_0005_1112-Q1,1617-Q2 | BEIS | Amber | Not new
DECC_0010_1112-Q1 | Smart Metering Implementation Programme | AR 2017 | 1617-Q2 | BEIS | Amber | 2009-12-02 | 2020-12-31 | 524.26 | 523.96 | -0.3 | -0.00057224 | 17215.7801 | 124.11 | 17091.6701 | Infrastructure and Construction | 11.0877 | DECC_0010_1112-Q1,1617-Q2 | BEIS | Amber | Not new
DECC_0012_1213-Q1 | FID Enabling for Hinkley Point C | AR 2017 | 1617-Q2 | BEIS | Green | 2011-09-01 | 2016-09-30 | 1.8 | 1.7 | -0.1 | -0.055556 | 49891.2 | 25.8 | 49865.4 | Infrastructure and Construction | 5.0849 | DECC_0012_1213-Q1,1617-Q2 | BEIS | Green | Not new
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | AR 2017 | 1617-Q2 | BEIS | Amber | 2012-04-03 | 2015-08-31 | 692 | 434 | -258 | -0.37283 | 3860 | 3860 | 0 | Infrastructure and Construction | 3.411 | DECC_0013_1213-Q1,1617-Q2 | BEIS | Amber | Not new
DECC_0017_1516-Q1 | Sellafield Model Change (SMC) | AR 2017 | 1617-Q2 | BEIS | Amber | 2015-01-13 | 2017-05-24 | 2302.5 | 2204.5 | -98 | -0.042562 | 29992.92 | 29992.92 | 0 | Government Transformation and Service Delivery | 2.3616 | DECC_0017_1516-Q1,1617-Q2 | BEIS | Amber | Not new
CO_0011_1415-Q4 | ISSC2 | AR 2017 | 1617-Q2 | CO | Amber | 2012-12-28 | 2015-04-30 | 5.7 | 5.7 | 0 | 0 | 26.1 | 26.1 | 0 | Government Transformation and Service Delivery | 2.337 | CO_0011_1415-Q4,1617-Q2 | CO | Amber | Not new
CO_0012_1415-Q4 | Commercial Capability Programme | AR 2017 | 1617-Q2 | CO | Amber | 2015-01-01 | 2018-03-31 | 6.2 | 6.2 | 0 | 0 | 17.5 | 17.5 | 0 | Government Transformation and Service Delivery | 3.2466 | CO_0012_1415-Q4,1617-Q2 | CO | Amber | Not new
CO_0013_1516-Q2 | Foxhound Programme | AR 2017 | 1617-Q2 | CO | Amber | 2013-09-01 | 2018-07-01 | 21.75 | 21.75 | 0 | 0 | 189.3 | 189.3 | 0 | ICT | 4.8329 | CO_0013_1516-Q2,1617-Q2 | CO | Amber | Not new
CO_0014_1516-Q2 | Government Hubs Programme | AR 2017 | 1617-Q2 | CO | Amber | 2015-05-01 | 2021-12-31 | 55.6 | 51.9 | -3.7 | -0.066547 | 1076.9 | 1076.9 | 0 | Government Transformation and Service Delivery | 6.674 | CO_0014_1516-Q2,1617-Q2 | CO | Amber | Not new
CO_0015_1516-Q2 | GOV UK Verify | AR 2017 | 1617-Q2 | CO | Amber/Green | 2012-04-01 | 2020-03-31 | 0 | 0 | 0 | 0 | Exempt |  | 0 | ICT | 8.0027 | CO_0015_1516-Q2,1617-Q2 | CO | Amber/Green | Not new
CO_0016_1516-Q4 | 16/17 New Property Model Programme | AR 2017 | 1617-Q2 | CO | Amber | 2015-04-01 | 2021-04-01 | 17.9 | 17.9 | 0 | 0 | 94.5 | 94.5 | 0 | Government Transformation and Service Delivery | 6.0055 | CO_0016_1516-Q4,1617-Q2 | CO | Amber | Joiner
CPS_0001_1314-Q4 | ICTRestructure Programme | AR 2017 | 1617-Q2 | CPS | Amber/Green | 2013-10-01 | 2016-08-31 | 21.7 | 22 | 0.3 | 0.013825 | 146 | 146 | 0 | ICT | 2.9178 | CPS_0001_1314-Q4,1617-Q2 | CPS | Amber/Green | Not new
DCMS_0001_1112-Q1 | Broadband Delivery Programme | AR 2017 | 1617-Q2 | DCMS | Amber/Green | 2010-12-06 | 2020-12-31 | 456.1 | 437.8 | -18.3 | -0.040123 | 2223.9 | 838.9 | 1385 | Infrastructure and Construction | 10.0767 | DCMS_0001_1112-Q1,1617-Q2 | DCMS | Amber/Green | Not new
DCMS_0004_1112-Q1 | The Tate Modern Project | AR 2017 | 1617-Q2 | DCMS | Green | 2010-01-01 | 2016-12-31 | 12.9 | 10.9 | -2 | -0.15504 | 271 | 73.1 | 197.9 | Infrastructure and Construction | 7.0027 | DCMS_0004_1112-Q1,1617-Q2 | DCMS | Green | Not new
DCMS_0008_1516-Q4 | Blythe House Programme | AR 2017 | 1617-Q2 | DCMS | Amber/Red | 2015-11-25 | 2023-03-31 | 29 | 16.42 | -12.58 | -0.43379 | 337.95 | 150 | 187.95 | Infrastructure and Construction | 7.3507 | DCMS_0008_1516-Q4,1617-Q2 | DCMS | Amber/Red | Joiner
DCMS_0009_1516-Q4 | 700 MHz Clearance Programme | AR 2017 | 1617-Q2 | DCMS | Amber | 2016-01-13 | 2022-01-01 | 71.78 | 34.119 | -37.661 | -0.52467 | 594.9 | 594.9 | 0 | Infrastructure and Construction | 5.9726 | DCMS_0009_1516-Q4,1617-Q2 | DCMS | Amber | Joiner
DEFRA_0001_1112-Q1 | CAP Delivery Programme | AR 2017 | 1617-Q2 | DEFRA | Amber | 2011-01-01 | 2017-03-31 | 13.14 | 24.6 | 11.46 | 0.87215 | 215.88 | 215.88 | 0 | Government Transformation and Service Delivery | 6.2493 | DEFRA_0001_1112-Q1,1617-Q2 | DEFRA | Amber | Not new
DEFRA_0004_1112-Q1 | Thames Estuary Asset Management Programme (TEAM2100) | AR 2017 | 1617-Q2 | DEFRA | Green | 2010-04-01 | 2025-12-31 | 23.4 | 20.3 | -3.1 | -0.13248 | 318.42 | 318.42 | 0 | Infrastructure and Construction | 15.7616 | DEFRA_0004_1112-Q1,1617-Q2 | DEFRA | Green | Not new
DEFRA_0005_1213-Q3 | Thames Tideway Tunnel | AR 2017 | 1617-Q2 | DEFRA | Amber/Green | 2010-09-07 | 2023-12-31 | 1.5 | 1.5 | 0 | 0 | 4159.8 | 22.8 | 4137 | Infrastructure and Construction | 13.3233 | DEFRA_0005_1213-Q3,1617-Q2 | DEFRA | Amber/Green | Not new
DEFRA_0006_1516-Q1 | DEFRA UNITY PROGRAMME | AR 2017 | 1617-Q2 | DEFRA | Amber/Red | 2014-11-01 | 2018-10-31 | 160.8 | 160.8 | 0 | 0 | 1048.4 | 1048.4 | 0 | ICT | 4 | DEFRA_0006_1516-Q1,1617-Q2 | DEFRA | Amber/Red | Not new
BIS_0008_1112-Q1 | ICR Student Loans Monetisation | AR 2017 | 1617-Q2 | DFE | Amber | 2010-03-01 | 2017-03-31 | 0 | 5.5 | 5.5 | 0 | 15.29 | 15.29 | 0 | Government Transformation and Service Delivery | 7.0877 | BIS_0008_1112-Q1,1617-Q2 | DFE | Amber | Not new
DFE_0005_1415-Q2 | PSBP Private Finance | AR 2017 | 1617-Q2 | DFE | Amber/Green | 2011-07-19 | 2043-07-01 | 329.8954 | 326.8556 | -3.0398 | -0.0092144 | 2153.0367 | 2153.0367 | 0 | Infrastructure and Construction | 31.9726 | DFE_0005_1415-Q2,1617-Q2 | DFE | Amber/Green | Not new
DFE_0007_1617-Q1 | 30 Hrs Free Childcare Project | AR 2017 | 1617-Q2 | DFE | Amber/Red | 2015-05-11 | 2020-03-31 | 80 | 79.3 | -0.7 | -0.00875 | 1920.72 | 1920.72 | 0 | Government Transformation and Service Delivery | 4.8932 | DFE_0007_1617-Q1,1617-Q2 | DFE | Amber/Red | Joiner
DfE_0008_1617-Q1 | Priority School Building Programme (PSBP) | AR 2017 | 1617-Q2 | DFE | Amber | 2011-07-19 | 2075-12-31 | 745.07 | 724.07 | -21 | -0.028185 | 4403.01 | 4403.01 | 0 | Infrastructure and Construction | 64.4959 | DfE_0008_1617-Q1,1617-Q2 | DFE | Amber | Joiner
DfE_0009_1617-Q2 | Apprenticeships Reform Programme | AR 2017 | 1617-Q2 | DFE | Amber/Red | 2015-05-08 | 2021-04-01 | 1919.4 | 1784.2 | -135.2 | -0.070439 | 11347.5 | 11347.5 | 0 | Government Transformation and Service Delivery | 5.9041 | DfE_0009_1617-Q2,1617-Q2 | DFE | Amber/Red | Joiner
DFID_0001_1112-Q1 | St Helena Airport | AR 2017 | 1617-Q2 | DFID | Amber/Red | 2005-03-15 | 2026-08-31 | 7.2 | 11.5 | 4.3 | 0.59722 | 445.45 | 445.45 | 0 | Infrastructure and Construction | 21.4767 | DFID_0001_1112-Q1,1617-Q2 | DFID | Amber/Red | Not new
DFT_0001_1112-Q1 | Crossrail Programme | AR 2017 | 1617-Q2 | DFT | Amber/Green | 2008-07-22 | 2019-12-31 | 770.49 | 2167.2 | 1396.71 | 1.8128 | 14768.87 | 7576.77 | 7192.1 | Infrastructure and Construction | 11.4493 | DFT_0001_1112-Q1,1617-Q2 | DFT | Amber/Green | Not new
DFT_0004_1112-Q1 | High Speed Rail Programme (HS2) | AR 2017 | 1617-Q2 | DFT | Amber/Red | 2011-02-28 | 2033-12-31 | 928.617 | 928.617 | 0 | 0 | 55700 | 55700 | 0 | Infrastructure and Construction | 22.8548 | DFT_0004_1112-Q1,1617-Q2 | DFT | Amber/Red | Not new
DFT_0005_1112-Q1 | Intercity Express Programme | AR 2017 | 1617-Q2 | DFT | Amber | 2005-06-01 | 2020-02-06 | 98 | 146.34 | 48.34 | 0.49327 | 6512.95 | 236.95 | 6276 | Infrastructure and Construction | 14.6932 | DFT_0005_1112-Q1,1617-Q2 | DFT | Amber | Not new
DFT_0014_1112-Q1 | Search and Rescue Helicopters | AR 2017 | 1617-Q2 | DFT | Amber/Green | 2011-02-08 | 2017-09-08 | 207.6 | 193.5 | -14.1 | -0.067919 | 2157.4 | 2157.4 | 0 | Infrastructure and Construction | 6.5863 | DFT_0014_1112-Q1,1617-Q2 | DFT | Amber/Green | Not new
DFT_0015_1112-Q1 | Shared Services Implementation Programme | AR 2017 | 1617-Q2 | DFT | Amber | 2010-12-10 | 2013-06-01 | 20.2 | 9.9 | -10.3 | -0.5099 | 161.1 | 161.1 | 0 | ICT | 2.4767 | DFT_0015_1112-Q1,1617-Q2 | DFT | Amber | Not new
DFT_0016_1112-Q1 | Thameslink Programme | AR 2017 | 1617-Q2 | DFT | Amber/Green | 2005-07-01 | 2026-12-31 | 20.74 | 20.99 | 0.25 | 0.012054 | 7287.7 | 337.7 | 6950 | Infrastructure and Construction | 21.5151 | DFT_0016_1112-Q1,1617-Q2 | DFT | Amber/Green | Not new
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | AR 2017 | 1617-Q2 | DFT | Amber | 2012-09-01 | 2021-09-30 | 106.3 | 131.9 | 25.6 | 0.24083 | 1492.3 | 1492.3 | 0 | Infrastructure and Construction | 9.0849 | DFT_0020_1314-Q2,1617-Q2 | DFT | Amber | Not new
DFT_0021_1314-Q3 | Rail Franchising Programme | AR 2017 | 1617-Q2 | DFT | Amber | 2013-03-26 | 2029-11-29 | -74.9 | -53.2 | 21.7 | -0.28972 | -7169.2 | -7169.2 | 0 | Government Transformation and Service Delivery | 16.6904 | DFT_0021_1314-Q3,1617-Q2 | DFT | Amber | Not new
DfT_0022_1415-Q4 | Lower Thames Crossing Feasibility | AR 2017 | 1617-Q2 | DFT | Amber/Red | 2014-05-30 | 2026-12-31 | 35.6 | 26.62 | -8.98 | -0.25225 | 199.1 | 199.1 | 0 | Infrastructure and Construction | 12.5973 | DfT_0022_1415-Q4,1617-Q2 | DFT | Amber/Red | Not new
DfT_0023_1516-Q3 | Airport Capacity Programme | AR 2017 | 1617-Q2 | DFT | Amber | 2015-07-01 | 2029-12-31 | 14 | 9 | -5 | -0.35714 | 79 | 79 | 0 | Infrastructure and Construction | 14.5123 | DfT_0023_1516-Q3,1617-Q2 | DFT | Amber | Joiner
DFT_0024_1516-Q4 | A303 Amesbury to Berwick Down | AR 2017 | 1617-Q2 | DFT | Red | 2014-12-01 | 2024-06-01 | 8.6 | 11.3 | 2.7 | 0.31395 | 385.11 | 385.11 | 0 | Infrastructure and Construction | 9.5068 | DFT_0024_1516-Q4,1617-Q2 | DFT | Red | Joiner
DFT_0025_1617-Q1 | East West Rail Programme (Western Section) | AR 2017 | 1617-Q2 | DFT | Amber/Red | 2012-10-31 | 2024-03-31 | 72.5 | 69.1 | -3.4 | -0.046897 | 1592 | 0 | 1592 | Infrastructure and Construction | 11.4219 | DFT_0025_1617-Q1,1617-Q2 | DFT | Amber/Red | Joiner
DFT_0026_1617-Q1 | Great Western Route Modernisation (GWRM) including electrification | AR 2017 | 1617-Q2 | DFT | Amber/Red | 2011-12-01 | 2024-12-31 | 772.4 | 740.1 | -32.3 | -0.041818 | 5507 | 0 | 5507 | Infrastructure and Construction | 13.0932 | DFT_0026_1617-Q1,1617-Q2 | DFT | Amber/Red | Joiner
DFT_0027_1617-Q1 | Midland Main Line Programme | AR 2017 | 1617-Q2 | DFT | Amber | 2011-01-01 | 2024-12-31 | 263.2 | 256.5 | -6.7 | -0.025456 | 2620 | 0 | 2620 | Infrastructure and Construction | 14.0082 | DFT_0027_1617-Q1,1617-Q2 | DFT | Amber | Joiner
DFT_0028_1617-Q1 | North of England Programme | AR 2017 | 1617-Q2 | DFT | Amber/Red | 2011-11-03 | 2022-12-31 | 652 | 474.5 | -177.5 | -0.27224 | 4826.8 | 947.1 | 3879.7 | Infrastructure and Construction | 11.1671 | DFT_0028_1617-Q1,1617-Q2 | DFT | Amber/Red | Joiner
DFT_0029_1617-Q1 | South West Route Capacity | AR 2017 | 1617-Q2 | DFT | Amber/Red | 2012-07-16 | 2019-12-31 | 178.86 | 180.96 | 2.1 | 0.011741 | 733.9 | 132.7 | 601.2 | Infrastructure and Construction | 7.463 | DFT_0029_1617-Q1,1617-Q2 | DFT | Amber/Red | Joiner
DFT_0030_1617-Q2 | M20 Lorry Area | AR 2017 | 1617-Q2 | DFT | Red | 2015-11-25 | 2018-01-20 | 230 | 86.5 | -143.5 | -0.62391 | 250 | 250 | 0 | Infrastructure and Construction | 2.1562 | DFT_0030_1617-Q2,1617-Q2 | DFT | Red | Joiner
DH_0008_1112-Q1 | Electronic Transmission of Prescriptions ETP - Electronic Prescription Service (EPS) Release 2 | AR 2017 | 1617-Q2 | DH | Amber | 2003-01-01 | 2016-12-31 | 3.46 | 5.58 | 2.12 | 0.61272 | 77.73 | 77.73 | 0 | ICT | 14.0082 | DH_0008_1112-Q1,1617-Q2 | DH | Amber | Not new
DH_0015_1112-Q1 | CSC Local Service Provider (LSP) Delivery Programme | AR 2017 | 1617-Q2 | DH | Amber/Green | 2003-06-23 | 2017-12-31 | 100.8738 | 74 | -26.8738 | -0.26641 | 2109.8358 | 2109.8358 | 0 | Government Transformation and Service Delivery | 14.5342 | DH_0015_1112-Q1,1617-Q2 | DH | Amber/Green | Not new
DH_0017_1112-Q1 | PHE Science Hub | AR 2017 | 1617-Q2 | DH | Amber | 2013-06-28 | 2023-03-31 | 276.6 | 152.7 | -123.9 | -0.44794 | 10997.761 | 10997.761 | 0 | Infrastructure and Construction | 9.7616 | DH_0017_1112-Q1,1617-Q2 | DH | Amber | Not new
DH_0028_1314-Q1 | General Practice System of Choice (GPSoC) Replacement | AR 2017 | 1617-Q2 | DH | Amber | 2012-01-26 | 2015-03-31 | 179.47 | 171.32 | -8.15 | -0.045411 | 527.54 | 527.54 | 0 | ICT | 3.1781 | DH_0028_1314-Q1,1617-Q2 | DH | Amber | Not new
DH_0029_1314-Q1 | Liaison and Diversion Programme | AR 2017 | 1617-Q2 | DH | Amber | 2011-04-01 | 2014-04-01 | 39.8 | 39.8 | 0 | 0 | 389.3 | 389.3 | 0 | Government Transformation and Service Delivery | 3.0027 | DH_0029_1314-Q1,1617-Q2 | DH | Amber | Not new
DH_0030_1314-Q1 | National Pandemic Flu Service | AR 2017 | 1617-Q2 | DH | Amber/Green | 2012-03-19 | 2016-10-30 | 8.3 | 5.8 | -2.5 | -0.3012 | 26.5 | 26.5 | 0 | ICT | 4.6192 | DH_0030_1314-Q1,1617-Q2 | DH | Amber/Green | Not new
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | AR 2017 | 1617-Q2 | DH | Amber | 2012-01-01 | 2018-05-30 | 87.3663 | 67.3204 | -20.0459 | -0.22945 | 1247.2498 | 1227.2498 | 20 | Government Transformation and Service Delivery | 6.4137 | DH_0031_1314-Q1,1617-Q2 | DH | Amber | Not new
DH_0033_1314-Q1 | Childhood Flu Immunisation Programme | AR 2017 | 1617-Q2 | DH | Amber/Green | 2013-09-03 | 2018-09-01 | 78.9 | 78.9 | 0 | 0 | 318.81 | 318.81 | 0 | Government Transformation and Service Delivery | 4.9973 | DH_0033_1314-Q1,1617-Q2 | DH | Amber/Green | Not new
DH_0039_1314-Q2 | NHS e-Referral Service | AR 2017 | 1617-Q2 | DH | Amber | 2012-03-29 | 2018-03-31 | 27.86 | 20.5986 | -7.2614 | -0.26064 | 131.17 | 131.17 | 0 | ICT | 6.0082 | DH_0039_1314-Q2,1617-Q2 | DH | Amber | Not new
DH_0040_1314-Q2 | NHSmail 2 | AR 2017 | 1617-Q2 | DH | Amber | 2012-03-29 | 2021-02-26 | 17.19 | 25.1081 | 7.9181 | 0.46062 | 133.03 | 133.03 | 0 | ICT | 8.9205 | DH_0040_1314-Q2,1617-Q2 | DH | Amber | Not new
DH_0041_1314-Q2 | Health & Social Care Network | AR 2017 | 1617-Q2 | DH | Amber/Red | 2012-03-29 | 2020-04-01 | 137.26 | 86.57 | -50.69 | -0.3693 | 720.18 | 720.18 | 0 | ICT | 8.0137 | DH_0041_1314-Q2,1617-Q2 | DH | Amber/Red | Not new
DH_0042_1314-Q3 | NHS Electronic Staff Record Reprocurement Project | AR 2017 | 1617-Q2 | DH | Amber/Green | 2013-06-10 | 2015-11-30 | 44.8741 | 51.3156 | 6.4415 | 0.14355 | 267.0108 | 267.0108 | 0 | ICT | 2.474 | DH_0042_1314-Q3,1617-Q2 | DH | Amber/Green | Not new
DH_0043_1314-Q3 | NHS Pension Re-let | AR 2017 | 1617-Q2 | DH | Amber | 2013-07-05 | 2017-07-21 | 10.5 | 10.5 | 0 | 0 | 20.4 | 20.4 | 0 | Government Transformation and Service Delivery | 4.0466 | DH_0043_1314-Q3,1617-Q2 | DH | Amber | Not new
DH_0048_1415-Q1 | 100,000 Genomes Project | AR 2017 | 1617-Q2 | DH | Amber/Red | 2013-04-10 | 2017-12-31 | 50 | 47.9 | -2.1 | -0.042 | 350 | 350 | 0 | Government Transformation and Service Delivery | 4.7288 | DH_0048_1415-Q1,1617-Q2 | DH | Amber/Red | Not new
DH_0056_1415-Q3 | Visitor and Migrant NHS Cost Recovery Programme | AR 2017 | 1617-Q2 | DH | Amber/Red | 2013-09-01 | 2018-03-31 | 8.78 | 7.265 | -1.515 | -0.17255 | 19.28 | 19.28 | 0 | Government Transformation and Service Delivery | 4.5808 | DH_0056_1415-Q3,1617-Q2 | DH | Amber/Red | Not new
DH_0058_1516-Q4 | National Data Services Development Programme | AR 2017 | 1617-Q2 | DH | Amber/Red | 2015-02-23 | 2020-03-31 | 30.18 | 30.18 | 0 | 0 | 167.96 | 167.96 | 0 | ICT | 5.1041 | DH_0058_1516-Q4,1617-Q2 | DH | Amber/Red | Joiner
DH_0059_1617-Q1 | Procurement Transformation Programme | AR 2017 | 1617-Q2 | DH | Amber | 2015-03-31 | 2019-03-31 | 16.8 | 16.8 | 0 | 0 | 140.6456 | 140.6456 | 0 | Government Transformation and Service Delivery | 4.0027 | DH_0059_1617-Q1,1617-Q2 | DH | Amber | Joiner
DH_0060_1617-Q1 | NHS UK | AR 2017 | 1617-Q2 | DH | Amber | 2016-04-01 | 2020-12-31 | 2.12 | 8.1 | 5.98 | 2.8208 | 2.914 | 2.914 | 0 | Government Transformation and Service Delivery | 4.7534 | DH_0060_1617-Q1,1617-Q2 | DH | Amber | Joiner
DWP_0025_1516-Q4 | Application Development Maintenance and Support (ADMS) | AR 2017 | 1617-Q2 | DWP | Amber | 2016-03-01 | 2017-03-31 | 168.6249 | 168.6249 | 0 | 0 | 602.8626 | 602.8626 | 0 | ICT | 1.0822 | DWP_0025_1516-Q4,1617-Q2 | DWP | Amber | Joiner
DWP_0005_1112-Q1 | Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme) | AR 2017 | 1617-Q2 | DWP | Amber | 2007-05-01 | 2018-11-30 | 101.9 | 67.8 | -34.1 | -0.33464 | 995.4 | 995.4 | 0 | Government Transformation and Service Delivery | 11.5918 | DWP_0005_1112-Q1,1617-Q2 | DWP | Amber | Not new
DWP_0024_1516-Q3 | DWP People and Locations Programme | AR 2017 | 1617-Q2 | DWP | Amber/Red | 2015-11-19 | 2018-04-27 | 91.29 | 45.93 | -45.36 | -0.49688 | 5560.67 | 5560.67 | 0 | Government Transformation and Service Delivery | 2.4384 | DWP_0024_1516-Q3,1617-Q2 | DWP | Amber/Red | Joiner
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | AR 2017 | 1617-Q2 | DWP | Amber/Green | 2012-04-02 | 2017-03-31 | 110.8 | 83 | -27.8 | -0.2509 | 821.9 | 821.9 | 0 | Government Transformation and Service Delivery | 4.9973 | DWP_0016_1213-Q2,1617-Q2 | DWP | Amber/Green | Not new
DWP_0026_1516-Q4 | Hosting | AR 2017 | 1617-Q2 | DWP | Amber | 2016-03-30 | 2018-02-08 | 287.9661 | 241.39 | -46.5761 | -0.16174 | 1187.6726 | 1187.6726 | 0 | ICT | 1.863 | DWP_0026_1516-Q4,1617-Q2 | DWP | Amber | Joiner
DWP_0009_1112-Q1 | Universal Credit Programme | AR 2017 | 1617-Q2 | DWP | Amber | 2011-11-17 | 2022-06-30 | 534.88 | 496.65 | -38.23 | -0.071474 | 13573.69 | 13573.69 | 0 | Government Transformation and Service Delivery | 10.6247 | DWP_0009_1112-Q1,1617-Q2 | DWP | Amber | Not new
DWP_0027_1617-Q2 | Work and Health Programme | AR 2017 | 1617-Q2 | DWP | Amber | 2015-12-01 | 2018-03-31 | 14 | 3.88 | -10.12 | -0.72286 | 401 | 401 | 0 | Government Transformation and Service Delivery | 2.3315 | DWP_0027_1617-Q2,1617-Q2 | DWP | Amber | Joiner
FCO_0001_1112-Q1 | ABUJA New Office and Residence | AR 2017 | 1617-Q2 | FCO | Amber | 2011-01-01 | 2017-12-01 | 13.4 | 13.7 | 0.3 | 0.022388 | 46 | 46 | 0 | Infrastructure and Construction | 6.9205 | FCO_0001_1112-Q1,1617-Q2 | FCO | Amber | Not new
FCO_0006_1213-Q2 | UKERP | AR 2017 | 1617-Q2 | FCO | Amber | 2011-06-01 | 2015-08-01 | 0 | 0.5 | 0.5 | 0 | 65 | 65 | 0 | Infrastructure and Construction | 4.1699 | FCO_0006_1213-Q2,1617-Q2 | FCO | Amber | Not new
FCO_0008_1415-Q4 | Technology Overhaul | AR 2017 | 1617-Q2 | FCO | Amber | 2015-11-01 | 2018-03-31 | 38 | 29.6 | -8.4 | -0.22105 | 105.4 | 105.4 | 0 | ICT | 2.4137 | FCO_0008_1415-Q4,1617-Q2 | FCO | Amber | Not new
FCO_0009_1516-Q2 | Movement of Personal Effects Contract | AR 2017 | 1617-Q2 | FCO | Amber/Green | 2015-07-06 | 2017-03-31 | 12.5 | 12.5 | 0 | 0 | 62.5 | 62.5 | 0 | Government Transformation and Service Delivery | 1.737 | FCO_0009_1516-Q2,1617-Q2 | FCO | Amber/Green | Not new
HMRC_0012_1415-Q1 | Tax-Free Childcare | AR 2017 | 1617-Q2 | HMRC | Amber | 2013-09-10 | 2018-06-30 | 65.642 | 56.779 | -8.863 | -0.13502 | 356.861 | 356.861 | 0 | Government Transformation and Service Delivery | 4.8055 | HMRC_0012_1415-Q1,1617-Q2 | HMRC | Amber | Not new
HMRC_0013_1415-Q4 | Columbus (formerly Aspire Replacement Programme) | AR 2017 | 1617-Q2 | HMRC | Amber/Green | 2014-01-01 | 2021-12-31 | 894 | 894 | 0 | 0 | 6310 | 6310 | 0 | ICT | 8.0027 | HMRC_0013_1415-Q4,1617-Q2 | HMRC | Amber/Green | Not new
HMRC_0014_1415-Q4 | CUSTOMS DECLARATION SERVICES (CDS) Programme | AR 2017 | 1617-Q2 | HMRC | Amber | 2013-10-16 | 2018-12-31 | 36.51 | 31.43 | -5.08 | -0.13914 | 117.062 | 117.062 | 0 | ICT | 5.211 | HMRC_0014_1415-Q4,1617-Q2 | HMRC | Amber | Not new
HMRC_0015_1617-Q1 | Building Our Future Locations Programme | AR 2017 | 1617-Q2 | HMRC | Amber/Red | 2016-01-05 | 2021-04-05 | 310.2 | 340.7 | 30.5 | 0.098324 | 2099.3 | 2099.3 | 0 | Government Transformation and Service Delivery | 5.2521 | HMRC_0015_1617-Q1,1617-Q2 | HMRC | Amber/Red | Joiner
HMRC_0016_1617-Q2 | Making Tax Digital for Individuals | AR 2017 | 1617-Q2 | HMRC | Amber | 2016-04-01 | 2021-03-31 | 51.5 | 51.5 | 0 | 0 | 205.62 | 205.62 | 0 | Government Transformation and Service Delivery | 5 | HMRC_0016_1617-Q2,1617-Q2 | HMRC | Amber | Joiner
HMRC_0017_1617-Q2 | Making Tax Digital for Business | AR 2017 | 1617-Q2 | HMRC | Amber/Red | 2016-04-01 | 2021-03-31 | 48 | 48 | 0 | 0 | 227 | 227 | 0 | ICT | 5 | HMRC_0017_1617-Q2,1617-Q2 | HMRC | Amber/Red | Joiner
HO_0012_1112-Q3 | Communications Capabilities Development Programme | AR 2017 | 1617-Q2 | HO | Amber/Green | 2010-05-01 | 2020-04-01 | 0 | 0 | 0 | 0 | Exempt |  | 0 | ICT | 9.926 | HO_0012_1112-Q3,1617-Q2 | HO | Amber/Green | Not new
HO_0034_1516-Q2 | Cyclamen Project | AR 2017 | 1617-Q2 | HO | Amber/Red | 2014-04-01 | 2021-04-01 | 0 | 0 | 0 | 0 | Exempt | #VALUE! | 0 | ICT | 7.0055 | HO_0034_1516-Q2,1617-Q2 | HO | Amber/Red | Not new
HO_0011_1112-Q2 | Disclosure and Barring Service (DBS) Programme | AR 2017 | 1617-Q2 | HO | Amber/Red | 2010-12-29 | 2017-12-31 | 113.5 | 154.3 | 40.8 | 0.35947 | 785.7 | 785.7 | 0 | Government Transformation and Service Delivery | 7.011 | HO_0011_1112-Q2,1617-Q2 | HO | Amber/Red | Not new
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2017 | 1617-Q2 | HO | Amber | 2011-06-01 | 2020-12-31 | 89 | 89 | 0 | 0 | 4861.7 | 4861.7 | 0 | Infrastructure and Construction | 9.5918 | HO_0016_1213-Q1,1617-Q2 | HO | Amber | Not new
HO_0029_1314-Q4 | Immigration Platform Technologies (IPT) | AR 2017 | 1617-Q2 | HO | Amber | 2013-04-01 | 2017-03-31 | 41.1 | 80.5 | 39.4 | 0.95864 | 208.8 | 208.8 | 0 | ICT | 4 | HO_0029_1314-Q4,1617-Q2 | HO | Amber | Not new
HO_0030_1415-Q1 | Adelphi Modernisation Programme | AR 2017 | 1617-Q2 | HO | Reset | 2016-09-01 | 2019-06-01 | 18.0286 | 18.0286 | 0 | 0 | 262.8074 | 262.8074 | 0 | ICT | 2.7479 | HO_0030_1415-Q1,1617-Q2 | HO | Reset | Not new
HO_0031_1415-Q1 | Digital Services at the Border | AR 2017 | 1617-Q2 | HO | Amber/Red | 2014-02-12 | 2019-03-31 | 27 | 26.2 | -0.8 | -0.02963 | 341.4 | 341.4 | 0 | ICT | 5.1315 | HO_0031_1415-Q1,1617-Q2 | HO | Amber/Red | Not new
HO_0032_1415-Q1 | Technology Platforms for Tomorrow | AR 2017 | 1617-Q2 | HO | Amber | 2014-02-01 | 2017-10-31 | 47.4 | 47.6 | 0.2 | 0.0042194 | 374.6 | 374.6 | 0 | ICT | 3.7479 | HO_0032_1415-Q1,1617-Q2 | HO | Amber | Not new
HO_0033_1415-Q3 | Home Office Biometrics Programme | AR 2017 | 1617-Q2 | HO | Amber/Green | 2014-04-01 | 2019-12-31 | 108.3 | 108.3 | 0 | 0 | 584.4 | 584.4 | 0 | ICT | 5.7534 | HO_0033_1415-Q3,1617-Q2 | HO | Amber/Green | Not new
HO_0035_1617-Q1 | Smarter Working Programme | AR 2017 | 1617-Q2 | HO | Amber | 2015-10-28 | 2020-03-31 | 41.4 | 38 | -3.4 | -0.082126 | 128.15 | 128.15 | 0 | Government Transformation and Service Delivery | 4.4274 | HO_0035_1617-Q1,1617-Q2 | HO | Amber | Joiner
HO_0036_1617-Q2 | National Law Enforcement Data Programme | AR 2017 | 1617-Q2 | HO | Amber/Red | 2014-04-01 | 2020-03-31 | 54.7 | 54.7 | 0 | 0 | 518.3 | 518.3 | 0 | ICT | 6.0027 | HO_0036_1617-Q2,1617-Q2 | HO | Amber/Red | Joiner
MOD_0017_1112-Q1 | Crowsnest Programme | AR 2017 | 1617-Q2 | MOD | Amber | 2013-03-31 | 2023-06-30 | 53.353 | 53.359 | 0.006 | 0.00011246 | Exempt |  | 0 | Military Capability | 10.2548 | MOD_0017_1112-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0055_1112-Q1 | Type 26 Global Combat Ship Programme | AR 2017 | 1617-Q2 | MOD | Exempt | 2008-07-21 | 2034-12-31 | 293.23 | 292.99 | -0.24 | -0.00081847 | Exempt | #VALUE! | 0 | Military Capability | 26.463 | MOD_0055_1112-Q1,1617-Q2 | MOD | Exempt | Not new
MOD_0001_1112-Q1 | A400M | AR 2017 | 1617-Q2 | MOD | Amber | 2000-05-17 | 2022-03-31 | 274.386 | 292.571 | 18.185 | 0.066275 | 3614.929 | 3614.929 | 0 | Military Capability | 21.8849 | MOD_0001_1112-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0004_1112-Q1 | Airseeker | AR 2017 | 1617-Q2 | MOD | Amber/Green | 2010-03-18 | 2018-04-01 | 91.406 | 102.974 | 11.568 | 0.12656 | 759.839 | 759.839 | 0 | Military Capability | 8.0438 | MOD_0004_1112-Q1,1617-Q2 | MOD | Amber/Green | Not new
MOD_0033_1112-Q1 | MARSHALL | AR 2017 | 1617-Q2 | MOD | Amber/Red | 2006-04-03 | 2020-10-04 | 124.786 | 124.389 | -0.397 | -0.0031814 | 1769.157 | 1769.157 | 0 | Military Capability | 14.5151 | MOD_0033_1112-Q1,1617-Q2 | MOD | Amber/Red | Not new
MOD_0036_1112-Q1 | Maritime Sustainment Programme | AR 2017 | 1617-Q2 | MOD | Amber/Red | 2005-07-25 | 2018-04-30 | 126.837 | 126.837 | 0 | 0 | 596.374 | 596.374 | 0 | Military Capability | 12.7726 | MOD_0036_1112-Q1,1617-Q2 | MOD | Amber/Red | Not new
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2017 | 1617-Q2 | MOD | Exempt | 2008-04-01 | 2025-04-30 | 993.191 | 1026.973 | 33.782 | 0.034014 | 20310.55 | 20310.55 | 0 | Military Capability | 17.0904 | MOD_0038_1112-Q1,1617-Q2 | MOD | Exempt | Not new
MOD_0042_1112-Q1 | Queen Elizabeth Programme | AR 2017 | 1617-Q2 | MOD | Amber | 1998-12-01 | 2023-03-31 | 601.837 | 593.273 | -8.564 | -0.01423 | 7400.075 | 7400.075 | 0 | Military Capability | 24.3452 | MOD_0042_1112-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0047_1112-Q1 | Spearfish Upgrade Programme | AR 2017 | 1617-Q2 | MOD | Amber/Green | 2008-04-01 | 2024-03-31 | 39.947 | 40.017 | 0.07 | 0.0017523 | 416.078 | 416.078 | 0 | Military Capability | 16.0082 | MOD_0047_1112-Q1,1617-Q2 | MOD | Amber/Green | Not new
MOD_0095_1415-Q2 | Cryptographic Enabling Services | AR 2017 | 1617-Q2 | MOD | Exempt |  |  | 0 | 0 | 0 | 0 | Exempt | #VALUE! | 0 | ICT | 0 | MOD_0095_1415-Q2,1617-Q2 | MOD | Exempt | Not new
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2017 | 1617-Q2 | MOD | Amber | 1998-03-01 | 2017-07-03 | 43.159 | 40.77 | -2.389 | -0.055353 | 1116.75 | 1116.75 | 0 | Military Capability | 19.3534 | MOD_0061_1112-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0062_1112-Q1 | Wildcat Programme | AR 2017 | 1617-Q2 | MOD | Amber | 2001-12-01 | 2016-05-31 | 13.164 | 12.67 | -0.494 | -0.037527 | 1609.235 | 1609.235 | 0 | Military Capability | 14.5068 | MOD_0062_1112-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0064_1112-Q2 | Carrier Enabled Power Projection | AR 2017 | 1617-Q2 | MOD | Amber | 2011-01-31 | 2030-12-01 | 1.581 | 1.329 | -0.252 | -0.15939 | 21.801 | 21.801 | 0 | Military Capability | 19.8466 | MOD_0064_1112-Q2,1617-Q2 | MOD | Amber | Not new
MOD_0069_1112-Q2 | Logistics Commodities Services Transformation | AR 2017 | 1617-Q2 | MOD | Amber | 2011-08-01 | 2018-02-01 | 92.614 | 115.271 | 22.657 | 0.24464 | 652.415 | 652.415 | 0 | Military Capability | 6.5096 | MOD_0069_1112-Q2,1617-Q2 | MOD | Amber | Not new
MOD_0070_1112-Q2 | New Employment Model | AR 2017 | 1617-Q2 | MOD | Amber/Green | 2011-05-02 | 2021-10-01 | 95.152 | 92.374 | -2.778 | -0.029195 | 211.079 | 211.079 | 0 | Government Transformation and Service Delivery | 10.4247 | MOD_0070_1112-Q2,1617-Q2 | MOD | Amber/Green | Not new
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2017 | 1617-Q2 | MOD | Amber/Red | 1997-03-17 | 2024-03-31 | 574.91 | 529.824 | -45.086 | -0.078423 | 9869.699 | 9869.699 | 0 | Military Capability | 27.0575 | MOD_0076_1213-Q1,1617-Q2 | MOD | Amber/Red | Not new
MOD_0077_1213-Q1 | Complex Weapons | AR 2017 | 1617-Q2 | MOD | Amber | 2008-03-31 | 2032-04-01 | 729.353 | 719.576 | -9.777 | -0.013405 | 21355.093 | 21355.093 | 0 | Military Capability | 24.0192 | MOD_0077_1213-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0078_1213-Q1 | Core Production Capability | AR 2017 | 1617-Q2 | MOD | Red | 2012-04-01 | 2028-05-15 | 197.356 | 197.203 | -0.153 | -0.00077525 | 1700.07 | 1700.07 | 0 | Military Capability | 16.1315 | MOD_0078_1213-Q1,1617-Q2 | MOD | Red | Not new
MOD_0079_1213-Q1 | Lightning Programme | AR 2017 | 1617-Q2 | MOD | Amber | 2001-10-01 | 2035-03-31 | 808.53 | 888.461 | 79.931 | 0.09886 | 13383.06 | 13383.06 | 0 | Military Capability | 33.5178 | MOD_0079_1213-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0080_1213-Q1 | Successor SSBN | AR 2017 | 1617-Q2 | MOD | Amber/Red | 2011-04-14 |  | 844.756 | 859.845 | 15.089 | 0.017862 | 31614.284 | 31614.284 | 0 | Military Capability | -111.3616 | MOD_0080_1213-Q1,1617-Q2 | MOD | Amber/Red | Not new
MOD_0085_1314-Q2 | Army Basing Programme | AR 2017 | 1617-Q2 | MOD | Amber | 2013-05-22 | 2020-03-31 | 306.851 | 294.504 | -12.347 | -0.040238 | 2009.474 | 2009.474 | 0 | Military Capability | 6.863 | MOD_0085_1314-Q2,1617-Q2 | MOD | Amber | Not new
MOD_0087_1314-Q2 | The Materiel Strategy | AR 2017 | 1617-Q2 | MOD | Amber | 2011-05-02 | 2018-05-01 | 91.206 | 91.206 | 0 | 0 | 379.066 | 379.066 | 0 | Military Capability | 7.0027 | MOD_0087_1314-Q2,1617-Q2 | MOD | Amber | Not new
MOD_0091_1415-Q3 | Armoured Cavalry 2025 | AR 2017 | 1617-Q2 | MOD | Amber | 2014-12-04 | 2025-04-30 | 317.425 | 309.066 | -8.359 | -0.026334 | 6248.626 | 6248.626 | 0 | Military Capability | 10.411 | MOD_0091_1415-Q3,1617-Q2 | MOD | Amber | Not new
MOD_0092_1415-Q3 | Armoured Infantry 2026 | AR 2017 | 1617-Q2 | MOD | Amber/Red | 2014-12-04 | 2026-12-31 | 87.84 | 68.093 | -19.747 | -0.22481 | 1612.709 | 1612.709 | 0 | Military Capability | 12.0822 | MOD_0092_1415-Q3,1617-Q2 | MOD | Amber/Red | Not new
MOD_0093_1415-Q3 | Army Reserve Development Programme | AR 2017 | 1617-Q2 | MOD | Amber/Green | 2014-12-01 | 2017-01-01 | 197.571 | 202.55 | 4.979 | 0.025201 | 1856.758 | 1856.758 | 0 | Military Capability | 2.0877 | MOD_0093_1415-Q3,1617-Q2 | MOD | Amber/Green | Not new
MOD_0094_1415-Q3 | Contracting, Purchasing and Finance | AR 2017 | 1617-Q2 | MOD | Amber/Red | 2011-12-01 | 2018-03-31 | 35.881 | 30.935 | -4.946 | -0.13784 | 146.734 | 146.734 | 0 | Government Transformation and Service Delivery | 6.3342 | MOD_0094_1415-Q3,1617-Q2 | MOD | Amber/Red | Not new
MOD_0100_1516-Q1 | Future Beyond Line Of Sight | AR 2017 | 1617-Q2 | MOD | Amber | 2011-01-01 | 2041-12-31 | 0 | 0 | 0 | 0 | Exempt |  | 0 | ICT | 31.0192 | MOD_0100_1516-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0101_1516-Q1 | New Style of Information Technology (Base) | AR 2017 | 1617-Q2 | MOD | Amber | 2015-04-01 | 2018-03-05 | 0 | 0 | 0 | 0 | Exempt |  | 0 | ICT | 2.9288 | MOD_0101_1516-Q1,1617-Q2 | MOD | Amber | Not new
MOD_0109_1617-Q2 | New Style of Information Technology Deployed | AR 2017 | 1617-Q2 | MOD | Exempt |  |  | 0 | 0 | 0 | 0 | Exempt | #VALUE! | 0 | ICT | 0 | MOD_0109_1617-Q2,1617-Q2 | MOD | Exempt | Joiner
MOD_0104_1617-Q1 | Armour MBT 2025 | AR 2017 | 1617-Q2 | MOD | Amber | 2014-12-04 | 2026-06-01 | 6.373 | 5.573 | -0.8 | -0.12553 | 744.783 | 744.783 | 0 | Military Capability | 11.4986 | MoD_0104_1617-Q1,1617-Q2 | MOD | Amber | Joiner
MOD_0105_1617-Q1 | Land Environment Tactical Communication and Information Systems | AR 2017 | 1617-Q2 | MOD | Amber/Red | 2013-05-01 | 2035-12-01 | 168.545 | 169.373 | 0.828 | 0.0049126 | 11148.485 | 11148.485 | 0 | Military Capability | 22.6 | MoD_0105_1617-Q1,1617-Q2 | MOD | Amber/Red | Joiner
MOD_0106_1617-Q1 | Maritime Patrol Aircraft | AR 2017 | 1617-Q2 | MOD | Amber | 2014-07-08 | 2024-04-01 | 7.373 | 5.573 | -1.8 | -0.24413 | 2132.494 | 2132.494 | 0 | Military Capability | 9.7397 | MoD_0106_1617-Q1,1617-Q2 | MOD | Amber | Joiner
MOD_0107_1617-Q1 | PROTECTOR | AR 2017 | 1617-Q2 | MOD | Amber | 2009-04-30 | 2023-05-31 | 13.774 | 15.274 | 1.5 | 0.1089 | 929.321 | 929.321 | 0 | Military Capability | 14.0932 | MoD_0107_1617-Q1,1617-Q2 | MOD | Amber | Joiner
MOJ_0003_1112-Q1 | Electronic Monitoring | AR 2017 | 1617-Q2 | MOJ | Amber/Red | 2011-05-10 | 2016-11-30 | 62.5 | 88.3 | 25.8 | 0.4128 | 380.6 | 380.6 | 0 | Government Transformation and Service Delivery | 5.5644 | MOJ_0003_1112-Q1,1617-Q2 | MOJ | Amber/Red | Not new
MOJ_0004_1112-Q1 | Future IT Sourcing Programme (FITS) | AR 2017 | 1617-Q2 | MOJ | Amber/Red | 2011-03-01 | 2017-11-30 | 375 | 388.129 | 13.129 | 0.035011 | 2879.249 | 2879.249 | 0 | ICT | 6.7562 | MOJ_0004_1112-Q1,1617-Q2 | MOJ | Amber/Red | Not new
MOJ_0006_1112-Q1 | Integrated Delivery Programme | AR 2017 | 1617-Q2 | MOJ | Amber/Green | 2009-07-01 | 2016-04-30 | 0 | 0 | 0 | 0 | 35.31 | 35.31 | 0 | ICT | 6.8356 | MOJ_0006_1112-Q1,1617-Q2 | MOJ | Amber/Green | Not new
MOJ_0008_1112-Q1 | Shared Services (ISSC2) Evolve | AR 2017 | 1617-Q2 | MOJ | Amber/Red | 2013-09-07 | 2015-11-05 | 76.764 | 75.512 | -1.252 | -0.01631 | 395.1452 | 395.1452 | 0 | ICT | 2.1616 | MOJ_0008_1112-Q1,1617-Q2 | MOJ | Amber/Red | Not new
MOJ_0015_1112-Q2 | NOMS ICTS Services (NIS) Programme (formally part of Quantum Re-compete Project) | AR 2017 | 1617-Q2 | MOJ | Green | 2011-07-18 | 2016-06-30 | 13.4 | 12.08 | -1.32 | -0.098507 | 40.8 | 40.8 | 0 | ICT | 4.9562 | MOJ_0015_1112-Q2,1617-Q2 | MOJ | Green | Not new
MOJ_0021_1314-Q1 | CJS Common Platform | AR 2017 | 1617-Q2 | MOJ | Amber | 2012-11-01 | 2019-03-29 | 92.74 | 73.11 | -19.63 | -0.21167 | 380.89 | 380.89 | 0 | ICT | 6.4082 | MOJ_0021_1314-Q1,1617-Q2 | MOJ | Amber | Not new
MOJ_0023_1314-Q1 | Berwyn Programme | AR 2017 | 1617-Q2 | MOJ | Amber | 2013-01-10 | 2018-05-31 | 104.4 | 122 | 17.6 | 0.16858 | 2252.7 | 2252.7 | 0 | Infrastructure and Construction | 5.389 | MOJ_0023_1314-Q1,1617-Q2 | MOJ | Amber | Not new
MOJ_0027_1314-Q2 | CJS Efficiency Programme Phase 3 | AR 2017 | 1617-Q2 | MOJ | Green | 2013-04-30 | 2016-06-30 | 7.33 | 9.07 | 1.74 | 0.23738 | 84.85 | 84.85 | 0 | ICT | 3.1699 | MOJ_0027_1314-Q2,1617-Q2 | MOJ | Green | Not new
MOJ_0028_1314-Q2 | HMCTS Reform | AR 2017 | 1617-Q2 | MOJ | Amber/Red | 2015-01-05 | 2022-03-31 | 147.2 | 139.19 | -8.01 | -0.054416 | 1638.48 | 1638.48 | 0 | Government Transformation and Service Delivery | 7.2384 | MOJ_0028_1314-Q2,1617-Q2 | MOJ | Amber/Red | Not new
MOJ_0030_1516-Q1 | Secure Training Centre (STC) Retendering | AR 2017 | 1617-Q2 | MOJ | Amber/Red | 2012-11-05 | 2017-05-01 | 10.83 | 10.83 | 0 | 0 | 86.98 | 86.98 | 0 | Government Transformation and Service Delivery | 4.4877 | MOJ_0030_1516-Q1,1617-Q2 | MOJ | Amber/Red | Not new
MOJ_0032_1617-Q2 | MoJ Future FM | AR 2017 | 1617-Q2 | MOJ | Amber | 2016-07-01 | 2018-04-01 | 1.6 | 1.6 | 0 | 0 | 288.8 | 288.8 | 0 | Government Transformation and Service Delivery | 1.7507 | MOJ_0032_1617-Q2,1617-Q2 | MOJ | Amber | Joiner
MOJ_0033_1617-Q2 | Prison Estate Transformation Programme (PETP) | AR 2017 | 1617-Q2 | MOJ | Amber | 2016-04-01 | 2021-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Infrastructure and Construction | 5.7534 | MOJ_0033_1617-Q2,1617-Q2 | MOJ | Amber | Joiner
MOJ_0034_1617-Q2 | NOMS Digital Transformation Programme | AR 2017 | 1617-Q2 | MOJ | Amber | 2016-01-01 | 2021-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Government Transformation and Service Delivery | 5.2493 | MOJ_0034_1617-Q2,1617-Q2 | MOJ | Amber | Joiner
NCA_0001_1415-Q2 | NCA Transformation Programme | AR 2017 | 1617-Q2 | NCA | Amber | 2014-04-01 | 2019-03-31 | 25.5 | 25.5 | 0 | 0 | 306.8 | 306.8 | 0 | Government Transformation and Service Delivery | 5 | NCA_0001_1415-Q2,1617-Q2 | NCA | Amber | Not new
NCA_0002_1617-Q2 | IT Transformation Programme | AR 2017 | 1617-Q2 | NCA | Amber | 2016-04-01 | 2022-07-31 | 14 | 14 | 0 | 0 | 168.6844 | 168.6844 | 0 | ICT | 6.3342 | NCA_0002_1617-Q2,1617-Q2 | NCA | Amber | Joiner
ONS_0002_1112-Q1 | Census Transformation Programme | AR 2017 | 1617-Q2 | ONS | Amber | 2015-01-01 | 2025-03-31 | 36.03 | 36.03 | 0 | 0 | 905.76 | 905.76 | 0 | Government Transformation and Service Delivery | 10.2521 | ONS_0002_1112-Q1,1617-Q2 | ONS | Amber | Not new
BEIS_0001_1617-Q2 | Heat Networks Investment Project | AR 2018 | 1718-Q2 | BEIS | Exempt | 2015-11-25 | 2021-03-31 | 33.67 | 21.6 | -12.07 | -35.85% | 365.98 |  |  | Infrastructure and Construction | 0 | BEIS_0001_1617-Q2,1718 - Q2 |  | Exempt | Not new
BEIS_0002_1718-Q1 | UKRI Implementation Programme | AR 2018 | 1718-Q2 | BEIS | Amber | 2016-01-01 | 2018-10-01 | 9.4 | 9.4 | 0 | 0% | 9.4 |  |  | Government Transformation and Service Delivery | 0 | BEIS_0002_1718-Q1,1718 - Q2 |  | Amber | Joiner
BIS_0014_1415-Q3 | New Polar Research Vessel | AR 2018 | 1718-Q2 | BEIS | Amber/Green | 2014-05-01 | 2022-12-31 | 113 | 111 | -2 | -1.77% | 1403 |  |  | Infrastructure and Construction | 8.674 | BIS_0014_1415-Q3,1718 - Q2 |  | Amber/Green | Not new
BIS_0015_1516-Q1 | Local Land Charges (LLC) Programme | AR 2018 | 1718-Q2 | BEIS | Amber | 2014-03-01 | 2023-11-17 | 25.8 | 13.6 | -12.2 | -47.29% | 193.3 |  |  | ICT | 0 | BIS_0015_1516-Q1,1718 - Q2 |  | Amber | Not new
CO_0011_1415-Q4 | ISSC2 | AR 2018 | 1718-Q2 | CO | Amber | 2012-12-28 | 2021-03-28 | 380.3 | 323 | -57.3 | -15.07% | 2728.5 |  |  | Government Transformation and Service Delivery | 8.2521 | CO_0011_1415-Q4,1718 - Q2 |  | Amber | Not new
CO_0012_1415-Q4 | Commercial Capability Programme | AR 2018 | 1718-Q2 | CO | Amber | 2015-01-01 | 2018-03-31 | 9.2 | 9.2 | 0 | 0% | 20.6 |  |  | Government Transformation and Service Delivery | 0 | CO_0012_1415-Q4,1718 - Q2 |  | Amber | Not new
CO_0013_1516-Q2 | Foxhound Programme | AR 2018 | 1718-Q2 | CO | Amber/Green | 2013-09-01 | 2018-12-31 | 27.6 | 33.05 | 5.45 | 19.75% | 174.3 |  |  | ICT | 0 | CO_0013_1516-Q2,1718 - Q2 |  | Amber/Green | Not new
CO_0014_1516-Q2 | Government Hubs Programme | AR 2018 | 1718-Q2 | CO | Amber | 2015-05-01 | 2025-03-31 | 86.5 | 86.5 | 0 | 0% | 638.87 |  |  | Government Transformation and Service Delivery | 0 | CO_0014_1516-Q2,1718 - Q2 |  | Amber | Not new
CO_0015_1516-Q2 | Gov UK Verify | AR 2018 | 1718-Q2 | CO | Amber | 2012-04-01 | 2020-03-31 | Exempt | Exempt | - | - | Exempt |  |  | ICT | 8.0027 | CO_0015_1516-Q2,1718 - Q2 |  | Exempt | Not new
CO_0016_1516-Q4 | 1617 New Property Model Programme | AR 2018 | 1718-Q2 | CO | Amber/Red | 2015-04-01 | 2021-04-01 | 11.1 | 11.1 | 0 | 0% | 93.93 |  |  | Government Transformation and Service Delivery | 0 | CO_0016_1516-Q4,1718 - Q2 |  | Amber/Red | Not new
CO_0018_1617-Q3 | Common Technology Services | AR 2018 | 1718-Q2 | CO | Amber | 2016-04-01 | 2020-03-31 | 12.2 | 11.7 | -0.5 | -4.098% | 52.6 |  |  | Government Transformation and Service Delivery | 0 | CO_0018_1617-Q3,1718 - Q2 |  | Amber | Joiner
CO_0019_1617-Q4 | Government as a Platform | AR 2018 | 1718-Q2 | CO | Amber | 2015-12-31 | 2021-03-31 | 23 | 22 | -1 | -4.348% | 90 |  |  | ICT | 0 | CO_0019_1617-Q4,1718 - Q2 |  | Amber | Joiner
DCMS_0001_1112-Q1 | Broadband Delivery Programme | AR 2018 | 1718-Q2 | DCMS | Amber/Green | 2010-12-06 | 2020-12-31 | 236.1 | 187.6 | -48.5 | -20.54% | 2439.21 |  |  | Infrastructure and Construction | 10.0767 | DCMS_0001_1112-Q1,1718 - Q2 |  | Amber/Green | Not new
DCMS_0008_1516-Q4 | Blythe House Programme | AR 2018 | 1718-Q2 | DCMS | Amber | 2015-11-25 | 2023-03-31 | 62.6 | 68.41 | 5.81 | 9.281% | 338 |  |  | Infrastructure and Construction | 0 | DCMS_0008_1516-Q4,1718 - Q2 |  | Amber | Not new
DCMS_0009_1516-Q4 | 700 MHz Clearance Programme | AR 2018 | 1718-Q2 | DCMS | Amber/Green | 2016-01-13 | 2022-01-01 | 103.7 | 91.7 | -12 | -11.57% | 594.92 |  |  | Infrastructure and Construction | 0 | DCMS_0009_1516-Q4,1718 - Q2 |  | Amber/Green | Not new
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2018 | 1718-Q2 | BEIS | Amber/Red | 2008-06-30 | 2040-12-31 | 32.24 | 32.25 | 0.01 | 0.03102% | 12131.5 |  |  | Infrastructure and Construction | 32.526 | DECC_0005_1112-Q1,1718 - Q2 |  | Amber/Red | Not new
DECC_0010_1112-Q1 | Smart Metering Implementation Programme | AR 2018 | 1718-Q2 | BEIS | Amber | 2009-12-02 | 2020-12-31 | 736.51 | 737.76 | 1.25 | 0.1697% | 17215.78 |  |  | Infrastructure and Construction | 11.0877 | DECC_0010_1112-Q1,1718 - Q2 |  | Amber | Not new
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | AR 2018 | 1718-Q2 | BEIS | Amber | 2012-04-03 | 2015-08-31 | 572 | 555 | -17 | -2.972% | 3081 |  |  | Infrastructure and Construction | 3.411 | DECC_0013_1213-Q1,1718 - Q2 |  | Amber | Not new
DECC_0017_1516-Q1 | Sellafield Model Change (SMC) | AR 2018 | 1718-Q2 | BEIS | Amber/Green | 2015-01-13 | 2017-05-24 | 2341.7 | 2260.7 | -81 | -3.459% | 30011.2 |  |  | Government Transformation and Service Delivery | 2.3616 | DECC_0017_1516-Q1,1718 - Q2 |  | Amber/Green | Not new
DEFRA_0006_1516-Q1 | DEFRA UNITY PROGRAMME | AR 2018 | 1718-Q2 | DEFRA | Amber | 2014-11-01 | 2018-10-31 | 197.6 | 162.6 | -35 | -17.71% | 1048.4 |  |  | ICT | 4 | DEFRA_0006_1516-Q1,1718 - Q2 |  | Amber | Not new
DFE_0004_1415-Q2 | Priority School Building Programme 1 | AR 2018 | 1718-Q2 | DfE | Amber/Green | 2011-07-19 | 2021-09-19 | 381.85 | 319.29 | -62.56 | -16.38% | 2313.79 |  |  | Infrastructure and Construction | 10.1781 | DFE_0004_1415-Q2,1718 - Q2 |  | Amber/Green | Joiner
DFE_0005_1415-Q2 | PSBP Private Finance | AR 2018 | 1718-Q2 | DfE | Green | 2011-07-19 | 2043-07-01 | 186.5 | 190.1 | 3.6 | 1.93% | 2652 |  |  | Infrastructure and Construction | 31.9726 | DFE_0005_1415-Q2,1718 - Q2 |  | Green | Not new
DFE_0006_1415-Q3 | Priority School Building Programme 2 | AR 2018 | 1718-Q2 | DfE | Amber/Red | 2014-05-01 | 2022-12-31 | 402.25 | 100.91 | -301.34 | -74.91% | 2089.31 |  |  | Infrastructure and Construction | 8.674 | DFE_0006_1415-Q3,1718 - Q2 |  | Amber/Red | Joiner
DFE_0007_1617-Q1 | 30 Hrs Free Childcare Project | AR 2018 | 1718-Q2 | DfE | Amber | 2015-05-11 | 2018-09-30 | 409.1 | 436.903 | 27.803 | 6.796% | 1920.72 |  |  | Government Transformation and Service Delivery | 3.3918 | DFE_0007_1617-Q1,1718 - Q2 |  | Amber | Not new
DfE_0009_1617-Q2 | Apprenticeships Reform Programme | AR 2018 | 1718-Q2 | DfE | Amber | 2015-05-08 | 2021-04-01 | 2036.1 | 1684.1 | -352 | -17.29% | 11347.5 |  |  | Government Transformation and Service Delivery | 5.9041 | DfE_0009_1617-Q2,1718 - Q2 |  | Amber | Not new
DFID_0001_1112-Q1 | St Helena Airport | AR 2018 | 1718-Q2 | DFID | Amber/Green | 2005-03-15 | 2026-08-31 | 6 | 6.5 | 0.5 | 8.333% | 445.12 |  |  | Infrastructure and Construction | 0 | DFID_0001_1112-Q1,1718 - Q2 |  | Amber/Green | Not new
DFT_0001_1112-Q1 | Crossrail Programme | AR 2018 | 1718-Q2 | DfT | Amber | 22/07/2008 | 31/12/2019 | 972.02 | 1857.1 | 885.08 | 91.06% | 14768.87 |  |  | Infrastructure and Construction | 11.4493 | DFT_0001_1112-Q1,1718 - Q2 |  | Amber | Not new
DFT_0004_1112-Q1 | High Speed Rail Programme (HS2) | AR 2018 | 1718-Q2 | DfT | Amber/Red | 2011-02-28 | 2033-12-31 | 1845.8 | 1845.8 | 0 | 0% | 55700 |  |  | Infrastructure and Construction | 22.8548 | DFT_0004_1112-Q1,1718 - Q2 |  | Amber/Red | Not new
DFT_0005_1112-Q1 | Intercity Express Programme | AR 2018 | 1718-Q2 | DfT | Red | 2005-06-01 | 2020-02-06 | 224.9 | 242.8 | 17.9 | 7.959% | 6679.25 |  |  | Infrastructure and Construction | 14.6932 | DFT_0005_1112-Q1,1718 - Q2 |  | Red | Not new
DFT_0014_1112-Q1 | Search and Rescue Helicopters | AR 2018 | 1718-Q2 | DfT | Green | 2011-02-08 | 2017-09-08 | 224.3 | 204.4 | -19.9 | -8.872% | 2157.4 |  |  | Infrastructure and Construction | 6.5863 | DFT_0014_1112-Q1,1718 - Q2 |  | Green | Not new
DFT_0016_1112-Q1 | Thameslink | AR 2018 | 1718-Q2 | DfT | Amber | 2005-07-01 | 2026-12-31 | 22 | 22 | 0 | 0% | 7210 |  |  | Infrastructure and Construction | 21.5151 | DFT_0016_1112-Q1,1718 - Q2 |  | Amber | Not new
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | AR 2018 | 1718-Q2 | DfT | Amber | 2012-09-01 | 30/09/2021 | 414.9 | 363.9 | -51 | -12.29% | 1423.8 |  |  | Infrastructure and Construction | 9.0849 | DFT_0020_1314-Q2,1718 - Q2 |  | Amber | Not new
DFT_0021_1314-Q3 | Rail Franchising Programme | AR 2018 | 1718-Q2 | DfT | Amber/Red | 2013-03-26 | 2019-12-01 | 8.7 | 8.7 | 0 | 0% | 35.3 |  |  | Government Transformation and Service Delivery | 6.6877 | DFT_0021_1314-Q3,1718 - Q2 |  | Amber/Red | Not new
DfT_0022_1415-Q4 | Lower Thames Crossing Feasibility | AR 2018 | 1718-Q2 | DfT | Amber/Red | 2014-05-30 | 2028-07-31 | 49.9 | 49.9 | 0 | 0% | 4648.8 |  |  | Infrastructure and Construction | 14.1808 | DfT_0022_1415-Q4,1718 - Q2 |  | Amber/Red | Not new
DfT_0023_1516-Q3 | Airport Capacity Programme | AR 2018 | 1718-Q2 | DfT | Amber | 2015-07-01 | 2029-12-31 | 14.7 | 8.8 | -5.9 | -40.14% | 22747 |  |  | Infrastructure and Construction | 14.5123 | DfT_0023_1516-Q3,1718 - Q2 |  | Amber | Not new
DFT_0024_1516-Q4 | A303 Amesbury to Berwick Down | AR 2018 | 1718-Q2 | DfT | Amber | 2014-12-01 | 2026-06-01 | 15.6 | 15.6 | 0 | 0% | 1901.9 |  |  | Infrastructure and Construction | 11.5068 | DFT_0024_1516-Q4,1718 - Q2 |  | Amber | Not new
DFT_0025_1617-Q1 | East West Rail | AR 2018 | 1718-Q2 | DfT | Amber/Red | 2012-10-31 | 2024-03-31 | 14.9 | 58.6 | 43.7 | 293.3% | 1465.8 |  |  | Infrastructure and Construction | 11.4219 | DFT_0025_1617-Q1,1718 - Q2 |  | Amber/Red | Not new
DFT_0026_1617-Q1 | Great Western Route Modernisation (GWRM) including electrification | AR 2018 | 1718-Q2 | DfT | Amber/Red | 2011-12-01 | 31/12/2024 | 876.9 | 789.9 | -87 | -9.921% | 5507 |  |  | Infrastructure and Construction | 13.0932 | DFT_0026_1617-Q1,1718 - Q2 |  | Amber/Red | Not new
DFT_0027_1617-Q1 | Midland Main Line Programme | AR 2018 | 1718-Q2 | DfT | Amber | 2011-01-01 | 2024-12-31 | 271.6 | 270.7 | -0.9 | -0.3314% | 1521.6 |  |  | Infrastructure and Construction | 14.0082 | DFT_0027_1617-Q1,1718 - Q2 |  | Amber | Not new
DFT_0028_1617-Q1 | North of England Programme | AR 2018 | 1718-Q2 | DfT | Amber/Red | 2009-07-23 | 2022-12-31 | 494.3 | 629.9 | 135.6 | 27.43% | 5114.9 |  |  | Infrastructure and Construction | 13.4493 | DFT_0028_1617-Q1,1718 - Q2 |  | Amber/Red | Not new
DFT_0029_1617-Q1 | South West Route Capacity | AR 2018 | 1718-Q2 | DfT | Amber/Red | 16/07/2012 | 2019-12-31 | 193.72 | 226.32 | 32.6 | 16.83% | 734.7 |  |  | Infrastructure and Construction | 7.463 | DFT_0029_1617-Q1,1718 - Q2 |  | Amber/Red | Not new
DFT_0030_1617-Q2 | M20 Lorry Area | AR 2018 | 1718-Q2 | DfT | Red | 25/11/2015 | 20/01/2018 | 153.7 | 5.6 | -148.1 | -96.36% | 246.5 |  |  | Infrastructure and Construction | 2.1562 | DFT_0030_1617-Q2,1718 - Q2 |  | Red | Not new
DH_0015_1112-Q1 | CSC Local Service Provider (LSP) Delivery Programme | AR 2018 | 1718-Q2 | DH | Amber/Green | 2003-06-23 | 2018-03-31 | 69.4435 | 78.6293 | 9.1858 | 13.23% | 2109.8515 |  |  | Government Transformation and Service Delivery | 14.7808 | DH_0015_1112-Q1,1718 - Q2 |  | Amber/Green | Not new
DH_0017_1112-Q1 | PHE Science Hub | AR 2018 | 1718-Q2 | DH | Amber | 2013-06-28 | 2025-06-30 | 157.514 | 185.687 | 28.173 | 17.89% | 11621.878 |  |  | Infrastructure and Construction | 12.0137 | DH_0017_1112-Q1,1718 - Q2 |  | Amber | Not new
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | AR 2018 | 1718-Q2 | DH | Amber/Red | 2012-01-01 | 2018-05-30 | 66.64 | 62.8 | -3.84 | -5.762% | 1247.24 |  |  | Government Transformation and Service Delivery | 6.4137 | DH_0031_1314-Q1,1718 - Q2 |  | Amber/Red | Not new
DH_0039_1314-Q2 | NHS e-Referral Service | AR 2018 | 1718-Q2 | DH | Amber/Red | 2012-03-29 | 2018-03-31 | 28.47 | 22.62 | -5.85 | -20.55% | 131.17 |  |  | ICT | 6.0082 | DH_0039_1314-Q2,1718 - Q2 |  | Amber/Red | Not new
DH_0040_1314-Q2 | NHSmail 2 | AR 2018 | 1718-Q2 | DH | Amber/Green | 2012-03-29 | 2021-02-26 | 18.39 | 23.7998 | 5.4098 | 29.42% | 133.05 |  |  | ICT | 8.9205 | DH_0040_1314-Q2,1718 - Q2 |  | Amber/Green | Not new
DH_0041_1314-Q2 | Health & Social Care Network | AR 2018 | 1718-Q2 | DH | Amber | 2012-03-29 | 2021-03-31 | 155.05 | 96.12 | -58.93 | -38.01% | 699.46 |  |  | ICT | 9.011 | DH_0041_1314-Q2,1718 - Q2 |  | Amber | Not new
DH_0043_1314-Q3 | NHS Pension Re-let | AR 2018 | 1718-Q2 | DH | Amber | 2013-07-05 | 2017-07-21 | 36.4 | 36.4 | 0 | 0% | 274.24 |  |  | Government Transformation and Service Delivery | 4.0466 | DH_0043_1314-Q3,1718 - Q2 |  | Amber | Not new
DH_0046_1415-Q1 | Medical Examiners Programme | AR 2018 | 1718-Q2 | DH | Amber/Red | 2007-07-24 | 2020-09-30 | 0.78 | 0.8 | 0.02 | 2.564% | 43.06 |  |  | Government Transformation and Service Delivery | 13.1973 | DH_0046_1415-Q1,1718 - Q2 |  | Amber/Red | Not new
DH_0048_1415-Q1 | 100000 Genomes Project | AR 2018 | 1718-Q2 | DH | Amber | 2013-04-10 | 2018-12-31 | 77.8 | 77.8 | 0 | 0% | 392.9 |  |  | Government Transformation and Service Delivery | 5.7288 | DH_0048_1415-Q1,1718 - Q2 |  | Amber | Not new
DH_0056_1415-Q3 | Visitor and Migrant NHS Cost Recovery Programme | AR 2018 | 1718-Q2 | DH | Amber/Red | 2013-09-01 | 2019-03-31 | 6.23 | 6.18 | -0.05 | -0.8026% | 25.53 |  |  | Government Transformation and Service Delivery | 5.5808 | DH_0056_1415-Q3,1718 - Q2 |  | Amber/Red | Not new
DH_0058_1516-Q4 | National Data Services Development Programme | AR 2018 | 1718-Q2 | DH | Amber/Green | 2015-02-23 | 2020-03-31 | 19.62 | 10.6 | -9.02 | -45.97% | 79.39 |  |  | ICT | 5.1041 | DH_0058_1516-Q4,1718 - Q2 |  | Amber/Green | Not new
DH_0059_1617-Q1 | Procurement Transformation Programme | AR 2018 | 1718-Q2 | DH | Amber | 2015-03-31 | 2019-03-31 | 29.7642 | 26.3417 | -3.4225 | -11.5% | 134.152 |  |  | Government Transformation and Service Delivery | 4.0027 | DH_0059_1617-Q1,1718 - Q2 |  | Amber | Not new
DH_0060_1617-Q1 | NHS UK | AR 2018 | 1718-Q2 | DH | Amber | 2016-04-01 | 2020-12-31 | 12 | 12 | 0 | 0% | 79.8 |  |  | Government Transformation and Service Delivery | 4.7534 | DH_0060_1617-Q1,1718 - Q2 |  | Amber | Not new
DH_0061_1617-Q3 | IT Infrastructure Sourcing Programme | AR 2018 | 1718-Q2 | DH | Amber/Red | 2013-12-01 | 2019-06-30 | 20.8 | 15.9 | -4.9 | -23.56% | 126.71 |  |  | ICT | 5.5808 | DH_0061_1617-Q3,1718 - Q2 |  | Amber/Red | Joiner
DWP_0005_1112-Q1 | Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme) | AR 2018 | 1718-Q2 | DWP | Amber/Green | 2007-05-01 | 2019-11-30 | 103.08 | 70.98 | -32.1 | -31.14% | 1249 |  |  | Government Transformation and Service Delivery | 12.5918 | DWP_0005_1112-Q1,1718 - Q2 |  | Amber/Green | Not new
DWP_0009_1112-Q1 | Universal Credit Programme | AR 2018 | 1718-Q2 | DWP | Amber | 2011-11-17 | 2022-06-30 | 853.4196 | 683.0811 | -170.3386 | -19.96% | 13573.7235 |  |  | Government Transformation and Service Delivery | 10.6247 | DWP_0009_1112-Q1,1718 - Q2 |  | Amber | Not new
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | AR 2018 | 1718-Q2 | DWP | Amber | 2012-04-02 | 2021-03-31 | 87 | 89.7929 | 2.7929 | 3.21% | 786.5 |  |  | Government Transformation and Service Delivery | 9 | DWP_0016_1213-Q2,1718 - Q2 |  | Amber | Not new
DWP_0024_1516-Q3 | DWP People and Locations Programme | AR 2018 | 1718-Q2 | DWP | Amber/Red | 2015-11-19 | 2018-04-27 | 329.8 | 230.9 | -98.9 | -29.99% | 5903.78 |  |  | Government Transformation and Service Delivery | 2.4384 | DWP_0024_1516-Q3,1718 - Q2 |  | Amber/Red | Not new
DWP_0027_1617-Q2 | Work and Health Programme | AR 2018 | 1718-Q2 | DWP | Amber | 2015-12-01 | 2018-03-31 | 26.22 | 26.22 | 0 | 0% | 532.7 |  |  | Government Transformation and Service Delivery | 2.3315 | DWP_0027_1617-Q2,1718 - Q2 |  | Amber | Not new
FCO_0008_1415-Q4 | Technology Overhaul | AR 2018 | 1718-Q2 | FCO | Amber/Green | 2015-11-01 | 2018-12-31 | 51.7 | 58 | 6.3 | 12.19% | 120 |  |  | ICT | 3.1671 | FCO_0008_1415-Q4,1718 - Q2 |  | Amber/Green | Not new
FCO_0010_1617-Q3 | Echo 2 Programme | AR 2018 | 1718-Q2 | FCO | Amber/Red | 2015-09-01 | 2020-03-31 | 2.33 | 2.4 | 0.07 | 3.004% | 171.4 |  |  | ICT | 4.5836 | FCO_0010_1617-Q3,1718 - Q2 |  | Amber/Red | Joiner
HMRC_0012_1415-Q1 | Tax-Free Childcare | AR 2018 | 1718-Q2 | HMRC | Amber/Red | 2013-09-10 | 2018-09-30 | 78.294 | 68.657 | -9.637 | -12.31% | 356.861 |  |  | Government Transformation and Service Delivery | 5.0575 | HMRC_0012_1415-Q1,1718 - Q2 |  | Amber/Red | Not new
HMRC_0013_1415-Q4 | Columbus (formerly Aspire Replacement Programme) | AR 2018 | 1718-Q2 | HMRC | Amber/Green | 2014-01-01 | 2021-12-31 | 266 | 70.3 | -195.7 | -73.57% | 694 |  |  | ICT | 8.0027 | HMRC_0013_1415-Q4,1718 - Q2 |  | Amber/Green | Not new
HMRC_0014_1415-Q4 | CUSTOMS DECLARATION SERVICES (CDS) Programme | AR 2018 | 1718-Q2 | HMRC | Amber | 2013-10-16 | 2018-12-31 | 35.7 | 36.42 | 0.72 | 2.017% | 133.22 |  |  | ICT | 5.211 | HMRC_0014_1415-Q4,1718 - Q2 |  | Amber | Not new
HMRC_0015_1617-Q1 | Building Our Future Locations Programme | AR 2018 | 1718-Q2 | HMRC | Amber | 2016-01-05 | 2026-03-31 | 310.8 | 316.5 | 5.7 | 1.834% | 2835.8 |  |  | Government Transformation and Service Delivery | 10.2411 | HMRC_0015_1617-Q1,1718 - Q2 |  | Amber | Not new
HMRC_0016_1617-Q2 | Making Tax Digital for Individuals | AR 2018 | 1718-Q2 | HMRC | Amber | 2016-04-01 | 2021-03-31 | 62.3 | 41.6 | -20.7 | -33.23% | 205.62 |  |  | Government Transformation and Service Delivery | 5 | HMRC_0016_1617-Q2,1718 - Q2 |  | Amber | Not new
HMRC_0017_1617-Q2 | Making Tax Digital for Business | AR 2018 | 1718-Q2 | HMRC | Amber | 2016-04-01 | 2021-03-31 | 76.83 | 49.7 | -27.13 | -35.31% | 234.46 |  |  | ICT | 5 | HMRC_0017_1617-Q2,1718 - Q2 |  | Amber | Not new
HMRC_0018_1617-Q3 | Compliance For The Future Programme | AR 2018 | 1718-Q2 | HMRC | Amber | 2016-04-01 | 2021-03-31 | 22.7 | 22.3 | -0.4 | -1.762% | 188.25 |  |  | Government Transformation and Service Delivery | 5 | HMRC_0018_1617-Q3,1718 - Q2 |  | Amber | Joiner
HO_0011_1112-Q2 | Disclosure and Barring Service (DBS) Programme | AR 2018 | 1718-Q2 | HO | Amber/Red | 2010-12-29 | 2018-03-31 | 113.5 | 156.8 | 43.3 | 38.15% | 785.7 |  |  | Government Transformation and Service Delivery | 7.2575 | HO_0011_1112-Q2,1718 - Q2 |  | Amber/Red | Not new
HO_0012_1112-Q3 | Communications Capabilities Development Programme | AR 2018 | 1718-Q2 | HO | Amber/Green | 2010-05-01 | 2020-04-01 | Exempt | Exempt | - | - | Exempt |  |  | ICT | 9.926 | HO_0012_1112-Q3,1718 - Q2 |  | Exempt | Not new
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2018 | 1718-Q2 | HO | Red | 2011-06-01 | 2020-12-31 | 712.4653 | 712.4653 | 0 | 0% | 5058.6323 |  |  | Infrastructure and Construction | 9.5918 | HO_0016_1213-Q1,1718 - Q2 |  | Red | Not new
HO_0029_1314-Q4 | Immigration Platform Technologies (IPT) | AR 2018 | 1718-Q2 | HO | Amber | 2013-04-01 | 2019-03-31 | 43.8 | 43.8 | 0 | 0% | 252.5 |  |  | ICT | 6 | HO_0029_1314-Q4,1718 - Q2 |  | Amber | Not new
HO_0030_1415-Q1 | Metis Programme | AR 2018 | 1718-Q2 | HO | Amber | 2016-09-01 | 2019-06-01 | 49.8 | 49.8 | 0 | 0% | 290.56 |  |  | ICT | 2.7479 | HO_0030_1415-Q1,1718 - Q2 |  | Amber | Not new
HO_0031_1415-Q1 | Digital Services at the Border | AR 2018 | 1718-Q2 | HO | Amber/Red | 2014-02-12 | 2019-03-31 | 44 | 44 | 0 | 0% | 340.9 |  |  | ICT | 5.1315 | HO_0031_1415-Q1,1718 - Q2 |  | Amber/Red | Not new
HO_0032_1415-Q1 | Technology Platforms for Tomorrow | AR 2018 | 1718-Q2 | HO | Amber | 2014-02-01 | 2017-10-31 | 55.4 | 96.5 | 41.1 | 74.19% | 374.6 |  |  | ICT | 3.7479 | HO_0032_1415-Q1,1718 - Q2 |  | Amber | Not new
HO_0033_1415-Q3 | Home Office Biometrics Programme | AR 2018 | 1718-Q2 | HO | Amber/Green | 2014-04-01 | 2020-03-31 | 90.9 | 90.9 | 0 | 0% | 667.4 |  |  | ICT | 6.0027 | HO_0033_1415-Q3,1718 - Q2 |  | Amber/Green | Not new
HO_0034_1516-Q2 | Cyclamen Project | AR 2018 | 1718-Q2 | HO | Amber | 2014-04-01 | 2021-04-01 | Exempt | Exempt | - | - | Exempt |  |  | Government Transformation and Service Delivery | 7.0055 | HO_0034_1516-Q2,1718 - Q2 |  | Exempt | Not new
HO_0035_1617-Q1 | Smarter Working Programme | AR 2018 | 1718-Q2 | HO | Amber | 2015-10-28 | 2020-03-31 | 43.1 | 45.4 | 2.3 | 5.336% | 144.5 |  |  | Government Transformation and Service Delivery | 4.4274 | HO_0035_1617-Q1,1718 - Q2 |  | Amber | Not new
HO_0036_1617-Q2 | National Law Enforcement Data Programme | AR 2018 | 1718-Q2 | HO | Amber | 2014-04-01 | 2020-03-31 | 60.8 | 73 | 12.2 | 20.07% | 469.4 |  |  | ICT | 6.0027 | HO_0036_1617-Q2,1718 - Q2 |  | Amber | Not new
HO_0037_1718-Q1 | Asylum Accommodation and Support Transformation (AAST) | AR 2018 | 1718-Q2 | HO | Amber | 2016-08-29 | 2019-09-02 | 2.93 | 2.54 | -0.39 | -13.31% | 7.51 |  |  | Government Transformation and Service Delivery | 3.011 | HO_0037_1718-Q1,1718 - Q2 |  | Amber | Joiner
MOD_0001_1112-Q1 | A400M | AR 2018 | 1718-Q2 | MOD | Amber | 2000-05-17 | 2023-03-31 | 173.39 | 123.76 | -49.63 | -28.62% | 3519.16 |  |  | Military Capability | 22.8849 | MOD_0001_1112-Q1,1718 - Q2 |  | Amber | Not new
MOD_0017_1112-Q1 | Crowsnest Programme | AR 2018 | 1718-Q2 | MOD | Amber | 2013-03-31 | 2023-06-30 | 65.83 | 65.05 | -0.78 | -1.185% | Exempt |  |  | Military Capability | 10.2548 | MOD_0017_1112-Q1,1718 - Q2 |  | Exempt | Not new
MOD_0033_1112-Q1 | MARSHALL | AR 2018 | 1718-Q2 | MOD | Red | 2006-04-03 | 2020-10-04 | 114.04 | 102.52 | -11.52 | -10.1% | 1854.82 |  |  | Military Capability | 14.5151 | MOD_0033_1112-Q1,1718 - Q2 |  | Red | Not new
MOD_0036_1112-Q1 | Maritime Sustainment Programme | AR 2018 | 1718-Q2 | MOD | Amber/Green | 2005-07-25 | 2019-02-28 | 46.82 | 68.19 | 21.37 | 45.64% | 596.38 |  |  | Military Capability | 13.6055 | MOD_0036_1112-Q1,1718 - Q2 |  | Amber/Green | Not new
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2018 | 1718-Q2 | MOD | Exempt | 2008-04-01 | 2025-04-30 | 1013.69 | 1024.53 | 10.84 | 1.069% | 19894.38 |  |  | Military Capability | 17.0904 | MOD_0038_1112-Q1,1718 - Q2 |  | Exempt | Not new
MOD_0042_1112-Q1 | Queen Elizabeth Programme | AR 2018 | 1718-Q2 | MOD | Amber | 1998-12-01 | 2023-03-31 | 401.08 | 402.83 | 1.75 | 0.4363% | 6705.64 |  |  | Military Capability | 24.3452 | MOD_0042_1112-Q1,1718 - Q2 |  | Amber | Not new
MOD_0047_1112-Q1 | Spearfish Upgrade Programme | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2008-04-01 | 2024-03-31 | 41.05 | 39.45 | -1.6 | -3.898% | 416.61 |  |  | Military Capability | 16.0082 | MOD_0047_1112-Q1,1718 - Q2 |  | Amber/Red | Not new
MOD_0055_1112-Q1 | Type 26 Global Combat Ship Programme | AR 2018 | 1718-Q2 | MOD | Amber/Green | 2008-07-21 | 2035-05-01 | 392.94 | 382.04 | -10.9 | -2.774% | Exempt |  |  | Military Capability | 26.7945 | MOD_0055_1112-Q1,1718 - Q2 |  | Exempt | Not new
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2018 | 1718-Q2 | MOD | Amber | 1998-03-01 | 2017-07-03 | 0.98 | 2.01 | 1.03 | 105.1% | 1117.73 |  |  | Military Capability | 19.3534 | MOD_0061_1112-Q1,1718 - Q2 |  | Amber | Not new
MOD_0062_1112-Q1 | Wildcat Programme | AR 2018 | 1718-Q2 | MOD | Amber/Green | 2001-12-01 | 2016-05-31 | 6.22 | 9.16 | 2.94 | 47.27% | 1607.27 |  |  | Military Capability | 14.5068 | MOD_0062_1112-Q1,1718 - Q2 |  | Amber/Green | Not new
MOD_0064_1112-Q2 | Carrier Enabled Power Projection | AR 2018 | 1718-Q2 | MOD | Amber | 2011-01-31 | 2030-12-01 | 1.77 | 1.75 | -0.02 | -1.13% | 21.58 |  |  | Military Capability | 19.8466 | MOD_0064_1112-Q2,1718 - Q2 |  | Amber | Not new
MOD_0069_1112-Q2 | Logistics Commodities Services Transformation | AR 2018 | 1718-Q2 | MOD | Amber/Green | 2011-08-01 | 2018-02-01 | 62.28 | 61.06 | -1.22 | -1.959% | 640.44 |  |  | Military Capability | 6.5096 | MOD_0069_1112-Q2,1718 - Q2 |  | Amber/Green | Not new
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2018 | 1718-Q2 | MOD | Red | 1997-03-17 | 2024-03-31 | 541.08 | 562.62 | 21.54 | 3.981% | 9941.96 |  |  | Military Capability | 27.0575 | MOD_0076_1213-Q1,1718 - Q2 |  | Red | Not new
MOD_0077_1213-Q1 | Complex Weapons | AR 2018 | 1718-Q2 | MOD | Amber | 2008-03-31 | 2032-04-01 | 736.16 | 704.43 | -31.73 | -4.31% | 22179.52 |  |  | Military Capability | 24.0192 | MOD_0077_1213-Q1,1718 - Q2 |  | Amber | Not new
MOD_0078_1213-Q1 | Core Production Capability | AR 2018 | 1718-Q2 | MOD | Red | 2012-04-01 | 2028-04-30 | 182.96 | 187.13 | 4.17 | 2.279% | 1585.1 |  |  | Military Capability | 16.0904 | MOD_0078_1213-Q1,1718 - Q2 |  | Red | Not new
MOD_0079_1213-Q1 | Lightning Programme | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2001-10-01 | 2035-03-31 | 935.45 | 903.35 | -32.1 | -3.432% | 10109.38 |  |  | Military Capability | 33.5178 | MOD_0079_1213-Q1,1718 - Q2 |  | Amber/Red | Not new
MOD_0080_1213-Q1 | DREADNOUGHT | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2011-04-14 | Exempt | 1004.66 | 1249.39 | 244.73 | 24.36% | 31497.93 |  |  | Military Capability | 0 | MOD_0080_1213-Q1,1718 - Q2 |  | Exempt | Not new
MOD_0085_1314-Q2 | Army Basing Programme | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2013-05-22 | 2022-11-28 | 417.34 | 431.07 | 13.73 | 3.29% | 2001.57 |  |  | Military Capability | 9.526 | MOD_0085_1314-Q2,1718 - Q2 |  | Amber/Red | Not new
MOD_0087_1314-Q2 | The Materiel Strategy | AR 2018 | 1718-Q2 | MOD | Amber/Green | 2011-05-02 | 2018-05-16 | 79.41 | 78.95 | -0.46 | -0.5793% | 379.06 |  |  | Government Transformation and Service Delivery | 7.0438 | MOD_0087_1314-Q2,1718 - Q2 |  | Amber/Green | Not new
MOD_0091_1415-Q3 | Armoured Cavalry 2025 | AR 2018 | 1718-Q2 | MOD | Amber | 2014-01-22 | 2025-04-30 | 512 | 491.41 | -20.59 | -4.021% | 6258.19 |  |  | Military Capability | 11.2767 | MOD_0091_1415-Q3,1718 - Q2 |  | Amber | Not new
MOD_0092_1415-Q3 | Armoured Infantry 2026 | AR 2018 | 1718-Q2 | MOD | Red | 2014-12-04 | 2026-12-31 | 80.95 | 64.8 | -16.15 | -19.95% | Exempt |  |  | Military Capability | 12.0822 | MOD_0092_1415-Q3,1718 - Q2 |  | Red | Not new
MOD_0094_1415-Q3 | Contracting, Purchasing and Finance | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2011-12-01 | 2018-03-31 | 13.5 | 11.2 | -2.3 | -17.04% | 146.74 |  |  | Government Transformation and Service Delivery | 6.3342 | MOD_0094_1415-Q3,1718 - Q2 |  | Amber/Red | Not new
MOD_0100_1516-Q1 | Future Beyond Line Of Sight | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2011-01-01 | 2041-12-31 | Exempt | Exempt | - | - | Exempt |  |  | ICT | 31.0192 | MOD_0100_1516-Q1,1718 - Q2 |  | Exempt | Not new
MOD_0101_1516-Q1 | New Style of Information Technology (Base) | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2015-04-01 | 2018-03-05 | Exempt | Exempt | - | - | Exempt |  |  | ICT | 2.9288 | MOD_0101_1516-Q1,1718 - Q2 |  | Exempt | Not new
MOD_0104_1617-Q1 | Armour MBT 2025 | AR 2018 | 1718-Q2 | MOD | Amber | 2014-12-04 | 2026-06-01 | 26.51 | 26.02 | -0.49 | -1.848% | Exempt |  |  | Military Capability | 11.4986 | MOD_0104_1617-Q1,1718 - Q2 |  | Amber | Not new
MOD_0105_1617-Q1 | Land Environment Tactical Communication and Information Systems | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2013-05-01 | 2035-12-31 | 279.49 | 258.44 | -21.05 | -7.532% | 11063.27 |  |  | Military Capability | 22.6822 | MOD_0105_1617-Q1,1718 - Q2 |  | Amber/Red | Not new
MOD_0106_1617-Q1 | Maritime Patrol Aircraft | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2014-07-08 | 2024-04-01 | 12.74 | 30.56 | 17.82 | 139.9% | 2144.43 |  |  | Military Capability | 9.7397 | MOD_0106_1617-Q1,1718 - Q2 |  | Amber/Red | Not new
MOD_0107_1617-Q1 | PROTECTOR | AR 2018 | 1718-Q2 | MOD | Red | 2009-04-30 | 2035-03-31 | 150.27 | 70.67 | -79.6 | -52.97% | 907.91 |  |  | Military Capability | 25.9342 | MOD_0107_1617-Q1,1718 - Q2 |  | Red | Not new
MoD_0109_1617-Q2 | New Style of Information Technology Deployed | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2015-04-01 | 2025-03-25 | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 9.989 | MoD_0109_1617-Q2,1718 - Q2 |  | Exempt | Not new
MOD_0110_1718-Q1 | MODnet Evolve | AR 2018 | 1718-Q2 | MOD | Amber | 2016-02-29 | Missing Data | 15.2 | 14.87 | -0.33 | -2.171% | Exempt |  |  | Military Capability | 0 | MOD_0110_1718-Q1,1718 - Q2 |  | Amber | Joiner
MOD_0111_1718-Q1 | Joint Crypt Key Programme | AR 2018 | 1718-Q2 | MOD | Exempt | Exempt | Exempt | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 0 | MOD_0111_1718-Q1,1718 - Q2 |  | Amber | Joiner
MOD_0112_1718-Q1 | Type 31e | AR 2018 | 1718-Q2 | MOD | Exempt | 2016-04-01 | Exempt | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 0 | MOD_0112_1718-Q1,1718 - Q2 |  | Red | Joiner
MOD_0113_1718-Q1 | Armed Forces People Programme | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2015-11-25 | 2021-03-31 | 11.1 | 24.56 | 13.46 | 121.3% | 57.38 |  |  | Government Transformation and Service Delivery | 5.3507 | MOD_0113_1718-Q1,1718 - Q2 |  | Amber/Red | Joiner
MOD_0114_1718-Q1 | Defence Estate Optimisation | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2016-09-30 | 2041-03-31 | 0 | 0 | 0 | - | 0 |  |  | Military Capability | 24.5151 | MOD_0114_1718-Q1,1718 - Q2 |  | Amber/Red | Joiner
MOD_0115_1718-Q2 | Mechanised Infantry Programme | AR 2018 | 1718-Q2 | MOD | Amber | Exempt | Exempt | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 0 | MOD_0115_1718-Q2,1718 - Q2 |  | Amber | Joiner
MOD_0116_1718-Q2 | Fleet Solid Support | AR 2018 | 1718-Q2 | MOD | Amber | 2016-03-14 | 2030-04-30 | 3.27 | 3.27 | 0 | 0% | 17.27 |  |  | Military Capability | 14.137 | MOD_0116_1718-Q2,1718 - Q2 |  | Amber | Joiner
MOD_0117_1718-Q2 | Future Maritime Support Strategy | AR 2018 | 1718-Q2 | MOD | Amber/Red | 2016-09-26 | 2019-09-27 | 0 | 0 | 0 | - | 0 |  |  | Military Capability | 3.0027 | MOD_0117_1718-Q2,1718 - Q2 |  | Amber/Red | Joiner
MOJ_0003_1112-Q1 | Electronic Monitoring | AR 2018 | 1718-Q2 | MoJ | Amber/Red | 2011-05-10 | 2024-08-31 | 79.3 | 74.03 | -5.27 | -6.646% | 580.5 |  |  | Government Transformation and Service Delivery | 13.3205 | MOJ_0003_1112-Q1,1718 - Q2 |  | Amber/Red | Not new
MOJ_0004_1112-Q1 | Future IT Sourcing Programme (FITS) | AR 2018 | 1718-Q2 | MoJ | Amber | 2011-03-01 | 2017-11-30 | 314.3 | 314.3 | 0 | 0% | 2879.25 |  |  | ICT | 6.7562 | MOJ_0004_1112-Q1,1718 - Q2 |  | Amber | Not new
MOJ_0008_1112-Q1 | Shared Services (ISSC2) Evolve | AR 2018 | 1718-Q2 | MoJ | Amber/Green | 2013-09-07 | 2015-11-05 | 43.86 | 46.03 | 2.17 | 4.948% | 398.07 |  |  | ICT | 2.1616 | MOJ_0008_1112-Q1,1718 - Q2 |  | Amber/Green | Not new
MOJ_0021_1314-Q1 | CJS Common Platform | AR 2018 | 1718-Q2 | MoJ | Amber/Red | 2012-11-01 | 2019-03-29 | 73.59 | 52.33 | -21.26 | -28.89% | 380.96 |  |  | ICT | 6.4082 | MOJ_0021_1314-Q1,1718 - Q2 |  | Amber/Red | Not new
MOJ_0023_1314-Q1 | Berwyn Programme | AR 2018 | 1718-Q2 | MoJ | Amber/Green | 2013-01-10 | 2018-05-31 | 43.8 | 60.6 | 16.8 | 38.36% | 2269.7 |  |  | Infrastructure and Construction | 5.389 | MOJ_0023_1314-Q1,1718 - Q2 |  | Amber/Green | Not new
MOJ_0028_1314-Q2 | HMCTS Reform | AR 2018 | 1718-Q2 | MoJ | Amber/Red | 2015-01-05 | 2022-03-31 | 192.85 | 192.85 | 0 | 0% | 1647.02 |  |  | Government Transformation and Service Delivery | 7.2384 | MOJ_0028_1314-Q2,1718 - Q2 |  | Amber/Red | Not new
MOJ_0032_1617-Q2 | MoJ Future FM | AR 2018 | 1718-Q2 | MoJ | Amber | 2016-07-01 | 2018-04-01 | 43.3 | 25.9 | -17.4 | -40.18% | 430.2 |  |  | Government Transformation and Service Delivery | 1.7507 | MOJ_0032_1617-Q2,1718 - Q2 |  | Amber | Not new
MOJ_0033_1617-Q2 | Prison Estate Transformation Programme (PETP) | AR 2018 | 1718-Q2 | MoJ | Amber/Red | 2016-04-01 | 2021-12-31 | 0 | 0 | 0 | - | 0 |  |  | Infrastructure and Construction | 5.7534 | MOJ_0033_1617-Q2,1718 - Q2 |  | Amber/Red | Not new
MOJ_0034_1617-Q2 | NOMS Digital Transformation Programme | AR 2018 | 1718-Q2 | MoJ | Amber | 2016-01-01 | 2021-03-31 | 37.8 | 48.1 | 10.3 | 27.25% | 212.2 |  |  | Government Transformation and Service Delivery | 5.2493 | MOJ_0034_1617-Q2,1718 - Q2 |  | Amber | Not new
MOJ_0035_1617-Q3 | Criminal Justice System Exchange Re-provisioning | AR 2018 | 1718-Q2 | MoJ | Amber | 2015-10-31 | 2017-10-31 | 16.06 | 19.91 | 3.85 | 23.97% | 39.88 |  |  | ICT | 2.0027 | MOJ_0035_1617-Q3,1718 - Q2 |  | Amber | Joiner
MOJ_0037_1617-Q4 | Transforming Compliance Enforcment Programme (TCEP) | AR 2018 | 1718-Q2 | MoJ | Amber/Red | 2016-01-04 | 2019-04-26 | 27.4 | 27.4 | 0 | 0% | 123 |  |  | Government Transformation and Service Delivery | 3.3096 | MOJ_0037_1617-Q4,1718 - Q2 |  | Red | Joiner
NCA_0001_1415-Q2 | NCA Transformation Programme | AR 2018 | 1718-Q2 | NCA | Amber | 2014-04-01 | 2019-03-31 | 61 | 61 | 0 | 0% | 304.3 |  |  | Government Transformation and Service Delivery | 5 | NCA_0001_1415-Q2,1718 - Q2 |  | Amber | Not new
NCA_0002_1617-Q2 | IT Transformation Programme | AR 2018 | 1718-Q2 | NCA | Amber | 2016-04-01 | 2022-07-31 | 38.8 | 38.8 | 0 | 0% | 167.68 |  |  | ICT | 6.3342 | NCA_0002_1617-Q2,1718 - Q2 |  | Amber | Not new
ONS_0002_1112-Q1 | Census Transformation Programme | AR 2018 | 1718-Q2 | ONS | Amber | 2015-01-01 | 2025-03-31 | 55.6 | 55.01 | -0.59 | -1.061% | 905.76 |  |  | Government Transformation and Service Delivery | 10.2521 | ONS_0002_1112-Q1,1718 - Q2 |  | Amber | Not new
BEIS_0001_1617-Q2 | Heat Networks Investment Project | AR 2019 | 1819-Q2 | BEIS | Amber | 2015-11-25 | 2021-03-31 | 10.4 | 7.89 | -2.51 | -24.13% | 371.8 |  |  | Infrastructure and Construction | 5.3507 | BEIS_0001_1617-Q2-1819-Q2 |  |  | Not new
BEIS_0002_1718-Q1 | UKRI Implementation Programme | AR 2019 | 1819-Q2 | BEIS | Green | 2016-01-01 | 2018-10-01 | 0 | 0 | 0 | - | 10.37 |  |  | Government Transformation and Service Delivery | 2.7507 | BEIS_0002_1718-Q1-1819-Q2 |  |  | Not new
BEIS_0003_1819-Q2 | The Next Magnox Operating Model | AR 2019 | 1819-Q2 | BEIS | Amber | 2017-09-01 | 2019-09-01 | 2 | 2 | 0 | 0% | 5 |  |  | Government Transformation and Service Delivery | 2 | BEIS_0003_1819-Q2-1819-Q2 |  |  | Joiner
BIS_0014_1415-Q3 | New Polar Research Vessel | AR 2019 | 1819-Q2 | BEIS | Amber | 2014-05-01 | 2022-12-31 | 113 | 111 | -2 | -1.77% | 1403 |  |  | Infrastructure and Construction | 8.674 | BIS_0014_1415-Q3-1819-Q2 |  |  | Not new
BIS_0015_1516-Q1 | Local Land Charges (LLC) Programme | AR 2019 | 1819-Q2 | BEIS | Amber | 2014-03-01 | 2023-11-17 | 31.2 | 9.18 | -22.02 | -70.58% | 193.3 |  |  | ICT | 9.7205 | BIS_0015_1516-Q1-1819-Q2 |  |  | Not new
CO_0013_1516-Q2 | Foxhound Programme | AR 2019 | 1819-Q2 | CO | Amber/Green | 2013-09-01 | 2018-07-01 | 26.1 | 22.7 | -3.4 | -13.03% | 126.5 |  |  | ICT | 4.8329 | CO_0013_1516-Q2-1819-Q2 |  |  | Not new
CO_0014_1516-Q2 | Government Hubs Programme | AR 2019 | 1819-Q2 | CO | Amber | 2015-05-01 | 2036-03-31 | 111.41 | 111.41 | 0 | 0% | 564.1 |  |  | Government Transformation and Service Delivery | 20.9315 | CO_0014_1516-Q2-1819-Q2 |  |  | Not new
CO_0015_1516-Q2 | GOV UK Verify | AR 2019 | 1819-Q2 | CO | Red | 2012-04-01 | 2020-03-31 | 30 | 30 | 0 | 0% | 209.6 |  |  | ICT | 8.0027 | CO_0015_1516-Q2-1819-Q2 |  |  | Not new
CO_0016_1516-Q4 | 1617 New Property Model Programme | AR 2019 | 1819-Q2 | CO | Amber | 2015-04-01 | 2021-04-01 | 7 | 7 | 0 | 0% | 270.741 |  |  | Government Transformation and Service Delivery | 6.0055 | CO_0016_1516-Q4-1819-Q2 |  |  | Not new
CO_0018_1617-Q3 | Common Technology Services | AR 2019 | 1819-Q2 | CO | Amber | 2016-04-01 | 2020-03-31 | 8.1 | 5.2 | -2.9 | -35.8% | 43.96 |  |  | Government Transformation and Service Delivery | 4 | CO_0018_1617-Q3-1819-Q2 |  |  | Not new
CO_0019_1617-Q4 | Government as a Platform | AR 2019 | 1819-Q2 | CO | Amber | 2015-12-31 | 2020-03-31 | 20 | 15.8 | -4.2 | -21% | 90 |  |  | ICT | 4.2521 | CO_0019_1617-Q4-1819-Q2 |  |  | Not new
CO_0020_1718-Q4 | Commercial Capability Expansion Programme | AR 2019 | 1819-Q2 | CO | Amber/Red | 2017-04-01 | 2020-03-31 | 6 | 6.2 | 0.2 | 3.333% | 11.7 |  |  | Government Transformation and Service Delivery | 3 | CO_0020_1718-Q4-1819-Q2 |  |  | Joiner
DCMS_0008_1516-Q4 | Blythe House Programme | AR 2019 | 1819-Q2 | DCMS | Amber | 2015-11-25 | 2023-03-31 | 88.7494 | 23.5 | -65.2494 | -73.52% | 338 |  |  | Infrastructure and Construction | 7.3507 | DCMS_0008_1516-Q4-1819-Q2 |  |  | Not new
DCMS_0009_1516-Q4 | 700 MHz Clearance Programme | AR 2019 | 1819-Q2 | DCMS | Amber | 2015-01-13 | 2022-01-01 | 164.3 | 87.1 | -77.2 | -46.99% | 594.92 |  |  | Infrastructure and Construction | 6.9726 | DCMS_0009_1516-Q4-1819-Q2 |  |  | Not new
DCMS_0010_1718-Q3 | Local Full Fibre Networks | AR 2019 | 1819-Q2 | DCMS | Amber/Green | 2017-04-01 | 2021-12-01 | 50.7 | 58 | 7.3 | 14.4% | 318.7 |  |  | Infrastructure and Construction | 4.6712 | DCMS_0010_1718-Q3-1819-Q2 |  |  | Joiner
DCMS_0011_1718-Q3 | 5G Testbeds & Trials | AR 2019 | 1819-Q2 | DCMS | Amber/Red | 2017-02-28 | 2021-03-31 | 79.15 | 42.65 | -36.5 | -46.11% | 217.05 |  |  | Infrastructure and Construction | 4.0877 | DCMS_0011_1718-Q3-1819-Q2 |  |  | Joiner
DCMS_0012_1819-Q2 | Birmingham 2022 Commonwealth Games | AR 2019 | 1819-Q2 | DCMS | Amber/Red | 2017-12-21 | 2023-03-31 | Exempt | Exempt | - | - | Exempt |  |  | Government Transformation and Service Delivery | 5.2767 | DCMS_0012_1819-Q2-1819-Q2 |  |  | Joiner
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2019 | 1819-Q2 | BEIS | Amber | 2008-06-30 | 2040-12-31 | 40.27 | 37.4 | -2.87 | -7.127% | 12343.96 |  |  | Infrastructure and Construction | 32.526 | DECC_0005_1112-Q1-1819-Q2 |  |  | Not new
DECC_0010_1112-Q1 | Smart Metering Implementation Programme | AR 2019 | 1819-Q2 | BEIS | Amber/Red | 2009-12-02 | 2020-12-31 | 1060.9711 | 1064.0435 | 3.0724 | 0.2896% | 17215.7754 |  |  | Infrastructure and Construction | 11.0877 | DECC_0010_1112-Q1-1819-Q2 |  |  | Not new
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | AR 2019 | 1819-Q2 | BEIS | Amber | 2012-04-03 | 2019-08-31 | 490 | 532 | 42 | 8.571% | 2782 |  |  | Infrastructure and Construction | 7.4137 | DECC_0013_1213-Q1-1819-Q2 |  |  | Not new
DECC_0017_1516-Q1 | Sellafield Model Change (SMC) | AR 2019 | 1819-Q2 | BEIS | Green | 2015-01-13 | 2017-05-24 | 2292.8 | 2038.8 | -254 | -11.08% | 30011.2 |  |  | Government Transformation and Service Delivery | 2.3616 | DECC_0017_1516-Q1-1819-Q2 |  |  | Not new
DEFRA_0006_1516-Q1 | DEFRA UNITY PROGRAMME | AR 2019 | 1819-Q2 | DEFRA | Amber | 2014-11-01 | 2020-04-30 | 121.2 | 159 | 37.8 | 31.19% | 1048.4 |  |  | ICT | 5.4986 | DEFRA_0006_1516-Q1-1819-Q2 |  |  | Not new
DFE_0006_1415-Q3 | Priority School Building Programme 2 | AR 2019 | 1819-Q2 | DFE | Amber/Red | 2014-05-01 | 2022-12-31 | 448.6 | 448.6 | 0 | 0% | 2398.5 |  |  | Infrastructure and Construction | 8.674 | DFE_0006_1415-Q3-1819-Q2 |  |  | Not new
DFE_0007_1617-Q1 | 30 Hrs Free Childcare Programme | AR 2019 | 1819-Q2 | DFE | Amber/Green | 2015-05-11 | 2018-03-31 | 750.02 | 750.51 | 0.49 | 0.06533% | 5874.92 |  |  | Government Transformation and Service Delivery | 2.8904 | DFE_0007_1617-Q1-1819-Q2 |  |  | Not new
DfE_0009_1617-Q2 | Apprenticeships Reform Programme | AR 2019 | 1819-Q2 | DFE | Amber | 2015-05-08 | 2021-04-01 | 2243.3 | 1863.6 | -379.7 | -16.93% | 11347.5 |  |  | Government Transformation and Service Delivery | 5.9041 | DfE_0009_1617-Q2-1819-Q2 |  |  | Not new
DFE_0010_1819-Q1 | T Level Programme | AR 2019 | 1819-Q2 | DFE | Amber/Red | 2016-10-25 | 2023-09-30 | 50 | 50 | 0 | 0% | 146.2 |  |  | Government Transformation and Service Delivery | 6.9342 | DFE_0010_1819-Q1-1819-Q2 |  |  | Joiner
DFE_0011_1819-Q2 | Social Work England | AR 2019 | 1819-Q2 | DFE | Amber | 2016-05-09 | Exempt | 11.35 | 7.885 | -3.465 | -30.53% | 21.31 |  |  | Government Transformation and Service Delivery | 0 | DFE_0011_1819-Q2-1819-Q2 |  |  | Joiner
DFID_0001_1112-Q1 | St Helena Airport | AR 2019 | 1819-Q2 | DFID | Amber | 2005-03-15 | 2026-08-31 | 4 | 4.64 | 0.64 | 16% | 445.1 |  |  | Infrastructure and Construction | 21.4767 | DFID_0001_1112-Q1-1819-Q2 |  |  | Not new
DFT_0001_1112-Q1 | Crossrail Programme | AR 2019 | 1819-Q2 | DFT | Red | 2008-07-22 |  | 466.75 | 1089.2 | 622.45 | 133.4% | 15474.61 |  |  | Infrastructure and Construction | 0 | DFT_0001_1112-Q1-1819-Q2 |  |  | Not new
DFT_0004_1112-Q1 | High Speed Rail Programme (HS2) | AR 2019 | 1819-Q2 | DFT | Amber/Red | 2011-02-28 | 2033-12-31 | 2976 | 3009 | 33 | 1.109% | 55710.37 |  |  | Infrastructure and Construction | 22.8548 | DFT_0004_1112-Q1-1819-Q2 |  |  | Not new
DFT_0005_1112-Q1 | Intercity Express Programme | AR 2019 | 1819-Q2 | DFT | Amber/Red | 2005-06-01 | 2020-02-06 | 120.1 | 154.9 | 34.8 | 28.98% | 6583.25 |  |  | Infrastructure and Construction | 14.6932 | DFT_0005_1112-Q1-1819-Q2 |  |  | Not new
DFT_0016_1112-Q1 | Thameslink Programme | AR 2019 | 1819-Q2 | DFT | Amber | 2005-07-01 | 2026-12-31 | 2178.7 | 2026.7 | -152 | -6.977% | 7269.4 |  |  | Infrastructure and Construction | 21.5151 | DFT_0016_1112-Q1-1819-Q2 |  |  | Not new
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | AR 2019 | 1819-Q2 | DFT | Amber/Green | 2012-09-01 | 2021-09-30 | 407.3 | 475 | 67.7 | 16.62% | 1435.3 |  |  | Infrastructure and Construction | 9.0849 | DFT_0020_1314-Q2-1819-Q2 |  |  | Not new
DFT_0021_1314-Q3 | Rail Franchising Programme | AR 2019 | 1819-Q2 | DFT | Amber/Red | 2016-05-19 | 2019-03-31 | 10.6 | 12.7 | 2.1 | 19.81% | 20.6 |  |  | Government Transformation and Service Delivery | 2.8658 | DFT_0021_1314-Q3-1819-Q2 |  |  | Not new
DfT_0022_1415-Q4 | Lower Thames Crossing | AR 2019 | 1819-Q2 | DFT | Amber | 2014-05-30 | 2028-07-31 | 61.9 | 81 | 19.1 | 30.86% | 5509 |  |  | Infrastructure and Construction | 14.1808 | DfT_0022_1415-Q4-1819-Q2 |  |  | Not new
DfT_0023_1516-Q3 | Heathrow Expansion | AR 2019 | 1819-Q2 | DFT | Amber | 2015-07-01 | 2029-12-31 | 14.7 | 7.9 | -6.8 | -46.26% | 22732.9 |  |  | Infrastructure and Construction | 14.5123 | DfT_0023_1516-Q3-1819-Q2 |  |  | Not new
DFT_0024_1516-Q4 | A303 Amesbury to Berwick Down | AR 2019 | 1819-Q2 | DFT | Amber | 2014-12-01 | 2028-06-01 | 22.9 | 33.19 | 10.29 | 44.93% | 1556.4 |  |  | Infrastructure and Construction | 13.5096 | DFT_0024_1516-Q4-1819-Q2 |  |  | Not new
DFT_0025_1617-Q1 | East West Rail Programme (Western Section) | AR 2019 | 1819-Q2 | DFT | Amber | 2011-11-30 | 2024-06-30 | 89.7 | 89.7 | 0 | 0% | 1091.4 |  |  | Infrastructure and Construction | 12.5918 | DFT_0025_1617-Q1-1819-Q2 |  |  | Not new
DFT_0026_1617-Q1 | Great Western Route Modernisation (GWRM) including electrification | AR 2019 | 1819-Q2 | DFT | Amber/Red | 2011-12-01 | 2024-12-31 | 655 | 769 | 114 | 17.4% | 5001 |  |  | Infrastructure and Construction | 13.0932 | DFT_0026_1617-Q1-1819-Q2 |  |  | Not new
DFT_0027_1617-Q1 | Midland Main Line Programme | AR 2019 | 1819-Q2 | DFT | Amber | 2011-01-01 | 2024-12-31 | 501.9 | 441.3 | -60.6 | -12.07% | 1671.2 |  |  | Infrastructure and Construction | 14.0082 | DFT_0027_1617-Q1-1819-Q2 |  |  | Not new
DFT_0028_1617-Q1 | North of England Programme | AR 2019 | 1819-Q2 | DFT | Amber | 2009-07-23 | 2022-12-31 | 285 | 367.7 | 82.7 | 29.02% | 6052 |  |  | Infrastructure and Construction | 13.4493 | DFT_0028_1617-Q1-1819-Q2 |  |  | Not new
DFT_0029_1617-Q1 | South West Route Capacity | AR 2019 | 1819-Q2 | DFT | Amber/Green | 2012-07-16 | 2019-12-31 | 178.22 | 129.02 | -49.2 | -27.61% | 820.2 |  |  | Infrastructure and Construction | 7.463 | DFT_0029_1617-Q1-1819-Q2 |  |  | Not new
DFT_0030_1617-Q2 | M20 Lorry Area | AR 2019 | 1819-Q2 | DFT | Amber | 2015-11-01 | 2023-07-01 | 0 | 3.7 | 3.7 | - | 0 |  |  | Infrastructure and Construction | 7.6685 | DFT_0030_1617-Q2-1819-Q2 |  |  | Not new
DFT_0031_1819-Q1 | A428 Black Cat to Caxton Gibbet | AR 2019 | 1819-Q2 | DFT | Amber/Green | 2015-04-01 | 2025-04-01 | 14.3 | 8.3 | -6 | -41.96% | 809.8 |  |  | Infrastructure and Construction | 10.0082 | DFT_0031_1819-Q1-1819-Q2 |  |  | Joiner
DFT_0032_1819-Q1 | Digital Railway | AR 2019 | 1819-Q2 | DFT | Amber | 2016-11-23 | 2023-04-01 | 32 | 32.02 | 0.02 | 0.0625% | 450 |  |  | Infrastructure and Construction | 6.3562 | DFT_0032_1819-Q1-1819-Q2 |  |  | Joiner
DFT_0033_1819-Q1 | East Coast Mainline Programme | AR 2019 | 1819-Q2 | DFT | Amber/Green | 2014-04-01 | 2023-12-01 | 141.2 | 141.2 | 0 | 0% | 1040.37 |  |  | Infrastructure and Construction | 9.674 | DFT_0033_1819-Q1-1819-Q2 |  |  | Joiner
DH_0017_1112-Q1 | PHE Science Hub | AR 2019 | 1819-Q2 | DH | Amber | 2013-06-28 | 2024-12-31 | 204.793 | 188.728 | -16.065 | -7.845% | 2656.318 |  |  | Infrastructure and Construction | 11.5178 | DOH_0017_1112-Q1-1819-Q2 |  |  | Not new
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | AR 2019 | 1819-Q2 | DH | Amber | 2012-01-01 | 2018-05-30 | 54.899 | 74.5113 | 19.6123 | 35.72% | 1247.2397 |  |  | Government Transformation and Service Delivery | 6.4137 | DOH_0031_1314-Q1-1819-Q2 |  |  | Not new
DH_0039_1314-Q2 | NHS e-Referral Service | AR 2019 | 1819-Q2 | DH | Green | 2012-03-29 | 2018-03-31 | 19.99 | 22.8532 | 2.8632 | 14.32% | 151.15 |  |  | ICT | 6.0082 | DOH_0039_1314-Q2-1819-Q2 |  |  | Not new
DH_0041_1314-Q2 | Health & Social Care Network | AR 2019 | 1819-Q2 | DH | Amber/Red | 2012-03-29 | 2021-03-31 | 83.71 | 86.44 | 2.73 | 3.261% | 392.76 |  |  | ICT | 9.011 | DOH_0041_1314-Q2-1819-Q2 |  |  | Not new
DH_0043_1314-Q3 | NHS Pension Re-let | AR 2019 | 1819-Q2 | DH | Amber/Green | 2013-07-05 | 2017-07-21 | 28.98 | 28.98 | 0 | 0% | 274.24 |  |  | Government Transformation and Service Delivery | 4.0466 | DOH_0043_1314-Q3-1819-Q2 |  |  | Not new
DH_0046_1415-Q1 | Medical Examiners Programme | AR 2019 | 1819-Q2 | DH | Amber/Red | 2007-07-24 | 2020-09-30 | 19.7 | 19.7 | 0 | 0% | 76.1 |  |  | Government Transformation and Service Delivery | 13.1973 | DOH_0046_1415-Q1-1819-Q2 |  |  | Not new
DH_0048_1415-Q1 | One Hundred Thousand Genomes Project | AR 2019 | 1819-Q2 | DH | Amber | 2013-04-10 | 2018-12-31 | 50 | 82.7 | 32.7 | 65.4% | 369.9 |  |  | Government Transformation and Service Delivery | 5.7288 | DOH_0048_1415-Q1-1819-Q2 |  |  | Not new
DH_0056_1415-Q3 | Visitor and Migrant NHS Cost Recovery Programme | AR 2019 | 1819-Q2 | DH | Amber/Green | 2013-09-01 | 2019-03-31 | 7.62 | 7.62 | 0 | 0% | 33.15 |  |  | Government Transformation and Service Delivery | 5.5808 | DOH_0056_1415-Q3-1819-Q2 |  |  | Not new
DH_0058_1516-Q4 | Data Services Platform Programme | AR 2019 | 1819-Q2 | DH | Amber | 2015-02-23 | 2020-03-31 | 20.49 | 18.64 | -1.85 | -9.029% | 75.25 |  |  | ICT | 5.1041 | DOH_0058_1516-Q4-1819-Q2 |  |  | Not new
DH_0059_1617-Q1 | Procurement Transformation Programme | AR 2019 | 1819-Q2 | DH | Amber | 2015-03-31 | 2019-03-31 | 32.21 | 51.54 | 19.33 | 60.01% | 168.73 |  |  | Government Transformation and Service Delivery | 4.0027 | DOH_0059_1617-Q1-1819-Q2 |  |  | Not new
DH_0060_1617-Q1 | NHS UK | AR 2019 | 1819-Q2 | DH | Amber | 2016-04-01 | 2020-12-31 | 12.815 | 12.815 | 0 | 0% | 54.954 |  |  | Government Transformation and Service Delivery | 4.7534 | DOH_0060_1617-Q1-1819-Q2 |  |  | Not new
DH_0061_1617-Q3 | IT Infrastructure Sourcing Programme | AR 2019 | 1819-Q2 | DH | Amber/Red | 2013-12-01 | 2019-12-31 | 22.1 | 22.1 | 0 | 0% | 129.5 |  |  | ICT | 6.0849 | DOH_0061_1617-Q3-1819-Q2 |  |  | Not new
DWP_0005_1112-Q1 | Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme) | AR 2019 | 1819-Q2 | DWP | Amber/Green | 2007-05-01 | 2019-11-30 | 66.16 | 66.1 | -0.06 | -0.09069% | 1125 |  |  | Government Transformation and Service Delivery | 12.5918 | DWP_0005_1112-Q1-1819-Q2 |  |  | Not new
DWP_0009_1112-Q1 | Universal Credit Programme | AR 2019 | 1819-Q2 | DWP | Amber | 2011-11-17 | 2023-06-30 | 836.7159 | 819.3859 | -17.33 | -2.071% | 12716.9535 |  |  | Government Transformation and Service Delivery | 11.6247 | DWP_0009_1112-Q1-1819-Q2 |  |  | Not new
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | AR 2019 | 1819-Q2 | DWP | Amber/Green | 2012-04-02 | 2021-03-31 | 108.7666 | 94.8762 | -13.8904 | -12.77% | 1174.7047 |  |  | Government Transformation and Service Delivery | 9 | DWP_0016_1213-Q2-1819-Q2 |  |  | Not new
FCO_0008_1415-Q4 | Technology Overhaul | AR 2019 | 1819-Q2 | FCO | Amber | 2015-11-01 | 2019-03-31 | 20.4 | 24.966 | 4.566 | 22.38% | 120 |  |  | ICT | 3.4137 | FCO_0008_1415-Q4-1819-Q2 |  |  | Not new
FCO_0010_1617-Q3 | Echo 2 Programme | AR 2019 | 1819-Q2 | FCO | Amber | 2015-09-01 | 2021-08-31 | 28.9 | 31.3521 | 2.4521 | 8.485% | 203.84 |  |  | ICT | 6.0027 | FCO_0010_1617-Q3-1819-Q2 |  |  | Not new
FCO_0011_1718-Q3 | Washington Embassy Refurbishment | AR 2019 | 1819-Q2 | FCO | Amber | 2017-01-01 | 2022-12-12 | 8.7 | 8.7 | 0 | 0% | 63.7 |  |  | Infrastructure and Construction | 5.9479 | FCO_0011_1718-Q3-1819-Q2 |  |  | Joiner
FCO_0012_1718-Q4 | Atlas Programme (IPA ID 2410) | AR 2019 | 1819-Q2 | FCO | Amber | 2017-07-01 | 2020-06-30 | 9.3 | 9.3 | 0 | 0% | 21.8 |  |  | ICT | 3 | FCO_0012_1718-Q4-1819-Q2 |  |  | Joiner
HMRC_0012_1415-Q1 | Tax-Free Childcare | AR 2019 | 1819-Q2 | HMRC | Amber | 2013-09-10 | 2019-09-30 | 54.06 | 50.909 | -3.151 | -5.829% | 356.89 |  |  | Government Transformation and Service Delivery | 6.0575 | HMRC_0012_1415-Q1-1819-Q2 |  |  | Not new
HMRC_0013_1415-Q4 | Columbus (formerly Aspire Replacement Programme) | AR 2019 | 1819-Q2 | HMRC | Amber | 2014-01-01 | 2021-12-31 | 104 | 6 | -98 | -94.23% | 694 |  |  | ICT | 8.0027 | HMRC_0013_1415-Q4-1819-Q2 |  |  | Not new
HMRC_0014_1415-Q4 | CUSTOMS DECLARATION SERVICES (CDS) Programme | AR 2019 | 1819-Q2 | HMRC | Amber/Red | 2013-10-16 | 2019-01-31 | 75.49 | 75.57 | 0.08 | 0.106% | 226.33 |  |  | ICT | 5.2959 | HMRC_0014_1415-Q4-1819-Q2 |  |  | Not new
HMRC_0015_1617-Q1 | Building Our Future Locations Programme | AR 2019 | 1819-Q2 | HMRC | Amber | 2016-01-05 | 2026-03-31 | 326.1 | 302.8 | -23.3 | -7.145% | 2835.9 |  |  | Government Transformation and Service Delivery | 10.2411 | HMRC_0015_1617-Q1-1819-Q2 |  |  | Not new
HMRC_0017_1617-Q2 | Making Tax Digital for Business | AR 2019 | 1819-Q2 | HMRC | Amber/Red | 2016-04-01 | 2021-03-31 | 77.09 | 75.15 | -1.94 | -2.517% | 334.48 |  |  | ICT | 5 | HMRC_0017_1617-Q2-1819-Q2 |  |  | Not new
HMRC_0018_1617-Q3 | Compliance For The Future Programme | AR 2019 | 1819-Q2 | HMRC | Amber/Red | 2016-04-01 | 2021-03-31 | 50.45 | 34.4001 | -16.0499 | -31.81% | 188.184 |  |  | Government Transformation and Service Delivery | 5 | HMRC_0018_1617-Q3-1819-Q2 |  |  | Not new
HMRC_0019_1718-Q4 | Government Gateway Transformation | AR 2019 | 1819-Q2 | HMRC | Amber | 2017-04-01 | 2019-03-31 | 28.04 | 25.1868 | -2.8532 | -10.18% | 131.11 |  |  | ICT | 1.9973 | HMRC_0019_1718-Q4-1819-Q2 |  |  | Joiner
HO_0011_1112-Q2 | Disclosure and Barring Service (DBS) Programme | AR 2019 | 1819-Q2 | HO | Amber/Red | 2010-12-29 | 2019-12-31 | 110.4 | 172 | 61.6 | 55.8% | 785.7 |  |  | Government Transformation and Service Delivery | 9.011 | HO_0011_1112-Q2-1819-Q2 |  |  | Not new
HO_0012_1112-Q3 | Communications Capabilities Development (CCD) Programme | AR 2019 | 1819-Q2 | HO | Green | 2010-05-01 | 2020-04-01 | Exempt | Exempt | - | - | Exempt |  |  | ICT | 9.926 | HO_0012_1112-Q3-1819-Q2 |  |  | Not new
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2019 | 1819-Q2 | HO | Amber/Red | 2011-06-01 | 2020-12-31 | 773.87 | 773.87 | 0 | 0% | 5058.63 |  |  | Infrastructure and Construction | 9.5918 | HO_0016_1213-Q1-1819-Q2 |  |  | Not new
HO_0029_1314-Q4 | Immigration Platform Technologies (IPT) | AR 2019 | 1819-Q2 | HO | Amber | 2013-04-01 | 2017-03-31 | 40.7 | 50.7 | 10 | 24.57% | 264.95 |  |  | ICT | 4 | HO_0029_1314-Q4-1819-Q2 |  |  | Not new
HO_0030_1415-Q1 | Metis Programme | AR 2019 | 1819-Q2 | HO | Amber/Red | 2016-09-01 | 2019-06-01 | 53.3 | 56.12 | 2.82 | 5.291% | 290.53 |  |  | ICT | 2.7479 | HO_0030_1415-Q1-1819-Q2 |  |  | Not new
HO_0031_1415-Q1 | Digital Services at the Border (DSAB) | AR 2019 | 1819-Q2 | HO | Amber | 2014-02-12 | 2019-03-31 | 52.6 | 64.1 | 11.5 | 21.86% | 346.9 |  |  | ICT | 5.1315 | HO_0031_1415-Q1-1819-Q2 |  |  | Not new
HO_0032_1415-Q1 | Technology Platforms for Tomorrow (TPT) | AR 2019 | 1819-Q2 | HO | Amber | 2014-02-01 | 2019-03-31 | 70.32 | 76.5 | 6.18 | 8.788% | 592.07 |  |  | ICT | 5.1616 | HO_0032_1415-Q1-1819-Q2 |  |  | Not new
HO_0033_1415-Q3 | Home Office Biometrics (HOB) Programme | AR 2019 | 1819-Q2 | HO | Amber/Green | 2014-04-01 | 2020-03-31 | 75.4 | 75.4 | 0 | 0% | 842.37 |  |  | ICT | 6.0027 | HO_0033_1415-Q3-1819-Q2 |  |  | Not new
HO_0034_1516-Q2 | Cyclamen Project | AR 2019 | 1819-Q2 | HO | Amber | 2014-04-01 | 2020-04-01 | Exempt | Exempt | - | - | Exempt |  |  | Government Transformation and Service Delivery | 6.0055 | HO_0034_1516-Q2-1819-Q2 |  |  | Not new
HO_0035_1617-Q1 | Smarter Working Programme (SWP) | AR 2019 | 1819-Q2 | HO | Amber | 2015-10-28 | 2020-03-31 | 25.6 | 4.82 | -20.78 | -81.17% | 144.5 |  |  | Government Transformation and Service Delivery | 4.4274 | HO_0035_1617-Q1-1819-Q2 |  |  | Not new
HO_0036_1617-Q2 | National Law Enforcement Data Programme (NLEDP) | AR 2019 | 1819-Q2 | HO | Amber/Red | 2014-04-01 | 2020-03-31 | 67.5 | 82.1 | 14.6 | 21.63% | 469.4 |  |  | ICT | 6.0027 | HO_0036_1617-Q2-1819-Q2 |  |  | Not new
HO_0037_1718-Q1 | Asylum Accommodation and Support Transformation (AAST) | AR 2019 | 1819-Q2 | HO | Amber | 2016-08-29 | 2019-09-02 | 3.64 | 19.97 | 16.33 | 448.6% | 5062.02 |  |  | Government Transformation and Service Delivery | 3.011 | HO_0037_1718-Q1-1819-Q2 |  |  | Not new
MOD_0001_1112-Q1 | A400M | AR 2019 | 1819-Q2 | MOD | Amber | 2000-05-17 | 2023-03-31 | 118.42 | 95.29 | -23.13 | -19.53% | 3394.888 |  |  | Military Capability | 22.8849 | MOD_0001_1112-Q1-1819-Q2 |  |  | Not new
MOD_0017_1112-Q1 | Crowsnest Programme | AR 2019 | 1819-Q2 | MOD | Amber | 2013-03-31 | 2023-06-30 | 104.86 | 104.86 | 0 | 0% | Exempt |  |  | Military Capability | 10.2548 | MOD_0017_1112-Q1-1819-Q2 |  |  | Not new
MOD_0033_1112-Q1 | MARSHALL | AR 2019 | 1819-Q2 | MOD | Amber/Green | 2006-04-03 | 2024-12-31 | 125.706 | 108.221 | -17.485 | -13.91% | 1807.594 |  |  | Military Capability | 18.7589 | MOD_0033_1112-Q1-1819-Q2 |  |  | Not new
MOD_0036_1112-Q1 | Maritime Sustainment Programme | AR 2019 | 1819-Q2 | MOD | Amber | 2005-07-25 | 2019-02-28 | 25.531 | 25.531 | 0 | 0% | 618.808 |  |  | Military Capability | 13.6055 | MOD_0036_1112-Q1-1819-Q2 |  |  | Not new
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2019 | 1819-Q2 | MOD | Exempt | 2008-04-01 | 2025-04-30 | 1065.18 | 1039.76 | -25.42 | -2.386% | 19895.89 |  |  | Military Capability | 17.0904 | MOD_0038_1112-Q1-1819-Q2 |  |  | Not new
MOD_0042_1112-Q1 | Queen Elizabeth Programme | AR 2019 | 1819-Q2 | MOD | Amber | 1998-12-01 | 2023-03-31 | 258.07 | 249.434 | -8.636 | -3.346% | 6797.641 |  |  | Military Capability | 24.3452 | MOD_0042_1112-Q1-1819-Q2 |  |  | Not new
MOD_0047_1112-Q1 | Spearfish Upgrade Programme | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2008-04-01 | 2024-03-31 | 38.689 | 37.896 | -0.793 | -2.05% | 413.89 |  |  | Military Capability | 16.0082 | MOD_0047_1112-Q1-1819-Q2 |  |  | Not new
MOD_0055_1112-Q1 | Type 26 Global Combat Ship Programme | AR 2019 | 1819-Q2 | MOD | Amber/Green | 2008-07-21 | 2035-05-01 | 432.151 | 430.854 | -1.297 | -0.3001% | Exempt |  |  | Military Capability | 26.7945 | MOD_0055_1112-Q1-1819-Q2 |  |  | Not new
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2019 | 1819-Q2 | MOD | Amber | 1998-03-01 | 2017-07-03 | 0 | 0.275 | 0.275 | - | 1117.73 |  |  | Military Capability | 19.3534 | MOD_0061_1112-Q1-1819-Q2 |  |  | Not new
MOD_0064_1112-Q2 | Carrier Enabled Power Projection | AR 2019 | 1819-Q2 | MOD | Amber | 2011-01-31 | 2030-12-01 | 1.855 | 1.824 | -0.031 | -1.671% | 21.57 |  |  | Military Capability | 19.8466 | MOD_0064_1112-Q2-1819-Q2 |  |  | Not new
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2019 | 1819-Q2 | MOD | Amber | 1997-03-17 | 2025-04-30 | 502.505 | 479.792 | -22.713 | -4.52% | 9970.77 |  |  | Military Capability | 28.1397 | MOD_0076_1213-Q1-1819-Q2 |  |  | Not new
MOD_0077_1213-Q1 | Complex Weapons | AR 2019 | 1819-Q2 | MOD | Amber | 2008-03-31 | 2032-04-01 | 726.246 | 778.15 | 51.904 | 7.147% | 26034.99 |  |  | Military Capability | 24.0192 | MOD_0077_1213-Q1-1819-Q2 |  |  | Not new
MOD_0078_1213-Q1 | Core Production Capability | AR 2019 | 1819-Q2 | MOD | Amber | 2012-04-01 | 2028-04-30 | 182.3 | 182.3 | 0 | 0% | 1659.23 |  |  | Military Capability | 16.0904 | MOD_0078_1213-Q1-1819-Q2 |  |  | Not new
MOD_0079_1213-Q1 | Lightning Programme | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2001-10-01 | 2035-03-31 | 803.332 | 786.495 | -16.837 | -2.096% | 10475.19 |  |  | Military Capability | 33.5178 | MOD_0079_1213-Q1-1819-Q2 |  |  | Not new
MOD_0080_1213-Q1 | DREADNOUGHT | AR 2019 | 1819-Q2 | MOD | Amber | 2011-04-14 | Exempt | 1505.634 | 1339.286 | -166.348 | -11.05% | 30060.069 |  |  | Military Capability | 0 | MOD_0080_1213-Q1-1819-Q2 |  |  | Not new
MOD_0085_1314-Q2 | Army Basing Programme | AR 2019 | 1819-Q2 | MOD | Amber | 2013-05-22 | 2021-11-26 | 630.319 | 499.578 | -130.741 | -20.74% | 2059.26 |  |  | Military Capability | 8.5205 | MOD_0085_1314-Q2-1819-Q2 |  |  | Not new
MOD_0091_1415-Q3 | Armoured Cavalry 2025 | AR 2019 | 1819-Q2 | MOD | Amber | 2014-01-22 | 2025-04-30 | 627.856 | 542.5 | -85.356 | -13.59% | 6291.94 |  |  | Military Capability | 11.2767 | MOD_0091_1415-Q3-1819-Q2 |  |  | Not new
MOD_0092_1415-Q3 | Armoured Infantry 2026 | AR 2019 | 1819-Q2 | MOD | Red | 2014-12-04 | 2026-12-31 | 64.167 | 42.789 | -21.378 | -33.32% | Exempt |  |  | Military Capability | 12.0822 | MOD_0092_1415-Q3-1819-Q2 |  |  | Not new
MOD_0094_1415-Q3 | Contracting; Purchasing and Finance | AR 2019 | 1819-Q2 | MOD | Amber | 2011-12-01 | 2018-03-31 | 7.873 | 9.116 | 1.243 | 15.79% | 146.734 |  |  | Government Transformation and Service Delivery | 6.3342 | MOD_0094_1415-Q3-1819-Q2 |  |  | Not new
MOD_0100_1516-Q1 | Future Beyond Line Of Sight | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2011-01-01 | 2041-12-31 | Exempt | Exempt | - | - | Exempt |  |  | ICT | 31.0192 | MOD_0100_1516-Q1-1819-Q2 |  |  | Not new
MOD_0101_1516-Q1 | New Style of Information Technology (Base) | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2015-04-01 | 2018-03-05 | Exempt | Exempt | - | - | Exempt |  |  | ICT | 2.9288 | MOD_0101_1516-Q1-1819-Q2 |  |  | Not new
MOD_0104_1617-Q1 | Armour MBT 2025 | AR 2019 | 1819-Q2 | MOD | Amber | 2014-12-04 | 2026-06-01 | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 11.4986 | MoD_0104_1617-Q1-1819-Q2 |  |  | Not new
MOD_0105_1617-Q1 | Land Environment Tactical Communication and Information Systems | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2013-05-01 | 2035-12-31 | 273.661 | 251.695 | -21.966 | -8.027% | 11142.64 |  |  | Military Capability | 22.6822 | MoD_0105_1617-Q1-1819-Q2 |  |  | Not new
MOD_0106_1617-Q1 | Maritime Patrol Aircraft | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2014-07-08 | 2024-04-01 | 186.186 | 177.897 | -8.289 | -4.452% | 2048.899 |  |  | Military Capability | 9.7397 | MoD_0106_1617-Q1-1819-Q2 |  |  | Not new
MOD_0107_1617-Q1 | PROTECTOR | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2009-04-30 | 2035-03-31 | 64.244 | 52.72 | -11.524 | -17.94% | 1039.247 |  |  | Military Capability | 25.9342 | MoD_0107_1617-Q1-1819-Q2 |  |  | Not new
MOD_0109_1617-Q2 | New Style of Information Technology Deployed | AR 2019 | 1819-Q2 | MOD | Amber | 2015-04-01 | 2025-03-25 | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 9.989 | MoD_0109_1617-Q2-1819-Q2 |  |  | Not new
MOD_0110_1718-Q1 | MODnet Evolve | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2016-02-29 | 2022-07-11 | Exempt | Exempt | Exempt | - | Exempt |  |  | Military Capability | 6.3671 | MOD_0110_1718-Q1-1819-Q2 |  |  | Not new
MOD_0111_1718-Q1 | Joint Crypt Key Programme | AR 2019 | 1819-Q2 | MOD | Exempt | Exempt | Exempt | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 0 | MOD_0111_1718-Q1-1819-Q2 |  |  | Not new
MOD_0112_1718-Q1 | Type 31e | AR 2019 | 1819-Q2 | MOD | Exempt | 2016-04-01 | Exempt | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 0 | MOD_0112_1718-Q1-1819-Q2 |  |  | Not new
MOD_0113_1718-Q1 | Armed Forces People Programme | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2015-11-25 | 2021-03-31 | 27.267 | 22.526 | -4.741 | -17.39% | 69.65 |  |  | Government Transformation and Service Delivery | 5.3507 | MOD_0113_1718-Q1-1819-Q2 |  |  | Not new
MOD_0114_1718-Q1 | Defence Estate Optimisation | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2016-09-30 | 2041-03-31 | 201.05 | 85.349 | -115.701 | -57.55% | 1166.87 |  |  | Military Capability | 24.5151 | MOD_0114_1718-Q1-1819-Q2 |  |  | Not new
MOD_0115_1718-Q2 | Mechanised Infantry Programme | AR 2019 | 1819-Q2 | MOD | Amber | Exempt | Exempt | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | Exempt | MOD_0115_1718-Q2-1819-Q2 |  |  | Not new
MOD_0116_1718-Q2 | Fleet Solid Support | AR 2019 | 1819-Q2 | MOD | Amber | 2016-03-14 | 2030-04-30 | 1.968 | 1.968 | 0 | 0% | 11.78 |  |  | Military Capability | 14.137 | MOD_0116_1718-Q2-1819-Q2 |  |  | Not new
MOD_0117_1718-Q2 | Future Maritime Support Programme | AR 2019 | 1819-Q2 | MOD | Amber/Red | 2016-09-26 | 2019-09-27 | Exempt | Exempt | - | - | Exempt |  |  | Military Capability | 3.0027 | MOD_0117_1718-Q2-1819-Q2 |  |  | Not new
MOD_0118_1718-Q3 | Clyde Infrastructure | AR 2019 | 1819-Q2 | MOD | Amber/Green | 00:00:00 | 00:00:00 | 161.191 | 155.066 | -6.125 | -3.8% | 1771.62 |  |  | Military Capability | 0 | MOD_0118_1718-Q3-1819-Q2 |  |  | Joiner
MOJ_0003_1112-Q1 | Electronic Monitoring | AR 2019 | 1819-Q2 | MOJ | Amber/Green | 2011-05-10 | 2024-08-31 | 106.8 | 94.9 | -11.9 | -11.14% | 580.5 |  |  | Government Transformation and Service Delivery | 13.3205 | MOJ_0003_1112-Q1-1819-Q2 |  |  | Not new
MOJ_0004_1112-Q1 | Future IT Sourcing Programme (FITS) | AR 2019 | 1819-Q2 | MOJ | Amber/Green | 2011-03-01 | 2017-11-30 | 220.23 | 238 | 17.77 | 8.069% | 2879.23 |  |  | ICT | 6.7562 | MOJ_0004_1112-Q1-1819-Q2 |  |  | Not new
MOJ_0021_1314-Q1 | CJS Common Platform | AR 2019 | 1819-Q2 | MOJ | Amber/Red | 2012-11-01 | 2019-03-29 | 74.96 | 58.48 | -16.48 | -21.99% | 398.84 |  |  | ICT | 6.4082 | MOJ_0021_1314-Q1-1819-Q2 |  |  | Not new
MOJ_0028_1314-Q2 | HMCTS Reform | AR 2019 | 1819-Q2 | MOJ | Amber/Red | 2015-01-05 | 2020-03-31 | 242.01 | 242.01 | 0 | 0% | 1546.83 |  |  | Government Transformation and Service Delivery | 5.2384 | MOJ_0028_1314-Q2-1819-Q2 |  |  | Not new
MOJ_0032_1617-Q2 | MoJ Future FM | AR 2019 | 1819-Q2 | MOJ | Amber/Red | 2016-07-01 | 2018-04-01 | 81.4 | 67.1 | -14.3 | -17.57% | 430.2 |  |  | Government Transformation and Service Delivery | 1.7507 | MOJ_0032_1617-Q2-1819-Q2 |  |  | Not new
MOJ_0033_1617-Q2 | Prison Estate Transformation Programme (PETP) | AR 2019 | 1819-Q2 | MOJ | Amber/Red | 2016-04-01 | 2026-05-07 | 67.81 | 67.81 | 0 | 0% | 30165.85 |  |  | Infrastructure and Construction | 10.1041 | MOJ_0033_1617-Q2-1819-Q2 |  |  | Not new
MOJ_0037_1617-Q4 | Transforming Compliance Enforcment Programme (TCEP) | AR 2019 | 1819-Q2 | MOJ | Red | 2016-01-04 | 2019-04-26 | 37.3 | 5.5 | -31.8 | -85.25% | 123 |  |  | Government Transformation and Service Delivery | 3.3096 | MOJ_0037_1617-Q4-1819-Q2 |  |  | Not new
MOJ_0038_1718-Q4 | HMCTS Facilities Management Reprocurement Project (FMRP) | AR 2019 | 1819-Q2 | MOJ | Amber/Red | 2017-03-01 | 2019-12-31 | 0.9 | 0.9 | 0 | 0% | 787.2 |  |  | Government Transformation and Service Delivery | 2.8356 | MOJ_0038_1718-Q4-1819-Q2 |  |  | Joiner
MOJ_0039_1718-Q3 | Prison Education Programme | AR 2019 | 1819-Q2 | MOJ | Amber/Green | 2017-04-01 | 2019-06-30 | 156.5 | 156.5 | 0 | 0% | 1223.2 |  |  | Government Transformation and Service Delivery | 2.2466 | MOJ_0039_1718-Q3-1819-Q2 |  |  | Joiner
MOJ_0040_1718-Q3 | YOUTH JUSTICE REFORM PROGRAMME | AR 2019 | 1819-Q2 | MOJ | Amber | 2016-12-12 | 2022-12-31 | 12.7 | 11.5 | -1.2 | -9.449% | 311.13 |  |  | Government Transformation and Service Delivery | 6.0548 | MOJ_0040_1718-Q3-1819-Q2 |  |  | Joiner
MOJ_0041_1819-Q1 | Prisoner Escort and Custody Services (PECS) Generation 4 | AR 2019 | 1819-Q2 | MOJ | Amber/Red | 2017-04-01 | 2021-03-31 | 2.9 | 2.9 | 0 | 0% | 1622.3 |  |  | Government Transformation and Service Delivery | 4 | MOJ_0041_1819-Q1-1819-Q2 |  |  | Joiner
MOJ_0042_1819-Q2 | Probation Programme | AR 2019 | 1819-Q2 | MOJ | Amber/Red | 2017-10-01 | 2020-03-01 | 385 | 394 | 9 | 2.338% | 1200 |  |  | Government Transformation and Service Delivery | 2.4164 | MOJ_0042_1819-Q2-1819-Q2 |  |  | Joiner
NCA_0001_1415-Q2 | NCA Transformation Programme | AR 2019 | 1819-Q2 | NCA | Amber | 2014-04-01 | 2022-03-31 | 62.8 | 51 | -11.8 | -18.79% | 306.8 |  |  | Government Transformation and Service Delivery | 8.0027 | NCA_0001_1415-Q2-1819-Q2 |  |  | Not new
ONS_0002_1112-Q1 | Census & Data Collection Transformation Programme | AR 2019 | 1819-Q2 | ONS | Amber | 2015-01-01 | 2025-03-31 | 94 | 89.5 | -4.5 | -4.787% | 906.5 |  |  | Government Transformation and Service Delivery | 10.2521 | ONS_0002_1112-Q1-1819-Q2 |  |  | Not new
MOD_0101_1516-Q1 | New Style of Information Technology (Base) | AR 2020 | 1920-Q2 | MOD | Amber/Red | 2015-04-01 | 2022-03-31 | Exempt | Exempt | Exempt | Exempt | Exempt |  |  | ICT | 7.0027 |  |  |  | Not new | David Lynam | To deliver a cost-effective and modern â€˜New Style of ITâ€™ across the Defence estate.
MOD_0110_1718-Q1 | MODnet Evolve | AR 2020 | 1920-Q2 | MOD | Amber/Red | 2016-02-29 | 2021-09-01 | Exempt | Exempt | Exempt | Exempt | Exempt |  |  | ICT | 5.5096 |  |  |  | Not new | David Lynam | Sustain OFFICIAL and SECRET Information Communications and Technology (ICT) services in the Base and Base Overseas environments from the end of the ATLAS New Style of IT (Base) (NSOIT(B)) contract.
MOD_0115_1718-Q2 | Mechanised Infantry Programme | AR 2020 | 1920-Q2 | MOD | Amber | 2018-04-02 | 2032-12-31 | 7.837 | 8.161 | 0.324 | 4.134% | 4663.305 |  |  | Military Capability | 14.7589 |  |  |  | Not new | Simon Hamilton | Delivers agile Mechanised Infantry able to operate at reach, at speed, in complex terrain and with low logistic need.
MOD_0033_1112-Q1 | MARSHALL | AR 2020 | 1920-Q2 | MOD | Amber | 2006-04-03 | 2024-12-31 | 127.259 | 129.152 | 1.893 | 1.488% | 1335.622 |  |  | Military Capability | 18.7589 |  |  |  | Not new | Richard Barrow | Delivering a sustainable Air Traffic Management capability.
MOD_0036_1112-Q1 | Maritime Sustainment Programme | AR 2020 | 1920-Q2 | MOD | Green | 2005-07-25 | 2019-02-28 | 0 | 0.812 | 0.812 |  | 618.808 |  |  | Military Capability | 13.6055 |  |  |  | Not new | D Lamb | The Military Afloat Reach and Sustainability (MARS) Tankers will replace the current single hulled tankers operated by the Royal Fleet Auxiliary.
MOD_0079_1213-Q1 | Lightning Programme | AR 2020 | 1920-Q2 | MOD | Amber | 2001-10-01 | 2035-03-31 | 711.858 | 750.371 | 38.513 | 5.41% | 10393.3 |  |  | Military Capability | 33.5178 |  |  |  | Not new | David Bradshaw | To deliver a multi-role, carrier-capable aircraft, to be operated jointly by the Royal Air Force and Royal Navy.
MOD_0111_1718-Q1 | Joint Crypt Key Programme | AR 2020 | 1920-Q2 | MOD | Exempt | Exempt | Exempt | Exempt | Exempt | Exempt | Exempt | Exempt |  |  | ICT | Exempt |  |  |  | Not new | David Lynam | To support the department's Information Assurance Capability.
MOD_0117_1718-Q2 | Future Maritime Support Programme | AR 2020 | 1920-Q2 | MOD | RED | 2016-09-26 | 2030-03-31 | 14.478 | 20.196 | 5.718 | 39.49% | 11127.659 |  |  | Military Capability | 13.5178 |  |  |  | Not new | Matthew Harrison | Commercial arrangements for the provision of Ship & Submarine Engineering and Naval Base Services.
MOD_0100_1516-Q1 | Future Beyond Line Of Sight | AR 2020 | 1920-Q2 | MOD | Amber/Red | 2011-01-01 | 2041-12-31 | Exempt | Exempt | Exempt | Exempt | Exempt |  |  | ICT | 31.0192 |  |  |  | Not new | Stephen Fisher | Replaces the existing UK sovereign SKYNET 5 secure space-based satellite communications capability.
MOD_0116_1718-Q2 | Fleet Solid Support | AR 2020 | 1920-Q2 | MOD | Amber | 2016-04-01 | 2030-04-30 | 0.657 | 0.657 | 0 | 0% | Exempt |  |  | Military Capability | 14.0877 |  |  |  | Not new | Paul Marshall | Auxiliary Shipping to provide stores, ammunition and food sustainment to Naval Forces at Sea.
MOD_0080_1213-Q1 | DREADNOUGHT | AR 2020 | 1920-Q2 | MOD | Amber | 2011-04-14 | Exempt under Freedom of Information Act 2000 sections 24 (National Security) 26 (Defence) and 35 (Formulation of government policy). | 1613.355 | 1613.356 | 0.001 | 6.198e-05% | 30099.344 |  |  | Military Capability | Exempt |  |  |  | Not new | Timothy Hodgson | The design, development and manufacture of the Dreadnought ballistic missile submarines.
MOD_0114_1718-Q1 | Defence Estate Optimisation | AR 2020 | 1920-Q2 | MOD | Amber/Red | 2016-11-01 | 2041-03-31 | 19.37 | 11.75 | -7.62 | -39.34% | 1754.74 |  |  | Military Capability | 24.4274 |  |  |  | Not new | Sherin Aminossehe | Helping create a smaller, better and a more efficient estate to deliver the required Military Capability.
MOD_0017_1112-Q1 | Crowsnest Programme | AR 2020 | 1920-Q2 | MOD | Red | 2013-03-31 | 2023-06-30 | 87.087 | 75.241 | -11.846 | -13.6% | 429.434 |  |  | Military Capability | 10.2548 |  |  |  | Not new | Adrian Orchard | Equip 10 Merlin Mk2 helicopters with an advanced airborne surveillance system to meet the Force Protection requirement of the Maritime Task Group.
MOD_0078_1213-Q1 | Core Production Capability | AR 2020 | 1920-Q2 | MOD | Amber | 2012-04-01 | 2028-04-30 | 163.577 | 163.107 | -0.47 | -0.2873% | 1826.708 |  |  | Military Capability | 16.0904 |  |  |  | Not new | Tim Hodgson | Delivers safe nuclear reactor cores to meet the Royal Navy's submarine programme, now and for the long term.
MOD_0094_1415-Q3 | Contracting; Purchasing and Finance | AR 2020 | 1920-Q2 | MOD | Amber | 2011-12-01 | 2021-08-13 | 4.97 | 4.894 | -0.076 | -1.529% | 130.202 |  |  | Government Transformation and Service Delivery | 9.7068 |  |  |  | Not new | Lee Rimmer | To provide a single online end to end procurement system for all MOD procurement activity.
MOD_0077_1213-Q1 | Complex Weapons | AR 2020 | 1920-Q2 | MOD | Amber | 2008-03-31 | 2032-04-01 | 755.261 | 728.748 | -26.513 | -3.51% | 28717.221 |  |  | Military Capability | 24.0192 |  |  |  | Not new | John Cunningham | Delivers Complex Weapons for use by the 3 Front Line Commands.
MOD_0118_1718-Q3 | Clyde Infrastructure | AR 2020 | 1920-Q2 | MOD | Amber | 2015-09-07 | 2032-03-30 | 112.7 | 117.7 | 5 | 4% | 1774.573 |  |  | Military Capability | 16.5726 |  |  |  | Not new | Matt Harrison | Managing the design, delivery and transition into operational use, new build and updated infrastructure facilities in HMNB Clyde (Faslane and Coulport).
MOD_0064_1112-Q2 | Carrier Enabled Power Projection | AR 2020 | 1920-Q2 | MOD | Amber | 2011-01-31 | 2030-12-31 | 1.782 | 1.752 | -0.03 | -1.684% | 21.57 |  |  | Military Capability | 19.9288 |  |  |  | Not new | Richard Knighton | An integrated and sustainable joint capability, interoperable with NATO and coalition allies. The project will enable the projection of UK Carrier Strike and Littoral Manoeuvre power, the ability to support a Special Forces raid as well as delivering Humanitarian Assistance and Defence Diplomacy.
MOD_0076_1213-Q1 | Astute Boats 1-7 | AR 2020 | 1920-Q2 | MOD | Amber/Red | Exempt | Exempt | 467.432 | 424.113 | -43.319 | -9.267% | 10769.423 |  |  | Military Capability | Exempt |  |  |  | Not new | Tim Hodgson | The design, development and manufacture of Astute class submarines.
MOD_0085_1314-Q2 | Army Basing Programme | AR 2020 | 1920-Q2 | MOD | Amber/Green | 2013-05-22 | 2021-03-31 | 307.953 | 314.49 | 6.537 | 2.123% | 2270.791 |  |  | Military Capability | 7.863 |  |  |  | Not new | David Southall | An infastructure led transformation programme to enable the Army 2020 structure and withdraw of personnel from Germany.
MOD_0092_1415-Q3 | Armoured Infantry 2026 | AR 2020 | 1920-Q2 | MOD | Amber/Red | 2014-12-04 | 2026-12-31 | Exempt | Exempt | Exempt | Exempt | Exempt |  |  | Military Capability | 12.0822 |  |  |  | Not new | Simon Hamilton | Deliver an Armoured Infantry that is more capable, with enhanced lethality and upgraded situational awareness, better integration with dismounts and improved combined arms cooperation.
MOD_0091_1415-Q3 | Armoured Cavalry 2025 | AR 2020 | 1920-Q2 | MOD | Amber | 2014-12-04 | 2025-04-30 | 694.712 | 643.003 | -51.709 | -7.443% | 6288.95 |  |  | Military Capability | 10.411 |  |  |  | Not new | Simon Hamilton | To deliver an integrated multi-role capability that will include the delivery of the AJAX armoured fighting vehicle and its training solution into service.
MOD_0119_1920-Q2 | Armed Forces Recruitment Project | AR 2020 | 1920-Q2 | MOD | Amber/Red | 2018-03-15 | 2023-02-01 | 5.1 | 5.1 | 0 | 0% | 1730.24 |  |  | Military Capability | 4.8877 |  |  |  | Joiner | Sharon Nesmith | The Armed Forces Recruiting Programme (AFRP) is the tri-Service (tS) programme responsible for delivering a single, common tS Recruiting Op Model for the Armed Forces.
MOD_0001_1112-Q1 | A400M | AR 2020 | 1920-Q2 | MOD | Amber | 2000-05-17 | 2024-03-31 | 197.815 | 186.194 | -11.621 | -5.875% | 3356.227 |  |  | Military Capability | 23.8877 |  |  |  | Not new | Simon EDWARDS | Delivery of A400M ATLAS Air Transport Aircraft.
MOD_0061_1112-Q1 | WATCHKEEPER | AR 2020 | 1920-Q2 | MOD | Amber/Green | 1998-03-01 | 2021-03-31 | 0 | 0.04 | 0.04 | -12.49% | 1117.73 |  |  | Military Capability | 23.0986 |  |  |  | Not new | Michael Dooley | An unmanned air system (UAS) platform that will provide Intelligence, Surveillance, Target Acquisition and Reconnaissance capability to the land tactical commander in the context of Joint Operations.
MOD_0112_1718-Q1 | Type 31e | AR 2020 | 1920-Q2 | MOD | Amber | 2016-04-01 | 2030-02-28 | 13.244 | 12.762 | -0.482 | -3.639% | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) |  |  | Military Capability | 13.9205 |  |  |  | Not new | Paul Marshall | Aims to deliver a pipeline of credible, affordable and exportable warships enabling Defence to increase its global footprint.
MOD_0055_1112-Q1 | Type 26 Global Combat Ship Programme | AR 2020 | 1920-Q2 | MOD | Amber | 2008-07-21 | 2035-05-01 | 502.376 | 502.279 | -0.097 | -0.01931% | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) |  |  | Military Capability | 26.7945 |  |  |  | Not new | Paul Marshall | Procure 8 x Anti Submarine Warfare (ASW) ships and associated support.
MOD_0047_1112-Q1 | Spearfish Upgrade Programme | AR 2020 | 1920-Q2 | MOD | Red | 2008-04-01 | 2024-03-31 | 37.678 | 35.316 | -2.362 | -6.269% | 414.519 |  |  | Military Capability | 16.0082 |  |  |  | Not new | Bob Anstey | To update the UK's submarine weapon systems. This includes improvements to the safety system to minimise residual risks and deliver improved performance against increasingly capable threats.
MOD_0042_1112-Q1 | Queen Elizabeth Programme | AR 2020 | 1920-Q2 | MOD | Amber | 1998-12-01 | 2023-03-31 | 141.625 | 145.273 | 3.648 | 2.576% | 6782.651 |  |  | Military Capability | 24.3452 |  |  |  | Not new | Martin Connell | Deliver 2 x Queen Elizabeth Class aircraft carriers, capable of operating Lightning II and Merlin aircraft (Crowsnest/ASW), as key elements of the Carrier Enabled Power Projection Programme (CEPP).
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | AR 2020 | 1920-Q2 | MOD | Exempt | 2008-04-01 | 2025-04-30 | 1087.997 | 1028.692 | -59.305 | -5.451% | 20900.747 |  |  | Military Capability | 17.0904 |  |  |  | Not new | Paul Hollinshead | To deliver and sustain the capability (skills, technology, science, personnel, production and support) to underwrite the UK nuclear warhead stockpile now and in the future.
MoD_0109_1617-Q2 | New Style of Information Technology Deployed | AR 2020 | 1920-Q2 | MOD | Amber | 2015-04-01 | 2025-03-25 | Exempt | Exempt | Exempt | Exempt | Exempt |  |  | Military Capability | 9.989 |  |  |  | Not new | Andy Fallows | The provision of an IT system which will deliver operational information service to Land, Air, Maritime and Joint users in all physical environments.
MOD_0107_1617-Q1 | PROTECTOR | AR 2020 | 1920-Q2 | MOD | Amber | 2009-04-30 | 2035-03-31 | 127.374 | 140.354 | 12.98 | 10.19% | 1155.839 |  |  | Military Capability | 25.9342 |  |  |  | Not new | Richard Barrow | Delivery of a Remotely Piloted Air System.
MOD_0106_1617-Q1 | Maritime Patrol Aircraft | AR 2020 | 1920-Q2 | MOD | Amber | 2016-06-13 | 2024-04-01 | 437.11 | 513.47 | 76.36 | 11.6% | 2229.59 |  |  | Military Capability | 7.8055 |  |  |  | Not new | Richard Barrow | To deliver a Maritime Patrol Aircraft (MPA) to provide persistent, responsive, effective and adaptive Military Capabilities in the Under Water, Above Water, Littoral and Land environments.
MOD_0105_1617-Q1 | Land Environment Tactical Communication and Information Systems | AR 2020 | 1920-Q2 | MOD | Amber | 2013-10-16 | 2035-12-31 | 235.382 | 238.179 | 2.797 | 1.188% | 11399.76 |  |  | Military Capability | 22.2219 |  |  |  | Not new | Jonathan Cole | A transformational change programme that will 'information-enable' the Land Environment in the full conduct of operations.
MOD_0104_1617-Q1 | Armour MBT 2025 | AR 2020 | 1920-Q2 | MOD | Amber | 2014-12-04 | 2028-07-31 | 12.456 | 11.953 | -0.503 | -4.038% | 1304.188 |  |  | Military Capability | 13.6658 |  |  |  | Not new | Andrew Stuart | An extension of the Armyâ€™s MBT capability as part of a balanced force, credible and employable against current and emerging threats, across the mosaic of conflict, and the identification of future capability options beyond 2035.
BEIS_0004_1920-Q2 | Futured Shared Services Programme | AR 2020 | 1920-Q2 | BEIS | Amber | 2018-11-01 | 2023-05-31 | 32.24 | 32.24 | 0 | 0% | 423.916 |  |  | ICT | 4.5808 |  |  |  | Joiner | Karl Hoods | The Future Shared Services Programme was initiated in 2018, the programme is born out of a need to replace the existing Oracle and Workday platforms
DECC_0010_1112-Q1 | Smart Metering Implementation Programme | AR 2020 | 1920-Q2 | BEIS | Amber | 2009-12-02 | 2024-12-31 | 1065.904 | 1065.904 | 0 | 0% | 20136.9509 |  |  | Infrastructure and Construction | 15.0904 |  |  |  | Not new | Daron Walker | To offer every home and small business a Smart Meter by 2020.
BEIS_0003_1819-Q2 | The Next Magnox Operating Model | AR 2020 | 1920-Q2 | BEIS | Amber/Green | 2017-09-01 | 2019-09-01 | 3 | 3 | 0 | 0% | 5 |  |  | Government Transformation and Service Delivery | 2 |  |  |  | Not new | Alan Cumming | Changing the model for delivery of decommissioning of the Magnox Sites from the current Parent Body Organisation (PBO) model to an NDA Subsidiary Model.
BIS_0014_1415-Q3 | New Polar Research Vessel | AR 2020 | 1920-Q2 | BEIS | Amber | 2014-05-01 | 2022-12-31 | 68 | 64.5 | -3.5 | -5.147% | 1403 |  |  | Infrastructure and Construction | 8.674 |  |  |  | Not new | Nigel Bird | Royal Research Ship Sir David Attenborough will replace two existing polar research/supply vessels with one dual purpose ship which planned to save Â£102m over 30 years
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | AR 2020 | 1920-Q2 | BEIS | Amber | 2012-04-03 | 2019-08-31 | 198 | 192 | -6 | -3.03% | 2782 |  |  | Infrastructure and Construction | 7.4137 |  |  |  | Not new | Alan Cumming | The appointment of a Parent Body Organisation to manage the Magnox and RSRL SLCs to deliver all twelve sites into Care and Maintenance, with a 10% saving, over a 14 year period. The contract has subsequently been terminated and will now deliver a series of Milestones and Termination States over a five year period ending September 2019.
BIS_0015_1516-Q1 | Local Land Charges (LLC) Programme | AR 2020 | 1920-Q2 | BEIS | Amber | 2014-03-01 | 2023-11-17 | 32.5 | 7 | -25.5 | -78.46% | 193.3 |  |  | ICT | 9.7205 |  |  |  | Not new | Karina Singh | The Programme will deliver a single Local Land Charges (LLC) Service for England.
BEIS_0001_1617-Q2 | Heat Networks Investment Project | AR 2020 | 1920-Q2 | BEIS | Amber | 2015-11-25 | 2021-03-31 | 86.6 | 66.9 | -19.7 | -22.75% | 375.9 |  |  | Infrastructure and Construction | 5.3507 |  |  |  | Not new | Dan Osgood | Helping create a self-sustaining heat network market through Â£320m capital investment and short-term actions to address market barriers
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | AR 2020 | 1920-Q2 | BEIS | Amber | 2008-06-30 | 2040-12-31 | 46.522 | 46.522 | 0 | 0% | 12742.997 |  |  | Infrastructure and Construction | 32.526 |  |  |  | Not new | Stephen Speed | To site and construct a Geological Disposal Facility for the disposal for higher activity radioactive waste.
CO_0022_1819-Q4 | Transforming Government Security | AR 2020 | 1920-Q2 | CO | Amber/Green | 2016-10-01 | 2020-04-01 | 12.5 | 12.5 | 0 | 0% | 31.044 |  |  | Government Transformation and Service Delivery | 3.5014 |  |  |  | Joiner | Michael Brennan | Improve security outcomes by raising minimum standards, provide clarity for security across HMG, provide governance and security leadership to enable a better understanding and management of the threats and risks to government and its assets.
CO_0014_1516-Q2 | Government Hubs Programme | AR 2020 | 1920-Q2 | CO | Amber | 2015-05-01 | 2036-03-31 | 19.08 | 19.08 | 0 | 0% | 564.1 |  |  | Government Transformation and Service Delivery | 20.9315 |  |  |  | Not new | Martin Sellar | The Government Hubs Programme will consolidate and modernise the government's office estate, creating an office network that supports smarter working and great places to work.
CO_0019_1617-Q4 | Government as a Platform | AR 2020 | 1920-Q2 | CO | Amber/Green | 2015-12-31 | 2020-03-31 | 17 | 12 | -5 | -29.41% | 90 |  |  | ICT | 4.2521 |  |  |  | Not new | Chris Russell | Development of common platforms for use by digital services across government to avoid duplication of effort.
CO_0015_1516-Q2 | GOV UK Verify | AR 2020 | 1920-Q2 | CO | Red | 2012-04-01 | 2020-03-31 | 3 | 17.9 | 14.9 | 496.7% | 206.1 |  |  | ICT | 8.0027 |  |  |  | Not new | Lisa Barrett | A new way to prove who you are online and for public service providers to be assured you are who you say you are
CO_0018_1617-Q3 | Common Technology Services | AR 2020 | 1920-Q2 | CO | Amber/Green | 2016-04-01 | 2020-03-31 | 4.96 | 1.3 | -3.66 | -73.79% | 44.19 |  |  | Government Transformation and Service Delivery | 4 |  |  |  | Not new | Chris Russell | Enabling Government to transform the way Civil Servants work by supporting departments during the adoption of modern, flexible and secure technology that will increase their efficiency and deliver value for money.
CO_0020_1718-Q4 | Commercial Capability Expansion Programme | AR 2020 | 1920-Q2 | CO | Amber/Red | 2017-04-01 | 2020-03-31 | 2.3 | 3.126 | 0.826 | 35.91% | 11.7 |  |  | Government Transformation and Service Delivery | 3 |  |  |  | Not new | Gareth Rhys Williams | Improve commercial capability across central government and the wider public bodies sector by expanding capability building interventions applied to commercial specialists (at Grade 6 and above) into new target populations.
CO_0023_1920-Q1 | Transforming CCS | AR 2020 | 1920-Q2 | CO | Amber | 2019-04-01 | 2022-03-31 | 8.23 | 7.85 | -0.38 | -4.617% | 28.34 |  |  | Government Transformation and Service Delivery | 3 |  |  |  | Joiner | Simon Tse | The Transforming CCS programme will encompass both digital delivery and organisational transformation to deliver the transformation vision that will transition CCS into a digitally enabled organisation that puts the customer at the heart of everything it does.
DCMS_0014_1920-Q2 | Rural Gigabit Connectivity Programme | AR 2020 | 1920-Q2 | DCMS | Red | 2019-05-01 | 2021-05-01 | 79.5 | 41.059 | -38.441 | -48.35% | 212.8 |  |  | Infrastructure and Construction | 2.0027 |  |  |  | Joiner | Raj Kalia | The Rural Gigabit Connectivity Programme will pilot and test innovative approaches to deploying full fibre in the most difficult to reach areas where the market alone is unlikely to deliver.
DCMS_0012_1819-Q2 | Birmingham 2022 Commonwealth Games | AR 2020 | 1920-Q2 | DCMS | Amber/Red | 2017-12-21 | 2023-03-31 | 63.363 | 34.97 | -28.393 | -44.81% | 777.919 |  |  | Infrastructure and Construction | 5.2767 |  |  |  | Not new | Dean Creamer | Delivery of the Birmingham 2022 Commonwealth Games.
DCMS_0008_1516-Q4 | Blythe House Programme | AR 2020 | 1920-Q2 | DCMS | Amber/Green | 2015-04-01 | 2023-03-31 | 77.7 | 95.69 | 17.99 | 23.15% | 210.239 |  |  | Infrastructure and Construction | 8.0027 |  |  |  | Not new | Dean Creamer | Ensure Blythe House is put to its most efficient and effective use in order to deliver maximum value for money and that its museums are able to care for their collections in the most efficient and effective way.
DCMS_0011_1718-Q3 | 5G Testbeds & Trials | AR 2020 | 1920-Q2 | DCMS | Amber | 2017-02-28 | 2021-03-31 | 67.4 | 37.7 | -29.7 | -44.07% | 232.75 |  |  | Infrastructure and Construction | 4.0877 |  |  |  | Not new | James Heath | To foster, build and lead the development of the UK's 5G ecosystem.
DCMS_0013_1819-Q3 | 4th National Lottery Licence Competition | AR 2020 | 1920-Q2 | DCMS | Amber | 2018-11-16 | 2023-08-01 | 7.84 | 13.208 | 5.368 | 68.47% | 64.339 |  |  | Government Transformation and Service Delivery | 4.7096 |  |  |  | Joiner | John Tanner | The project aims to run a competition to award the next National Lottery licence (4th), that delivers statutory duties of due propriety and player protection, while incentivising responsible innovation and maximising returns to good causes.
DCMS_0010_1718-Q3 | Local Full Fibre Networks | AR 2020 | 1920-Q2 | DCMS | Red | 2017-04-01 | 2021-12-01 | 132.4 | 82.018 | -50.382 | -38.05% | 321.1 |  |  | Infrastructure and Construction | 4.6712 |  |  |  | Not new | Raj Kalia | Designed to stimulate greater commercial investment in full fibre networks across the UK to deliver faster and more reliable connectivity.
DCMS_0009_1516-Q4 | 700 MHz Clearance Programme | AR 2020 | 1920-Q2 | DCMS | Amber/Green | 2015-01-13 | 2022-01-01 | 156 | 94.2 | -61.8 | -39.62% | 595 |  |  | Infrastructure and Construction | 6.9726 |  |  |  | Not new | Raj Kalia | Investing up to Â£600m to clear the 700MHz spectrum by mid-2020 for use for mobile broadband services in the future.
DEFRA_0006_1516-Q1 | DEFRA UNITY PROGRAMME | AR 2020 | 1920-Q2 | DEFRA | Amber | 2014-11-01 | 2020-04-30 | 140.3 | 142.7 | 2.4 | 2% | 1067.6 |  |  | ICT | 5.4986 |  |  |  | Not new | CHRIS HOWES | The Defra UnITy Programme has been established to exploit the opportunity presented from the expiry of its two largest ICTcontracts. The programme will now run until 04/2020 to develop a delivery mechanism leveraging good outcomes in a multi-vendor environment.
DFE_0011_1819-Q2 | Social Work England | AR 2020 | 1920-Q2 | DFE | Amber | 2016-05-09 | 2019-09-30 | 6.591 | 11.003 | 4.412 | 66.94% | 21.311 |  |  | Government Transformation and Service Delivery | 3.3945 |  |  |  | Not new | Sam Olsen | Establishing a new specialist social work regulator, Social Work England, which will focus on public protection and practice improvement.
DFE_0010_1819-Q1 | T Level Programme | AR 2020 | 1920-Q2 | DfE | Amber/Red | 2016-10-25 | 2023-09-30 | 105.6 | 123.6 | 18 | 17.05% | 155.6 |  |  | Government Transformation and Service Delivery | 6.9342 |  |  |  | Not new | Jennifer Coupland | To manage the development and delivery of new T Level qualifications, closure and benefit realisation
DFE_0012_1920-Q1 | Test Operation Services Transition Programme (TOpS) | AR 2020 | 1920-Q2 | DFE | Amber/Red | 2018-09-01 | 2020-03-30 | 10.999 | 11.14 | 0.141 | 1.282% | 125.609 |  |  | Government Transformation and Service Delivery | 1.5781 |  |  |  | Joiner | Una Bennett | Programme of work to move from a multi supplier model to a single supplier model
DFE_0006_1415-Q3 | Priority School Building Programme 2 | AR 2020 | 1920-Q2 | DFE | Amber | 2014-05-01 | 2025-02-25 | 740.8 | 716.22 | -24.58 | -3.318% | 2398.5 |  |  | Infrastructure and Construction | 10.8301 |  |  |  | Not new | Rory Kennedy | Meeting the needs of the school buildings in the very worst condition across the country.
DFE_0009_1617-Q2 | Apprenticeships Reform Programme | AR 2020 | 1920-Q2 | DFE | Amber/Red | 2015-05-08 | 2021-04-01 | 2470.01 | 2182.9994 | -287.0106 | -11.62% | 11347.41 |  |  | Government Transformation and Service Delivery | 5.9041 |  |  |  | Not new | Keith Smith | To create more high quality apprenticeships, meet the skills needs of employers and the country, to create progression for apprentices and to widen participation and social mobility in apprenticeships.
DFID_0001_1112-Q1 | St Helena Airport | AR 2020 | 1920-Q2 | DFID | Amber/Green | 2005-03-15 | 2026-08-31 | 3.9 | 4.54 | 0.64 | 16.41% | 445.72 |  |  | Infrastructure and Construction | 21.4767 |  |  |  | Not new | Alasdair Wardhaugh
DFT_0001_1112-Q1 | Crossrail Programme | AR 2020 | 1920-Q2 | DFT | Red | 2008-07-22 |  | 1137.7 | 1131.2 | -6.5 | -0.5713% | 17630.9 |  |  | Infrastructure and Construction | Crossrail |  |  |  | Not new | Matthew Lodge | A new high-frequency rail service which will increase rail-based capacity in London by up to 10% and cut journey times across London and the South East.
DFT_0033_1819-Q1 | East Coast Mainline Programme | AR 2020 | 1920-Q2 | DFT | Amber | 2014-04-01 | 2023-12-01 | 208.8 | 166.7 | -42.1 | -20% | 1040.4 |  |  | Infrastructure and Construction | 9.674 |  |  |  | Not new | Cavendish Elithorn | Improving capacity and frequency of the services on the East Coast Mainline, increasing passenger seat capacity to major stations along the route, reducing journey times and improving the customer experience through the introduction of new trains.
DFT_0026_1617-Q1 | Great Western Route Modernisation (GWRM) including electrification | AR 2020 | 1920-Q2 | DFT | Amber | 2011-12-01 | 2024-12-31 | 289 | 324 | 35 | 12.11% | 5007 |  |  | Infrastructure and Construction | 13.0932 |  |  |  | Not new | Matthew Lodge | An extensive programme to modernise existing infrastructure on the Great Western mainline. It will create faster and more reliable services, better stations and increased freight capacity.
DFT_0005_1112-Q1 | Intercity Express Programme | AR 2020 | 1920-Q2 | DFT | Amber | 2005-06-01 | 2020-06-04 | 38.46 | 38.11 | -0.35 | -0.91% | 6445.73 |  |  | Infrastructure and Construction | 15.0192 |  |  |  | Not new | Matthew Lodge | Renewing the UK's high speed train fleet on the Great Western and East Coast. Through Train Operating Companies IEP is a key means to deliver the passenger benefits including more capacity, improved reliability, reduced journey times, and better environmental performance.
DFT_0027_1617-Q1 | Midland Main Line Programme | AR 2020 | 1920-Q2 | DFT | Amber | 2011-01-01 | 2024-12-31 | 299.3 | 288.34 | -10.96 | -3.662% | 1671.2 |  |  | Infrastructure and Construction | 14.0082 |  |  |  | Not new | Cavendish Elithorn | Modernisation of the Midland Main Line Route to provide more passenger capacity and reduced journey times into London and between major Midland cities.
DFT_0028_1617-Q1 | North of England Programme | AR 2020 | 1920-Q2 | DFT | Amber/Red | 2009-07-23 | 2022-12-31 | 753 | 251 | -502 | -66.67% | 5849 |  |  | Infrastructure and Construction | 13.4493 |  |  |  | Not new | Cavendish Elithorn | The enhancements provided by the North of England Programme will support economic growth, bring improved journey times, offer additional train services and enable modern trains to run across the North.
DFT_0029_1617-Q1 | South West Route Capacity | AR 2020 | 1920-Q2 | DFT | Amber/Green | 2012-07-16 | 2019-12-31 | 49.42 | 34.16 | -15.26 | -31% | 817.7 |  |  | Infrastructure and Construction | 7.463 |  |  |  | Not new | Matthew Lodge | Programme of infrastructure upgrades and new rolling stock to increase passenger capacity including enhancements works at Waterloo station.
DFT_0016_1112-Q1 | Thameslink Programme | AR 2020 | 1920-Q2 | DFT | Amber | 2005-07-01 | 2026-12-31 | 84.1 | 169.2 | 85.1 | 101.2% | 7269.4 |  |  | Infrastructure and Construction | 21.5151 |  |  |  | Not new | Matthew Lodge | A significantly enhanced high-frequency rail service which will increase rail-based capacity in London and across the wider South East and provide new journey opportunities.
DFT_0021_1314-Q3 | Rail Franchising Programme | AR 2020 | 1920-Q2 | DFT | Amber/Red | 2015-01-15 | 2019-09-14 | 3.17 | 2.12 | -1.05 | -33.12% | 24.47 |  |  | Government Transformation and Service Delivery | 4.6658 |  |  |  | Not new | Peter Wilkinson | To secure the provision of passenger rail services as set out under the Railways Act 1993 (as amended) by letting Rail Franchises.
DFT_0004_1112-Q1 | High Speed Rail Programme (HS2) | AR 2020 | 1920-Q2 | DFT | Red | 2009-01-14 | 2033-12-31 | 3732.5 | 2784.7 | -947.8 |  | 55700 |  |  | Infrastructure and Construction | 24.9781 |  |  |  | Not new | Clive Maxwell | HS2 will form the backbone of the UKâ€™s transport network, connecting eight out of ten of Britainâ€™s largest cities. By making it easier to move between the North, Midlands and South, cutting many journeys by half, HS2 will make it easier for people to live and work where they want.
DfT_0023_1516-Q3 | Heathrow Expansion Programme | AR 2020 | 1920-Q2 | DFT | Amber | 2015-07-01 | 2050-12-31 | 9.38 | 9.375 | -0.005 | 0% | 32607.78 |  |  | Infrastructure and Construction | 35.526 |  |  |  | Not new | Caroline Low | The Heathrow Expansion Programme covers the Government activities to enable delivery of a new Northwest runway at Heathrow Airport (subject to the granting of development consent).
DFT_0025_1617-Q1 | East West Rail Programme (Western Section) | AR 2020 | 1920-Q2 | DFT | Red | 2011-11-30 | 2024-06-30 | 112.1 | 100 | -12.1 | -10.79% | 1091.5 |  |  | Infrastructure and Construction | 12.5918 |  |  |  | Not new | Cavendish Elithorn | The programme will reconstruct and upgrade a partly disused railway between Bicester and Milton Keynes /Bedford allowing for the introduction of new passenger services improving connectivity and journey times along the corridor.
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | AR 2020 | 1920-Q2 | DFT | Green | 2012-09-01 | 2021-09-30 | 401 | 323.2 | -77.8 | -19.4% | 1435.3 |  |  | Infrastructure and Construction | 9.0849 |  |  |  | Not new | Christopher Taylor | To improve the A14 which is a major national and inter-urban regional transport artery between Cambridge and Huntingdon to relieve congestion and support both national and regional economic growth.
DFT_0024_1516-Q4 | A303 Amesbury to Berwick Down | AR 2020 | 1920-Q2 | DFT | Amber | 2014-12-01 | 2028-06-01 | 39.7 | 39.7 | 0 | 0% | 1919.9 |  |  | Infrastructure and Construction | 13.5096 |  |  |  | Not new | Christopher Taylor | Freeflowing dual carriageway replacing the current single lane on the A303 between Amesbury and Berwick down including a twin bored tunnel under the majority of the world heritage site and a northern by-pass of Winterbourne Stoke.
DFT_0031_1819-Q1 | A428 Black Cat to Caxton Gibbet | AR 2020 | 1920-Q2 | DFT | Amber/Green | 2015-04-01 | 2025-04-01 | 11.02 | 19.3 | 8.28 | 75.14% | 809.98 |  |  | Infrastructure and Construction | 10.0082 |  |  |  | Not new | Christopher Taylor | The scheme provides a new off-line two lane dual carriageway between Black Cat roundabout on the A1 in Bedfordshire and Caxton Gibbet roundabout on the A428 in Cambridgeshire.
DFT_0034_1920-Q2 | A12 Chelmsford to A120 Widening | AR 2020 | 1920-Q2 | DfT | Amber | 2015-04-01 | 2028-05-01 | 12.98 | 12.98 | 0 | 0% | 1145.37 |  |  | Infrastructure and Construction | 13.0932 |  |  |  | Joiner | Dean Sporn | A12 Chelmsford to A120 Widening â€“ widening the A12 to three lanes between junction 19 (north of Chelmsford) and junction 25 (A120 interchange).
DfT_0022_1415-Q4 | Lower Thames Crossing | AR 2020 | 1920-Q2 | DFT | Amber | 2014-05-30 | 2028-07-31 | 165 | 165 | 0 | 0% | 6052.2 |  |  | Infrastructure and Construction | 14.1808 |  |  |  | Not new | christopher taylor | A new free-flowing road crossing of the Lower Thames east of Gravesend and Tilbury. It will improve network resilience and the performance of the existing crossings at Dartford enabling local regional and national economic growth.
DH_0063_1819-Q3 | GP IT Futures Programme | AR 2020 | 1920-Q2 | DH | Amber/Red | 2016-09-01 | 2023-03-31 | 35.987 | 50.9548 | 14.9678 | 41.59% | 423.0005 |  |  | ICT | 6.5808 |  |  |  | Joiner | Masood Nazir | The GP IT Futures programme will deliver a new procurement framework, to replace the General Practice Systems of Choice (GPSoC) procurement framework. In so doing, it will create an open, competitive and innovative market with an ultimate goal to creating a world leading health ecosystem which will underpin the requirements set out in the NHS Long Term Plan.
DH_0017_1112-Q1 | PHE Science Hub | AR 2020 | 1920-Q2 | DH | Amber/Red | 2013-06-28 | 2025-06-30 | 311.247 | 188.936 | -122.311 | -39.3% | 2656.318 |  |  | Infrastructure and Construction | 12.0137 |  |  |  | Not new | Richard Gleave | To create an integrated national centre of excellence for public health science, to act as an enabling platform to ensure the scientific expert advice for protection of the publicâ€™s health against threats.
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | AR 2020 | 1920-Q2 | DH | Amber/Red | 2012-01-01 | 2018-05-30 | 48.4526 | 66.6112 | 18.1586 | 37.48% | 1247.2397 |  |  | Government Transformation and Service Delivery | 6.4137 |  |  |  | Not new | Cathy Edwards | Develop NHS Proton Beam Therapy centres to treat patients for whom evidence supports proton therapy as the most clinically effective treatment.
DH_0060_1617-Q1 | NHS UK | AR 2020 | 1920-Q2 | DH | Amber | 2016-04-01 | 2020-12-31 | 9.201 | 8.618 | -0.583 | -6.336% | 54.954 |  |  | Government Transformation and Service Delivery | 4.7534 |  |  |  | Not new | Polly Bishop | Transforming the website NHS Choices, and designing a digital service that better connects patients to the information and services that they need.
DH_0046_1415-Q1 | Medical Examiners Programme | AR 2020 | 1920-Q2 | DH | Amber/Red | 2007-07-24 | 2020-09-30 | 38 | 38 | 0 | 0% | 68.4 |  |  | Government Transformation and Service Delivery | 13.1973 |  |  |  | Not new | Mark Davies | Introducing the role of medical examiners to provide a system of effective medical scrutiny applicable to all deaths that do not require a coronerâ€™s investigation.
DH_0062_1819-Q3 | Local Health and Care Records | AR 2020 | 1920-Q2 | DH | Amber | 2018-03-31 | 2022-03-31 | 55.28 | 28.83 | -26.45 | -47.85% | 763.93 |  |  | ICT | 4.0027 |  |  |  | Joiner | Tim Donohoe | The aim of the programme is to create an information sharing environment that helps our health and care services continually improve the treatments we use, that health and care professionals have access to a comprehensive care record with the information they need to inform their care decisions, when and where they need it, and can empower people to make informed choices about their own health and care. Being able to analyse the data to enable more precise and actionable interventions and support the development of population health management and access to a rich information base of de-personalised and anonymous information to support research into conditions, the development of new treatments, and pathways for care .
DH_0061_1617-Q3 | IT Infrastructure Sourcing Programme | AR 2020 | 1920-Q2 | DH | Red | 2014-12-01 | 2019-06-30 | 19.4 | 22.461 | 3.061 | 15.78% | 121.4 |  |  | ICT | 4.5808 |  |  |  | Not new | Nick O'Reilly | Implementing a mix of internal and external supplier towers and a strengthened retained IT organisation.
DH_0041_1314-Q2 | Health & Social Care Network | AR 2020 | 1920-Q2 | DH | Amber | 2012-03-29 | 2021-03-31 | 75.53 | 71.1 | -4.43 | -5.865% | 392.76 |  |  | ICT | 9.011 |  |  |  | Not new | Tom Denwood | A key transitional stage in achieving the vision of making digital health and social care services ubiquitously available over the internet.
DH_0058_1516-Q4 | Data Processing Services Programme | AR 2020 | 1920-Q2 | DH | Amber | 2015-02-23 | 2020-03-31 | 12.1123 | 12.837 | 0.7247 | 5.983% | 69.4975 |  |  | ICT | 5.1041 |  |  |  | Not new | Tim Donohoe | To deliver a modern data platform (DSP) to improve how NHS Digital manages, analyses and provides access to data for healthcare planning and research.
DH_0065_1819-Q4 | Clinical Triage Platform (CTP) | AR 2020 | 1920-Q2 | DH | Amber | 2016-04-01 | 2021-03-31 | 9.71 | 8.48 | -1.23 | -12.67% | 33.364 |  |  | ICT | 5 |  |  |  | Joiner | Samit Shah | The programmeâ€™s overall aim is to support â€˜first contact resolutionâ€™, that is, to the greatest extent where we can, we should deal with the patientsâ€™ concern there and then, and ensure patients are treated by the most appropriate healthcare professionals in the most appropriate place for their needs.
DWP_0009_1112-Q1 | Universal Credit Programme | AR 2020 | 1920-Q2 | DWP | Amber | 2011-11-17 | 2024-12-31 | 1059.9715 | 1010.2636 | -49.7079 | -4.69% | 12716.9535 |  |  | Government Transformation and Service Delivery | 13.1315 |  |  |  | Not new | Neil Couling | Universal Credit replaces six separate benefits and tax credits for working age people, bringing together in and out of work systems into one, to make work pay.
DWP_0028_1819-Q3 | Health Transformation Programme | AR 2020 | 1920-Q2 | DWP | Red | 2018-03-28 | 2024-03-31 | 87.516 | 66.3818 | -21.1342 | -24.15% | 6598.7639 |  |  | Government Transformation and Service Delivery | 6.0137 |  |  |  | Joiner | James Bolton | To offer a more joined-up service to disabled people, the DWP Health Transformation Programme will be integrating the services that deliver PIP and Work Capability Assessments from 2021.nsform the health and disability services we provide for people with disabilities and health conditions.
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | AR 2020 | 1920-Q2 | DWP | Amber/Green | 2012-04-02 | 2020-12-01 | 99.6789 | 93.2371 | -6.4418 | -6.463% | 1219.8492 |  |  | Government Transformation and Service Delivery | 8.6712 |  |  |  | Not new | Bozena Hillyer | Delivers major transformational outcomes designed to ensure the department manages fraud, error and debt in a systematic way.
FCO_0012_1718-Q4 | Atlas Programme (IPA ID 2410) | AR 2020 | 1920-Q2 | FCO | Amber/Red | 2016-05-01 | 2021-10-31 | 13.2811 | 13.2811 | 0 | 0% | 93.8287 |  |  | ICT | 5.5041 |  |  |  | Not new | Andrew Sanderson | To support the FCO's Diplomacy 20:20 agenda and the Government's shared services strategy through the implementation of a modern Oracle Cloud based Enterprise Resource Planning (ERP) system.
FCO_0010_1617-Q3 | Echo 2 Programme | AR 2020 | 1920-Q2 | FCO | Amber/Red | 2015-09-01 | 2021-09-30 | EXEMPt | EXEPT | - | 0% | EXEMPT |  |  | ICT | 6.0849 |  |  |  | Not new | Stephen Robbins | A joint initiative between DfID, FCO and the British Council to re-procure the current Connectivity and Voice & Video services, covering a network of over 500 offices in over 170 countries.
FCO_0011_1718-Q3 | Washington Embassy Refurbishment | AR 2020 | 1920-Q2 | FCO | Amber | 2017-01-01 | 2022-12-12 | 8 | 8 | 0 | 0% | 118.7 |  |  | Infrastructure and Construction | 5.9479 |  |  |  | Not new | Anthony Whitehead | Refurbishment and upgrading of key buildings on our Washington, USA, compound.
HO_0031_1415-Q1 | Digital Services at the Border (DSAB) | AR 2020 | 1920-Q2 | HO | Amber/Red | 2014-02-12 | 2019-03-31 | 37.7 | 37.7 | 0 | 0% | 452.1 |  |  | ICT | 5.1315 |  |  |  | Not new | John Gillan | To deliver digital services that will provide systems capable of transforming the way that Border Force (BF) and its partners operate.
HO_0029_1314-Q4 | Immigration Platform Technologies (IPT) | AR 2020 | 1920-Q2 | HO | Amber/Red | 2013-04-01 | 2020-09-30 | 30 | 44.34 | 14.34 | 47.8% | 304.95 |  |  | ICT | 7.5041 |  |  |  | Not new | Deborah Chittenden | Delivering the technology and information systems to support the immigration service now and in the future.
HO_0036_1617-Q2 | National Law Enforcement Data Programme (NLEDP) | AR 2020 | 1920-Q2 | HO | Amber/Red | 2014-04-01 | 2023-03-31 | 67.5 | 87.4283 | 19.9283 | 29.52% | 469.4 |  |  | ICT | 9.0027 |  |  |  | Not new | Stephen Webb | Will replace the current Police National Computer (PNC) and Police National Database (PND) systems with one modernised solution.
HO_0033_1415-Q3 | Home Office Biometrics (HOB) Programme | AR 2020 | 1920-Q2 | HO | Amber | 2014-04-01 | 2021-09-30 | 85.56 | 85.56 | 0 | 0% | 869.7 |  |  | ICT | 7.5041 |  |  |  | Not new | Stephen Webb | Home Office wide convergence programme for biometrics within Government, covering border security, law enforcement and intelligence.
HO_0034_1516-Q2 | Cyclamen Project | AR 2020 | 1920-Q2 | HO | Amber/Green | 2014-04-01 | 2020-03-31 | Exempt | Exempt | - | Exempt | Exempt |  |  | Government Transformation and Service Delivery | 6.0027 |  |  |  | Not new | Paul Dean | Cyclamen equipment provides the capability to detect and intercept, and thereby deter the illicit movement of radiological materials into the United Kingdom.
HO_0037_1718-Q1 | Asylum Accommodation and Support Transformation (AAST) | AR 2020 | 1920-Q2 | HO | Amber/Green | 2016-08-29 | 2019-09-03 | 328.58 | 300.07 | -28.51 | -8.677% | 4605 |  |  | Government Transformation and Service Delivery | 3.0137 |  |  |  | Not new | Sean Palmer | Aims to deliver an asylum accommodation and support model which will ensure the safety and security of service users and their host communities and represents value for money for the UK Government, learning the lessons from previous asylum support contracts.
HO_0032_1415-Q1 | Technology Platforms for Tomorrow (TPT) | AR 2020 | 1920-Q2 | HO | Amber | 2014-02-01 | 2019-03-31 | 69.97 | 64.1265 | -5.8435 | -8.351% | 602.57 |  |  | ICT | 5.1616 |  |  |  | Not new | Peter Rose | Delivering modern End User Devices and collaboration tooling, replacing the Departmentâ€™s legacy application estate with the use of cloud services.
HO_0030_1415-Q1 | Metis Programme | AR 2020 | 1920-Q2 | HO | Amber/Red | 2016-09-01 | 2019-06-01 | 53.3 | 56.12 | 2.82 | 5.291% | 290.53 |  |  | ICT | 2.7479 |  |  |  | Not new | Richard Hornby | To move to an updated Enterprise Resource Planning tool (ERP) and a common shared service model to provide transactional human resource (HR), finance (including payroll) and procurement services
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | AR 2020 | 1920-Q2 | HO | Amber/Red | 2011-06-01 | 2022-12-31 | 816.9987 | 816.9987 | 0 | 0% | 9521.9169 |  |  | Infrastructure and Construction | 11.5918 |  |  |  | Not new | Stephen Webb | Aims to replace the mobile communications service used by the three Emergency Services and other public safety users with an Emergency Services Network (ESN).
HO_0038_1819-Q3 | DBS Service Transition | AR 2020 | 1920-Q2 | HO | Amber/Green | 2018-08-01 | 2021-03-31 | 23.12 | 20.75 | -2.37 | -10.25% | 27.43 |  |  | Government Transformation and Service Delivery | 2.6658 |  |  |  | Joiner | Gary Blanchard | The DBS Service Transition Programme has been established to transfer services securely, and in doing so maintain the capability and capacity of DBS to achieve its core responsibilities.
MOJ_0044_1920-Q2 | Prison Technology Transformation Programme (PTTP) | AR 2020 | 1920-Q2 | MoJ | Amber/Red |  |  | 0 | 0 | 0 |  | 0 |  |  | ICT | 0 |  |  |  | Joiner | Adrian Scott | The programme has been commissioned to replace the common technology solution across all public prisons in England and Wales. It will also provide new technology services to HMPPS HQ and Prisons ( Staff/Users) who are still on the legacy â€œQuantumâ€ prison system. Providing staff across the prison service with modern, mobile technology services that are a pleasure to use, and which make their duties easier to perform.
MOJ_0038_1718-Q4 | HMCTS Facilities Management Reprocurement Project (FMRP) | AR 2020 | 1920-Q2 | MOJ | Amber | 2017-03-01 | 2019-12-31 | 0 | 6.38 | 6.38 |  | 1039.53 |  |  | Government Transformation and Service Delivery | 2.8356 |  |  |  | Not new | Tim James | To re-procure replacement contracts for the expiring Total Facilities Management (TFM) contracts which provide services to the HMCTS estate.
MOJ_0040_1718-Q3 | YOUTH JUSTICE REFORM PROGRAMME | AR 2020 | 1920-Q2 | MOJ | Amber/Red | 2016-12-12 | 2022-12-31 | 22.5 | 18.9 | -3.6 | -16% | 345.08 |  |  | Government Transformation and Service Delivery | 6.0548 |  |  |  | Not new | Helga Swidenbank | To make youth custody a place of safety, both for children and those who work there; and to improve the life chances of children in custody.
MoJ_0045_1920-Q2 | Wellingborough New Build Prison | AR 2020 | 1920-Q2 | MoJ | Amber | 2018-08-17 | 2022-06-14 | 189.638 | 122.9856 | -66.6525 | -35.15% | 6316.0146 |  |  | Infrastructure and Construction | 3.8274 |  |  |  | Joiner | Robin Seaton | This project is to design, build and procure private services to operate a new, Category C resettlement prison at Wellingborough.
MOJ_0042_1819-Q2 | Probation Programme | AR 2020 | 1920-Q2 | MOJ | Amber/Red | 2017-10-01 | 2020-03-01 | 617 | 954.7784 | 337.7784 | 54.75% | 8235.2338 |  |  | Government Transformation and Service Delivery | 2.4164 |  |  |  | Not new | Jim Barton | Aims to open commercial discussions with Community Rehabilitation Companies (CRCs) , that run probation services, to agree an option for early termination of contracts by mutual agreement and negotiate amendments to contracts to secure service improvements during an exit period.
MOJ_0039_1718-Q3 | Prison Education Programme | AR 2020 | 1920-Q2 | MOJ | Green | 2017-04-01 | 2019-06-30 | 156.5 | 156.5 | 0 | 0% | 763.3 |  |  | Government Transformation and Service Delivery | 2.2466 |  |  |  | Not new | Adrian Scott | Provision of education services for adult prisons in England.
MOJ_0041_1819-Q1 | Prisoner Escort and Custody Services (PECS) Generation 4 Programme | AR 2020 | 1920-Q2 | MOJ | Amber/Green | 2017-04-01 | 2020-09-30 | 8.14 | 8.34 | 0.2 | 2.457% | 1635.83 |  |  | Government Transformation and Service Delivery | 3.5014 |  |  |  | Not new | Gary Badley | PECS Gen 4 Programme, procures business critical contracts ensuring the continued safe and decent movement of prisoners between police stations, courts & prisons.
MOJ_0032_1617-Q2 | MoJ Future FM | AR 2020 | 1920-Q2 | MOJ | Amber/Red | 2016-07-01 | 2018-04-01 | 83.5 | 74.3 | -9.2 | -11.02% | 430.2 |  |  | Government Transformation and Service Delivery | 1.7507 |  |  |  | Not new | Andy Mills | To re-procure the expiring facilities management contracts which provide services to the shared estates cluster.
MOJ_0028_1314-Q2 | HMCTS Reform | AR 2020 | 1920-Q2 | MOJ | Amber/Red | 2015-12-01 | 2023-12-31 | 263.47 | 244.25 | -19.22 | -7.295% | 2153.17 |  |  | Government Transformation and Service Delivery | 8.0877 |  |  |  | Not new | Susan Acland-Hood | Modernise the infrastructure and deliver a better and more flexible service to court users; modernise and transform courts and tribunal service to increase efficiency, improve service quality and reduce the cost to the tax payer.
MoJ_0043_1920-Q2 | Glen Parva New Build Prison | AR 2020 | 1920-Q2 | MoJ | Amber | 2019-01-31 | 2023-11-05 | 16.0301 | 9.917 | -6.1131 | -38.14% | 6104.77 |  |  | Infrastructure and Construction | 4.7644 |  |  |  | Joiner | Robin Seaton | This project is to design, build and procure private services to operate a new, Category C resettlement prison at Glen Parva.
MOJ_0003_1112-Q1 | Electronic Monitoring | AR 2020 | 1920-Q2 | MOJ | Amber/Red | 2011-05-10 | 2024-08-31 | 70.1 | 90.2401 | 20.1401 | 28.73% | 580.5 |  |  | Government Transformation and Service Delivery | 13.3205 |  |  |  | Not new | Adrian Scott | Implementing a new electronic monitoring system and a service for the day-to-day monitoring of subjects wearing the devices.
NCA_0001_1415-Q2 | NCA Transformation Programme | AR 2020 | 1920-Q2 | NCA | Amber | 2014-04-01 | 2022-03-31 | 480.0614 | 480.0614 | 0 | 0% | 5302.1367 |  |  | Government Transformation and Service Delivery | 8.0027 |  |  |  | Not new | Nina Cope | The NCA's Transformation Programme will deliver the culture, capability and capacity to enable the NCA to be a world-class law enforcement agency, leading the work to cut serious and organised crime.
ONS_0002_1112-Q1 | Census & Data Collection Transformation Programme | AR 2020 | 1920-Q2 | ONS | Amber | 2015-01-01 | 2025-03-31 | 141.521 | 141.521 | 0 | 0% | 905.591 |  |  | Government Transformation and Service Delivery | 10.2521 |  |  |  | Not new | Iain Moore McCormack Bell | Delivering a successful 2021 Census, researching how to make it the last of its kind and transforming the work of ONS in how we collect, process and analyse data.
HMRC_0012_1415-Q1 | Tax Free Childcare | AR 2020 | 1920-Q2 | HMRC | Amber | 2013-09-10 | 2015-12-01 | 45.44 | 41.92 | -3.52 | -8% | 356.87 |  |  | Government Transformation and Service Delivery | 2.2247 |  |  |  | Not new | Angela MacDonald | Responsible for delivering the childcare service through which parents can apply for Tax-Free Childcare and the DfE’s 30 hours free childcare initiative.
HMRC_0014_1415-Q4 | Customs Declaration Services | AR 2020 | 1920-Q2 | HMRC | Amber/Red | 2013-10-16 | 2019-12-31 | 69.92 | 69.92 | 0 | 0% | 334.14 |  |  | ICT | 6.211 |  |  |  | Not new | Jim Harra | To provide a more flexible customs declaration system to meet future needs.
HMRC_0015_1617-Q1 | Building Our Future Locations Programme | AR 2020 | 1920-Q2 | HMRC | Amber/Green | 2016-01-05 | 2026-03-31 | 387.7 | 348.3 | -39.4 | -10% | 2835.9 |  |  | Government Transformation and Service Delivery | 10.2411 |  |  |  | Not new | Justin Holliday | HMRC will be a transformed organisation operating from 13 large, modern Regional Centres (RCs), 5 Specialist Sites and a London Headquarters equipped with the digital infrastructure and training facilities needed to support and motivate our people, and from which we can better serve our customers as an effective, efficient and impartial tax and payments authority.
HMRC_0020_1819-Q3 | Securing our Technical Future | AR 2020 | 1920-Q2 | HMRC | Amber | 2018-04-01 | 2022-06-30 | 86.41 | 85.45 | -0.96 | -1% | 312.06 |  |  | ICT | 4.2493 |  |  |  | Joiner | Denise Dourado | The SOTF Programme has been established to ‘stabilise’ HMRC's current estate which is aged and out of support as a result of limited on-going maintenance; remediating high priority vulnerabilities; exiting our 3 data centres the contracts for which expire in 2022. The programme will migrate all services within the data centres to the new supported platforms, Cloud and Crown Hosting (for physical assets), enabling HMRC to fully exploit the benefits of Cloud and Crown hosting opportunities.
HMRC_0017_1617-Q2 | Making Tax Digital for Business | AR 2020 | 1920-Q2 | HMRC | Amber/Green | 2016-04-01 | 2024-03-31 | 75.26 | 78.96 | 3.7 | 5% | 402.07 |  |  | ICT | 8.0027 |  |  |  | Not new | Ruth Stanier | Delivering modernised IT to digitise tax reporting for businesses and agents and delivering a better customer experience.
Note on F866: Amar Morjaria: Agreed exemption from Amber/Red
Note on I874: Amar Morjaria: Agreed exemption
Note on J874: Amar Morjaria: Agreed exemption. Was £59.40m
Note on M874: Amar Morjaria: Agreed exemption. Was £266.50m
Note on M882: Amar Morjaria: Agreed change from £17215.77m
Note on H889: Amar Morjaria: Agreed change from 31/03/2018
Note on M889: Amar Morjaria: Agreed change from £1920.70m
Note on J897: Amar Morjaria: Agreed change from £371.60m
Note on M897: Amar Morjaria: Agreed change from £1435.30m
Note on I898: Amar Morjaria: Agreed change from £35.3m
Note on J898: Amar Morjaria: Agreed change from £39.80m
Note on J902: Amar Morjaria: Agreed change from £36.40m
Note on M902: Amar Morjaria: Agreed change from £1,098.3m.
Note on H906: Amar Morjaria: Agreed change from 31/12/2018
Note on I922: Amar Morjaria: Agreed change from £165.78m
Note on M922: Amar Morjaria: Agreed change from £1166.38m
Note on H927: Amar Morjaria: Agreed change from 30/06/2018
Note on I928: Amar Morjaria: Agreed change from £30.36m
Note on J928: Amar Morjaria: Agreed change from £3.50m
Note on M928: Amar Morjaria: Agreed change from £203.84m
Note on H932: Amar Morjaria: Agreed change from 05/04/2021
Note on I937: Amar Morjaria: Agreed exemption. Was £100.8m.
Note on J937: Amar Morjaria: Agreed exemption. Was £100.80m
Note on M937: Amar Morjaria: Agreed exemption. Was £14889.2m
Note on H939: Amar Morjaria: Agreed change from 31/03/2017
Note on H943: Amar Morjaria: Agreed change from 31/12/2019
Note on I944: Amar Morjaria: Agreed exempt. Was £27.00m
Note on J944: Amar Morjaria: Agreed exemption. Was £26.50m.
Note on M944: Amar Morjaria: Agreed exemption. Was £173.63m
Note on M949: Amar Morjaria: Agreed exemption. Was £389.57m
Note on M950: Amar Morjaria: Agreed change from £2378.56m
Note on F952: Amar Morjaria: Agreed exemption from Amber/Red
Note on M955: Amar Morjaria: Agreed exemption. Was £23376.6m
Note on I960: Amar Morjaria: Adjusted from £541.04m to £541.08m
Note on H964: Amar Morjaria: Agreed exemption
Note on G967: Amar Morjaria: Agreed change from 04/12/2014
Note on M968: Amar Morjaria: Agreed exemption. Was £1733.24m
Note on I970: Amar Morjaria: Agreed exemption. Was £32.11m
Note on J970: Amar Morjaria: Agreed exemption. Was £15.46m
Note on M970: Amar Morjaria: Agreed exemption. Was £6042.75m
Note on I971: Amar Morjaria: Agreed exemption. Was £254.73
Note on J971: Amar Morjaria: Agreed exemption. Was £222.66m
Note on M971: Amar Morjaria: Agreed exemption. Was £1231.15m
Note on M972: Amar Morjaria: Agreed exemption. Was £744.80m
Note on I976: Amar Morjaria: Agreed exemption. Was £90.56m
Note on J976: Amar Morjaria: Agreed exemption. Was £78.97m.
Note on M976: Amar Morjaria: Agreed exemption. Was £193.1m
Note on M977: Amar Morjaria: Agreed exemption. Was £1374.93m
Note on F978: Amar Morjaria: Agreed exemption from Amber
Note on G978: Amar Morjaria: Agreed exemption
Note on H978: Amar Morjaria: Agreed exemption
Note on I978: Amar Morjaria: Agreed exemption. Was £227.37m
Note on J978: Amar Morjaria: Agreed exemption. Was £125.55m.
Note on M978: Amar Morjaria: Agreed exemption. Was £3561.55m
Note on F979: Amar Morjaria: Agreed exemption from Red
Note on H979: Amar Morjaria: Agreed exemption
Note on I979: Amar Morjaria: Agreed exemption. Was £3.2m
Note on J979: Amar Morjaria: Agreed exemption. Was £3.26m.
Note on M979: Amar Morjaria: Agreed exemption. Was £22.72m
Note on G982: Amar Morjaria: Agreed exemption
Note on H982: Amar Morjaria: Agreed exemption
Note on I982: Amar Morjaria: Agreed exemption. Was £0m
Note on J982: Amar Morjaria: Agreed exemption. Was £0m.
Note on M982: Amar Morjaria: Agreed exemption. Was £0m
Note on G984: Amar Morjaria: Agreed change from 'Missing Data'
Note on H984: Amar Morjaria: Agreed change from "Missing Data"
Note on M996: Amar Morjaria: Agreed change from £306.8m
Note on H1145: Andrew Potthurst: Should be 30/4/2028
Note on K1156: Andrew Potthurst: Should be -£0.04m B=0 F=£0.04
Note on H1157: Andrew Potthurst: Should be 28/2/30
Note on I1189: Andrew Potthurst: Updated from £106.2 due to defra error
Note on M1189: Andrew Potthurst: Changed from £1027.9
Note on M1195: Ravi Mehta: Changed from £285.4
Note on L1197: Andrew Potthurst: changed from -30%
Note on L1202: Andrew Potthurst: changed from +41%
Note on M1227: Andrew Potthurst: applying for exemption

## Sheet2 (hidden)
GMPP ID Number | Project Name | Department | MPA RAG (Departmental RAG used if MPA RAG missing) | Project - Start Date (Latest Approved Start Date) | Project - End Date (Latest Approved End Date) | FY Budget (£m) inc Non Gov | FY Forecast (£m) inc Non Gov | Budget Variance (£m) | Budget Variance (%) | TOTAL BUDGETED WHOLE LIFE COSTS including Non-Government Costs
MOD_0101_1516-Q1 | New Style of Information Technology (Base) | MOD | Amber/Red | 2015-04-01 | 2022-03-31 | Exempt | Exempt | Exempt | Exempt | Exempt
MOD_0110_1718-Q1 | MODnet Evolve | MOD | Amber/Red | 2016-02-29 | 2021-09-01 | Exempt | Exempt | Exempt | Exempt | Exempt
MOD_0115_1718-Q2 | Mechanised Infantry Programme | MOD | Amber | 2018-04-02 | 2032-12-31 | 7.837 | 8.161 | 0.324 | 4.134% | 4663.305
MOD_0033_1112-Q1 | MARSHALL | MOD | Amber | 2006-04-03 | 2024-12-31 | 127.259 | 129.152 | 1.893 | 1.488% | 1335.622
MOD_0036_1112-Q1 | Maritime Sustainment Programme | MOD | Green | 2005-07-25 | 2019-02-28 | 0 | 0.812 | 0.812 |  | 618.808
MOD_0079_1213-Q1 | Lightning Programme | MOD | Amber | 2001-10-01 | 2035-03-31 | 711.858 | 750.371 | 38.513 | 5.41% | 10393.3
MOD_0111_1718-Q1 | Joint Crypt Key Programme | MOD | Exempt | Exempt | Exempt | Exempt | Exempt | Exempt | Exempt | Exempt
MOD_0117_1718-Q2 | Future Maritime Support Programme | MOD | RED | 2016-09-26 | 2030-03-31 | 14.478 | 20.196 | 5.718 | 39.49% | 11127.659
MOD_0100_1516-Q1 | Future Beyond Line Of Sight | MOD | Amber/Red | 2011-01-01 | 2041-12-31 | Exempt | Exempt | Exempt | Exempt | Exempt
MOD_0116_1718-Q2 | Fleet Solid Support | MOD | Amber | 2016-04-01 | 2030-04-30 | 0.657 | 0.657 | 0 | 0% | Exempt
MOD_0080_1213-Q1 | DREADNOUGHT | MOD | Amber | 2011-04-14 | Exempt under Freedom of Information Act 2000 sections 24 (National Security) 26 (Defence) and 35 (Formulation of government policy). | 1613.355 | 1613.356 | 0.001 | 6.198e-05% | 30099.344
MOD_0114_1718-Q1 | Defence Estate Optimisation | MOD | Amber/Red | 2016-11-01 | 2041-03-31 | 19.37 | 11.75 | -7.62 | -39.34% | 1754.74
MOD_0017_1112-Q1 | Crowsnest Programme | MOD | Red | 2013-03-31 | 2023-06-30 | 87.087 | 75.241 | -11.846 | -13.6% | 429.434
MOD_0078_1213-Q1 | Core Production Capability | MOD | Amber | 2012-04-01 | 2028-04-30 | 163.577 | 163.107 | -0.47 | -0.2873% | 1826.708
MOD_0094_1415-Q3 | Contracting; Purchasing and Finance | MOD | Amber | 2011-12-01 | 2021-08-13 | 4.97 | 4.894 | -0.076 | -1.529% | 130.202
MOD_0077_1213-Q1 | Complex Weapons | MOD | Amber | 2008-03-31 | 2032-04-01 | 755.261 | 728.748 | -26.513 | -3.51% | 28717.221
MOD_0118_1718-Q3 | Clyde Infrastructure | MOD | Amber | 2015-09-07 | 2032-03-30 | 112.7 | 117.7 | 5 | 4% | 1774.573
MOD_0064_1112-Q2 | Carrier Enabled Power Projection | MOD | Amber | 2011-01-31 | 2030-12-31 | 1.782 | 1.752 | -0.03 | -1.684% | 21.57
MOD_0076_1213-Q1 | Astute Boats 1-7 | MOD | Amber/Red | Exempt | Exempt | 467.432 | 424.113 | -43.319 | -9.267% | 10769.423
MOD_0085_1314-Q2 | Army Basing Programme | MOD | Amber/Green | 2013-05-22 | 2021-03-31 | 307.953 | 314.49 | 6.537 | 2.123% | 2270.791
MOD_0092_1415-Q3 | Armoured Infantry 2026 | MOD | Amber/Red | 2014-12-04 | 2026-12-31 | Exempt | Exempt | Exempt | Exempt | Exempt
MOD_0091_1415-Q3 | Armoured Cavalry 2025 | MOD | Amber | 2014-12-04 | 2025-04-30 | 694.712 | 643.003 | -51.709 | -7.443% | 6288.95
MOD_0119_1920-Q2 | Armed Forces Recruitment Project | MOD | Amber/Red | 2018-03-15 | 2023-02-01 | 5.1 | 5.1 | 0 | 0% | 1730.24
MOD_0001_1112-Q1 | A400M | MOD | Amber | 2000-05-17 | 2024-03-31 | 197.815 | 186.194 | -11.621 | -5.875% | 3356.227
MOD_0061_1112-Q1 | WATCHKEEPER | MOD | Amber/Green | 1998-03-01 | 2021-03-31 | 0 | 0.04 | 0.04 | -12.49% | 1117.73
MOD_0112_1718-Q1 | Type 31e | MOD | Amber | 2016-04-01 | 2030-02-28 | 13.244 | 12.762 | -0.482 | -3.639% | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests)
MOD_0055_1112-Q1 | Type 26 Global Combat Ship Programme | MOD | Amber | 2008-07-21 | 2035-05-01 | 502.376 | 502.279 | -0.097 | -0.01931% | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests)
MOD_0047_1112-Q1 | Spearfish Upgrade Programme | MOD | Red | 2008-04-01 | 2024-03-31 | 37.678 | 35.316 | -2.362 | -6.269% | 414.519
MOD_0042_1112-Q1 | Queen Elizabeth Programme | MOD | Amber | 1998-12-01 | 2023-03-31 | 141.625 | 145.273 | 3.648 | 2.576% | 6782.651
MOD_0038_1112-Q1 | Nuclear Warhead Capability Sustainment Programme | MOD | Exempt | 2008-04-01 | 2025-04-30 | 1087.997 | 1028.692 | -59.305 | -5.451% | 20900.747
MoD_0109_1617-Q2 | New Style of Information Technology Deployed | MOD | Amber | 2015-04-01 | 2025-03-25 | Exempt | Exempt | Exempt | Exempt | Exempt
MOD_0107_1617-Q1 | PROTECTOR | MOD | Amber | 2009-04-30 | 2035-03-31 | 127.374 | 140.354 | 12.98 | 10.19% | 1155.839
MOD_0106_1617-Q1 | Maritime Patrol Aircraft | MOD | Amber | 2016-06-13 | 2024-04-01 | 437.11 | 513.47 | 76.36 | 11.6% | 2229.59
MOD_0105_1617-Q1 | Land Environment Tactical Communication and Information Systems | MOD | Amber | 2013-10-16 | 2035-12-31 | 235.382 | 238.179 | 2.797 | 1.188% | 11399.76
MOD_0104_1617-Q1 | Armour MBT 2025 | MOD | Amber | 2014-12-04 | 2028-07-31 | 12.456 | 11.953 | -0.503 | -4.038% | 1304.188
BEIS_0004_1920-Q2 | Futured Shared Services Programme | BEIS | Amber | 2018-11-01 | 2023-05-31 | 32.24 | 32.24 | 0 | 0% | 423.916
DECC_0010_1112-Q1 | Smart Metering Implementation Programme | BEIS | Amber | 2009-12-02 | 2024-12-31 | 1065.904 | 1065.904 | 0 | 0% | 20136.9509
BEIS_0003_1819-Q2 | The Next Magnox Operating Model | BEIS | Amber/Green | 2017-09-01 | 2019-09-01 | 3 | 3 | 0 | 0% | 5
BIS_0014_1415-Q3 | New Polar Research Vessel | BEIS | Amber | 2014-05-01 | 2022-12-31 | 68 | 64.5 | -3.5 | -5.147% | 1403
DECC_0013_1213-Q1 | Magnox & RSRL PBO Competition | BEIS | Amber | 2012-04-03 | 2019-08-31 | 198 | 192 | -6 | -3.03% | 2782
BIS_0015_1516-Q1 | Local Land Charges (LLC) Programme | BEIS | Amber | 2014-03-01 | 2023-11-17 | 32.5 | 7 | -25.5 | -78.46% | 193.3
BEIS_0001_1617-Q2 | Heat Networks Investment Project | BEIS | Amber | 2015-11-25 | 2021-03-31 | 86.6 | 66.9 | -19.7 | -22.75% | 375.9
DECC_0005_1112-Q1 | Geological Disposal Facility Programme (GDF) | BEIS | Amber | 2008-06-30 | 2040-12-31 | 46.522 | 46.522 | 0 | 0% | 12742.997
CO_0022_1819-Q4 | Transforming Government Security | CO | Amber/Green | 2016-10-01 | 2020-04-01 | 12.5 | 12.5 | 0 | 0% | 31.044
CO_0014_1516-Q2 | Government Hubs Programme | CO | Amber | 2015-05-01 | 2036-03-31 | 19.08 | 19.08 | 0 | 0% | 564.1
CO_0019_1617-Q4 | Government as a Platform | CO | Amber/Green | 2015-12-31 | 2020-03-31 | 17 | 12 | -5 | -29.41% | 90
CO_0015_1516-Q2 | GOV UK Verify | CO | Red | 2012-04-01 | 2020-03-31 | 3 | 17.9 | 14.9 | 496.7% | 206.1
CO_0018_1617-Q3 | Common Technology Services | CO | Amber/Green | 2016-04-01 | 2020-03-31 | 4.96 | 1.3 | -3.66 | -73.79% | 44.19
CO_0020_1718-Q4 | Commercial Capability Expansion Programme | CO | Amber/Red | 2017-04-01 | 2020-03-31 | 2.3 | 3.126 | 0.826 | 35.91% | 11.7
CO_0023_1920-Q1 | Transforming CCS | CO | Amber | 2019-04-01 | 2022-03-31 | 8.23 | 7.85 | -0.38 | -4.617% | 28.34
DCMS_0014_1920-Q2 | Rural Gigabit Connectivity Programme | DCMS | Red | 2019-05-01 | 2021-05-01 | 79.5 | 41.059 | -38.441 | -48.35% | 212.8
DCMS_0012_1819-Q2 | Birmingham 2022 Commonwealth Games | DCMS | Amber/Red | 2017-12-21 | 2023-03-31 | 63.363 | 34.97 | -28.393 | -44.81% | 777.919
DCMS_0008_1516-Q4 | Blythe House Programme | DCMS | Amber/Green | 2015-04-01 | 2023-03-31 | 77.7 | 95.69 | 17.99 | 23.15% | 210.239
DCMS_0011_1718-Q3 | 5G Testbeds & Trials | DCMS | Amber | 2017-02-28 | 2021-03-31 | 67.4 | 37.7 | -29.7 | -44.07% | 232.75
DCMS_0013_1819-Q3 | 4th National Lottery Licence Competition | DCMS | Amber | 2018-11-16 | 2023-08-01 | 7.84 | 13.208 | 5.368 | 68.47% | 64.339
DCMS_0010_1718-Q3 | Local Full Fibre Networks | DCMS | Red | 2017-04-01 | 2021-12-01 | 132.4 | 82.018 | -50.382 | -38.05% | 321.1
DCMS_0009_1516-Q4 | 700 MHz Clearance Programme | DCMS | Amber/Green | 2015-01-13 | 2022-01-01 | 156 | 94.2 | -61.8 | -39.62% | 595
DEFRA_0006_1516-Q1 | DEFRA UNITY PROGRAMME | DEFRA | Amber | 2014-11-01 | 2020-04-30 | 140.3 | 142.7 | 2.4 | 2% | 1067.6
DFE_0011_1819-Q2 | Social Work England | DFE | Amber | 2016-05-09 | 2019-09-30 | 6.591 | 11.003 | 4.412 | 66.94% | 21.311
DFE_0010_1819-Q1 | T Level Programme | DfE | Amber/Red | 2016-10-25 | 2023-09-30 | 105.6 | 123.6 | 18 | 17.05% | 155.6
DFE_0012_1920-Q1 | Test Operation Services Transition Programme (TOpS) | DFE | Amber/Red | 2018-09-01 | 2020-03-30 | 10.999 | 11.14 | 0.141 | 1.282% | 125.609
DFE_0006_1415-Q3 | Priority School Building Programme 2 | DFE | Amber | 2014-05-01 | 2025-02-25 | 740.8 | 716.22 | -24.58 | -3.318% | 2398.5
DFE_0009_1617-Q2 | Apprenticeships Reform Programme | DFE | Amber/Red | 2015-05-08 | 2021-04-01 | 2470.01 | 2182.9994 | -287.0106 | -11.62% | 11347.41
DFID_0001_1112-Q1 | St Helena Airport | DFID | Amber/Green | 2005-03-15 | 2026-08-31 | 3.9 | 4.54 | 0.64 | 16.41% | 445.72
DFT_0001_1112-Q1 | Crossrail Programme | DFT | Red | 2008-07-22 |  | 1137.7 | 1131.2 | -6.5 | -0.5713% | 17630.9
DFT_0033_1819-Q1 | East Coast Mainline Programme | DFT | Amber | 2014-04-01 | 2023-12-01 | 208.8 | 166.7 | -42.1 | -20% | 1040.4
DFT_0026_1617-Q1 | Great Western Route Modernisation (GWRM) including electrification | DFT | Amber | 2011-12-01 | 2024-12-31 | 289 | 324 | 35 | 12.11% | 5007
DFT_0005_1112-Q1 | Intercity Express Programme | DFT | Amber | 2005-06-01 | 2020-06-04 | 38.46 | 38.11 | -0.35 | -0.91% | 6445.73
DFT_0027_1617-Q1 | Midland Main Line Programme | DFT | Amber | 2011-01-01 | 2024-12-31 | 299.3 | 288.34 | -10.96 | -3.662% | 1671.2
DFT_0028_1617-Q1 | North of England Programme | DFT | Amber/Red | 2009-07-23 | 2022-12-31 | 753 | 251 | -502 | -66.67% | 5849
DFT_0029_1617-Q1 | South West Route Capacity | DFT | Amber/Green | 2012-07-16 | 2019-12-31 | 49.42 | 34.16 | -15.26 | -31% | 817.7
DFT_0016_1112-Q1 | Thameslink Programme | DFT | Amber | 2005-07-01 | 2026-12-31 | 84.1 | 169.2 | 85.1 | 101.2% | 7269.4
DFT_0021_1314-Q3 | Rail Franchising Programme | DFT | Amber/Red | 2015-01-15 | 2019-09-14 | 3.17 | 2.12 | -1.05 | -33.12% | 24.47
DFT_0004_1112-Q1 | High Speed Rail Programme (HS2) | DFT | Red | 2009-01-14 | 2033-12-31 | 3732.5 | 2784.7 | -947.8 |  | 55700
DfT_0023_1516-Q3 | Heathrow Expansion Programme | DFT | Amber | 2015-07-01 | 2050-12-31 | 9.38 | 9.375 | -0.005 | 0% | 32607.78
DFT_0025_1617-Q1 | East West Rail Programme (Western Section) | DFT | Red | 2011-11-30 | 2024-06-30 | 112.1 | 100 | -12.1 | -10.79% | 1091.5
DFT_0020_1314-Q2 | A14 Cambridge to Huntingdon Improvement Scheme | DFT | Green | 2012-09-01 | 2021-09-30 | 401 | 323.2 | -77.8 | -19.4% | 1435.3
DFT_0024_1516-Q4 | A303 Amesbury to Berwick Down | DFT | Amber | 2014-12-01 | 2028-06-01 | 39.7 | 39.7 | 0 | 0% | 1919.9
DFT_0031_1819-Q1 | A428 Black Cat to Caxton Gibbet | DFT | Amber/Green | 2015-04-01 | 2025-04-01 | 11.02 | 19.3 | 8.28 | 75.14% | 809.98
DFT_0034_1920-Q2 | A12 Chelmsford to A120 Widening | DfT | Amber | 2015-04-01 | 2028-05-01 | 12.98 | 12.98 | 0 | 0% | 1145.37
DfT_0022_1415-Q4 | Lower Thames Crossing | DFT | Amber | 2014-05-30 | 2028-07-31 | 165 | 165 | 0 | 0% | 6052.2
DH_0063_1819-Q3 | GP IT Futures Programme | DH | Amber/Red | 2016-09-01 | 2023-03-31 | 35.987 | 50.9548 | 14.9678 | 41.59% | 423.0005
DH_0017_1112-Q1 | PHE Science Hub | DH | Amber/Red | 2013-06-28 | 2025-06-30 | 311.247 | 188.936 | -122.311 | -39.3% | 2656.318
DH_0031_1314-Q1 | National Proton Beam Therapy (PBT) Service Development Programme | DH | Amber/Red | 2012-01-01 | 2018-05-30 | 48.4526 | 66.6112 | 18.1586 | 37.48% | 1247.2397
DH_0060_1617-Q1 | NHS UK | DH | Amber | 2016-04-01 | 2020-12-31 | 9.201 | 8.618 | -0.583 | -6.336% | 54.954
DH_0046_1415-Q1 | Medical Examiners Programme | DH | Amber/Red | 2007-07-24 | 2020-09-30 | 38 | 38 | 0 | 0% | 68.4
DH_0062_1819-Q3 | Local Health and Care Records | DH | Amber | 2018-03-31 | 2022-03-31 | 55.28 | 28.83 | -26.45 | -47.85% | 763.93
DH_0061_1617-Q3 | IT Infrastructure Sourcing Programme | DH | Red | 2014-12-01 | 2019-06-30 | 19.4 | 22.461 | 3.061 | 15.78% | 121.4
DH_0041_1314-Q2 | Health & Social Care Network | DH | Amber | 2012-03-29 | 2021-03-31 | 75.53 | 71.1 | -4.43 | -5.865% | 392.76
DH_0058_1516-Q4 | Data Processing Services Programme | DH | Amber | 2015-02-23 | 2020-03-31 | 12.1123 | 12.837 | 0.7247 | 5.983% | 69.4975
DH_0065_1819-Q4 | Clinical Triage Platform (CTP) | DH | Amber | 2016-04-01 | 2021-03-31 | 9.71 | 8.48 | -1.23 | -12.67% | 33.364
DWP_0009_1112-Q1 | Universal Credit Programme | DWP | Amber | 2011-11-17 | 2024-12-31 | 1059.9715 | 1010.2636 | -49.7079 | -4.69% | 12716.9535
DWP_0028_1819-Q3 | Health Transformation Programme | DWP | Red | 2018-03-28 | 2024-03-31 | 87.516 | 66.3818 | -21.1342 | -24.15% | 6598.7639
DWP_0016_1213-Q2 | Fraud, Error and Debt Programme | DWP | Amber/Green | 2012-04-02 | 2020-12-01 | 99.6789 | 93.2371 | -6.4418 | -6.463% | 1219.8492
FCO_0012_1718-Q4 | Atlas Programme (IPA ID 2410) | FCO | Amber/Red | 2016-05-01 | 2021-10-31 | 13.2811 | 13.2811 | 0 | 0% | 93.8287
FCO_0010_1617-Q3 | Echo 2 Programme | FCO | Amber/Red | 2015-09-01 | 2021-09-30 | EXEMPt | EXEPT | - | 0% | EXEMPT
FCO_0011_1718-Q3 | Washington Embassy Refurbishment | FCO | Amber | 2017-01-01 | 2022-12-12 | 8 | 8 | 0 | 0% | 118.7
HO_0031_1415-Q1 | Digital Services at the Border (DSAB) | HO | Amber/Red | 2014-02-12 | 2019-03-31 | 37.7 | 37.7 | 0 | 0% | 452.1
HO_0029_1314-Q4 | Immigration Platform Technologies (IPT) | HO | Amber/Red | 2013-04-01 | 2020-09-30 | 30 | 44.34 | 14.34 | 47.8% | 304.95
HO_0036_1617-Q2 | National Law Enforcement Data Programme (NLEDP) | HO | Amber/Red | 2014-04-01 | 2023-03-31 | 67.5 | 87.4283 | 19.9283 | 29.52% | 469.4
HO_0033_1415-Q3 | Home Office Biometrics (HOB) Programme | HO | Amber | 2014-04-01 | 2021-09-30 | 85.56 | 85.56 | 0 | 0% | 869.7
HO_0034_1516-Q2 | Cyclamen Project | HO | Amber/Green | 2014-04-01 | 2020-03-31 | Exempt | Exempt | - | Exempt | Exempt
HO_0037_1718-Q1 | Asylum Accommodation and Support Transformation (AAST) | HO | Amber/Green | 2016-08-29 | 2019-09-03 | 328.58 | 300.07 | -28.51 | -8.677% | 4605
HO_0032_1415-Q1 | Technology Platforms for Tomorrow (TPT) | HO | Amber | 2014-02-01 | 2019-03-31 | 69.97 | 64.1265 | -5.8435 | -8.351% | 602.57
HO_0030_1415-Q1 | Metis Programme | HO | Amber/Red | 2016-09-01 | 2019-06-01 | 53.3 | 56.12 | 2.82 | 5.291% | 290.53
HO_0016_1213-Q1 | Emergency Services Mobile Communications Programme (ESMCP) | HO | Amber/Red | 2011-06-01 | 2022-12-31 | 816.9987 | 816.9987 | 0 | 0% | 9521.9169
HO_0038_1819-Q3 | DBS Service Transition | HO | Amber/Green | 2018-08-01 | 2021-03-31 | 23.12 | 20.75 | -2.37 | -10.25% | 27.43
MOJ_0044_1920-Q2 | Prison Technology Transformation Programme (PTTP) | MoJ | Amber/Red |  |  | 0 | 0 | 0 |  | 0
MOJ_0038_1718-Q4 | HMCTS Facilities Management Reprocurement Project (FMRP) | MOJ | Amber | 2017-03-01 | 2019-12-31 | 0 | 6.38 | 6.38 |  | 1039.53
MOJ_0040_1718-Q3 | YOUTH JUSTICE REFORM PROGRAMME | MOJ | Amber/Red | 2016-12-12 | 2022-12-31 | 22.5 | 18.9 | -3.6 | -16% | 345.08
MoJ_0045_1920-Q2 | Wellingborough New Build Prison | MoJ | Amber | 2018-08-17 | 2022-06-14 | 189.638 | 122.9856 | -66.6525 | -35.15% | 6316.0146
MOJ_0042_1819-Q2 | Probation Programme | MOJ | Amber/Red | 2017-10-01 | 2020-03-01 | 617 | 954.7784 | 337.7784 | 54.75% | 8235.2338
MOJ_0039_1718-Q3 | Prison Education Programme | MOJ | Green | 2017-04-01 | 2019-06-30 | 156.5 | 156.5 | 0 | 0% | 763.3
MOJ_0041_1819-Q1 | Prisoner Escort and Custody Services (PECS) Generation 4 Programme | MOJ | Amber/Green | 2017-04-01 | 2020-09-30 | 8.14 | 8.34 | 0.2 | 2.457% | 1635.83
MOJ_0032_1617-Q2 | MoJ Future FM | MOJ | Amber/Red | 2016-07-01 | 2018-04-01 | 83.5 | 74.3 | -9.2 | -11.02% | 430.2
MOJ_0028_1314-Q2 | HMCTS Reform | MOJ | Amber/Red | 2015-12-01 | 2023-12-31 | 263.47 | 244.25 | -19.22 | -7.295% | 2153.17
MoJ_0043_1920-Q2 | Glen Parva New Build Prison | MoJ | Amber | 2019-01-31 | 2023-11-05 | 16.0301 | 9.917 | -6.1131 | -38.14% | 6104.77
MOJ_0003_1112-Q1 | Electronic Monitoring | MOJ | Amber/Red | 2011-05-10 | 2024-08-31 | 70.1 | 90.2401 | 20.1401 | 28.73% | 580.5
NCA_0001_1415-Q2 | NCA Transformation Programme | NCA | Amber | 2014-04-01 | 2022-03-31 | 480.0614 | 480.0614 | 0 | 0% | 5302.1367
ONS_0002_1112-Q1 | Census & Data Collection Transformation Programme | ONS | Amber | 2015-01-01 | 2025-03-31 | 141.521 | 141.521 | 0 | 0% | 905.591
HMRC_0012_1415-Q1 | Tax Free Childcare | HMRC | Amber | 2013-09-10 | 2015-12-01 | 45.44 | 41.92 | -3.52 | -8% | 356.87
HMRC_0014_1415-Q4 | Customs Declaration Services | HMRC | Amber/Red | 2013-10-16 | 2019-12-31 | 69.92 | 69.92 | 0 | 0% | 334.14
HMRC_0015_1617-Q1 | Building Our Future Locations Programme | HMRC | Amber/Green | 2016-01-05 | 2026-03-31 | 387.7 | 348.3 | -39.4 | -10% | 2835.9
HMRC_0020_1819-Q3 | Securing our Technical Future | HMRC | Amber | 2018-04-01 | 2022-06-30 | 86.41 | 85.45 | -0.96 | -1% | 312.06
HMRC_0017_1617-Q2 | Making Tax Digital for Business | HMRC | Amber/Green | 2016-04-01 | 2024-03-31 | 75.26 | 78.96 | 3.7 | 5% | 402.07

## MoJ
GMPP ID Number | MOJ_0003_1112-Q1 | MoJ_0043_1920-Q2 | MOJ_0038_1718-Q4 | MOJ_0028_1314-Q2 | MOJ_0032_1617-Q2 | MOJ_0039_1718-Q3 | MOJ_0044_1920-Q2 | MOJ_0041_1819-Q1 | MOJ_0042_1819-Q2 | MoJ_0045_1920-Q2 | MOJ_0040_1718-Q3
Project Name | Electronic Monitoring | Glen Parva New Build Prison | HMCTS Facilities Management Reprocurement Project (FMRP) | HMCTS Reform | MoJ Future FM | Prison Education Programme | Prison Technology Transformation Programme (PTTP) | Prisoner Escort and Custody Services (PECS) Generation 4 Programme | Probation Programme | Wellingborough New Build Prison | Youth Justice Reform programme
Department | MoJ | MoJ | MoJ | MoJ | MoJ | MoJ | MoJ | MoJ | MoJ | MoJ | MoJ
Description / Aims | Implementing a new electronic monitoring system and a service for the day-to-day monitoring of subjects wearing the devices. | This project is to design, build and procure private services to operate a new, Category C resettlement prison at Glen Parva. | To re-procure replacement contracts for the expiring Total Facilities Management (TFM) contracts which provide services to the HMCTS estate. | Modernise the infrastructure and deliver a better and more flexible service to court users; modernise and transform courts and tribunal service to increase efficiency, improve service quality and reduce the cost to the tax payer. | To re-procure the expiring facilities management contracts which provide services to the shared estates cluster. | Provision of education services for adult prisons in England. | The programme has been commissioned to replace the common technology solution across all public prisons in England and Wales. It will also provide new technology services to HMPPS HQ and Prisons ( Staff/Users) who are still on the legacy Quantum prison system. Providing staff across the prison service with modern, mobile technology services that are a pleasure to use, and which make their duties easier to perform. | PECS Gen 4 Programme, procures business critical contracts ensuring the continued safe and decent movement of prisoners between police stations, courts & prisons. | Aims to open commercial discussions with Community Rehabilitation Companies (CRCs) , that run probation services, to agree an option for early termination of contracts by mutual agreement and negotiate amendments to contracts to secure service improvements during an exit period. | This project is to design, build and procure private services to operate a new, Category C resettlement prison at Wellingborough. | To make youth custody a place of safety, both for children and those who work there; and to improve the life chances of children in custody.
IPA Delivery Confidence Assessment (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the IPA Annual Report on Major Projects) | Amber/Red | Amber | Amber | Amber/Red | Amber/Red | Green | Amber/Red | Amber/Green | Amber/Red | Amber | Amber/Red
Departmental commentary on actions planned or taken on the IPA RAG rating. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, which has declined since last year’s Q2 1819 Amber/Green, due primarily to the following factors; - Systems Integration Testing has fallen behind schedule with numerous defects not resolved in a timely manner - Difficulties in the working relationship with suppliers hampered collaboration and diverted attention to conflict resolution Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - The General Election and the accompanying Purdah period delayed conclusion of the Settlement Agreement with our primary supplier. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - The Programme plan was rebaselined in response to Programme delays in order to better reflect the reality of the Programme and improve the tracking of milestones and deliverables - The Settlement Agreement was signed with suppliers, committing both sides to a newly collaborative relationship - Testing was re-started, with Systems Integration Testing ongoing and planning for User Acceptance Testing underway | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber, due primarily to the following factors; - The project was on track and within budget profile. Some risks remained whilst contract plans were being agreed. - Design is progressing through RIBA (Royal Institute of British Architects) plan of work based on lessons learned from Wellingborough design. - Some risks remain until contractor plans agreed and other e.g. ground related could occur Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - Covid-19 presents the biggest risk to the project; the extent of this impact is currently unclear. At present design milestones are on track and The contractor has issued two Early Warning Notices Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - Early orders and early works packages have been agreed to de-risk the main works programme. Early works are due to begin in July and these are essential for meeting the overall programme end date. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber, which has improved since last year’s Q2 1819 Amber/Red, due primarily to the following factors; - The Project has undergone three Assurance reviews since September '18. The last a Delivery Confidence Assessment (DCA) rating of Amber was returned. - The Projects Full Business Case was approved by the Lord Chancellor & Secretary of State for Justice on 24th September 2019 and was subsequently been approved by Cabinet Office and HM Treasury. Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - The Full Business Case (FBC) was approved by Cabinet Office on 11th October 2019 and by HM Treasury on 14th October 2019. - Following the approval of the FBC the new National FM and Security Services Contracts were successfully launched on 1st April 2020. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, which has not changed since last year’s Q2 1819 Amber/Red, due primarily to the following factors; - By Q2 1920 we had delivered most of what we had planned, but reform remains an extremely challenging and complex programme. It proved challenging to hire software developers for the Civil, Family and Tribunals programme which resulted in delay to the delivery of some services and associated benefits. - Establishing a set of common capabilities that would support all the Civil, Family and Tribunal services proved challenging, and let to a change in strategy to ensure that we can use the common capabilities to run end to end services. - There were delays in the delivery of the common platform, which were caused by dependencies with other government agencies and challenges to the pace of software development. We have worked hard to implement a number of changes to pull back this delay. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - The impact of IR35 assessments has meant that we have been unable to keep a lot of our experienced contractor resource, which has had an impact on delivery. - COVID-19 has had a significant impact on the programme, with some productivity expected to be lost due to a lack of co-working and an increase in staff absences. A number of programme resources have been re-prioritised to support operational staff and the rollout of video and audio hearing capabilities. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - In late 2019 Reform reorganised part of its structure and created two new programmes: Future Hearings, which focuses on enabling work to be heard in new efficient and effective ways, and Future Operations, which focuses on defining our new way of running the organisation including the Service Centres. - Civil, Family and Tribunal programme continues to deliver products more slowly than expected. To address, CFT have agreed to a new approach, resequencing work to focus on completing both the Common Component and service elements of a single service (services already in delivery will continue as now). - We have opened a third Courts and Tribunals Service Centre (CTSC) in early 2020. This allows us to provide better services to users but also requires additional work, especially considering the impacts of COVID-19. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, which has not changed since last year’s Q2 1819 Amber/Red, due primarily to the following factors; - This project closed in October 2019. The anticipated savings were not made and we are now running a strand of work FM Strategy Programme that is assisting with the improvements on the existing contract. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - The project was deemed closed by MoJ and IPA as of 1st October 2019. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - The project closed in October 2019. A review was undertaken and we are now looking at key activities to improve the current contract and set up for success in the new one. Key activities include.• Review of in house FM team organisation and processes leading to implementation of improvement plan increasing in-house FM resource managing FM supply chain and contractual deliverables. Expecting resource increase by approximately 30%. • Individual FM supply chain and integrator contract reviews commencing May 2020 to drive improvements for remaining life of the contracts and inform future contracts. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Green, which has improved since last year’s Q2 1819 Amber/Green, due primarily to the following factors; - The programme successfully delivered all elements of the Prison Education Framework (PEF) programme plan, successfully mobilising all four suppliers appointed under the framework contracts with minimal issues encountered. - The programme successfully introduced the Dynamic Purchasing System (DPS) designed to encourage small local suppliers into the market. A range of suppliers have been appointed to the DPS framework and call-off contracts for the provision of services have commenced. Since the Q2 1920 (30th September 2019) Green IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - The programme has now closed following successful delivery of all elements of the programme plan, as such, no project actions have been undertaken which might impact the original Q2 IPA DCA. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, due primarily to the following factors; - HMT Approval had not yet been provided and there was uncertainty in relation to available funding - The programme team was embryonic and additional capacity and capability was needed - The recommendations and concerns around programme being fully scoped needed to be addressed Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - COVID19 has impacted technical resource availability - Ability to identify and onbboard specialist technical resources at pace Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - HMT approval for the OBC was gained in Jan 2020 and funding was secured for 2019/20 and 2020/21 - The programme team has been bolstered with critical roles now filled and additional capacity and capability sourced - Key programme artefacts to manage and control delivery have been delivered, including: Governance framework has been established to support decision making and to oversee the programme at the right level. The programme has undertaken significant planning activities, to identify key milestones and critical path to produce High Level Designs for a Technical Roadmap and Delivery Plan | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Green, which has improved since last year’s Q2 1819 Amber/Red, due primarily to the following factors; - Supplier BAFO bids received, winning bidders selected and Full Business Case (FBC) completed my mid-July. FBC cleared all internal approvals and sent to Cabinet Office for final approval on schedule, mid-September. - Outstanding modelling assumptions agreed and Target Operating Model signed-off. Specifications finalised and future service deemed affordable. - Mobilisation preparation and planning underway. Digital deliverables and timetable agreed including clearly defined Minimum Viable Product (MVP). Since the Q2 1920 (30th September 2019) Amber/Green IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - Improved modelling in programmes/projects that we had dependencies on for future move volume assumptions. - Collaboration from Cabinet Office Market and Suppliers Team on the proposed Payment Mechanism and their agreement to proceed. Since the Q2 1920 (30th September 2019) Amber/Green IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - Good progress on the Commercial timetable and completion of successful negotiations with suppliers. Agreement to and refinement of improved service specifications, including a significantly changed digital specification from Gen 3. - Robust management of the FBC approvals timetable, including early and pro-active work with approvers to discuss FBC content ahead of presentations and address potential blockers in advance. - Digital contractor team in place and products in development and testing. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, which has not changed since last year’s Q2 1819 Amber/Red, due primarily to the following factors; - Since the DCA Q2 1819 Amber/Red rating, considerable progress has been made to expand the team, including the appointment of external delivery partners, and improved governance. However, this programme has inherent risk. We are implementing a transition to a significantly different commercial model in the context of contracts that are operationally and commercially fragile. The timeline to achieve this transition has, on existing plans, negligible contingency. - There are decisions around the Dynamic Framework, Accelerated Transition and potential contract extensions which mean the baseline will have to be reassessed and we cannot therefore be confident in moving the programme status to Amber at this stage. Work is needed to: Complete discussions with CRCs on the potential early transition of case management in parts of England. Complete in-housing of offender management in Wales in December. Develop workforce strategy for probation, including the scope, policy direction and delivery plans for the Professional Recognition Programme. - The programme received an Amber/Red rating for its Programme Assurance Review which took place from 23- 27 Sept. The Review Team identified and praised the significant progress made since the last review but the Review Team concluded that the DCA should remain Amber / Red. the Review sighted that risk assessed plans need to be developed by workstream owners to give greater confidence in the delivery date and an opportunity to work up a more structured benefit delivery case, with some optionality on the balance of investment. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - The announcement of the General Election resulted in an impact assessment of the programme timeline. We planned to publish the OJEU for the Probation Delivery Partner competition in early November 2019. Any event which leads to delays in obtaining approval to proceed and therefore delaying the publication of OJEU later than 16th December 2019 would have significant impact on the Programme’s ability to deliver the transition to new providers by the due date. - Recruitment of an additional 20,000 police officers - the impacts and effects flowing from this will affect the Programme Business Case and is therefore a factor that must be taken into account in assessing the overall DCA rating Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - Consideration of plans to extend current Community Rehabilitation Contracts (CRCs) to end of June 2021 has meant that a change from DCA Amber / Red to Amber was not viable due to the risks associated with enacting the extension - The need for optimising governance structures to enable quicker decision-making; strengthening the benefits case and developing more risk assessed Programme plans. Detailing more supporting analysis of the end-state costs and Offender Management (OM) transition plans. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber, due primarily to the following factors; - Construction has encountered minor delays due to asbestos found on site but no significant delays to completion are expected. Operator Competition was on track to award Summer 2020. - IPA attendance at the New Prisons Board provide external challenge and support to delivery. - The contract with Kier for the construction of the new prison at Wellingborough was signed in April, and work began on site in May, with the first prisoner expected in Autumn 2021. Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - Covid-19 is limiting our capacity to make up lost time, putting pressure on the remaining programme and budget for delivery. A management plan has been implemented as well as issuing early warning notices have been issued by the contractor notifying HMPPS of this risk. - Adverse weather in February caused a delay of 5 days to the programme. Mitigation plans were put in place and has so far reduced this delay by 2 days. | The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, which has declined since last year’s Q2 1819 Amber, due primarily to the following factors; - Secure Children Home registration - The previous Medway building design was highly unlikely to achieve Children's Home registration. - Charitable status - Concerns remain regarding the secure school achieving charitable status. - Invitation to tender - The impact of SCH and charitable status delayed refurbishment timelines. The ITT could not launch until the scope of works were agreed. Therefore, seeking approval for additional funding for refurbishment remained unidentified. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; - The delivery of the secure school has become a manifesto commitment since December 2019. Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; - Following extensive engagement with key stakeholders, we now have a revised building design for the Medway site. - Charitable status options continue to be explored.
Project - Start Date (Latest Approved Start Date) | 2011-05-10 | 2019-01-31 | 2017-03-01 | 2016-12-01 | 2016-07-01 | 2017-04-01 | Data Not Provided | 2017-04-01 | 2017-10-01 | 2018-08-17 | 2016-12-12
Project - End Date (Latest Approved End Date) | 2024-08-31 | 2023-11-05 | 2019-12-31 | 2023-12-31 | 2018-04-01 | 2019-06-30 | Data Not Provided | 2020-09-30 | 2021-04-01 | 2022-06-14 | 2022-12-31
Departmental narrative on schedule, including any deviation from planned schedule (if necessary) | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 31/08/24, has not changed since last year's Q2 1819 date of 31/08/24, due primarily to the following factors; - Continual optimisation work was performed on the Programme plan in order to maintain the Programme end date - Consistent work was done on costing and finance estimates in order to ensure that the Programme end date was affected as little as possible by delays - The decision was taken to release a Minimum Viable Product, which achieved the Programme’s primary objective and decreased the amount of work to be completed between the rebaselining of the Programme plan and the Programme end date Since the Q2 1920 (30th September 2019) baseline project end date of 31/08/24, the following non-project operating environment activities have impacted the original Q2 baseline project end date; - There was a risk that a General Election and the accompanying Purdah period could have prevented the programme from reaching agreement with suppliers and therefore have delayed the signing of the Settlement Agreement. This could have put the Programme further behind schedule and have had financial implications as a result of the delay compensation included in the Agreement Since the Q2 1920 (30th September 2019) baseline project end date of 31/08/24, the following primary project actions have impacted the original Q2 baseline project end date; - The Programme plan was rebaselined in response to programme delays. Optimisation work was done and the Programme collaborated extensively with suppliers to ensure that both sides were committed to delivery - The Settlement Agreement was signed with suppliers, committing both sides to a newly collaborative relationship, providing compensation to the Authority for delays incurred and changing future payment schedules to de-risk further slippage | The scheduled project end date at Q2 1920 (30th September 2019) is 05/11/23, due primarily to the following factors; - The prison is due to accept the first intake of prisoners in May 2023. This is the Service Commencement Date (SCD). Since the Q2 1920 (30th September 2019) baseline project end date of 05/11/23, the following non-project operating environment activities have impacted the original Q2 baseline project end date; - Covid-19 is impacting our programme and the project end date could be affected as a result of this. Since the Q2 1920 (30th September 2019) baseline project end date of 05/11/23, the following primary project actions have impacted the original Q2 baseline project end date; - In November 2019, the project board agreed that handover to BAU date would be provisionally set for 3 months post-SCD. This is currently forecasted as May 2023 and we are working to mitigate any potential impact of Covid-19. | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 31/12/19, has not changed since last year's Q2 1819 date of 31/12/19, due primarily to the following factors; - The Project end was revised to 30th May 2020 in September 2019 however due to the timing of the reporting cycle this was not reflected in the return. The end date for the project is now July 2020. - The Procurement stage of the Project took longer than planned resulting in the requirement to revised the Project end date. Since the Q2 1920 (30th September 2019) baseline project end date of 31/12/19, the following primary project actions have impacted the original Q2 baseline project end date; - The Procurement stage of the Project took longer than planned resulting in the requirement to revised the Project end date. | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 31/12/23, has lengthened by 1370 days since last year's Q2 1819 date of 31/03/20, due primarily to the following factors; - The decision was made to extend the programme following an internal review as part of the programme's most recent Portfolio Business case, which suggested that extension would ensure an effective transition from legacy services to reformed services and to develop the underpinning support for these new services. - Extension allows us to ensure changes to the physical court estate consequent on reform take place only when we can demonstrate that the programme has delivered the enabling changes, as per the recommendations of the Public Accounts Committee (PAC). - The extension to reform is not expected to impact on the programme's overall budget. Since the Q2 1920 (30th September 2019) baseline project end date of 31/12/23, the following non-project operating environment activities have impacted the original Q2 baseline project end date; - The ongoing impact of COVID-19 may change the timetable of reform, but the extent of this change is yet to be determined. Since the Q2 1920 (30th September 2019) baseline project end date of 31/12/23, the following primary project actions have impacted the original Q2 baseline project end date; - No change. | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 01/04/18, has not changed since last year's Q2 1819 date of 01/04/18, due primarily to the following factors; - At this time the contracts had gone live so the project was coming to the end therefore there was very few people remaining in the project team. The project was already nearing the end of MOJ and IPA closure process at this time. Since the Q2 1920 (30th September 2019) baseline project end date of 01/04/18, the following non-project operating environment activities have impacted the original Q2 baseline project end date; - The project closed in October 2019 Since the Q2 1920 (30th September 2019) baseline project end date of 01/04/18, the following primary project actions have impacted the original Q2 baseline project end date; - The project closed in October 2019. A review was undertaken and we are now looking at key activities to improve the current contract and set up for success in the new one. Key activities include.• Review of in house FM team organisation and processes leading to implementation of improvement plan increasing in-house FM resource managing FM supply chain and contractual deliverables. Expecting resource increase by approximately 30%. • Individual FM supply chain and integrator contract reviews commencing May 2020 to drive improvements for remaining life of the contracts and inform future contracts. | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 30/06/19, has not changed since last year's Q2 1819 date of 30/06/19, due primarily to the following factors; - The baseline programme end date has not changed due to the programme team successfully delivering all programme objectives in line with forecast programme timelines. - As the programme has closed, no changes to the forecast end date are applicable. Since the Q2 1920 (30th September 2019) baseline project end date of 30/06/19, the following primary project actions have impacted the original Q2 baseline project end date; - No project actions have been undertaken or impacted the timelines as the programme has closed. | Due to HMT approval not being granted until Q4 no scheduled dates were provided for this project. [Note: HMT approval was gained - January 2020] | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 30/09/20, has shortened by 182 days since last year's Q2 1819 date of 31/03/21, due primarily to the following factors; - It has lengthened by 182 days not shortened. Qrt2 18 showed project closure as 30/09/20 and Qrt2 19 shows closure as 31/03/21. Qtr. 2 19 return states "Recent allocation of digital funding and resultant likely business benefits change activity expected to extend the programme closure date". - Delays to the Commercial timetable due to delayed approval from Cabinet Office on the proposed Payment Mechanism. - Request from Suppliers for more time to complete bids as a result of ITN being split in to two phases to minimise the delays from publication of the Payment Mechanism. Since the Q2 1920 (30th September 2019) baseline project end date of 30/09/20, the following non-project operating environment activities have impacted the original Q2 baseline project end date; - Delayed allocation of Digital funding for required work. - Delayed Cabinet Office approval of the Payment Mechanism. Since the Q2 1920 (30th September 2019) baseline project end date of 30/09/20, the following primary project actions have impacted the original Q2 baseline project end date; - Mobilisation planning identified a need for continued programme support of business change activities beyond Go-Live. - Original programme planning had not considered Gate 5 and programme closure activities in sufficient detail to forecast official closure beyond Go-Live date for new service. - Revised budget planning has allowed for programme continuation post Go-Live. | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 01/04/21, has lengthened by 396 days since last year's Q2 1819 date of 01/03/20, due primarily to the following factors; - Previous business cases considered alternative options to the Unified Model including a full inhouse option, a re-procurement of CRC contracts and an option that adopted the UM in Wales, and a re-procurement option in England, but these have since been ruled out. The baseline end date has been re-assessed based on the preferred option of a Unified Model - Extension of the current Community Rehabilitation Companies (CRCs) - To ensure adequate time to complete competition to put in place new CRC providers; to subsequently ensure a safe and effective mobilisation to new provider; and to provide contingency to ensure effective transition to the new Target Operating Model. Since the Q2 1920 (30th September 2019) baseline project end date of 01/04/21, the following non-project operating environment activities have impacted the original Q2 baseline project end date; - The numbers are heavily based on assumptions until a more detailed model has been available. Numbers are still to be finalised hence the baseline is still subject to SR negotiations but forecast has been raised as pressure risk to HMPPS. Since the Q2 1920 (30th September 2019) baseline project end date of 01/04/21, the following primary project actions have impacted the original Q2 baseline project end date; - Decision to extend current CRC contracts. | The scheduled project end date at Q2 1920 (30th September 2019) is 14/06/22, due primarily to the following factors; - The prison is due to accept the first intake of prisoners in December 2021. This is the Service Commencement Date (SCD). The mobilisation phase of the project was due to complete 6 months post SCD. Since the Q2 1920 (30th September 2019) baseline project end date of 14/06/22, the following non-project operating environment activities have impacted the original Q2 baseline project end date; - Covid-19 is impacting our programme and the project end date is at risk as a result of this. Since the Q2 1920 (30th September 2019) baseline project end date of 14/06/22, the following primary project actions have impacted the original Q2 baseline project end date; - In November 2019, the project board agreed that handover to BAU date would be provisionally set for 3 months post-SCD. This is currently forecasted as December 2021 and we are working to mitigate any potential impact of Covid-19. | The scheduled baseline project end date at Q2 1920 (30th September 2019) is 31/12/22, has not changed since last year's Q2 1819 date of 31/12/22, due primarily to the following factors; - Reform programme scheduled to end as detailed in SOBC - Reform programme has not been rebaselined as on target to complete 31/12/2022, as reported in Q2 2019/20
Financial Year Baseline (£m) (including Non-Government Costs) | 70.1 | 16.0301 | 4.46 | 263.47 | 83.5 | 156.5 | Data Not Provided | 8.14 | 617 | 189.638 | 22.5
Financial Year Forecast (£m) (including Non-Government Costs) | 90.2401 | 9.917 | 6.38 | 244.25 | 74.3 | 156.5 | Data Not Provided | 8.34 | 954.7784 | 122.9856 | 18.9
Financial Year Variance (%) | 28.73% | -38.14% | 43% | -7.295% | -11.02% | 0% | Data Not Provided | 2.457% | 54.75% | -35.15% | -16%
TOTAL Baseline Whole Life Costs (£m) (including Non-Government Costs) | 580.5 | 6104.77 | 1039.53 | 2153.17 | 430.2 | 763.3 | Data Not Provided | 1635.83 | 8235.2338 | 6316.0146 | 345.08
Departmental narrative on budget/forecast variance for 2018/19 (if variance is more than 5%) | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of 29%, is due primarily to the following factors; - The increase in spend against previous forecast reflects delays in programme go live, resulting in ongoing requirements for supplier mobilisation and programme teams. Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 29%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; - The forecast is sensitive to the number of subjects on the caseload, which will have a consequential impact on costs. Volumes will be reforecast in line with the standard timetable. Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 29%, the following primary project actions have impacted the original Q2 19/20 in-year variance; - The achievement of a settlement agreement and assurances on maintaining forecast price reductions provides some mitigation to cost increases due to delay | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -38%, is due primarily to the following factors; - The pre-construction services contract was agreed several months later than assumed in the baseline Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -38%, the following primary project actions have impacted the original Q2 19/20 in-year variance; - The pre-construction services contract was agreed several months later than assumed in the baseline | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of 100%, is due primarily to the following factors; - In-year Baseline at 19/20 Q2 was £4.46m - the variance between the forecast and in-year baseline is due to the start date of the contract being pushed back which resulted in increase staff and mobilisation costs. | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -7%, is due primarily to the following factors; - The 7% drop is attributable to slippage across the programme. Resource DEL underspend on Voluntary Exit Departures (VEDs) (£6m), career transition (£1m), property sales slippage (£2m) and a reduction in our contingency forecast (£2m). - Transfer of sales proceeds into from 2018/19 into 2019/20 (£10m) which was offset by small overspend in projects across the portfolio (£3m). Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -7%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; - External factors meant property sales slipped and didn't materialise in line with expectations. Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -7%, the following primary project actions have impacted the original Q2 19/20 in-year variance; - Expectation that staff would exit the organisation didn't materialise as they were largely able to find roles in the newly stood up service centres. - Project delivery slipped meaning the required technology was not in place to allow new online systems to go live. This resulted in unplanned staff retention. | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -11%, is due primarily to the following factors; - It is recognised that the initial bid information in relation to both the number of assets (circa 40% higher) and the NIA (circa 20% higher) was incorrect; this affected the Target Operating Model and has therefore not led to the achievement of savings that were expected Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -11%, the following primary project actions have impacted the original Q2 19/20 in-year variance; - The project closed in October 2019 | Budget variance less than 5% | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -, is due primarily to the following factors; - Due to HMT approval not being in place at Q2 we cannot report on this but we will be able to report in the next annual report return Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; - Delays in delivery of £2.1M of hardware from overseas due to COVID-19. Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -, the following primary project actions have impacted the original Q2 19/20 in-year variance; - Seed funding of £20m was identified within HMPPS and MoJ for the programme in 2019/20, of which £5.3m had been used by 31/03/2020. - Variance is due to time taken to recruit and onboard suppliers and wider team members. | Budget variance less than 5% | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of 55%, is due primarily to the following factors; - The costs were heavily based on assumptions until a more detailed model has been available. Prominent changes to the service design assumptions since the previous Outline Business Case was produced include a revision to the resettlement model, updated assumptions on the eligibility for interventions on the dynamic framework and revisions to what it will cost to transition to the UM. Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 55%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; - The Government Policy to recruitment of 20,000 police officers has an impact on the original forecast. Based on our initial workforce assumptions, we anticipate we will need to factor in additional recruitment on top of 'Business A Usual' staffing levels to effectively respond to this increase in demand. Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 55%, the following primary project actions have impacted the original Q2 19/20 in-year variance; - Changes to the service design assumptions since the previous Outline Business Case include a revision to the resettlement model, updated assumptions on the eligibility for interventions on the dynamic framework and revisions to what it will cost to transition to the Unified Model | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -35%, is due primarily to the following factors; - Difference between pre and post contract award of spend profile in construction phase Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -35%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; - Contaminated land and adverse weather further impacted spend against revised 19/20 baseline | The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -16%, is due primarily to the following factors; - Resource underspend due mainly to recruitment not progressing at the pace originally expected, and private sector workforce reforms not yet agreed and implemented - Capital underspend due to delays to the secure schools project. Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -16%, the following primary project actions have impacted the original Q2 19/20 in-year variance; - There has not been re-baselining or specific actions impacting in-year variance
Departmental Narrative on Budgeted Whole Life Costs | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £580.50 m, has not changed since last year's Q2 1819 (£m) baseline Whole Life Cost of £580.50 m, due primarily to the following factors; - There has not been a significant change in programme cost or scope to require rebaselining and republication of the FBC. Since the Q2 1920 (30th September 2019) £580.50 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - There has not been a significant change in programme cost or scope to require rebaselining and republication of the FBC. | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £6,104.77 m, due primarily to the following factors; - Baseline costs reflect the project's OBC Since the Q2 1920 (30th September 2019) £6,104.77 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - At Q3 the baseline and forecasts were updated to reflect that the planned date for construction to be completed and the prison to accept first prisoner had moved back by 12 months. | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £1,039.53 m, has increased by £252.33 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £787.20 m, due primarily to the following factors; - Life cycle costs - The additional requirement for the need to put in place a programme of what in broad terms might be described as asset repair spend to reduce the level of equipment and asset failure. Also, to reduce the risk of compensation claims from the contractor that the assets the contract requires them to maintain are life-expired. - Increased Planned Maintenance and Cleaning costs as a result of potential understated net internal area and number of assets stated. The asset and internal area data provided to bidders was provided by the current contract suppliers. - Impact of change in National Minimum Wage - primarily relates to the Security and FM-Cleaning elements of the arrangements, affects both the fixed and variable costs. Assumed the first 2% of any increase as a result of a pay award will be covered by the CPI increase specified in the contract, the addition covers the cost of any minimum wage rises above this. 75% of costs relating to Security with the remaining 25% within Cleaning. Since the Q2 1920 (30th September 2019) £1,039.53 m baseline Whole Life Cost, the following non-project operating environment activities have impacted the original baseline Q2 Whole Life Cost; - Impact of change in National Minimum Wage - 75% of costs relating to Security with the remaining 25% within Cleaning. - Tupe Premium - Some members of staff who were TUPE'd to the new contract are on high wages then the new suppliers bidded at, HMCTS is paying the differential. Since the Q2 1920 (30th September 2019) £1,039.53 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - Extended KPI holiday given to suppliers in return for a reduction in mobilisation fees - the impact is estimated to be nominal. | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £2,153.17 m, has increased by £606.34 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £1,546.83 m, due primarily to the following factors; - The increase of £600m masks a £273m integration of the common platform programme into the fifth iteration of the reform business case and is not an increase to the whole life costs of the programme. - There is an error in the 2018/19 return of £100m CDEL omitted from the numbers provided. Whilst we are unsure as to why this error was made, it is believed it could be due to an omission of optimism bias. - The extension of the programme timeline and deliverables has moved the BAU costs to the right resulting in a reduction of WLC by c.£38m, but in the 2019/20 return the dis-benefits costs were pushed out for a further 2 years increasing the WLC by £278m. Since the Q2 1920 (30th September 2019) £2,153.17 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - The omission of £100m believed to be optimism bias - The programmes decision to increase the timeline of Reform by a further 2 years has increased the WLC as dis-benefits run for a further 2 years. It should be noted that Implementation costs have not increased. | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £430.20 m, has not changed since last year's Q2 1819 (£m) baseline Whole Life Cost of £430.20 m, due primarily to the following factors; - The project Closed in October 2019 | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £763.30 m, has decreased by £459.90 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £1,223.20 m, due primarily to the following factors; - Following consultation with the IPA, whole life costs were revised to remove those attributed to an optional two year contract extension, as any future extension would require the production of a separate business case covering the costs for the extension period. Since the Q2 1920 (30th September 2019) £763.30 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - The programme has closed. As such no project actions have been undertaken that have impacted the original Q2 baseline. | Due to HMT approval not being in place at Q2 we cannot report on this but we will be able to report in the next annual report return | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £1,635.83 m, has increased by £13.53 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £1,622.30 m, due primarily to the following factors; - Revised Gen 4 service/ contract costs in FBC based on actual tenders from suppliers. - Revised programme staffing costs. - Revised digital (CDEL) costs. Since the Q2 1920 (30th September 2019) £1,635.83 m baseline Whole Life Cost, the following non-project operating environment activities have impacted the original baseline Q2 Whole Life Cost; - OBR Forecasts of inflation relating to CPI (Consumer Prices Index) and AWE (Average Weekly Earnings). Since the Q2 1920 (30th September 2019) £1,635.83 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - Contract/ Service costs updated in line with tendered bids and Full Business Case, including effects of Office of Budget Responsibility (OBR) forecasts for Consumer Price Index (CPI) and Average Weekly Earnings(AWE) indices. Forecast of in-year spend includes Mobilisation, Transition and Redundancy costs included within tenders, the actual spend for which will begin from Nov/Dec 2019 and continue until March 2021. - Extension of programme team (RDEL) costs to cover the revised programme closure date (+182 days). - Extension of Digital (CDEL) costs to include revised digital deliverables and timetable. | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £8,235.23 m, has increased by £7035.23 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £1,200.00 m, due primarily to the following factors; - The increase in the National Probation Service budget due to caseload increases that weren’t accounted for in the previous Outline Business Case. The increase in the National Probation operational support costs of account for the additional resource required to manage more regions. - The increase in staff required in courts to ensure offenders get the most effective sentence, and the right start to that sentence.* The increase in estates due to improved information on the portfolio of properties and their requirements. Since the Q2 1920 (30th September 2019) £8,235.23 m baseline Whole Life Cost, the following non-project operating environment activities have impacted the original baseline Q2 Whole Life Cost; - The effect of the policy to recruit an additional 20,000 police officers Since the Q2 1920 (30th September 2019) £8,235.23 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - Detailed decision making, analysis and costings on the introduction of the new offender management model for the future probation services in England and Wales - consequently we will have greater clarity on costs ahead of the investment decision point | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £6,316.01 m, due primarily to the following factors; - The baseline costs are based on the business case. The costs represents the cost of building and then operating the prison for a period of 60 years Since the Q2 1920 (30th September 2019) £6,316.01 m baseline Whole Life Cost, the following non-project operating environment activities have impacted the original baseline Q2 Whole Life Cost; - Some of the tendered prices returned by the supply chain were greater than originally estimated meaning overall construction cost are more than in the baseline Since the Q2 1920 (30th September 2019) £6,316.01 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; - The baseline is currently the same as at Q2 | The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £345.08 m, has increased by £33.95 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £311.13 m, due primarily to the following factors; - The main reason for the increase of £32m is another year of cost has been added to the WLC, due to increased workforce costs and permanent improvements to education provision having no end-date. (The figures stated refer to the entirety of the Youth Justice Reform Programme, including secure schools.)
Annual Report Category | Government Transformation and Service Delivery | Infrastructure and Construction | Government Transformation and Service Delivery | Government Transformation and Service Delivery | Government Transformation and Service Delivery | Government Transformation and Service Delivery | ICT | Government Transformation and Service Delivery | Government Transformation and Service Delivery | Infrastructure and Construction | Government Transformation and Service Delivery
The IPA Annual Report publishes the whole life cycle costs on projects, based on figures from their Business Cases, whilst the National Infrastructure and Construction Pipeline (NICP) focuses primarily on the upfront capital investment on a project. Where both documents refer to the same projects, this distinction will be the principal reason for any differences in the data sets published. Other government publications may use different methodologies to derive cost figures