## SourceTable
GMPP ID Number	Project Name	AR Year	Quarter	Department	MPA RAG / (Departmental RAG used if MPA RAG missing)	Project - Start Date / (Latest Approved Start Date)	Project - End Date / (Latest Approved End Date)	FY Budget (£m) inc Non Gov	FY Forecast (£m) inc Non Gov	Budget Variance (£m)	Budget Variance (%)	TOTAL BUDGETED WHOLE LIFE COSTS including Non-Government Costs	Gov WLC	Non-Gov WLC	PROJECT CATEGORY	Project Length	Unique ID	Department Grouped	MPA RAG Grouped	Joiner	SRO	Description
BIS_0001_1112-Q1	BIS Shared Services	AR 2013	1213-Q2	BEIS	Amber	04/05/2011	30/04/2013	£11.26m	£11.41m			15.54				1.99	BIS_0001_1112-Q1,1213-Q2	BEIS	Amber	Joiner
BIS_0005_1112-Q1	Further Education Fee Loans Programme	AR 2013	1213-Q2	BEIS	Amber/Green	30/11/2010	01/04/2016	£5.45m	£5.45m			576.59				5.34	BIS_0005_1112-Q1,1213-Q2	BEIS	Amber/Green	Joiner
BIS_0008_1112-Q1	Student Loans Monetisation Feasibility Study	AR 2013	1213-Q2	BEIS	Amber/Red	01/03/2010	31/12/2014	£0.12m	£0.12m			6.22				4.84	BIS_0008_1112-Q1,1213-Q2	BEIS	Amber/Red	Joiner
BIS_0009_1112-Q1	The Francis Crick Institute (formerly UKCMRI)	AR 2013	1213-Q2	BEIS	Amber/Green	01/10/2006	21/12/2017	£58.00m	£58.00m			753.00				11.22	BIS_0009_1112-Q1,1213-Q2	BEIS	Amber/Green	Joiner
BIS_0011_1213-Q1	Core Systems Replacement	AR 2013	1213-Q2	BEIS	Amber	01/03/2012	19/03/2016	£2.91m	£2.62m			131.91				4.05	BIS_0011_1213-Q1,1213-Q2	BEIS	Amber	Joiner
BIS_0002_1112-Q1	Business Improvement Programme	AR 2013	1213-Q2	BEIS	Green	01/08/2010	14/03/2013	£50.10m	£50.10m			206.00				2.62	BIS_0002_1112-Q1,1213-Q2	BEIS	Green	Joiner
BIS_0003_1112-Q1	Technology and innovation centres	AR 2013	1213-Q2	BEIS	Amber/Green	01/12/2010	01/04/2013	£60.00m	£60.00m			476.00				2.33	BIS_0003_1112-Q1,1213-Q2	BEIS	Amber/Green	Joiner
BIS_0004_1112-Q1	FE Capital Investment Programme	AR 2013	1213-Q2	BEIS	Amber/Green	31/05/2010	31/03/2015	£272.66m	£272.66m			4578.42				4.83	BIS_0004_1112-Q1,1213-Q2	BEIS	Amber/Green	Joiner
BIS_0006_1112-Q1	Green Investment Bank	AR 2013	1213-Q2	BEIS	Amber	01/06/2010	01/09/2012	£799.00m	£329.00m			1857.00				2.25	BIS_0006_1112-Q1,1213-Q2	BEIS	Amber	Joiner
BIS_0007_1112-Q1	HE Reform Programme	AR 2013	1213-Q2	BEIS	Amber	30/06/2011	31/12/2015	£370.00m	£370.00m			4600.00				4.50	BIS_0007_1112-Q1,1213-Q2	BEIS	Amber	Joiner
CO_0001_1112-Q1	Electoral Registration Transformation Programme	AR 2013	1213-Q2	CO	Amber	01/03/2010	01/01/2016	£5.90m	£5.90m			218.23				5.84	CO_0001_1112-Q1,1213-Q2	CO	Amber	Joiner
CO_0004_1112-Q1	National Citizen Service	AR 2013	1213-Q2	CO	Amber	01/10/2011	31/12/2014	£59.86m	£59.86m			324.06				3.25	CO_0004_1112-Q1,1213-Q2	CO	Amber	Joiner
CO_0005_1112-Q1	National Cyber Security Programme	AR 2013	1213-Q2	CO	Amber	01/04/2011	01/04/2015	£155.00m	£155.00m			650.00				4.00	CO_0005_1112-Q1,1213-Q2	CO	Amber	Joiner
CO_0006_1112-Q2	Public Services Network Programme	AR 2013	1213-Q2	CO	Green	31/08/2011	30/01/2015	£1.05m	£1.05m			24.96				3.42	CO_0006_1112-Q2,1213-Q2	CO	Green	Joiner
CO_0002_1112-Q1	G-Cloud Programme (covers Data Centre Consolidation and Application Store)	AR 2013	1213-Q2	CO	Amber/Red	31/10/2011	30/06/2015	£0.58m	£0.58m			0.58				3.66	CO_0002_1112-Q1,1213-Q2	CO	Amber/Red	Joiner
DCLG_0005_1112-Q4	ICTRelet Project (formerly entitled ICTDesktop Refresh)	AR 2013	1213-Q2	DCLG	Amber/Red	16/11/2011	28/02/2014	£1.90m	£1.90m			36.63				2.29	DCLG_0005_1112-Q4,1213-Q2	DCLG	Amber/Red	Joiner
DCLG_0006_1112-Q4	Enterprise Zones Programme	AR 2013	1213-Q2	DCLG	Amber	23/03/2011	31/03/2015	£0.00m	£0.00m			0.00				4.02	DCLG_0006_1112-Q4,1213-Q2	DCLG	Amber	Joiner
DCLG_0004_1112-Q1	Reform of the Audit Commission	AR 2013	1213-Q2	DCLG	Amber	30/06/2011	01/11/2012	£24.99m	£0.05m			53.08				1.34	DCLG_0004_1112-Q1,1213-Q2	DCLG	Amber	Joiner
DCLG_0001_1112-Q1	Housing Investment and Regulatory Reform Programme (HIRRP)	AR 2013	1213-Q2	DCLG	Green	01/11/2011	31/03/2012	£6.90m	£6.90m			25.50				0.41	DCLG_0001_1112-Q1,1213-Q2	DCLG	Green	Joiner
DCMS_0001_1112-Q1	Broadband Delivery Programme	AR 2013	1213-Q2	DCMS	Amber/Red	01/05/2011	31/03/2015	£91.00m	£91.00m			529.00				3.92	DCMS_0001_1112-Q1,1213-Q2	DCMS	Amber/Red	Joiner
DCMS_0004_1112-Q1	The Tate Modern Project	AR 2013	1213-Q2	DCMS	Exempt	01/01/2010	01/05/2015	£5.34m	£5.34m			215.00				5.33	DCMS_0004_1112-Q1,1213-Q2	DCMS	Exempt	Joiner
DCMS_0005_1112-Q1	World Conservation and Exhibitions Centre	AR 2013	1213-Q2	DCMS	Amber/Green	31/03/2008	01/04/2014	£0.00m	£0.00m			135.00				6.00	DCMS_0005_1112-Q1,1213-Q2	DCMS	Amber/Green	Joiner
DCMS_0006_1112-Q4	Mobile Infrastructure Project	AR 2013	1213-Q2	DCMS	Amber	03/10/2011	31/03/2015	£12.50m	£4.50m			154.50				3.49	DCMS_0006_1112-Q4,1213-Q2	DCMS	Amber	Joiner
DCMS_0007_1112-Q4	Urban Broadband Fund - Super-connected City Initiative	AR 2013	1213-Q2	DCMS	Amber/Red	26/06/2012	31/03/2015	£10.00m	£0.00m			150.00				2.76	DCMS_0007_1112-Q4,1213-Q2	DCMS	Amber/Red	Joiner
DCMS_0003_1112-Q1	Spectrum Clearance and Awards Programme	AR 2013	1213-Q2	DCMS	Amber	22/06/2011	31/12/2014	£116.40m	£101.99m			281.20				3.53	DCMS_0003_1112-Q1,1213-Q2	DCMS	Amber	Joiner
BIS_0010_1112-Q4	Urenco Future Options	AR 2013	1213-Q2	BEIS	Exempt	01/02/2010	23/12/2013	£2.50m	£2.50m			11.98				3.89	BIS_0010_1112-Q4,1213-Q2	BEIS	Exempt	Joiner
DECC_0003_1112-Q1	Dounreay Parent Body Organisation (PBO)	AR 2013	1213-Q2	BEIS	Green	21/09/2009	31/12/2025	£150.00m	£154.70m			1578.00				16.28	DECC_0003_1112-Q1,1213-Q2	BEIS	Green	Joiner
DECC_0004_1112-Q1	Electricity Market Reform Programme	AR 2013	1213-Q2	BEIS	Exempt	10/12/2010	31/12/2030	£10.20m	£10.20m			40.10				20.06	DECC_0004_1112-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2013	1213-Q2	BEIS	Exempt	30/06/2011	31/12/2040	£22.00m	£22.20m			11626.20				29.51	DECC_0005_1112-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0009_1112-Q1	Renewable Heat Incentive	AR 2013	1213-Q2	BEIS	Exempt	30/11/2008	01/02/2014	£108.00m	£41.00m			33149.00				5.17	DECC_0009_1112-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0010_1112-Q1	Smart Meters Programme	AR 2013	1213-Q2	BEIS	Exempt	02/12/2009	23/09/2019	£20.15m	£20.15m			17171.95				9.81	DECC_0010_1112-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0011_1112-Q3	Carbon Capture & Storage - Programme	AR 2013	1213-Q2	BEIS	Exempt	25/10/2011	01/01/2045	£4.90m	£4.90m			exempt				33.19	DECC_0011_1112-Q3,1213-Q2	BEIS	Exempt	Joiner
DECC_0012_1213-Q1	FID Enabling	AR 2013	1213-Q2	BEIS	Exempt	01/09/2011	30/11/2013	£11.60m	£11.00m			20.92				2.25	DECC_0012_1213-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	AR 2013	1213-Q2	BEIS	Exempt	20/04/2012	30/06/2028	£740.00m	£740.00m			7603.00				16.19	DECC_0013_1213-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0008_1112-Q1	Plutonium Management	AR 2013	1213-Q2	BEIS	Exempt	23/05/2011	31/03/2110	exempt	exempt			exempt				98.85	DECC_0008_1112-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0007_1112-Q1	New Nuclear Programme	AR 2013	1213-Q2	BEIS	Exempt	31/01/2008	31/12/2019	£2.00m	£2.00m			40.79				11.92	DECC_0007_1112-Q1,1213-Q2	BEIS	Exempt	Joiner
DECC_0006_1112-Q1	Green Deal	AR 2013	1213-Q2	BEIS	Exempt	20/05/2010	31/12/2030	£66.50m	£66.50m			10304.20				20.62	DECC_0006_1112-Q1,1213-Q2	BEIS	Exempt	Joiner
DEFRA_0001_1112-Q1	CAP Delivery Programme (formerly the Future Options Programme)	AR 2013	1213-Q2	DEFRA	Amber	01/01/2011	01/03/2015	£8.53m	£8.53m			13.03				4.16	DEFRA_0001_1112-Q1,1213-Q2	DEFRA	Amber	Joiner
DEFRA_0002_1112-Q1	Covent Garden Market Authority (CGMA) Redevelopment - Project Chrysalis	AR 2013	1213-Q2	DEFRA	Amber	29/09/2008	01/12/2018	£0.00m	£0.00m			0.00				10.17	DEFRA_0002_1112-Q1,1213-Q2	DEFRA	Amber	Joiner
DEFRA_0003_1112-Q1	New Waterways Charity	AR 2013	1213-Q2	DEFRA	Green	01/06/2009	31/08/2012	£39.00m	£39.00m			873.72				3.25	DEFRA_0003_1112-Q1,1213-Q2	DEFRA	Green	Joiner
DEFRA_0004_1112-Q1	Thames Estuary 2100 (TE2100) Plan	AR 2013	1213-Q2	DEFRA	Amber	01/04/2010	31/03/2024	£35.00m	£32.00m			3082.00				14.00	DEFRA_0004_1112-Q1,1213-Q2	DEFRA	Amber	Joiner
DFE_0003_1112-Q4	Priority School Building Programme	AR 2013	1213-Q2	DFE	Amber	19/07/2011	01/08/2044	£4.50m	£4.58m			397.00				33.04	DFE_0003_1112-Q4,1213-Q2	DFE	Amber	Joiner
DFE_0001_1112-Q1	Building Schools for the Future (BSF)	AR 2013	1213-Q2	DFE	Amber/Green	12/07/2011	02/07/2017	£677.00m	£677.00m			6302.00				5.97	DFE_0001_1112-Q1,1213-Q2	DFE	Amber/Green	Joiner
DFID_0001_1112-Q1	St Helena Airport	AR 2013	1213-Q2	DFID	Amber/Green	15/03/2005	31/08/2026	£70.09m	£69.77m			423.47				21.46	DFID_0001_1112-Q1,1213-Q2	DFID	Amber/Green	Joiner
DFT_0001_1112-Q1	Crossrail	AR 2013	1213-Q2	DFT	Amber/Green	22/07/2008	31/12/2019	£1206.50m	£1206.50m			14510.98				11.44	DFT_0001_1112-Q1,1213-Q2	DFT	Amber/Green	Joiner
DFT_0015_1112-Q1	Shared Services Futures Project	AR 2013	1213-Q2	DFT	Amber/Red	10/12/2010	31/12/2014	£0.50m	£0.50m			3.20				4.06	DFT_0015_1112-Q1,1213-Q2	DFT	Amber/Red	Joiner
DFT_0004_1112-Q1	High Speed Rail Programme	AR 2013	1213-Q2	DFT	Amber/Red	28/02/2011	31/12/2033	£306.80m	£209.00m			1117.90				22.84	DFT_0004_1112-Q1,1213-Q2	DFT	Amber/Red	Joiner
DFT_0006_1112-Q1	M25 DBFO (Design, Build, Finance and Operate)	AR 2013	1213-Q2	DFT	Green	31/05/2009	31/07/2013	£99.61m	£74.77m			990.75				4.17	DFT_0006_1112-Q1,1213-Q2	DFT	Green	Joiner
DFT_0007_1112-Q1	Managed Motorways	AR 2013	1213-Q2	DFT	Amber/Green	31/10/2011	30/09/2017	£219.19m	£245.45m			1431.27				5.92	DFT_0007_1112-Q1,1213-Q2	DFT	Amber/Green	Joiner
DFT_0008_1112-Q1	Olympics Transport Programme	AR 2013	1213-Q2	DFT	Green	13/09/2007	31/12/2012	£24.61m	£24.86m			34.49				5.30	DFT_0008_1112-Q1,1213-Q2	DFT	Green	Joiner
DFT_0011_1112-Q1	Rail ReFranchising Management Programme - GA Long	AR 2013	1213-Q2	DFT	Amber/Green	19/07/2012	31/01/2015	£0.00m	£0.00m			0.00				2.54	DFT_0011_1112-Q1,1213-Q2	DFT	Amber/Green	Joiner
DFT_0012_1112-Q1	Rail ReFranchising Management Programme - Greater Anglia Short	AR 2013	1213-Q2	DFT	Green	01/06/2010	28/02/2013	-£144.70m	-£154.90m			-396.78				2.75	DFT_0012_1112-Q1,1213-Q2	DFT	Green	Joiner
DFT_0013_1112-Q1	Rail ReFranchising Management Programme - West Coast	AR 2013	1213-Q2	DFT	Red	22/09/2010	08/04/2014	£0.00m	£0.00m			0.00				3.54	DFT_0013_1112-Q1,1213-Q2	DFT	Red	Joiner
DFT_0017_1213-Q1	Great Western refranchising	AR 2013	1213-Q2	DFT	Amber	21/07/2011	16/01/2015	£0.00m	£0.00m			0.00				3.49	DFT_0017_1213-Q1,1213-Q2	DFT	Amber	Joiner
DFT_0018_1213-Q1	Thameslink, Southern and Great Northern refranchising project	AR 2013	1213-Q2	DFT	Amber/Red	30/10/2011	27/02/2015	£0.00m	£0.00m			0.00				3.33	DFT_0018_1213-Q1,1213-Q2	DFT	Amber/Red	Joiner
DFT_0010_1112-Q1	Rail ReFranchising Management Programme - East Coast	AR 2013	1213-Q2	DFT	Amber	20/07/2009	31/05/2013	£0.00m	£0.00m			0.00				3.86	DFT_0010_1112-Q1,1213-Q2	DFT	Amber	Joiner
DFT_0002_1112-Q1	DVLA ICTContract Procurement	AR 2013	1213-Q2	DFT	Amber	01/03/2011	30/09/2015	£6.96m	£3.46m			102.06				4.58	DFT_0002_1112-Q1,1213-Q2	DFT	Amber	Joiner
DFT_0005_1112-Q1	Intercity Express Programme (IEP)	AR 2013	1213-Q2	DFT	Amber/Green	01/06/2005	31/12/2019	£5.86m	£5.86m			1288.68				14.58	DFT_0005_1112-Q1,1213-Q2	DFT	Amber/Green	Joiner
DFT_0009_1112-Q1	Periodic Review 2013 (HLOS)	AR 2013	1213-Q2	DFT	Green	31/08/2011	31/07/2012	£0.00m	£0.00m			18566.79				0.92	DFT_0009_1112-Q1,1213-Q2	DFT	Green	Joiner
DFT_0014_1112-Q1	Search & Rescue Helicopters (SARH)	AR 2013	1213-Q2	DFT	Amber	08/02/2011	08/09/2017	£37.00m	£37.00m			3286.00				6.58	DFT_0014_1112-Q1,1213-Q2	DFT	Amber	Joiner
DH_0008_1112-Q1	Electronic Prescription Service (EPS) Release 2	AR 2013	1213-Q2	DH	Amber/Green	28/11/2003	31/03/2014	£8.85m	£10.26m			36.38				10.34	DH_0008_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DFT_0016_1112-Q1	Thameslink	AR 2013	1213-Q2	DFT	Amber/Green	01/07/2005	01/12/2018	£28.83m	£26.83m			5638.26				13.42	DFT_0016_1112-Q1,1213-Q2	DFT	Amber/Green	Joiner
DH_0015_1112-Q1	NME Programme for IT	AR 2013	1213-Q2	DH	Amber	01/04/2004	31/07/2016	£273.05m	£405.75m			5636.19				12.33	DH_0015_1112-Q1,1213-Q2	DH	Amber	Joiner
DH_0018_1112-Q1	Pre-Pandemic Vaccine	AR 2013	1213-Q2	DH	Amber/Green	01/10/2011	01/07/2014	£0.00m	£0.00m			0.00				2.75	DH_0018_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0003_1112-Q1	Brighton & Sussex University Hospitals NHS Trust (3Ts Programme - The development of a leading teaching, trauma and tertiary care centre)	AR 2013	1213-Q2	DH	Amber/Green	31/05/2012	24/12/2021	£26.80m	£54.38m			500.80				9.57	DH_0003_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0004_1112-Q1	Broadmoor Redevelopment Programme	AR 2013	1213-Q2	DH	Amber/Green	01/08/2011	01/11/2018	£16.22m	£16.22m			256.25				7.25	DH_0004_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0022_1112-Q1	Summary Care Record (SCR)	AR 2013	1213-Q2	DH	Amber/Green	01/04/2006	31/03/2016	£24.87m	£24.17m			51.10				10.00	DH_0022_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0023_1112-Q2	London Programme for IT	AR 2013	1213-Q2	DH	Amber/Red	18/12/2003	19/10/2015	£163.35m	£174.67m			627.59				11.84	DH_0023_1112-Q2,1213-Q2	DH	Amber/Red	Joiner
DH_0026_1112-Q2	Southern Programme for IT	AR 2013	1213-Q2	DH	Amber/Green	26/01/2004	31/10/2015	£102.39m	£78.95m			634.06				11.76	DH_0026_1112-Q2,1213-Q2	DH	Amber/Green	Joiner
DH_0014_1112-Q1	NHSmail service refresh	AR 2013	1213-Q2	DH	Amber/Green	31/10/2004	30/06/2013	£7.90m	£22.83m			96.05				8.66	DH_0014_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0010_1112-Q1	Health and Care Modernisation Transition Programme	AR 2013	1213-Q2	DH	Amber/Red	01/10/2011	01/04/2013	£699.30m	£699.30m			1563.90				1.50	DH_0010_1112-Q1,1213-Q2	DH	Amber/Red	Joiner
DH_0012_1112-Q1	IMS3	AR 2013	1213-Q2	DH	Green	16/05/2011	29/03/2013	£70.11m	£55.40m			139.38				1.87	DH_0012_1112-Q1,1213-Q2	DH	Green	Joiner
DH_0005_1112-Q1	CAB Variation	AR 2013	1213-Q2	DH	Amber/Green	01/10/2011	15/12/2013	£30.09m	£29.10m			54.24				2.21	DH_0005_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0024_1112-Q2	N3 Extension	AR 2013	1213-Q2	DH	Amber	19/02/2004	31/03/2014	£114.31m	£120.34m			371.89				10.11	DH_0024_1112-Q2,1213-Q2	DH	Amber	Joiner
DH_0006_1112-Q1	E &N Herts. NHS Trust - LIFT scheme - new QEII hospital in Welwyn Garden City	AR 2013	1213-Q2	DH	Amber/Green	23/03/2011	01/04/2014	£0.00m	£0.00m			70.25				3.03	DH_0006_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0016_1112-Q1	Pandemic Vaccine Sleeping Contract	AR 2013	1213-Q2	DH	Green	01/04/2010	01/06/2012	£0.00m	£0.00m			0.00				2.17	DH_0016_1112-Q1,1213-Q2	DH	Green	Joiner
DWP_0003_1112-Q1	Child Maintenance Group Change	AR 2013	1213-Q2	DWP	Amber/Red	01/08/2009	29/01/2014	£72.50m	£87.35m			1203.39				4.50	DWP_0003_1112-Q1,1213-Q2	DWP	Amber/Red	Joiner
DWP_0005_1112-Q1	Enabling Retirement Savings Programme	AR 2013	1213-Q2	DWP	Amber	18/05/2007	01/10/2018	£112.00m	£98.80m			1004.30				11.37	DWP_0005_1112-Q1,1213-Q2	DWP	Amber	Joiner
DWP_0009_1112-Q1	Universal Credit Programme	AR 2013	1213-Q2	DWP	Amber/Red	17/11/2011	31/12/2017	£386.50m	£378.99m			12845.38				6.12	DWP_0009_1112-Q1,1213-Q2	DWP	Amber/Red	Joiner
DWP_0011_1112-Q2	Personal Independence Payment Implementation	AR 2013	1213-Q2	DWP	Amber/Red	31/10/2011	31/03/2016	£139.43m	£126.72m			2771.38				4.42	DWP_0011_1112-Q2,1213-Q2	DWP	Amber/Red	Joiner
DWP_0016_1213-Q2	Fraud and Error Programme	AR 2013	1213-Q2	DWP	Amber/Red	02/04/2012	01/03/2015	£156.30m	£128.65m			770.30				2.91	DWP_0016_1213-Q2,1213-Q2	DWP	Amber/Red	Joiner
DWP_0010_1112-Q1	Work Programme	AR 2013	1213-Q2	DWP	Amber	25/11/2010	18/10/2011	£735.70m	£777.00m			5626.70				0.90	DWP_0010_1112-Q1,1213-Q2	DWP	Amber	Joiner
DWP_0007_1112-Q1	Incapacity Benefit Reassessment	AR 2013	1213-Q2	DWP	Green	09/07/2009	23/03/2012	£143.60m	£140.99m			891.80				2.70	DWP_0007_1112-Q1,1213-Q2	DWP	Green	Joiner
DWP_0002_1112-Q1	Central Payment System	AR 2013	1213-Q2	DWP	Green	01/09/2008	21/06/2012	£23.50m	£22.32m			284.90				3.80	DWP_0002_1112-Q1,1213-Q2	DWP	Green	Joiner
DWP_0012_1112-Q4	Benefit Cap	AR 2013	1213-Q2	DWP	Amber/Red	19/04/2012	31/07/2013	£28.53m	£27.00m			49.03				1.28	DWP_0012_1112-Q4,1213-Q2	DWP	Amber/Red	Joiner
DWP_0015_1112-Q4	Youth Contract	AR 2013	1213-Q2	DWP	Green	19/01/2012	21/06/2012	£139.97m	£182.04m			741.93				0.42	DWP_0015_1112-Q4,1213-Q2	DWP	Green	Joiner
DWP_0013_1112-Q4	Specialist Disability Employment Programme	AR 2013	1213-Q2	DWP	Amber	16/02/2012	31/07/2014	£33.52m	£35.63m			202.98				2.45	DWP_0013_1112-Q4,1213-Q2	DWP	Amber	Joiner
DWP_0014_1112-Q4	State Pension Reform - Single Tier	AR 2013	1213-Q2	DWP	Amber/Green	27/02/2012	31/10/2017	£2.70m	£1.12m			114.16				5.68	DWP_0014_1112-Q4,1213-Q2	DWP	Amber/Green	Joiner
DH_0007_1112-Q1	E & N Herts NHS Trust - Lister Hospital ('Our Changing Hospitals' Phase 4 Programme)	AR 2013	1213-Q2	DH	Amber/Red	04/08/2011	17/01/2014	£28.43m	£21.49m			201.52				2.46	DH_0007_1112-Q1,1213-Q2	DH	Amber/Red	Joiner
FCO_0004_1112-Q1	Prism and Firecrest Re-procurement Programme	AR 2013	1213-Q2	FCO	Amber	01/01/2011	30/11/2013	£0.00m	£0.00m			0.00				2.91	FCO_0004_1112-Q1,1213-Q2	FCO	Amber	Joiner
DH_0013_1112-Q1	Mersey Care NHS LIFT scheme (TIME - To Improve Mental health Environments)	AR 2013	1213-Q2	DH	Amber/Green	30/08/2011	20/01/2015	£0.00m	£0.00m			208.80				3.39	DH_0013_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
FCO_0002_1112-Q1	Echo	AR 2013	1213-Q2	FCO	Amber/Green	09/06/2009	31/12/2012	£29.96m	£32.07m			179.19				3.56	FCO_0002_1112-Q1,1213-Q2	FCO	Amber/Green	Joiner
FCO_0003_1112-Q1	JAKARTA: New Embassy	AR 2013	1213-Q2	FCO	Amber/Green	01/04/2004	01/09/2014	£11.06m	£11.06m			29.45				10.42	FCO_0003_1112-Q1,1213-Q2	FCO	Amber/Green	Joiner
FCO_0005_1112-Q1	TEL AVIV: Embassy Upgrade	AR 2013	1213-Q2	FCO	Green	28/10/2009	01/11/2013	£3.82m	£2.62m			21.50				4.01	FCO_0005_1112-Q1,1213-Q2	FCO	Green	Joiner
HMRC_0002_1112-Q1	Debt Management & Banking (DMB) Staff Reinvestment	AR 2013	1213-Q2	HMRC	Amber/Green	01/04/2011	01/04/2015	£11.26m	£11.27m			56.41				4.00	HMRC_0002_1112-Q1,1213-Q2	HMRC	Amber/Green	Joiner
HMRC_0004_1112-Q1	One Click	AR 2013	1213-Q2	HMRC	Amber/Red	24/03/2010	10/04/2013	£10.01m	£26.04m			113.18				3.05	HMRC_0004_1112-Q1,1213-Q2	HMRC	Amber/Red	Joiner
HMRC_0006_1112-Q1	Real Time Information (RTI)	AR 2013	1213-Q2	HMRC	Amber	05/07/2010	31/10/2014	£28.32m	£28.32m			241.10				4.32	HMRC_0006_1112-Q1,1213-Q2	HMRC	Amber	Joiner
HMRC_0007_1112-Q2	Expanding the use of Debt Collection Agencies	AR 2013	1213-Q2	HMRC	Amber/Green	01/04/2011	31/03/2015	£20.15m	£18.70m			70.68				4.00	HMRC_0007_1112-Q2,1213-Q2	HMRC	Amber/Green	Joiner
HMRC_0008_1112-Q2	Organised Crime	AR 2013	1213-Q2	HMRC	Amber/Green	01/04/2011	02/07/2012	£25.42m	£25.21m			82.73				1.25	HMRC_0008_1112-Q2,1213-Q2	HMRC	Amber/Green	Joiner
HMRC_0009_1112-Q2	Volume Crime	AR 2013	1213-Q2	HMRC	Amber/Green	01/04/2011	31/03/2013	£11.20m	£11.08m			42.04				2.00	HMRC_0009_1112-Q2,1213-Q2	HMRC	Amber/Green	Joiner
HMRC_0003_1112-Q1	Electronic Exchange of Social Security Information (EESSI) Programme	AR 2013	1213-Q2	HMRC	Amber/Green	02/12/2009	31/05/2014	£0.12m	£0.12m			5.29				4.49	HMRC_0003_1112-Q1,1213-Q2	HMRC	Amber/Green	Joiner
HMRC_0010_1112-Q2	Wider Coverage Project	AR 2013	1213-Q2	HMRC	Amber	14/09/2011	30/06/2015	£104.74m	£103.77m			552.59				3.79	HMRC_0010_1112-Q2,1213-Q2	HMRC	Amber	Joiner
HMRC_0005_1112-Q1	Open Cases Programme	AR 2013	1213-Q2	HMRC	Green	31/10/2010	31/10/2012	£19.43m	£19.43m			57.28				2.00	HMRC_0005_1112-Q1,1213-Q2	HMRC	Green	Joiner
HMT_0001_1112-Q1	Equitable Life Payment Scheme	AR 2013	1213-Q2	HMT	Amber/Red	01/05/2010	01/04/2014	£0.00m	£0.00m			0.00				3.92	HMT_0001_1112-Q1,1213-Q2	HMT	Amber/Red	Joiner
HMT_0002_1112-Q1	Project OSCAR	AR 2013	1213-Q2	HMT	Amber	24/08/2011	07/02/2013	£4.71m	£4.67m			19.56				1.46	HMT_0002_1112-Q1,1213-Q2	HMT	Amber	Joiner
HO_0007_1112-Q1	SOCA Information Systems and Operating Technology (ISOT) Programme	AR 2013	1213-Q2	HO	Amber/Red	01/04/2008	30/09/2013	£43.71m	£44.54m			398.60				5.50	HO_0007_1112-Q1,1213-Q2	HO	Amber/Red	Joiner
HO_0008_1112-Q1	Schengen Information Systems (SIS) II Programme	AR 2013	1213-Q2	HO	Amber	01/04/2006	31/03/2015	£11.86m	£14.48m			168.17				9.00	HO_0008_1112-Q1,1213-Q2	HO	Amber	Joiner
HO_0009_1112-Q1	Transforming the Customer Experience (Formerly A&E)	AR 2013	1213-Q2	HO	Red	14/05/2007	31/03/2012	£46.72m	£50.01m			424.29				4.88	HO_0009_1112-Q1,1213-Q2	HO	Red	Joiner
HO_0011_1112-Q2	SIG Disclosure & Barring Service Programme (formerly Convergence Programme)	AR 2013	1213-Q2	HO	Amber	29/12/2010	01/10/2015	£127.43m	£5.92m			709.77				4.76	HO_0011_1112-Q2,1213-Q2	HO	Amber	Joiner
HO_0012_1112-Q3	Communications Capabilities Development programme	AR 2013	1213-Q2	HO	Amber	00/01/1900	00/01/1900	£0.00m	£0.00m			0.00				0.00	HO_0012_1112-Q3,1213-Q2	HO	Amber	Joiner
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2013	1213-Q2	HO	Exempt	01/06/2011	31/12/2020	£0.00m	£0.00m			0.00				9.59	HO_0016_1213-Q1,1213-Q2	HO	Exempt	Joiner
HO_0023_1213-Q1	Next Generation Outsourced Visa Services Contract (P098)	AR 2013	1213-Q2	HO	Amber/Green	09/12/2011	01/07/2014	£0.00m	£0.00m			0.00				2.56	HO_0023_1213-Q1,1213-Q2	HO	Amber/Green	Joiner
HO_0025_1213-Q2	Harmondsworth and Colnbrook Retender (P110)	AR 2013	1213-Q2	HO	Green	26/02/2012	31/08/2014	£0.00m	£0.00m			0.00				2.51	HO_0025_1213-Q2,1213-Q2	HO	Green	Joiner
HO_0004_1112-Q1	Immigration and Asylum Biometric System (IABS)	AR 2013	1213-Q2	HO	Amber/Green	01/10/2006	31/12/2012	£24.69m	£27.70m			367.15				6.25	HO_0004_1112-Q1,1213-Q2	HO	Amber/Green	Joiner
HO_0019_1213-Q1	IMPACT	AR 2013	1213-Q2	HO	Amber	01/04/2004	31/03/2012	£5.93m	£5.93m			184.84				8.00	HO_0019_1213-Q1,1213-Q2	HO	Amber	Joiner
HO_0001_1112-Q1	Commercial and Operating Managers Procuring Asylum Support Services (COMPASS)	AR 2013	1213-Q2	HO	Amber/Green	01/07/2009	30/09/2011	£54.38m	£54.35m			686.70				2.25	HO_0001_1112-Q1,1213-Q2	HO	Amber/Green	Joiner
HO_0026_1213-Q2	National Crime Agency (NCA)	AR 2013	1213-Q2	HO	Amber	08/06/2011	01/10/2013	£424.85m	£424.85m			1687.29				2.32	HO_0026_1213-Q2,1213-Q2	HO	Amber	Joiner
HO_0003_1112-Q1	eBorders	AR 2013	1213-Q2	HO	Amber	26/10/2011	01/08/2014	£0.00m	£0.00m			0.00				2.77	HO_0003_1112-Q1,1213-Q2	HO	Amber	Joiner
HO_0005_1112-Q1	Immigration Case Work (ICW)	AR 2013	1213-Q2	HO	Amber/Red	25/06/2007	30/07/2013	£59.97m	£59.97m			374.00				6.10	HO_0005_1112-Q1,1213-Q2	HO	Amber/Red	Joiner
HO_0014_1213-Q1	SOCA Catalyst	AR 2013	1213-Q2	HO	Amber/Green	01/06/2010	30/09/2012	£6.74m	£6.74m			216.70				2.33	HO_0014_1213-Q1,1213-Q2	HO	Amber/Green	Joiner
HO_0015_1213-Q1	College of Policing project (formerly Police Professional Body Project)	AR 2013	1213-Q2	HO	Amber	01/10/2011	30/12/2012	£56.10m	£56.10m			202.80				1.25	HO_0015_1213-Q1,1213-Q2	HO	Amber	Joiner
HO_0017_1213-Q1	Escorting and Travel	AR 2013	1213-Q2	HO	Green	01/07/2008	01/06/2011	£74.88m	£79.17m			283.56				2.92	HO_0017_1213-Q1,1213-Q2	HO	Green	Joiner
HO_0018_1213-Q1	Extend and Blend	AR 2013	1213-Q2	HO	Green	01/10/2009	30/04/2012	£69.98m	£66.23m			503.30				2.58	HO_0018_1213-Q1,1213-Q2	HO	Green	Joiner
HO_0022_1213-Q1	New Passport Programme	AR 2013	1213-Q2	HO	Green	01/03/2008	01/11/2012	£45.71m	£45.27m			455.95				4.67	HO_0022_1213-Q1,1213-Q2	HO	Green	Joiner
HO_0024_1213-Q1	Police ICTCompany Programme	AR 2013	1213-Q2	HO	Amber	01/09/2011	31/08/2012	£0.00m	£0.00m			0.00				1.00	HO_0024_1213-Q1,1213-Q2	HO	Amber	Joiner
MOD_0001_1112-Q1	A400M	AR 2013	1213-Q2	MOD	Amber	17/05/2000	31/12/2046	£189.77m	£189.77m			0.00				46.62	MOD_0001_1112-Q1,1213-Q2	MOD	Amber	Joiner
MOD_0004_1112-Q1	Airseeker	AR 2013	1213-Q2	MOD	Amber/Green	18/03/2010	01/04/2018	£110.49m	£128.88m			1271.12				8.04	MOD_0004_1112-Q1,1213-Q2	MOD	Amber/Green	Joiner
MOD_0009_1112-Q1	BORONA	AR 2013	1213-Q2	MOD	Amber	01/08/2006	01/03/2019	£31.17m	£30.39m			1151.30				12.58	MOD_0009_1112-Q1,1213-Q2	MOD	Amber	Joiner
MOD_0017_1112-Q1	CROWSNEST	AR 2013	1213-Q2	MOD	Exempt	31/03/2013	30/09/2022	£3.50m	£2.00m			0.00				9.50	MOD_0017_1112-Q1,1213-Q2	MOD	Exempt	Joiner
MOD_0019_1112-Q1	Defence Information Infrastructure	AR 2013	1213-Q2	MOD	Amber/Red	01/09/2001	31/03/2015	£850.24m	£831.40m			7331.72				13.58	MOD_0019_1112-Q1,1213-Q2	MOD	Amber/Red	Joiner
MOD_0033_1112-Q1	MARSHALL	AR 2013	1213-Q2	MOD	Exempt	01/04/2006	31/03/2035	£2.02m	£1.13m			0.00				29.00	MOD_0033_1112-Q1,1213-Q2	MOD	Exempt	Joiner
MOD_0035_1112-Q1	Merlin Capability Sustainment Programme (MCSP)	AR 2013	1213-Q2	MOD	Green	01/06/2003	01/10/2016	£87.90m	£87.90m			796.44				13.34	MOD_0035_1112-Q1,1213-Q2	MOD	Green	Joiner
MOD_0036_1112-Q1	Military Afloat Reach and Sustainability	AR 2013	1213-Q2	MOD	Green	25/07/2005	30/06/2019	£52.30m	£52.30m			1860.20				13.93	MOD_0036_1112-Q1,1213-Q2	MOD	Green	Joiner
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2013	1213-Q2	MOD	Exempt	01/04/2008	30/04/2025	£906.28m	£907.61m			12139.30				17.08	MOD_0038_1112-Q1,1213-Q2	MOD	Exempt	Joiner
MOD_0040_1112-Q1	Puma Helicopter Life Extension Programme	AR 2013	1213-Q2	MOD	Amber	30/09/2009	31/10/2014	£97.82m	£89.80m			279.28				5.08	MOD_0040_1112-Q1,1213-Q2	MOD	Amber	Joiner
MOD_0042_1112-Q1	QEC Aircraft Carriers	AR 2013	1213-Q2	MOD	Red	01/12/1998	01/12/2018	£657.72m	£658.50m			0.00				20.00	MOD_0042_1112-Q1,1213-Q2	MOD	Red	Joiner
MOD_0047_1112-Q1	Spearfish Upgrade (SFU)	AR 2013	1213-Q2	MOD	Exempt	30/04/2010	31/12/2022	£23.00m	£23.00m			0.00				12.67	MOD_0047_1112-Q1,1213-Q2	MOD	Exempt	Joiner
MOD_0055_1112-Q1	Type 26 Global Combat Ship (T26 GCS) (P900005700)	AR 2013	1213-Q2	MOD	Exempt	21/07/2008	00/01/1900	£62.94m	£57.80m			0.00				-108.56	MOD_0055_1112-Q1,1213-Q2	MOD	Exempt	Joiner
MOD_0057_1112-Q1	Typhoon	AR 2013	1213-Q2	MOD	Amber/Green	01/06/2003	10/04/2018	£827.79m	£863.68m			18251.98				14.86	MOD_0057_1112-Q1,1213-Q2	MOD	Amber/Green	Joiner
MOD_0061_1112-Q1	WATCHKEEPER	AR 2013	1213-Q2	MOD	Red	01/03/1998	31/12/2040	£91.38m	£59.16m			1079.08				42.84	MOD_0061_1112-Q1,1213-Q2	MOD	Red	Joiner
MOD_0062_1112-Q1	Wildcat	AR 2013	1213-Q2	MOD	Amber	01/12/2001	31/03/2046	£209.02m	£203.88m			1661.37				44.33	MOD_0062_1112-Q1,1213-Q2	MOD	Amber	Joiner
MOD_0065_1112-Q2	Chinook (incl. project Julius)	AR 2013	1213-Q2	MOD	Amber	01/04/2008	31/03/2017	£139.98m	£153.00m			1185.51				9.00	MOD_0065_1112-Q2,1213-Q2	MOD	Amber	Joiner
MOD_0067_1112-Q2	Defence Core Network Services	AR 2013	1213-Q2	MOD	Red	01/12/2009	01/03/2020	£18.00m	£13.79m			5051.05				10.25	MOD_0067_1112-Q2,1213-Q2	MOD	Red	Joiner
MOD_0069_1112-Q2	Logistics Commodities Services Transformation	AR 2013	1213-Q2	MOD	Amber	01/08/2011	01/02/2018	£8.36m	£8.36m			2056.19				6.51	MOD_0069_1112-Q2,1213-Q2	MOD	Amber	Joiner
MOD_0070_1112-Q2	New Employment Model	AR 2013	1213-Q2	MOD	Amber	03/05/2011	01/10/2021	£0.00m	£0.00m			0.00				10.41	MOD_0070_1112-Q2,1213-Q2	MOD	Amber	Joiner
MOD_0071_1112-Q2	Submarine Enterprise Performance Programme	AR 2013	1213-Q2	MOD	Amber	01/05/2010	01/03/2014	£0.00m	£0.00m			0.00				3.83	MOD_0071_1112-Q2,1213-Q2	MOD	Amber	Joiner
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2013	1213-Q2	MOD	Amber	17/03/1997	31/03/2024	£557.30m	£553.26m			9947.22				27.04	MOD_0076_1213-Q1,1213-Q2	MOD	Amber	Joiner
MOD_0077_1213-Q1	Complex Weapons	AR 2013	1213-Q2	MOD	Amber	11/06/2008	00/01/1900	£254.72m	£254.72m			3624.05				-108.45	MOD_0077_1213-Q1,1213-Q2	MOD	Amber	Joiner
MOD_0078_1213-Q1	Core Production Capability	AR 2013	1213-Q2	MOD	Green	01/04/2012	19/03/2023	£115.00m	£75.00m			0.00				10.96	MOD_0078_1213-Q1,1213-Q2	MOD	Green	Joiner
MOD_0079_1213-Q1	Joint Combat Aircraft	AR 2013	1213-Q2	MOD	Amber/Green	01/10/2001	31/03/2050	£192.50m	£163.30m			15979.16				48.50	MOD_0079_1213-Q1,1213-Q2	MOD	Amber/Green	Joiner
MOD_0080_1213-Q1	Successor SSBN 1, 2 & 3	AR 2013	1213-Q2	MOD	Exempt	14/04/2011	00/01/1900	£410.28m	£413.28m			0.00				-111.29	MOD_0080_1213-Q1,1213-Q2	MOD	Exempt	Joiner
MOD_0081_1213-Q2	Future Reserves 2020	AR 2013	1213-Q2	MOD	Amber	01/09/2011	01/03/2018	£0.00m	£0.00m			0.00				6.50	MOD_0081_1213-Q2,1213-Q2	MOD	Amber	Joiner
MOD_0056_1112-Q1	Type 45 Destroyers	AR 2013	1213-Q2	MOD	Green	15/08/2000	31/07/2014	£252.24m	£146.86m			0.00				13.96	MOD_0056_1112-Q1,1213-Q2	MOD	Green	Joiner
MOD_0020_1112-Q1	Defence Infrastructure Transformation Programme	AR 2013	1213-Q2	MOD	Amber	11/01/2011	01/03/2015	£37.86m	£37.86m			124.55	GMPP ID Number			4.13	MOD_0020_1112-Q1,1213-Q2	MOD	Amber	Joiner
MOD_0016_1112-Q1	Corporate Services Transformation Programme	AR 2013	1213-Q2	MOD	Amber/Green	01/07/2010	01/12/2016	£7.40m	£9.01m			38.40				6.42	MOD_0016_1112-Q1,1213-Q2	MOD	Amber/Green	Joiner
MOD_0008_1112-Q1	Beyond Visual Range Air-to-Air Missile (Meteor)	AR 2013	1213-Q2	MOD	Green	20/10/1995	01/12/2019	£60.87m	£60.87m			1185.34				24.11	MOD_0008_1112-Q1,1213-Q2	MOD	Green	Joiner
MOD_0013_1112-Q1	CIPHER	AR 2013	1213-Q2	MOD	Exempt	10/07/2007	31/07/2031	£0.00m	£0.00m			0.00				24.06	MOD_0013_1112-Q1,1213-Q2	MOD	Exempt	Joiner
MOD_0023_1112-Q1	Falcon - 02 (Increments A & C amalgamated at 1/4/11)	AR 2013	1213-Q2	MOD	Green	01/01/1998	31/03/2035	£29.02m	£29.02m			1467.04				37.24	MOD_0023_1112-Q1,1213-Q2	MOD	Green	Joiner
MOD_0048_1112-Q1	Specialist Vehicles - Recce Block 1	AR 2013	1213-Q2	MOD	Green	16/12/2009	00/01/1900	£147.29m	£132.78m			0.00				-109.96	MOD_0048_1112-Q1,1213-Q2	MOD	Green	Joiner
MOD_0060_1112-Q1	Warrior Capability Sustainment Programme	AR 2013	1213-Q2	MOD	Green	31/10/2011	01/03/2022	£49.01m	£66.51m			1667.04				10.33	MOD_0060_1112-Q1,1213-Q2	MOD	Green	Joiner
MOD_0022_1112-Q1	End Crypto Units (ECU)	AR 2013	1213-Q2	MOD	Exempt	31/08/2007	31/08/2040	£0.00m	£0.00m			0.00				33.00	MOD_0022_1112-Q1,1213-Q2	MOD	Exempt	Joiner
MOJ_0002_1112-Q1	Court Estates Reform	AR 2013	1213-Q2	MOJ	Green	10/05/2010	30/09/2014	£9.56m	£14.26m			45.44				4.39	MOJ_0002_1112-Q1,1213-Q2	MOJ	Green	Joiner
MOJ_0003_1112-Q1	Electronic Monitoring	AR 2013	1213-Q2	MOJ	Amber	10/05/2011	30/09/2013	£0.99m	£0.99m			891.96				2.39	MOJ_0003_1112-Q1,1213-Q2	MOJ	Amber	Joiner
MOJ_0004_1112-Q1	Future IT Sourcing Programme (FITS)	AR 2013	1213-Q2	MOJ	Amber	01/03/2011	31/12/2014	£22.10m	£22.10m			138.50				3.84	MOJ_0004_1112-Q1,1213-Q2	MOJ	Amber	Joiner
MOJ_0005_1112-Q1	Court Fines Compliance & Enforcement Project	AR 2013	1213-Q2	MOJ	Amber	31/08/2010	01/02/2014	£4.50m	£2.50m			8.60				3.42	MOJ_0005_1112-Q1,1213-Q2	MOJ	Amber	Joiner
MOJ_0006_1112-Q1	Integrated Delivery Programme	AR 2013	1213-Q2	MOJ	Amber/Green	01/07/2009	30/10/2013	£13.59m	£13.59m			73.89				4.33	MOJ_0006_1112-Q1,1213-Q2	MOJ	Amber/Green	Joiner
MOJ_0007_1112-Q1	Legal Aid Reform Implementation	AR 2013	1213-Q2	MOJ	Amber/Green	01/04/2011	31/10/2013	£9.62m	£9.62m			19.86				2.58	MOJ_0007_1112-Q1,1213-Q2	MOJ	Amber/Green	Joiner
MOJ_0008_1112-Q1	MoJ Shared Services	AR 2013	1213-Q2	MOJ	Red	01/07/2009	07/06/2013	£42.94m	£58.94m			127.09				3.93	MOJ_0008_1112-Q1,1213-Q2	MOJ	Red	Joiner
MOJ_0015_1112-Q2	Quantum Re-compete Project	AR 2013	1213-Q2	MOJ	Amber	18/07/2011	30/11/2012	£103.73m	£103.73m			156.97				1.37	MOJ_0015_1112-Q2,1213-Q2	MOJ	Amber	Joiner
MOJ_0018_1112-Q2	Prison Competitions Phase Two	AR 2013	1213-Q2	MOJ	Amber	13/07/2011	31/01/2014	£4.31m	£4.31m			2403.99				2.55	MOJ_0018_1112-Q2,1213-Q2	MOJ	Amber	Joiner
MOJ_0021_1213-Q2	NOMS Organisational Restructure Programme	AR 2013	1213-Q2	MOJ	Green	01/11/2010	31/10/2013	£4.03m	£4.03m			37.98				3.00	MOJ_0021_1213-Q2,1213-Q2	MOJ	Green	Joiner
MOJ_0020_1213-Q2	National Offender Management Information Systems (NOMIS) Programme	AR 2013	1213-Q2	MOJ	Amber	08/01/2008	31/10/2013	£8.00m	£40.00m			444.00				5.81	MOJ_0020_1213-Q2,1213-Q2	MOJ	Amber	Joiner
MOJ_0009_1112-Q1	Prison Competitions Phase One	AR 2013	1213-Q2	MOJ	Amber/Green	01/04/2009	31/05/2012	£59.63m	£59.63m			878.71				3.16	MOJ_0009_1112-Q1,1213-Q2	MOJ	Amber/Green	Joiner
MOJ_0010_1112-Q1	Prison Escort and Custody Services Re-competition	AR 2013	1213-Q2	MOJ	Green	01/07/2009	28/02/2012	£136.78m	£136.78m			1029.21				2.66	MOJ_0010_1112-Q1,1213-Q2	MOJ	Green	Joiner
MOJ_0011_1112-Q1	Property Services and Works	AR 2013	1213-Q2	MOJ	Amber/Green	01/02/2010	01/09/2015	£155.00m	£155.00m			966.00				5.58	MOJ_0011_1112-Q1,1213-Q2	MOJ	Amber/Green	Joiner
MOJ_0013_1112-Q2	Capacity Management Portfolio (CMP)	AR 2013	1213-Q2	MOJ	Amber/Green	01/07/2011	31/07/2013	£2.31m	£3.24m			15.04				2.08	MOJ_0013_1112-Q2,1213-Q2	MOJ	Amber/Green	Joiner
MOJ_0014_1112-Q2	Community Payback	AR 2013	1213-Q2	MOJ	Amber/Green	01/10/2010	31/12/2012	£6.85m	£6.85m			43.26				2.25	MOJ_0014_1112-Q2,1213-Q2	MOJ	Amber/Green	Joiner
MOJ_0017_1112-Q2	Payment by Results Pilot Programme	AR 2013	1213-Q2	MOJ	Amber/Red	01/04/2011	31/12/2015	£7.63m	£7.63m			119.03				4.75	MOJ_0017_1112-Q2,1213-Q2	MOJ	Amber/Red	Joiner
MOJ_0019_1112-Q4	STC Re-tendering Programme	AR 2013	1213-Q2	MOJ	Amber	15/03/2011	13/07/2015	£0.55m	£0.55m			336.16				4.33	MOJ_0019_1112-Q4,1213-Q2	MOJ	Amber	Joiner
HMT_0003_1112-Q1	Yoda Project (Outsourced Services Retender Project)	AR 2013	1213-Q2	NS&I	Amber/Red	05/04/2009	01/04/2014	£2.50m	£2.50m			0.00				4.99	HMT_0003_1112-Q1,1213-Q2	NS&I	Amber/Red	Joiner
ONS_0001_1112-Q1	2011 Census	AR 2013	1213-Q2	ONS	Amber/Green	01/09/2002	31/03/2014	£21.98m	£21.94m			482.45				11.58	ONS_0001_1112-Q1,1213-Q2	ONS	Amber/Green	Joiner
ONS_0002_1112-Q1	Beyond 2011 Programme	AR 2013	1213-Q2	ONS	Amber/Green	01/04/2011	31/03/2015	£5.00m	£5.75m			25.00				4.00	ONS_0002_1112-Q1,1213-Q2	ONS	Amber/Green	Joiner
ONS_0003_1112-Q4	Web Data Access (WDA) Project	AR 2013	1213-Q2	ONS	Red	01/04/2011	31/03/2013	£6.36m	£7.07m			13.55				2.00	ONS_0003_1112-Q4,1213-Q2	ONS	Red	Joiner
ONS_0004_1213-Q2	Electronic Data Collection (EDC)	AR 2013	1213-Q2	ONS	Amber/Green	02/04/2012	31/03/2014	£0.00m	£0.00m			0.00				1.99	ONS_0004_1213-Q2,1213-Q2	ONS	Amber/Green	Joiner
ONS_0005_1213-Q2	European Systems of Accounting 2010 (ESA 10)	AR 2013	1213-Q2	ONS	Red	05/02/2011	30/06/2020	£0.00m	£0.00m			0.00				9.40	ONS_0005_1213-Q2,1213-Q2	ONS	Red	Joiner
DH_0017_1112-Q1	HPA Chrysalis	AR 2013	1213-Q2	DH	Amber	30/11/2013	17/05/2019	£91.02m	£5.90m			6237.56				5.46	DH_0017_1112-Q1,1213-Q2	DH	Amber	Joiner
DH_0019_1112-Q1	PFI - Royal Liverpool and Broadgreen ('World Class Hospitals; World Class Services - Renewing the Royal Liverpool University Hospital')	AR 2013	1213-Q2	DH	Amber/Green	01/06/2010	01/11/2016	£7.90m	£7.90m			1117.70				6.42	DH_0019_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
DH_0020_1112-Q1	Royal National Orthopaedic Hospital NHS Trust PFI Project	AR 2013	1213-Q2	DH	Green	09/04/2010	28/11/2016	£0.00m	£0.00m			309.93				6.64	DH_0020_1112-Q1,1213-Q2	DH	Green	Joiner
DH_0021_1112-Q1	Sandwell and West Birmingham Hospitals NHS Trust - The Midland Metropolitan Hospital Project	AR 2013	1213-Q2	DH	Amber/Green	31/03/2013	01/04/2019	£0.00m	£0.00m			1116.00				6.00	DH_0021_1112-Q1,1213-Q2	DH	Amber/Green	Joiner
FCO_0001_1112-Q1	ABUJA: New Office and Residence	AR 2013	1213-Q2	FCO	Amber	01/12/2010	01/12/2017	£0.95m	£0.95m			39.00				7.00	FCO_0001_1112-Q1,1213-Q2	FCO	Amber	Joiner
FCO_0006_1213-Q2	UKERP	AR 2013	1213-Q2	FCO	Amber	01/06/2011	01/08/2016	£1.44m	£1.44m			78.79				5.17	FCO_0006_1213-Q2,1213-Q2	FCO	Amber	Joiner
BIS_0001_1112-Q1	BIS Shared Services	AR 2014	1314-Q2	BEIS	Amber	04/05/2011	01/04/2014	£3.79m	£3.79m	£0.00m	0%	19.27			Government Transformation and Service Delivery	2.91	BIS_0001_1112-Q1,1314-Q2	BEIS	Amber	Not new
BIS_0005_1112-Q1	Further Education 24+ Learning Loans Programme	AR 2014	1314-Q2	BEIS	Amber/Red	30/11/2010	31/10/2013	£83.65m	£84.60m	£0.95m	£0.01m	572.29			Government Transformation and Service Delivery	2.92	BIS_0005_1112-Q1,1314-Q2	BEIS	Amber/Red	Not new
BIS_0008_1112-Q1	ICR Monetisation	AR 2014	1314-Q2	DFE	Amber/Red	01/03/2010	31/12/2018	£5.50m	£5.50m	£0.00m	£0.00m	28.61			Government Transformation and Service Delivery	8.84	BIS_0008_1112-Q1,1314-Q2	DFE	Amber/Red	Not new
BIS_0009_1112-Q1	The Francis Crick Institute (formerly UKCMRI)	AR 2014	1314-Q2	BEIS	Amber/Green	01/10/2006	21/12/2017	£112.00m	£112.00m	£0.00m	£0.00m	753.00			Infrastructure and Construction	11.22	BIS_0009_1112-Q1,1314-Q2	BEIS	Amber/Green	Not new
BIS_0011_1213-Q1	SLC Transformation Programme	AR 2014	1314-Q2	BEIS	Amber	01/03/2012	19/03/2016	£19.86m	£19.86m	£0.00m	£0.00m	139.13			Government Transformation and Service Delivery	4.05	BIS_0011_1213-Q1,1314-Q2	BEIS	Amber	Not new
BIS_0003_1112-Q1	Catapult Centres	AR 2014	1314-Q2	BEIS	Amber/Green	01/12/2010	01/04/2013	£127.00m	£127.00m	£0.00m	£0.00m	757.00			Infrastructure and Construction	2.33	BIS_0003_1112-Q1,1314-Q2	BEIS	Amber/Green	Not new
BIS_0004_1112-Q1	FE Capital Investment Programme	AR 2014	1314-Q2	BEIS	Amber/Green	31/05/2010	01/09/2015	£450.37m	£450.37m	£0.00m	£0.00m	5609.46				5.25	BIS_0004_1112-Q1,1314-Q2	BEIS	Amber/Green	Not new
BIS_0006_1112-Q1	Green Investment Bank	AR 2014	1314-Q2	BEIS	Green	01/06/2010	01/09/2012	£0.00m	£0.00m	£0.00m	£0.00m	278.00			Government Transformation and Service Delivery	2.25	BIS_0006_1112-Q1,1314-Q2	BEIS	Green	Not new
BIS_0007_1112-Q1	HE Reform Programme	AR 2014	1314-Q2	BEIS	Amber/Green	30/06/2011	31/12/2015	£970.00m	£1180.00m	£210.00m	£0.22m	4600.00			Government Transformation and Service Delivery	4.50	BIS_0007_1112-Q1,1314-Q2	BEIS	Amber/Green	Not new
CO_0001_1112-Q1	Electoral Registration Transformation Programme	AR 2014	1314-Q2	CO	Amber	01/02/2010	01/01/2016	£26.05m	£26.05m	£0.00m	£0.00m	170.92			Government Transformation and Service Delivery	5.91	CO_0001_1112-Q1,1314-Q2	CO	Amber	Not new
CO_0004_1112-Q1	National Citizen Service	AR 2014	1314-Q2	CO	Amber	01/10/2011	31/12/2014	£104.85m	£104.85m	£0.00m	£0.00m	325.40			Government Transformation and Service Delivery	3.25	CO_0004_1112-Q1,1314-Q2	CO	Amber	Not new
CO_0005_1112-Q1	National Cyber Security Programme	AR 2014	1314-Q2	CO	Amber/Green	01/04/2011	01/04/2016	£180.00m	£179.90m	-£0.10m	£0.00m	860.00			ICT	5.00	CO_0005_1112-Q1,1314-Q2	CO	Amber/Green	Not new
CO_0006_1112-Q2	Public Services Network Programme	AR 2014	1314-Q2	CO	Amber	16/08/2012	13/10/2015	£0.00m	£0.00m	£0.00m	£0.00m	27.29			ICT	3.16	CO_0006_1112-Q2,1314-Q2	CO	Amber	Not new
CO_0002_1112-Q1	G-Cloud Programme (covers Data Centre Consolidation and Application Store)	AR 2014	1314-Q2	CO	Amber/Red			£1.00m	£0.00m	-£1.00m	-£1.00m	6.00				0.00	CO_0002_1112-Q1,1314-Q2	CO	Amber/Red	Not new
DCLG_0005_1112-Q4	CONNECT Project (formerly ICTRelet Project)	AR 2014	1314-Q2	DCLG	Amber/Green	16/11/2011	28/02/2014	£4.83m	£4.83m	£0.00m	£0.00m	24.60			ICT	2.29	DCLG_0005_1112-Q4,1314-Q2	DCLG	Amber/Green	Not new
DCLG_0006_1112-Q4	Enterprise Zones Programme	AR 2014	1314-Q2	DCLG	Amber/Green	23/03/2011	31/03/2038	£111.00m	£0.00m	-£111.00m	-£1.00m	211.00			Government Transformation and Service Delivery	27.02	DCLG_0006_1112-Q4,1314-Q2	DCLG	Amber/Green	Not new
DCLG_0004_1112-Q1	The Future of Local Audit	AR 2014	1314-Q2	DCLG	Amber	30/06/2011	01/11/2012	£0.00m	£0.00m	£0.00m	£0.00m	45.08			Government Transformation and Service Delivery	1.34	DCLG_0004_1112-Q1,1314-Q2	DCLG	Amber	Not new
DCMS_0001_1112-Q1	Broadband Delivery Programme	AR 2014	1314-Q2	DCMS	Amber	06/12/2010	31/12/2016	£99.50m	£99.50m	£0.00m	£0.00m	529.00			Infrastructure and Construction	6.07	DCMS_0001_1112-Q1,1314-Q2	DCMS	Amber	Not new
DCMS_0004_1112-Q1	The Tate Modern Project	AR 2014	1314-Q2	DCMS	Amber/Red	01/01/2010	01/05/2015	-£2.70m	-£2.70m	£0.00m	£0.00m	215.00			Infrastructure and Construction	5.33	DCMS_0004_1112-Q1,1314-Q2	DCMS	Amber/Red	Not new
DCMS_0005_1112-Q1	World Conservation and Exhibitions Centre	AR 2014	1314-Q2	DCMS	Amber/Green	31/03/2008	01/04/2014	£0.00m	£0.00m	£0.00m	£0.00m	135.00			Infrastructure and Construction	6.00	DCMS_0005_1112-Q1,1314-Q2	DCMS	Amber/Green	Not new
DCMS_0006_1112-Q4	Mobile Infrastructure Project	AR 2014	1314-Q2	DCMS	Amber/Green	01/10/2011	31/03/2015	£71.00m	£14.00m	-£57.00m	-£0.80m	155.00			ICT	3.50	DCMS_0006_1112-Q4,1314-Q2	DCMS	Amber/Green	Not new
DCMS_0007_1112-Q4	Urban Broadband Fund - Super-connected City Initiative	AR 2014	1314-Q2	DCMS	Amber/Red	05/12/2012	31/03/2015	£23.00m	£30.00m	£7.00m	£0.30m	150.00			Infrastructure and Construction	2.32	DCMS_0007_1112-Q4,1314-Q2	DCMS	Amber/Red	Not new
DCMS_0003_1112-Q1	Spectrum Clearance and Awards Programme	AR 2014	1314-Q2	DCMS	Amber/Green	22/06/2011	31/12/2014	£86.16m	£55.03m	-£31.13m	-£0.36m	247.43			ICT	3.53	DCMS_0003_1112-Q1,1314-Q2	DCMS	Amber/Green	Not new
BIS_0010_1112-Q4	Urenco Future Options	AR 2014	1314-Q2	BEIS	Exempt	01/02/2010	Data exempt under section 27 and section 43 of the Freedom of Information Act (2000)	£5.89m	£4.09m	-£1.80m	-£0.31m	18.42				0.00	BIS_0010_1112-Q4,1314-Q2	BEIS	Exempt	Not new
DECC_0003_1112-Q1	Dounreay Parent Body Organisation (PBO) - Delivery Phase	AR 2014	1314-Q2	BEIS	Green	21/09/2009	31/12/2025	£150.00m	£158.30m	£8.30m	£0.06m	1578.00			Infrastructure and Construction	16.28	DECC_0003_1112-Q1,1314-Q2	BEIS	Green	Not new
DECC_0004_1112-Q1	Electricity Market Reform Programme	AR 2014	1314-Q2	BEIS	Exempt	10/12/2010	31/12/2030	£20.41m	£20.41m	£0.00m	£0.00m	66.15			Government Transformation and Service Delivery	20.06	DECC_0004_1112-Q1,1314-Q2	BEIS	Exempt	Not new
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2014	1314-Q2	BEIS	Amber	30/06/2008	31/12/2040	£24.00m	£23.74m	-£0.26m	-£0.01m	11626.40			Infrastructure and Construction	32.50	DECC_0005_1112-Q1,1314-Q2	BEIS	Amber	Not new
DECC_0009_1112-Q1	Renewable Heat Incentive	AR 2014	1314-Q2	BEIS	Amber	30/11/2008	10/09/2014	£219.00m	£80.10m	-£138.90m	-£0.63m	48261.80			Government Transformation and Service Delivery	5.78	DECC_0009_1112-Q1,1314-Q2	BEIS	Amber	Not new
DECC_0010_1112-Q1	Smart Meters Implementation Programme	AR 2014	1314-Q2	BEIS	Amber	02/12/2009	30/09/2020	£15.61m	£18.61m	£3.00m	£0.19m	17184.65			Government Transformation and Service Delivery	10.83	DECC_0010_1112-Q1,1314-Q2	BEIS	Amber	Not new
DECC_0011_1112-Q3	Carbon Capture & Storage Commercialisation Programme	AR 2014	1314-Q2	BEIS	Amber	25/10/2011	31/03/2050	£36.60m	£36.56m	-£0.04m	£0.00m	Data exempt under Section 43(2) of the Freedom of Information Act (2000)			Infrastructure and Construction	38.43	DECC_0011_1112-Q3,1314-Q2	BEIS	Amber	Not new
DECC_0012_1213-Q1	FID Enabling for Hinkley Point C	AR 2014	1314-Q2	BEIS	Exempt	01/09/2011	01/02/2015	£3.97m	£6.73m	£2.76m	£0.69m	13.69			Infrastructure and Construction	3.42	DECC_0012_1213-Q1,1314-Q2	BEIS	Exempt	Not new
DECC_0013_1213-Q1	Magnox & Research Sites Restoration Ltd Parent Body Organisations Competition	AR 2014	1314-Q2	BEIS	Amber/Green	03/04/2012	01/09/2028	£0.00m	£0.00m	£0.00m	£0.00m	5716.00				16.41	DECC_0013_1213-Q1,1314-Q2	BEIS	Amber/Green	Not new
DECC_0007_1112-Q1	New Nuclear Programme	AR 2014	1314-Q2	BEIS	Exempt	31/01/2008	31/03/2019	£1.38m	£1.38m	£0.00m	£0.00m	31.29				11.16	DECC_0007_1112-Q1,1314-Q2	BEIS	Exempt	Not new
DECC_0006_1112-Q1	Green Deal	AR 2014	1314-Q2	BEIS	Exempt	20/05/2010	31/12/2030	£200.00m	£200.00m	£0.00m	£0.00m	10311.92			Government Transformation and Service Delivery	20.62	DECC_0006_1112-Q1,1314-Q2	DECC	Exempt	Not new
DEFRA_0001_1112-Q1	CAP Delivery Programme (formerly the Future Options Programme)	AR 2014	1314-Q2	DEFRA	Amber	01/01/2011	01/12/2016	£23.00m	£23.00m	£0.00m	£0.00m	154.78				5.92	DEFRA_0001_1112-Q1,1314-Q2	DEFRA	Amber	Not new
DECC_0014_1314-Q1	FID Enabling for Renewables	AR 2014	1314-Q2	BEIS	Exempt	17/12/2012	31/12/2013	£1.86m	£2.84m	£0.98m	£0.53m	3.69			Infrastructure and Construction	1.04	DECC_0014_1314-Q1,1314-Q2	BEIS	Exempt	Joiner
DEFRA_0004_1112-Q1	Thames Estuary Programme Phase 1 (TEP1)	AR 2014	1314-Q2	DEFRA	Amber/Green	01/04/2010	31/12/2025	£2.04m	£2.30m	£0.26m	£0.13m	318.74			Infrastructure and Construction	15.75	DEFRA_0004_1112-Q1,1314-Q2	DEFRA	Amber/Green	Not new
DFE_0003_1112-Q4	Priority School Building Programme	AR 2014	1314-Q2	DFE	Amber	19/07/2011	31/12/2017	£110.53m	£110.53m	£0.00m	£0.00m	3889.76			Infrastructure and Construction	6.45	DFE_0003_1112-Q4,1314-Q2	DFE	Amber	Not new
DEFRA_0005_1213-Q3	Thames Tideway Tunnel	AR 2014	1314-Q2	DEFRA	Amber/Red	07/09/2010	31/03/2023	£3.13m	£3.13m	£0.00m	£0.00m	4217.88			Infrastructure and Construction	12.56	DEFRA_0005_1213-Q3,1314-Q2	DEFRA	Amber/Red	Joiner
DFE_0001_1112-Q1	Building Schools for the Future (BSF)	AR 2014	1314-Q2	DFE	Amber/Green	01/04/2004	02/07/2017	£335.00m	£350.00m	£15.00m	£0.04m	6302.00			Infrastructure and Construction	13.25	DFE_0001_1112-Q1,1314-Q2	DFE	Amber/Green	Not new
DFID_0001_1112-Q1	St Helena Airport	AR 2014	1314-Q2	DFID	Amber	15/03/2005	31/08/2026	£53.25m	£60.63m	£7.38m	£0.14m	445.11			Infrastructure and Construction	21.46	DFID_0001_1112-Q1,1314-Q2	DFID	Amber	Not new
DFT_0001_1112-Q1	Crossrail	AR 2014	1314-Q2	DFT	Amber/Green	22/07/2008	31/12/2019	£1200.00m	£1199.10m	-£0.90m	£0.00m	14518.98			Infrastructure and Construction	11.44	DFT_0001_1112-Q1,1314-Q2	DFT	Amber/Green	Not new
DFT_0015_1112-Q1	Shared Services Implementation Programme	AR 2014	1314-Q2	DFT	Amber	10/12/2010	01/06/2015	£35.40m	£31.22m	-£4.18m	-£0.12m	222.27			ICT	4.47	DFT_0015_1112-Q1,1314-Q2	DFT	Amber	Not new
DFT_0004_1112-Q1	High Speed Rail Programme	AR 2014	1314-Q2	DFT	Amber/Red	28/02/2011	31/12/2033	£347.60m	£347.60m	£0.00m	£0.00m	42600.00			Infrastructure and Construction	22.84	DFT_0004_1112-Q1,1314-Q2	DFT	Amber/Red	Not new
DFT_0018_1213-Q1	Thameslink, Southern, Great Northern Franchise Competition	AR 2014	1314-Q2	DFT	Amber	26/03/2013	14/09/2014	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)				1.47	DFT_0018_1213-Q1,1314-Q2	DFT	Amber	Not new
DFT_0010_1112-Q1	London, North East and Scotland Franchise Competition	AR 2014	1314-Q2	DFT	Amber	26/03/2013	06/02/2015	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)				1.87	DFT_0010_1112-Q1,1314-Q2	DFT	Amber	Not new
DFT_0002_1112-Q1	ICTContract Let Procurement Programme (CLPP)	AR 2014	1314-Q2	DFT	Amber	01/03/2011	30/12/2015	£8.99m	£8.99m	£0.00m	£0.00m	79.77				4.83	DFT_0002_1112-Q1,1314-Q2	DFT	Amber	Not new
DFT_0005_1112-Q1	Intercity Express Programme (IEP)	AR 2014	1314-Q2	DFT	Amber/Green	01/06/2005	31/12/2019	£6.00m	£5.38m	-£0.62m	-£0.10m	1308.35			Infrastructure and Construction	14.58	DFT_0005_1112-Q1,1314-Q2	DFT	Amber/Green	Not new
DFT_0009_1112-Q1	Periodic Review 2013 (Rail Investment Strategy - HLOS & SOFA)	AR 2014	1314-Q2	DFT	Amber/Green	31/08/2011	31/07/2012	£0.00m	£0.00m	£0.00m	£0.00m	16840.61			Infrastructure and Construction	0.92	DFT_0009_1112-Q1,1314-Q2	DFT	Amber/Green	Not new
DFT_0014_1112-Q1	Search & Rescue Helicopters (SARH)	AR 2014	1314-Q2	DFT	Amber/Green	08/02/2011	08/09/2017	£0.00m	£0.00m	£0.00m	£0.00m	1923.00			Infrastructure and Construction	6.58	DFT_0014_1112-Q1,1314-Q2	DFT	Amber/Green	Not new
DH_0008_1112-Q1	Electronic Prescription Service (EPS) Release 2	AR 2014	1314-Q2	DH	Amber/Red	28/11/2003	31/03/2014	£5.86m	£5.80m	-£0.06m	-£0.01m	36.38			Government Transformation and Service Delivery	10.34	DH_0008_1112-Q1,1314-Q2	DH	Amber/Red	Not new
DFT_0016_1112-Q1	Thameslink	AR 2014	1314-Q2	DFT	Amber/Green	01/07/2005	31/12/2018	£43.04m	£43.04m	£0.00m	£0.00m	4796.04			Infrastructure and Construction	13.50	DFT_0016_1112-Q1,1314-Q2	DFT	Amber/Green	Not new
DH_0015_1112-Q1	NME Programme For IT	AR 2014	1314-Q2	DH	Amber	01/04/2004	31/07/2016	£297.35m	£224.62m	-£72.73m	-£0.24m	5636.19				12.33	DH_0015_1112-Q1,1314-Q2	DH	Amber	Not new
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	AR 2014	1314-Q2	DFT	Amber	01/09/2012	12/03/2020	£5.88m	£5.88m	£0.00m	£0.00m	1519.32			Infrastructure and Construction	7.53	DFT_0020_1314-Q2,1314-Q2	DFT	Amber	Joiner
DH_0018_1112-Q1	Pre-Pandemic Vaccine	AR 2014	1314-Q2	DH	Green	01/10/2011	01/07/2014	Exempt under section 43 of the FoI Act (2000)	Exempt under section 43 of the FoI Act (2000)	Exempt under section 43 of the FoI Act (2000)	n/a	259.00			Government Transformation and Service Delivery	2.75	DH_0018_1112-Q1,1314-Q2	DH	Green	Not new
DH_0003_1112-Q1	Brighton & Sussex University Hospitals NHS Trust (3Ts Programme - The development of a leading teaching, trauma and tertiary care centre)	AR 2014	1314-Q2	DH	No DCA	27/01/2012	24/12/2021	£79.85m	£22.99m	-£56.86m	-£0.71m	500.80			Infrastructure and Construction	9.91	DH_0003_1112-Q1,1314-Q2	DH	No DCA	Not new
DH_0004_1112-Q1	Broadmoor Redevelopment Programme	AR 2014	1314-Q2	DH	No DCA	01/03/2010	01/11/2018	£16.07m	£16.07m	£0.00m	£0.00m	287.43			Infrastructure and Construction	8.67	DH_0004_1112-Q1,1314-Q2	DH	No DCA	Not new
DH_0022_1112-Q1	Summary Care Record (SCR)	AR 2014	1314-Q2	DH	Amber/Green	01/04/2006	31/03/2016	£14.49m	£15.35m	£0.86m	£0.06m	51.11			ICT	10.00	DH_0022_1112-Q1,1314-Q2	DH	Amber/Green	Not new
DH_0023_1112-Q2	London Programme for IT	AR 2014	1314-Q2	DH	Amber/Green	18/12/2003	30/10/2015	£149.58m	£188.15m	£38.57m	£0.26m	628.20				11.87	DH_0023_1112-Q2,1314-Q2	DH	Amber/Green	Not new
DH_0026_1112-Q2	Southern Programme for IT	AR 2014	1314-Q2	DH	Amber/Green	26/01/2004	31/10/2015	£75.98m	£47.47m	-£28.51m	-£0.38m	634.06				11.76	DH_0026_1112-Q2,1314-Q2	DH	Amber/Green	Not new
DH_0014_1112-Q1	NHSmail Service	AR 2014	1314-Q2	DH	Green	31/10/2004	30/06/2014	£22.80m	£20.66m	-£2.14m	-£0.09m	235.45			ICT	9.66	DH_0014_1112-Q1,1314-Q2	DH	Green	Not new
DH_0010_1112-Q1	Health and Care Modernisation Transition Programme	AR 2014	1314-Q2	DH	Amber/Red	01/10/2011	01/04/2013	£364.50m	£328.70m	-£35.80m	-£0.10m	1485.20			Government Transformation and Service Delivery	1.50	DH_0010_1112-Q1,1314-Q2	DH	Amber/Red	Not new
DH_0012_1112-Q1	IMS3	AR 2014	1314-Q2	DH	Amber/Green	16/05/2011	29/03/2013	£14.30m	£22.99m	£8.69m	£0.61m	139.38			Government Transformation and Service Delivery	1.87	DH_0012_1112-Q1,1314-Q2	DH	Amber/Green	Not new
DH_0005_1112-Q1	CAB Variation	AR 2014	1314-Q2	DH	Amber/Red	01/10/2011	15/12/2013	£15.75m	£16.13m	£0.38m	£0.02m	54.24				2.21	DH_0005_1112-Q1,1314-Q2	DH	Amber/Red	Not new
DH_0024_1112-Q2	N3 Extension	AR 2014	1314-Q2	DH	Red	19/02/2004	31/03/2014	£125.33m	£99.23m	-£26.10m	-£0.21m	371.88				10.11	DH_0024_1112-Q2,1314-Q2	DH	Red	Not new
DH_0006_1112-Q1	E&N Herts NHS Trust - LIFT scheme - new QEII hospital in Welwyn Garden City	AR 2014	1314-Q2	DH	No DCA	23/03/2011	01/04/2014	£0.00m	£0.00m	£0.00m	No departmental narrative	67.44			Infrastructure and Construction	3.03	DH_0006_1112-Q1,1314-Q2	DH	No DCA	Not new
DWP_0003_1112-Q1	Child Maintenance Group Change	AR 2014	1314-Q2	DWP	Amber/Green	01/08/2009	27/10/2014	£77.97m	£66.13m	-£35.93m	-£0.35m	1218.33			Government Transformation and Service Delivery	5.24	DWP_0003_1112-Q1,1314-Q2	DWP	Amber/Green	Not new
DWP_0005_1112-Q1	Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme)	AR 2014	1314-Q2	DWP	Amber	01/05/2007	31/10/2018	£106.00m	£94.30m	-£11.70m	-£0.11m	995.40			Government Transformation and Service Delivery	11.50	DWP_0005_1112-Q1,1314-Q2	DWP	Amber	Not new
DWP_0009_1112-Q1	Universal Credit Programme	AR 2014	1314-Q2	DWP	Reset	17/11/2011	Reset	£571.52m	£201.40m	-£370.12m	-£0.65m	Reset			Government Transformation and Service Delivery	0.00	DWP_0009_1112-Q1,1314-Q2	DWP	Reset	Not new
DWP_0011_1112-Q2	Personal Independence Payment Implementation	AR 2014	1314-Q2	DWP	Amber/Red	31/10/2011	31/03/2016	£191.21m	£179.45m	-£11.76m	-£0.06m	2518.57			Government Transformation and Service Delivery	4.42	DWP_0011_1112-Q2,1314-Q2	DWP	Amber/Red	Not new
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	AR 2014	1314-Q2	DWP	Amber/Red	02/04/2012	31/03/2015	£120.60m	£61.83m	-£58.78m	-£0.49m	770.30			Government Transformation and Service Delivery	2.99	DWP_0016_1213-Q2,1314-Q2	DWP	Amber/Red	Not new
DWP_0010_1112-Q1	Work Programme	AR 2014	1314-Q2	DWP	Amber	25/11/2010	18/10/2011	£800.30m	£1002.00m	£201.70m	£0.25m	5626.70				0.90	DWP_0010_1112-Q1,1314-Q2	DWP	Amber	Not new
DWP_0007_1112-Q1	Incapacity Benefit Reassessment	AR 2014	1314-Q2	DWP	Green	09/07/2009	23/03/2012	£142.00m	£142.79m	£0.79m	£0.01m	891.80				2.70	DWP_0007_1112-Q1,1314-Q2	DWP	Green	Not new
DWP_0002_1112-Q1	Central Payment System	AR 2014	1314-Q2	DWP	Green	01/09/2008	21/06/2012	£17.50m	£17.60m	£0.10m	£0.01m	284.90				3.80	DWP_0002_1112-Q1,1314-Q2	DWP	Green	Not new
DWP_0012_1112-Q4	Benefit Cap	AR 2014	1314-Q2	DWP	Amber/Green	19/04/2012	19/12/2013	£25.41m	£14.63m	-£10.78m	-£0.42m	46.31			Government Transformation and Service Delivery	1.67	DWP_0012_1112-Q4,1314-Q2	DWP	Amber/Green	Not new
DWP_0015_1112-Q4	Youth Contract	AR 2014	1314-Q2	DWP	Amber/Green	19/01/2012	21/06/2012	£259.40m	£250.61m	-£8.79m	-£0.03m	741.93				0.42	DWP_0015_1112-Q4,1314-Q2	DWP	Amber/Green	Not new
DWP_0013_1112-Q4	Specialist Disability Employment Programme	AR 2014	1314-Q2	DWP	Amber	16/02/2012	31/07/2014	£32.14m	£7.13m	-£25.01m	-£0.78m	213.34			Government Transformation and Service Delivery	2.45	DWP_0013_1112-Q4,1314-Q2	DWP	Amber	Not new
DWP_0014_1112-Q4	State Pension Reform - Single Tier	AR 2014	1314-Q2	DWP	Amber/Red	27/02/2012	31/10/2017	£14.00m	£8.87m	-£5.13m	-£0.37m	114.16			Government Transformation and Service Delivery	5.68	DWP_0014_1112-Q4,1314-Q2	DWP	Amber/Red	Not new
DH_0007_1112-Q1	E&N Herts NHS Trust - Lister Hospital ('Our Changing Hospitals' Phase 4 Programme)	AR 2014	1314-Q2	DH	No DCA	04/08/2011	17/03/2014	£14.12m	£41.33m	£27.21m	£1.93m	212.03			Infrastructure and Construction	2.62	DH_0007_1112-Q1,1314-Q2	DH	No DCA	Not new
FCO_0004_1112-Q1	ICTRe-procurement	AR 2014	1314-Q2	FCO	Amber	01/01/2011	30/11/2013	£43.70m	£45.20m	£1.50m	£0.03m	242.90			ICT	2.91	FCO_0004_1112-Q1,1314-Q2	FCO	Amber	Not new
DH_0013_1112-Q1	Mersey Care NHS LIFT scheme (TIME - To Improve Mental Health Environments)	AR 2014	1314-Q2	DH	No DCA	30/08/2011	20/01/2015	£0.00m	£0.00m	£0.00m	No departmental narrative	208.80			Infrastructure and Construction	3.39	DH_0013_1112-Q1,1314-Q2	DH	No DCA	Not new
FCO_0002_1112-Q1	Echo	AR 2014	1314-Q2	FCO	Amber/Green	09/06/2009	31/12/2012	£22.82m	£22.82m	£0.00m	£0.00m	182.85			ICT	3.56	FCO_0002_1112-Q1,1314-Q2	FCO	Amber/Green	Not new
FCO_0003_1112-Q1	JAKARTA: New Embassy	AR 2014	1314-Q2	FCO	Amber/Green	01/04/2004	01/09/2014	£5.64m	£2.44m	-£3.20m	-£0.57m	29.45			Infrastructure and Construction	10.42	FCO_0003_1112-Q1,1314-Q2	FCO	Amber/Green	Not new
HMRC_0002_1112-Q1	Debt Staff Reinvestment	AR 2014	1314-Q2	HMRC	Amber/Green	01/04/2011	01/04/2015	£16.89m	£16.89m	£0.00m	£0.00m	56.42			Government Transformation and Service Delivery	4.00	HMRC_0002_1112-Q1,1314-Q2	HMRC	Amber/Green	Not new
HMRC_0004_1112-Q1	One Click	AR 2014	1314-Q2	HMRC	Amber/Green	24/03/2010	01/07/2013	£8.78m	£9.02m	£0.24m	£0.03m	111.06			Government Transformation and Service Delivery	3.27	HMRC_0004_1112-Q1,1314-Q2	HMRC	Amber/Green	Not new
HMRC_0006_1112-Q1	Real Time Information (RTI)	AR 2014	1314-Q2	HMRC	Amber	05/07/2010	31/10/2014	£74.87m	£72.45m	-£2.42m	-£0.03m	333.02			ICT	4.32	HMRC_0006_1112-Q1,1314-Q2	HMRC	Amber	Not new
HMRC_0007_1112-Q2	Expanding the use of Debt Collection Agencies	AR 2014	1314-Q2	HMRC	Amber/Green	01/04/2011	31/03/2015	£15.22m	£14.86m	-£0.36m	-£0.02m	70.68			Government Transformation and Service Delivery	4.00	HMRC_0007_1112-Q2,1314-Q2	HMRC	Amber/Green	Not new
HMRC_0008_1112-Q2	Organised Crime	AR 2014	1314-Q2	HMRC	Amber	01/04/2011	31/10/2013	£25.30m	£25.51m	£0.21m	£0.01m	82.71			Government Transformation and Service Delivery	2.58	HMRC_0008_1112-Q2,1314-Q2	HMRC	Amber	Not new
HMRC_0009_1112-Q2	Volume Crime	AR 2014	1314-Q2	HMRC	Green	01/04/2011	29/05/2013	£11.13m	£11.37m	£0.24m	£0.02m	42.05			Government Transformation and Service Delivery	2.16	HMRC_0009_1112-Q2,1314-Q2	HMRC	Green	Not new
HMRC_0010_1112-Q2	Wider Coverage Project	AR 2014	1314-Q2	HMRC	Amber/Green	14/09/2011	30/06/2015	£174.42m	£172.12m	-£2.30m	-£0.01m	552.25			ICT	3.79	HMRC_0010_1112-Q2,1314-Q2	HMRC	Amber/Green	Not new
HMT_0001_1112-Q1	Equitable Life Payment Scheme	AR 2014	1314-Q2	HMT	Amber	01/05/2010	01/07/2014	£0.00m	£0.00m	£0.00m	£0.00m	0.00			Government Transformation and Service Delivery	4.17	HMT_0001_1112-Q1,1314-Q2	HMT	Amber	Not new
HO_0007_1112-Q1	ISOT Programme	AR 2014	1314-Q2	NCA	Red	01/04/2008	30/09/2013	£41.97m	£38.11m	-£3.86m	-£0.09m	398.65				5.50	HO_0007_1112-Q1,1314-Q2	NCA	Red	Not new
HO_0008_1112-Q1	Schengen Information Systems (SIS) II Programme	AR 2014	1314-Q2	HO	Amber	01/04/2006	31/03/2015	£13.98m	£14.67m	£0.69m	£0.05m	173.18				9.00	HO_0008_1112-Q1,1314-Q2	HO	Amber	Not new
HO_0009_1112-Q1	Transforming the Customer Experience (Formerly A&E)	AR 2014	1314-Q2	HO	Amber	14/05/2007	01/11/2014	£11.35m	£13.56m	£2.21m	£0.19m	202.06			ICT	7.47	HO_0009_1112-Q1,1314-Q2	HO	Amber	Not new
HO_0011_1112-Q2	Disclosure & Barring Programme (formerly SIG Convergence Programme)	AR 2014	1314-Q2	HO	Amber/Red	29/12/2010	01/10/2015	£130.57m	£161.50m	£30.93m	£0.24m	645.67				4.76	HO_0011_1112-Q2,1314-Q2	HO	Amber/Red	Not new
HO_0012_1112-Q3	Communications Capabilities Development programme	AR 2014	1314-Q2	HO	Amber/Red	01/04/2006	01/04/2020	Exempt under Section 24 of the Freedom of Information Act (2000)	Exempt under Section 24 of the Freedom of Information Act (2000)	Exempt under Section 24 of the Freedom of Information Act (2000)	Exempt under Section 24 of the Freedom of Information Act (2000)	Exempt under Section 24 of the Freedom of Information Act (2000)			ICT	14.00	HO_0012_1112-Q3,1314-Q2	HO	Amber/Red	Not new
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2014	1314-Q2	HO	Amber/Red	01/06/2011	31/12/2020	£6.82m	£10.24m	£3.42m	£0.50m	16.75			ICT	9.59	HO_0016_1213-Q1,1314-Q2	HO	Amber/Red	Not new
HO_0023_1213-Q1	Next Generation Outsourced Visa (NGOV) Services Contract	AR 2014	1314-Q2	HO	Amber/Green	09/12/2011	01/07/2014	£1.54m	£1.54m	£0.00m	£0.00m	595.69				2.56	HO_0023_1213-Q1,1314-Q2	HO	Amber/Green	Not new
HO_0025_1213-Q2	Harmondsworth and Colnbrook Retender	AR 2014	1314-Q2	HO	Amber/Green	01/03/2012	31/08/2014	£0.04m	£0.04m	£0.00m	£0.00m	183.52				2.50	HO_0025_1213-Q2,1314-Q2	HO	Amber/Green	Not new
HO_0004_1112-Q1	Immigration and Asylum Biometric System (IABS)	AR 2014	1314-Q2	HO	Green	01/10/2006	31/12/2012	£20.89m	£21.61m	£0.72m	£0.03m	368.49			ICT	6.25	HO_0004_1112-Q1,1314-Q2	HO	Green	Not new
HO_0019_1213-Q1	PND (IMPACT)	AR 2014	1314-Q2	HO	Amber/Red	01/04/2004	30/04/2013	£4.90m	£4.90m	£0.00m	£0.00m	188.49				9.08	HO_0019_1213-Q1,1314-Q2	HO	Amber/Red	Not new
HO_0001_1112-Q1	Commercial and Operating Managers Procuring Asylum Support Services (COMPASS)	AR 2014	1314-Q2	HO	Amber/Green	01/07/2009	30/09/2012	£94.92m	£97.80m	£2.88m	£0.03m	686.73			Government Transformation and Service Delivery	3.25	HO_0001_1112-Q1,1314-Q2	HO	Amber/Green	Not new
HO_0026_1213-Q2	National Crime Agency (NCA)	AR 2014	1314-Q2	HO	Amber/Green	08/06/2011	31/03/2014	£417.70m	£417.70m	£0.00m	£0.00m	1697.80				2.81	HO_0026_1213-Q2,1314-Q2	HO	Amber/Green	Not new
HO_0024_1213-Q1	Police ICTCompany Programme	AR 2014	1314-Q2	HO	Exempt	01/09/2011	Data exempt under section 43 of the Freedom of Information Act (2000)	Data exempt under section 43 of the Freedom of Information Act (2000)	Data exempt under section 43 of the Freedom of Information Act (2000)	n/a	n/a	Data exempt under section 43 of the Freedom of Information Act (2000)				0.00	HO_0024_1213-Q1,1314-Q2	HO	Exempt	Not new
MOD_0001_1112-Q1	A400M	AR 2014	1314-Q2	MOD	Amber/Green	17/05/2000	31/03/2022	£149.00m	£149.00m	£0.00m	£0.00m	Exempt under Section 43 of the Freedom of Information Act (2000)			Military Capability	21.87	MOD_0001_1112-Q1,1314-Q2	MOD	Amber/Green	Not new
MOD_0004_1112-Q1	Airseeker	AR 2014	1314-Q2	MOD	Amber	18/03/2010	01/04/2018	£141.57m	£150.19m	£8.62m	£0.06m	1219.40			Military Capability	8.04	MOD_0004_1112-Q1,1314-Q2	MOD	Amber	Not new
MOD_0009_1112-Q1	BORONA	AR 2014	1314-Q2	MOD	Amber	31/08/2006	31/03/2019	£117.91m	£96.76m	-£21.15m	-£0.18m	1609.49			Government Transformation and Service Delivery	12.58	MOD_0009_1112-Q1,1314-Q2	MOD	Amber	Not new
MOD_0017_1112-Q1	CROWSNEST programme	AR 2014	1314-Q2	MOD	Exempt	31/03/2013	30/09/2022	£2.00m	£3.51m	£1.51m	£0.76m	Exempt under Section 43 of the Freedom of Information Act (2000)			Military Capability	9.50	MOD_0017_1112-Q1,1314-Q2	MOD	Exempt	Not new
MOD_0019_1112-Q1	Defence Information Infrastructure	AR 2014	1314-Q2	MOD	Amber/Red	03/09/2001	21/03/2015	£777.49m	£794.80m	£17.31m	£0.02m	7349.97			ICT	13.54	MOD_0019_1112-Q1,1314-Q2	MOD	Amber/Red	Not new
MOD_0033_1112-Q1	MARSHALL	AR 2014	1314-Q2	MOD	Exempt	03/04/2006	04/10/2020	£1.31m	£1.48m	£0.17m	£0.13m	Exempt under Section 43 of the Freedom of Information Act (2000)			Military Capability	14.51	MOD_0033_1112-Q1,1314-Q2	MOD	Exempt	Not new
MOD_0035_1112-Q1	Merlin Programme	AR 2014	1314-Q2	MOD	Amber/Green	01/06/2003	31/03/2016	£79.10m	£101.19m	£22.09m	£0.28m	755.44			Military Capability	12.83	MOD_0035_1112-Q1,1314-Q2	MOD	Amber/Green	Not new
MOD_0036_1112-Q1	Maritime Sustainment Programme	AR 2014	1314-Q2	MOD	Green	25/07/2005	30/04/2018	£57.30m	£57.30m	£0.00m	£0.00m	1664.03			Military Capability	12.76	MOD_0036_1112-Q1,1314-Q2	MOD	Green	Not new
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2014	1314-Q2	MOD	Exempt	01/04/2008	30/04/2025	£911.74m	£863.11m	-£48.63m	-£0.05m	21883.89			Military Capability	17.08	MOD_0038_1112-Q1,1314-Q2	MOD	Exempt	Not new
MOD_0040_1112-Q1	Puma Helicopter Life Extension Programme	AR 2014	1314-Q2	MOD	Amber/Green	01/02/2007	31/12/2015	£33.39m	£30.03m	-£3.36m	-£0.10m	265.66			Military Capability	8.91	MOD_0040_1112-Q1,1314-Q2	MOD	Amber/Green	Not new
MOD_0042_1112-Q1	Queen Elizabeth Programme	AR 2014	1314-Q2	MOD	Red	01/12/1998	31/03/2023	£781.00m	£781.00m	£0.00m	£0.00m	6221.35			Military Capability	24.33	MOD_0042_1112-Q1,1314-Q2	MOD	Red	Not new
MOD_0047_1112-Q1	Spearfish Upgrade (SFU) Programme	AR 2014	1314-Q2	MOD	Exempt	01/04/2008	31/12/2022	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	£0.00m	£0.00m	Exempt under Section 43(2) of the Freedom of Information Act (2000)				14.75	MOD_0047_1112-Q1,1314-Q2	MOD	Exempt	Not new
MOD_0055_1112-Q1	Type 26 Global Combat Ship (T26 GCS)	AR 2014	1314-Q2	MOD	Exempt	21/07/2008	Exempt under Section 22 of the Freedom of Information Act (2000)	£87.35m	£82.42m	-£4.93m	-£0.06m	Exempt under Section 43 of the Freedom of Information Act (2000)				0.00	MOD_0055_1112-Q1,1314-Q2	MOD	Exempt	Not new
MOD_0057_1112-Q1	Typhoon	AR 2014	1314-Q2	MOD	Amber/Green	06/11/1987	30/03/2024	£1215.66m	£1215.57m	-£0.09m	£0.00m	20147.01			Military Capability	36.40	MOD_0057_1112-Q1,1314-Q2	MOD	Amber/Green	Not new
MOD_0061_1112-Q1	WATCHKEEPER	AR 2014	1314-Q2	MOD	Amber/Red	01/03/1998	31/12/2040	£79.28m	£67.25m	-£12.03m	-£0.15m	1518.26			Military Capability	42.84	MOD_0061_1112-Q1,1314-Q2	MOD	Amber/Red	Not new
MOD_0062_1112-Q1	Wildcat	AR 2014	1314-Q2	MOD	Amber/Red	01/12/2001	31/05/2016	£175.57m	£175.57m	£0.00m	£0.00m	1661.36			Military Capability	14.50	MOD_0062_1112-Q1,1314-Q2	MOD	Amber/Red	Not new
MOD_0065_1112-Q2	CHINOOK (incl Project Julius)	AR 2014	1314-Q2	MOD	Amber	01/04/2008	31/03/2017	£249.82m	£247.23m	-£2.59m	-£0.01m	1053.87			Military Capability	9.00	MOD_0065_1112-Q2,1314-Q2	MOD	Amber	Not new
MOD_0067_1112-Q2	Defence Core Network Services	AR 2014	1314-Q2	MOD	Amber/Red	01/12/2009	02/03/2020	£33.51m	£29.62m	-£3.89m	-£0.12m	5632.58			ICT	10.25	MOD_0067_1112-Q2,1314-Q2	MOD	Amber/Red	Not new
MOD_0069_1112-Q2	Logistics Commodities Services Transformation	AR 2014	1314-Q2	MOD	Exempt	01/08/2011	01/02/2018	£7.14m	£7.14m	£0.00m	£0.00m	Exempt under Section 43 of the Freedom of Information Act (2000)			Government Transformation and Service Delivery	6.51	MOD_0069_1112-Q2,1314-Q2	MOD	Exempt	Not new
MOD_0070_1112-Q2	New Employment Model	AR 2014	1314-Q2	MOD	Amber/Green	02/05/2011	01/10/2021	£16.69m	£17.58m	£0.89m	£0.05m	85.82			Government Transformation and Service Delivery	10.42	MOD_0070_1112-Q2,1314-Q2	MOD	Amber/Green	Not new
MOD_0071_1112-Q2	Submarine Enterprise Performance Programme	AR 2014	1314-Q2	MOD	Amber	31/05/2010	31/03/2014	£4.48m	£0.30m	-£4.18m	-£0.93m	12.42			Government Transformation and Service Delivery	3.83	MOD_0071_1112-Q2,1314-Q2	MOD	Amber	Not new
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2014	1314-Q2	MOD	Amber	17/03/1997	31/03/2024	£549.02m	£534.00m	-£15.02m	-£0.03m	9867.58			Military Capability	27.04	MOD_0076_1213-Q1,1314-Q2	MOD	Amber	Not new
MOD_0077_1213-Q1	Complex Weapons	AR 2014	1314-Q2	MOD	Amber	31/03/2008	00/01/1900	£450.09m	£389.59m	-£60.50m	-£0.13m	15948.67			Military Capability	-108.25	MOD_0077_1213-Q1,1314-Q2	MOD	Amber	Not new
MOD_0078_1213-Q1	Core Production Capability	AR 2014	1314-Q2	MOD	Green	01/04/2012	19/03/2023	£102.97m	£102.86m	-£0.11m	£0.00m	1232.35			Military Capability	10.96	MOD_0078_1213-Q1,1314-Q2	MOD	Green	Not new
MOD_0079_1213-Q1	Joint Combat Aircraft (Lightning)	AR 2014	1314-Q2	MOD	Amber	01/10/2001	31/03/2050	£137.14m	£141.89m	£4.75m	£0.03m	15291.29				48.50	MOD_0079_1213-Q1,1314-Q2	MOD	Amber	Not new
MOD_0080_1213-Q1	Successor SSBN	AR 2014	1314-Q2	MOD	Amber/Green	14/04/2011	Exempt under Section 22 of the Freedom of Information Act (2000)	£472.46m	£507.40m	£34.94m	£0.07m	Exempt under Section 43 of the Freedom of Information Act (2000)				0.00	MOD_0080_1213-Q1,1314-Q2	MOD	Amber/Green	Not new
MOD_0081_1213-Q2	Future Reserves 2020	AR 2014	1314-Q2	MOD	Amber/Red	30/09/2011	31/03/2018	£144.24m	£144.24m	£0.00m	£0.00m	1810.26			Government Transformation and Service Delivery	6.50	MOD_0081_1213-Q2,1314-Q2	MOD	Amber/Red	Not new
MOD_0056_1112-Q1	Type 45 Destroyers	AR 2014	1314-Q2	MOD	Green	15/08/2000	31/03/2014	£109.67m	£85.68m	-£23.99m	-£0.22m	5610.77			Military Capability	13.62	MOD_0056_1112-Q1,1314-Q2	MOD	Green	Not new
MOD_0020_1112-Q1	Defence Infrastructure Transformation Programme	AR 2014	1314-Q2	MOD	Amber	03/01/2011	31/03/2015	£23.62m	£23.62m	£0.00m	£0.00m	125.71				4.24	MOD_0020_1112-Q1,1314-Q2	MOD	Amber	Not new
MOD_0016_1112-Q1	Corporate Services Transformation Programme	AR 2014	1314-Q2	MOD	Amber/Green	02/07/2010	01/12/2016	£13.85m	£14.32m	£0.47m	£0.03m	41.46			Government Transformation and Service Delivery	6.42	MOD_0016_1112-Q1,1314-Q2	MOD	Amber/Green	Not new
MOD_0022_1112-Q1	End Crypto Units (ECU)	AR 2014	1314-Q2	MOD	Exempt	31/08/2007	31/08/2040	£27.81m	£27.35m	-£0.46m	-£0.02m	188.43				33.00	MOD_0022_1112-Q1,1314-Q2	MOD	Exempt	Not new
MOJ_0002_1112-Q1	Court Estates Reform	AR 2014	1314-Q2	MOJ	Green	10/05/2010	30/09/2014	£10.96m	£4.52m	-£6.44m	-£0.59m	45.44			Government Transformation and Service Delivery	4.39	MOJ_0002_1112-Q1,1314-Q2	MOJ	Green	Not new
MOJ_0003_1112-Q1	Electronic Monitoring	AR 2014	1314-Q2	MOJ	Amber/Red	10/05/2011	30/09/2013	£100.54m	£33.42m	-£67.12m	-£0.67m	912.53			Government Transformation and Service Delivery	2.39	MOJ_0003_1112-Q1,1314-Q2	MOJ	Amber/Red	Not new
MOJ_0004_1112-Q1	Future IT Sourcing Programme (FITS)	AR 2014	1314-Q2	MOJ	Amber	01/03/2011	01/04/2016	£31.30m	£31.30m	£0.00m	£0.00m	1375.30			ICT	5.09	MOJ_0004_1112-Q1,1314-Q2	MOJ	Amber	Not new
MOJ_0005_1112-Q1	HMCTS Compliance & Enforcement Services Project	AR 2014	1314-Q2	MOJ	Amber	31/08/2010	31/07/2015	£5.29m	£2.21m	-£3.08m	-£0.58m	12.19			Government Transformation and Service Delivery	4.91	MOJ_0005_1112-Q1,1314-Q2	MOJ	Amber	Not new
MOJ_0006_1112-Q1	Integrated Delivery Programme	AR 2014	1314-Q2	MOJ	Amber	01/07/2009	01/03/2014	£10.81m	£10.81m	£0.00m	£0.00m	68.80			ICT	4.67	MOJ_0006_1112-Q1,1314-Q2	MOJ	Amber	Not new
MOJ_0007_1112-Q1	Legal Aid Reform Implementation	AR 2014	1314-Q2	MOJ	Green	01/04/2011	31/10/2013	£2.80m	£2.80m	£0.00m	£0.00m	19.06			Government Transformation and Service Delivery	2.58	MOJ_0007_1112-Q1,1314-Q2	MOJ	Green	Not new
MOJ_0008_1112-Q1	MoJ Shared Services	AR 2014	1314-Q2	MOJ	Amber/Red	01/01/2009	07/07/2015	£31.30m	£14.24m	-£17.06m	-£0.55m	244.40			ICT	6.51	MOJ_0008_1112-Q1,1314-Q2	MOJ	Amber/Red	Not new
MOJ_0015_1112-Q2	NOMS ICTS Services (NIS) Programme (formally part of Quantum Re-compete Project)	AR 2014	1314-Q2	MOJ	Amber	18/07/2011	30/11/2014	£88.70m	£88.70m	£0.00m	£0.00m	248.82			ICT	3.37	MOJ_0015_1112-Q2,1314-Q2	MOJ	Amber	Not new
MOJ_0018_1112-Q2	Prison Competitions Phase 2	AR 2014	1314-Q2	MOJ	Amber	13/07/2011	31/01/2014	£39.69m	£39.69m	£0.00m	£0.00m	786.69			Government Transformation and Service Delivery	2.55	MOJ_0018_1112-Q2,1314-Q2	MOJ	Amber	Not new
MOJ_0021_1213-Q2	NOMS Organisational Restructure Programme	AR 2014	1314-Q2	MOJ	Green	01/11/2010	30/10/2013	£0.61m	£0.45m	-£0.16m	-£0.26m	38.37				3.00	MOJ_0021_1213-Q2,1314-Q2	MOJ	Green	Not new
MOJ_0020_1213-Q2	National Offender Management Information Systems (NOMIS) Programme	AR 2014	1314-Q2	MOJ	Amber/Green	08/01/2008	31/10/2013	£20.93m	£17.90m	-£3.03m	-£0.14m	477.28				5.81	MOJ_0020_1213-Q2,1314-Q2	MOJ	Amber/Green	Not new
HMT_0003_1112-Q1	Yoda Project (Outsourced Services Retender Project)	AR 2014	1314-Q2	NS&I	Green	05/04/2009	31/05/2014	£0.38m	£0.38m	£0.00m	£0.00m	677.71			Government Transformation and Service Delivery	5.15	HMT_0003_1112-Q1,1314-Q2	NS&I	Green	Not new
ONS_0001_1112-Q1	2011 Census	AR 2014	1314-Q2	ONS	Amber/Green	01/09/2002	31/03/2014	£10.10m	£10.10m	£0.00m	£0.00m	481.63			Government Transformation and Service Delivery	11.58	ONS_0001_1112-Q1,1314-Q2	ONS	Amber/Green	Not new
ONS_0002_1112-Q1	Beyond 2011 Programme	AR 2014	1314-Q2	ONS	Amber/Green	01/04/2011	31/03/2015	£8.00m	£7.52m	-£0.48m	-£0.06m	25.10			Government Transformation and Service Delivery	4.00	ONS_0002_1112-Q1,1314-Q2	ONS	Amber/Green	Not new
ONS_0003_1112-Q4	Web Data Access (WDA) Project	AR 2014	1314-Q2	ONS	Amber/Green	01/04/2011	31/12/2013	£3.36m	£3.36m	£0.00m	£0.00m	16.11			ICT	2.75	ONS_0003_1112-Q4,1314-Q2	ONS	Amber/Green	Not new
ONS_0004_1213-Q2	Electronic Data Collection (EDC)	AR 2014	1314-Q2	ONS	Amber/Red	02/04/2012	31/03/2024	£4.23m	£4.23m	£0.00m	£0.00m	66.35			ICT	11.99	ONS_0004_1213-Q2,1314-Q2	ONS	Amber/Red	Not new
ONS_0005_1213-Q2	ESA10/BPM6 Programme (European Systems of Accounting 2010)	AR 2014	1314-Q2	ONS	Amber	05/02/2011	30/03/2020	£7.11m	£6.66m	-£0.45m	-£0.06m	57.85			Government Transformation and Service Delivery	9.15	ONS_0005_1213-Q2,1314-Q2	ONS	Amber	Not new
BIS_0012_1213-Q4	Business Bank Project	AR 2014	1314-Q2	BEIS	Amber/Green	24/09/2012	15/11/2014	£237.92m	£185.57m	-£52.35m	-£0.22m	1567.45			Government Transformation and Service Delivery	2.14	BIS_0012_1213-Q4,1314-Q2	BEIS	Amber/Green	Joiner
CO_0008_1213-Q4	Next Generation Shared Services	AR 2014	1314-Q2	CO	Amber/Red	28/12/2012	30/04/2015	£8.00m	£8.00m	£0.00m	£0.00m	11.60			Government Transformation and Service Delivery	2.34	CO_0008_1213-Q4,1314-Q2	CO	Amber/Red	Joiner
CO_0009_1314-Q1	New Civil Service 2015 Pension Scheme Implementation	AR 2014	1314-Q2	CO	Amber	15/04/2013	30/06/2016	£0.00m	£0.00m	£0.00m	£0.00m	0.00			Government Transformation and Service Delivery	3.21	CO_0009_1314-Q1,1314-Q2	CO	Amber	Joiner
DH_0017_1112-Q1	PHE Science Hub	AR 2014	1314-Q2	DH	Amber/Red	28/06/2013	30/03/2021	£13.00m	£13.60m	£0.60m	£0.05m	6237.56			Infrastructure and Construction	7.75	DH_0017_1112-Q1,1314-Q2	DH	Amber/Red	Not new
DH_0019_1112-Q1	Royal Liverpool & Broadgreen ('World Class Hospitals; World Class Services - Renewing the Royal Liverpool University Hospital')	AR 2014	1314-Q2	DH	No DCA	01/06/2010	01/11/2016	£7.50m	£7.50m	£0.00m	£0.00m	837.00			Infrastructure and Construction	6.42	DH_0019_1112-Q1,1314-Q2	DH	No DCA	Not new
DH_0020_1112-Q1	Royal National Orthopaedic Hospital (RNOH) NHS Trust PFI Project	AR 2014	1314-Q2	DH	No DCA	15/01/2011	28/11/2016	£0.00m	£0.00m	£0.00m	No departmental narrative	208.79			Infrastructure and Construction	5.87	DH_0020_1112-Q1,1314-Q2	DH	No DCA	Not new
DH_0021_1112-Q1	Sandwell and West Birmingham Hospitals NHS Trust - The Midland Metropolitan Hospital Project	AR 2014	1314-Q2	DH	No DCA	01/10/2008	01/04/2019	£0.00m	£0.00m	£0.00m	No departmental narrative	1116.00			Infrastructure and Construction	10.50	DH_0021_1112-Q1,1314-Q2	DH	No DCA	Not new
DH_0027_1213-Q4	South Acute Programme	AR 2014	1314-Q2	DH	Amber	02/01/2012	27/06/2017	£40.40m	£42.69m	£2.29m	£0.06m	189.06			ICT	5.48	DH_0027_1213-Q4,1314-Q2	DH	Amber	Joiner
DH_0028_1314-Q1	General Practice System of Choice (GPSoC) Replacement	AR 2014	1314-Q2	DH	Amber	26/01/2012	31/03/2015	£100.74m	£96.45m	-£4.29m	-£0.04m	319.03			ICT	3.18	DH_0028_1314-Q1,1314-Q2	DH	Amber	Joiner
DH_0029_1314-Q1	Liaison and Diversion Programme	AR 2014	1314-Q2	DH	Amber/Red	01/04/2011	01/04/2014	£35.00m	£19.37m	-£15.63m	-£0.45m	59.47			ICT	3.00	DH_0029_1314-Q1,1314-Q2	DH	Amber/Red	Joiner
DH_0030_1314-Q1	National Pandemic Flu Service	AR 2014	1314-Q2	DH	Amber	19/03/2012	01/12/2015	Exempt under section 43 of the FoI Act (2000)	Exempt under section 43 of the FoI Act (2000)	N/A	N/A	Exempt under section 43 of the FoI Act (2000)			Government Transformation and Service Delivery	3.70	DH_0030_1314-Q1,1314-Q2	DH	Amber	Joiner
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	AR 2014	1314-Q2	DH	Amber/Red	01/01/2012	01/12/2018	£4.81m	£4.87m	£0.06m	£0.01m	1312.94			Infrastructure and Construction	6.92	DH_0031_1314-Q1,1314-Q2	DH	Amber/Red	Joiner
DH_0032_1314-Q1	Rotavirus Immunisation Programme	AR 2014	1314-Q2	DH	Green	05/03/2009	01/04/2014	£19.20m	£19.20m	£0.00m	£0.00m	70.20			Government Transformation and Service Delivery	5.07	DH_0032_1314-Q1,1314-Q2	DH	Green	Joiner
DH_0033_1314-Q1	Seasonal Flu Extension to Children Programme	AR 2014	1314-Q2	DH	Amber/Red	03/09/2013	01/09/2017	£34.20m	£34.20m	£0.00m	£0.00m	719.50				3.99	DH_0033_1314-Q1,1314-Q2	DH	Amber/Red	Joiner
DH_0035_1314-Q1	Shingles Immunisation Programme	AR 2014	1314-Q2	DH	Amber/Green	11/12/2012	01/11/2013	£51.30m	£51.30m	£0.00m	£0.00m	171.53			Government Transformation and Service Delivery	0.89	DH_0035_1314-Q1,1314-Q2	DH	Amber/Green	Joiner
DH_0036_1314-Q1	Spine 2	AR 2014	1314-Q2	DH	Amber	10/05/2010	30/03/2018	£204.00m	£28.95m	-£175.05m	-£0.86m	857.00			ICT	7.89	DH_0036_1314-Q1,1314-Q2	DH	Amber	Joiner
DH_0038_1314-Q2	Health Visitor Programme	AR 2014	1314-Q2	DH	Amber/Red	31/10/2010	30/06/2015	£123.80m	£123.80m	£0.00m	£0.00m	335.80			Government Transformation and Service Delivery	4.66	DH_0038_1314-Q2,1314-Q2	DH	Amber/Red	Joiner
DH_0039_1314-Q2	NHS e-Referral Service	AR 2014	1314-Q2	DH	Amber/Red	29/03/2012	31/03/2018	£12.43m	£12.43m	£0.00m	£0.00m	212.03			Government Transformation and Service Delivery	6.00	DH_0039_1314-Q2,1314-Q2	DH	Amber/Red	Joiner
DH_0041_1314-Q2	Public Services Network for Health (PSNH)	AR 2014	1314-Q2	DH	Red	29/03/2012	10/10/2014	£11.60m	£0.57m	-£11.03m	-£0.95m	748.16			ICT	2.53	DH_0041_1314-Q2,1314-Q2	DH	Red	Joiner
FCO_0001_1112-Q1	ABUJA: New Office and Residence	AR 2014	1314-Q2	FCO	Amber	01/01/2011	01/12/2017	£0.66m	£0.66m	£0.00m	£0.00m	39.00			Infrastructure and Construction	6.92	FCO_0001_1112-Q1,1314-Q2	FCO	Amber	Not new
FCO_0006_1213-Q2	UKERP	AR 2014	1314-Q2	FCO	Amber	01/06/2011	01/08/2016	£4.43m	£4.43m	£0.00m	£0.00m	82.43			Infrastructure and Construction	5.17	FCO_0006_1213-Q2,1314-Q2	FCO	Amber	Not new
HMRC_0011_1314-Q1	Digital Solutions Portfolio	AR 2014	1314-Q2	HMRC	Amber	14/11/2012	05/04/2015	£37.76m	£32.03m	-£5.73m	-£0.15m	134.29			Government Transformation and Service Delivery	2.39	HMRC_0011_1314-Q1,1314-Q2	HMRC	Amber	Joiner
MOD_0064_1112-Q2	Carrier Enabled Power Projection (CEPP)	AR 2014	1314-Q2	MOD	Amber/Red	31/01/2011	31/12/2030	£2.50m	£1.50m	-£1.00m	-£0.40m	23.75				19.92	MOD_0064_1112-Q2,1314-Q2	MOD	Amber/Red	Joiner
MOD_0066_1112-Q2	Corporate Services Systems Convergence Programme	AR 2014	1314-Q2	MOD	Amber	01/02/2010	28/02/2020	£9.32m	£9.78m	£0.46m	£0.05m	66.55			Government Transformation and Service Delivery	10.07	MOD_0066_1112-Q2,1314-Q2	MOD	Amber	Joiner
MOD_0082_1213-Q3	Next Generation Estates Contracts	AR 2014	1314-Q2	MOD	Amber	02/03/2009	01/04/2014	£20.84m	£20.84m	£0.00m	£0.00m	3328.79			Government Transformation and Service Delivery	5.08	MOD_0082_1213-Q3,1314-Q2	MOD	Amber	Joiner
MOD_0083_1213-Q3	Whole Fleet Management	AR 2014	1314-Q2	MOD	Amber	31/01/2001	30/06/2025	£57.29m	£32.23m	-£25.06m	-£0.44m	1448.56			Military Capability	24.41	MOD_0083_1213-Q3,1314-Q2	MOD	Amber	Joiner
MOD_0084_1213-Q4	Army 2020	AR 2014	1314-Q2	MOD	Amber	31/08/2011	30/04/2020	£0.00m	£0.00m	£0.00m	£0.00m	0.00			Government Transformation and Service Delivery	8.67	MOD_0084_1213-Q4,1314-Q2	MOD	Amber	Joiner
MOD_0085_1314-Q2	Army Basing Programme	AR 2014	1314-Q2	MOD	Amber/Green	22/05/2013	31/03/2020	£0.00m	£0.00m	£0.00m	£0.00m	0.00			Government Transformation and Service Delivery	6.86	MOD_0085_1314-Q2,1314-Q2	MOD	Amber/Green	Joiner
MOD_0086_1314-Q2	Mounted Close Combat	AR 2014	1314-Q2	MOD	Amber/Green	16/03/2010	31/12/2033	£168.82m	£104.65m	-£64.17m	-£0.38m	9631.30			Military Capability	23.79	MOD_0086_1314-Q2,1314-Q2	MOD	Amber/Green	Joiner
MOD_0087_1314-Q2	The Material Strategy	AR 2014	1314-Q2	MOD	Amber	02/05/2011	01/04/2016	£32.57m	£31.35m	-£1.22m	-£0.04m	66.15				4.92	MOD_0087_1314-Q2,1314-Q2	MOD	Amber	Joiner
MOJ_0021_1314-Q1	Common Platform	AR 2014	1314-Q2	MOJ	Amber/Red	01/11/2012	31/01/2017	£0.00m	£0.00m	£0.00m	No departmental narrative	0.00			ICT	4.25	MOJ_0021_1314-Q1,1314-Q2	MOJ	Amber/Red	Joiner
MOJ_0022_1314-Q1	Legal Aid Transformation	AR 2014	1314-Q2	MOJ	Amber	04/12/2012	31/12/2014	£0.00m	£0.00m	£0.00m	No departmental narrative	0.00			Government Transformation and Service Delivery	2.07	MOJ_0022_1314-Q1,1314-Q2	MOJ	Amber	Joiner
MOJ_0023_1314-Q1	New Prison -Wales	AR 2014	1314-Q2	MOJ	Green	10/01/2013	31/05/2018	£0.00m	£0.00m	£0.00m	No departmental narrative	252.30			Infrastructure and Construction	5.39	MOJ_0023_1314-Q1,1314-Q2	MOJ	Green	Joiner
MOJ_0024_1314-Q1	Prison Unit Cost Programme	AR 2014	1314-Q2	MOJ	Amber/Green	20/11/2012	01/12/2016	£117.50m	£117.50m	£0.00m	£0.00m	212.00			Government Transformation and Service Delivery	4.03	MOJ_0024_1314-Q1,1314-Q2	MOJ	Amber/Green	Joiner
MOJ_0025_1314-Q1	Rehabilitation Programme	AR 2014	1314-Q2	MOJ	Exempt	05/11/2012	Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests)	Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests)	Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests)	Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests)	Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests)	Exempt - Section 43(2) of Freedom of Information Act 2000 (Prejudice to Commercial Interests)			Government Transformation and Service Delivery	0.00	MOJ_0025_1314-Q1,1314-Q2	MOJ	Exempt	Joiner
MOJ_0026_1314-Q1	Transforming Youth Custody	AR 2014	1314-Q2	MOJ	Amber	05/11/2012	15/07/2018	£0.00m	£0.00m	£0.00m	No departmental narrative	0.00			Government Transformation and Service Delivery	5.69	MOJ_0026_1314-Q1,1314-Q2	MOJ	Amber	Joiner
MOJ_0027_1314-Q2	CJS Efficiency Programme Phase 2	AR 2014	1314-Q2	MOJ	Amber	30/04/2013	31/12/2016	£11.65m	£11.33m	-£0.32m	-£0.03m	102.85			ICT	3.67	MOJ_0027_1314-Q2,1314-Q2	MOJ	Amber	Joiner
MOJ_0028_1314-Q2	HMCTS Reform	AR 2014	1314-Q2	MOJ	Amber/Red	21/03/2013	01/01/2016	£0.00m	£0.00m	£0.00m	No departmental narrative	0.00			Government Transformation and Service Delivery	2.78	MOJ_0028_1314-Q2,1314-Q2	MOJ	Amber/Red	Joiner
BIS_0013_1213-Q4	Royal Mail Sale of Shares	AR 2014	1314-Q2	BEIS	Amber	01/04/2012	17/10/2013	£380.00m	£350.00m	-£30.00m	-£0.08m	31.20				1.54	BIS_0013_1213-Q4,1314-Q2	BEIS	Amber	Joiner
DH_0037_1314-Q1	Spine Extension	AR 2014	1314-Q2	DH	Amber/Green	28/06/2011	31/12/2014	£57.99m	£55.51m	-£2.48m	-£0.04m	104.51			ICT	3.51	DH_0037_1314-Q1,1314-Q2	DH	Amber/Green	Joiner
DH_0040_1314-Q2	NHSmail2	AR 2014	1314-Q2	DH	Amber	29/03/2012	18/11/2014	£0.83m	£1.44m	£0.61m	£0.73m	157.38			ICT	2.64	DH_0040_1314-Q2,1314-Q2	DH	Amber	Joiner
DFT_0019_1314-Q1	Essex Thameside Franchise Competition	AR 2014	1314-Q2	DFT	Amber/Red	26/03/2013	30/11/2014	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)	Exempt under Section 43(2) of the Freedom of Information Act (2000)				1.68	DFT_0019_1314-Q1,1314-Q2	DFT	Amber/Red	Joiner
DH_0034_1314-Q1	Shared Services Programme	AR 2014	1314-Q2	DH	Amber	01/12/2011	31/03/2015	£3.97m	£3.97m	£0.00m	£0.00m	72.19			Government Transformation and Service Delivery	3.33	DH_0034_1314-Q1,1314-Q2	DH	Amber	Joiner
HO_0028_1314-Q2	Tinsley House Immigration Removal Centre Expansion	AR 2014	1314-Q2	HO	Amber/Green	01/01/2013	01/06/2015	£0.08m	£0.08m	£0.00m	£0.00m	217.38			Infrastructure and Construction	2.41	HO_0028_1314-Q2,1314-Q2	HO	Amber/Green	Joiner
CO_0007_1213-Q4	Civil Service Reform Programme	AR 2014	1314-Q2	CO	Amber	19/06/2012	31/12/2015	£2.99m	£2.99m	£0.00m	£0.00m	10.67			Government Transformation and Service Delivery	3.53	CO_0007_1213-Q4,1314-Q2	CO	Amber	Joiner
MOD_0074_1112-Q3	Defence Reform Programme	AR 2014	1314-Q2	MOD	Amber/Green	01/07/2011	01/04/2014	£1.78m	£1.78m	£0.00m	£0.00m	4.63			Government Transformation and Service Delivery	2.75	MOD_0074_1112-Q3,1314-Q2	MOD	Amber/Green	Joiner
HO_0027_1314-Q2	Border Systems Programme	AR 2014	1314-Q2	HO	Amber/Red	29/04/2013	30/03/2024	£0.00m	£0.00m	£0.00m	£0.00m	0.00			ICT	10.92	HO_0027_1314-Q2,1314-Q2	HO	Amber/Red	Joiner
BIS_0001_1112-Q1	BIS Shared Services	AR 2015	1415-Q2	BEIS	Amber	04/05/2011	01/04/2015	£1.90m	£1.90m	£0.00m	£0.00m	26.19			Government Transformation and Service Delivery	3.91	BIS_0001_1112-Q1,1415-Q2	BEIS	Amber	Not new
BIS_0005_1112-Q1	Further Education 24+ Learning Loans Programme	AR 2015	1415-Q2	BEIS	Amber/Green	30/11/2010	31/10/2013	£242.66m	£122.55m	-£120.11m	-£0.49m	303.00			Government Transformation and Service Delivery	2.92	BIS_0005_1112-Q1,1415-Q2	BEIS	Amber/Green	Not new
BIS_0008_1112-Q1	ICR Monetisation	AR 2015	1415-Q2	DFE	Amber	01/03/2010	31/12/2018	£6.96m	£3.88m	-£3.08m	-£0.44m	29.48			Government Transformation and Service Delivery	8.84	BIS_0008_1112-Q1,1415-Q2	DFE	Amber	Not new
BIS_0009_1112-Q1	The Francis Crick Institute (formerly UKCMRI)	AR 2015	1415-Q2	BEIS	Amber/Green	01/10/2006	21/12/2017	£18.00m	£18.00m	£0.00m	£0.00m	753.00		£469.42m	Infrastructure and Construction	11.22	BIS_0009_1112-Q1,1415-Q2	BEIS	Amber/Green	Not new
BIS_0011_1213-Q1	SLC Transformation Programme	AR 2015	1415-Q2	BEIS	Amber/Red	19/03/2012	31/03/2017	£46.29m	£46.46m	£0.17m	£0.00m	139.13			Government Transformation and Service Delivery	5.03	BIS_0011_1213-Q1,1415-Q2	BEIS	Amber/Red	Not new
CO_0001_1112-Q1	Electoral Registration Transformation Programme	AR 2015	1415-Q2	CO	Amber/Green	01/02/2010	31/03/2016	£65.50m	£65.50m	£0.00m	£0.00m	173.65	£173.65m		Government Transformation and Service Delivery	6.16	CO_0001_1112-Q1,1415-Q2	CO	Amber/Green	Not new
CO_0004_1112-Q1	National Citizen Service	AR 2015	1415-Q2	CO	Amber/Green	01/10/2011	01/03/2015	£140.00m	£140.00m	£0.00m	£0.00m	437.00	£225.00m		Government Transformation and Service Delivery	3.41	CO_0004_1112-Q1,1415-Q2	CO	Amber/Green	Not new
CO_0005_1112-Q1	National Cyber Security Programme	AR 2015	1415-Q2	CO	Green	01/04/2011	01/04/2016	£210.00m	£220.00m	£10.00m	£0.05m	860.00	£860.00m		ICT	5.00	CO_0005_1112-Q1,1415-Q2	CO	Green	Not new
DCLG_0006_1112-Q4	Enterprise Zones Programme	AR 2015	1415-Q2	DCLG	Amber	23/03/2011	31/03/2038	£220.30m	£220.30m	£0.00m	£0.00m	228.30			Government Transformation and Service Delivery	27.02	DCLG_0006_1112-Q4,1415-Q2	DCLG	Amber	Not new
DCLG_0004_1112-Q1	The Future of Local Audit	AR 2015	1415-Q2	DCLG	Amber	30/06/2011	01/11/2012	£45.08m	£12.08m	-£33.00m	-£0.73m	45.08			Government Transformation and Service Delivery	1.34	DCLG_0004_1112-Q1,1415-Q2	DCLG	Amber	Not new
DCMS_0001_1112-Q1	Broadband Delivery Programme	AR 2015	1415-Q2	DCMS	Amber/Green	06/12/2010	31/12/2017	£321.35m	£300.67m	-£20.68m	-£0.06m	792.36		£0.00m	Infrastructure and Construction	7.07	DCMS_0001_1112-Q1,1415-Q2	DCMS	Amber/Green	Not new
DCMS_0004_1112-Q1	The Tate Modern Project	AR 2015	1415-Q2	DCMS	Amber/Red	01/01/2010	31/12/2016	£0.00m	£0.00m	£0.00m	0%	215.00		£164.69m	Infrastructure and Construction	7.00	DCMS_0004_1112-Q1,1415-Q2	DCMS	Amber/Red	Not new
DCMS_0005_1112-Q1	World Conservation and Exhibitions Centre	AR 2015	1415-Q2	DCMS	Green	31/03/2008	01/04/2014	£0.00m	£0.00m	£0.00m	0%	135.00		£112.45m	Infrastructure and Construction	6.00	DCMS_0005_1112-Q1,1415-Q2	DCMS	Green	Not new
DCMS_0006_1112-Q4	Mobile Infrastructure Project	AR 2015	1415-Q2	DCMS	Amber/Red	01/10/2011	31/03/2016	£71.54m	£25.59m	-£45.95m	-£0.64m	157.11		£0.00m	ICT	4.50	DCMS_0006_1112-Q4,1415-Q2	DCMS	Amber/Red	Not new
DCMS_0007_1112-Q4	Urban Broadband Fund - Super-Connected City Initiative	AR 2015	1415-Q2	DCMS	Amber	05/12/2012	31/03/2015	£117.58m	£107.24m	-£10.34m	-£0.09m	152.08		£0.00m	Infrastructure and Construction	2.32	DCMS_0007_1112-Q4,1415-Q2	DCMS	Amber	Not new
BIS_0010_1112-Q4	Project Eagle (formerly Urenco Future Options)	AR 2015	1415-Q2	BEIS	Amber/Red	01/02/2010	01/10/2015	£5.30m	£3.65m	-£1.65m	-£0.31m	23.73			Government transformation and Service Delivery	5.66	BIS_0010_1112-Q4,1415-Q2	BEIS	Amber/Red	Not new
DECC_0003_1112-Q1	Dounreay Parent Body Organisation (PBO) - Delivery Phase	AR 2015	1415-Q2	BEIS	Green	21/09/2009	31/12/2025	£162.86m	£162.86m	£0.00m	£0.00m	1678.22			Infrastructure and Construction	16.28	DECC_0003_1112-Q1,1415-Q2	BEIS	Green	Not new
DECC_0004_1112-Q1	ELECTRICITY MARKET REFORM PROGRAMME	AR 2015	1415-Q2	BEIS	Amber	16/12/2010	31/12/2030	£36.10m	£35.10m	-£1.00m	-£0.03m	47513.95		£47226.29m	Government Transformation and Service Delivery	20.04	DECC_0004_1112-Q1,1415-Q2	BEIS	Amber	Not new
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2015	1415-Q2	BEIS	Amber	12/06/2008	31/12/2040	£26.38m	£26.38m	£0.00m	£0.00m	11252.48			Infrastructure and Construction	32.55	DECC_0005_1112-Q1,1415-Q2	BEIS	Amber	Not new
DECC_0009_1112-Q1	Renewable Heat Incentive	AR 2015	1415-Q2	BEIS	Amber	30/11/2008	01/12/2014	£231.79m	£233.00m	£1.21m	£0.01m	43658.13		£0.00m	Government Transformation and Service Delivery	6.00	DECC_0009_1112-Q1,1415-Q2	BEIS	Amber	Not new
DECC_0010_1112-Q1	Smart Meters Implementation Programme	AR 2015	1415-Q2	BEIS	Amber	02/12/2009	31/12/2020	£11.38m	£13.14m	£1.76m	£0.15m	19258.00		£19026.57m	Government Transformation and Service Delivery	11.08	DECC_0010_1112-Q1,1415-Q2	BEIS	Amber	Not new
DECC_0011_1112-Q3	Carbon Capture & Storage Commercialisation Programme	AR 2015	1415-Q2	BEIS	Amber	25/10/2011	31/03/2050	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)		exempt	Infrastructure and Construction	38.43	DECC_0011_1112-Q3,1415-Q2	BEIS	Amber	Not new
DECC_0012_1213-Q1	FID Enabling for Hinkley Point C	AR 2015	1415-Q2	BEIS	Exempt	01/09/2011	30/04/2015	£3.68m	£6.61m	£2.93m	£0.79m	14470.33		£14451.93m	Infrastructure and Construction	3.66	DECC_0012_1213-Q1,1415-Q2	BEIS	Exempt	Not new
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	AR 2015	1415-Q2	BEIS	Amber/Green	03/04/2012	01/09/2028	£428.00m	£390.00m	-£38.00m	-£0.09m	3860.00			Infrastructure and Construction	16.41	DECC_0013_1213-Q1,1415-Q2	BEIS	Amber/Green	Not new
DEFRA_0001_1112-Q1	CAP Delivery Programme	AR 2015	1415-Q2	DEFRA	Amber/Red	01/01/2011	01/12/2016	£54.59m	£52.84m	-£1.76m	-£0.03m	154.79			Government transformation and Service Delivery	5.92	DEFRA_0001_1112-Q1,1415-Q2	DEFRA	Amber/Red	Not new
DECC_0014_1314-Q1	FID Enabling for Renewables	AR 2015	1415-Q2	BEIS	Amber	17/12/2012	30/11/2014	£1.02m	£1.18m	£0.15m	£0.15m	22486.20		£22481.72m	Infrastructure and Construction	1.95	DECC_0014_1314-Q1,1415-Q2	BEIS	Amber	Not new
DEFRA_0004_1112-Q1	Thames Estuary Programme Phase 1 (TEP1)	AR 2015	1415-Q2	DEFRA	Green	01/04/2010	31/12/2025	£1.37m	£2.15m	£0.78m	£0.57m	318.42			Infrastructure and Construction	15.75	DEFRA_0004_1112-Q1,1415-Q2	DEFRA	Green	Not new
DEFRA_0005_1213-Q3	Thames Tideway Tunnel	AR 2015	1415-Q2	DEFRA	Amber/Red	07/09/2010	31/12/2023	£2.48m	£2.48m	£0.00m	£0.00m	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)		exempt	Infrastructure and Construction	13.31	DEFRA_0005_1213-Q3,1415-Q2	DEFRA	Amber/Red	Not new
DFE_0001_1112-Q1	Building Schools for the Future (BSF)	AR 2015	1415-Q2	DFE	Green	01/04/2004	02/07/2017	£95.00m	£95.00m	£0.00m	£0.00m	6283.00		£0.00m	Infrastructure and Construction	13.25	DFE_0001_1112-Q1,1415-Q2	DFE	Green	Not new
DFE_0004_1415-Q2	Priority School Building Programme - Capital	AR 2015	1415-Q2	DFE	Amber/Red	19/07/2011	01/01/2019	£607.30m	£358.40m	-£248.90m	-£0.41m	2023.34			Infrastructure and Construction	7.46	DFE_0004_1415-Q2,1415-Q2	DFE	Amber/Red	Joiner
DFE_0005_1415-Q2	Priority School Building Programme - Private Finance	AR 2015	1415-Q2	DFE	Amber/Red	19/07/2011	31/07/2017	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept			Infrastructure and Construction	6.03	DFE_0005_1415-Q2,1415-Q2	DFE	Amber/Red	Joiner
DFID_0001_1112-Q1	St Helena Airport	AR 2015	1415-Q2	DFID	Amber/Green	15/03/2005	31/08/2026	£33.54m	£34.57m	£1.03m	£0.03m	445.17		£159.62m	Infrastructure and Construction	21.46	DFID_0001_1112-Q1,1415-Q2	DFID	Amber/Green	Not new
DFT_0001_1112-Q1	Crossrail	AR 2015	1415-Q2	DFT	Amber/Green	22/07/2008	31/12/2019	£1083.50m	£1083.50m	£0.00m	£0.00m	14714.37		£9478.00m	Infrastructure and Construction	11.44	DFT_0001_1112-Q1,1415-Q2	DFT	Amber/Green	Not new
DFT_0015_1112-Q1	Shared Services Implementation Programme	AR 2015	1415-Q2	DFT	Amber/Red	10/12/2010	01/10/2015	£21.70m	£23.91m	£2.21m	£0.10m	222.27		£0.00m	ICT	4.81	DFT_0015_1112-Q1,1415-Q2	DFT	Amber/Red	Not new
DFT_0004_1112-Q1	High Speed Rail Programme	AR 2015	1415-Q2	DFT	Amber/Red	28/02/2011	31/12/2033	£380.01m	£483.01m	£103.00m	£0.27m	42559.51		£0.00m	Infrastructure and Construction	22.84	DFT_0004_1112-Q1,1415-Q2	DFT	Amber/Red	Not new
DFT_0005_1112-Q1	Intercity Express Programme (IEP)	AR 2015	1415-Q2	DFT	Amber/Green	01/06/2005	06/02/2020	£4.00m	£5.01m	£1.01m	£0.25m	1308.35		£1222.00m	Infrastructure and Construction	14.68	DFT_0005_1112-Q1,1415-Q2	DFT	Amber/Green	Not new
DFT_0009_1112-Q1	Periodic Review 2013 (Rail Investment Strategy - HLOS & SOFA)	AR 2015	1415-Q2	DFT	Green	17/08/2011	31/07/2012	£3164.93m	£2764.10m	-£1083.03m	-£0.28m	16840.61		£0.00m	Infrastructure and Construction	0.96	DFT_0009_1112-Q1,1415-Q2	DFT	Green	Not new
DFT_0014_1112-Q1	Search & Rescue Helicopters (SARH)	AR 2015	1415-Q2	DFT	Amber/Green	08/02/2011	08/09/2017	£0.00m	£0.00m	£0.00m	0%	1923.00		£0.00m	Infrastructure and Construction	6.58	DFT_0014_1112-Q1,1415-Q2	DFT	Amber/Green	Not new
DH_0003_1112-Q1	Brighton & Sussex University Hospitals NHS Trust (3Ts Programme - The development of a leading teaching, trauma and tertiary care centre)	AR 2015	1415-Q2	DH Capital	Amber/Green	27/01/2012	24/12/2021	£28.13m	£33.75m	£5.62m	£0.20m	445.76		£0.00m	Infrastructure and Construction	9.91	DH_0003_1112-Q1,1415-Q2	DH	Amber/Green	Not new
DFT_0016_1112-Q1	Thameslink	AR 2015	1415-Q2	DFT	Amber	01/07/2005	31/12/2018	£40.70m	£36.64m	-£4.06m	-£0.10m	4897.82		£4547.25m	Infrastructure and Construction	13.50	DFT_0016_1112-Q1,1415-Q2	DFT	Amber	Not new
DH_0004_1112-Q1	Broadmoor Redevelopment Programme	AR 2015	1415-Q2	DH Capital	Green	10/07/2012	11/02/2020	£42.11m	£25.92m	-£16.19m	-£0.38m	287.42		£0.00m	Infrastructure and Construction	7.59	DH_0004_1112-Q1,1415-Q2	DH	Green	Not new
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	AR 2015	1415-Q2	DFT	Amber/Green	01/09/2012	30/09/2021	£23.50m	£17.49m	-£6.01m	-£0.26m	1519.32		£0.00m	Infrastructure and Construction	9.08	DFT_0020_1314-Q2,1415-Q2	DFT	Amber/Green	Not new
DH_0007_1112-Q1	E&N Herts NHS Trust - Lister Hospital ('Our Changing Hospitals' Phase 4 Programme)	AR 2015	1415-Q2	DH Capital	Amber/Green	04/08/2011	17/03/2014	£0.00m	£21.56m	£21.56m		212.03			Infrastructure and Construction	2.62	DH_0007_1112-Q1,1415-Q2	DH	Amber/Green	Not new
DFT_0021_1314-Q3	Rail Franchising Programme	AR 2015	1415-Q2	DFT	Amber	26/03/2013	31/12/2022	-£2.60m	£3.30m	£5.90m	-£2.27m	134.20		£0.00m	Infrastructure and Construction	9.77	DFT_0021_1314-Q3,1415-Q2	DFT	Amber	Joiner
DH_0008_1112-Q1	Electronic Prescription Service (EPS) Release 2	AR 2015	1415-Q2	DH Non Capital	Amber	01/01/2003	31/12/2016	£4.28m	£4.55m	£0.27m	£0.06m	77.74		£0.00m	Government Transformation and Service Delivery	14.00	DH_0008_1112-Q1,1415-Q2	DH	Amber	Not new
DH_0013_1112-Q1	Mersey Care NHS LIFT scheme (TIME - To Improve Mental Health Environments)	AR 2015	1415-Q2	DH Capital	Amber/Green	16/09/2011	20/01/2015	£1.74m	£0.69m	-£1.05m	-£0.60m	208.80		£0.00m	Infrastructure and Construction	3.35	DH_0013_1112-Q1,1415-Q2	DH	Amber/Green	Not new
DH_0015_1112-Q1	CSC LSP Delivery Programme	AR 2015	1415-Q2	DH Non Capital	Amber/Red	23/06/2003	31/07/2016	£213.76m	£134.11m	-£79.65m	-£0.37m	2294.07			ICT	13.11	DH_0015_1112-Q1,1415-Q2	DH	Amber/Red	Not new
DWP_0003_1112-Q1	Child Maintenance Group Change	AR 2015	1415-Q2	DWP	Amber/Green	01/08/2009	31/12/2015	£86.66m	£69.18m	-£17.48m	-£0.20m	1218.33			Government Transformation and Service Delivery	6.41	DWP_0003_1112-Q1,1415-Q2	DWP	Amber/Green	Not new
DWP_0005_1112-Q1	Automatic Enrolment Programme	AR 2015	1415-Q2	DWP	Amber	01/05/2007	30/11/2018	£117.50m	£120.21m	£2.71m	£0.02m	995.40			Government Transformation and Service Delivery	11.58	DWP_0005_1112-Q1,1415-Q2	DWP	Amber	Not new
DWP_0009_1112-Q1	Universal Credit	AR 2015	1415-Q2	DWP	Amber/Red	17/11/2011	30/04/2020	£323.80m	£323.80m	£0.00m	£0.00m	15844.02		£0.00m	Government Transformation and Service Delivery	8.45	DWP_0009_1112-Q1,1415-Q2	DWP	Amber/Red	Not new
DWP_0011_1112-Q2	Personal Independence Payment Programme	AR 2015	1415-Q2	DWP	Amber/Red	31/10/2011	31/03/2016	£231.48m	£303.61m	£72.13m	£0.31m	2525.94			Government Transformation and Service Delivery	4.42	DWP_0011_1112-Q2,1415-Q2	DWP	Amber/Red	Not new
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	AR 2015	1415-Q2	DWP	Amber	02/04/2012	31/03/2017	£111.30m	£98.81m	-£12.49m	-£0.11m	838.90		£0.00m	Government Transformation and Service Delivery	4.99	DWP_0016_1213-Q2,1415-Q2	DWP	Amber	Not new
DH_0017_1112-Q1	PHE Science Hub	AR 2015	1415-Q2	DH Capital	Amber	09/08/2013	30/03/2021	£29.68m	£15.67m	-£14.01m	-£0.47m	10447.57		£0.00m	Infrastructure and Construction	7.64	DH_0017_1112-Q1,1415-Q2	DH	Amber	Not new
FCO_0004_1112-Q1	ICTRe-procurement	AR 2015	1415-Q2	FCO	Amber/Red	01/01/2011	30/11/2013	£53.40m	£49.80m	-£3.60m	-£0.07m	242.10			ICT	2.91	FCO_0004_1112-Q1,1415-Q2	FCO	Amber/Red	Not new
HMRC_0002_1112-Q1	Debt Staff Reinvestment	AR 2015	1415-Q2	HMRC	Green	01/04/2011	01/04/2015	£22.54m	£22.54m	£0.00m	£0.00m	56.42			Government Transformation and Service Delivery	4.00	HMRC_0002_1112-Q1,1415-Q2	HMRC	Green	Not new
HMRC_0004_1112-Q1	One Click	AR 2015	1415-Q2	HMRC	Amber/Green	24/03/2010	16/10/2013	£8.65m	£8.73m	£0.08m	£0.01m	111.06			Government Transformation and Service Delivery	3.56	HMRC_0004_1112-Q1,1415-Q2	HMRC	Amber/Green	Not new
HMRC_0006_1112-Q1	Real Time Information (RTI)	AR 2015	1415-Q2	HMRC	Amber/Green	05/07/2010	30/06/2015	£45.87m	£45.70m	-£0.17m	£0.00m	333.02			ICT	4.99	HMRC_0006_1112-Q1,1415-Q2	HMRC	Amber/Green	Not new
HMRC_0007_1112-Q2	Expanding the use of Debt Collection Agencies	AR 2015	1415-Q2	HMRC	Green	01/04/2011	31/03/2015	£14.49m	£14.12m	-£0.37m	-£0.03m	69.29			Government Transformation and Service Delivery	4.00	HMRC_0007_1112-Q2,1415-Q2	HMRC	Green	Not new
HMRC_0008_1112-Q2	Organised Crime	AR 2015	1415-Q2	HMRC	Amber/Green	01/11/2010	30/06/2014	£22.04m	£21.73m	-£0.31m	-£0.01m	74.70			Government Transformation and Service Delivery	3.66	HMRC_0008_1112-Q2,1415-Q2	HMRC	Amber/Green	Not new
HMRC_0009_1112-Q2	Volume Crime	AR 2015	1415-Q2	HMRC	Green	01/04/2011	29/05/2013	£11.05m	£11.02m	-£0.03m	£0.00m	42.05			Government Transformation and Service Delivery	2.16	HMRC_0009_1112-Q2,1415-Q2	HMRC	Green	Not new
HMT_0001_1112-Q1	Equitable Life Payment Scheme	AR 2015	1415-Q2	HMT	Green	01/05/2010	31/12/2015	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept			Government Transformation and Service Delivery	5.67	HMT_0001_1112-Q1,1415-Q2	HMT	Green	Not new
HO_0007_1112-Q1	NCA ICTModernisation Programme (was SOCA ISOT)	AR 2015	1415-Q2	NCA	Amber/Red	01/04/2008	30/09/2013	£33.73m	£38.74m	£5.01m	£0.15m	398.65			ICT	5.50	HO_0007_1112-Q1,1415-Q2	NCA	Amber/Red	Not new
HO_0008_1112-Q1	Schengen Information System (SIS II) Programme	AR 2015	1415-Q2	HO	Amber/Red	01/04/2006	31/03/2015	£14.25m	£16.66m	£2.41m	£0.17m	190.57		£0.00m	ICT	9.00	HO_0008_1112-Q1,1415-Q2	HO	Amber/Red	Not new
HO_0009_1112-Q1	Transforming the Customer Experience (Formerly A&E)	AR 2015	1415-Q2	HO	Amber/Green	14/05/2007	01/11/2014	£11.00m	£11.26m	£0.26m	£0.02m	201.41			ICT	7.47	HO_0009_1112-Q1,1415-Q2	HO	Amber/Green	Not new
HO_0011_1112-Q2	Disclosure and Barring Service (DBS) Programme	AR 2015	1415-Q2	HO	Amber	29/12/2010	31/07/2015	£136.00m	£136.00m	£0.00m	£0.00m	741.63			ICT	4.59	HO_0011_1112-Q2,1415-Q2	HO	Amber	Not new
HO_0012_1112-Q3	Communications Capabilities Development Programme	AR 2015	1415-Q2	HO	Amber	01/04/2006	01/04/2020	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)		exempt	ICT	14.00	HO_0012_1112-Q3,1415-Q2	HO	Amber	Not new
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2015	1415-Q2	HO	Amber	01/06/2011	31/12/2020	£9.60m	£13.20m	£3.60m	£0.38m	5367.08			Government Transformation and Service Delivery	9.59	HO_0016_1213-Q1,1415-Q2	HO	Amber	Not new
HO_0023_1213-Q1	Next Generation Outsourced Visa Services Contract	AR 2015	1415-Q2	HO	Green	01/12/2011	01/07/2014	£85.01m	£83.90m	-£1.11m	-£0.01m	595.70			ICT	2.58	HO_0023_1213-Q1,1415-Q2	HO	Green	Not new
HO_0025_1213-Q2	Harmondsworth and Colnbrook Retender (P110)	AR 2015	1415-Q2	HO	Green	01/03/2012	01/06/2015	£16.98m	£16.98m	£0.00m	£0.00m	199.62			ICT	3.25	HO_0025_1213-Q2,1415-Q2	HO	Green	Not new
MOD_0001_1112-Q1	A400M	AR 2015	1415-Q2	Military Capability	Amber/Green	01/07/1997	31/03/2022	£646.36m	£640.69m	-£5.67m	-£0.01m	3833.15			Military Capability	24.75	MOD_0001_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0004_1112-Q1	Airseeker	AR 2015	1415-Q2	Military Capability	Amber/Green	18/03/2010	01/04/2018	£132.22m	£127.96m	-£4.26m	-£0.03m	753.11			Military Capability	8.04	MOD_0004_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0009_1112-Q1	BORONA	AR 2015	1415-Q2	MOD Transformation	Amber/Green	31/08/2006	31/03/2019	£161.10m	£147.01m	-£14.09m	-£0.09m	1557.10			Government Transformation and Service Delivery	12.58	MOD_0009_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0017_1112-Q1	Crowsnest Programme	AR 2015	1415-Q2	Military Capability	Green	26/03/2013	30/09/2022	£19.86m	£14.60m	-£5.26m	-£0.26m	Data Exempt under Section 43 of the Freedom of Information Act (2000)		exempt	Military Capability	9.51	MOD_0017_1112-Q1,1415-Q2	MOD	Green	Not new
MOD_0019_1112-Q1	Defence Information Infrastructure	AR 2015	1415-Q2	Military Capability	Amber/Red	03/09/2001	21/03/2015	£770.20m	£787.39m	£17.19m	£0.02m	7432.41			ICT	13.54	MOD_0019_1112-Q1,1415-Q2	MOD	Amber/Red	Not new
MOD_0033_1112-Q1	MARSHALL	AR 2015	1415-Q2	Military Capability	Amber	03/04/2006	04/10/2020	£41.50m	£41.50m	£0.00m	£0.00m	716.60			Military Capability	14.51	MOD_0033_1112-Q1,1415-Q2	MOD	Amber	Not new
MOD_0035_1112-Q1	Merlin Programme	AR 2015	1415-Q2	Military Capability	Green	01/06/2003	31/03/2016	£90.50m	£25.67m	-£64.83m	-£0.72m	806.44			Military Capability	12.83	MOD_0035_1112-Q1,1415-Q2	MOD	Green	Not new
MOD_0036_1112-Q1	Maritime Sustainment Programme	AR 2015	1415-Q2	Military Capability	Amber/Green	25/07/2005	30/04/2018	£68.71m	£75.73m	£7.02m	£0.10m	596.51			Military Capability	12.76	MOD_0036_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2015	1415-Q2	Military Capability	Exempt	01/04/2008	30/04/2025	£1090.98m	£1064.55m	-£26.43m	-£0.02m	20957.16			Military Capability	17.08	MOD_0038_1112-Q1,1415-Q2	MOD	Exempt	Not new
MOD_0040_1112-Q1	Puma Helicopter Life Extension Programme	AR 2015	1415-Q2	Military Capability	Amber/Green	01/02/2007	31/12/2015	£10.15m	£8.46m	-£1.69m	-£0.17m	377.79			Military Capability	8.91	MOD_0040_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0042_1112-Q1	Queen Elizabeth Programme	AR 2015	1415-Q2	Military Capability	Amber/Red	01/12/1998	31/03/2023	£844.81m	£810.06m	-£34.75m	-£0.04m	7209.06			Military Capability	24.33	MOD_0042_1112-Q1,1415-Q2	MOD	Amber/Red	Not new
MOD_0047_1112-Q1	Spearfish Upgrade Programme	AR 2015	1415-Q2	Military Capability	Amber/Green	01/04/2008	31/12/2022	£21.65m	£23.55m	£1.90m	£0.09m	428.89			Military Capability	14.75	MOD_0047_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0055_1112-Q1	Type 26 Global Combat Ship Programme	AR 2015	1415-Q2	Military Capability	Exempt	21/07/2008	31/12/2034	£182.00m	£169.51m	-£12.49m	-£0.07m	Data Exempt under Section 43 of the Freedom of Information Act (2000)		exempt	Military Capability	26.44	MOD_0055_1112-Q1,1415-Q2	MOD	Exempt	Not new
MOD_0057_1112-Q1	Typhoon	AR 2015	1415-Q2	Military Capability	Amber/Green	06/11/1987	30/03/2024	£1069.46m	£1023.39m	-£46.07m	-£0.04m	19210.68			Military Capability	36.40	MOD_0057_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0061_1112-Q1	WATCHKEEPER	AR 2015	1415-Q2	Military Capability	Amber/Green	01/03/1998	31/12/2040	£63.37m	£68.04m	£4.67m	£0.07m	1167.56			Military Capability	42.84	MOD_0061_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0062_1112-Q1	Wildcat	AR 2015	1415-Q2	Military Capability	Amber/Green	01/12/2001	31/05/2016	£106.87m	£105.45m	-£1.42m	-£0.01m	1601.52			Military Capability	14.50	MOD_0062_1112-Q1,1415-Q2	MOD	Amber/Green	Not new
MOD_0065_1112-Q2	CHINOOK (incl Project Julius)	AR 2015	1415-Q2	Military Capability	Amber/Green	01/04/2008	31/03/2017	£240.03m	£226.56m	-£13.47m	-£0.06m	1048.33			Military Capability	9.00	MOD_0065_1112-Q2,1415-Q2	MOD	Amber/Green	Not new
MOD_0067_1112-Q2	Defence Core Network Services	AR 2015	1415-Q2	Military Capability	Amber/Red	01/12/2009	02/03/2020	£46.27m	£24.85m	-£21.42m	-£0.46m	6113.33			ICT	10.25	MOD_0067_1112-Q2,1415-Q2	MOD	Amber/Red	Not new
MOD_0069_1112-Q2	Logistics Commodities Services Transformation	AR 2015	1415-Q2	MOD Transformation	Amber	01/08/2011	01/02/2018	£12.17m	£11.85m	-£0.32m	-£0.03m	803.73			Government Transformation and Service Delivery	6.51	MOD_0069_1112-Q2,1415-Q2	MOD	Amber	Not new
MOD_0070_1112-Q2	New Employment Model	AR 2015	1415-Q2	MOD Transformation	Amber	02/05/2011	01/10/2021	£12.29m	£8.56m	-£3.73m	-£0.30m	66.72			Government Transformation and Service Delivery	10.42	MOD_0070_1112-Q2,1415-Q2	MOD	Amber	Not new
MOD_0071_1112-Q2	Submarine Enterprise Performance Programme	AR 2015	1415-Q2	Military Capability	Amber	31/05/2010	31/03/2014	£0.28m	£0.23m	-£0.05m	-£0.18m	15.73			Government Transformation and Service Delivery	3.83	MOD_0071_1112-Q2,1415-Q2	MOD	Amber	Not new
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2015	1415-Q2	Military Capability	Amber/Red	17/03/1997	31/03/2024	£558.10m	£645.59m	£87.49m	£0.16m	9860.64			Military Capability	27.04	MOD_0076_1213-Q1,1415-Q2	MOD	Amber/Red	Not new
MOD_0077_1213-Q1	Complex Weapons	AR 2015	1415-Q2	Military Capability	Amber	31/03/2008	01/04/2032	£508.61m	£527.70m	£19.09m	£0.04m	17490.60			Military Capability	24.00	MOD_0077_1213-Q1,1415-Q2	MOD	Amber	Not new
MOD_0078_1213-Q1	Core Production Capability	AR 2015	1415-Q2	Military Capability	Amber	23/04/2012	23/08/2024	£144.15m	£144.23m	£0.08m	£0.00m	1268.97			Military Capability	12.33	MOD_0078_1213-Q1,1415-Q2	MOD	Amber	Not new
MOD_0079_1213-Q1	Lightning II Programme	AR 2015	1415-Q2	Military Capability	Amber	01/10/2001	31/03/2035	£306.68m	£290.40m	-£16.28m	-£0.05m	13203.23			Military Capability	33.49	MOD_0079_1213-Q1,1415-Q2	MOD	Amber	Not new
MOD_0080_1213-Q1	Successor SSBN	AR 2015	1415-Q2	Military Capability	Amber/Red	14/04/2011	Data Exempt under Section 35 of the Freedom of Information Act (2000)	£623.19m	£628.04m	£4.85m	£0.01m	Data Exempt under Section 43 of the Freedom of Information Act (2000)		exempt	Military Capability	0.00	MOD_0080_1213-Q1,1415-Q2	MOD	Amber/Red	Not new
MOD_0081_1213-Q2	Future Reserves 2020	AR 2015	1415-Q2	MOD Transformation	Red	30/09/2011	31/03/2018	£174.00m	£174.00m	£0.00m	£0.00m	1819.00			Government Transformation and Service Delivery	6.50	MOD_0081_1213-Q2,1415-Q2	MOD	Red	Not new
MOJ_0002_1112-Q1	Court Estates Reform	AR 2015	1415-Q2	MOJ	Green	10/05/2010	30/09/2014	£0.59m	£0.09m	-£0.50m	-£0.85m	45.44		£0.00m	Government Transformation and Service Delivery	4.39	MOJ_0002_1112-Q1,1415-Q2	MOJ	Green	Not new
MOJ_0003_1112-Q1	Electronic Monitoring	AR 2015	1415-Q2	MOJ	Amber	10/05/2011	30/09/2013	£49.90m	£49.90m	£0.00m	£0.00m	425.83			Government Transformation and Service Delivery	2.39	MOJ_0003_1112-Q1,1415-Q2	MOJ	Amber	Not new
MOJ_0004_1112-Q1	Future IT Sourcing Programme (FITS)	AR 2015	1415-Q2	MOJ	Amber	01/03/2011	01/09/2016	£77.00m	£77.00m	£0.00m	£0.00m	1205.00			ICT	5.51	MOJ_0004_1112-Q1,1415-Q2	MOJ	Amber	Not new
MOJ_0005_1112-Q1	HMCTS Compliance & Enforcement Services Project	AR 2015	1415-Q2	MOJ	Amber/Green	21/06/2012	31/07/2015	£47.67m	£52.29m	£4.62m	£0.10m	439.20		£0.00m	Government Transformation and Service Delivery	3.11	MOJ_0005_1112-Q1,1415-Q2	MOJ	Amber/Green	Not new
MOJ_0006_1112-Q1	Integrated Delivery Programme	AR 2015	1415-Q2	MOJ	Amber	01/07/2009	01/09/2014	£3.94m	£3.97m	£0.02m	£0.01m	71.49		£0.00m	ICT	5.17	MOJ_0006_1112-Q1,1415-Q2	MOJ	Amber	Not new
MOJ_0007_1112-Q1	Legal Aid Reform Implementation	AR 2015	1415-Q2	MOJ	Green	01/04/2011	31/10/2013	£0.00m	£0.00m	£0.00m	0%	19.06			Government Transformation and Service Delivery	2.58	MOJ_0007_1112-Q1,1415-Q2	MOJ	Green	Not new
MOJ_0008_1112-Q1	MoJ Shared Services	AR 2015	1415-Q2	MOJ	Amber	04/10/2009	07/07/2015	£27.60m	£30.50m	£2.90m	£0.11m	357.30		£0.00m	ICT	5.75	MOJ_0008_1112-Q1,1415-Q2	MOJ	Amber	Not new
MOJ_0015_1112-Q2	NOMS ICTS Services (NIS) Programme (formally part of Quantum Re-compete Project)	AR 2015	1415-Q2	MOJ	Red	18/07/2011	30/11/2014	£89.40m	£95.80m	£6.40m	£0.07m	248.82			ICT	3.37	MOJ_0015_1112-Q2,1415-Q2	MOJ	Red	Not new
MOJ_0018_1112-Q2	Prison Competitions Phase 2	AR 2015	1415-Q2	MOJ	Green	13/07/2011	31/01/2014	£70.13m	£32.61m	-£37.52m	-£0.53m	786.71			Government Transformation and Service Delivery	2.55	MOJ_0018_1112-Q2,1415-Q2	MOJ	Green	Not new
HMT_0003_1112-Q1	YODA Project (Outsourced Services Retender Project)	AR 2015	1415-Q2	NS&I	Green	05/04/2009	31/05/2014	£184.19m	£184.19m	£0.00m	£0.00m	722.39		£0.00m	Government Transformation and Service Delivery	5.15	HMT_0003_1112-Q1,1415-Q2	NS&I	Green	Not new
ONS_0001_1112-Q1	2011 Census	AR 2015	1415-Q2	ONS	Green	01/09/2002	30/09/2014	£4.01m	£3.85m	-£0.16m	-£0.04m	482.09		£0.00m	Government Transformation and Service Delivery	12.08	ONS_0001_1112-Q1,1415-Q2	ONS	Green	Not new
ONS_0002_1112-Q1	Beyond 2011	AR 2015	1415-Q2	ONS	Amber/Green	01/04/2011	31/03/2015	£8.00m	£7.99m	-£0.01m	£0.00m	25.00			Government Transformation and Service Delivery	4.00	ONS_0002_1112-Q1,1415-Q2	ONS	Amber/Green	Not new
ONS_0003_1112-Q4	Web Data Access (WDA) Project	AR 2015	1415-Q2	ONS	Green	01/04/2011	31/12/2013	£0.60m	£1.01m	£0.41m	£0.68m	16.11		£0.00m	ICT	2.75	ONS_0003_1112-Q4,1415-Q2	ONS	Green	Not new
ONS_0004_1213-Q2	Electronic Data Collection	AR 2015	1415-Q2	ONS	Amber	27/01/2014	01/11/2019	£6.64m	£6.64m	£0.00m	£0.00m	40.04			ICT	5.76	ONS_0004_1213-Q2,1415-Q2	ONS	Amber	Not new
ONS_0005_1213-Q2	ESA10/BPM6 Programme (European Systems of Accounting 2010)	AR 2015	1415-Q2	ONS	Amber/Green	05/02/2011	30/03/2020	£11.16m	£9.36m	-£1.80m	-£0.16m	57.84			Government Transformation and Service Delivery	9.15	ONS_0005_1213-Q2,1415-Q2	ONS	Amber/Green	Not new
BIS_0012_1213-Q4	Business Bank Project	AR 2015	1415-Q2	BEIS	Amber/Green	24/09/2012	01/11/2014	£312.00m	£322.40m	£10.40m	£0.03m	495.70			Government Transformation and Service Delivery	2.10	BIS_0012_1213-Q4,1415-Q2	BEIS	Amber/Green	Not new
CO_0008_1213-Q4	Next Generation Shared Services	AR 2015	1415-Q2	CO	Amber/Red	28/12/2012	30/04/2015	£12.00m	£12.00m	£0.00m	£0.00m	31.10	£31.10m		Government Transformation and Service Delivery	2.34	CO_0008_1213-Q4,1415-Q2	CO	Amber/Red	Not new
CO_0009_1314-Q1	New Civil Service 2015 Pension Scheme Implementation	AR 2015	1415-Q2	CO	Amber	15/04/2013	30/06/2016	£11.70m	£11.40m	-£0.30m	-£0.03m	13.40			Government Transformation and Service Delivery	3.21	CO_0009_1314-Q1,1415-Q2	CO	Amber	Not new
CPS_0001_1314-Q4	ICTProcurement Programme	AR 2015	1415-Q2	CPS	Amber	01/10/2013	31/03/2016	£3.00m	£3.00m	£0.00m	£0.00m	183.98			ICT	2.50	CPS_0001_1314-Q4,1415-Q2	CPS	Amber	Joiner
DH_0018_1112-Q1	Pre-Pandemic Vaccine	AR 2015	1415-Q2	DH Non Capital	Amber/Red	01/10/2011	01/07/2014	Data Exempt under section 43 (2) of the Freedom of Information Act 2000	Data Exempt under section 43 (2) of the Freedom of Information Act 2001	Data Exempt under section 43 (2) of the Freedom of Information Act 2002	Data Exempt under section 43 (2) of the Freedom of Information Act 2003	Data Exempt under section 43 (2) of the Freedom of Information Act 2004		exempt	Government Transformation and Service Delivery	2.75	DH_0018_1112-Q1,1415-Q2	DH	Amber/Red	Not new
DECC_0015_1415-Q1	Household Energy Efficiency	AR 2015	1415-Q2	BEIS	Amber/Red	30/04/2014	31/05/2015	£164.00m	£164.00m	£0.00m	£0.00m	4723.61		£4068.22m	Government Transformation and Service Delivery	1.08	DECC_0015_1415-Q1,1415-Q2	BEIS	Amber/Red	Joiner
DH_0019_1112-Q1	Royal Liverpool & Broadgreen ('World Class Hospitals; World Class Services - Renewing the Royal Liverpool University Hospital')	AR 2015	1415-Q2	DH Capital	Green	01/06/2010	01/11/2016	£19.50m	£19.50m	£0.00m	£0.00m	828.00		£7.50m	Infrastructure and Construction	6.42	DH_0019_1112-Q1,1415-Q2	DH	Green	Not new
DH_0020_1112-Q1	Royal National Orthopaedic Hospital (RNOH) NHS Trust PFI Project	AR 2015	1415-Q2	DH Capital	Green	15/01/2011	28/11/2016	£0.00m	£0.00m	£0.00m	0%	53.54			Infrastructure and Construction	5.87	DH_0020_1112-Q1,1415-Q2	DH	Green	Not new
DH_0021_1112-Q1	Sandwell and West Birmingham Hospitals NHS Trust - The Midland Metropolitan Hospital Project	AR 2015	1415-Q2	DH Capital	Amber/Green	01/10/2008	15/10/2018	£0.00m	£0.00m	£0.00m	0%	1036.30			Infrastructure and Construction	10.04	DH_0021_1112-Q1,1415-Q2	DH	Amber/Green	Not new
DH_0022_1112-Q1	Summary Care Record (SCR)	AR 2015	1415-Q2	DH Non Capital	Amber	01/04/2006	31/03/2016	£7.77m	£10.95m	£3.19m	£0.41m	51.10			ICT	10.00	DH_0022_1112-Q1,1415-Q2	DH	Amber	Not new
DH_0023_1112-Q2	BT LSP (London)	AR 2015	1415-Q2	DH Non Capital	Amber/Red	18/12/2003	30/10/2015	£97.50m	£121.00m	£23.50m	£0.24m	1108.97			ICT	11.87	DH_0023_1112-Q2,1415-Q2	DH	Amber/Red	Not new
DH_0026_1112-Q2	BT LSP (South)	AR 2015	1415-Q2	DH Non Capital	Amber/Red	26/01/2004	31/10/2015	£40.11m	£68.77m	£28.66m	£0.71m	634.06			ICT	11.76	DH_0026_1112-Q2,1415-Q2	DH	Amber/Red	Not new
DH_0027_1213-Q4	South Acute Programme	AR 2015	1415-Q2	DH Non Capital	Amber/Green	01/11/2011	27/06/2017	£40.91m	£11.05m	-£29.86m	-£0.73m	189.06		£0.00m	ICT	5.65	DH_0027_1213-Q4,1415-Q2	DH	Amber/Green	Not new
DH_0028_1314-Q1	General Practice System of Choice (GPSoC) Replacement	AR 2015	1415-Q2	DH Non Capital	Amber	26/01/2012	31/03/2015	£79.64m	£90.34m	£10.70m	£0.13m	309.42			ICT	3.18	DH_0028_1314-Q1,1415-Q2	DH	Amber	Not new
DH_0029_1314-Q1	Liaison and Diversion Programme	AR 2015	1415-Q2	DH Non Capital	Amber	01/04/2011	01/04/2014	£50.00m	£25.40m	-£24.60m	-£0.49m	213.17			ICT	3.00	DH_0029_1314-Q1,1415-Q2	DH	Amber	Not new
DH_0030_1314-Q1	National Pandemic Flu Service	AR 2015	1415-Q2	DH Non Capital	Red	19/03/2012	01/12/2015	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)		exempt	Government Transformation and Service Delivery	3.70	DH_0030_1314-Q1,1415-Q2	DH	Red	Not new
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	AR 2015	1415-Q2	DH Non Capital	Amber	01/01/2012	31/12/2018	£9.40m	£9.40m	£0.00m	£0.00m	1295.53		£34.80m	Infrastructure and Construction	7.00	DH_0031_1314-Q1,1415-Q2	DH	Amber	Not new
DH_0032_1314-Q1	Rotavirus Immunisation Programme	AR 2015	1415-Q2	DH Non Capital	Green	05/03/2009	01/04/2014	£25.50m	£25.50m	£0.00m	£0.00m	70.20		£0.00m	Government Transformation and Service Delivery	5.07	DH_0032_1314-Q1,1415-Q2	DH	Green	Not new
DH_0033_1314-Q1	Childhood Flu Immunisation Programme	AR 2015	1415-Q2	DH Non Capital	Amber	16/09/2013	01/09/2018	£59.83m	£59.83m	£0.00m	£0.00m	436.09			Government transformation and Service Delivery	4.96	DH_0033_1314-Q1,1415-Q2	DH	Amber	Not new
DH_0035_1314-Q1	Shingles Immunisation Programme	AR 2015	1415-Q2	DH Non Capital	Green	11/12/2012	01/11/2013	£67.34m	£67.34m	£0.00m	£0.00m	171.53		£0.00m	Government Transformation and Service Delivery	0.89	DH_0035_1314-Q1,1415-Q2	DH	Green	Not new
DH_0036_1314-Q1	Spine 2	AR 2015	1415-Q2	DH Non Capital	Amber	10/05/2010	30/03/2018	£65.86m	£73.68m	£7.82m	£0.12m	205.71			ICT	7.89	DH_0036_1314-Q1,1415-Q2	DH	Amber	Not new
DH_0038_1314-Q2	Health Visitor Programme	AR 2015	1415-Q2	DH Non Capital	Amber	31/10/2010	31/12/2015	£242.05m	£242.05m	£0.00m	£0.00m	653.15		£0.00m	Government Transformation and Service Delivery	5.17	DH_0038_1314-Q2,1415-Q2	DH	Amber	Not new
DH_0039_1314-Q2	NHS e-Referral Service	AR 2015	1415-Q2	DH Non Capital	Amber	26/07/2012	31/03/2018	£35.41m	£33.98m	-£1.44m	-£0.04m	131.16		£0.00m	Government Transformation and Service Delivery	5.68	DH_0039_1314-Q2,1415-Q2	DH	Amber	Not new
DH_0040_1314-Q2	NHSmail2	AR 2015	1415-Q2	DH Non Capital	Amber	29/03/2012	30/06/2016	£27.39m	£19.09m	-£8.30m	-£0.30m	168.09			ICT	4.25	DH_0040_1314-Q2,1415-Q2	DH	Amber	Not new
FCO_0001_1112-Q1	ABUJA: New Office and Residence	AR 2015	1415-Q2	FCO	Amber/Green	01/01/2011	01/12/2017	£19.89m	£19.89m	£0.00m	£0.00m	46.00			Infrastructure and Construction	6.92	FCO_0001_1112-Q1,1415-Q2	FCO	Amber/Green	Not new
DH_0041_1314-Q2	Health and Social Care Network (Formerly Public Services Network for Health (PSNH))	AR 2015	1415-Q2	DH Non Capital	Red	29/03/2012	10/10/2014	£177.46m	£1.89m	-£175.57m	-£0.99m	748.16			ICT	2.53	DH_0041_1314-Q2,1415-Q2	DH	Red	Not new
FCO_0006_1213-Q2	UKERP	AR 2015	1415-Q2	FCO	Amber/Green	01/06/2011	01/08/2016	£22.04m	£22.04m	£0.00m	£0.00m	64.95			Infrastructure and Construction	5.17	FCO_0006_1213-Q2,1415-Q2	FCO	Amber/Green	Not new
DH_0042_1314-Q3	NHS Electronic Staff Record Reprocurement Project	AR 2015	1415-Q2	DH Non Capital	Amber/Green	10/06/2013	30/11/2015	£7.75m	£12.80m	£5.05m	£0.65m	425.38		£0.00m	ICT	2.47	DH_0042_1314-Q3,1415-Q2	DH	Amber/Green	Joiner
DWP_0017_1314-Q3	Estates Programme	AR 2015	1415-Q2	DWP	Amber/Green	16/02/2012	31/03/2018	£23.57m	£18.72m	-£4.85m	-£0.21m	173.31		£0.00m	Government transformation and Service Delivery	6.12	DWP_0017_1314-Q3,1415-Q2	DWP	Amber/Green	Joiner
DWP_0018_1314-Q3	Fit for Work (previously called Health and Work Service)	AR 2015	1415-Q2	DWP	Amber	27/02/2013	31/03/2015	£28.99m	£18.97m	-£10.03m	-£0.35m	324.11		£0.00m	Government transformation and Service Delivery	2.09	DWP_0018_1314-Q3,1415-Q2	DWP	Amber	Joiner
DWP_0019_1314-Q3	IT Transformation Programme	AR 2015	1415-Q2	DWP	Amber/Red	01/04/2013	28/02/2016	£36.50m	£30.40m	-£6.10m	-£0.17m	165.50		£0.00m	ICT	2.91	DWP_0019_1314-Q3,1415-Q2	DWP	Amber/Red	Joiner
DWP_0020_1314-Q4	Help to Work Package	AR 2015	1415-Q2	DWP	Amber	19/12/2013	23/04/2015	£127.25m	£130.96m	£3.71m	£0.03m	695.66		£0.00m	Government transformation and Service Delivery	1.34	DWP_0020_1314-Q4,1415-Q2	DWP	Amber	Joiner
DWP_0021_1314-Q4	Conditionality Package	AR 2015	1415-Q2	DWP	Amber	19/12/2013	23/04/2015	£135.02m	£136.16m	£1.14m	£0.01m	1902.28		£0.00m	Government transformation and Service Delivery	1.34	DWP_0021_1314-Q4,1415-Q2	DWP	Amber	Joiner
DWP_0023_1415-Q2	New State Pension Project	AR 2015	1415-Q2	DWP	Amber	27/02/2012	31/10/2017	£19.87m	£19.87m	£0.00m	£0.00m	168.16		£0.00m	Government Transformation and Service Delivery	5.68	DWP_0023_1415-Q2,1415-Q2	DWP	Amber	Joiner
FCO_0007_1415-Q1	Overseas Healthcare Provision	AR 2015	1415-Q2	FCO	Amber/Green	26/09/2013	01/04/2016	£0.09m	£0.09m	£0.00m	£0.00m	55.99			Government Transformation and Service Delivery	2.51	FCO_0007_1415-Q1,1415-Q2	FCO	Amber/Green	Joiner
HMRC_0011_1314-Q1	Digital Solutions Portfolio	AR 2015	1415-Q2	HMRC	Amber	14/11/2012	05/04/2015	£33.41m	£28.86m	-£4.55m	-£0.14m	116.70			Government Transformation and Service Delivery	2.39	HMRC_0011_1314-Q1,1415-Q2	HMRC	Amber	Not new
HMRC_0012_1415-Q1	Tax-Free Childcare	AR 2015	1415-Q2	HMRC	Amber/Red	01/08/2013	30/06/2016	£30.40m	£19.07m	£11.33m	£0.37m	31.79			ICT	2.91	HMRC_0012_1415-Q1,1415-Q2	HMRC	Amber/Red	Joiner
HO_0029_1314-Q4	Immigration Platform Technologies (IPT)	AR 2015	1415-Q2	HO	Amber	01/04/2013	31/03/2017	£77.64m	£54.85m	-£22.79m	-£0.29m	208.66			ICT	4.00	HO_0029_1314-Q4,1415-Q2	HO	Amber	Joiner
HO_0030_1415-Q1	Adelphi Modernisation Project	AR 2015	1415-Q2	HO	Amber	03/07/2014	31/03/2016	£0.00m	£0.00m	£0.00m	0%	25.60			ICT	1.74	HO_0030_1415-Q1,1415-Q2	HO	Amber	Joiner
HO_0031_1415-Q1	Digital Services at the Border	AR 2015	1415-Q2	HO	Amber	12/02/2014	31/03/2019	£16.20m	£16.03m	-£0.17m	-£0.01m	178.25		£0.00m	ICT	5.13	HO_0031_1415-Q1,1415-Q2	HO	Amber	Joiner
HO_0032_1415-Q1	Technology Reset Programme (TRP)	AR 2015	1415-Q2	HO	Amber/Red	01/02/2014	01/09/2016	£32.00m	£32.00m	£0.00m	£0.00m	242.00			ICT	2.58	HO_0032_1415-Q1,1415-Q2	HO	Amber/Red	Joiner
MOD_0064_1112-Q2	CEPP	AR 2015	1415-Q2	Military Capability	Amber/Red	31/01/2011	01/12/2030	£1.58m	£1.58m	£0.00m	£0.00m	21.70			Government Transformation and Service Delivery	19.83	MOD_0064_1112-Q2,1415-Q2	MOD	Amber/Red	Not new
MOD_0066_1112-Q2	Corporate Services Systems Convergence Programme	AR 2015	1415-Q2	MOD Transformation	Amber	01/02/2010	28/02/2020	£27.02m	£14.33m	-£12.69m	-£0.47m	77.96			Government Transformation and Service Delivery	10.07	MOD_0066_1112-Q2,1415-Q2	MOD	Amber	Not new
MOD_0082_1213-Q3	Next Generation Estates Contracts	AR 2015	1415-Q2	MOD Transformation	Amber/Green	02/03/2009	20/03/2015	£75.58m	£66.25m	-£9.33m	-£0.12m	2250.69			Government Transformation and Service Delivery	6.05	MOD_0082_1213-Q3,1415-Q2	MOD	Amber/Green	Not new
MOD_0083_1213-Q3	Whole Fleet Management	AR 2015	1415-Q2	MOD Transformation	Amber	31/01/2001	30/06/2025	£22.76m	£19.90m	-£2.86m	-£0.13m	1295.46			Military Capability	24.41	MOD_0083_1213-Q3,1415-Q2	MOD	Amber	Not new
MOD_0084_1213-Q4	Army 2020	AR 2015	1415-Q2	MOD Transformation	Amber	31/08/2011	30/04/2020	£0.00m	£0.00m	£0.00m	£0.00m	0.00			Government Transformation and Service Delivery	8.67	MOD_0084_1213-Q4,1415-Q2	MOD	Amber	Not new
MOD_0085_1314-Q2	Army Basing Programme	AR 2015	1415-Q2	MOD Transformation	Red	22/05/2013	31/03/2020	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept			Government Transformation and Service Delivery	6.86	MOD_0085_1314-Q2,1415-Q2	MOD	Red	Not new
MOD_0086_1314-Q2	Mounted Close Combat	AR 2015	1415-Q2	Military Capability	Amber	16/03/2010	31/12/2033	£288.34m	£308.75m	£20.41m	£0.07m	17251.83			Military Capability	23.79	MOD_0086_1314-Q2,1415-Q2	MOD	Amber	Not new
MOD_0087_1314-Q2	The Materiel Strategy	AR 2015	1415-Q2	Military Capability	Amber/Red	02/05/2011	31/05/2017	£23.00m	£42.03m	£19.03m	£0.83m	98.68			Government transformation and Service Delivery	6.08	MOD_0087_1314-Q2,1415-Q2	MOD	Amber/Red	Not new
MOD_0088_1314-Q4	Head Office and Customer Design	AR 2015	1415-Q2	MOD Transformation	Amber	01/01/2014	31/07/2015	£11.16m	£10.12m	-£1.04m	-£0.09m	14.73			Government transformation and Service Delivery	1.58	MOD_0088_1314-Q4,1415-Q2	MOD	Amber	Joiner
MOD_0089_1314-Q4	Strategic Business Partner Implementation Programme	AR 2015	1415-Q2	MOD Transformation	Green	06/03/2014	30/12/2016	£26.11m	£26.11m	£0.00m	£0.00m	205.70			Government transformation and Service Delivery	2.82	MOD_0089_1314-Q4,1415-Q2	MOD	Green	Joiner
MOD_0090_1415-Q1	Operating Model Rollout	AR 2015	1415-Q2	MOD Transformation	Amber/Green	06/11/2013	26/02/2016	£17.37m	£17.37m	£0.00m	£0.00m	61.57			Government Transformation and Service Delivery	2.31	MOD_0090_1415-Q1,1415-Q2	MOD	Amber/Green	Joiner
MOJ_0021_1314-Q1	Common Platform	AR 2015	1415-Q2	MOJ	Amber/Red	01/11/2012	31/01/2017	£38.37m	£25.94m	-£12.43m	-£0.32m	374.07			ICT	4.25	MOJ_0021_1314-Q1,1415-Q2	MOJ	Amber/Red	Not new
MOJ_0022_1314-Q1	Legal Aid Transformation	AR 2015	1415-Q2	MOJ	Amber	04/12/2012	01/08/2015	£4.90m	£3.80m	-£1.10m	-£0.22m	11.80		£0.00m	Government Transformation and Service Delivery	2.66	MOJ_0022_1314-Q1,1415-Q2	MOJ	Amber	Not new
MOJ_0023_1314-Q1	New Wales Prison	AR 2015	1415-Q2	MOJ	Green	10/01/2013	31/03/2018	£14.24m	£15.24m	£1.00m	£0.07m	208.04			Infrastructure and Construction	5.22	MOJ_0023_1314-Q1,1415-Q2	MOJ	Green	Not new
MOJ_0024_1314-Q1	Prison Unit Cost Programme	AR 2015	1415-Q2	MOJ	Amber	20/11/2012	01/12/2016	£85.20m	£23.20m	-£62.00m	-£0.73m	866.40			Government Transformation and Service Delivery	4.03	MOJ_0024_1314-Q1,1415-Q2	MOJ	Amber	Not new
MOJ_0025_1314-Q1	Rehabilitation Programme	AR 2015	1415-Q2	MOJ	Amber/Red	05/11/2012	31/03/2015	£437.91m	£437.91m	£0.00m	£0.00m	9607.74		£0.00m	Government Transformation and Service Delivery	2.40	MOJ_0025_1314-Q1,1415-Q2	MOJ	Amber/Red	Not new
MOJ_0026_1314-Q1	Transforming Youth Custody	AR 2015	1415-Q2	MOJ	Amber	05/11/2012	15/07/2018	£17.60m	£17.60m	£0.00m	£0.00m	3466.30			Government Transformation and Service Delivery	5.69	MOJ_0026_1314-Q1,1415-Q2	MOJ	Amber	Not new
MOJ_0027_1314-Q2	CJS Efficiency Programme Phase 2	AR 2015	1415-Q2	MOJ	Amber	30/04/2013	31/12/2016	£34.28m	£31.45m	-£2.83m	-£0.08m	141.19			ICT	3.67	MOJ_0027_1314-Q2,1415-Q2	MOJ	Amber	Not new
MOJ_0028_1314-Q2	HMCTS Reform	AR 2015	1415-Q2	MOJ	Amber/Red	21/03/2013	No end date	£23.80m	£12.10m	-£11.70m	-£0.49m	619.75			Government Transformation and Service Delivery	0.00	MOJ_0028_1314-Q2,1415-Q2	MOJ	Amber/Red	Not new
MOJ_0029_1415-Q1	Crime Change Programme	AR 2015	1415-Q2	MOJ	Amber/Green	07/07/2013	31/07/2015	£10.36m	£10.36m	£0.00m	£0.00m	28.82			ICT	2.06	MOJ_0029_1415-Q1,1415-Q2	MOJ	Amber/Green	Joiner
NCA_0001_1415-Q2	Novo Programme	AR 2015	1415-Q2	NCA	Amber	01/04/2014	31/03/2019	£56.00m	£56.00m	£0.00m	£0.00m	296.00		£0.00m	Government Transformation and Service Delivery	5.00	NCA_0001_1415-Q2,1415-Q2	NCA	Amber	Joiner
ONS_0006_1314-Q3	Consumer and Retail Prices Indices (CPI/RPI) Re-engineering	AR 2015	1415-Q2	ONS	Amber	01/01/2011	20/03/2015	£1.32m	£1.32m	£0.01m	£0.00m	13.04			ICT	4.21	ONS_0006_1314-Q3,1415-Q2	ONS	Amber	Joiner
MOD_0095_1415-Q2	Cryptographic Enabling Services	AR 2015	1415-Q2	Military Capability	Exempt	24/06/2014	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept			ICT	0.00	MOD_0095_1415-Q2,1415-Q2	MOD	Exempt	Joiner
DH_0043_1314-Q3	NHS Pension Re-let Project	AR 2015	1415-Q2	DH Non Capital	Amber/Red	05/07/2013	31/07/2017	£1.70m	£1.70m	£0.00m	£0.00m	1.90		£0.00m	ICT	4.07	DH_0043_1314-Q3,1415-Q2	DH	Amber/Red	Joiner
DH_0044_1314-Q4	Care and Support Implementation Programme	AR 2015	1415-Q2	DH Non Capital	Amber/Red	04/06/2013	01/12/2016	£62.90m	£0.40m	-£62.50m	-£0.99m	1682.40		£0.00m	Government transformation and Service Delivery	3.49	DH_0044_1314-Q4,1415-Q2	DH	Amber/Red	Joiner
DH_0045_1415-Q1	care.data	AR 2015	1415-Q2	DH Non Capital	Red	01/09/2012	No end date	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept			ICT	0.00	DH_0045_1415-Q1,1415-Q2	DH	Red	Joiner
DH_0046_1415-Q1	Death Certification	AR 2015	1415-Q2	DH Non Capital	Red	24/07/2007	No end date	£0.00m	£0.00m	£0.00m	0%	411.61		£0.00m	Government Transformation and Service Delivery	0.00	DH_0046_1415-Q1,1415-Q2	DH	Red	Joiner
DH_0047_1415-Q1	Francis & Compassionate Care programme	AR 2015	1415-Q2	DH Non Capital	Amber/Red	01/03/2013	01/03/2018	£2.50m	£2.16m	-£0.34m	-£0.14m	14.55		£0.00m	Government Transformation and Service Delivery	5.00	DH_0047_1415-Q1,1415-Q2	DH	Amber/Red	Joiner
DH_0048_1415-Q1	Genomics Programme	AR 2015	1415-Q2	DH Non Capital	Amber	10/04/2013	31/12/2017	£50.00m	£19.20m	-£30.80m	-£0.62m	160.00			Government Transformation and Service Delivery	4.73	DH_0048_1415-Q1,1415-Q2	DH	Amber	Joiner
DH_0049_1415-Q1	NHS Choices	AR 2015	1415-Q2	DH Non Capital	Red	02/09/2013	No end date	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept	Data not provided by dept			ICT	0.00	DH_0049_1415-Q1,1415-Q2	DH	Red	Joiner
DH_0050_1415-Q1	NHS Procurement Efficiency Programme	AR 2015	1415-Q2	DH Non Capital	Amber/Red	01/09/2013	31/03/2016	£21.76m	£7.76m	-£14.00m	-£0.64m	39.44		£0.00m	Government Transformation and Service Delivery	2.58	DH_0050_1415-Q1,1415-Q2	DH	Amber/Red	Joiner
DH_0051_1415-Q1	North Tees & Hartlepool Foundation Trust - New Hospital Development	AR 2015	1415-Q2	DH Capital	Green	01/04/2013	30/06/2017	£0.00m	£0.00m	£0.00m	0%	975.83		£0.00m	Infrastructure and Construction	4.25	DH_0051_1415-Q1,1415-Q2	DH	Green	Joiner
DH_0052_1415-Q1	Nursing Technology Fund	AR 2015	1415-Q2	DH Non Capital	Amber	01/11/2013	No end date	£70.00m	£70.35m	£0.35m	£0.00m	100.00		£0.00m	ICT	0.00	DH_0052_1415-Q1,1415-Q2	DH	Amber	Joiner
DH_0053_1415-Q1	Papworth Foundation Trust - New Papworth Hospital	AR 2015	1415-Q2	DH Capital	Amber/Green	01/12/2003	01/11/2017	£18.00m	£18.00m	£0.00m	£0.00m	697.50			Infrastructure and Construction	13.92	DH_0053_1415-Q1,1415-Q2	DH	Amber/Green	Joiner
DH_0054_1415-Q1	SUS Transition	AR 2015	1415-Q2	DH Non Capital	Amber/Red	20/08/2013	05/12/2014	£30.67m	£30.67m	£0.00m	£0.00m	53.61			ICT	1.29	DH_0054_1415-Q1,1415-Q2	DH	Amber/Red	Joiner
DH_0055_1415-Q2	Better Care Fund	AR 2015	1415-Q2	DH Non Capital	Amber/Red	07/07/2014	31/03/2015	£5.38m	£5.38m	£0.00m	£0.00m	5.38			Government Transformation and Service Delivery	0.73	DH_0055_1415-Q2,1415-Q2	DH	Amber/Red	Joiner
BIS_0010_1112-Q4	Project Eagle (formerly Urenco Future Options)	AR 2016	1516-Q2	BEIS	Amber/Red	01/02/2010	15/06/2017	£1.30m	£1.30m	-£0.01m	£0.00m	12.90			Government Transformation and Service Delivery	7.37	BIS_0010_1112-Q4,1516-Q2	BEIS	Amber/Red	Not new
BIS_0008_1112-Q1	ICR Monetisation	AR 2016	1516-Q2	DFE	Amber/Red	01/03/2010	31/12/2018	£5.79m	£5.79m	£0.00m	£0.00m	15.29			Government Transformation and Service Delivery	8.84	BIS_0008_1112-Q1,1516-Q2	DFE	Amber/Red	Not new
BIS_0015_1516-Q1	Local Land Charges (LLC) Programme	AR 2016	1516-Q2	BEIS	Amber/Red	01/03/2014	28/06/2018	£5.50m	£5.50m	£0.00m	£0.00m	193.30			ICT	4.33	BIS_0015_1516-Q1,1516-Q2	BEIS	Amber/Red	Joiner
BIS_0014_1415-Q3	New Polar Research Vessel	AR 2016	1516-Q2	BEIS	Amber/Green	01/05/2014	05/08/2019	£41.00m	£39.70m	-£1.30m	-£0.03m	1186.00			Infrastructure and Construction	5.26	BIS_0014_1415-Q3,1516-Q2	BEIS	Amber/Green	Joiner
BIS_0009_1112-Q1	The Francis Crick Institute (formerly UKCMRI)	AR 2016	1516-Q2	BEIS	Amber/Green	01/10/2006	31/12/2016	£6.20m	£6.20m	£0.00m	£0.00m	752.70			Infrastructure and Construction	10.25	BIS_0009_1112-Q1,1516-Q2	BEIS	Amber/Green	Not new
CO_0014_1516-Q2	Government Office Hubs Programme	AR 2016	1516-Q2	CO	Amber/Red	01/05/2015	31/12/2023	£7.00m	£7.00m	£0.00m	£0.00m	42.00			Government Transformation and Service Delivery	8.67	CO_0014_1516-Q2,1516-Q2	CO	Amber/Red	Joiner
CO_0010_1415-Q4	ISSC1	AR 2016	1516-Q2	CO	Red	28/12/2012	01/06/2016	£1.40m	£1.20m	-£0.20m	-£0.14m	8.20			Government Transformation and Service Delivery	3.43	CO_0010_1415-Q4,1516-Q2	CO	Red	Joiner
CO_0012_1415-Q4	Commercial Capability Programme	AR 2016	1516-Q2	CO	Amber/Red	01/01/2015	31/03/2017	£5.20m	£5.20m	£0.00m	£0.00m	10.40			Government Transformation and Service Delivery	2.25	CO_0012_1415-Q4,1516-Q2	CO	Amber/Red	Joiner
CO_0001_1112-Q1	Electoral Registration Transformation Programme	AR 2016	1516-Q2	CO	Amber/Green	01/02/2010	31/03/2016	£37.41m	£37.41m	£0.00m	£0.00m	129.40			Government Transformation and Service Delivery	6.16	CO_0001_1112-Q1,1516-Q2	CO	Amber/Green	Not new
CO_0013_1516-Q2	FOXHOUND Programme	AR 2016	1516-Q2	CO	Amber	01/09/2013	01/07/2018	£18.80m	£18.80m	£0.00m	£0.00m	187.80			ICT	4.83	CO_0013_1516-Q2,1516-Q2	CO	Amber	Joiner
CO_0015_1516-Q2	GOV.UK Verify	AR 2016	1516-Q2	CO	Amber/Green	01/04/2012	01/04/2020	£30.00m	£30.00m	£0.00m	£0.00m	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)			ICT	8.00	CO_0015_1516-Q2,1516-Q2	CO	Amber/Green	Joiner
CO_0011_1415-Q4	ISSC2	AR 2016	1516-Q2	CO	Amber/Red	28/12/2012	30/04/2015	£5.70m	£4.70m	-£1.00m	-£0.18m	32.80			Government Transformation and Service Delivery	2.34	CO_0011_1415-Q4,1516-Q2	CO	Amber/Red	Joiner
CO_0005_1112-Q1	National Cyber Security Programme	AR 2016	1516-Q2	CO	Green	01/04/2011	01/04/2016	£212.00m	£212.00m	£0.00m	£0.00m	860.00			ICT	5.00	CO_0005_1112-Q1,1516-Q2	CO	Green	Not new
CO_0009_1314-Q1	New Civil Service 2015 Pension Scheme Implementation	AR 2016	1516-Q2	CO	Amber/Red	15/04/2013	31/12/2015	£1.70m	£3.50m	£1.80m	£1.06m	14.90			Government Transformation and Service Delivery	2.71	CO_0009_1314-Q1,1516-Q2	CO	Amber/Red	Not new
CPS_0001_1314-Q4	ICTRestructure Programme	AR 2016	1516-Q2	CPS	Amber	01/10/2013	01/05/2016	£27.57m	£27.80m	£0.23m	£0.01m	144.30			ICT	2.58	CPS_0001_1314-Q4,1516-Q2	CPS	Amber	Not new
DCMS_0007_1112-Q4	Super-Connected City Programme	AR 2016	1516-Q2	DCMS	Green	05/12/2012	31/03/2016	£42.27m	£61.67m	£19.40m	£0.46m	154.60			Infrastructure and Construction	3.32	DCMS_0007_1112-Q4,1516-Q2	DCMS	Green	Not new
DCMS_0001_1112-Q1	Broadband Delivery Programme	AR 2016	1516-Q2	DCMS	Amber/Green	06/12/2010	31/12/2017	£250.00m	£164.06m	-£85.94m	-£0.34m	1910.11			Infrastructure and Construction	7.07	DCMS_0001_1112-Q1,1516-Q2	DCMS	Amber/Green	Not new
DCMS_0006_1112-Q4	Mobile Infrastructure Project	AR 2016	1516-Q2	DCMS	Amber	01/10/2011	31/03/2016	£28.47m	£28.07m	-£0.40m	-£0.01m	43.97			Infrastructure and Construction	4.50	DCMS_0006_1112-Q4,1516-Q2	DCMS	Amber	Not new
DCMS_0004_1112-Q1	The Tate Modern Project	AR 2016	1516-Q2	DCMS	Amber	01/01/2010	31/12/2016	£43.50m	£43.50m	£0.00m	£0.00m	255.50			Infrastructure and Construction	7.00	DCMS_0004_1112-Q1,1516-Q2	DCMS	Amber	Not new
DECC_0011_1112-Q3	Carbon Capture & Storage Commercialisation Programme	AR 2016	1516-Q2	BEIS	Amber	25/10/2011	31/12/2016	£40.27m	£29.23m	-£11.04m	-£0.27m	Data Exempt under Section 43(2) of the Freedom of Information Act (2000)			Infrastructure and Construction	5.19	DECC_0011_1112-Q3,1516-Q2	BEIS	Amber	Not new
DECC_0012_1213-Q1	FID Enabling for Hinkley Point C	AR 2016	1516-Q2	BEIS	Exempt	01/09/2011	01/06/2016	£2.30m	£5.90m	£3.60m	£1.57m	36963.64			Infrastructure and Construction	4.75	DECC_0012_1213-Q1,1516-Q2	BEIS	Exempt	Not new
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2016	1516-Q2	BEIS	Amber	30/06/2008	31/12/2040	£25.58m	£25.83m	£0.25m	£0.01m	11393.00			Infrastructure and Construction	32.50	DECC_0005_1112-Q1,1516-Q2	BEIS	Amber	Not new
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	AR 2016	1516-Q2	BEIS	Amber/Green	03/04/2012	01/09/2028	£674.00m	£549.00m	-£125.00m	-£0.19m	3860.00			Infrastructure and Construction	16.41	DECC_0013_1213-Q1,1516-Q2	BEIS	Amber/Green	Not new
DECC_0017_1516-Q1	Sellafield Model Change (SMC)	AR 2016	1516-Q2	BEIS	Amber	13/01/2015	24/05/2017	£2217.25m	£2217.25m	£0.00m	£0.00m	29975.00			Government Transformation and Service Delivery	2.36	DECC_0017_1516-Q1,1516-Q2	BEIS	Amber	Joiner
DECC_0010_1112-Q1	Smart Meters Implementation Programme	AR 2016	1516-Q2	BEIS	Amber	02/12/2009	31/12/2020	£12.00m	£12.00m	£0.00m	£0.00m	19261.09			Government Transformation and Service Delivery	11.08	DECC_0010_1112-Q1,1516-Q2	BEIS	Amber	Not new
DEFRA_0001_1112-Q1	CAP Delivery Programme	AR 2016	1516-Q2	DEFRA	Amber/Red	01/01/2011	31/03/2016	£25.29m	£60.63m	£35.34m	£1.40m	154.80			Government Transformation and Service Delivery	5.25	DEFRA_0001_1112-Q1,1516-Q2	DEFRA	Amber/Red	Not new
DEFRA_0006_1516-Q1	DEFRA UNITY PROGRAMME	AR 2016	1516-Q2	DEFRA	Amber/Red	01/11/2014	01/06/2018	£291.00m	£291.00m	£0.00m	£0.00m	1666.00			ICT	3.58	DEFRA_0006_1516-Q1,1516-Q2	DEFRA	Amber/Red	Joiner
DEFRA_0004_1112-Q1	Thames Estuary Asset Management Programme (TEAM2100)	AR 2016	1516-Q2	DEFRA	Green	01/04/2010	31/12/2025	£7.35m	£12.30m	£4.95m	£0.67m	318.42			Infrastructure and Construction	15.75	DEFRA_0004_1112-Q1,1516-Q2	DEFRA	Green	Not new
DEFRA_0005_1213-Q3	Thames Tideway Tunnel	AR 2016	1516-Q2	DEFRA	Amber/Green	07/09/2010	31/12/2023	£2.38m	£3.00m	£0.62m	£0.26m	4221.10			Infrastructure and Construction	13.31	DEFRA_0005_1213-Q3,1516-Q2	DEFRA	Amber/Green	Not new
DFE_0004_1415-Q2	Priority School Building Programme 1 (PSBP1) - Capital	AR 2016	1516-Q2	DFE	Amber/Red	19/07/2011	01/01/2019	£693.44m	£801.80m	£108.36m	£0.16m	2023.30			Infrastructure and Construction	7.46	DFE_0004_1415-Q2,1516-Q2	DFE	Amber/Red	Not new
DFE_0006_1415-Q3	Priority School Building Programme 2	AR 2016	1516-Q2	DFE	Amber/Red	01/05/2014	31/03/2021	£38.50m	£10.33m	-£28.17m	-£0.73m	1580.79			Infrastructure and Construction	6.92	DFE_0006_1415-Q3,1516-Q2	DFE	Amber/Red	Joiner
DFE_0005_1415-Q2	Priority School Building Programme - Private Finance	AR 2016	1516-Q2	DFE	Amber/Green	19/07/2011	01/02/2018	£221.42m	£234.35m	£12.93m	£0.06m	2085.52			Infrastructure and Construction	6.54	DFE_0005_1415-Q2,1516-Q2	DFE	Amber/Green	Not new
DFID_0001_1112-Q1	St Helena Airport	AR 2016	1516-Q2	DFID	Amber	15/03/2005	31/08/2026	£25.98m	£25.56m	-£0.42m	-£0.02m	445.17			Infrastructure and Construction	21.46	DFID_0001_1112-Q1,1516-Q2	DFID	Amber	Not new
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	AR 2016	1516-Q2	DFT	Amber	01/09/2012	30/09/2021	£40.10m	£41.73m	£1.63m	£0.04m	1519.32			Infrastructure and Construction	9.08	DFT_0020_1314-Q2,1516-Q2	DFT	Amber	Not new
DFT_0001_1112-Q1	Crossrail Programme	AR 2016	1516-Q2	DFT	Amber/Green	22/07/2008	31/12/2019	£1794.50m	£2068.90m	£274.40m	£0.15m	14768.87			Infrastructure and Construction	11.44	DFT_0001_1112-Q1,1516-Q2	DFT	Amber/Green	Not new
DFT_0004_1112-Q1	High Speed Rail Programme (HS2)	AR 2016	1516-Q2	DFT	Amber/Red	28/02/2011	31/12/2033	£713.00m	£713.00m	£0.00m	£0.00m	42559.51			Infrastructure and Construction	22.84	DFT_0004_1112-Q1,1516-Q2	DFT	Amber/Red	Not new
DFT_0005_1112-Q1	InterCity Express Programme (IEP)	AR 2016	1516-Q2	DFT	Amber	01/06/2005	06/02/2020	£98.75m	£98.00m	-£0.75m	-£0.01m	6246.89			Infrastructure and Construction	14.68	DFT_0005_1112-Q1,1516-Q2	DFT	Amber	Not new
DfT_0022_1415-Q4	Lower Thames Crossing	AR 2016	1516-Q2	DFT	Amber	30/05/2014	31/12/2026	£19.10m	£16.40m	-£2.70m	-£0.14m	199.10			Infrastructure and Construction	12.59	DfT_0022_1415-Q4,1516-Q2	DFT	Amber	Joiner
DFT_0009_1112-Q1	Periodic Review 2013 (Rail Investment Strategy - HLOS & SOFA)	AR 2016	1516-Q2	DFT	Green	31/08/2011	31/07/2012	£3381.94m	£2577.40m	-£804.54m	-£0.24m	16840.60			Infrastructure and Construction	0.92	DFT_0009_1112-Q1,1516-Q2	DFT	Green	Not new
DFT_0021_1314-Q3	Rail Franchising Programme	AR 2016	1516-Q2	DFT	Amber	26/03/2013	31/12/2022	£0.00m	£0.00m	£0.00m	£0.00m	1036.30			Infrastructure and Construction	9.77	DFT_0021_1314-Q3,1516-Q2	DFT	Amber	Not new
DFT_0014_1112-Q1	Search and Rescue Helicopters	AR 2016	1516-Q2	DFT	Amber/Green	08/02/2011	08/09/2017	£119.00m	£112.80m	-£6.20m	-£0.05m	1923.00			Infrastructure and Construction	6.58	DFT_0014_1112-Q1,1516-Q2	DFT	Amber/Green	Not new
DFT_0015_1112-Q1	Shared Services Implementation Programme	AR 2016	1516-Q2	DFT	Red	10/12/2010	01/06/2015	£20.20m	£11.17m	-£9.03m	-£0.45m	222.30			ICT	4.47	DFT_0015_1112-Q1,1516-Q2	DFT	Red	Not new
DFT_0016_1112-Q1	Thameslink Programme	AR 2016	1516-Q2	DFT	Amber	01/07/2005	31/12/2018	£29.58m	£29.58m	£0.00m	£0.00m	6830.50			Infrastructure and Construction	13.50	DFT_0016_1112-Q1,1516-Q2	DFT	Amber	Not new
DH_0029_1314-Q1	Liaison and Diversion Programme	AR 2016	1516-Q2	DH	Amber	01/04/2011	01/04/2017	£34.80m	£34.80m	£0.00m	£0.00m	199.10			Government Transformation and Service Delivery	6.00	DH_0029_1314-Q1,1516-Q2	DH	Amber	Not new
DH_0041_1314-Q2	Health & Social Care Network	AR 2016	1516-Q2	DH	Amber/Red	29/03/2012	01/04/2020	£166.95m	£87.38m	-£79.57m	-£0.48m	748.20			ICT	8.01	DH_0041_1314-Q2,1516-Q2	DH	Amber/Red	Not new
DH_0008_1112-Q1	Electronic Prescription Service (EPS) Release 2	AR 2016	1516-Q2	DH	Amber	01/01/2003	31/12/2016	£4.96m	£7.83m	£2.87m	£0.58m	77.73			ICT	14.00	DH_0008_1112-Q1,1516-Q2	DH	Amber	Not new
DH_0015_1112-Q1	CSC Local Service Provider (LSP) Delivery Programme	AR 2016	1516-Q2	DH	Amber/Red	23/06/2003	31/03/2023	£237.73m	£115.70m	-£122.03m	-£0.51m	2294.07			Government Transformation and Service Delivery	19.77	DH_0015_1112-Q1,1516-Q2	DH	Amber/Red	Not new
DH_0017_1112-Q1	PHE Science Hub	AR 2016	1516-Q2	DH	Amber	28/06/2013	31/03/2023	£197.25m	£135.56m	-£61.69m	-£0.31m	10447.57			Infrastructure and Construction	9.75	DH_0017_1112-Q1,1516-Q2	DH	Amber	Not new
DH_0028_1314-Q1	General Practice System of Choice (GPSoC) Replacement	AR 2016	1516-Q2	DH	Amber/Green	26/01/2012	31/03/2015	£87.32m	£82.13m	-£5.18m	-£0.06m	309.43			ICT	3.18	DH_0028_1314-Q1,1516-Q2	DH	Amber/Green	Not new
DH_0030_1314-Q1	National Pandemic Flu Service	AR 2016	1516-Q2	DH	Amber/Red	19/03/2012	30/10/2016	Exempt under section 43 of the Freedom of Information Act (2000).	Exempt under section 43 of the Freedom of Information Act (2000).	£0.00m	£0.00m	Exempt under section 43 of the Freedom of Information Act (2000).			ICT	4.62	DH_0030_1314-Q1,1516-Q2	DH	Amber/Red	Not new
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	AR 2016	1516-Q2	DH	Amber/Green	01/01/2012	31/12/2018	£52.15m	£52.15m	£0.00m	£0.00m	1247.26			Government Transformation and Service Delivery	7.00	DH_0031_1314-Q1,1516-Q2	DH	Amber/Green	Not new
DH_0033_1314-Q1	Childhood Flu Immunisation Programme	AR 2016	1516-Q2	DH	Amber	03/09/2013	01/09/2018	£69.28m	£69.28m	£0.00m	£0.00m	348.00			Government Transformation and Service Delivery	4.99	DH_0033_1314-Q1,1516-Q2	DH	Amber	Not new
DH_0038_1314-Q2	Health Visitor Programme	AR 2016	1516-Q2	DH	Green	31/10/2010	31/12/2015	£0.41m	£0.41m	£0.00m	£0.00m	654.31			Government Transformation and Service Delivery	5.17	DH_0038_1314-Q2,1516-Q2	DH	Green	Not new
DH_0039_1314-Q2	NHS e-Referral Service	AR 2016	1516-Q2	DH	Amber	29/03/2012	31/03/2018	£27.00m	£30.77m	£3.77m	£0.14m	131.16			ICT	6.00	DH_0039_1314-Q2,1516-Q2	DH	Amber	Not new
DH_0040_1314-Q2	NHSmail 2	AR 2016	1516-Q2	DH	Amber/Red	29/03/2012	01/06/2020	£29.32m	£28.40m	-£0.92m	-£0.03m	133.03			ICT	8.18	DH_0040_1314-Q2,1516-Q2	DH	Amber/Red	Not new
DH_0042_1314-Q3	NHS Electronic Staff Record Reprocurement Project	AR 2016	1516-Q2	DH	Amber	10/06/2013	30/11/2015	£47.10m	£45.31m	-£1.79m	-£0.04m	267.00			ICT	2.47	DH_0042_1314-Q3,1516-Q2	DH	Amber	Not new
DH_0043_1314-Q3	NHS Pension Re-let	AR 2016	1516-Q2	DH	Amber	05/07/2013	21/07/2017	£2.50m	£2.50m	£0.00m	£0.00m	10.84			Government Transformation and Service Delivery	4.04	DH_0043_1314-Q3,1516-Q2	DH	Amber	Not new
DH_0044_1314-Q4	Care and Support Implementation Programme	AR 2016	1516-Q2	DH	Amber/Green	04/06/2013	01/12/2016	£512.10m	£354.50m	-£157.60m	-£0.31m	18619.20			Government Transformation and Service Delivery	3.49	DH_0044_1314-Q4,1516-Q2	DH	Amber/Green	Not new
DH_0045_1415-Q1	care.data	AR 2016	1516-Q2	DH	Amber/Red	01/09/2012	31/03/2020	£4.19m	£4.10m	-£0.09m	-£0.02m	0.00			ICT	7.58	DH_0045_1415-Q1,1516-Q2	DH	Amber/Red	Not new
DH_0048_1415-Q1	100,000 Genomes Project	AR 2016	1516-Q2	DH	Amber/Red	10/04/2013	31/12/2017	£50.00m	£27.40m	-£22.60m	-£0.45m	160.00			Government Transformation and Service Delivery	4.73	DH_0048_1415-Q1,1516-Q2	DH	Amber/Red	Not new
DH_0049_1415-Q1	NHS Choices	AR 2016	1516-Q2	DH	Amber/Red	03/08/2015	03/02/2016	£0.00m	£0.00m	£0.00m	£0.00m	0.00			ICT	0.50	DH_0049_1415-Q1,1516-Q2	DH	Amber/Red	Not new
DH_0050_1415-Q1	NHS Procurement Efficiency Programme	AR 2016	1516-Q2	DH	Red	01/09/2013	31/03/2016	£18.50m	£18.50m	£0.00m	£0.00m	71.90			Government Transformation and Service Delivery	2.58	DH_0050_1415-Q1,1516-Q2	DH	Red	Not new
DH_0056_1415-Q3	Visitor and Migrant NHS Cost Recovery Programme	AR 2016	1516-Q2	DH	Amber	01/09/2013	31/03/2017	£4.00m	£3.00m	-£1.00m	-£0.25m	10.50			Government Transformation and Service Delivery	3.58	DH_0056_1415-Q3,1516-Q2	DH	Amber	Joiner
DH_0057_1516-Q1	BT LSP	AR 2016	1516-Q2	DH	Amber	18/12/2003	31/10/2015	£59.89m	£82.77m	£22.88m	£0.38m	1743.03			Government Transformation and Service Delivery	11.87	DH_0057_1516-Q1,1516-Q2	DH	Amber	Joiner
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	AR 2016	1516-Q2	DWP	Amber/Green	02/04/2012	31/03/2017	£152.00m	£124.05m	-£27.95m	-£0.18m	834.00			Government Transformation and Service Delivery	4.99	DWP_0016_1213-Q2,1516-Q2	DWP	Amber/Green	Not new
DWP_0005_1112-Q1	Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme)	AR 2016	1516-Q2	DWP	Amber	01/05/2007	30/11/2018	£117.50m	£100.96m	-£16.54m	-£0.14m	995.40			Government Transformation and Service Delivery	11.58	DWP_0005_1112-Q1,1516-Q2	DWP	Amber	Not new
DWP_0003_1112-Q1	Child Maintenance Group	AR 2016	1516-Q2	DWP	Amber/Green	01/08/2009	31/12/2016	£122.20m	£122.20m	£0.00m	£0.00m	955.84			Government Transformation and Service Delivery	7.42	DWP_0003_1112-Q1,1516-Q2	DWP	Amber/Green	Not new
DWP_0018_1314-Q3	Fit for Work (formally Health & Work Service) Programme	AR 2016	1516-Q2	DWP	Amber	27/02/2013	31/03/2015	£15.60m	£14.07m	-£1.53m	-£0.10m	276.36			Government Transformation and Service Delivery	2.09	DWP_0018_1314-Q3,1516-Q2	DWP	Amber	Not new
DWP_0023_1415-Q2	New State Pension Project	AR 2016	1516-Q2	DWP	Amber/Green	27/02/2012	30/06/2016	£44.82m	£30.00m	-£14.82m	-£0.33m	174.11			Government Transformation and Service Delivery	4.34	DWP_0023_1415-Q2,1516-Q2	DWP	Amber/Green	Not new
DWP_0011_1112-Q2	Personal Independence Payment	AR 2016	1516-Q2	DWP	Amber/Red	31/10/2011	30/04/2018	£365.81m	£351.05m	-£14.76m	-£0.04m	3603.04			Government Transformation and Service Delivery	6.50	DWP_0011_1112-Q2,1516-Q2	DWP	Amber/Red	Not new
DWP_0009_1112-Q1	Universal Credit Programme	AR 2016	1516-Q2	DWP	Amber	17/11/2011	30/04/2020	£585.49m	£429.33m	-£156.16m	-£0.27m	15844.02			Government Transformation and Service Delivery	8.45	DWP_0009_1112-Q1,1516-Q2	DWP	Amber	Not new
FCO_0001_1112-Q1	ABUJA New Office and Residence	AR 2016	1516-Q2	FCO	Amber	01/01/2011	01/12/2016	£18.80m	£18.80m	£0.00m	£0.00m	46.00			Infrastructure and Construction	5.92	FCO_0001_1112-Q1,1516-Q2	FCO	Amber	Not new
FCO_0004_1112-Q1	ICTRe-procurement	AR 2016	1516-Q2	FCO	Amber/Green	01/01/2011	18/12/2015	£27.29m	£31.95m	£4.66m	£0.17m	161.10			ICT	4.96	FCO_0004_1112-Q1,1516-Q2	FCO	Amber/Green	Not new
FCO_0009_1516-Q2	Movement of Personal Effects Contract	AR 2016	1516-Q2	FCO	Amber	06/07/2015	30/09/2016	£0.00m	£0.00m	£0.00m	£0.00m	42.50			Government Transformation and Service Delivery	1.24	FCO_0009_1516-Q2,1516-Q2	FCO	Amber	Joiner
FCO_0008_1415-Q4	Technology Overhaul	AR 2016	1516-Q2	FCO	Amber	01/11/2015	01/03/2018	£25.56m	£13.40m	-£12.16m	-£0.48m	114.50			ICT	2.33	FCO_0008_1415-Q4,1516-Q2	FCO	Amber	Joiner
FCO_0006_1213-Q2	UKERP	AR 2016	1516-Q2	FCO	Amber/Red	01/06/2011	01/08/2016	£31.26m	£31.26m	£0.00m	£0.00m	64.90			Infrastructure and Construction	5.17	FCO_0006_1213-Q2,1516-Q2	FCO	Amber/Red	Not new
HMRC_0012_1415-Q1	Tax-Free Childcare	AR 2016	1516-Q2	HMRC	Amber	10/09/2013	30/06/2018	£41.87m	£37.51m	-£4.36m	-£0.10m	241.83			Government Transformation and Service Delivery	4.80	HMRC_0012_1415-Q1,1516-Q2	HMRC	Amber	Not new
HMRC_0013_1415-Q4	Columbus (formerly Aspire Replacement Programme)	AR 2016	1516-Q2	HMRC	Amber/Red	01/01/2014	31/12/2021	£88.00m	£88.00m	£0.00m	£0.00m	600.00			ICT	8.00	HMRC_0013_1415-Q4,1516-Q2	HMRC	Amber/Red	Joiner
HMRC_0014_1415-Q4	CUSTOMS DECLARATION SERVICES (CDS) Programme	AR 2016	1516-Q2	HMRC	Amber/Red	16/10/2013	31/12/2018	£21.94m	£18.98m	-£2.97m	-£0.14m	71.16			ICT	5.21	HMRC_0014_1415-Q4,1516-Q2	HMRC	Amber/Red	Joiner
HO_0030_1415-Q1	Adelphi Modernisation Programme	AR 2016	1516-Q2	HO	Red	05/06/2014	31/03/2016	£32.42m	£26.82m	-£5.60m	-£0.17m	185.30			ICT	1.82	HO_0030_1415-Q1,1516-Q2	HO	Red	Not new
HO_0012_1112-Q3	Communications Capabilities Development Programme	AR 2016	1516-Q2	HO	Amber	01/05/2010	01/04/2020	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)	Data Exempt under Section 24 of the Freedom of Information Act (2000)			ICT	9.92	HO_0012_1112-Q3,1516-Q2	HO	Amber	Not new
HO_0011_1112-Q2	Disclosure and Barring Service (DBS) Programme	AR 2016	1516-Q2	HO	Amber/Red	29/12/2010	31/07/2015	£123.56m	£147.50m	£23.94m	£0.19m	785.63			Government Transformation and Service Delivery	4.59	HO_0011_1112-Q2,1516-Q2	HO	Amber/Red	Not new
HO_0031_1415-Q1	Digital Services at the Border	AR 2016	1516-Q2	HO	Amber/Red	12/02/2014	31/03/2019	£16.67m	£17.89m	£1.22m	£0.07m	307.93			ICT	5.13	HO_0031_1415-Q1,1516-Q2	HO	Amber/Red	Not new
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2016	1516-Q2	HO	Amber	01/06/2011	31/12/2020	£34.13m	£34.13m	£0.00m	£0.00m	5319.23			ICT	9.59	HO_0016_1213-Q1,1516-Q2	HO	Amber	Not new
HO_0033_1415-Q3	Home Office Biometrics Programme	AR 2016	1516-Q2	HO	Amber	01/04/2014	30/11/2019	£63.70m	£63.70m	£0.00m	£0.00m	640.30			ICT	5.66	HO_0033_1415-Q3,1516-Q2	HO	Amber	Joiner
HO_0029_1314-Q4	Immigration Platform Technologies (IPT)	AR 2016	1516-Q2	HO	Amber/Red	01/04/2013	31/03/2017	£71.10m	£49.00m	-£22.10m	-£0.31m	208.80			ICT	4.00	HO_0029_1314-Q4,1516-Q2	HO	Amber/Red	Not new
HO_0008_1112-Q1	SIS II Programme	AR 2016	1516-Q2	HO	Amber/Green	01/04/2006	30/06/2015	£9.50m	£9.50m	£0.00m	£0.00m	195.10			ICT	9.25	HO_0008_1112-Q1,1516-Q2	HO	Amber/Green	Not new
HO_0032_1415-Q1	Technology Platforms for Tomorrow	AR 2016	1516-Q2	HO	Amber/Red	01/02/2014	01/09/2016	£29.00m	£29.00m	£0.00m	£0.00m	369.50			ICT	2.58	HO_0032_1415-Q1,1516-Q2	HO	Amber/Red	Not new
MOD_0064_1112-Q2	Carrier Enabled Power Projection	AR 2016	1516-Q2	MOD	Amber	31/01/2011	01/12/2026	£1.44m	£1.44m	£0.00m	£0.00m	21.69			Government Transformation and Service Delivery	15.83	MOD_0064_1112-Q2,1516-Q2	MOD	Amber	Not new
MOD_0065_1112-Q2	CHINOOK (incl. Project Julius)	AR 2016	1516-Q2	MOD	Green	01/04/2008	30/06/2017	£97.70m	£97.70m	£0.00m	£0.00m	1009.17			Military Capability	9.25	MOD_0065_1112-Q2,1516-Q2	MOD	Green	Not new
MOD_0078_1213-Q1	Core Production Capability	AR 2016	1516-Q2	MOD	Amber	23/04/2012	14/11/2028	£170.50m	£158.13m	-£12.37m	-£0.07m	1443.46			Military Capability	16.56	MOD_0078_1213-Q1,1516-Q2	MOD	Amber	Not new
HO_0034_1516-Q2	Cyclamen Project	AR 2016	1516-Q2	HO	Exempt	01/04/2014	01/04/2021	Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000)	Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000)	Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000)	Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000)	Exempt under Sections 24 and 31(1) of the Freedom of Information Act (2000)			ICT	7.00	HO_0034_1516-Q2,1516-Q2	HO	Exempt	Joiner
MOD_0079_1213-Q1	Lightning II Programme	AR 2016	1516-Q2	MOD	Amber	01/10/2001	31/03/2026	£551.47m	£529.44m	-£22.03m	-£0.04m	12941.61			Military Capability	24.50	MOD_0079_1213-Q1,1516-Q2	MOD	Amber	Not new
MOD_0033_1112-Q1	MARSHALL	AR 2016	1516-Q2	MOD	Amber/Green	03/04/2006	04/10/2020	£74.42m	£70.29m	-£4.13m	-£0.06m	1819.96			Military Capability	14.51	MOD_0033_1112-Q1,1516-Q2	MOD	Amber/Green	Not new
MOD_0070_1112-Q2	New Employment Model	AR 2016	1516-Q2	MOD	Amber	02/05/2011	29/10/2021	£13.61m	£8.92m	-£4.69m	-£0.34m	202.88			Government Transformation and Service Delivery	10.49	MOD_0070_1112-Q2,1516-Q2	MOD	Amber	Not new
MOD_0103_1516-Q1	Operational Information Services	AR 2016	1516-Q2	MOD	Red	01/04/2019	01/04/2024	£9.60m	£9.60m	£0.00m	£0.00m	73.83			Military Capability	5.00	MOD_0103_1516-Q1,1516-Q2	MOD	Red	Joiner
MOD_0040_1112-Q1	PUMA	AR 2016	1516-Q2	MOD	Green	01/02/2007	31/03/2016	£2.16m	£2.25m	£0.09m	£0.04m	374.93			Military Capability	9.16	MOD_0040_1112-Q1,1516-Q2	MOD	Green	Not new
MOD_0047_1112-Q1	Spearfish Upgrade Programme	AR 2016	1516-Q2	MOD	Amber/Green	01/04/2008	31/03/2024	£37.40m	£37.09m	-£0.31m	-£0.01m	415.97			Military Capability	16.00	MOD_0047_1112-Q1,1516-Q2	MOD	Amber/Green	Not new
MOD_0087_1314-Q2	The Materiel Strategy	AR 2016	1516-Q2	MOD	Amber	02/05/2011	01/05/2018	£78.00m	£74.23m	-£3.77m	-£0.05m	379.07			Government Transformation and Service Delivery	7.00	MOD_0087_1314-Q2,1516-Q2	MOD	Amber	Not new
MOD_0001_1112-Q1	A400M	AR 2016	1516-Q2	MOD	Amber/Green	17/05/2000	31/03/2022	£541.67m	£491.80m	-£49.87m	-£0.09m	3713.09			Military Capability	21.87	MOD_0001_1112-Q1,1516-Q2	MOD	Amber/Green	Not new
MOD_0004_1112-Q1	Airseeker	AR 2016	1516-Q2	MOD	Amber/Green	18/03/2010	01/04/2018	£134.59m	£132.06m	-£2.52m	-£0.02m	757.80			Military Capability	8.04	MOD_0004_1112-Q1,1516-Q2	MOD	Amber/Green	Not new
MOD_0091_1415-Q3	Armoured Cavalry 2025	AR 2016	1516-Q2	MOD	Amber	22/01/2014	30/04/2025	£245.92m	£237.06m	-£8.86m	-£0.04m	6831.53			Military Capability	11.27	MOD_0091_1415-Q3,1516-Q2	MOD	Amber	Joiner
MOD_0092_1415-Q3	Armoured Infantry 2026	AR 2016	1516-Q2	MOD	Amber	04/12/2014	31/12/2026	£90.50m	£84.15m	-£6.34m	-£0.07m	2176.45			Military Capability	12.07	MOD_0092_1415-Q3,1516-Q2	MOD	Amber	Joiner
MOD_0085_1314-Q2	Army Basing Programme	AR 2016	1516-Q2	MOD	Amber/Red	22/05/2013	31/03/2020	£345.74m	£146.74m	-£199.00m	-£0.58m	1972.11			Government Transformation and Service Delivery	6.86	MOD_0085_1314-Q2,1516-Q2	MOD	Amber/Red	Not new
MOD_0093_1415-Q3	Army Reserve Development Programme	AR 2016	1516-Q2	MOD	Amber/Red	01/12/2014	01/01/2017	£168.84m	£162.61m	-£6.23m	-£0.04m	1998.39			Military Capability	2.09	MOD_0093_1415-Q3,1516-Q2	MOD	Amber/Red	Joiner
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2016	1516-Q2	MOD	Amber/Red	17/03/1997	31/03/2024	£638.65m	£641.67m	£3.02m	£0.00m	9935.48			Military Capability	27.04	MOD_0076_1213-Q1,1516-Q2	MOD	Amber/Red	Not new
MOD_0077_1213-Q1	Complex Weapons	AR 2016	1516-Q2	MOD	Amber	31/03/2008	01/04/2032	£444.09m	£336.84m	-£107.26m	-£0.24m	18499.66			Military Capability	24.00	MOD_0077_1213-Q1,1516-Q2	MOD	Amber	Not new
MOD_0094_1415-Q3	Contracting, Purchasing and Finance	AR 2016	1516-Q2	MOD	Amber/Red	01/12/2011	31/03/2018	£38.64m	£33.85m	-£4.79m	-£0.12m	159.73			Government Transformation and Service Delivery	6.33	MOD_0094_1415-Q3,1516-Q2	MOD	Amber/Red	Joiner
MOD_0017_1112-Q1	Crowsnest Programme	AR 2016	1516-Q2	MOD	Amber/Green	26/03/2013	30/09/2022	£4.08m	£13.60m	£9.52m	£2.34m	Exempt under section 43 of the Freedom of Information Act (2000).			Military Capability	9.51	MOD_0017_1112-Q1,1516-Q2	MOD	Amber/Green	Not new
MOD_0099_1516-Q1	EMPORIUM	AR 2016	1516-Q2	MOD	Amber	21/10/2011	01/12/2017	£7.22m	£7.22m	£0.00m	£0.00m	236.48			Government Transformation and Service Delivery	6.11	MOD_0099_1516-Q1,1516-Q2	MOD	Amber	Joiner
MOD_0100_1516-Q1	Future Beyond Line Of Sight	AR 2016	1516-Q2	MOD	Amber	01/01/2011	31/08/2040	£9.84m	£4.37m	-£5.47m		7280.69			Military Capability	29.66	MOD_0100_1516-Q1,1516-Q2	MOD	Amber	Joiner
MOD_0102_1516-Q1	GRAPEVINE 2	AR 2016	1516-Q2	MOD	Amber	01/12/2009	22/06/2020	£110.03m	£131.12m	£21.09m	£0.19m	1334.77			Government Transformation and Service Delivery	10.56	MOD_0102_1516-Q1,1516-Q2	MOD	Amber	Joiner
MOD_0069_1112-Q2	Logistics Commodities Services Transformation	AR 2016	1516-Q2	MOD	Amber	01/08/2011	01/02/2018	£113.52m	£119.29m	£5.77m	£0.05m	652.42			Government Transformation and Service Delivery	6.51	MOD_0069_1112-Q2,1516-Q2	MOD	Amber	Not new
MOD_0036_1112-Q1	Maritime Sustainment Programme	AR 2016	1516-Q2	MOD	Amber/Green	25/07/2005	30/04/2018	£194.98m	£176.84m	-£18.14m	-£0.09m	596.50			Military Capability	12.76	MOD_0036_1112-Q1,1516-Q2	MOD	Amber/Green	Not new
MOD_0035_1112-Q1	Merlin Programme	AR 2016	1516-Q2	MOD	Green	01/06/2003	31/03/2016	£1.00m	£0.55m	-£0.45m	-£0.45m	718.17			Military Capability	12.83	MOD_0035_1112-Q1,1516-Q2	MOD	Green	Not new
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2016	1516-Q2	MOD	Exempt	01/04/2008	30/04/2025	£1085.43m	£1009.75m	-£75.69m	-£0.07m	21028.75			Military Capability	17.08	MOD_0038_1112-Q1,1516-Q2	MOD	Exempt	Not new
MOD_0042_1112-Q1	Queen Elizabeth Programme	AR 2016	1516-Q2	MOD	Amber	01/12/1998	31/03/2023	£712.93m	£687.01m	-£25.92m	-£0.04m	7289.68			Military Capability	24.33	MOD_0042_1112-Q1,1516-Q2	MOD	Amber	Not new
MOD_0055_1112-Q1	Type 26 Global Combat Ship Programme	AR 2016	1516-Q2	MOD	Exempt	21/07/2008	31/12/2034	£222.30m	£222.00m	-£0.30m	£0.00m	Exempt under sections 36 and 43 of the Freedom of Information Act (2000)			Military Capability	26.44	MOD_0055_1112-Q1,1516-Q2	MOD	Exempt	Not new
MOD_0061_1112-Q1	WATCHKEEPER	AR 2016	1516-Q2	MOD	Amber	01/03/1998	03/07/2017	£61.03m	£58.94m	-£2.09m	-£0.03m	1169.78			Military Capability	19.34	MOD_0061_1112-Q1,1516-Q2	MOD	Amber	Not new
MOD_0062_1112-Q1	Wildcat Programme	AR 2016	1516-Q2	MOD	Amber/Green	01/12/2001	31/05/2016	£39.46m	£39.46m	-£0.01m	£0.00m	1610.84			Military Capability	14.50	MOD_0062_1112-Q1,1516-Q2	MOD	Amber/Green	Not new
MOJ_0004_1112-Q1	Future IT Sourcing Programme (FITS)	AR 2016	1516-Q2	MOJ	Amber/Red	01/03/2011	30/11/2017	£457.00m	£457.00m	£0.00m	£0.00m	1706.00			ICT	6.75	MOJ_0004_1112-Q1,1516-Q2	MOJ	Amber/Red	Not new
MOJ_0023_1314-Q1	North Wales Prison (NWP ) Programme	AR 2016	1516-Q2	MOJ	Amber	10/01/2013	31/03/2018	£101.00m	£81.20m	-£19.80m	-£0.20m	2541.00			Infrastructure and Construction	5.22	MOJ_0023_1314-Q1,1516-Q2	MOJ	Amber	Not new
MOJ_0021_1314-Q1	Common Platform (CP)	AR 2016	1516-Q2	MOJ	Amber/Red	01/11/2012	29/03/2019	£63.19m	£63.19m	£0.00m	£0.00m	380.84			ICT	6.40	MOJ_0021_1314-Q1,1516-Q2	MOJ	Amber/Red	Not new
MOJ_0027_1314-Q2	CJS Efficiency Programme (CJS Efficiency)	AR 2016	1516-Q2	MOJ	Amber/Green	30/04/2013	31/12/2016	£28.10m	£33.90m	£5.80m	£0.21m	85.10			ICT	3.67	MOJ_0027_1314-Q2,1516-Q2	MOJ	Amber/Green	Not new
MOJ_0029_1415-Q1	Legal Aid Crime Change (LACC) Programme	AR 2016	1516-Q2	MOJ	Green	07/07/2013	29/02/2016	£4.35m	£5.61m	£1.26m	£0.29m	45.01			ICT	2.65	MOJ_0029_1415-Q1,1516-Q2	MOJ	Green	Not new
MOJ_0003_1112-Q1	Electronic Monitoring (EM)	AR 2016	1516-Q2	MOJ	Red	10/05/2011	30/11/2016	£117.10m	£90.82m	-£26.28m	-£0.22m	411.60			Government Transformation and Service Delivery	5.56	MOJ_0003_1112-Q1,1516-Q2	MOJ	Red	Not new
MOJ_0005_1112-Q1	Her Majesty's Courts and Tribunals Services (HMCTS) Compliance & Enforcement Services Project (CESP)	AR 2016	1516-Q2	MOJ	Amber/Red	21/06/2012	07/01/2017	£44.80m	£45.12m	£0.32m	£0.01m	439.20			Government Transformation and Service Delivery	4.55	MOJ_0005_1112-Q1,1516-Q2	MOJ	Amber/Red	Not new
MOJ_0006_1112-Q1	Integrated Delivery Programme (IDP)	AR 2016	1516-Q2	MOJ	Amber	01/07/2009	31/03/2016	£2.69m	£2.49m	-£0.20m	-£0.07m	71.48			ICT	6.75	MOJ_0006_1112-Q1,1516-Q2	MOJ	Amber	Not new
MOJ_0028_1314-Q2	Her Majesty's Courts and Tribunals Services (HMCTS) Reform Programme	AR 2016	1516-Q2	MOJ	Amber/Red	21/03/2013	31/03/2020	£48.16m	£48.20m	£0.04m	£0.00m	510.40			Government Transformation and Service Delivery	7.03	MOJ_0028_1314-Q2,1516-Q2	MOJ	Amber/Red	Not new
MOJ_0022_1314-Q1	Legal Aid Transformation Programme (LAT)	AR 2016	1516-Q2	MOJ	Amber	04/12/2012	01/11/2015	£1.32m	£2.11m	£0.79m	£0.60m	6.17			Government Transformation and Service Delivery	2.91	MOJ_0022_1314-Q1,1516-Q2	MOJ	Amber	Not new
MOJ_0015_1112-Q2	NOMS ICTS Services (NICTS) Programme (formally part of Quantum Re-compete Project)	AR 2016	1516-Q2	MOJ	Amber	18/07/2011	29/03/2016	£0.00m	£14.43m	£14.43m	£0.00m	41.75			ICT	4.70	MOJ_0015_1112-Q2,1516-Q2	MOJ	Amber	Not new
MOJ_0024_1314-Q1	Prison Unit Cost Programme (PUCP)	AR 2016	1516-Q2	MOJ	Amber	20/11/2012	01/12/2016	£30.50m	£23.30m	-£7.20m	-£0.24m	119.50			Government Transformation and Service Delivery	4.03	MOJ_0024_1314-Q1,1516-Q2	MOJ	Amber	Not new
MOJ_0025_1314-Q1	Transforming Rehabilitation (TR) Programme	AR 2016	1516-Q2	MOJ	Green	05/11/2012	31/03/2015	£932.93m	£932.95m	£0.02m	£0.00m	9127.61			Government Transformation and Service Delivery	2.40	MOJ_0025_1314-Q1,1516-Q2	MOJ	Green	Not new
MOJ_0008_1112-Q1	MoJ Shared Services Evolve (SS Evolve) Programme	AR 2016	1516-Q2	MOJ	Amber/Red	07/09/2013	05/11/2015	£93.91m	£82.05m	-£11.86m	-£0.13m	390.77			ICT	2.16	MOJ_0008_1112-Q1,1516-Q2	MOJ	Amber/Red	Not new
MOJ_0030_1516-Q1	Secure Training centre (STC) Retendering Project	AR 2016	1516-Q2	MOJ	Amber/Green	05/11/2012	01/05/2017	£0.73m	£0.73m	£0.00m	£0.00m	165.20			Government Transformation and Service Delivery	4.48	MOJ_0030_1516-Q1,1516-Q2	MOJ	Amber/Green	Joiner
MOJ_0031_1516-Q2	Transforming Prisoner Telephony (TPT)	AR 2016	1516-Q2	MOJ	Amber/Red	01/02/2015	31/03/2020	£0.90m	£0.90m	£0.00m	£0.00m	39.30			Government Transformation and Service Delivery	5.16	MOJ_0031_1516-Q2,1516-Q2	MOJ	Amber/Red	Joiner
NCA_0001_1415-Q2	Novo (NCA Transformation) Programme	AR 2016	1516-Q2	NCA	Amber	01/04/2014	31/03/2019	£44.80m	£38.70m	-£6.10m	-£0.14m	151.50			Government Transformation and Service Delivery	5.00	NCA_0001_1415-Q2,1516-Q2	NCA	Amber	Not new
ONS_0002_1112-Q1	Census Transformation Programme	AR 2016	1516-Q2	ONS	Amber/Green	01/01/2015	31/03/2025	£19.93m	£19.90m	-£0.03m	£0.00m	981.32			Government Transformation and Service Delivery	10.25	ONS_0002_1112-Q1,1516-Q2	ONS	Amber/Green	Not new
ONS_0004_1213-Q2	Electronic Data Collection (EDC)	AR 2016	1516-Q2	ONS	Amber	27/01/2014	01/11/2019	£6.03m	£6.11m	£0.08m	£0.01m	23.70			Government Transformation and Service Delivery	5.76	ONS_0004_1213-Q2,1516-Q2	ONS	Amber	Not new
ONS_0005_1213-Q2	ESA10/BPM6 Programme (European Systems of Accounting 2010)	AR 2016	1516-Q2	ONS	Amber/Green	05/02/2011	30/03/2020	£11.49m	£9.45m	-£2.04m	-£0.18m	57.85			Government Transformation and Service Delivery	9.15	ONS_0005_1213-Q2,1516-Q2	ONS	Amber/Green	Not new
MOD_0080_1213-Q1	Successor SSBN	AR 2016	1516-Q2	MOD	Amber/Red	14/04/2011	Exempt under section 35 of the Freedom of Information Act (2000)	£770.41m	£739.34m	-£31.06m	-£0.04m	Exempt under section 43 of the Freedom of Information Act (2000)			Military Capability	0.00	MOD_0080_1213-Q1,1516-Q2	MOD	Amber/Red	Not new
MOD_0095_1415-Q2	Cryptographic Enabling Services	AR 2016	1516-Q2	MOD	Exempt	Exempt under section 26 of the Freedom of Information Act (2000)	Exempt under section 26 of the Freedom of Information Act (2000)	Exempt under section 26 of the Freedom of Information Act (2000)	Exempt under section 26 of the Freedom of Information Act (2000)	£0.00m	£0.00m	Exempt under section 26 of the Freedom of Information Act (2000)			Military Capability	0.00	MOD_0095_1415-Q2,1516-Q2	MOD	Exempt	Not new
MOD_0101_1516-Q1	GRAPEVINE 1	AR 2016	1516-Q2	MOD	Amber	01/04/2015	05/03/2018	Exempt under section 43 of the Freedom of Information Act (2000).	Exempt under section 43 of the Freedom of Information Act (2000).			Exempt under section 43 of the Freedom of Information Act (2000).			Government Transformation and Service Delivery	2.93	MOD_0101_1516-Q1,1516-Q2	MOD	Amber	Joiner
BEIS_0001_1617-Q2	Heat Networks Investment Project	AR 2017	1617-Q2	BEIS	Exempt	25/11/2015	31/03/2021	£36.60m	£36.60m	£0.00m	£0.00m	352.70	£352.70m	£0.00m	Infrastructure and Construction	5.35	BEIS_0001_1617-Q2,1617-Q2	BEIS	Exempt	Joiner
BIS_0009_1112-Q1	The Francis Crick Institute	AR 2017	1617-Q2	BEIS	Amber	01/10/2006	31/12/2016	£27.70m	£24.00m	-£3.70m	-£0.13m	752.70	£283.70m	£469.00m	Infrastructure and Construction	10.26	BIS_0009_1112-Q1,1617-Q2	BEIS	Amber	Not new
BIS_0010_1112-Q4	Project Eagle (formerly Urenco Future Options)	AR 2017	1617-Q2	BEIS	Red	01/02/2010	30/04/2013	£1.70m	£1.70m	£0.00m	£0.00m	32.60	£32.60m	£0.00m	Government Transformation and Service Delivery	3.24	BIS_0010_1112-Q4,1617-Q2	BEIS	Red	Not new
BIS_0014_1415-Q3	New Polar Research Vessel	AR 2017	1617-Q2	BEIS	Amber/Green	01/05/2014	01/07/2020	£63.00m	£71.50m	£8.50m	£0.13m	1403.00	£1403.00m	£0.00m	Infrastructure and Construction	6.17	BIS_0014_1415-Q3,1617-Q2	BEIS	Amber/Green	Not new
BIS_0015_1516-Q1	Local Land Charges (LLC) Programme	AR 2017	1617-Q2	BEIS	Amber	01/03/2014	17/11/2023	£12.20m	£9.90m	-£2.30m	-£0.19m	193.30	£193.30m	£0.00m	ICT	9.72	BIS_0015_1516-Q1,1617-Q2	BEIS	Amber	Not new
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2017	1617-Q2	BEIS	Amber	30/06/2008	31/12/2040	£28.47m	£28.53m	£0.06m	£0.00m	11751.97	£11751.97m	£0.00m	Infrastructure and Construction	32.53	DECC_0005_1112-Q1,1617-Q2	BEIS	Amber	Not new
DECC_0010_1112-Q1	Smart Metering Implementation Programme	AR 2017	1617-Q2	BEIS	Amber	02/12/2009	31/12/2020	£524.26m	£523.96m	-£0.30m	£0.00m	17215.78	£124.11m	£17091.67m	Infrastructure and Construction	11.09	DECC_0010_1112-Q1,1617-Q2	BEIS	Amber	Not new
DECC_0012_1213-Q1	FID Enabling for Hinkley Point C	AR 2017	1617-Q2	BEIS	Green	01/09/2011	30/09/2016	£1.80m	£1.70m	-£0.10m	-£0.06m	49891.20	£25.80m	£49865.40m	Infrastructure and Construction	5.08	DECC_0012_1213-Q1,1617-Q2	BEIS	Green	Not new
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	AR 2017	1617-Q2	BEIS	Amber	03/04/2012	31/08/2015	£692.00m	£434.00m	-£258.00m	-£0.37m	3860.00	£3860.00m	£0.00m	Infrastructure and Construction	3.41	DECC_0013_1213-Q1,1617-Q2	BEIS	Amber	Not new
DECC_0017_1516-Q1	Sellafield Model Change (SMC)	AR 2017	1617-Q2	BEIS	Amber	13/01/2015	24/05/2017	£2302.50m	£2204.50m	-£98.00m	-£0.04m	29992.92	£29992.92m	£0.00m	Government Transformation and Service Delivery	2.36	DECC_0017_1516-Q1,1617-Q2	BEIS	Amber	Not new
CO_0011_1415-Q4	ISSC2	AR 2017	1617-Q2	CO	Amber	28/12/2012	30/04/2015	£5.70m	£5.70m	£0.00m	£0.00m	26.10	£26.10m	£0.00m	Government Transformation and Service Delivery	2.34	CO_0011_1415-Q4,1617-Q2	CO	Amber	Not new
CO_0012_1415-Q4	Commercial Capability Programme	AR 2017	1617-Q2	CO	Amber	01/01/2015	31/03/2018	£6.20m	£6.20m	£0.00m	£0.00m	17.50	£17.50m	£0.00m	Government Transformation and Service Delivery	3.25	CO_0012_1415-Q4,1617-Q2	CO	Amber	Not new
CO_0013_1516-Q2	Foxhound Programme	AR 2017	1617-Q2	CO	Amber	01/09/2013	01/07/2018	£21.75m	£21.75m	£0.00m	£0.00m	189.30	£189.30m	£0.00m	ICT	4.83	CO_0013_1516-Q2,1617-Q2	CO	Amber	Not new
CO_0014_1516-Q2	Government Hubs Programme	AR 2017	1617-Q2	CO	Amber	01/05/2015	31/12/2021	£55.60m	£51.90m	-£3.70m	-£0.07m	1076.90	£1076.90m	£0.00m	Government Transformation and Service Delivery	6.67	CO_0014_1516-Q2,1617-Q2	CO	Amber	Not new
CO_0015_1516-Q2	GOV UK Verify	AR 2017	1617-Q2	CO	Amber/Green	01/04/2012	31/03/2020	£0.00m	£0.00m	£0.00m	£0.00m	Exempt		£0.00m	ICT	8.00	CO_0015_1516-Q2,1617-Q2	CO	Amber/Green	Not new
CO_0016_1516-Q4	16/17 New Property Model Programme	AR 2017	1617-Q2	CO	Amber	01/04/2015	01/04/2021	£17.90m	£17.90m	£0.00m	£0.00m	94.50	£94.50m	£0.00m	Government Transformation and Service Delivery	6.01	CO_0016_1516-Q4,1617-Q2	CO	Amber	Joiner
CPS_0001_1314-Q4	ICTRestructure Programme	AR 2017	1617-Q2	CPS	Amber/Green	01/10/2013	31/08/2016	£21.70m	£22.00m	£0.30m	£0.01m	146.00	£146.00m	£0.00m	ICT	2.92	CPS_0001_1314-Q4,1617-Q2	CPS	Amber/Green	Not new
DCMS_0001_1112-Q1	Broadband Delivery Programme	AR 2017	1617-Q2	DCMS	Amber/Green	06/12/2010	31/12/2020	£456.10m	£437.80m	-£18.30m	-£0.04m	2223.90	£838.90m	£1385.00m	Infrastructure and Construction	10.08	DCMS_0001_1112-Q1,1617-Q2	DCMS	Amber/Green	Not new
DCMS_0004_1112-Q1	The Tate Modern Project	AR 2017	1617-Q2	DCMS	Green	01/01/2010	31/12/2016	£12.90m	£10.90m	-£2.00m	-£0.16m	271.00	£73.10m	£197.90m	Infrastructure and Construction	7.00	DCMS_0004_1112-Q1,1617-Q2	DCMS	Green	Not new
DCMS_0008_1516-Q4	Blythe House Programme	AR 2017	1617-Q2	DCMS	Amber/Red	25/11/2015	31/03/2023	£29.00m	£16.42m	-£12.58m	-£0.43m	337.95	£150.00m	£187.95m	Infrastructure and Construction	7.35	DCMS_0008_1516-Q4,1617-Q2	DCMS	Amber/Red	Joiner
DCMS_0009_1516-Q4	700 MHz Clearance Programme	AR 2017	1617-Q2	DCMS	Amber	13/01/2016	01/01/2022	£71.78m	£34.12m	-£37.66m	-£0.52m	594.90	£594.90m	£0.00m	Infrastructure and Construction	5.97	DCMS_0009_1516-Q4,1617-Q2	DCMS	Amber	Joiner
DEFRA_0001_1112-Q1	CAP Delivery Programme	AR 2017	1617-Q2	DEFRA	Amber	01/01/2011	31/03/2017	£13.14m	£24.60m	£11.46m	£0.87m	215.88	£215.88m	£0.00m	Government Transformation and Service Delivery	6.25	DEFRA_0001_1112-Q1,1617-Q2	DEFRA	Amber	Not new
DEFRA_0004_1112-Q1	Thames Estuary Asset Management Programme (TEAM2100)	AR 2017	1617-Q2	DEFRA	Green	01/04/2010	31/12/2025	£23.40m	£20.30m	-£3.10m	-£0.13m	318.42	£318.42m	£0.00m	Infrastructure and Construction	15.76	DEFRA_0004_1112-Q1,1617-Q2	DEFRA	Green	Not new
DEFRA_0005_1213-Q3	Thames Tideway Tunnel	AR 2017	1617-Q2	DEFRA	Amber/Green	07/09/2010	31/12/2023	£1.50m	£1.50m	£0.00m	£0.00m	4159.80	£22.80m	£4137.00m	Infrastructure and Construction	13.32	DEFRA_0005_1213-Q3,1617-Q2	DEFRA	Amber/Green	Not new
DEFRA_0006_1516-Q1	DEFRA UNITY PROGRAMME	AR 2017	1617-Q2	DEFRA	Amber/Red	01/11/2014	31/10/2018	£160.80m	£160.80m	£0.00m	£0.00m	1048.40	£1048.40m	£0.00m	ICT	4.00	DEFRA_0006_1516-Q1,1617-Q2	DEFRA	Amber/Red	Not new
BIS_0008_1112-Q1	ICR Student Loans Monetisation	AR 2017	1617-Q2	DFE	Amber	01/03/2010	31/03/2017	£0.00m	£5.50m	£5.50m	£0.00m	15.29	£15.29m	£0.00m	Government Transformation and Service Delivery	7.09	BIS_0008_1112-Q1,1617-Q2	DFE	Amber	Not new
DFE_0005_1415-Q2	PSBP Private Finance	AR 2017	1617-Q2	DFE	Amber/Green	19/07/2011	01/07/2043	£329.90m	£326.86m	-£3.04m	-£0.01m	2153.04	£2153.04m	£0.00m	Infrastructure and Construction	31.97	DFE_0005_1415-Q2,1617-Q2	DFE	Amber/Green	Not new
DFE_0007_1617-Q1	30 Hrs Free Childcare Project	AR 2017	1617-Q2	DFE	Amber/Red	11/05/2015	31/03/2020	£80.00m	£79.30m	-£0.70m	-£0.01m	1920.72	£1920.72m	£0.00m	Government Transformation and Service Delivery	4.89	DFE_0007_1617-Q1,1617-Q2	DFE	Amber/Red	Joiner
DfE_0008_1617-Q1	Priority School Building Programme (PSBP)	AR 2017	1617-Q2	DFE	Amber	19/07/2011	31/12/2075	£745.07m	£724.07m	-£21.00m	-£0.03m	4403.01	£4403.01m	£0.00m	Infrastructure and Construction	64.50	DfE_0008_1617-Q1,1617-Q2	DFE	Amber	Joiner
DfE_0009_1617-Q2	Apprenticeships Reform Programme	AR 2017	1617-Q2	DFE	Amber/Red	08/05/2015	01/04/2021	£1919.40m	£1784.20m	-£135.20m	-£0.07m	11347.50	£11347.50m	£0.00m	Government Transformation and Service Delivery	5.90	DfE_0009_1617-Q2,1617-Q2	DFE	Amber/Red	Joiner
DFID_0001_1112-Q1	St Helena Airport	AR 2017	1617-Q2	DFID	Amber/Red	15/03/2005	31/08/2026	£7.20m	£11.50m	£4.30m	£0.60m	445.45	£445.45m	£0.00m	Infrastructure and Construction	21.48	DFID_0001_1112-Q1,1617-Q2	DFID	Amber/Red	Not new
DFT_0001_1112-Q1	Crossrail Programme	AR 2017	1617-Q2	DFT	Amber/Green	22/07/2008	31/12/2019	£770.49m	£2167.20m	£1396.71m	£1.81m	14768.87	£7576.77m	£7192.10m	Infrastructure and Construction	11.45	DFT_0001_1112-Q1,1617-Q2	DFT	Amber/Green	Not new
DFT_0004_1112-Q1	High Speed Rail Programme (HS2)	AR 2017	1617-Q2	DFT	Amber/Red	28/02/2011	31/12/2033	£928.62m	£928.62m	£0.00m	£0.00m	55700.00	£55700.00m	£0.00m	Infrastructure and Construction	22.85	DFT_0004_1112-Q1,1617-Q2	DFT	Amber/Red	Not new
DFT_0005_1112-Q1	Intercity Express Programme	AR 2017	1617-Q2	DFT	Amber	01/06/2005	06/02/2020	£98.00m	£146.34m	£48.34m	£0.49m	6512.95	£236.95m	£6276.00m	Infrastructure and Construction	14.69	DFT_0005_1112-Q1,1617-Q2	DFT	Amber	Not new
DFT_0014_1112-Q1	Search and Rescue Helicopters	AR 2017	1617-Q2	DFT	Amber/Green	08/02/2011	08/09/2017	£207.60m	£193.50m	-£14.10m	-£0.07m	2157.40	£2157.40m	£0.00m	Infrastructure and Construction	6.59	DFT_0014_1112-Q1,1617-Q2	DFT	Amber/Green	Not new
DFT_0015_1112-Q1	Shared Services Implementation Programme	AR 2017	1617-Q2	DFT	Amber	10/12/2010	01/06/2013	£20.20m	£9.90m	-£10.30m	-£0.51m	161.10	£161.10m	£0.00m	ICT	2.48	DFT_0015_1112-Q1,1617-Q2	DFT	Amber	Not new
DFT_0016_1112-Q1	Thameslink Programme	AR 2017	1617-Q2	DFT	Amber/Green	01/07/2005	31/12/2026	£20.74m	£20.99m	£0.25m	£0.01m	7287.70	£337.70m	£6950.00m	Infrastructure and Construction	21.52	DFT_0016_1112-Q1,1617-Q2	DFT	Amber/Green	Not new
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	AR 2017	1617-Q2	DFT	Amber	01/09/2012	30/09/2021	£106.30m	£131.90m	£25.60m	£0.24m	1492.30	£1492.30m	£0.00m	Infrastructure and Construction	9.08	DFT_0020_1314-Q2,1617-Q2	DFT	Amber	Not new
DFT_0021_1314-Q3	Rail Franchising Programme	AR 2017	1617-Q2	DFT	Amber	26/03/2013	29/11/2029	-£74.90m	-£53.20m	£21.70m	-£0.29m	-7169.20	-£7169.20m	£0.00m	Government Transformation and Service Delivery	16.69	DFT_0021_1314-Q3,1617-Q2	DFT	Amber	Not new
DfT_0022_1415-Q4	Lower Thames Crossing Feasibility	AR 2017	1617-Q2	DFT	Amber/Red	30/05/2014	31/12/2026	£35.60m	£26.62m	-£8.98m	-£0.25m	199.10	£199.10m	£0.00m	Infrastructure and Construction	12.60	DfT_0022_1415-Q4,1617-Q2	DFT	Amber/Red	Not new
DfT_0023_1516-Q3	Airport Capacity Programme	AR 2017	1617-Q2	DFT	Amber	01/07/2015	31/12/2029	£14.00m	£9.00m	-£5.00m	-£0.36m	79.00	£79.00m	£0.00m	Infrastructure and Construction	14.51	DfT_0023_1516-Q3,1617-Q2	DFT	Amber	Joiner
DFT_0024_1516-Q4	A303 Amesbury to Berwick Down	AR 2017	1617-Q2	DFT	Red	01/12/2014	01/06/2024	£8.60m	£11.30m	£2.70m	£0.31m	385.11	£385.11m	£0.00m	Infrastructure and Construction	9.51	DFT_0024_1516-Q4,1617-Q2	DFT	Red	Joiner
DFT_0025_1617-Q1	East West Rail Programme (Western Section)	AR 2017	1617-Q2	DFT	Amber/Red	31/10/2012	31/03/2024	£72.50m	£69.10m	-£3.40m	-£0.05m	1592.00	£0.00m	£1592.00m	Infrastructure and Construction	11.42	DFT_0025_1617-Q1,1617-Q2	DFT	Amber/Red	Joiner
DFT_0026_1617-Q1	Great Western Route Modernisation (GWRM) including electrification	AR 2017	1617-Q2	DFT	Amber/Red	01/12/2011	31/12/2024	£772.40m	£740.10m	-£32.30m	-£0.04m	5507.00	£0.00m	£5507.00m	Infrastructure and Construction	13.09	DFT_0026_1617-Q1,1617-Q2	DFT	Amber/Red	Joiner
DFT_0027_1617-Q1	Midland Main Line Programme	AR 2017	1617-Q2	DFT	Amber	01/01/2011	31/12/2024	£263.20m	£256.50m	-£6.70m	-£0.03m	2620.00	£0.00m	£2620.00m	Infrastructure and Construction	14.01	DFT_0027_1617-Q1,1617-Q2	DFT	Amber	Joiner
DFT_0028_1617-Q1	North of England Programme	AR 2017	1617-Q2	DFT	Amber/Red	03/11/2011	31/12/2022	£652.00m	£474.50m	-£177.50m	-£0.27m	4826.80	£947.10m	£3879.70m	Infrastructure and Construction	11.17	DFT_0028_1617-Q1,1617-Q2	DFT	Amber/Red	Joiner
DFT_0029_1617-Q1	South West Route Capacity	AR 2017	1617-Q2	DFT	Amber/Red	16/07/2012	31/12/2019	£178.86m	£180.96m	£2.10m	£0.01m	733.90	£132.70m	£601.20m	Infrastructure and Construction	7.46	DFT_0029_1617-Q1,1617-Q2	DFT	Amber/Red	Joiner
DFT_0030_1617-Q2	M20 Lorry Area	AR 2017	1617-Q2	DFT	Red	25/11/2015	20/01/2018	£230.00m	£86.50m	-£143.50m	-£0.62m	250.00	£250.00m	£0.00m	Infrastructure and Construction	2.16	DFT_0030_1617-Q2,1617-Q2	DFT	Red	Joiner
DH_0008_1112-Q1	Electronic Transmission of Prescriptions ETP - Electronic Prescription Service (EPS) Release 2	AR 2017	1617-Q2	DH	Amber	01/01/2003	31/12/2016	£3.46m	£5.58m	£2.12m	£0.61m	77.73	£77.73m	£0.00m	ICT	14.01	DH_0008_1112-Q1,1617-Q2	DH	Amber	Not new
DH_0015_1112-Q1	CSC Local Service Provider (LSP) Delivery Programme	AR 2017	1617-Q2	DH	Amber/Green	23/06/2003	31/12/2017	£100.87m	£74.00m	-£26.87m	-£0.27m	2109.84	£2109.84m	£0.00m	Government Transformation and Service Delivery	14.53	DH_0015_1112-Q1,1617-Q2	DH	Amber/Green	Not new
DH_0017_1112-Q1	PHE Science Hub	AR 2017	1617-Q2	DH	Amber	28/06/2013	31/03/2023	£276.60m	£152.70m	-£123.90m	-£0.45m	10997.76	£10997.76m	£0.00m	Infrastructure and Construction	9.76	DH_0017_1112-Q1,1617-Q2	DH	Amber	Not new
DH_0028_1314-Q1	General Practice System of Choice (GPSoC) Replacement	AR 2017	1617-Q2	DH	Amber	26/01/2012	31/03/2015	£179.47m	£171.32m	-£8.15m	-£0.05m	527.54	£527.54m	£0.00m	ICT	3.18	DH_0028_1314-Q1,1617-Q2	DH	Amber	Not new
DH_0029_1314-Q1	Liaison and Diversion Programme	AR 2017	1617-Q2	DH	Amber	01/04/2011	01/04/2014	£39.80m	£39.80m	£0.00m	£0.00m	389.30	£389.30m	£0.00m	Government Transformation and Service Delivery	3.00	DH_0029_1314-Q1,1617-Q2	DH	Amber	Not new
DH_0030_1314-Q1	National Pandemic Flu Service	AR 2017	1617-Q2	DH	Amber/Green	19/03/2012	30/10/2016	£8.30m	£5.80m	-£2.50m	-£0.30m	26.50	£26.50m	£0.00m	ICT	4.62	DH_0030_1314-Q1,1617-Q2	DH	Amber/Green	Not new
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	AR 2017	1617-Q2	DH	Amber	01/01/2012	30/05/2018	£87.37m	£67.32m	-£20.05m	-£0.23m	1247.25	£1227.25m	£20.00m	Government Transformation and Service Delivery	6.41	DH_0031_1314-Q1,1617-Q2	DH	Amber	Not new
DH_0033_1314-Q1	Childhood Flu Immunisation Programme	AR 2017	1617-Q2	DH	Amber/Green	03/09/2013	01/09/2018	£78.90m	£78.90m	£0.00m	£0.00m	318.81	£318.81m	£0.00m	Government Transformation and Service Delivery	5.00	DH_0033_1314-Q1,1617-Q2	DH	Amber/Green	Not new
DH_0039_1314-Q2	NHS e-Referral Service	AR 2017	1617-Q2	DH	Amber	29/03/2012	31/03/2018	£27.86m	£20.60m	-£7.26m	-£0.26m	131.17	£131.17m	£0.00m	ICT	6.01	DH_0039_1314-Q2,1617-Q2	DH	Amber	Not new
DH_0040_1314-Q2	NHSmail 2	AR 2017	1617-Q2	DH	Amber	29/03/2012	26/02/2021	£17.19m	£25.11m	£7.92m	£0.46m	133.03	£133.03m	£0.00m	ICT	8.92	DH_0040_1314-Q2,1617-Q2	DH	Amber	Not new
DH_0041_1314-Q2	Health & Social Care Network	AR 2017	1617-Q2	DH	Amber/Red	29/03/2012	01/04/2020	£137.26m	£86.57m	-£50.69m	-£0.37m	720.18	£720.18m	£0.00m	ICT	8.01	DH_0041_1314-Q2,1617-Q2	DH	Amber/Red	Not new
DH_0042_1314-Q3	NHS Electronic Staff Record Reprocurement Project	AR 2017	1617-Q2	DH	Amber/Green	10/06/2013	30/11/2015	£44.87m	£51.32m	£6.44m	£0.14m	267.01	£267.01m	£0.00m	ICT	2.47	DH_0042_1314-Q3,1617-Q2	DH	Amber/Green	Not new
DH_0043_1314-Q3	NHS Pension Re-let	AR 2017	1617-Q2	DH	Amber	05/07/2013	21/07/2017	£10.50m	£10.50m	£0.00m	£0.00m	20.40	£20.40m	£0.00m	Government Transformation and Service Delivery	4.05	DH_0043_1314-Q3,1617-Q2	DH	Amber	Not new
DH_0048_1415-Q1	100,000 Genomes Project	AR 2017	1617-Q2	DH	Amber/Red	10/04/2013	31/12/2017	£50.00m	£47.90m	-£2.10m	-£0.04m	350.00	£350.00m	£0.00m	Government Transformation and Service Delivery	4.73	DH_0048_1415-Q1,1617-Q2	DH	Amber/Red	Not new
DH_0056_1415-Q3	Visitor and Migrant NHS Cost Recovery Programme	AR 2017	1617-Q2	DH	Amber/Red	01/09/2013	31/03/2018	£8.78m	£7.27m	-£1.52m	-£0.17m	19.28	£19.28m	£0.00m	Government Transformation and Service Delivery	4.58	DH_0056_1415-Q3,1617-Q2	DH	Amber/Red	Not new
DH_0058_1516-Q4	National Data Services Development Programme	AR 2017	1617-Q2	DH	Amber/Red	23/02/2015	31/03/2020	£30.18m	£30.18m	£0.00m	£0.00m	167.96	£167.96m	£0.00m	ICT	5.10	DH_0058_1516-Q4,1617-Q2	DH	Amber/Red	Joiner
DH_0059_1617-Q1	Procurement Transformation Programme	AR 2017	1617-Q2	DH	Amber	31/03/2015	31/03/2019	£16.80m	£16.80m	£0.00m	£0.00m	140.65	£140.65m	£0.00m	Government Transformation and Service Delivery	4.00	DH_0059_1617-Q1,1617-Q2	DH	Amber	Joiner
DH_0060_1617-Q1	NHS UK	AR 2017	1617-Q2	DH	Amber	01/04/2016	31/12/2020	£2.12m	£8.10m	£5.98m	£2.82m	2.91	£2.91m	£0.00m	Government Transformation and Service Delivery	4.75	DH_0060_1617-Q1,1617-Q2	DH	Amber	Joiner
DWP_0025_1516-Q4	Application Development Maintenance and Support (ADMS)	AR 2017	1617-Q2	DWP	Amber	01/03/2016	31/03/2017	£168.62m	£168.62m	£0.00m	£0.00m	602.86	£602.86m	£0.00m	ICT	1.08	DWP_0025_1516-Q4,1617-Q2	DWP	Amber	Joiner
DWP_0005_1112-Q1	Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme)	AR 2017	1617-Q2	DWP	Amber	01/05/2007	30/11/2018	£101.90m	£67.80m	-£34.10m	-£0.33m	995.40	£995.40m	£0.00m	Government Transformation and Service Delivery	11.59	DWP_0005_1112-Q1,1617-Q2	DWP	Amber	Not new
DWP_0024_1516-Q3	DWP People and Locations Programme	AR 2017	1617-Q2	DWP	Amber/Red	19/11/2015	27/04/2018	£91.29m	£45.93m	-£45.36m	-£0.50m	5560.67	£5560.67m	£0.00m	Government Transformation and Service Delivery	2.44	DWP_0024_1516-Q3,1617-Q2	DWP	Amber/Red	Joiner
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	AR 2017	1617-Q2	DWP	Amber/Green	02/04/2012	31/03/2017	£110.80m	£83.00m	-£27.80m	-£0.25m	821.90	£821.90m	£0.00m	Government Transformation and Service Delivery	5.00	DWP_0016_1213-Q2,1617-Q2	DWP	Amber/Green	Not new
DWP_0026_1516-Q4	Hosting	AR 2017	1617-Q2	DWP	Amber	30/03/2016	08/02/2018	£287.97m	£241.39m	-£46.58m	-£0.16m	1187.67	£1187.67m	£0.00m	ICT	1.86	DWP_0026_1516-Q4,1617-Q2	DWP	Amber	Joiner
DWP_0009_1112-Q1	Universal Credit Programme	AR 2017	1617-Q2	DWP	Amber	17/11/2011	30/06/2022	£534.88m	£496.65m	-£38.23m	-£0.07m	13573.69	£13573.69m	£0.00m	Government Transformation and Service Delivery	10.62	DWP_0009_1112-Q1,1617-Q2	DWP	Amber	Not new
DWP_0027_1617-Q2	Work and Health Programme	AR 2017	1617-Q2	DWP	Amber	01/12/2015	31/03/2018	£14.00m	£3.88m	-£10.12m	-£0.72m	401.00	£401.00m	£0.00m	Government Transformation and Service Delivery	2.33	DWP_0027_1617-Q2,1617-Q2	DWP	Amber	Joiner
FCO_0001_1112-Q1	ABUJA New Office and Residence	AR 2017	1617-Q2	FCO	Amber	01/01/2011	01/12/2017	£13.40m	£13.70m	£0.30m	£0.02m	46.00	£46.00m	£0.00m	Infrastructure and Construction	6.92	FCO_0001_1112-Q1,1617-Q2	FCO	Amber	Not new
FCO_0006_1213-Q2	UKERP	AR 2017	1617-Q2	FCO	Amber	01/06/2011	01/08/2015	£0.00m	£0.50m	£0.50m	£0.00m	65.00	£65.00m	£0.00m	Infrastructure and Construction	4.17	FCO_0006_1213-Q2,1617-Q2	FCO	Amber	Not new
FCO_0008_1415-Q4	Technology Overhaul	AR 2017	1617-Q2	FCO	Amber	01/11/2015	31/03/2018	£38.00m	£29.60m	-£8.40m	-£0.22m	105.40	£105.40m	£0.00m	ICT	2.41	FCO_0008_1415-Q4,1617-Q2	FCO	Amber	Not new
FCO_0009_1516-Q2	Movement of Personal Effects Contract	AR 2017	1617-Q2	FCO	Amber/Green	06/07/2015	31/03/2017	£12.50m	£12.50m	£0.00m	£0.00m	62.50	£62.50m	£0.00m	Government Transformation and Service Delivery	1.74	FCO_0009_1516-Q2,1617-Q2	FCO	Amber/Green	Not new
HMRC_0012_1415-Q1	Tax-Free Childcare	AR 2017	1617-Q2	HMRC	Amber	10/09/2013	30/06/2018	£65.64m	£56.78m	-£8.86m	-£0.14m	356.86	£356.86m	£0.00m	Government Transformation and Service Delivery	4.81	HMRC_0012_1415-Q1,1617-Q2	HMRC	Amber	Not new
HMRC_0013_1415-Q4	Columbus (formerly Aspire Replacement Programme)	AR 2017	1617-Q2	HMRC	Amber/Green	01/01/2014	31/12/2021	£894.00m	£894.00m	£0.00m	£0.00m	6310.00	£6310.00m	£0.00m	ICT	8.00	HMRC_0013_1415-Q4,1617-Q2	HMRC	Amber/Green	Not new
HMRC_0014_1415-Q4	CUSTOMS DECLARATION SERVICES (CDS) Programme	AR 2017	1617-Q2	HMRC	Amber	16/10/2013	31/12/2018	£36.51m	£31.43m	-£5.08m	-£0.14m	117.06	£117.06m	£0.00m	ICT	5.21	HMRC_0014_1415-Q4,1617-Q2	HMRC	Amber	Not new
HMRC_0015_1617-Q1	Building Our Future Locations Programme	AR 2017	1617-Q2	HMRC	Amber/Red	05/01/2016	05/04/2021	£310.20m	£340.70m	£30.50m	£0.10m	2099.30	£2099.30m	£0.00m	Government Transformation and Service Delivery	5.25	HMRC_0015_1617-Q1,1617-Q2	HMRC	Amber/Red	Joiner
HMRC_0016_1617-Q2	Making Tax Digital for Individuals	AR 2017	1617-Q2	HMRC	Amber	01/04/2016	31/03/2021	£51.50m	£51.50m	£0.00m	£0.00m	205.62	£205.62m	£0.00m	Government Transformation and Service Delivery	5.00	HMRC_0016_1617-Q2,1617-Q2	HMRC	Amber	Joiner
HMRC_0017_1617-Q2	Making Tax Digital for Business	AR 2017	1617-Q2	HMRC	Amber/Red	01/04/2016	31/03/2021	£48.00m	£48.00m	£0.00m	£0.00m	227.00	£227.00m	£0.00m	ICT	5.00	HMRC_0017_1617-Q2,1617-Q2	HMRC	Amber/Red	Joiner
HO_0012_1112-Q3	Communications Capabilities Development Programme	AR 2017	1617-Q2	HO	Amber/Green	01/05/2010	01/04/2020	£0.00m	£0.00m	£0.00m	£0.00m	Exempt		£0.00m	ICT	9.93	HO_0012_1112-Q3,1617-Q2	HO	Amber/Green	Not new
HO_0034_1516-Q2	Cyclamen Project	AR 2017	1617-Q2	HO	Amber/Red	01/04/2014	01/04/2021	£0.00m	£0.00m	£0.00m	£0.00m	Exempt	#VALUE!	£0.00m	ICT	7.01	HO_0034_1516-Q2,1617-Q2	HO	Amber/Red	Not new
HO_0011_1112-Q2	Disclosure and Barring Service (DBS) Programme	AR 2017	1617-Q2	HO	Amber/Red	29/12/2010	31/12/2017	£113.50m	£154.30m	£40.80m	£0.36m	785.70	£785.70m	£0.00m	Government Transformation and Service Delivery	7.01	HO_0011_1112-Q2,1617-Q2	HO	Amber/Red	Not new
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2017	1617-Q2	HO	Amber	01/06/2011	31/12/2020	£89.00m	£89.00m	£0.00m	£0.00m	4861.70	£4861.70m	£0.00m	Infrastructure and Construction	9.59	HO_0016_1213-Q1,1617-Q2	HO	Amber	Not new
HO_0029_1314-Q4	Immigration Platform Technologies (IPT)	AR 2017	1617-Q2	HO	Amber	01/04/2013	31/03/2017	£41.10m	£80.50m	£39.40m	£0.96m	208.80	£208.80m	£0.00m	ICT	4.00	HO_0029_1314-Q4,1617-Q2	HO	Amber	Not new
HO_0030_1415-Q1	Adelphi Modernisation Programme	AR 2017	1617-Q2	HO	Reset	01/09/2016	01/06/2019	£18.03m	£18.03m	£0.00m	£0.00m	262.81	£262.81m	£0.00m	ICT	2.75	HO_0030_1415-Q1,1617-Q2	HO	Reset	Not new
HO_0031_1415-Q1	Digital Services at the Border	AR 2017	1617-Q2	HO	Amber/Red	12/02/2014	31/03/2019	£27.00m	£26.20m	-£0.80m	-£0.03m	341.40	£341.40m	£0.00m	ICT	5.13	HO_0031_1415-Q1,1617-Q2	HO	Amber/Red	Not new
HO_0032_1415-Q1	Technology Platforms for Tomorrow	AR 2017	1617-Q2	HO	Amber	01/02/2014	31/10/2017	£47.40m	£47.60m	£0.20m	£0.00m	374.60	£374.60m	£0.00m	ICT	3.75	HO_0032_1415-Q1,1617-Q2	HO	Amber	Not new
HO_0033_1415-Q3	Home Office Biometrics Programme	AR 2017	1617-Q2	HO	Amber/Green	01/04/2014	31/12/2019	£108.30m	£108.30m	£0.00m	£0.00m	584.40	£584.40m	£0.00m	ICT	5.75	HO_0033_1415-Q3,1617-Q2	HO	Amber/Green	Not new
HO_0035_1617-Q1	Smarter Working Programme	AR 2017	1617-Q2	HO	Amber	28/10/2015	31/03/2020	£41.40m	£38.00m	-£3.40m	-£0.08m	128.15	£128.15m	£0.00m	Government Transformation and Service Delivery	4.43	HO_0035_1617-Q1,1617-Q2	HO	Amber	Joiner
HO_0036_1617-Q2	National Law Enforcement Data Programme	AR 2017	1617-Q2	HO	Amber/Red	01/04/2014	31/03/2020	£54.70m	£54.70m	£0.00m	£0.00m	518.30	£518.30m	£0.00m	ICT	6.00	HO_0036_1617-Q2,1617-Q2	HO	Amber/Red	Joiner
MOD_0017_1112-Q1	Crowsnest Programme	AR 2017	1617-Q2	MOD	Amber	31/03/2013	30/06/2023	£53.35m	£53.36m	£0.01m	£0.00m	Exempt		£0.00m	Military Capability	10.25	MOD_0017_1112-Q1,1617-Q2	MOD	Amber	Not new
MOD_0055_1112-Q1	Type 26 Global Combat Ship Programme	AR 2017	1617-Q2	MOD	Exempt	21/07/2008	31/12/2034	£293.23m	£292.99m	-£0.24m	£0.00m	Exempt	#VALUE!	£0.00m	Military Capability	26.46	MOD_0055_1112-Q1,1617-Q2	MOD	Exempt	Not new
MOD_0001_1112-Q1	A400M	AR 2017	1617-Q2	MOD	Amber	17/05/2000	31/03/2022	£274.39m	£292.57m	£18.19m	£0.07m	3614.93	£3614.93m	£0.00m	Military Capability	21.88	MOD_0001_1112-Q1,1617-Q2	MOD	Amber	Not new
MOD_0004_1112-Q1	Airseeker	AR 2017	1617-Q2	MOD	Amber/Green	18/03/2010	01/04/2018	£91.41m	£102.97m	£11.57m	£0.13m	759.84	£759.84m	£0.00m	Military Capability	8.04	MOD_0004_1112-Q1,1617-Q2	MOD	Amber/Green	Not new
MOD_0033_1112-Q1	MARSHALL	AR 2017	1617-Q2	MOD	Amber/Red	03/04/2006	04/10/2020	£124.79m	£124.39m	-£0.40m	£0.00m	1769.16	£1769.16m	£0.00m	Military Capability	14.52	MOD_0033_1112-Q1,1617-Q2	MOD	Amber/Red	Not new
MOD_0036_1112-Q1	Maritime Sustainment Programme	AR 2017	1617-Q2	MOD	Amber/Red	25/07/2005	30/04/2018	£126.84m	£126.84m	£0.00m	£0.00m	596.37	£596.37m	£0.00m	Military Capability	12.77	MOD_0036_1112-Q1,1617-Q2	MOD	Amber/Red	Not new
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2017	1617-Q2	MOD	Exempt	01/04/2008	30/04/2025	£993.19m	£1026.97m	£33.78m	£0.03m	20310.55	£20310.55m	£0.00m	Military Capability	17.09	MOD_0038_1112-Q1,1617-Q2	MOD	Exempt	Not new
MOD_0042_1112-Q1	Queen Elizabeth Programme	AR 2017	1617-Q2	MOD	Amber	01/12/1998	31/03/2023	£601.84m	£593.27m	-£8.56m	-£0.01m	7400.08	£7400.08m	£0.00m	Military Capability	24.35	MOD_0042_1112-Q1,1617-Q2	MOD	Amber	Not new
MOD_0047_1112-Q1	Spearfish Upgrade Programme	AR 2017	1617-Q2	MOD	Amber/Green	01/04/2008	31/03/2024	£39.95m	£40.02m	£0.07m	£0.00m	416.08	£416.08m	£0.00m	Military Capability	16.01	MOD_0047_1112-Q1,1617-Q2	MOD	Amber/Green	Not new
MOD_0095_1415-Q2	Cryptographic Enabling Services	AR 2017	1617-Q2	MOD	Exempt			£0.00m	£0.00m	£0.00m	£0.00m	Exempt	#VALUE!	£0.00m	ICT	0.00	MOD_0095_1415-Q2,1617-Q2	MOD	Exempt	Not new
MOD_0061_1112-Q1	WATCHKEEPER	AR 2017	1617-Q2	MOD	Amber	01/03/1998	03/07/2017	£43.16m	£40.77m	-£2.39m	-£0.06m	1116.75	£1116.75m	£0.00m	Military Capability	19.35	MOD_0061_1112-Q1,1617-Q2	MOD	Amber	Not new
MOD_0062_1112-Q1	Wildcat Programme	AR 2017	1617-Q2	MOD	Amber	01/12/2001	31/05/2016	£13.16m	£12.67m	-£0.49m	-£0.04m	1609.24	£1609.24m	£0.00m	Military Capability	14.51	MOD_0062_1112-Q1,1617-Q2	MOD	Amber	Not new
MOD_0064_1112-Q2	Carrier Enabled Power Projection	AR 2017	1617-Q2	MOD	Amber	31/01/2011	01/12/2030	£1.58m	£1.33m	-£0.25m	-£0.16m	21.80	£21.80m	£0.00m	Military Capability	19.85	MOD_0064_1112-Q2,1617-Q2	MOD	Amber	Not new
MOD_0069_1112-Q2	Logistics Commodities Services Transformation	AR 2017	1617-Q2	MOD	Amber	01/08/2011	01/02/2018	£92.61m	£115.27m	£22.66m	£0.24m	652.42	£652.42m	£0.00m	Military Capability	6.51	MOD_0069_1112-Q2,1617-Q2	MOD	Amber	Not new
MOD_0070_1112-Q2	New Employment Model	AR 2017	1617-Q2	MOD	Amber/Green	02/05/2011	01/10/2021	£95.15m	£92.37m	-£2.78m	-£0.03m	211.08	£211.08m	£0.00m	Government Transformation and Service Delivery	10.42	MOD_0070_1112-Q2,1617-Q2	MOD	Amber/Green	Not new
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2017	1617-Q2	MOD	Amber/Red	17/03/1997	31/03/2024	£574.91m	£529.82m	-£45.09m	-£0.08m	9869.70	£9869.70m	£0.00m	Military Capability	27.06	MOD_0076_1213-Q1,1617-Q2	MOD	Amber/Red	Not new
MOD_0077_1213-Q1	Complex Weapons	AR 2017	1617-Q2	MOD	Amber	31/03/2008	01/04/2032	£729.35m	£719.58m	-£9.78m	-£0.01m	21355.09	£21355.09m	£0.00m	Military Capability	24.02	MOD_0077_1213-Q1,1617-Q2	MOD	Amber	Not new
MOD_0078_1213-Q1	Core Production Capability	AR 2017	1617-Q2	MOD	Red	01/04/2012	15/05/2028	£197.36m	£197.20m	-£0.15m	£0.00m	1700.07	£1700.07m	£0.00m	Military Capability	16.13	MOD_0078_1213-Q1,1617-Q2	MOD	Red	Not new
MOD_0079_1213-Q1	Lightning Programme	AR 2017	1617-Q2	MOD	Amber	01/10/2001	31/03/2035	£808.53m	£888.46m	£79.93m	£0.10m	13383.06	£13383.06m	£0.00m	Military Capability	33.52	MOD_0079_1213-Q1,1617-Q2	MOD	Amber	Not new
MOD_0080_1213-Q1	Successor SSBN	AR 2017	1617-Q2	MOD	Amber/Red	14/04/2011		£844.76m	£859.85m	£15.09m	£0.02m	31614.28	£31614.28m	£0.00m	Military Capability	-111.36	MOD_0080_1213-Q1,1617-Q2	MOD	Amber/Red	Not new
MOD_0085_1314-Q2	Army Basing Programme	AR 2017	1617-Q2	MOD	Amber	22/05/2013	31/03/2020	£306.85m	£294.50m	-£12.35m	-£0.04m	2009.47	£2009.47m	£0.00m	Military Capability	6.86	MOD_0085_1314-Q2,1617-Q2	MOD	Amber	Not new
MOD_0087_1314-Q2	The Materiel Strategy	AR 2017	1617-Q2	MOD	Amber	02/05/2011	01/05/2018	£91.21m	£91.21m	£0.00m	£0.00m	379.07	£379.07m	£0.00m	Military Capability	7.00	MOD_0087_1314-Q2,1617-Q2	MOD	Amber	Not new
MOD_0091_1415-Q3	Armoured Cavalry 2025	AR 2017	1617-Q2	MOD	Amber	04/12/2014	30/04/2025	£317.43m	£309.07m	-£8.36m	-£0.03m	6248.63	£6248.63m	£0.00m	Military Capability	10.41	MOD_0091_1415-Q3,1617-Q2	MOD	Amber	Not new
MOD_0092_1415-Q3	Armoured Infantry 2026	AR 2017	1617-Q2	MOD	Amber/Red	04/12/2014	31/12/2026	£87.84m	£68.09m	-£19.75m	-£0.22m	1612.71	£1612.71m	£0.00m	Military Capability	12.08	MOD_0092_1415-Q3,1617-Q2	MOD	Amber/Red	Not new
MOD_0093_1415-Q3	Army Reserve Development Programme	AR 2017	1617-Q2	MOD	Amber/Green	01/12/2014	01/01/2017	£197.57m	£202.55m	£4.98m	£0.03m	1856.76	£1856.76m	£0.00m	Military Capability	2.09	MOD_0093_1415-Q3,1617-Q2	MOD	Amber/Green	Not new
MOD_0094_1415-Q3	Contracting, Purchasing and Finance	AR 2017	1617-Q2	MOD	Amber/Red	01/12/2011	31/03/2018	£35.88m	£30.94m	-£4.95m	-£0.14m	146.73	£146.73m	£0.00m	Government Transformation and Service Delivery	6.33	MOD_0094_1415-Q3,1617-Q2	MOD	Amber/Red	Not new
MOD_0100_1516-Q1	Future Beyond Line Of Sight	AR 2017	1617-Q2	MOD	Amber	01/01/2011	31/12/2041	£0.00m	£0.00m	£0.00m	£0.00m	Exempt		£0.00m	ICT	31.02	MOD_0100_1516-Q1,1617-Q2	MOD	Amber	Not new
MOD_0101_1516-Q1	New Style of Information Technology (Base)	AR 2017	1617-Q2	MOD	Amber	01/04/2015	05/03/2018	£0.00m	£0.00m	£0.00m	£0.00m	Exempt		£0.00m	ICT	2.93	MOD_0101_1516-Q1,1617-Q2	MOD	Amber	Not new
MOD_0109_1617-Q2	New Style of Information Technology Deployed	AR 2017	1617-Q2	MOD	Exempt			£0.00m	£0.00m	£0.00m	£0.00m	Exempt	#VALUE!	£0.00m	ICT	0.00	MOD_0109_1617-Q2,1617-Q2	MOD	Exempt	Joiner
MOD_0104_1617-Q1	Armour MBT 2025	AR 2017	1617-Q2	MOD	Amber	04/12/2014	01/06/2026	£6.37m	£5.57m	-£0.80m	-£0.13m	744.78	£744.78m	£0.00m	Military Capability	11.50	MoD_0104_1617-Q1,1617-Q2	MOD	Amber	Joiner
MOD_0105_1617-Q1	Land Environment Tactical Communication and Information Systems	AR 2017	1617-Q2	MOD	Amber/Red	01/05/2013	01/12/2035	£168.55m	£169.37m	£0.83m	£0.00m	11148.49	£11148.49m	£0.00m	Military Capability	22.60	MoD_0105_1617-Q1,1617-Q2	MOD	Amber/Red	Joiner
MOD_0106_1617-Q1	Maritime Patrol Aircraft	AR 2017	1617-Q2	MOD	Amber	08/07/2014	01/04/2024	£7.37m	£5.57m	-£1.80m	-£0.24m	2132.49	£2132.49m	£0.00m	Military Capability	9.74	MoD_0106_1617-Q1,1617-Q2	MOD	Amber	Joiner
MOD_0107_1617-Q1	PROTECTOR	AR 2017	1617-Q2	MOD	Amber	30/04/2009	31/05/2023	£13.77m	£15.27m	£1.50m	£0.11m	929.32	£929.32m	£0.00m	Military Capability	14.09	MoD_0107_1617-Q1,1617-Q2	MOD	Amber	Joiner
MOJ_0003_1112-Q1	Electronic Monitoring	AR 2017	1617-Q2	MOJ	Amber/Red	10/05/2011	30/11/2016	£62.50m	£88.30m	£25.80m	£0.41m	380.60	£380.60m	£0.00m	Government Transformation and Service Delivery	5.56	MOJ_0003_1112-Q1,1617-Q2	MOJ	Amber/Red	Not new
MOJ_0004_1112-Q1	Future IT Sourcing Programme (FITS)	AR 2017	1617-Q2	MOJ	Amber/Red	01/03/2011	30/11/2017	£375.00m	£388.13m	£13.13m	£0.04m	2879.25	£2879.25m	£0.00m	ICT	6.76	MOJ_0004_1112-Q1,1617-Q2	MOJ	Amber/Red	Not new
MOJ_0006_1112-Q1	Integrated Delivery Programme	AR 2017	1617-Q2	MOJ	Amber/Green	01/07/2009	30/04/2016	£0.00m	£0.00m	£0.00m	£0.00m	35.31	£35.31m	£0.00m	ICT	6.84	MOJ_0006_1112-Q1,1617-Q2	MOJ	Amber/Green	Not new
MOJ_0008_1112-Q1	Shared Services (ISSC2) Evolve	AR 2017	1617-Q2	MOJ	Amber/Red	07/09/2013	05/11/2015	£76.76m	£75.51m	-£1.25m	-£0.02m	395.15	£395.15m	£0.00m	ICT	2.16	MOJ_0008_1112-Q1,1617-Q2	MOJ	Amber/Red	Not new
MOJ_0015_1112-Q2	NOMS ICTS Services (NIS) Programme (formally part of Quantum Re-compete Project)	AR 2017	1617-Q2	MOJ	Green	18/07/2011	30/06/2016	£13.40m	£12.08m	-£1.32m	-£0.10m	40.80	£40.80m	£0.00m	ICT	4.96	MOJ_0015_1112-Q2,1617-Q2	MOJ	Green	Not new
MOJ_0021_1314-Q1	CJS Common Platform	AR 2017	1617-Q2	MOJ	Amber	01/11/2012	29/03/2019	£92.74m	£73.11m	-£19.63m	-£0.21m	380.89	£380.89m	£0.00m	ICT	6.41	MOJ_0021_1314-Q1,1617-Q2	MOJ	Amber	Not new
MOJ_0023_1314-Q1	Berwyn Programme	AR 2017	1617-Q2	MOJ	Amber	10/01/2013	31/05/2018	£104.40m	£122.00m	£17.60m	£0.17m	2252.70	£2252.70m	£0.00m	Infrastructure and Construction	5.39	MOJ_0023_1314-Q1,1617-Q2	MOJ	Amber	Not new
MOJ_0027_1314-Q2	CJS Efficiency Programme Phase 3	AR 2017	1617-Q2	MOJ	Green	30/04/2013	30/06/2016	£7.33m	£9.07m	£1.74m	£0.24m	84.85	£84.85m	£0.00m	ICT	3.17	MOJ_0027_1314-Q2,1617-Q2	MOJ	Green	Not new
MOJ_0028_1314-Q2	HMCTS Reform	AR 2017	1617-Q2	MOJ	Amber/Red	05/01/2015	31/03/2022	£147.20m	£139.19m	-£8.01m	-£0.05m	1638.48	£1638.48m	£0.00m	Government Transformation and Service Delivery	7.24	MOJ_0028_1314-Q2,1617-Q2	MOJ	Amber/Red	Not new
MOJ_0030_1516-Q1	Secure Training Centre (STC) Retendering	AR 2017	1617-Q2	MOJ	Amber/Red	05/11/2012	01/05/2017	£10.83m	£10.83m	£0.00m	£0.00m	86.98	£86.98m	£0.00m	Government Transformation and Service Delivery	4.49	MOJ_0030_1516-Q1,1617-Q2	MOJ	Amber/Red	Not new
MOJ_0032_1617-Q2	MoJ Future FM	AR 2017	1617-Q2	MOJ	Amber	01/07/2016	01/04/2018	£1.60m	£1.60m	£0.00m	£0.00m	288.80	£288.80m	£0.00m	Government Transformation and Service Delivery	1.75	MOJ_0032_1617-Q2,1617-Q2	MOJ	Amber	Joiner
MOJ_0033_1617-Q2	Prison Estate Transformation Programme (PETP)	AR 2017	1617-Q2	MOJ	Amber	01/04/2016	31/12/2021	£0.00m	£0.00m	£0.00m	£0.00m	0.00	£0.00m	£0.00m	Infrastructure and Construction	5.75	MOJ_0033_1617-Q2,1617-Q2	MOJ	Amber	Joiner
MOJ_0034_1617-Q2	NOMS Digital Transformation Programme	AR 2017	1617-Q2	MOJ	Amber	01/01/2016	31/03/2021	£0.00m	£0.00m	£0.00m	£0.00m	0.00	£0.00m	£0.00m	Government Transformation and Service Delivery	5.25	MOJ_0034_1617-Q2,1617-Q2	MOJ	Amber	Joiner
NCA_0001_1415-Q2	NCA Transformation Programme	AR 2017	1617-Q2	NCA	Amber	01/04/2014	31/03/2019	£25.50m	£25.50m	£0.00m	£0.00m	306.80	£306.80m	£0.00m	Government Transformation and Service Delivery	5.00	NCA_0001_1415-Q2,1617-Q2	NCA	Amber	Not new
NCA_0002_1617-Q2	IT Transformation Programme	AR 2017	1617-Q2	NCA	Amber	01/04/2016	31/07/2022	£14.00m	£14.00m	£0.00m	£0.00m	168.68	£168.68m	£0.00m	ICT	6.33	NCA_0002_1617-Q2,1617-Q2	NCA	Amber	Joiner
ONS_0002_1112-Q1	Census Transformation Programme	AR 2017	1617-Q2	ONS	Amber	01/01/2015	31/03/2025	£36.03m	£36.03m	£0.00m	£0.00m	905.76	£905.76m	£0.00m	Government Transformation and Service Delivery	10.25	ONS_0002_1112-Q1,1617-Q2	ONS	Amber	Not new
BEIS_0001_1617-Q2	Heat Networks Investment Project	AR 2018	1718-Q2	BEIS	Exempt	25/11/2015	31/03/2021	£33.67m	£21.60m	-£12.07m	-36%	365.98			Infrastructure and Construction	0.00	BEIS_0001_1617-Q2,1718 - Q2		Exempt	Not new
BEIS_0002_1718-Q1	UKRI Implementation Programme	AR 2018	1718-Q2	BEIS	Amber	01/01/2016	01/10/2018	£9.40m	£9.40m	£0.00m	0%	9.40			Government Transformation and Service Delivery	0.00	BEIS_0002_1718-Q1,1718 - Q2		Amber	Joiner
BIS_0014_1415-Q3	New Polar Research Vessel	AR 2018	1718-Q2	BEIS	Amber/Green	01/05/2014	31/12/2022	£113.00m	£111.00m	-£2.00m	-2%	1403.00			Infrastructure and Construction	8.67	BIS_0014_1415-Q3,1718 - Q2		Amber/Green	Not new
BIS_0015_1516-Q1	Local Land Charges (LLC) Programme	AR 2018	1718-Q2	BEIS	Amber	01/03/2014	17/11/2023	£25.80m	£13.60m	-£12.20m	-47%	193.30			ICT	0.00	BIS_0015_1516-Q1,1718 - Q2		Amber	Not new
CO_0011_1415-Q4	ISSC2	AR 2018	1718-Q2	CO	Amber	28/12/2012	28/03/2021	£380.30m	£323.00m	-£57.30m	-15%	2728.50			Government Transformation and Service Delivery	8.25	CO_0011_1415-Q4,1718 - Q2		Amber	Not new
CO_0012_1415-Q4	Commercial Capability Programme	AR 2018	1718-Q2	CO	Amber	01/01/2015	31/03/2018	£9.20m	£9.20m	£0.00m	0%	20.60			Government Transformation and Service Delivery	0.00	CO_0012_1415-Q4,1718 - Q2		Amber	Not new
CO_0013_1516-Q2	Foxhound Programme	AR 2018	1718-Q2	CO	Amber/Green	01/09/2013	31/12/2018	£27.60m	£33.05m	£5.45m	20%	174.30			ICT	0.00	CO_0013_1516-Q2,1718 - Q2		Amber/Green	Not new
CO_0014_1516-Q2	Government Hubs Programme	AR 2018	1718-Q2	CO	Amber	01/05/2015	31/03/2025	£86.50m	£86.50m	£0.00m	0%	638.87			Government Transformation and Service Delivery	0.00	CO_0014_1516-Q2,1718 - Q2		Amber	Not new
CO_0015_1516-Q2	Gov UK Verify	AR 2018	1718-Q2	CO	Amber	01/04/2012	31/03/2020	Exempt	Exempt	-	-	Exempt			ICT	8.00	CO_0015_1516-Q2,1718 - Q2		Exempt	Not new
CO_0016_1516-Q4	1617 New Property Model Programme	AR 2018	1718-Q2	CO	Amber/Red	01/04/2015	01/04/2021	£11.10m	£11.10m	£0.00m	0%	93.93			Government Transformation and Service Delivery	0.00	CO_0016_1516-Q4,1718 - Q2		Amber/Red	Not new
CO_0018_1617-Q3	Common Technology Services	AR 2018	1718-Q2	CO	Amber	01/04/2016	31/03/2020	£12.20m	£11.70m	-£0.50m	-4%	52.60			Government Transformation and Service Delivery	0.00	CO_0018_1617-Q3,1718 - Q2		Amber	Joiner
CO_0019_1617-Q4	Government as a Platform	AR 2018	1718-Q2	CO	Amber	31/12/2015	31/03/2021	£23.00m	£22.00m	-£1.00m	-4%	90.00			ICT	0.00	CO_0019_1617-Q4,1718 - Q2		Amber	Joiner
DCMS_0001_1112-Q1	Broadband Delivery Programme	AR 2018	1718-Q2	DCMS	Amber/Green	06/12/2010	31/12/2020	£236.10m	£187.60m	-£48.50m	-21%	2439.21			Infrastructure and Construction	10.08	DCMS_0001_1112-Q1,1718 - Q2		Amber/Green	Not new
DCMS_0008_1516-Q4	Blythe House Programme	AR 2018	1718-Q2	DCMS	Amber	25/11/2015	31/03/2023	£62.60m	£68.41m	£5.81m	9%	338.00			Infrastructure and Construction	0.00	DCMS_0008_1516-Q4,1718 - Q2		Amber	Not new
DCMS_0009_1516-Q4	700 MHz Clearance Programme	AR 2018	1718-Q2	DCMS	Amber/Green	13/01/2016	01/01/2022	£103.70m	£91.70m	-£12.00m	-12%	594.92			Infrastructure and Construction	0.00	DCMS_0009_1516-Q4,1718 - Q2		Amber/Green	Not new
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2018	1718-Q2	BEIS	Amber/Red	30/06/2008	31/12/2040	£32.24m	£32.25m	£0.01m	0%	12131.50			Infrastructure and Construction	32.53	DECC_0005_1112-Q1,1718 - Q2		Amber/Red	Not new
DECC_0010_1112-Q1	Smart Metering Implementation Programme	AR 2018	1718-Q2	BEIS	Amber	02/12/2009	31/12/2020	£736.51m	£737.76m	£1.25m	0%	17215.78			Infrastructure and Construction	11.09	DECC_0010_1112-Q1,1718 - Q2		Amber	Not new
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	AR 2018	1718-Q2	BEIS	Amber	03/04/2012	31/08/2015	£572.00m	£555.00m	-£17.00m	-3%	3081.00			Infrastructure and Construction	3.41	DECC_0013_1213-Q1,1718 - Q2		Amber	Not new
DECC_0017_1516-Q1	Sellafield Model Change (SMC)	AR 2018	1718-Q2	BEIS	Amber/Green	13/01/2015	24/05/2017	£2341.70m	£2260.70m	-£81.00m	-3%	30011.20			Government Transformation and Service Delivery	2.36	DECC_0017_1516-Q1,1718 - Q2		Amber/Green	Not new
DEFRA_0006_1516-Q1	DEFRA UNITY PROGRAMME	AR 2018	1718-Q2	DEFRA	Amber	01/11/2014	31/10/2018	£197.60m	£162.60m	-£35.00m	-18%	1048.40			ICT	4.00	DEFRA_0006_1516-Q1,1718 - Q2		Amber	Not new
DFE_0004_1415-Q2	Priority School Building Programme 1	AR 2018	1718-Q2	DfE	Amber/Green	19/07/2011	19/09/2021	£381.85m	£319.29m	-£62.56m	-16%	2313.79			Infrastructure and Construction	10.18	DFE_0004_1415-Q2,1718 - Q2		Amber/Green	Joiner
DFE_0005_1415-Q2	PSBP Private Finance	AR 2018	1718-Q2	DfE	Green	19/07/2011	01/07/2043	£186.50m	£190.10m	£3.60m	2%	2652.00			Infrastructure and Construction	31.97	DFE_0005_1415-Q2,1718 - Q2		Green	Not new
DFE_0006_1415-Q3	Priority School Building Programme 2	AR 2018	1718-Q2	DfE	Amber/Red	01/05/2014	31/12/2022	£402.25m	£100.91m	-£301.34m	-75%	2089.31			Infrastructure and Construction	8.67	DFE_0006_1415-Q3,1718 - Q2		Amber/Red	Joiner
DFE_0007_1617-Q1	30 Hrs Free Childcare Project	AR 2018	1718-Q2	DfE	Amber	11/05/2015	30/09/2018	£409.10m	£436.90m	£27.80m	7%	1920.72			Government Transformation and Service Delivery	3.39	DFE_0007_1617-Q1,1718 - Q2		Amber	Not new
DfE_0009_1617-Q2	Apprenticeships Reform Programme	AR 2018	1718-Q2	DfE	Amber	08/05/2015	01/04/2021	£2036.10m	£1684.10m	-£352.00m	-17%	11347.50			Government Transformation and Service Delivery	5.90	DfE_0009_1617-Q2,1718 - Q2		Amber	Not new
DFID_0001_1112-Q1	St Helena Airport	AR 2018	1718-Q2	DFID	Amber/Green	15/03/2005	31/08/2026	£6.00m	£6.50m	£0.50m	8%	445.12			Infrastructure and Construction	0.00	DFID_0001_1112-Q1,1718 - Q2		Amber/Green	Not new
DFT_0001_1112-Q1	Crossrail Programme	AR 2018	1718-Q2	DfT	Amber	22/07/2008	31/12/2019	£972.02m	£1857.10m	£885.08m	91%	14768.87			Infrastructure and Construction	11.45	DFT_0001_1112-Q1,1718 - Q2		Amber	Not new
DFT_0004_1112-Q1	High Speed Rail Programme (HS2)	AR 2018	1718-Q2	DfT	Amber/Red	28/02/2011	31/12/2033	£1845.80m	£1845.80m	£0.00m	0%	55700.00			Infrastructure and Construction	22.85	DFT_0004_1112-Q1,1718 - Q2		Amber/Red	Not new
DFT_0005_1112-Q1	Intercity Express Programme	AR 2018	1718-Q2	DfT	Red	01/06/2005	06/02/2020	£224.90m	£242.80m	£17.90m	8%	6679.25			Infrastructure and Construction	14.69	DFT_0005_1112-Q1,1718 - Q2		Red	Not new
DFT_0014_1112-Q1	Search and Rescue Helicopters	AR 2018	1718-Q2	DfT	Green	08/02/2011	08/09/2017	£224.30m	£204.40m	-£19.90m	-9%	2157.40			Infrastructure and Construction	6.59	DFT_0014_1112-Q1,1718 - Q2		Green	Not new
DFT_0016_1112-Q1	Thameslink	AR 2018	1718-Q2	DfT	Amber	01/07/2005	31/12/2026	£22.00m	£22.00m	£0.00m	0%	7210.00			Infrastructure and Construction	21.52	DFT_0016_1112-Q1,1718 - Q2		Amber	Not new
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	AR 2018	1718-Q2	DfT	Amber	01/09/2012	30/09/2021	£414.90m	£363.90m	-£51.00m	-12%	1423.80			Infrastructure and Construction	9.08	DFT_0020_1314-Q2,1718 - Q2		Amber	Not new
DFT_0021_1314-Q3	Rail Franchising Programme	AR 2018	1718-Q2	DfT	Amber/Red	26/03/2013	01/12/2019	£8.70m	£8.70m	£0.00m	0%	35.30			Government Transformation and Service Delivery	6.69	DFT_0021_1314-Q3,1718 - Q2		Amber/Red	Not new
DfT_0022_1415-Q4	Lower Thames Crossing Feasibility	AR 2018	1718-Q2	DfT	Amber/Red	30/05/2014	31/07/2028	£49.90m	£49.90m	£0.00m	0%	4648.80			Infrastructure and Construction	14.18	DfT_0022_1415-Q4,1718 - Q2		Amber/Red	Not new
DfT_0023_1516-Q3	Airport Capacity Programme	AR 2018	1718-Q2	DfT	Amber	01/07/2015	31/12/2029	£14.70m	£8.80m	-£5.90m	-40%	22747.00			Infrastructure and Construction	14.51	DfT_0023_1516-Q3,1718 - Q2		Amber	Not new
DFT_0024_1516-Q4	A303 Amesbury to Berwick Down	AR 2018	1718-Q2	DfT	Amber	01/12/2014	01/06/2026	£15.60m	£15.60m	£0.00m	0%	1901.90			Infrastructure and Construction	11.51	DFT_0024_1516-Q4,1718 - Q2		Amber	Not new
DFT_0025_1617-Q1	East West Rail	AR 2018	1718-Q2	DfT	Amber/Red	31/10/2012	31/03/2024	£14.90m	£58.60m	£43.70m	293%	1465.80			Infrastructure and Construction	11.42	DFT_0025_1617-Q1,1718 - Q2		Amber/Red	Not new
DFT_0026_1617-Q1	Great Western Route Modernisation (GWRM) including electrification	AR 2018	1718-Q2	DfT	Amber/Red	01/12/2011	31/12/2024	£876.90m	£789.90m	-£87.00m	-10%	5507.00			Infrastructure and Construction	13.09	DFT_0026_1617-Q1,1718 - Q2		Amber/Red	Not new
DFT_0027_1617-Q1	Midland Main Line Programme	AR 2018	1718-Q2	DfT	Amber	01/01/2011	31/12/2024	£271.60m	£270.70m	-£0.90m	0%	1521.60			Infrastructure and Construction	14.01	DFT_0027_1617-Q1,1718 - Q2		Amber	Not new
DFT_0028_1617-Q1	North of England Programme	AR 2018	1718-Q2	DfT	Amber/Red	23/07/2009	31/12/2022	£494.30m	£629.90m	£135.60m	27%	5114.90			Infrastructure and Construction	13.45	DFT_0028_1617-Q1,1718 - Q2		Amber/Red	Not new
DFT_0029_1617-Q1	South West Route Capacity	AR 2018	1718-Q2	DfT	Amber/Red	16/07/2012	31/12/2019	£193.72m	£226.32m	£32.60m	17%	734.70			Infrastructure and Construction	7.46	DFT_0029_1617-Q1,1718 - Q2		Amber/Red	Not new
DFT_0030_1617-Q2	M20 Lorry Area	AR 2018	1718-Q2	DfT	Red	25/11/2015	20/01/2018	£153.70m	£5.60m	-£148.10m	-96%	246.50			Infrastructure and Construction	2.16	DFT_0030_1617-Q2,1718 - Q2		Red	Not new
DH_0015_1112-Q1	CSC Local Service Provider (LSP) Delivery Programme	AR 2018	1718-Q2	DH	Amber/Green	23/06/2003	31/03/2018	£69.44m	£78.63m	£9.19m	13%	2109.85			Government Transformation and Service Delivery	14.78	DH_0015_1112-Q1,1718 - Q2		Amber/Green	Not new
DH_0017_1112-Q1	PHE Science Hub	AR 2018	1718-Q2	DH	Amber	28/06/2013	30/06/2025	£157.51m	£185.69m	£28.17m	18%	11621.88			Infrastructure and Construction	12.01	DH_0017_1112-Q1,1718 - Q2		Amber	Not new
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	AR 2018	1718-Q2	DH	Amber/Red	01/01/2012	30/05/2018	£66.64m	£62.80m	-£3.84m	-6%	1247.24			Government Transformation and Service Delivery	6.41	DH_0031_1314-Q1,1718 - Q2		Amber/Red	Not new
DH_0039_1314-Q2	NHS e-Referral Service	AR 2018	1718-Q2	DH	Amber/Red	29/03/2012	31/03/2018	£28.47m	£22.62m	-£5.85m	-21%	131.17			ICT	6.01	DH_0039_1314-Q2,1718 - Q2		Amber/Red	Not new
DH_0040_1314-Q2	NHSmail 2	AR 2018	1718-Q2	DH	Amber/Green	29/03/2012	26/02/2021	£18.39m	£23.80m	£5.41m	29%	133.05			ICT	8.92	DH_0040_1314-Q2,1718 - Q2		Amber/Green	Not new
DH_0041_1314-Q2	Health & Social Care Network	AR 2018	1718-Q2	DH	Amber	29/03/2012	31/03/2021	£155.05m	£96.12m	-£58.93m	-38%	699.46			ICT	9.01	DH_0041_1314-Q2,1718 - Q2		Amber	Not new
DH_0043_1314-Q3	NHS Pension Re-let	AR 2018	1718-Q2	DH	Amber	05/07/2013	21/07/2017	£36.40m	£36.40m	£0.00m	0%	274.24			Government Transformation and Service Delivery	4.05	DH_0043_1314-Q3,1718 - Q2		Amber	Not new
DH_0046_1415-Q1	Medical Examiners Programme	AR 2018	1718-Q2	DH	Amber/Red	24/07/2007	30/09/2020	£0.78m	£0.80m	£0.02m	3%	43.06			Government Transformation and Service Delivery	13.20	DH_0046_1415-Q1,1718 - Q2		Amber/Red	Not new
DH_0048_1415-Q1	100000 Genomes Project	AR 2018	1718-Q2	DH	Amber	10/04/2013	31/12/2018	£77.80m	£77.80m	£0.00m	0%	392.90			Government Transformation and Service Delivery	5.73	DH_0048_1415-Q1,1718 - Q2		Amber	Not new
DH_0056_1415-Q3	Visitor and Migrant NHS Cost Recovery Programme	AR 2018	1718-Q2	DH	Amber/Red	01/09/2013	31/03/2019	£6.23m	£6.18m	-£0.05m	-1%	25.53			Government Transformation and Service Delivery	5.58	DH_0056_1415-Q3,1718 - Q2		Amber/Red	Not new
DH_0058_1516-Q4	National Data Services Development Programme	AR 2018	1718-Q2	DH	Amber/Green	23/02/2015	31/03/2020	£19.62m	£10.60m	-£9.02m	-46%	79.39			ICT	5.10	DH_0058_1516-Q4,1718 - Q2		Amber/Green	Not new
DH_0059_1617-Q1	Procurement Transformation Programme	AR 2018	1718-Q2	DH	Amber	31/03/2015	31/03/2019	£29.76m	£26.34m	-£3.42m	-11%	134.15			Government Transformation and Service Delivery	4.00	DH_0059_1617-Q1,1718 - Q2		Amber	Not new
DH_0060_1617-Q1	NHS UK	AR 2018	1718-Q2	DH	Amber	01/04/2016	31/12/2020	£12.00m	£12.00m	£0.00m	0%	79.80			Government Transformation and Service Delivery	4.75	DH_0060_1617-Q1,1718 - Q2		Amber	Not new
DH_0061_1617-Q3	IT Infrastructure Sourcing Programme	AR 2018	1718-Q2	DH	Amber/Red	01/12/2013	30/06/2019	£20.80m	£15.90m	-£4.90m	-24%	126.71			ICT	5.58	DH_0061_1617-Q3,1718 - Q2		Amber/Red	Joiner
DWP_0005_1112-Q1	Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme)	AR 2018	1718-Q2	DWP	Amber/Green	01/05/2007	30/11/2019	£103.08m	£70.98m	-£32.10m	-31%	1249.00			Government Transformation and Service Delivery	12.59	DWP_0005_1112-Q1,1718 - Q2		Amber/Green	Not new
DWP_0009_1112-Q1	Universal Credit Programme	AR 2018	1718-Q2	DWP	Amber	17/11/2011	30/06/2022	£853.42m	£683.08m	-£170.34m	-20%	13573.72			Government Transformation and Service Delivery	10.62	DWP_0009_1112-Q1,1718 - Q2		Amber	Not new
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	AR 2018	1718-Q2	DWP	Amber	02/04/2012	31/03/2021	£87.00m	£89.79m	£2.79m	3%	786.50			Government Transformation and Service Delivery	9.00	DWP_0016_1213-Q2,1718 - Q2		Amber	Not new
DWP_0024_1516-Q3	DWP People and Locations Programme	AR 2018	1718-Q2	DWP	Amber/Red	19/11/2015	27/04/2018	£329.80m	£230.90m	-£98.90m	-30%	5903.78			Government Transformation and Service Delivery	2.44	DWP_0024_1516-Q3,1718 - Q2		Amber/Red	Not new
DWP_0027_1617-Q2	Work and Health Programme	AR 2018	1718-Q2	DWP	Amber	01/12/2015	31/03/2018	£26.22m	£26.22m	£0.00m	0%	532.70			Government Transformation and Service Delivery	2.33	DWP_0027_1617-Q2,1718 - Q2		Amber	Not new
FCO_0008_1415-Q4	Technology Overhaul	AR 2018	1718-Q2	FCO	Amber/Green	01/11/2015	31/12/2018	£51.70m	£58.00m	£6.30m	12%	120.00			ICT	3.17	FCO_0008_1415-Q4,1718 - Q2		Amber/Green	Not new
FCO_0010_1617-Q3	Echo 2 Programme	AR 2018	1718-Q2	FCO	Amber/Red	01/09/2015	31/03/2020	£2.33m	£2.40m	£0.07m	3%	171.40			ICT	4.58	FCO_0010_1617-Q3,1718 - Q2		Amber/Red	Joiner
HMRC_0012_1415-Q1	Tax-Free Childcare	AR 2018	1718-Q2	HMRC	Amber/Red	10/09/2013	30/09/2018	£78.29m	£68.66m	-£9.64m	-12%	356.86			Government Transformation and Service Delivery	5.06	HMRC_0012_1415-Q1,1718 - Q2		Amber/Red	Not new
HMRC_0013_1415-Q4	Columbus (formerly Aspire Replacement Programme)	AR 2018	1718-Q2	HMRC	Amber/Green	01/01/2014	31/12/2021	£266.00m	£70.30m	-£195.70m	-74%	694.00			ICT	8.00	HMRC_0013_1415-Q4,1718 - Q2		Amber/Green	Not new
HMRC_0014_1415-Q4	CUSTOMS DECLARATION SERVICES (CDS) Programme	AR 2018	1718-Q2	HMRC	Amber	16/10/2013	31/12/2018	£35.70m	£36.42m	£0.72m	2%	133.22			ICT	5.21	HMRC_0014_1415-Q4,1718 - Q2		Amber	Not new
HMRC_0015_1617-Q1	Building Our Future Locations Programme	AR 2018	1718-Q2	HMRC	Amber	05/01/2016	31/03/2026	£310.80m	£316.50m	£5.70m	2%	2835.80			Government Transformation and Service Delivery	10.24	HMRC_0015_1617-Q1,1718 - Q2		Amber	Not new
HMRC_0016_1617-Q2	Making Tax Digital for Individuals	AR 2018	1718-Q2	HMRC	Amber	01/04/2016	31/03/2021	£62.30m	£41.60m	-£20.70m	-33%	205.62			Government Transformation and Service Delivery	5.00	HMRC_0016_1617-Q2,1718 - Q2		Amber	Not new
HMRC_0017_1617-Q2	Making Tax Digital for Business	AR 2018	1718-Q2	HMRC	Amber	01/04/2016	31/03/2021	£76.83m	£49.70m	-£27.13m	-35%	234.46			ICT	5.00	HMRC_0017_1617-Q2,1718 - Q2		Amber	Not new
HMRC_0018_1617-Q3	Compliance For The Future Programme	AR 2018	1718-Q2	HMRC	Amber	01/04/2016	31/03/2021	£22.70m	£22.30m	-£0.40m	-2%	188.25			Government Transformation and Service Delivery	5.00	HMRC_0018_1617-Q3,1718 - Q2		Amber	Joiner
HO_0011_1112-Q2	Disclosure and Barring Service (DBS) Programme	AR 2018	1718-Q2	HO	Amber/Red	29/12/2010	31/03/2018	£113.50m	£156.80m	£43.30m	38%	785.70			Government Transformation and Service Delivery	7.26	HO_0011_1112-Q2,1718 - Q2		Amber/Red	Not new
HO_0012_1112-Q3	Communications Capabilities Development Programme	AR 2018	1718-Q2	HO	Amber/Green	01/05/2010	01/04/2020	Exempt	Exempt	-	-	Exempt			ICT	9.93	HO_0012_1112-Q3,1718 - Q2		Exempt	Not new
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2018	1718-Q2	HO	Red	01/06/2011	31/12/2020	£712.47m	£712.47m	£0.00m	0%	5058.63			Infrastructure and Construction	9.59	HO_0016_1213-Q1,1718 - Q2		Red	Not new
HO_0029_1314-Q4	Immigration Platform Technologies (IPT)	AR 2018	1718-Q2	HO	Amber	01/04/2013	31/03/2019	£43.80m	£43.80m	£0.00m	0%	252.50			ICT	6.00	HO_0029_1314-Q4,1718 - Q2		Amber	Not new
HO_0030_1415-Q1	Metis Programme	AR 2018	1718-Q2	HO	Amber	01/09/2016	01/06/2019	£49.80m	£49.80m	£0.00m	0%	290.56			ICT	2.75	HO_0030_1415-Q1,1718 - Q2		Amber	Not new
HO_0031_1415-Q1	Digital Services at the Border	AR 2018	1718-Q2	HO	Amber/Red	12/02/2014	31/03/2019	£44.00m	£44.00m	£0.00m	0%	340.90			ICT	5.13	HO_0031_1415-Q1,1718 - Q2		Amber/Red	Not new
HO_0032_1415-Q1	Technology Platforms for Tomorrow	AR 2018	1718-Q2	HO	Amber	01/02/2014	31/10/2017	£55.40m	£96.50m	£41.10m	74%	374.60			ICT	3.75	HO_0032_1415-Q1,1718 - Q2		Amber	Not new
HO_0033_1415-Q3	Home Office Biometrics Programme	AR 2018	1718-Q2	HO	Amber/Green	01/04/2014	31/03/2020	£90.90m	£90.90m	£0.00m	0%	667.40			ICT	6.00	HO_0033_1415-Q3,1718 - Q2		Amber/Green	Not new
HO_0034_1516-Q2	Cyclamen Project	AR 2018	1718-Q2	HO	Amber	01/04/2014	01/04/2021	Exempt	Exempt	-	-	Exempt			Government Transformation and Service Delivery	7.01	HO_0034_1516-Q2,1718 - Q2		Exempt	Not new
HO_0035_1617-Q1	Smarter Working Programme	AR 2018	1718-Q2	HO	Amber	28/10/2015	31/03/2020	£43.10m	£45.40m	£2.30m	5%	144.50			Government Transformation and Service Delivery	4.43	HO_0035_1617-Q1,1718 - Q2		Amber	Not new
HO_0036_1617-Q2	National Law Enforcement Data Programme	AR 2018	1718-Q2	HO	Amber	01/04/2014	31/03/2020	£60.80m	£73.00m	£12.20m	20%	469.40			ICT	6.00	HO_0036_1617-Q2,1718 - Q2		Amber	Not new
HO_0037_1718-Q1	Asylum Accommodation and Support Transformation (AAST)	AR 2018	1718-Q2	HO	Amber	29/08/2016	02/09/2019	£2.93m	£2.54m	-£0.39m	-13%	7.51			Government Transformation and Service Delivery	3.01	HO_0037_1718-Q1,1718 - Q2		Amber	Joiner
MOD_0001_1112-Q1	A400M	AR 2018	1718-Q2	MOD	Amber	17/05/2000	31/03/2023	£173.39m	£123.76m	-£49.63m	-29%	3519.16			Military Capability	22.88	MOD_0001_1112-Q1,1718 - Q2		Amber	Not new
MOD_0017_1112-Q1	Crowsnest Programme	AR 2018	1718-Q2	MOD	Amber	31/03/2013	30/06/2023	£65.83m	£65.05m	-£0.78m	-1%	Exempt			Military Capability	10.25	MOD_0017_1112-Q1,1718 - Q2		Exempt	Not new
MOD_0033_1112-Q1	MARSHALL	AR 2018	1718-Q2	MOD	Red	03/04/2006	04/10/2020	£114.04m	£102.52m	-£11.52m	-10%	1854.82			Military Capability	14.52	MOD_0033_1112-Q1,1718 - Q2		Red	Not new
MOD_0036_1112-Q1	Maritime Sustainment Programme	AR 2018	1718-Q2	MOD	Amber/Green	25/07/2005	28/02/2019	£46.82m	£68.19m	£21.37m	46%	596.38			Military Capability	13.61	MOD_0036_1112-Q1,1718 - Q2		Amber/Green	Not new
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2018	1718-Q2	MOD	Exempt	01/04/2008	30/04/2025	£1013.69m	£1024.53m	£10.84m	1%	19894.38			Military Capability	17.09	MOD_0038_1112-Q1,1718 - Q2		Exempt	Not new
MOD_0042_1112-Q1	Queen Elizabeth Programme	AR 2018	1718-Q2	MOD	Amber	01/12/1998	31/03/2023	£401.08m	£402.83m	£1.75m	0%	6705.64			Military Capability	24.35	MOD_0042_1112-Q1,1718 - Q2		Amber	Not new
MOD_0047_1112-Q1	Spearfish Upgrade Programme	AR 2018	1718-Q2	MOD	Amber/Red	01/04/2008	31/03/2024	£41.05m	£39.45m	-£1.60m	-4%	416.61			Military Capability	16.01	MOD_0047_1112-Q1,1718 - Q2		Amber/Red	Not new
MOD_0055_1112-Q1	Type 26 Global Combat Ship Programme	AR 2018	1718-Q2	MOD	Amber/Green	21/07/2008	01/05/2035	£392.94m	£382.04m	-£10.90m	-3%	Exempt			Military Capability	26.79	MOD_0055_1112-Q1,1718 - Q2		Exempt	Not new
MOD_0061_1112-Q1	WATCHKEEPER	AR 2018	1718-Q2	MOD	Amber	01/03/1998	03/07/2017	£0.98m	£2.01m	£1.03m	105%	1117.73			Military Capability	19.35	MOD_0061_1112-Q1,1718 - Q2		Amber	Not new
MOD_0062_1112-Q1	Wildcat Programme	AR 2018	1718-Q2	MOD	Amber/Green	01/12/2001	31/05/2016	£6.22m	£9.16m	£2.94m	47%	1607.27			Military Capability	14.51	MOD_0062_1112-Q1,1718 - Q2		Amber/Green	Not new
MOD_0064_1112-Q2	Carrier Enabled Power Projection	AR 2018	1718-Q2	MOD	Amber	31/01/2011	01/12/2030	£1.77m	£1.75m	-£0.02m	-1%	21.58			Military Capability	19.85	MOD_0064_1112-Q2,1718 - Q2		Amber	Not new
MOD_0069_1112-Q2	Logistics Commodities Services Transformation	AR 2018	1718-Q2	MOD	Amber/Green	01/08/2011	01/02/2018	£62.28m	£61.06m	-£1.22m	-2%	640.44			Military Capability	6.51	MOD_0069_1112-Q2,1718 - Q2		Amber/Green	Not new
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2018	1718-Q2	MOD	Red	17/03/1997	31/03/2024	£541.08m	£562.62m	£21.54m	4%	9941.96			Military Capability	27.06	MOD_0076_1213-Q1,1718 - Q2		Red	Not new
MOD_0077_1213-Q1	Complex Weapons	AR 2018	1718-Q2	MOD	Amber	31/03/2008	01/04/2032	£736.16m	£704.43m	-£31.73m	-4%	22179.52			Military Capability	24.02	MOD_0077_1213-Q1,1718 - Q2		Amber	Not new
MOD_0078_1213-Q1	Core Production Capability	AR 2018	1718-Q2	MOD	Red	01/04/2012	30/04/2028	£182.96m	£187.13m	£4.17m	2%	1585.10			Military Capability	16.09	MOD_0078_1213-Q1,1718 - Q2		Red	Not new
MOD_0079_1213-Q1	Lightning Programme	AR 2018	1718-Q2	MOD	Amber/Red	01/10/2001	31/03/2035	£935.45m	£903.35m	-£32.10m	-3%	10109.38			Military Capability	33.52	MOD_0079_1213-Q1,1718 - Q2		Amber/Red	Not new
MOD_0080_1213-Q1	DREADNOUGHT	AR 2018	1718-Q2	MOD	Amber/Red	14/04/2011	Exempt	£1004.66m	£1249.39m	£244.73m	24%	31497.93			Military Capability	0.00	MOD_0080_1213-Q1,1718 - Q2		Exempt	Not new
MOD_0085_1314-Q2	Army Basing Programme	AR 2018	1718-Q2	MOD	Amber/Red	22/05/2013	28/11/2022	£417.34m	£431.07m	£13.73m	3%	2001.57			Military Capability	9.53	MOD_0085_1314-Q2,1718 - Q2		Amber/Red	Not new
MOD_0087_1314-Q2	The Materiel Strategy	AR 2018	1718-Q2	MOD	Amber/Green	02/05/2011	16/05/2018	£79.41m	£78.95m	-£0.46m	-1%	379.06			Government Transformation and Service Delivery	7.04	MOD_0087_1314-Q2,1718 - Q2		Amber/Green	Not new
MOD_0091_1415-Q3	Armoured Cavalry 2025	AR 2018	1718-Q2	MOD	Amber	22/01/2014	30/04/2025	£512.00m	£491.41m	-£20.59m	-4%	6258.19			Military Capability	11.28	MOD_0091_1415-Q3,1718 - Q2		Amber	Not new
MOD_0092_1415-Q3	Armoured Infantry 2026	AR 2018	1718-Q2	MOD	Red	04/12/2014	31/12/2026	£80.95m	£64.80m	-£16.15m	-20%	Exempt			Military Capability	12.08	MOD_0092_1415-Q3,1718 - Q2		Red	Not new
MOD_0094_1415-Q3	Contracting, Purchasing and Finance	AR 2018	1718-Q2	MOD	Amber/Red	01/12/2011	31/03/2018	£13.50m	£11.20m	-£2.30m	-17%	146.74			Government Transformation and Service Delivery	6.33	MOD_0094_1415-Q3,1718 - Q2		Amber/Red	Not new
MOD_0100_1516-Q1	Future Beyond Line Of Sight	AR 2018	1718-Q2	MOD	Amber/Red	01/01/2011	31/12/2041	Exempt	Exempt	-	-	Exempt			ICT	31.02	MOD_0100_1516-Q1,1718 - Q2		Exempt	Not new
MOD_0101_1516-Q1	New Style of Information Technology (Base)	AR 2018	1718-Q2	MOD	Amber/Red	01/04/2015	05/03/2018	Exempt	Exempt	-	-	Exempt			ICT	2.93	MOD_0101_1516-Q1,1718 - Q2		Exempt	Not new
MOD_0104_1617-Q1	Armour MBT 2025	AR 2018	1718-Q2	MOD	Amber	04/12/2014	01/06/2026	£26.51m	£26.02m	-£0.49m	-2%	Exempt			Military Capability	11.50	MOD_0104_1617-Q1,1718 - Q2		Amber	Not new
MOD_0105_1617-Q1	Land Environment Tactical Communication and Information Systems	AR 2018	1718-Q2	MOD	Amber/Red	01/05/2013	31/12/2035	£279.49m	£258.44m	-£21.05m	-8%	11063.27			Military Capability	22.68	MOD_0105_1617-Q1,1718 - Q2		Amber/Red	Not new
MOD_0106_1617-Q1	Maritime Patrol Aircraft	AR 2018	1718-Q2	MOD	Amber/Red	08/07/2014	01/04/2024	£12.74m	£30.56m	£17.82m	140%	2144.43			Military Capability	9.74	MOD_0106_1617-Q1,1718 - Q2		Amber/Red	Not new
MOD_0107_1617-Q1	PROTECTOR	AR 2018	1718-Q2	MOD	Red	30/04/2009	31/03/2035	£150.27m	£70.67m	-£79.60m	-53%	907.91			Military Capability	25.93	MOD_0107_1617-Q1,1718 - Q2		Red	Not new
MoD_0109_1617-Q2	New Style of Information Technology Deployed	AR 2018	1718-Q2	MOD	Amber/Red	01/04/2015	25/03/2025	Exempt	Exempt	-	-	Exempt			Military Capability	9.99	MoD_0109_1617-Q2,1718 - Q2		Exempt	Not new
MOD_0110_1718-Q1	MODnet Evolve	AR 2018	1718-Q2	MOD	Amber	29/02/2016	Missing Data	£15.20m	£14.87m	-£0.33m	-2%	Exempt			Military Capability	0.00	MOD_0110_1718-Q1,1718 - Q2		Amber	Joiner
MOD_0111_1718-Q1	Joint Crypt Key Programme	AR 2018	1718-Q2	MOD	Exempt	Exempt	Exempt	Exempt	Exempt	-	-	Exempt			Military Capability	0.00	MOD_0111_1718-Q1,1718 - Q2		Amber	Joiner
MOD_0112_1718-Q1	Type 31e	AR 2018	1718-Q2	MOD	Exempt	01/04/2016	Exempt	Exempt	Exempt	-	-	Exempt			Military Capability	0.00	MOD_0112_1718-Q1,1718 - Q2		Red	Joiner
MOD_0113_1718-Q1	Armed Forces People Programme	AR 2018	1718-Q2	MOD	Amber/Red	25/11/2015	31/03/2021	£11.10m	£24.56m	£13.46m	121%	57.38			Government Transformation and Service Delivery	5.35	MOD_0113_1718-Q1,1718 - Q2		Amber/Red	Joiner
MOD_0114_1718-Q1	Defence Estate Optimisation	AR 2018	1718-Q2	MOD	Amber/Red	30/09/2016	31/03/2041	£0.00m	£0.00m	£0.00m	-	0.00			Military Capability	24.52	MOD_0114_1718-Q1,1718 - Q2		Amber/Red	Joiner
MOD_0115_1718-Q2	Mechanised Infantry Programme	AR 2018	1718-Q2	MOD	Amber	Exempt	Exempt	Exempt	Exempt	-	-	Exempt			Military Capability	0.00	MOD_0115_1718-Q2,1718 - Q2		Amber	Joiner
MOD_0116_1718-Q2	Fleet Solid Support	AR 2018	1718-Q2	MOD	Amber	14/03/2016	30/04/2030	£3.27m	£3.27m	£0.00m	0%	17.27			Military Capability	14.14	MOD_0116_1718-Q2,1718 - Q2		Amber	Joiner
MOD_0117_1718-Q2	Future Maritime Support Strategy	AR 2018	1718-Q2	MOD	Amber/Red	26/09/2016	27/09/2019	£0.00m	£0.00m	£0.00m	-	0.00			Military Capability	3.00	MOD_0117_1718-Q2,1718 - Q2		Amber/Red	Joiner
MOJ_0003_1112-Q1	Electronic Monitoring	AR 2018	1718-Q2	MoJ	Amber/Red	10/05/2011	31/08/2024	£79.30m	£74.03m	-£5.27m	-7%	580.50			Government Transformation and Service Delivery	13.32	MOJ_0003_1112-Q1,1718 - Q2		Amber/Red	Not new
MOJ_0004_1112-Q1	Future IT Sourcing Programme (FITS)	AR 2018	1718-Q2	MoJ	Amber	01/03/2011	30/11/2017	£314.30m	£314.30m	£0.00m	0%	2879.25			ICT	6.76	MOJ_0004_1112-Q1,1718 - Q2		Amber	Not new
MOJ_0008_1112-Q1	Shared Services (ISSC2) Evolve	AR 2018	1718-Q2	MoJ	Amber/Green	07/09/2013	05/11/2015	£43.86m	£46.03m	£2.17m	5%	398.07			ICT	2.16	MOJ_0008_1112-Q1,1718 - Q2		Amber/Green	Not new
MOJ_0021_1314-Q1	CJS Common Platform	AR 2018	1718-Q2	MoJ	Amber/Red	01/11/2012	29/03/2019	£73.59m	£52.33m	-£21.26m	-29%	380.96			ICT	6.41	MOJ_0021_1314-Q1,1718 - Q2		Amber/Red	Not new
MOJ_0023_1314-Q1	Berwyn Programme	AR 2018	1718-Q2	MoJ	Amber/Green	10/01/2013	31/05/2018	£43.80m	£60.60m	£16.80m	38%	2269.70			Infrastructure and Construction	5.39	MOJ_0023_1314-Q1,1718 - Q2		Amber/Green	Not new
MOJ_0028_1314-Q2	HMCTS Reform	AR 2018	1718-Q2	MoJ	Amber/Red	05/01/2015	31/03/2022	£192.85m	£192.85m	£0.00m	0%	1647.02			Government Transformation and Service Delivery	7.24	MOJ_0028_1314-Q2,1718 - Q2		Amber/Red	Not new
MOJ_0032_1617-Q2	MoJ Future FM	AR 2018	1718-Q2	MoJ	Amber	01/07/2016	01/04/2018	£43.30m	£25.90m	-£17.40m	-40%	430.20			Government Transformation and Service Delivery	1.75	MOJ_0032_1617-Q2,1718 - Q2		Amber	Not new
MOJ_0033_1617-Q2	Prison Estate Transformation Programme (PETP)	AR 2018	1718-Q2	MoJ	Amber/Red	01/04/2016	31/12/2021	£0.00m	£0.00m	£0.00m	-	0.00			Infrastructure and Construction	5.75	MOJ_0033_1617-Q2,1718 - Q2		Amber/Red	Not new
MOJ_0034_1617-Q2	NOMS Digital Transformation Programme	AR 2018	1718-Q2	MoJ	Amber	01/01/2016	31/03/2021	£37.80m	£48.10m	£10.30m	27%	212.20			Government Transformation and Service Delivery	5.25	MOJ_0034_1617-Q2,1718 - Q2		Amber	Not new
MOJ_0035_1617-Q3	Criminal Justice System Exchange Re-provisioning	AR 2018	1718-Q2	MoJ	Amber	31/10/2015	31/10/2017	£16.06m	£19.91m	£3.85m	24%	39.88			ICT	2.00	MOJ_0035_1617-Q3,1718 - Q2		Amber	Joiner
MOJ_0037_1617-Q4	Transforming Compliance Enforcment Programme (TCEP)	AR 2018	1718-Q2	MoJ	Amber/Red	04/01/2016	26/04/2019	£27.40m	£27.40m	£0.00m	0%	123.00			Government Transformation and Service Delivery	3.31	MOJ_0037_1617-Q4,1718 - Q2		Red	Joiner
NCA_0001_1415-Q2	NCA Transformation Programme	AR 2018	1718-Q2	NCA	Amber	01/04/2014	31/03/2019	£61.00m	£61.00m	£0.00m	0%	304.30			Government Transformation and Service Delivery	5.00	NCA_0001_1415-Q2,1718 - Q2		Amber	Not new
NCA_0002_1617-Q2	IT Transformation Programme	AR 2018	1718-Q2	NCA	Amber	01/04/2016	31/07/2022	£38.80m	£38.80m	£0.00m	0%	167.68			ICT	6.33	NCA_0002_1617-Q2,1718 - Q2		Amber	Not new
ONS_0002_1112-Q1	Census Transformation Programme	AR 2018	1718-Q2	ONS	Amber	01/01/2015	31/03/2025	£55.60m	£55.01m	-£0.59m	-1%	905.76			Government Transformation and Service Delivery	10.25	ONS_0002_1112-Q1,1718 - Q2		Amber	Not new
BEIS_0001_1617-Q2	Heat Networks Investment Project	AR 2019	1819-Q2	BEIS	Amber	25/11/2015	31/03/2021	£10.40m	£7.89m	-£2.51m	-24%	371.80			Infrastructure and Construction	5.35	BEIS_0001_1617-Q2-1819-Q2			Not new
BEIS_0002_1718-Q1	UKRI Implementation Programme	AR 2019	1819-Q2	BEIS	Green	01/01/2016	01/10/2018	£0.00m	£0.00m	£0.00m	-	10.37			Government Transformation and Service Delivery	2.75	BEIS_0002_1718-Q1-1819-Q2			Not new
BEIS_0003_1819-Q2	The Next Magnox Operating Model	AR 2019	1819-Q2	BEIS	Amber	01/09/2017	01/09/2019	£2.00m	£2.00m	£0.00m	0%	5.00			Government Transformation and Service Delivery	2.00	BEIS_0003_1819-Q2-1819-Q2			Joiner
BIS_0014_1415-Q3	New Polar Research Vessel	AR 2019	1819-Q2	BEIS	Amber	01/05/2014	31/12/2022	£113.00m	£111.00m	-£2.00m	-2%	1403.00			Infrastructure and Construction	8.67	BIS_0014_1415-Q3-1819-Q2			Not new
BIS_0015_1516-Q1	Local Land Charges (LLC) Programme	AR 2019	1819-Q2	BEIS	Amber	01/03/2014	17/11/2023	£31.20m	£9.18m	-£22.02m	-71%	193.30			ICT	9.72	BIS_0015_1516-Q1-1819-Q2			Not new
CO_0013_1516-Q2	Foxhound Programme	AR 2019	1819-Q2	CO	Amber/Green	01/09/2013	01/07/2018	£26.10m	£22.70m	-£3.40m	-13%	126.50			ICT	4.83	CO_0013_1516-Q2-1819-Q2			Not new
CO_0014_1516-Q2	Government Hubs Programme	AR 2019	1819-Q2	CO	Amber	01/05/2015	31/03/2036	£111.41m	£111.41m	£0.00m	0%	564.10			Government Transformation and Service Delivery	20.93	CO_0014_1516-Q2-1819-Q2			Not new
CO_0015_1516-Q2	GOV UK Verify	AR 2019	1819-Q2	CO	Red	01/04/2012	31/03/2020	£30.00m	£30.00m	£0.00m	0%	209.60			ICT	8.00	CO_0015_1516-Q2-1819-Q2			Not new
CO_0016_1516-Q4	1617 New Property Model Programme	AR 2019	1819-Q2	CO	Amber	01/04/2015	01/04/2021	£7.00m	£7.00m	£0.00m	0%	270.74			Government Transformation and Service Delivery	6.01	CO_0016_1516-Q4-1819-Q2			Not new
CO_0018_1617-Q3	Common Technology Services	AR 2019	1819-Q2	CO	Amber	01/04/2016	31/03/2020	£8.10m	£5.20m	-£2.90m	-36%	43.96			Government Transformation and Service Delivery	4.00	CO_0018_1617-Q3-1819-Q2			Not new
CO_0019_1617-Q4	Government as a Platform	AR 2019	1819-Q2	CO	Amber	31/12/2015	31/03/2020	£20.00m	£15.80m	-£4.20m	-21%	90.00			ICT	4.25	CO_0019_1617-Q4-1819-Q2			Not new
CO_0020_1718-Q4	Commercial Capability Expansion Programme	AR 2019	1819-Q2	CO	Amber/Red	01/04/2017	31/03/2020	£6.00m	£6.20m	£0.20m	3%	11.70			Government Transformation and Service Delivery	3.00	CO_0020_1718-Q4-1819-Q2			Joiner
DCMS_0008_1516-Q4	Blythe House Programme	AR 2019	1819-Q2	DCMS	Amber	25/11/2015	31/03/2023	£88.75m	£23.50m	-£65.25m	-74%	338.00			Infrastructure and Construction	7.35	DCMS_0008_1516-Q4-1819-Q2			Not new
DCMS_0009_1516-Q4	700 MHz Clearance Programme	AR 2019	1819-Q2	DCMS	Amber	13/01/2015	01/01/2022	£164.30m	£87.10m	-£77.20m	-47%	594.92			Infrastructure and Construction	6.97	DCMS_0009_1516-Q4-1819-Q2			Not new
DCMS_0010_1718-Q3	Local Full Fibre Networks	AR 2019	1819-Q2	DCMS	Amber/Green	01/04/2017	01/12/2021	£50.70m	£58.00m	£7.30m	14%	318.70			Infrastructure and Construction	4.67	DCMS_0010_1718-Q3-1819-Q2			Joiner
DCMS_0011_1718-Q3	5G Testbeds & Trials	AR 2019	1819-Q2	DCMS	Amber/Red	28/02/2017	31/03/2021	£79.15m	£42.65m	-£36.50m	-46%	217.05			Infrastructure and Construction	4.09	DCMS_0011_1718-Q3-1819-Q2			Joiner
DCMS_0012_1819-Q2	Birmingham 2022 Commonwealth Games	AR 2019	1819-Q2	DCMS	Amber/Red	21/12/2017	31/03/2023	Exempt	Exempt	-	-	Exempt			Government Transformation and Service Delivery	5.28	DCMS_0012_1819-Q2-1819-Q2			Joiner
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2019	1819-Q2	BEIS	Amber	30/06/2008	31/12/2040	£40.27m	£37.40m	-£2.87m	-7%	12343.96			Infrastructure and Construction	32.53	DECC_0005_1112-Q1-1819-Q2			Not new
DECC_0010_1112-Q1	Smart Metering Implementation Programme	AR 2019	1819-Q2	BEIS	Amber/Red	02/12/2009	31/12/2020	£1060.97m	£1064.04m	£3.07m	0%	17215.78			Infrastructure and Construction	11.09	DECC_0010_1112-Q1-1819-Q2			Not new
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	AR 2019	1819-Q2	BEIS	Amber	03/04/2012	31/08/2019	£490.00m	£532.00m	£42.00m	9%	2782.00			Infrastructure and Construction	7.41	DECC_0013_1213-Q1-1819-Q2			Not new
DECC_0017_1516-Q1	Sellafield Model Change (SMC)	AR 2019	1819-Q2	BEIS	Green	13/01/2015	24/05/2017	£2292.80m	£2038.80m	-£254.00m	-11%	30011.20			Government Transformation and Service Delivery	2.36	DECC_0017_1516-Q1-1819-Q2			Not new
DEFRA_0006_1516-Q1	DEFRA UNITY PROGRAMME	AR 2019	1819-Q2	DEFRA	Amber	01/11/2014	30/04/2020	£121.20m	£159.00m	£37.80m	31%	1048.40			ICT	5.50	DEFRA_0006_1516-Q1-1819-Q2			Not new
DFE_0006_1415-Q3	Priority School Building Programme 2	AR 2019	1819-Q2	DFE	Amber/Red	01/05/2014	31/12/2022	£448.60m	£448.60m	£0.00m	0%	2398.50			Infrastructure and Construction	8.67	DFE_0006_1415-Q3-1819-Q2			Not new
DFE_0007_1617-Q1	30 Hrs Free Childcare Programme	AR 2019	1819-Q2	DFE	Amber/Green	11/05/2015	31/03/2018	£750.02m	£750.51m	£0.49m	0%	5874.92			Government Transformation and Service Delivery	2.89	DFE_0007_1617-Q1-1819-Q2			Not new
DfE_0009_1617-Q2	Apprenticeships Reform Programme	AR 2019	1819-Q2	DFE	Amber	08/05/2015	01/04/2021	£2243.30m	£1863.60m	-£379.70m	-17%	11347.50			Government Transformation and Service Delivery	5.90	DfE_0009_1617-Q2-1819-Q2			Not new
DFE_0010_1819-Q1	T Level Programme	AR 2019	1819-Q2	DFE	Amber/Red	25/10/2016	30/09/2023	£50.00m	£50.00m	£0.00m	0%	146.20			Government Transformation and Service Delivery	6.93	DFE_0010_1819-Q1-1819-Q2			Joiner
DFE_0011_1819-Q2	Social Work England	AR 2019	1819-Q2	DFE	Amber	09/05/2016	Exempt	£11.35m	£7.89m	-£3.47m	-31%	21.31			Government Transformation and Service Delivery	0.00	DFE_0011_1819-Q2-1819-Q2			Joiner
DFID_0001_1112-Q1	St Helena Airport	AR 2019	1819-Q2	DFID	Amber	15/03/2005	31/08/2026	£4.00m	£4.64m	£0.64m	16%	445.10			Infrastructure and Construction	21.48	DFID_0001_1112-Q1-1819-Q2			Not new
DFT_0001_1112-Q1	Crossrail Programme	AR 2019	1819-Q2	DFT	Red	22/07/2008		£466.75m	£1089.20m	£622.45m	133%	15474.61			Infrastructure and Construction	0.00	DFT_0001_1112-Q1-1819-Q2			Not new
DFT_0004_1112-Q1	High Speed Rail Programme (HS2)	AR 2019	1819-Q2	DFT	Amber/Red	28/02/2011	31/12/2033	£2976.00m	£3009.00m	£33.00m	1%	55710.37			Infrastructure and Construction	22.85	DFT_0004_1112-Q1-1819-Q2			Not new
DFT_0005_1112-Q1	Intercity Express Programme	AR 2019	1819-Q2	DFT	Amber/Red	01/06/2005	06/02/2020	£120.10m	£154.90m	£34.80m	29%	6583.25			Infrastructure and Construction	14.69	DFT_0005_1112-Q1-1819-Q2			Not new
DFT_0016_1112-Q1	Thameslink Programme	AR 2019	1819-Q2	DFT	Amber	01/07/2005	31/12/2026	£2178.70m	£2026.70m	-£152.00m	-7%	7269.40			Infrastructure and Construction	21.52	DFT_0016_1112-Q1-1819-Q2			Not new
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	AR 2019	1819-Q2	DFT	Amber/Green	01/09/2012	30/09/2021	£407.30m	£475.00m	£67.70m	17%	1435.30			Infrastructure and Construction	9.08	DFT_0020_1314-Q2-1819-Q2			Not new
DFT_0021_1314-Q3	Rail Franchising Programme	AR 2019	1819-Q2	DFT	Amber/Red	19/05/2016	31/03/2019	£10.60m	£12.70m	£2.10m	20%	20.60			Government Transformation and Service Delivery	2.87	DFT_0021_1314-Q3-1819-Q2			Not new
DfT_0022_1415-Q4	Lower Thames Crossing	AR 2019	1819-Q2	DFT	Amber	30/05/2014	31/07/2028	£61.90m	£81.00m	£19.10m	31%	5509.00			Infrastructure and Construction	14.18	DfT_0022_1415-Q4-1819-Q2			Not new
DfT_0023_1516-Q3	Heathrow Expansion	AR 2019	1819-Q2	DFT	Amber	01/07/2015	31/12/2029	£14.70m	£7.90m	-£6.80m	-46%	22732.90			Infrastructure and Construction	14.51	DfT_0023_1516-Q3-1819-Q2			Not new
DFT_0024_1516-Q4	A303 Amesbury to Berwick Down	AR 2019	1819-Q2	DFT	Amber	01/12/2014	01/06/2028	£22.90m	£33.19m	£10.29m	45%	1556.40			Infrastructure and Construction	13.51	DFT_0024_1516-Q4-1819-Q2			Not new
DFT_0025_1617-Q1	East West Rail Programme (Western Section)	AR 2019	1819-Q2	DFT	Amber	30/11/2011	30/06/2024	£89.70m	£89.70m	£0.00m	0%	1091.40			Infrastructure and Construction	12.59	DFT_0025_1617-Q1-1819-Q2			Not new
DFT_0026_1617-Q1	Great Western Route Modernisation (GWRM) including electrification	AR 2019	1819-Q2	DFT	Amber/Red	01/12/2011	31/12/2024	£655.00m	£769.00m	£114.00m	17%	5001.00			Infrastructure and Construction	13.09	DFT_0026_1617-Q1-1819-Q2			Not new
DFT_0027_1617-Q1	Midland Main Line Programme	AR 2019	1819-Q2	DFT	Amber	01/01/2011	31/12/2024	£501.90m	£441.30m	-£60.60m	-12%	1671.20			Infrastructure and Construction	14.01	DFT_0027_1617-Q1-1819-Q2			Not new
DFT_0028_1617-Q1	North of England Programme	AR 2019	1819-Q2	DFT	Amber	23/07/2009	31/12/2022	£285.00m	£367.70m	£82.70m	29%	6052.00			Infrastructure and Construction	13.45	DFT_0028_1617-Q1-1819-Q2			Not new
DFT_0029_1617-Q1	South West Route Capacity	AR 2019	1819-Q2	DFT	Amber/Green	16/07/2012	31/12/2019	£178.22m	£129.02m	-£49.20m	-28%	820.20			Infrastructure and Construction	7.46	DFT_0029_1617-Q1-1819-Q2			Not new
DFT_0030_1617-Q2	M20 Lorry Area	AR 2019	1819-Q2	DFT	Amber	01/11/2015	01/07/2023	£0.00m	£3.70m	£3.70m	-	0.00			Infrastructure and Construction	7.67	DFT_0030_1617-Q2-1819-Q2			Not new
DFT_0031_1819-Q1	A428 Black Cat to Caxton Gibbet	AR 2019	1819-Q2	DFT	Amber/Green	01/04/2015	01/04/2025	£14.30m	£8.30m	-£6.00m	-42%	809.80			Infrastructure and Construction	10.01	DFT_0031_1819-Q1-1819-Q2			Joiner
DFT_0032_1819-Q1	Digital Railway	AR 2019	1819-Q2	DFT	Amber	23/11/2016	01/04/2023	£32.00m	£32.02m	£0.02m	0%	450.00			Infrastructure and Construction	6.36	DFT_0032_1819-Q1-1819-Q2			Joiner
DFT_0033_1819-Q1	East Coast Mainline Programme	AR 2019	1819-Q2	DFT	Amber/Green	01/04/2014	01/12/2023	£141.20m	£141.20m	£0.00m	0%	1040.37			Infrastructure and Construction	9.67	DFT_0033_1819-Q1-1819-Q2			Joiner
DH_0017_1112-Q1	PHE Science Hub	AR 2019	1819-Q2	DH	Amber	28/06/2013	31/12/2024	£204.79m	£188.73m	-£16.07m	-8%	2656.32			Infrastructure and Construction	11.52	DOH_0017_1112-Q1-1819-Q2			Not new
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	AR 2019	1819-Q2	DH	Amber	01/01/2012	30/05/2018	£54.90m	£74.51m	£19.61m	36%	1247.24			Government Transformation and Service Delivery	6.41	DOH_0031_1314-Q1-1819-Q2			Not new
DH_0039_1314-Q2	NHS e-Referral Service	AR 2019	1819-Q2	DH	Green	29/03/2012	31/03/2018	£19.99m	£22.85m	£2.86m	14%	151.15			ICT	6.01	DOH_0039_1314-Q2-1819-Q2			Not new
DH_0041_1314-Q2	Health & Social Care Network	AR 2019	1819-Q2	DH	Amber/Red	29/03/2012	31/03/2021	£83.71m	£86.44m	£2.73m	3%	392.76			ICT	9.01	DOH_0041_1314-Q2-1819-Q2			Not new
DH_0043_1314-Q3	NHS Pension Re-let	AR 2019	1819-Q2	DH	Amber/Green	05/07/2013	21/07/2017	£28.98m	£28.98m	£0.00m	0%	274.24			Government Transformation and Service Delivery	4.05	DOH_0043_1314-Q3-1819-Q2			Not new
DH_0046_1415-Q1	Medical Examiners Programme	AR 2019	1819-Q2	DH	Amber/Red	24/07/2007	30/09/2020	£19.70m	£19.70m	£0.00m	0%	76.10			Government Transformation and Service Delivery	13.20	DOH_0046_1415-Q1-1819-Q2			Not new
DH_0048_1415-Q1	One Hundred Thousand Genomes Project	AR 2019	1819-Q2	DH	Amber	10/04/2013	31/12/2018	£50.00m	£82.70m	£32.70m	65%	369.90			Government Transformation and Service Delivery	5.73	DOH_0048_1415-Q1-1819-Q2			Not new
DH_0056_1415-Q3	Visitor and Migrant NHS Cost Recovery Programme	AR 2019	1819-Q2	DH	Amber/Green	01/09/2013	31/03/2019	£7.62m	£7.62m	£0.00m	0%	33.15			Government Transformation and Service Delivery	5.58	DOH_0056_1415-Q3-1819-Q2			Not new
DH_0058_1516-Q4	Data Services Platform Programme	AR 2019	1819-Q2	DH	Amber	23/02/2015	31/03/2020	£20.49m	£18.64m	-£1.85m	-9%	75.25			ICT	5.10	DOH_0058_1516-Q4-1819-Q2			Not new
DH_0059_1617-Q1	Procurement Transformation Programme	AR 2019	1819-Q2	DH	Amber	31/03/2015	31/03/2019	£32.21m	£51.54m	£19.33m	60%	168.73			Government Transformation and Service Delivery	4.00	DOH_0059_1617-Q1-1819-Q2			Not new
DH_0060_1617-Q1	NHS UK	AR 2019	1819-Q2	DH	Amber	01/04/2016	31/12/2020	£12.82m	£12.82m	£0.00m	0%	54.95			Government Transformation and Service Delivery	4.75	DOH_0060_1617-Q1-1819-Q2			Not new
DH_0061_1617-Q3	IT Infrastructure Sourcing Programme	AR 2019	1819-Q2	DH	Amber/Red	01/12/2013	31/12/2019	£22.10m	£22.10m	£0.00m	0%	129.50			ICT	6.08	DOH_0061_1617-Q3-1819-Q2			Not new
DWP_0005_1112-Q1	Automatic Enrolment Programme (originally called Enabling Retirement Savings Programme)	AR 2019	1819-Q2	DWP	Amber/Green	01/05/2007	30/11/2019	£66.16m	£66.10m	-£0.06m	0%	1125.00			Government Transformation and Service Delivery	12.59	DWP_0005_1112-Q1-1819-Q2			Not new
DWP_0009_1112-Q1	Universal Credit Programme	AR 2019	1819-Q2	DWP	Amber	17/11/2011	30/06/2023	£836.72m	£819.39m	-£17.33m	-2%	12716.95			Government Transformation and Service Delivery	11.62	DWP_0009_1112-Q1-1819-Q2			Not new
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	AR 2019	1819-Q2	DWP	Amber/Green	02/04/2012	31/03/2021	£108.77m	£94.88m	-£13.89m	-13%	1174.70			Government Transformation and Service Delivery	9.00	DWP_0016_1213-Q2-1819-Q2			Not new
FCO_0008_1415-Q4	Technology Overhaul	AR 2019	1819-Q2	FCO	Amber	01/11/2015	31/03/2019	£20.40m	£24.97m	£4.57m	22%	120.00			ICT	3.41	FCO_0008_1415-Q4-1819-Q2			Not new
FCO_0010_1617-Q3	Echo 2 Programme	AR 2019	1819-Q2	FCO	Amber	01/09/2015	31/08/2021	£28.90m	£31.35m	£2.45m	8%	203.84			ICT	6.00	FCO_0010_1617-Q3-1819-Q2			Not new
FCO_0011_1718-Q3	Washington Embassy Refurbishment	AR 2019	1819-Q2	FCO	Amber	01/01/2017	12/12/2022	£8.70m	£8.70m	£0.00m	0%	63.70			Infrastructure and Construction	5.95	FCO_0011_1718-Q3-1819-Q2			Joiner
FCO_0012_1718-Q4	Atlas Programme (IPA ID 2410)	AR 2019	1819-Q2	FCO	Amber	01/07/2017	30/06/2020	£9.30m	£9.30m	£0.00m	0%	21.80			ICT	3.00	FCO_0012_1718-Q4-1819-Q2			Joiner
HMRC_0012_1415-Q1	Tax-Free Childcare	AR 2019	1819-Q2	HMRC	Amber	10/09/2013	30/09/2019	£54.06m	£50.91m	-£3.15m	-6%	356.89			Government Transformation and Service Delivery	6.06	HMRC_0012_1415-Q1-1819-Q2			Not new
HMRC_0013_1415-Q4	Columbus (formerly Aspire Replacement Programme)	AR 2019	1819-Q2	HMRC	Amber	01/01/2014	31/12/2021	£104.00m	£6.00m	-£98.00m	-94%	694.00			ICT	8.00	HMRC_0013_1415-Q4-1819-Q2			Not new
HMRC_0014_1415-Q4	CUSTOMS DECLARATION SERVICES (CDS) Programme	AR 2019	1819-Q2	HMRC	Amber/Red	16/10/2013	31/01/2019	£75.49m	£75.57m	£0.08m	0%	226.33			ICT	5.30	HMRC_0014_1415-Q4-1819-Q2			Not new
HMRC_0015_1617-Q1	Building Our Future Locations Programme	AR 2019	1819-Q2	HMRC	Amber	05/01/2016	31/03/2026	£326.10m	£302.80m	-£23.30m	-7%	2835.90			Government Transformation and Service Delivery	10.24	HMRC_0015_1617-Q1-1819-Q2			Not new
HMRC_0017_1617-Q2	Making Tax Digital for Business	AR 2019	1819-Q2	HMRC	Amber/Red	01/04/2016	31/03/2021	£77.09m	£75.15m	-£1.94m	-3%	334.48			ICT	5.00	HMRC_0017_1617-Q2-1819-Q2			Not new
HMRC_0018_1617-Q3	Compliance For The Future Programme	AR 2019	1819-Q2	HMRC	Amber/Red	01/04/2016	31/03/2021	£50.45m	£34.40m	-£16.05m	-32%	188.18			Government Transformation and Service Delivery	5.00	HMRC_0018_1617-Q3-1819-Q2			Not new
HMRC_0019_1718-Q4	Government Gateway Transformation	AR 2019	1819-Q2	HMRC	Amber	01/04/2017	31/03/2019	£28.04m	£25.19m	-£2.85m	-10%	131.11			ICT	2.00	HMRC_0019_1718-Q4-1819-Q2			Joiner
HO_0011_1112-Q2	Disclosure and Barring Service (DBS) Programme	AR 2019	1819-Q2	HO	Amber/Red	29/12/2010	31/12/2019	£110.40m	£172.00m	£61.60m	56%	785.70			Government Transformation and Service Delivery	9.01	HO_0011_1112-Q2-1819-Q2			Not new
HO_0012_1112-Q3	Communications Capabilities Development (CCD) Programme	AR 2019	1819-Q2	HO	Green	01/05/2010	01/04/2020	Exempt	Exempt	-	-	Exempt			ICT	9.93	HO_0012_1112-Q3-1819-Q2			Not new
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2019	1819-Q2	HO	Amber/Red	01/06/2011	31/12/2020	£773.87m	£773.87m	£0.00m	0%	5058.63			Infrastructure and Construction	9.59	HO_0016_1213-Q1-1819-Q2			Not new
HO_0029_1314-Q4	Immigration Platform Technologies (IPT)	AR 2019	1819-Q2	HO	Amber	01/04/2013	31/03/2017	£40.70m	£50.70m	£10.00m	25%	264.95			ICT	4.00	HO_0029_1314-Q4-1819-Q2			Not new
HO_0030_1415-Q1	Metis Programme	AR 2019	1819-Q2	HO	Amber/Red	01/09/2016	01/06/2019	£53.30m	£56.12m	£2.82m	5%	290.53			ICT	2.75	HO_0030_1415-Q1-1819-Q2			Not new
HO_0031_1415-Q1	Digital Services at the Border (DSAB)	AR 2019	1819-Q2	HO	Amber	12/02/2014	31/03/2019	£52.60m	£64.10m	£11.50m	22%	346.90			ICT	5.13	HO_0031_1415-Q1-1819-Q2			Not new
HO_0032_1415-Q1	Technology Platforms for Tomorrow (TPT)	AR 2019	1819-Q2	HO	Amber	01/02/2014	31/03/2019	£70.32m	£76.50m	£6.18m	9%	592.07			ICT	5.16	HO_0032_1415-Q1-1819-Q2			Not new
HO_0033_1415-Q3	Home Office Biometrics (HOB) Programme	AR 2019	1819-Q2	HO	Amber/Green	01/04/2014	31/03/2020	£75.40m	£75.40m	£0.00m	0%	842.37			ICT	6.00	HO_0033_1415-Q3-1819-Q2			Not new
HO_0034_1516-Q2	Cyclamen Project	AR 2019	1819-Q2	HO	Amber	01/04/2014	01/04/2020	Exempt	Exempt	-	-	Exempt			Government Transformation and Service Delivery	6.01	HO_0034_1516-Q2-1819-Q2			Not new
HO_0035_1617-Q1	Smarter Working Programme (SWP)	AR 2019	1819-Q2	HO	Amber	28/10/2015	31/03/2020	£25.60m	£4.82m	-£20.78m	-81%	144.50			Government Transformation and Service Delivery	4.43	HO_0035_1617-Q1-1819-Q2			Not new
HO_0036_1617-Q2	National Law Enforcement Data Programme (NLEDP)	AR 2019	1819-Q2	HO	Amber/Red	01/04/2014	31/03/2020	£67.50m	£82.10m	£14.60m	22%	469.40			ICT	6.00	HO_0036_1617-Q2-1819-Q2			Not new
HO_0037_1718-Q1	Asylum Accommodation and Support Transformation (AAST)	AR 2019	1819-Q2	HO	Amber	29/08/2016	02/09/2019	£3.64m	£19.97m	£16.33m	449%	5062.02			Government Transformation and Service Delivery	3.01	HO_0037_1718-Q1-1819-Q2			Not new
MOD_0001_1112-Q1	A400M	AR 2019	1819-Q2	MOD	Amber	17/05/2000	31/03/2023	£118.42m	£95.29m	-£23.13m	-20%	3394.89			Military Capability	22.88	MOD_0001_1112-Q1-1819-Q2			Not new
MOD_0017_1112-Q1	Crowsnest Programme	AR 2019	1819-Q2	MOD	Amber	31/03/2013	30/06/2023	£104.86m	£104.86m	£0.00m	0%	Exempt			Military Capability	10.25	MOD_0017_1112-Q1-1819-Q2			Not new
MOD_0033_1112-Q1	MARSHALL	AR 2019	1819-Q2	MOD	Amber/Green	03/04/2006	31/12/2024	£125.71m	£108.22m	-£17.49m	-14%	1807.59			Military Capability	18.76	MOD_0033_1112-Q1-1819-Q2			Not new
MOD_0036_1112-Q1	Maritime Sustainment Programme	AR 2019	1819-Q2	MOD	Amber	25/07/2005	28/02/2019	£25.53m	£25.53m	£0.00m	0%	618.81			Military Capability	13.61	MOD_0036_1112-Q1-1819-Q2			Not new
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2019	1819-Q2	MOD	Exempt	01/04/2008	30/04/2025	£1065.18m	£1039.76m	-£25.42m	-2%	19895.89			Military Capability	17.09	MOD_0038_1112-Q1-1819-Q2			Not new
MOD_0042_1112-Q1	Queen Elizabeth Programme	AR 2019	1819-Q2	MOD	Amber	01/12/1998	31/03/2023	£258.07m	£249.43m	-£8.64m	-3%	6797.64			Military Capability	24.35	MOD_0042_1112-Q1-1819-Q2			Not new
MOD_0047_1112-Q1	Spearfish Upgrade Programme	AR 2019	1819-Q2	MOD	Amber/Red	01/04/2008	31/03/2024	£38.69m	£37.90m	-£0.79m	-2%	413.89			Military Capability	16.01	MOD_0047_1112-Q1-1819-Q2			Not new
MOD_0055_1112-Q1	Type 26 Global Combat Ship Programme	AR 2019	1819-Q2	MOD	Amber/Green	21/07/2008	01/05/2035	£432.15m	£430.85m	-£1.30m	0%	Exempt			Military Capability	26.79	MOD_0055_1112-Q1-1819-Q2			Not new
MOD_0061_1112-Q1	WATCHKEEPER	AR 2019	1819-Q2	MOD	Amber	01/03/1998	03/07/2017	£0.00m	£0.28m	£0.28m	-	1117.73			Military Capability	19.35	MOD_0061_1112-Q1-1819-Q2			Not new
MOD_0064_1112-Q2	Carrier Enabled Power Projection	AR 2019	1819-Q2	MOD	Amber	31/01/2011	01/12/2030	£1.86m	£1.82m	-£0.03m	-2%	21.57			Military Capability	19.85	MOD_0064_1112-Q2-1819-Q2			Not new
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2019	1819-Q2	MOD	Amber	17/03/1997	30/04/2025	£502.51m	£479.79m	-£22.71m	-5%	9970.77			Military Capability	28.14	MOD_0076_1213-Q1-1819-Q2			Not new
MOD_0077_1213-Q1	Complex Weapons	AR 2019	1819-Q2	MOD	Amber	31/03/2008	01/04/2032	£726.25m	£778.15m	£51.90m	7%	26034.99			Military Capability	24.02	MOD_0077_1213-Q1-1819-Q2			Not new
MOD_0078_1213-Q1	Core Production Capability	AR 2019	1819-Q2	MOD	Amber	01/04/2012	30/04/2028	£182.30m	£182.30m	£0.00m	0%	1659.23			Military Capability	16.09	MOD_0078_1213-Q1-1819-Q2			Not new
MOD_0079_1213-Q1	Lightning Programme	AR 2019	1819-Q2	MOD	Amber/Red	01/10/2001	31/03/2035	£803.33m	£786.50m	-£16.84m	-2%	10475.19			Military Capability	33.52	MOD_0079_1213-Q1-1819-Q2			Not new
MOD_0080_1213-Q1	DREADNOUGHT	AR 2019	1819-Q2	MOD	Amber	14/04/2011	Exempt	£1505.63m	£1339.29m	-£166.35m	-11%	30060.07			Military Capability	0.00	MOD_0080_1213-Q1-1819-Q2			Not new
MOD_0085_1314-Q2	Army Basing Programme	AR 2019	1819-Q2	MOD	Amber	22/05/2013	26/11/2021	£630.32m	£499.58m	-£130.74m	-21%	2059.26			Military Capability	8.52	MOD_0085_1314-Q2-1819-Q2			Not new
MOD_0091_1415-Q3	Armoured Cavalry 2025	AR 2019	1819-Q2	MOD	Amber	22/01/2014	30/04/2025	£627.86m	£542.50m	-£85.36m	-14%	6291.94			Military Capability	11.28	MOD_0091_1415-Q3-1819-Q2			Not new
MOD_0092_1415-Q3	Armoured Infantry 2026	AR 2019	1819-Q2	MOD	Red	04/12/2014	31/12/2026	£64.17m	£42.79m	-£21.38m	-33%	Exempt			Military Capability	12.08	MOD_0092_1415-Q3-1819-Q2			Not new
MOD_0094_1415-Q3	Contracting; Purchasing and Finance	AR 2019	1819-Q2	MOD	Amber	01/12/2011	31/03/2018	£7.87m	£9.12m	£1.24m	16%	146.73			Government Transformation and Service Delivery	6.33	MOD_0094_1415-Q3-1819-Q2			Not new
MOD_0100_1516-Q1	Future Beyond Line Of Sight	AR 2019	1819-Q2	MOD	Amber/Red	01/01/2011	31/12/2041	Exempt	Exempt	-	-	Exempt			ICT	31.02	MOD_0100_1516-Q1-1819-Q2			Not new
MOD_0101_1516-Q1	New Style of Information Technology (Base)	AR 2019	1819-Q2	MOD	Amber/Red	01/04/2015	05/03/2018	Exempt	Exempt	-	-	Exempt			ICT	2.93	MOD_0101_1516-Q1-1819-Q2			Not new
MOD_0104_1617-Q1	Armour MBT 2025	AR 2019	1819-Q2	MOD	Amber	04/12/2014	01/06/2026	Exempt	Exempt	-	-	Exempt			Military Capability	11.50	MoD_0104_1617-Q1-1819-Q2			Not new
MOD_0105_1617-Q1	Land Environment Tactical Communication and Information Systems	AR 2019	1819-Q2	MOD	Amber/Red	01/05/2013	31/12/2035	£273.66m	£251.70m	-£21.97m	-8%	11142.64			Military Capability	22.68	MoD_0105_1617-Q1-1819-Q2			Not new
MOD_0106_1617-Q1	Maritime Patrol Aircraft	AR 2019	1819-Q2	MOD	Amber/Red	08/07/2014	01/04/2024	£186.19m	£177.90m	-£8.29m	-4%	2048.90			Military Capability	9.74	MoD_0106_1617-Q1-1819-Q2			Not new
MOD_0107_1617-Q1	PROTECTOR	AR 2019	1819-Q2	MOD	Amber/Red	30/04/2009	31/03/2035	£64.24m	£52.72m	-£11.52m	-18%	1039.25			Military Capability	25.93	MoD_0107_1617-Q1-1819-Q2			Not new
MOD_0109_1617-Q2	New Style of Information Technology Deployed	AR 2019	1819-Q2	MOD	Amber	01/04/2015	25/03/2025	Exempt	Exempt	-	-	Exempt			Military Capability	9.99	MoD_0109_1617-Q2-1819-Q2			Not new
MOD_0110_1718-Q1	MODnet Evolve	AR 2019	1819-Q2	MOD	Amber/Red	29/02/2016	11/07/2022	Exempt	Exempt	Exempt	-	Exempt			Military Capability	6.37	MOD_0110_1718-Q1-1819-Q2			Not new
MOD_0111_1718-Q1	Joint Crypt Key Programme	AR 2019	1819-Q2	MOD	Exempt	Exempt	Exempt	Exempt	Exempt	-	-	Exempt			Military Capability	0.00	MOD_0111_1718-Q1-1819-Q2			Not new
MOD_0112_1718-Q1	Type 31e	AR 2019	1819-Q2	MOD	Exempt	01/04/2016	Exempt	Exempt	Exempt	-	-	Exempt			Military Capability	0.00	MOD_0112_1718-Q1-1819-Q2			Not new
MOD_0113_1718-Q1	Armed Forces People Programme	AR 2019	1819-Q2	MOD	Amber/Red	25/11/2015	31/03/2021	£27.27m	£22.53m	-£4.74m	-17%	69.65			Government Transformation and Service Delivery	5.35	MOD_0113_1718-Q1-1819-Q2			Not new
MOD_0114_1718-Q1	Defence Estate Optimisation	AR 2019	1819-Q2	MOD	Amber/Red	30/09/2016	31/03/2041	£201.05m	£85.35m	-£115.70m	-58%	1166.87			Military Capability	24.52	MOD_0114_1718-Q1-1819-Q2			Not new
MOD_0115_1718-Q2	Mechanised Infantry Programme	AR 2019	1819-Q2	MOD	Amber	Exempt	Exempt	Exempt	Exempt	-	-	Exempt			Military Capability	Exempt	MOD_0115_1718-Q2-1819-Q2			Not new
MOD_0116_1718-Q2	Fleet Solid Support	AR 2019	1819-Q2	MOD	Amber	14/03/2016	30/04/2030	£1.97m	£1.97m	£0.00m	0%	11.78			Military Capability	14.14	MOD_0116_1718-Q2-1819-Q2			Not new
MOD_0117_1718-Q2	Future Maritime Support Programme	AR 2019	1819-Q2	MOD	Amber/Red	26/09/2016	27/09/2019	Exempt	Exempt	-	-	Exempt			Military Capability	3.00	MOD_0117_1718-Q2-1819-Q2			Not new
MOD_0118_1718-Q3	Clyde Infrastructure	AR 2019	1819-Q2	MOD	Amber/Green	00:00:00	00:00:00	£161.19m	£155.07m	-£6.13m	-4%	1771.62			Military Capability	0.00	MOD_0118_1718-Q3-1819-Q2			Joiner
MOJ_0003_1112-Q1	Electronic Monitoring	AR 2019	1819-Q2	MOJ	Amber/Green	10/05/2011	31/08/2024	£106.80m	£94.90m	-£11.90m	-11%	580.50			Government Transformation and Service Delivery	13.32	MOJ_0003_1112-Q1-1819-Q2			Not new
MOJ_0004_1112-Q1	Future IT Sourcing Programme (FITS)	AR 2019	1819-Q2	MOJ	Amber/Green	01/03/2011	30/11/2017	£220.23m	£238.00m	£17.77m	8%	2879.23			ICT	6.76	MOJ_0004_1112-Q1-1819-Q2			Not new
MOJ_0021_1314-Q1	CJS Common Platform	AR 2019	1819-Q2	MOJ	Amber/Red	01/11/2012	29/03/2019	£74.96m	£58.48m	-£16.48m	-22%	398.84			ICT	6.41	MOJ_0021_1314-Q1-1819-Q2			Not new
MOJ_0028_1314-Q2	HMCTS Reform	AR 2019	1819-Q2	MOJ	Amber/Red	05/01/2015	31/03/2020	£242.01m	£242.01m	£0.00m	0%	1546.83			Government Transformation and Service Delivery	5.24	MOJ_0028_1314-Q2-1819-Q2			Not new
MOJ_0032_1617-Q2	MoJ Future FM	AR 2019	1819-Q2	MOJ	Amber/Red	01/07/2016	01/04/2018	£81.40m	£67.10m	-£14.30m	-18%	430.20			Government Transformation and Service Delivery	1.75	MOJ_0032_1617-Q2-1819-Q2			Not new
MOJ_0033_1617-Q2	Prison Estate Transformation Programme (PETP)	AR 2019	1819-Q2	MOJ	Amber/Red	01/04/2016	07/05/2026	£67.81m	£67.81m	£0.00m	0%	30165.85			Infrastructure and Construction	10.10	MOJ_0033_1617-Q2-1819-Q2			Not new
MOJ_0037_1617-Q4	Transforming Compliance Enforcment Programme (TCEP)	AR 2019	1819-Q2	MOJ	Red	04/01/2016	26/04/2019	£37.30m	£5.50m	-£31.80m	-85%	123.00			Government Transformation and Service Delivery	3.31	MOJ_0037_1617-Q4-1819-Q2			Not new
MOJ_0038_1718-Q4	HMCTS Facilities Management Reprocurement Project (FMRP)	AR 2019	1819-Q2	MOJ	Amber/Red	01/03/2017	31/12/2019	£0.90m	£0.90m	£0.00m	0%	787.20			Government Transformation and Service Delivery	2.84	MOJ_0038_1718-Q4-1819-Q2			Joiner
MOJ_0039_1718-Q3	Prison Education Programme	AR 2019	1819-Q2	MOJ	Amber/Green	01/04/2017	30/06/2019	£156.50m	£156.50m	£0.00m	0%	1223.20			Government Transformation and Service Delivery	2.25	MOJ_0039_1718-Q3-1819-Q2			Joiner
MOJ_0040_1718-Q3	YOUTH JUSTICE REFORM PROGRAMME	AR 2019	1819-Q2	MOJ	Amber	12/12/2016	31/12/2022	£12.70m	£11.50m	-£1.20m	-9%	311.13			Government Transformation and Service Delivery	6.05	MOJ_0040_1718-Q3-1819-Q2			Joiner
MOJ_0041_1819-Q1	Prisoner Escort and Custody Services (PECS) Generation 4	AR 2019	1819-Q2	MOJ	Amber/Red	01/04/2017	31/03/2021	£2.90m	£2.90m	£0.00m	0%	1622.30			Government Transformation and Service Delivery	4.00	MOJ_0041_1819-Q1-1819-Q2			Joiner
MOJ_0042_1819-Q2	Probation Programme	AR 2019	1819-Q2	MOJ	Amber/Red	01/10/2017	01/03/2020	£385.00m	£394.00m	£9.00m	2%	1200.00			Government Transformation and Service Delivery	2.42	MOJ_0042_1819-Q2-1819-Q2			Joiner
NCA_0001_1415-Q2	NCA Transformation Programme	AR 2019	1819-Q2	NCA	Amber	01/04/2014	31/03/2022	£62.80m	£51.00m	-£11.80m	-19%	306.80			Government Transformation and Service Delivery	8.00	NCA_0001_1415-Q2-1819-Q2			Not new
ONS_0002_1112-Q1	Census & Data Collection Transformation Programme	AR 2019	1819-Q2	ONS	Amber	01/01/2015	31/03/2025	£94.00m	£89.50m	-£4.50m	-5%	906.50			Government Transformation and Service Delivery	10.25	ONS_0002_1112-Q1-1819-Q2			Not new
MOD_0101_1516-Q1	New Style of Information Technology (Base)	AR 2020	1920-Q2	MOD	Amber/Red	01/04/2015	31/03/2022	Exempt	Exempt	Exempt	Exempt	Exempt			ICT	7.00				Not new	David Lynam	To deliver a cost-effective and modern â€˜New Style of ITâ€™ across the Defence estate.
MOD_0110_1718-Q1	MODnet Evolve	AR 2020	1920-Q2	MOD	Amber/Red	29/02/2016	01/09/2021	Exempt	Exempt	Exempt	Exempt	Exempt			ICT	5.51				Not new	David Lynam	Sustain OFFICIAL and SECRET Information Communications and Technology (ICT) services in the Base and Base Overseas environments from the end of the ATLAS New Style of IT (Base) (NSOIT(B)) contract.
MOD_0115_1718-Q2	Mechanised Infantry Programme	AR 2020	1920-Q2	MOD	Amber	02/04/2018	31/12/2032	7.837	£8.16m	£0.32m	4%	4663.305			Military Capability	14.76				Not new	Simon Hamilton	Delivers agile Mechanised Infantry able to operate at reach, at speed, in complex terrain and with low logistic need.
MOD_0033_1112-Q1	MARSHALL	AR 2020	1920-Q2	MOD	Amber	03/04/2006	31/12/2024	127.259	£129.15m	£1.89m	1%	1335.622			Military Capability	18.76				Not new	Richard Barrow	Delivering a sustainable Air Traffic Management capability.
MOD_0036_1112-Q1	Maritime Sustainment Programme	AR 2020	1920-Q2	MOD	Green	25/07/2005	28/02/2019	0	£0.81m	£0.81m		618.808			Military Capability	13.61				Not new	D Lamb	The Military Afloat Reach and Sustainability (MARS) Tankers will replace the current single hulled tankers operated by the Royal Fleet Auxiliary.
MOD_0079_1213-Q1	Lightning Programme	AR 2020	1920-Q2	MOD	Amber	01/10/2001	31/03/2035	711.858	£750.37m	£38.51m	5%	10393.3			Military Capability	33.52				Not new	David Bradshaw	To deliver a multi-role, carrier-capable aircraft, to be operated jointly by the Royal Air Force and Royal Navy.
MOD_0111_1718-Q1	Joint Crypt Key Programme	AR 2020	1920-Q2	MOD	Exempt	Exempt	Exempt	Exempt	Exempt	Exempt	Exempt	Exempt			ICT	Exempt				Not new	David Lynam	To support the department's Information Assurance Capability.
MOD_0117_1718-Q2	Future Maritime Support Programme	AR 2020	1920-Q2	MOD	RED	26/09/2016	31/03/2030	14.478	£20.20m	£5.72m	39%	11127.659			Military Capability	13.52				Not new	Matthew Harrison	Commercial arrangements for the provision of Ship & Submarine Engineering and Naval Base Services.
MOD_0100_1516-Q1	Future Beyond Line Of Sight	AR 2020	1920-Q2	MOD	Amber/Red	01/01/2011	31/12/2041	Exempt	Exempt	Exempt	Exempt	Exempt			ICT	31.02				Not new	Stephen Fisher	Replaces the existing UK sovereign SKYNET 5 secure space-based satellite communications capability.
MOD_0116_1718-Q2	Fleet Solid Support	AR 2020	1920-Q2	MOD	Amber	01/04/2016	30/04/2030	0.657	£0.66m	£0.00m	0%	Exempt			Military Capability	14.09				Not new	Paul Marshall	Auxiliary Shipping to provide stores, ammunition and food sustainment to Naval Forces at Sea.
MOD_0080_1213-Q1	DREADNOUGHT	AR 2020	1920-Q2	MOD	Amber	14/04/2011	Exempt under Freedom of Information Act 2000 sections 24 (National Security) 26 (Defence) and 35 (Formulation of government policy).	1613.355	£1613.36m	£0.00m	0%	30099.344			Military Capability	Exempt				Not new	Timothy Hodgson	The design, development and manufacture of the Dreadnought ballistic missile submarines.
MOD_0114_1718-Q1	Defence Estate Optimisation	AR 2020	1920-Q2	MOD	Amber/Red	01/11/2016	31/03/2041	19.37	£11.75m	-£7.62m	-39%	1754.74			Military Capability	24.43				Not new	Sherin Aminossehe	Helping create a smaller, better and a more efficient estate to deliver the required Military Capability.
MOD_0017_1112-Q1	Crowsnest Programme	AR 2020	1920-Q2	MOD	Red	31/03/2013	30/06/2023	87.087	£75.24m	-£11.85m	-14%	429.434			Military Capability	10.25				Not new	Adrian Orchard	Equip 10 Merlin Mk2 helicopters with an advanced airborne surveillance system to meet the Force Protection requirement of the Maritime Task Group.
MOD_0078_1213-Q1	Core Production Capability	AR 2020	1920-Q2	MOD	Amber	01/04/2012	30/04/2028	163.577	£163.11m	-£0.47m	0%	1826.708			Military Capability	16.09				Not new	Tim Hodgson	Delivers safe nuclear reactor cores to meet the Royal Navy's submarine programme, now and for the long term.
MOD_0094_1415-Q3	Contracting; Purchasing and Finance	AR 2020	1920-Q2	MOD	Amber	01/12/2011	13/08/2021	4.97	£4.89m	-£0.08m	-2%	130.202			Government Transformation and Service Delivery	9.71				Not new	Lee Rimmer	To provide a single online end to end procurement system for all MOD procurement activity.
MOD_0077_1213-Q1	Complex Weapons	AR 2020	1920-Q2	MOD	Amber	31/03/2008	01/04/2032	755.261	£728.75m	-£26.51m	-4%	28717.221			Military Capability	24.02				Not new	John Cunningham	Delivers Complex Weapons for use by the 3 Front Line Commands.
MOD_0118_1718-Q3	Clyde Infrastructure	AR 2020	1920-Q2	MOD	Amber	07/09/2015	30/03/2032	112.7	£117.70m	£5.00m	4%	1774.573			Military Capability	16.57				Not new	Matt Harrison	Managing the design, delivery and transition into operational use, new build and updated infrastructure facilities in HMNB Clyde (Faslane and Coulport).
MOD_0064_1112-Q2	Carrier Enabled Power Projection	AR 2020	1920-Q2	MOD	Amber	31/01/2011	31/12/2030	1.782	£1.75m	-£0.03m	-2%	21.57			Military Capability	19.93				Not new	Richard Knighton	An integrated and sustainable joint capability, interoperable with NATO and coalition allies. The project will enable the projection of UK Carrier Strike and Littoral Manoeuvre power, the ability to support a Special Forces raid as well as delivering Humanitarian Assistance and Defence Diplomacy.
MOD_0076_1213-Q1	Astute Boats 1-7	AR 2020	1920-Q2	MOD	Amber/Red	Exempt	Exempt	467.432	£424.11m	-£43.32m	-9%	10769.423			Military Capability	Exempt				Not new	Tim Hodgson	The design, development and manufacture of Astute class submarines.
MOD_0085_1314-Q2	Army Basing Programme	AR 2020	1920-Q2	MOD	Amber/Green	22/05/2013	31/03/2021	307.953	£314.49m	£6.54m	2%	2270.791			Military Capability	7.86				Not new	David Southall	An infastructure led transformation programme to enable the Army 2020 structure and withdraw of personnel from Germany.
MOD_0092_1415-Q3	Armoured Infantry 2026	AR 2020	1920-Q2	MOD	Amber/Red	04/12/2014	31/12/2026	Exempt	Exempt	Exempt	Exempt	Exempt			Military Capability	12.08				Not new	Simon Hamilton	Deliver an Armoured Infantry that is more capable, with enhanced lethality and upgraded situational awareness, better integration with dismounts and improved combined arms cooperation.
MOD_0091_1415-Q3	Armoured Cavalry 2025	AR 2020	1920-Q2	MOD	Amber	04/12/2014	30/04/2025	694.712	£643.00m	-£51.71m	-7%	6288.95			Military Capability	10.41				Not new	Simon Hamilton	To deliver an integrated multi-role capability that will include the delivery of the AJAX armoured fighting vehicle and its training solution into service.
MOD_0119_1920-Q2	Armed Forces Recruitment Project	AR 2020	1920-Q2	MOD	Amber/Red	15/03/2018	01/02/2023	5.1	£5.10m	£0.00m	0%	1730.24			Military Capability	4.89				Joiner	Sharon Nesmith	The Armed Forces Recruiting Programme (AFRP) is the tri-Service (tS) programme responsible for delivering a single, common tS Recruiting Op Model for the Armed Forces.
MOD_0001_1112-Q1	A400M	AR 2020	1920-Q2	MOD	Amber	17/05/2000	31/03/2024	197.815	£186.19m	-£11.62m	-6%	3356.227			Military Capability	23.89				Not new	Simon EDWARDS	Delivery of A400M ATLAS Air Transport Aircraft.
MOD_0061_1112-Q1	WATCHKEEPER	AR 2020	1920-Q2	MOD	Amber/Green	01/03/1998	31/03/2021	0	£0.04m	£0.04m	-12%	1117.73			Military Capability	23.10				Not new	Michael Dooley	An unmanned air system (UAS) platform that will provide Intelligence, Surveillance, Target Acquisition and Reconnaissance capability to the land tactical commander in the context of Joint Operations.
MOD_0112_1718-Q1	Type 31e	AR 2020	1920-Q2	MOD	Amber	01/04/2016	28/02/2030	13.244	£12.76m	-£0.48m	-4%	Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests)			Military Capability	13.92				Not new	Paul Marshall	Aims to deliver a pipeline of credible, affordable and exportable warships enabling Defence to increase its global footprint.
MOD_0055_1112-Q1	Type 26 Global Combat Ship Programme	AR 2020	1920-Q2	MOD	Amber	21/07/2008	01/05/2035	502.376	£502.28m	-£0.10m	0%	Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests)			Military Capability	26.79				Not new	Paul Marshall	Procure 8 x Anti Submarine Warfare (ASW) ships and associated support.
MOD_0047_1112-Q1	Spearfish Upgrade Programme	AR 2020	1920-Q2	MOD	Red	01/04/2008	31/03/2024	37.678	£35.32m	-£2.36m	-6%	414.519			Military Capability	16.01				Not new	Bob Anstey	To update the UK's submarine weapon systems. This includes improvements to the safety system to minimise residual risks and deliver improved performance against increasingly capable threats.
MOD_0042_1112-Q1	Queen Elizabeth Programme	AR 2020	1920-Q2	MOD	Amber	01/12/1998	31/03/2023	141.625	£145.27m	£3.65m	3%	6782.651			Military Capability	24.35				Not new	Martin Connell	Deliver 2 x Queen Elizabeth Class aircraft carriers, capable of operating Lightning II and Merlin aircraft (Crowsnest/ASW), as key elements of the Carrier Enabled Power Projection Programme / (CEPP).
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	AR 2020	1920-Q2	MOD	Exempt	01/04/2008	30/04/2025	1087.997	£1028.69m	-£59.31m	-5%	20900.747			Military Capability	17.09				Not new	Paul Hollinshead	To deliver and sustain the capability (skills, technology, science, personnel, production and support) to underwrite the UK nuclear warhead stockpile now and in the future.
MoD_0109_1617-Q2	New Style of Information Technology Deployed	AR 2020	1920-Q2	MOD	Amber	01/04/2015	25/03/2025	Exempt	Exempt	Exempt	Exempt	Exempt			Military Capability	9.99				Not new	Andy Fallows	The provision of an IT system which will deliver operational information service to Land, Air, Maritime and Joint users in all physical environments.
MOD_0107_1617-Q1	PROTECTOR	AR 2020	1920-Q2	MOD	Amber	30/04/2009	31/03/2035	127.374	£140.35m	£12.98m	10%	1155.839			Military Capability	25.93				Not new	Richard Barrow	Delivery of a Remotely Piloted Air System.
MOD_0106_1617-Q1	Maritime Patrol Aircraft	AR 2020	1920-Q2	MOD	Amber	13/06/2016	01/04/2024	437.11	£513.47m	£76.36m	12%	2229.59			Military Capability	7.81				Not new	Richard Barrow	To deliver a Maritime Patrol Aircraft (MPA) to provide persistent, responsive, effective and adaptive Military Capabilities in the Under Water, Above Water, Littoral and Land environments.
MOD_0105_1617-Q1	Land Environment Tactical Communication and Information Systems	AR 2020	1920-Q2	MOD	Amber	16/10/2013	31/12/2035	235.382	£238.18m	£2.80m	1%	11399.76			Military Capability	22.22				Not new	Jonathan Cole	A transformational change programme that will 'information-enable' the Land Environment in the full conduct of operations.
MOD_0104_1617-Q1	Armour MBT 2025	AR 2020	1920-Q2	MOD	Amber	04/12/2014	31/07/2028	12.456	£11.95m	-£0.50m	-4%	1304.188			Military Capability	13.67				Not new	Andrew Stuart	An extension of the Armyâ€™s MBT capability as part of a balanced force, credible and employable against current and emerging threats, across the mosaic of conflict, and the identification of future capability options beyond 2035.
BEIS_0004_1920-Q2	Futured Shared Services Programme	AR 2020	1920-Q2	BEIS	Amber	01/11/2018	31/05/2023	32.24	£32.24m	£0.00m	0%	423.916			ICT	4.58				Joiner	Karl Hoods	The Future Shared Services Programme was initiated in 2018, the programme is born out of a need to replace the existing Oracle and Workday platforms
DECC_0010_1112-Q1	Smart Metering Implementation Programme	AR 2020	1920-Q2	BEIS	Amber	02/12/2009	31/12/2024	1065.903972	£1065.90m	£0.00m	0%	20136.95093			Infrastructure and Construction	15.09				Not new	Daron Walker	To offer every home and small business a Smart Meter by 2020.
BEIS_0003_1819-Q2	The Next Magnox Operating Model	AR 2020	1920-Q2	BEIS	Amber/Green	01/09/2017	01/09/2019	3	£3.00m	£0.00m	0%	5			Government Transformation and Service Delivery	2.00				Not new	Alan Cumming	Changing the model for delivery of decommissioning of the Magnox Sites from the current Parent Body Organisation (PBO) model to an NDA Subsidiary Model.
BIS_0014_1415-Q3	New Polar Research Vessel	AR 2020	1920-Q2	BEIS	Amber	01/05/2014	31/12/2022	68	£64.50m	-£3.50m	-5%	1403			Infrastructure and Construction	8.67				Not new	Nigel Bird	Royal Research Ship Sir David Attenborough will replace two existing polar research/supply vessels with one dual purpose ship which planned to save Â£102m over 30 years
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	AR 2020	1920-Q2	BEIS	Amber	03/04/2012	31/08/2019	198	£192.00m	-£6.00m	-3%	2782			Infrastructure and Construction	7.41				Not new	Alan Cumming	The appointment of a Parent Body Organisation to manage the Magnox and RSRL SLCs to deliver all twelve sites into Care and Maintenance, with a 10% saving, over a 14 year period. The contract has subsequently been terminated and will now deliver a series of Milestones and Termination States over a five year period ending September 2019.
BIS_0015_1516-Q1	Local Land Charges (LLC) Programme	AR 2020	1920-Q2	BEIS	Amber	01/03/2014	17/11/2023	32.5	£7.00m	-£25.50m	-78%	193.3			ICT	9.72				Not new	Karina Singh	The Programme will deliver a single Local Land Charges (LLC) Service for England.
BEIS_0001_1617-Q2	Heat Networks Investment Project	AR 2020	1920-Q2	BEIS	Amber	25/11/2015	31/03/2021	86.6	£66.90m	-£19.70m	-23%	375.9			Infrastructure and Construction	5.35				Not new	Dan Osgood	Helping create a self-sustaining heat network market through Â£320m capital investment and short-term actions to address market barriers
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	AR 2020	1920-Q2	BEIS	Amber	30/06/2008	31/12/2040	46.522	£46.52m	£0.00m	0%	12742.997			Infrastructure and Construction	32.53				Not new	Stephen Speed	To site and construct a Geological Disposal Facility for the disposal for higher activity radioactive waste.
CO_0022_1819-Q4	Transforming Government Security	AR 2020	1920-Q2	CO	Amber/Green	01/10/2016	01/04/2020	12.5	£12.50m	£0.00m	0%	31.044			Government Transformation and Service Delivery	3.50				Joiner	Michael Brennan	Improve security outcomes by raising minimum standards, provide clarity for security across HMG, provide governance and security leadership to enable a better understanding and management of the threats and risks to government and its assets.
CO_0014_1516-Q2	Government Hubs Programme	AR 2020	1920-Q2	CO	Amber	01/05/2015	31/03/2036	19.08	£19.08m	£0.00m	0%	564.1			Government Transformation and Service Delivery	20.93				Not new	Martin Sellar	The Government Hubs Programme will consolidate and modernise the government's office estate, creating an office network that supports smarter working and great places to work.
CO_0019_1617-Q4	Government as a Platform	AR 2020	1920-Q2	CO	Amber/Green	31/12/2015	31/03/2020	17	£12.00m	-£5.00m	-29%	90			ICT	4.25				Not new	Chris Russell	Development of common platforms for use by digital services across government to avoid duplication of effort.
CO_0015_1516-Q2	GOV UK Verify	AR 2020	1920-Q2	CO	Red	01/04/2012	31/03/2020	3	£17.90m	£14.90m	497%	206.1			ICT	8.00				Not new	Lisa Barrett	A new way to prove who you are online and for public service providers to be assured you are who you say you are
CO_0018_1617-Q3	Common Technology Services	AR 2020	1920-Q2	CO	Amber/Green	01/04/2016	31/03/2020	4.96	£1.30m	-£3.66m	-74%	44.19			Government Transformation and Service Delivery	4.00				Not new	Chris Russell	Enabling Government to transform the way Civil Servants work by supporting departments during the adoption of modern, flexible and secure technology that will increase their efficiency and deliver value for money.
CO_0020_1718-Q4	Commercial Capability Expansion Programme	AR 2020	1920-Q2	CO	Amber/Red	01/04/2017	31/03/2020	2.3	£3.13m	£0.83m	36%	11.7			Government Transformation and Service Delivery	3.00				Not new	Gareth Rhys Williams	Improve commercial capability across central government and the wider public bodies sector by expanding capability building interventions applied to commercial specialists (at Grade 6 and above) into new target populations.
CO_0023_1920-Q1	Transforming CCS	AR 2020	1920-Q2	CO	Amber	01/04/2019	31/03/2022	8.23	£7.85m	-£0.38m	-5%	28.34			Government Transformation and Service Delivery	3.00				Joiner	Simon Tse	The Transforming CCS programme will encompass both digital delivery and organisational transformation to deliver the transformation vision that will transition CCS into a digitally enabled organisation that puts the customer at the heart of everything it does.
DCMS_0014_1920-Q2	Rural Gigabit Connectivity Programme	AR 2020	1920-Q2	DCMS	Red	01/05/2019	01/05/2021	79.5	£41.06m	-£38.44m	-48%	212.8			Infrastructure and Construction	2.00				Joiner	Raj Kalia	The Rural Gigabit Connectivity Programme will pilot and test innovative approaches to deploying full fibre in the most difficult to reach areas where the market alone is unlikely to deliver.
DCMS_0012_1819-Q2	Birmingham 2022 Commonwealth Games	AR 2020	1920-Q2	DCMS	Amber/Red	21/12/2017	31/03/2023	63.363	£34.97m	-£28.39m	-45%	777.919			Infrastructure and Construction	5.28				Not new	Dean Creamer	Delivery of the Birmingham 2022 Commonwealth Games.
DCMS_0008_1516-Q4	Blythe House Programme	AR 2020	1920-Q2	DCMS	Amber/Green	01/04/2015	31/03/2023	77.7	£95.69m	£17.99m	23%	210.239			Infrastructure and Construction	8.00				Not new	Dean Creamer	Ensure Blythe House is put to its most efficient and effective use in order to deliver maximum value for money and that its museums are able to care for their collections in the most efficient and effective way.
DCMS_0011_1718-Q3	5G Testbeds & Trials	AR 2020	1920-Q2	DCMS	Amber	28/02/2017	31/03/2021	67.4	£37.70m	-£29.70m	-44%	232.75			Infrastructure and Construction	4.09				Not new	James Heath	To foster, build and lead the development of the UK's 5G ecosystem.
DCMS_0013_1819-Q3	4th National Lottery Licence Competition	AR 2020	1920-Q2	DCMS	Amber	16/11/2018	01/08/2023	7.84	£13.21m	£5.37m	68%	64.339			Government Transformation and Service Delivery	4.71				Joiner	John Tanner	The project aims to run a competition to award the next National Lottery licence (4th), that delivers statutory duties of due propriety and player protection, while incentivising responsible innovation and maximising returns to good causes.
DCMS_0010_1718-Q3	Local Full Fibre Networks	AR 2020	1920-Q2	DCMS	Red	01/04/2017	01/12/2021	132.4	£82.02m	-£50.38m	-38%	321.1			Infrastructure and Construction	4.67				Not new	Raj Kalia	Designed to stimulate greater commercial investment in full fibre networks across the UK to deliver faster and more reliable connectivity.
DCMS_0009_1516-Q4	700 MHz Clearance Programme	AR 2020	1920-Q2	DCMS	Amber/Green	13/01/2015	01/01/2022	156	£94.20m	-£61.80m	-40%	595			Infrastructure and Construction	6.97				Not new	Raj Kalia	Investing up to Â£600m to clear the 700MHz spectrum by mid-2020 for use for mobile broadband services in the future.
DEFRA_0006_1516-Q1	DEFRA UNITY PROGRAMME	AR 2020	1920-Q2	DEFRA	Amber	01/11/2014	30/04/2020	140.3	£142.70m	£2.40m	2%	1067.6			ICT	5.50				Not new	CHRIS HOWES	The Defra UnITy Programme has been established to exploit the opportunity presented from the expiry of its two largest ICTcontracts. The programme will now run until 04/2020 to develop a delivery mechanism leveraging good outcomes in a multi-vendor environment.
DFE_0011_1819-Q2	Social Work England	AR 2020	1920-Q2	DFE	Amber	09/05/2016	30/09/2019	6.591	£11.00m	£4.41m	67%	21.311			Government Transformation and Service Delivery	3.39				Not new	Sam Olsen	Establishing a new specialist social work regulator, Social Work England, which will focus on public protection and practice improvement.
DFE_0010_1819-Q1	T Level Programme	AR 2020	1920-Q2	DfE	Amber/Red	25/10/2016	30/09/2023	105.6	£123.60m	£18.00m	17%	155.6			Government Transformation and Service Delivery	6.93				Not new	Jennifer Coupland	To manage the development and delivery of new T Level qualifications, closure and benefit realisation
DFE_0012_1920-Q1	Test Operation Services Transition Programme (TOpS)	AR 2020	1920-Q2	DFE	Amber/Red	01/09/2018	30/03/2020	10.999	£11.14m	£0.14m	1%	125.609			Government Transformation and Service Delivery	1.58				Joiner	Una Bennett	Programme of work to move from a multi supplier model to a single supplier model
DFE_0006_1415-Q3	Priority School Building Programme 2	AR 2020	1920-Q2	DFE	Amber	01/05/2014	25/02/2025	740.8	£716.22m	-£24.58m	-3%	2398.5			Infrastructure and Construction	10.83				Not new	Rory Kennedy	Meeting the needs of the school buildings in the very worst condition across the country.
DFE_0009_1617-Q2	Apprenticeships Reform Programme	AR 2020	1920-Q2	DFE	Amber/Red	08/05/2015	01/04/2021	2470.01	£2183.00m	-£287.01m	-12%	11347.41			Government Transformation and Service Delivery	5.90				Not new	Keith Smith	To create more high quality apprenticeships, meet the skills needs of employers and the country, to create progression for apprentices and to widen participation and social mobility in apprenticeships.
DFID_0001_1112-Q1	St Helena Airport	AR 2020	1920-Q2	DFID	Amber/Green	15/03/2005	31/08/2026	3.9	£4.54m	£0.64m	16%	445.72			Infrastructure and Construction	21.48				Not new	Alasdair Wardhaugh
DFT_0001_1112-Q1	Crossrail Programme	AR 2020	1920-Q2	DFT	Red	22/07/2008		1137.7	£1131.20m	-£6.50m	-1%	17630.9			Infrastructure and Construction	Crossrail				Not new	Matthew Lodge	A new high-frequency rail service which will increase rail-based capacity in London by up to 10% and cut journey times across London and the South East.
DFT_0033_1819-Q1	East Coast Mainline Programme	AR 2020	1920-Q2	DFT	Amber	01/04/2014	01/12/2023	208.8	£166.70m	-£42.10m	-20%	1040.4			Infrastructure and Construction	9.67				Not new	Cavendish Elithorn	Improving capacity and frequency of the services on the East Coast Mainline, increasing passenger seat capacity to major stations along the route, reducing journey times and improving the customer experience through the introduction of new trains.
DFT_0026_1617-Q1	Great Western Route Modernisation (GWRM) including electrification	AR 2020	1920-Q2	DFT	Amber	01/12/2011	31/12/2024	289	£324.00m	£35.00m	12%	5007			Infrastructure and Construction	13.09				Not new	Matthew Lodge	An extensive programme to modernise existing infrastructure on the Great Western mainline. It will create faster and more reliable services, better stations and increased freight capacity.
DFT_0005_1112-Q1	Intercity Express Programme	AR 2020	1920-Q2	DFT	Amber	01/06/2005	04/06/2020	38.46	£38.11m	-£0.35m	-1%	6445.73			Infrastructure and Construction	15.02				Not new	Matthew Lodge	Renewing the UK's high speed train fleet on the Great Western and East Coast. Through Train Operating Companies IEP is a key means to deliver the passenger benefits including more capacity, improved reliability, reduced journey times, and better environmental performance.
DFT_0027_1617-Q1	Midland Main Line Programme	AR 2020	1920-Q2	DFT	Amber	01/01/2011	31/12/2024	299.3	£288.34m	-£10.96m	-4%	1671.2			Infrastructure and Construction	14.01				Not new	Cavendish Elithorn	Modernisation of the Midland Main Line Route to provide more passenger capacity and reduced journey times into London and between major Midland cities.
DFT_0028_1617-Q1	North of England Programme	AR 2020	1920-Q2	DFT	Amber/Red	23/07/2009	31/12/2022	753	£251.00m	-£502.00m	-67%	5849			Infrastructure and Construction	13.45				Not new	Cavendish Elithorn	The enhancements provided by the North of England Programme will support economic growth, bring improved journey times, offer additional train services and enable modern trains to run across the North.
DFT_0029_1617-Q1	South West Route Capacity	AR 2020	1920-Q2	DFT	Amber/Green	16/07/2012	31/12/2019	49.42	£34.16m	-£15.26m	-31%	817.7			Infrastructure and Construction	7.46				Not new	Matthew Lodge	Programme of infrastructure upgrades and new rolling stock to increase passenger capacity including enhancements works at Waterloo station.
DFT_0016_1112-Q1	Thameslink Programme	AR 2020	1920-Q2	DFT	Amber	01/07/2005	31/12/2026	84.1	£169.20m	£85.10m	101%	7269.4			Infrastructure and Construction	21.52				Not new	Matthew Lodge	A significantly enhanced high-frequency rail service which will increase rail-based capacity in London and across the wider South East and provide new journey opportunities.
DFT_0021_1314-Q3	Rail Franchising Programme	AR 2020	1920-Q2	DFT	Amber/Red	15/01/2015	14/09/2019	3.17	£2.12m	-£1.05m	-33%	24.47			Government Transformation and Service Delivery	4.67				Not new	Peter Wilkinson	To secure the provision of passenger rail services as set out under the Railways Act 1993 (as amended) by letting Rail Franchises.
DFT_0004_1112-Q1	High Speed Rail Programme (HS2)	AR 2020	1920-Q2	DFT	Red	14/01/2009	31/12/2033	3732.5	£2784.70m	-£947.80m		55700			Infrastructure and Construction	24.98				Not new	Clive Maxwell	HS2 will form the backbone of the UKâ€™s transport network, connecting eight out of ten of Britainâ€™s largest cities. By making it easier to move between the North, Midlands and South, cutting many journeys by half, HS2 will make it easier for people to live and work where they want.
DfT_0023_1516-Q3	Heathrow Expansion Programme	AR 2020	1920-Q2	DFT	Amber	01/07/2015	31/12/2050	9.38	£9.38m	-£0.01m	0%	32607.78			Infrastructure and Construction	35.53				Not new	Caroline Low	The Heathrow Expansion Programme covers the Government activities to enable delivery of a new Northwest runway at Heathrow Airport (subject to the granting of development consent).
DFT_0025_1617-Q1	East West Rail Programme (Western Section)	AR 2020	1920-Q2	DFT	Red	30/11/2011	30/06/2024	112.1	£100.00m	-£12.10m	-11%	1091.5			Infrastructure and Construction	12.59				Not new	Cavendish Elithorn	The programme will reconstruct and upgrade a partly disused railway between Bicester and Milton Keynes /Bedford allowing for the introduction of new passenger services improving connectivity and journey times along the corridor.
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	AR 2020	1920-Q2	DFT	Green	01/09/2012	30/09/2021	401	£323.20m	-£77.80m	-19%	1435.3			Infrastructure and Construction	9.08				Not new	Christopher Taylor	To improve the A14 which is a major national and inter-urban regional transport artery between Cambridge and Huntingdon to relieve congestion and support both national and regional economic growth.
DFT_0024_1516-Q4	A303 Amesbury to Berwick Down	AR 2020	1920-Q2	DFT	Amber	01/12/2014	01/06/2028	39.7	£39.70m	£0.00m	0%	1919.9			Infrastructure and Construction	13.51				Not new	Christopher Taylor	Freeflowing dual carriageway replacing the current single lane on the A303 between Amesbury and Berwick down including a twin bored tunnel under the majority of the world heritage site and a northern by-pass of Winterbourne Stoke.
DFT_0031_1819-Q1	A428 Black Cat to Caxton Gibbet	AR 2020	1920-Q2	DFT	Amber/Green	01/04/2015	01/04/2025	11.02	£19.30m	£8.28m	75%	809.98			Infrastructure and Construction	10.01				Not new	Christopher Taylor	The scheme provides a new off-line two lane dual carriageway between Black Cat roundabout on the A1 in Bedfordshire and Caxton Gibbet roundabout on the A428 in Cambridgeshire.
DFT_0034_1920-Q2	A12 Chelmsford to A120 Widening	AR 2020	1920-Q2	DfT	Amber	01/04/2015	01/05/2028	12.98	£12.98m	£0.00m	0%	1145.37			Infrastructure and Construction	13.09				Joiner	Dean Sporn	A12 Chelmsford to A120 Widening â€“ widening the A12 to three lanes between junction 19 (north of Chelmsford) and junction 25 (A120 interchange).
DfT_0022_1415-Q4	Lower Thames Crossing	AR 2020	1920-Q2	DFT	Amber	30/05/2014	31/07/2028	165	£165.00m	£0.00m	0%	6052.2			Infrastructure and Construction	14.18				Not new	christopher taylor	A new free-flowing road crossing of the Lower Thames east of Gravesend and Tilbury. It will improve network resilience and the performance of the existing crossings at Dartford enabling local regional and national economic growth.
DH_0063_1819-Q3	GP IT Futures Programme	AR 2020	1920-Q2	DH	Amber/Red	01/09/2016	31/03/2023	35.98699488	£50.95m	£14.97m	42%	423.0005205			ICT	6.58				Joiner	Masood Nazir	The GP IT Futures programme will deliver a new procurement framework, to replace the General Practice Systems of Choice (GPSoC) procurement framework. In so doing, it will create an open, competitive and innovative market with an ultimate goal to creating a world leading health ecosystem which will underpin the requirements set out in the NHS Long Term Plan.
DH_0017_1112-Q1	PHE Science Hub	AR 2020	1920-Q2	DH	Amber/Red	28/06/2013	30/06/2025	311.247	£188.94m	-£122.31m	-39%	2656.318			Infrastructure and Construction	12.01				Not new	Richard Gleave	To create an integrated national centre of excellence for public health science, to act as an enabling platform to ensure the scientific expert advice for protection of the publicâ€™s health against threats.
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	AR 2020	1920-Q2	DH	Amber/Red	01/01/2012	30/05/2018	48.4526	£66.61m	£18.16m	37%	1247.2397			Government Transformation and Service Delivery	6.41				Not new	Cathy Edwards	Develop NHS Proton Beam Therapy centres to treat patients for whom evidence supports proton therapy as the most clinically effective treatment.
DH_0060_1617-Q1	NHS UK	AR 2020	1920-Q2	DH	Amber	01/04/2016	31/12/2020	9.201	£8.62m	-£0.58m	-6%	54.954			Government Transformation and Service Delivery	4.75				Not new	Polly Bishop	Transforming the website NHS Choices, and designing a digital service that better connects patients to the information and services that they need.
DH_0046_1415-Q1	Medical Examiners Programme	AR 2020	1920-Q2	DH	Amber/Red	24/07/2007	30/09/2020	38	£38.00m	£0.00m	0%	68.4			Government Transformation and Service Delivery	13.20				Not new	Mark Davies	Introducing the role of medical examiners to provide a system of effective medical scrutiny applicable to all deaths that do not require a coronerâ€™s investigation.
DH_0062_1819-Q3	Local Health and Care Records	AR 2020	1920-Q2	DH	Amber	31/03/2018	31/03/2022	55.28	£28.83m	-£26.45m	-48%	763.93			ICT	4.00				Joiner	Tim Donohoe	The aim of the programme is to create an information sharing environment that helps our health and care services continually improve the treatments we use, that health and care professionals have access to a comprehensive care record with the information they need to inform their care decisions, when and where they need it, and can empower people to make informed choices about their own health and care. Being able to analyse the data to enable more precise and actionable interventions and support the development of population health management and access to a rich information base of de-personalised and anonymous information to support research into conditions, the development of new treatments, and pathways for care .
DH_0061_1617-Q3	IT Infrastructure Sourcing Programme	AR 2020	1920-Q2	DH	Red	01/12/2014	30/06/2019	19.4	£22.46m	£3.06m	16%	121.4			ICT	4.58				Not new	Nick O'Reilly	Implementing a mix of internal and external supplier towers and a strengthened retained IT organisation.
DH_0041_1314-Q2	Health & Social Care Network	AR 2020	1920-Q2	DH	Amber	29/03/2012	31/03/2021	75.53	£71.10m	-£4.43m	-6%	392.76			ICT	9.01				Not new	Tom Denwood	A key transitional stage in achieving the vision of making digital health and social care services ubiquitously available over the internet.
DH_0058_1516-Q4	Data Processing Services Programme	AR 2020	1920-Q2	DH	Amber	23/02/2015	31/03/2020	12.1123	£12.84m	£0.72m	6%	69.4975			ICT	5.10				Not new	Tim Donohoe	To deliver a modern data platform (DSP) to improve how NHS Digital manages, analyses and provides access to data for healthcare planning and research.
DH_0065_1819-Q4	Clinical Triage Platform (CTP)	AR 2020	1920-Q2	DH	Amber	01/04/2016	31/03/2021	9.71	£8.48m	-£1.23m	-13%	33.364			ICT	5.00				Joiner	Samit Shah	The programmeâ€™s overall aim is to support â€˜first contact resolutionâ€™, that is, to the greatest extent where we can, we should deal with the patientsâ€™ concern there and then, and ensure patients are treated by the most appropriate healthcare professionals in the most appropriate place for their needs.
DWP_0009_1112-Q1	Universal Credit Programme	AR 2020	1920-Q2	DWP	Amber	17/11/2011	31/12/2024	1059.9715	£1010.26m	-£49.71m	-5%	12716.9535			Government Transformation and Service Delivery	13.13				Not new	Neil Couling	Universal Credit replaces six separate benefits and tax credits for working age people, bringing together in and out of work systems into one, to make work pay.
DWP_0028_1819-Q3	Health Transformation Programme	AR 2020	1920-Q2	DWP	Red	28/03/2018	31/03/2024	87.516	£66.38m	-£21.13m	-24%	6598.7639			Government Transformation and Service Delivery	6.01				Joiner	James Bolton	To offer a more joined-up service to disabled people, the DWP Health Transformation Programme will be integrating the services that deliver PIP and Work Capability Assessments from 2021.nsform the health and disability services we provide for people with disabilities and health conditions.
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	AR 2020	1920-Q2	DWP	Amber/Green	02/04/2012	01/12/2020	99.6789191	£93.24m	-£6.44m	-6%	1219.849173			Government Transformation and Service Delivery	8.67				Not new	Bozena Hillyer	Delivers major transformational outcomes designed to ensure the department manages fraud, error and debt in a systematic way.
FCO_0012_1718-Q4	Atlas Programme (IPA ID 2410)	AR 2020	1920-Q2	FCO	Amber/Red	01/05/2016	31/10/2021	13.28113745	£13.28m	£0.00m	0%	93.82871458			ICT	5.50				Not new	Andrew Sanderson	To support the FCO's Diplomacy 20:20 agenda and the Government's shared services strategy through the implementation of a modern Oracle Cloud based Enterprise Resource Planning (ERP) system.
FCO_0010_1617-Q3	Echo 2 Programme	AR 2020	1920-Q2	FCO	Amber/Red	01/09/2015	30/09/2021	EXEMPt	EXEPT	-	0%	EXEMPT			ICT	6.08				Not new	Stephen Robbins	A joint initiative between DfID, FCO and the British Council to re-procure the current Connectivity and Voice & Video services, covering a network of over 500 offices in over 170 countries.
FCO_0011_1718-Q3	Washington Embassy Refurbishment	AR 2020	1920-Q2	FCO	Amber	01/01/2017	12/12/2022	8	£8.00m	£0.00m	0%	118.7			Infrastructure and Construction	5.95				Not new	Anthony Whitehead	Refurbishment and upgrading of key buildings on our Washington, USA, compound.
HO_0031_1415-Q1	Digital Services at the Border (DSAB)	AR 2020	1920-Q2	HO	Amber/Red	12/02/2014	31/03/2019	37.7	£37.70m	£0.00m	0%	452.1			ICT	5.13				Not new	John Gillan	To deliver digital services that will provide systems capable of transforming the way that Border Force (BF) and its partners operate.
HO_0029_1314-Q4	Immigration Platform Technologies (IPT)	AR 2020	1920-Q2	HO	Amber/Red	01/04/2013	30/09/2020	30	£44.34m	£14.34m	48%	304.95			ICT	7.50				Not new	Deborah Chittenden	Delivering the technology and information systems to support the immigration service now and in the future.
HO_0036_1617-Q2	National Law Enforcement Data Programme (NLEDP)	AR 2020	1920-Q2	HO	Amber/Red	01/04/2014	31/03/2023	67.5	£87.43m	£19.93m	30%	469.4			ICT	9.00				Not new	Stephen Webb	Will replace the current Police National Computer (PNC) and Police National Database (PND) systems with one modernised solution.
HO_0033_1415-Q3	Home Office Biometrics (HOB) Programme	AR 2020	1920-Q2	HO	Amber	01/04/2014	30/09/2021	85.56	£85.56m	£0.00m	0%	869.7			ICT	7.50				Not new	Stephen Webb	Home Office wide convergence programme for biometrics within Government, covering border security, law enforcement and intelligence.
HO_0034_1516-Q2	Cyclamen Project	AR 2020	1920-Q2	HO	Amber/Green	01/04/2014	31/03/2020	Exempt	Exempt	-	Exempt	Exempt			Government Transformation and Service Delivery	6.00				Not new	Paul Dean	Cyclamen equipment provides the capability to detect and intercept, and thereby deter the illicit movement of radiological materials into the United Kingdom.
HO_0037_1718-Q1	Asylum Accommodation and Support Transformation (AAST)	AR 2020	1920-Q2	HO	Amber/Green	29/08/2016	03/09/2019	328.58	£300.07m	-£28.51m	-9%	4605			Government Transformation and Service Delivery	3.01				Not new	Sean Palmer	Aims to deliver an asylum accommodation and support model which will ensure the safety and security of service users and their host communities and represents value for money for the UK Government, learning the lessons from previous asylum support contracts.
HO_0032_1415-Q1	Technology Platforms for Tomorrow (TPT)	AR 2020	1920-Q2	HO	Amber	01/02/2014	31/03/2019	69.97	£64.13m	-£5.84m	-8%	602.57			ICT	5.16				Not new	Peter Rose	Delivering modern End User Devices and collaboration tooling, replacing the Departmentâ€™s legacy application estate with the use of cloud services.
HO_0030_1415-Q1	Metis Programme	AR 2020	1920-Q2	HO	Amber/Red	01/09/2016	01/06/2019	53.3	£56.12m	£2.82m	5%	290.53			ICT	2.75				Not new	Richard Hornby	To move to an updated Enterprise Resource Planning tool (ERP) and a common shared service model to provide transactional human resource (HR), finance (including payroll) and procurement services
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	AR 2020	1920-Q2	HO	Amber/Red	01/06/2011	31/12/2022	816.9986525	£817.00m	£0.00m	0%	9521.916853			Infrastructure and Construction	11.59				Not new	Stephen Webb	Aims to replace the mobile communications service used by the three Emergency Services and other public safety users with an Emergency Services Network (ESN).
HO_0038_1819-Q3	DBS Service Transition	AR 2020	1920-Q2	HO	Amber/Green	01/08/2018	31/03/2021	23.12	£20.75m	-£2.37m	-10%	27.43			Government Transformation and Service Delivery	2.67				Joiner	Gary Blanchard	The DBS Service Transition Programme has been established to transfer services securely, and in doing so maintain the capability and capacity of DBS to achieve its core responsibilities.
MOJ_0044_1920-Q2	Prison Technology Transformation Programme (PTTP)	AR 2020	1920-Q2	MoJ	Amber/Red			0	£0.00m	£0.00m		0			ICT	0.00				Joiner	Adrian Scott	The programme has been commissioned to replace the common technology solution across all public prisons in England and Wales. It will also provide new technology services to HMPPS HQ and Prisons ( Staff/Users) who are still on the legacy â€œQuantumâ€ prison system. Providing staff across the prison service with modern, mobile technology services that are a pleasure to use, and which make their duties easier to perform.
MOJ_0038_1718-Q4	HMCTS Facilities Management Reprocurement Project (FMRP)	AR 2020	1920-Q2	MOJ	Amber	01/03/2017	31/12/2019	0	£6.38m	£6.38m		1039.53			Government Transformation and Service Delivery	2.84				Not new	Tim James	To re-procure replacement contracts for the expiring Total Facilities Management (TFM) contracts which provide services to the HMCTS estate.
MOJ_0040_1718-Q3	YOUTH JUSTICE REFORM PROGRAMME	AR 2020	1920-Q2	MOJ	Amber/Red	12/12/2016	31/12/2022	22.5	£18.90m	-£3.60m	-16%	345.08			Government Transformation and Service Delivery	6.05				Not new	Helga Swidenbank	To make youth custody a place of safety, both for children and those who work there; and to improve the life chances of children in custody.
MoJ_0045_1920-Q2	Wellingborough New Build Prison	AR 2020	1920-Q2	MoJ	Amber	17/08/2018	14/06/2022	189.6380078	£122.99m	-£66.65m	-35%	6316.014618			Infrastructure and Construction	3.83				Joiner	Robin Seaton	This project is to design, build and procure private services to operate a new, Category C resettlement prison at Wellingborough.
MOJ_0042_1819-Q2	Probation Programme	AR 2020	1920-Q2	MOJ	Amber/Red	01/10/2017	01/03/2020	617	£954.78m	£337.78m	55%	8235.2338			Government Transformation and Service Delivery	2.42				Not new	Jim Barton	Aims to open commercial discussions with Community Rehabilitation Companies (CRCs) , that run probation services, to agree an option for early termination of contracts by mutual agreement and negotiate amendments to contracts to secure service improvements during an exit period.
MOJ_0039_1718-Q3	Prison Education Programme	AR 2020	1920-Q2	MOJ	Green	01/04/2017	30/06/2019	156.5	£156.50m	£0.00m	0%	763.3			Government Transformation and Service Delivery	2.25				Not new	Adrian Scott	Provision of education services for adult prisons in England.
MOJ_0041_1819-Q1	Prisoner Escort and Custody Services (PECS) Generation 4 Programme	AR 2020	1920-Q2	MOJ	Amber/Green	01/04/2017	30/09/2020	8.14	£8.34m	£0.20m	2%	1635.83			Government Transformation and Service Delivery	3.50				Not new	Gary Badley	PECS Gen 4 Programme, procures business critical contracts ensuring the continued safe and decent movement of prisoners between police stations, courts & prisons.
MOJ_0032_1617-Q2	MoJ Future FM	AR 2020	1920-Q2	MOJ	Amber/Red	01/07/2016	01/04/2018	83.5	£74.30m	-£9.20m	-11%	430.2			Government Transformation and Service Delivery	1.75				Not new	Andy Mills	To re-procure the expiring facilities management contracts which provide services to the shared estates cluster.
MOJ_0028_1314-Q2	HMCTS Reform	AR 2020	1920-Q2	MOJ	Amber/Red	01/12/2015	31/12/2023	263.47	£244.25m	-£19.22m	-7%	2153.17			Government Transformation and Service Delivery	8.09				Not new	Susan Acland-Hood	Modernise the infrastructure and deliver a better and more flexible service to court users; modernise and transform courts and tribunal service to increase efficiency, improve service quality and reduce the cost to the tax payer.
MoJ_0043_1920-Q2	Glen Parva New Build Prison	AR 2020	1920-Q2	MoJ	Amber	31/01/2019	05/11/2023	16.03011018	£9.92m	-£6.11m	-38%	6104.77			Infrastructure and Construction	4.76				Joiner	Robin Seaton	This project is to design, build and procure private services to operate a new, Category C resettlement prison at Glen Parva.
MOJ_0003_1112-Q1	Electronic Monitoring	AR 2020	1920-Q2	MOJ	Amber/Red	10/05/2011	31/08/2024	70.1	£90.24m	£20.14m	29%	580.5			Government Transformation and Service Delivery	13.32				Not new	Adrian Scott	Implementing a new electronic monitoring system and a service for the day-to-day monitoring of subjects wearing the devices.
NCA_0001_1415-Q2	NCA Transformation Programme	AR 2020	1920-Q2	NCA	Amber	01/04/2014	31/03/2022	480.0614121	£480.06m	£0.00m	0%	5302.136668			Government Transformation and Service Delivery	8.00				Not new	Nina Cope	The NCA's Transformation Programme will deliver the culture, capability and capacity to enable the NCA to be a world-class law enforcement agency, leading the work to cut serious and organised crime.
ONS_0002_1112-Q1	Census & Data Collection Transformation Programme	AR 2020	1920-Q2	ONS	Amber	01/01/2015	31/03/2025	141.521	£141.52m	£0.00m	0%	905.591			Government Transformation and Service Delivery	10.25				Not new	Iain Moore McCormack Bell	Delivering a successful 2021 Census, researching how to make it the last of its kind and transforming the work of ONS in how we collect, process and analyse data.
HMRC_0012_1415-Q1	Tax Free Childcare	AR 2020	1920-Q2	HMRC	Amber	10/09/2013	01/12/2015	45.44	41.92	-£3.52m	-8%	356.87			Government Transformation and Service Delivery	2.22				Not new	Angela MacDonald	Responsible for delivering the childcare service through which parents can apply for Tax-Free Childcare and the DfE’s 30 hours free childcare initiative.
HMRC_0014_1415-Q4	Customs Declaration Services	AR 2020	1920-Q2	HMRC	Amber/Red	16/10/2013	31/12/2019	69.92	69.92	£0.00m	0%	334.14			ICT	6.21				Not new	Jim Harra	To provide a more flexible customs declaration system to meet future needs.
HMRC_0015_1617-Q1	Building Our Future Locations Programme	AR 2020	1920-Q2	HMRC	Amber/Green	05/01/2016	31/03/2026	387.7	348.3	-£39.40m	-10%	2835.9			Government Transformation and Service Delivery	10.24				Not new	Justin Holliday	HMRC will be a transformed organisation operating from 13 large, modern Regional Centres (RCs), 5 Specialist Sites and a London Headquarters equipped with the digital infrastructure and training facilities needed to support and motivate our people, and from which we can better serve our customers as an effective, efficient and impartial tax and payments authority.
HMRC_0020_1819-Q3	Securing our Technical Future	AR 2020	1920-Q2	HMRC	Amber	01/04/2018	30/06/2022	86.41	85.45	-£0.96m	-1%	312.06			ICT	4.25				Joiner	Denise Dourado	The SOTF Programme has been established to ‘stabilise’ HMRC's current estate which is aged and out of support as a result of limited on-going maintenance; remediating high priority vulnerabilities; exiting our 3 data centres the contracts for which expire in 2022. The programme will migrate all services within the data centres to the new supported platforms, Cloud and Crown Hosting (for physical assets), enabling HMRC to fully exploit the benefits of Cloud and Crown hosting opportunities.
HMRC_0017_1617-Q2	Making Tax Digital for Business	AR 2020	1920-Q2	HMRC	Amber/Green	01/04/2016	31/03/2024	75.26	78.96	£3.70m	5%	402.07			ICT	8.00				Not new	Ruth Stanier	Delivering modernised IT to digitise tax reporting for businesses and agents and delivering a better customer experience.

## Sheet2
GMPP ID Number	Project Name	Department	MPA RAG / (Departmental RAG used if MPA RAG missing)	Project - Start Date / (Latest Approved Start Date)	Project - End Date / (Latest Approved End Date)	FY Budget (£m) inc Non Gov	FY Forecast (£m) inc Non Gov	Budget Variance (£m)	Budget Variance (%)	TOTAL BUDGETED WHOLE LIFE COSTS including Non-Government Costs
MOD_0101_1516-Q1	New Style of Information Technology (Base)	MOD	Amber/Red	01/04/2015	31/03/2022	Exempt	Exempt	Exempt	Exempt	Exempt
MOD_0110_1718-Q1	MODnet Evolve	MOD	Amber/Red	29/02/2016	01/09/2021	Exempt	Exempt	Exempt	Exempt	Exempt
MOD_0115_1718-Q2	Mechanised Infantry Programme	MOD	Amber	02/04/2018	31/12/2032	7.837	£8.16m	£0.32m	4%	4663.305
MOD_0033_1112-Q1	MARSHALL	MOD	Amber	03/04/2006	31/12/2024	127.259	£129.15m	£1.89m	1%	1335.622
MOD_0036_1112-Q1	Maritime Sustainment Programme	MOD	Green	25/07/2005	28/02/2019	0	£0.81m	£0.81m		618.808
MOD_0079_1213-Q1	Lightning Programme	MOD	Amber	01/10/2001	31/03/2035	711.858	£750.37m	£38.51m	5%	10393.3
MOD_0111_1718-Q1	Joint Crypt Key Programme	MOD	Exempt	Exempt	Exempt	Exempt	Exempt	Exempt	Exempt	Exempt
MOD_0117_1718-Q2	Future Maritime Support Programme	MOD	RED	26/09/2016	31/03/2030	14.478	£20.20m	£5.72m	39%	11127.659
MOD_0100_1516-Q1	Future Beyond Line Of Sight	MOD	Amber/Red	01/01/2011	31/12/2041	Exempt	Exempt	Exempt	Exempt	Exempt
MOD_0116_1718-Q2	Fleet Solid Support	MOD	Amber	01/04/2016	30/04/2030	0.657	£0.66m	£0.00m	0%	Exempt
MOD_0080_1213-Q1	DREADNOUGHT	MOD	Amber	14/04/2011	Exempt under Freedom of Information Act 2000 sections 24 (National Security) 26 (Defence) and 35 (Formulation of government policy).	1613.355	£1613.36m	£0.00m	0%	30099.344
MOD_0114_1718-Q1	Defence Estate Optimisation	MOD	Amber/Red	01/11/2016	31/03/2041	19.37	£11.75m	-£7.62m	-39%	1754.74
MOD_0017_1112-Q1	Crowsnest Programme	MOD	Red	31/03/2013	30/06/2023	87.087	£75.24m	-£11.85m	-14%	429.434
MOD_0078_1213-Q1	Core Production Capability	MOD	Amber	01/04/2012	30/04/2028	163.577	£163.11m	-£0.47m	0%	1826.708
MOD_0094_1415-Q3	Contracting; Purchasing and Finance	MOD	Amber	01/12/2011	13/08/2021	4.97	£4.89m	-£0.08m	-2%	130.202
MOD_0077_1213-Q1	Complex Weapons	MOD	Amber	31/03/2008	01/04/2032	755.261	£728.75m	-£26.51m	-4%	28717.221
MOD_0118_1718-Q3	Clyde Infrastructure	MOD	Amber	07/09/2015	30/03/2032	112.7	£117.70m	£5.00m	4%	1774.573
MOD_0064_1112-Q2	Carrier Enabled Power Projection	MOD	Amber	31/01/2011	31/12/2030	1.782	£1.75m	-£0.03m	-2%	21.57
MOD_0076_1213-Q1	Astute Boats 1-7	MOD	Amber/Red	Exempt	Exempt	467.432	£424.11m	-£43.32m	-9%	10769.423
MOD_0085_1314-Q2	Army Basing Programme	MOD	Amber/Green	22/05/2013	31/03/2021	307.953	£314.49m	£6.54m	2%	2270.791
MOD_0092_1415-Q3	Armoured Infantry 2026	MOD	Amber/Red	04/12/2014	31/12/2026	Exempt	Exempt	Exempt	Exempt	Exempt
MOD_0091_1415-Q3	Armoured Cavalry 2025	MOD	Amber	04/12/2014	30/04/2025	694.712	£643.00m	-£51.71m	-7%	6288.95
MOD_0119_1920-Q2	Armed Forces Recruitment Project	MOD	Amber/Red	15/03/2018	01/02/2023	5.1	£5.10m	£0.00m	0%	1730.24
MOD_0001_1112-Q1	A400M	MOD	Amber	17/05/2000	31/03/2024	197.815	£186.19m	-£11.62m	-6%	3356.227
MOD_0061_1112-Q1	WATCHKEEPER	MOD	Amber/Green	01/03/1998	31/03/2021	0	£0.04m	£0.04m	-12%	1117.73
MOD_0112_1718-Q1	Type 31e	MOD	Amber	01/04/2016	28/02/2030	13.244	£12.76m	-£0.48m	-4%	Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests)
MOD_0055_1112-Q1	Type 26 Global Combat Ship Programme	MOD	Amber	21/07/2008	01/05/2035	502.376	£502.28m	-£0.10m	0%	Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests)
MOD_0047_1112-Q1	Spearfish Upgrade Programme	MOD	Red	01/04/2008	31/03/2024	37.678	£35.32m	-£2.36m	-6%	414.519
MOD_0042_1112-Q1	Queen Elizabeth Programme	MOD	Amber	01/12/1998	31/03/2023	141.625	£145.27m	£3.65m	3%	6782.651
MOD_0038_1112-Q1	Nuclear Warhead Capability Sustainment Programme	MOD	Exempt	01/04/2008	30/04/2025	1087.997	£1028.69m	-£59.31m	-5%	20900.747
MoD_0109_1617-Q2	New Style of Information Technology Deployed	MOD	Amber	01/04/2015	25/03/2025	Exempt	Exempt	Exempt	Exempt	Exempt
MOD_0107_1617-Q1	PROTECTOR	MOD	Amber	30/04/2009	31/03/2035	127.374	£140.35m	£12.98m	10%	1155.839
MOD_0106_1617-Q1	Maritime Patrol Aircraft	MOD	Amber	13/06/2016	01/04/2024	437.11	£513.47m	£76.36m	12%	2229.59
MOD_0105_1617-Q1	Land Environment Tactical Communication and Information Systems	MOD	Amber	16/10/2013	31/12/2035	235.382	£238.18m	£2.80m	1%	11399.76
MOD_0104_1617-Q1	Armour MBT 2025	MOD	Amber	04/12/2014	31/07/2028	12.456	£11.95m	-£0.50m	-4%	1304.188
BEIS_0004_1920-Q2	Futured Shared Services Programme	BEIS	Amber	01/11/2018	31/05/2023	32.24	£32.24m	£0.00m	0%	423.916
DECC_0010_1112-Q1	Smart Metering Implementation Programme	BEIS	Amber	02/12/2009	31/12/2024	1065.903972	£1065.90m	£0.00m	0%	20136.95093
BEIS_0003_1819-Q2	The Next Magnox Operating Model	BEIS	Amber/Green	01/09/2017	01/09/2019	3	£3.00m	£0.00m	0%	5
BIS_0014_1415-Q3	New Polar Research Vessel	BEIS	Amber	01/05/2014	31/12/2022	68	£64.50m	-£3.50m	-5%	1403
DECC_0013_1213-Q1	Magnox & RSRL PBO Competition	BEIS	Amber	03/04/2012	31/08/2019	198	£192.00m	-£6.00m	-3%	2782
BIS_0015_1516-Q1	Local Land Charges (LLC) Programme	BEIS	Amber	01/03/2014	17/11/2023	32.5	£7.00m	-£25.50m	-78%	193.3
BEIS_0001_1617-Q2	Heat Networks Investment Project	BEIS	Amber	25/11/2015	31/03/2021	86.6	£66.90m	-£19.70m	-23%	375.9
DECC_0005_1112-Q1	Geological Disposal Facility Programme (GDF)	BEIS	Amber	30/06/2008	31/12/2040	46.522	£46.52m	£0.00m	0%	12742.997
CO_0022_1819-Q4	Transforming Government Security	CO	Amber/Green	01/10/2016	01/04/2020	12.5	£12.50m	£0.00m	0%	31.044
CO_0014_1516-Q2	Government Hubs Programme	CO	Amber	01/05/2015	31/03/2036	19.08	£19.08m	£0.00m	0%	564.1
CO_0019_1617-Q4	Government as a Platform	CO	Amber/Green	31/12/2015	31/03/2020	17	£12.00m	-£5.00m	-29%	90
CO_0015_1516-Q2	GOV UK Verify	CO	Red	01/04/2012	31/03/2020	3	£17.90m	£14.90m	497%	206.1
CO_0018_1617-Q3	Common Technology Services	CO	Amber/Green	01/04/2016	31/03/2020	4.96	£1.30m	-£3.66m	-74%	44.19
CO_0020_1718-Q4	Commercial Capability Expansion Programme	CO	Amber/Red	01/04/2017	31/03/2020	2.3	£3.13m	£0.83m	36%	11.7
CO_0023_1920-Q1	Transforming CCS	CO	Amber	01/04/2019	31/03/2022	8.23	£7.85m	-£0.38m	-5%	28.34
DCMS_0014_1920-Q2	Rural Gigabit Connectivity Programme	DCMS	Red	01/05/2019	01/05/2021	79.5	£41.06m	-£38.44m	-48%	212.8
DCMS_0012_1819-Q2	Birmingham 2022 Commonwealth Games	DCMS	Amber/Red	21/12/2017	31/03/2023	63.363	£34.97m	-£28.39m	-45%	777.919
DCMS_0008_1516-Q4	Blythe House Programme	DCMS	Amber/Green	01/04/2015	31/03/2023	77.7	£95.69m	£17.99m	23%	210.239
DCMS_0011_1718-Q3	5G Testbeds & Trials	DCMS	Amber	28/02/2017	31/03/2021	67.4	£37.70m	-£29.70m	-44%	232.75
DCMS_0013_1819-Q3	4th National Lottery Licence Competition	DCMS	Amber	16/11/2018	01/08/2023	7.84	£13.21m	£5.37m	68%	64.339
DCMS_0010_1718-Q3	Local Full Fibre Networks	DCMS	Red	01/04/2017	01/12/2021	132.4	£82.02m	-£50.38m	-38%	321.1
DCMS_0009_1516-Q4	700 MHz Clearance Programme	DCMS	Amber/Green	13/01/2015	01/01/2022	156	£94.20m	-£61.80m	-40%	595
DEFRA_0006_1516-Q1	DEFRA UNITY PROGRAMME	DEFRA	Amber	01/11/2014	30/04/2020	140.3	£142.70m	£2.40m	2%	1067.6
DFE_0011_1819-Q2	Social Work England	DFE	Amber	09/05/2016	30/09/2019	6.591	£11.00m	£4.41m	67%	21.311
DFE_0010_1819-Q1	T Level Programme	DfE	Amber/Red	25/10/2016	30/09/2023	105.6	£123.60m	£18.00m	17%	155.6
DFE_0012_1920-Q1	Test Operation Services Transition Programme (TOpS)	DFE	Amber/Red	01/09/2018	30/03/2020	10.999	£11.14m	£0.14m	1%	125.609
DFE_0006_1415-Q3	Priority School Building Programme 2	DFE	Amber	01/05/2014	25/02/2025	740.8	£716.22m	-£24.58m	-3%	2398.5
DFE_0009_1617-Q2	Apprenticeships Reform Programme	DFE	Amber/Red	08/05/2015	01/04/2021	2470.01	£2183.00m	-£287.01m	-12%	11347.41
DFID_0001_1112-Q1	St Helena Airport	DFID	Amber/Green	15/03/2005	31/08/2026	3.9	£4.54m	£0.64m	16%	445.72
DFT_0001_1112-Q1	Crossrail Programme	DFT	Red	22/07/2008		1137.7	£1131.20m	-£6.50m	-1%	17630.9
DFT_0033_1819-Q1	East Coast Mainline Programme	DFT	Amber	01/04/2014	01/12/2023	208.8	£166.70m	-£42.10m	-20%	1040.4
DFT_0026_1617-Q1	Great Western Route Modernisation (GWRM) including electrification	DFT	Amber	01/12/2011	31/12/2024	289	£324.00m	£35.00m	12%	5007
DFT_0005_1112-Q1	Intercity Express Programme	DFT	Amber	01/06/2005	04/06/2020	38.46	£38.11m	-£0.35m	-1%	6445.73
DFT_0027_1617-Q1	Midland Main Line Programme	DFT	Amber	01/01/2011	31/12/2024	299.3	£288.34m	-£10.96m	-4%	1671.2
DFT_0028_1617-Q1	North of England Programme	DFT	Amber/Red	23/07/2009	31/12/2022	753	£251.00m	-£502.00m	-67%	5849
DFT_0029_1617-Q1	South West Route Capacity	DFT	Amber/Green	16/07/2012	31/12/2019	49.42	£34.16m	-£15.26m	-31%	817.7
DFT_0016_1112-Q1	Thameslink Programme	DFT	Amber	01/07/2005	31/12/2026	84.1	£169.20m	£85.10m	101%	7269.4
DFT_0021_1314-Q3	Rail Franchising Programme	DFT	Amber/Red	15/01/2015	14/09/2019	3.17	£2.12m	-£1.05m	-33%	24.47
DFT_0004_1112-Q1	High Speed Rail Programme (HS2)	DFT	Red	14/01/2009	31/12/2033	3732.5	£2784.70m	-£947.80m		55700
DfT_0023_1516-Q3	Heathrow Expansion Programme	DFT	Amber	01/07/2015	31/12/2050	9.38	£9.38m	-£0.01m	0%	32607.78
DFT_0025_1617-Q1	East West Rail Programme (Western Section)	DFT	Red	30/11/2011	30/06/2024	112.1	£100.00m	-£12.10m	-11%	1091.5
DFT_0020_1314-Q2	A14 Cambridge to Huntingdon Improvement Scheme	DFT	Green	01/09/2012	30/09/2021	401	£323.20m	-£77.80m	-19%	1435.3
DFT_0024_1516-Q4	A303 Amesbury to Berwick Down	DFT	Amber	01/12/2014	01/06/2028	39.7	£39.70m	£0.00m	0%	1919.9
DFT_0031_1819-Q1	A428 Black Cat to Caxton Gibbet	DFT	Amber/Green	01/04/2015	01/04/2025	11.02	£19.30m	£8.28m	75%	809.98
DFT_0034_1920-Q2	A12 Chelmsford to A120 Widening	DfT	Amber	01/04/2015	01/05/2028	12.98	£12.98m	£0.00m	0%	1145.37
DfT_0022_1415-Q4	Lower Thames Crossing	DFT	Amber	30/05/2014	31/07/2028	165	£165.00m	£0.00m	0%	6052.2
DH_0063_1819-Q3	GP IT Futures Programme	DH	Amber/Red	01/09/2016	31/03/2023	35.98699488	£50.95m	£14.97m	42%	423.0005205
DH_0017_1112-Q1	PHE Science Hub	DH	Amber/Red	28/06/2013	30/06/2025	311.247	£188.94m	-£122.31m	-39%	2656.318
DH_0031_1314-Q1	National Proton Beam Therapy (PBT) Service Development Programme	DH	Amber/Red	01/01/2012	30/05/2018	48.4526	£66.61m	£18.16m	37%	1247.2397
DH_0060_1617-Q1	NHS UK	DH	Amber	01/04/2016	31/12/2020	9.201	£8.62m	-£0.58m	-6%	54.954
DH_0046_1415-Q1	Medical Examiners Programme	DH	Amber/Red	24/07/2007	30/09/2020	38	£38.00m	£0.00m	0%	68.4
DH_0062_1819-Q3	Local Health and Care Records	DH	Amber	31/03/2018	31/03/2022	55.28	£28.83m	-£26.45m	-48%	763.93
DH_0061_1617-Q3	IT Infrastructure Sourcing Programme	DH	Red	01/12/2014	30/06/2019	19.4	£22.46m	£3.06m	16%	121.4
DH_0041_1314-Q2	Health & Social Care Network	DH	Amber	29/03/2012	31/03/2021	75.53	£71.10m	-£4.43m	-6%	392.76
DH_0058_1516-Q4	Data Processing Services Programme	DH	Amber	23/02/2015	31/03/2020	12.1123	£12.84m	£0.72m	6%	69.4975
DH_0065_1819-Q4	Clinical Triage Platform (CTP)	DH	Amber	01/04/2016	31/03/2021	9.71	£8.48m	-£1.23m	-13%	33.364
DWP_0009_1112-Q1	Universal Credit Programme	DWP	Amber	17/11/2011	31/12/2024	1059.9715	£1010.26m	-£49.71m	-5%	12716.9535
DWP_0028_1819-Q3	Health Transformation Programme	DWP	Red	28/03/2018	31/03/2024	87.516	£66.38m	-£21.13m	-24%	6598.7639
DWP_0016_1213-Q2	Fraud, Error and Debt Programme	DWP	Amber/Green	02/04/2012	01/12/2020	99.6789191	£93.24m	-£6.44m	-6%	1219.849173
FCO_0012_1718-Q4	Atlas Programme (IPA ID 2410)	FCO	Amber/Red	01/05/2016	31/10/2021	13.28113745	£13.28m	£0.00m	0%	93.82871458
FCO_0010_1617-Q3	Echo 2 Programme	FCO	Amber/Red	01/09/2015	30/09/2021	EXEMPt	EXEPT	-	0%	EXEMPT
FCO_0011_1718-Q3	Washington Embassy Refurbishment	FCO	Amber	01/01/2017	12/12/2022	8	£8.00m	£0.00m	0%	118.7
HO_0031_1415-Q1	Digital Services at the Border (DSAB)	HO	Amber/Red	12/02/2014	31/03/2019	37.7	£37.70m	£0.00m	0%	452.1
HO_0029_1314-Q4	Immigration Platform Technologies (IPT)	HO	Amber/Red	01/04/2013	30/09/2020	30	£44.34m	£14.34m	48%	304.95
HO_0036_1617-Q2	National Law Enforcement Data Programme (NLEDP)	HO	Amber/Red	01/04/2014	31/03/2023	67.5	£87.43m	£19.93m	30%	469.4
HO_0033_1415-Q3	Home Office Biometrics (HOB) Programme	HO	Amber	01/04/2014	30/09/2021	85.56	£85.56m	£0.00m	0%	869.7
HO_0034_1516-Q2	Cyclamen Project	HO	Amber/Green	01/04/2014	31/03/2020	Exempt	Exempt	-	Exempt	Exempt
HO_0037_1718-Q1	Asylum Accommodation and Support Transformation (AAST)	HO	Amber/Green	29/08/2016	03/09/2019	328.58	£300.07m	-£28.51m	-9%	4605
HO_0032_1415-Q1	Technology Platforms for Tomorrow (TPT)	HO	Amber	01/02/2014	31/03/2019	69.97	£64.13m	-£5.84m	-8%	602.57
HO_0030_1415-Q1	Metis Programme	HO	Amber/Red	01/09/2016	01/06/2019	53.3	£56.12m	£2.82m	5%	290.53
HO_0016_1213-Q1	Emergency Services Mobile Communications Programme (ESMCP)	HO	Amber/Red	01/06/2011	31/12/2022	816.9986525	£817.00m	£0.00m	0%	9521.916853
HO_0038_1819-Q3	DBS Service Transition	HO	Amber/Green	01/08/2018	31/03/2021	23.12	£20.75m	-£2.37m	-10%	27.43
MOJ_0044_1920-Q2	Prison Technology Transformation Programme (PTTP)	MoJ	Amber/Red			0	£0.00m	£0.00m		0
MOJ_0038_1718-Q4	HMCTS Facilities Management Reprocurement Project (FMRP)	MOJ	Amber	01/03/2017	31/12/2019	0	£6.38m	£6.38m		1039.53
MOJ_0040_1718-Q3	YOUTH JUSTICE REFORM PROGRAMME	MOJ	Amber/Red	12/12/2016	31/12/2022	22.5	£18.90m	-£3.60m	-16%	345.08
MoJ_0045_1920-Q2	Wellingborough New Build Prison	MoJ	Amber	17/08/2018	14/06/2022	189.6380078	£122.99m	-£66.65m	-35%	6316.014618
MOJ_0042_1819-Q2	Probation Programme	MOJ	Amber/Red	01/10/2017	01/03/2020	617	£954.78m	£337.78m	55%	8235.2338
MOJ_0039_1718-Q3	Prison Education Programme	MOJ	Green	01/04/2017	30/06/2019	156.5	£156.50m	£0.00m	0%	763.3
MOJ_0041_1819-Q1	Prisoner Escort and Custody Services (PECS) Generation 4 Programme	MOJ	Amber/Green	01/04/2017	30/09/2020	8.14	£8.34m	£0.20m	2%	1635.83
MOJ_0032_1617-Q2	MoJ Future FM	MOJ	Amber/Red	01/07/2016	01/04/2018	83.5	£74.30m	-£9.20m	-11%	430.2
MOJ_0028_1314-Q2	HMCTS Reform	MOJ	Amber/Red	01/12/2015	31/12/2023	263.47	£244.25m	-£19.22m	-7%	2153.17
MoJ_0043_1920-Q2	Glen Parva New Build Prison	MoJ	Amber	31/01/2019	05/11/2023	16.03011018	£9.92m	-£6.11m	-38%	6104.77
MOJ_0003_1112-Q1	Electronic Monitoring	MOJ	Amber/Red	10/05/2011	31/08/2024	70.1	£90.24m	£20.14m	29%	580.5
NCA_0001_1415-Q2	NCA Transformation Programme	NCA	Amber	01/04/2014	31/03/2022	480.0614121	£480.06m	£0.00m	0%	5302.136668
ONS_0002_1112-Q1	Census & Data Collection Transformation Programme	ONS	Amber	01/01/2015	31/03/2025	141.521	£141.52m	£0.00m	0%	905.591
HMRC_0012_1415-Q1	Tax Free Childcare	HMRC	Amber	10/09/2013	01/12/2015	45.44	£41.92m	-£3.52m	-8%	356.87
HMRC_0014_1415-Q4	Customs Declaration Services	HMRC	Amber/Red	16/10/2013	31/12/2019	69.92	£69.92m	£0.00m	0%	334.14
HMRC_0015_1617-Q1	Building Our Future Locations Programme	HMRC	Amber/Green	05/01/2016	31/03/2026	387.7	£348.30m	-£39.40m	-10%	2835.9
HMRC_0020_1819-Q3	Securing our Technical Future	HMRC	Amber	01/04/2018	30/06/2022	86.41	£85.45m	-£0.96m	-1%	312.06
HMRC_0017_1617-Q2	Making Tax Digital for Business	HMRC	Amber/Green	01/04/2016	31/03/2024	75.26	£78.96m	£3.70m	5%	402.07

## DHSC
GMPP ID Number	DH_0065_1819-Q4	DH_0058_1516-Q4	DH_0063_1819-Q3	DH_0041_1314-Q2	DH_0061_1617-Q3	DH_0062_1819-Q3	DH_0046_1415-Q1	DH_0031_1314-Q1	DH_0060_1617-Q1	DH_0017_1112-Q1
Project Name	Clinical Triage Platform (CTP)	Data Processing Services Programme	GP IT Futures Programme	Health & Social Care Network	IT Infrastructure Sourcing Programme	Local Health and Care Records	Medical Examiners Programme	National Proton Beam Therapy (PBT) Service Development Programme	NHS UK	PHE Science Hub
Department	DHSC	DHSC	DHSC	DHSC	DHSC	DHSC	DHSC	DHSC	DHSC	DHSC
Description / Aims	The programme's overall aim is to support first contact resolution, that is, to the greatest extent where we can, we should deal with the patients concern there and then, and ensure patients are treated by the most appropriate healthcare professionals in the most appropriate place for their needs.	To deliver a modern data platform (DSP) to improve how NHS Digital manages, analyses and provides access to data for healthcare planning and research.	The GP IT Futures programme will deliver a new procurement framework, to replace the General Practice Systems of Choice (GPSoC) procurement framework. In so doing, it will create an open, competitive and innovative market with an ultimate goal to creating a world leading health ecosystem which will underpin the requirements set out in the NHS Long Term Plan.	A key transitional stage in achieving the vision of making digital health and social care services ubiquitously available over the internet.	Implementing a mix of internal and external supplier towers and a strengthened retained IT organisation.	The aim of the programme is to create an information sharing environment that helps our health and care services continually improve the treatments we use, that health and care professionals have access to a comprehensive care record with the information they need to inform their care decisions, when and where they need it, and can empower people to make informed choices about their own health and care. Being able to analyse the data to enable more precise and actionable interventions and support the development of population health management and access to a rich information base of de-personalised and anonymous information to support research into conditions, the development of new treatments, and pathways for care .	Introducing the role of medical examiners to provide a system of effective medical scrutiny applicable to all deaths that do not require a coroner's investigation.	Develop NHS Proton Beam Therapy centres to treat patients for whom evidence supports proton therapy as the most clinically effective treatment.	Transforming the website NHS Choices, and designing a digital service that better connects patients to the information and services that they need.	To create an integrated national centre of excellence for public health science, to act as an enabling platform to ensure the scientific expert advice for protection of the public's health against threats.
IPA Delivery Confidence Assessment / (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the IPA Annual Report on Major Projects)	Amber	Amber	Amber/Red	Amber	Red	Amber	Amber/Red	Amber/Red	Amber	Amber/Red
Departmental commentary on actions planned or taken on the IPA RAG rating.	Provision of narrative not possible due to prioritisation of Covid 19 response	The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber, which has not changed since last year’s Q2 1819 Amber, due primarily to the following factors; / - The Amber DCA rating at Q2 1819 was in line with an external Gateway 3 review at FBC stage in May 2018. The DCA remained Amber at Q2 1920 to reflect the risks at the early stage of delivery of the Data Processing Services, following FBC approval in May 2019.	The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, due primarily to the following factors; / - The time remaining in which to start, progress and / or, as applicable, complete: user engagement; to complete the contingency plans for the exit of one or more GPSoC Core suppliers from the market; to support an unknown number of new entrants to the framework; to implement the TOM, to get a robust baseline and approach for the benefits case; to hold the Red Lines on the framework; to keep to the current milestones for the FBC; to get funding for the affordability gap in the FBC. / - The resource available to the programme with which to start, progress and / or, as applicable, complete: user engagement; to complete the contingency plans for the exit of one or more GPSoC Core suppliers from the market; to deal speedily with an unknown number of new entrants to the framework; to resource the Target Operating Model. / Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; / - There have been no non-project operating environment activities that have impacted the DCA. / Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; / - A greater than anticipated number of suppliers submitted a compliant bid to deliver services through the new framework. This resulted in a greater number of solutions needing to be assessed and assured by the programme. / - The process of assessing and assuring suppliers' solutions as being compliant against the terms of the new framework was more complicated and time consuming than expected. This resulted in the end to end duration of each solutions' assessment and assurance journey taking longer than planned, impact the timescales in which Phase 1 transition activities could be completed.	The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber, which has improved since last year’s Q2 1819 Amber/Red, due primarily to the following factors; / - The significant progress made in migrating organisations onto new HSCN services, and decommissioning legacy connectivity. Migration pace had increased considerably leading to the programme setting a stretch target of 50% completion by 31st December 2020, which demonstrated the increased level of confidence in programme team capability, leadership, and ability to work productively with suppliers. / - Increased engagement with NHS England at regional level, and this has helped influence customer behaviours in order to increase pace of migrations / - Continued validation that HSCN is delivering best value connectivity in comparison to the wider market, and is on average 74% cheaper than legacy N3 connectivity (on a like for like basis) / Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; / - Levers and interventions have seen an increased growth in migration rates, however since the COVID-19 outbreak there has been a slight dip in migration progress. Migration to HSCN is however seen as an essential step for organisations to ensure improved and increased bandwidth during this time / Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; / - The programme team continue to drive all parties to accelerate the pace of migration: as of end March 2020, 75% of the legacy Transition Network was ceased, an increase of 40% since September 2019. We have also seen a peak of surplus 1000 migrations taking place within a single month. / - As a result of increased engagement, NHS England now play a more active role at regional level, taking ownership to influence customer behaviours across STP’s to help drive migration pace more effectively, and HSCN Programme Board membership now includes regional NHS England digital transformation leads. / - A tail management strategy including tactical solutions, migration acceleration support and BT interim solutions are in place to drive an August 2020 completion, supporting customers at risk of not migrating by August. The programme have also successfully negotiated a Year 4 extension to the Transition Network providing contingency to March 2021.	The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Red, which has declined since last year’s Q2 1819 Amber/Red, due primarily to the following factors; / - Delays in delivering data centre network connectivity which was postponed by the supplier first from 30th June to 31st August and then from August to December (note these were completed in December) meant we needed to do a full re-plan.. / - The data centre connectivity was a critical path without which other elements of the programme except for the transfer of end user computing could not proceed; however due to the ongoing lack of progress with the data centre our Quarter 2 submission reflected the week on week delay and not a full project re-plan / Since the Q2 1920 (30th September 2019) Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; / - The data centre delays were escalated both at Chief Executive Level and using the crown rep covering this supplier on a number of occasions, finally leading to some progress and new management oversight by the supplier. / Since the Q2 1920 (30th September 2019) Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; / - The data centre connections were delivered in December; following which a revised plan was agreed with all suppliers. / - Data network migration has been completed at 9 out of 12 sites and was on target to complete for mid April but due to Covid 19 this has been suspended / - The transfer of end user computing was completed in October 2019 and the first two planned application group migrations have both been completed on target with no issues; we plan to continue with some of these despite the Covid 19 pandemic as they can be carried out remotely	The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber, due primarily to the following factors; / - Senior leadership change and programme looking for new SRO and Programme Director in midst of reprioritisation exercise / - Programme is complex and ambitions and several risks exist around indirectly enabling the maturity and capability of local delivery. / Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; / - NHSX has continued development including impact of the NHS England Joint Working Programme consultation exercise which delayed introduction of a new operating model and recruitment of new staff / Since the Q2 1920 (30th September 2019) Amber IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; / - SRO role taken on an interim basis by member of the NHSX Senior Leadership Team / - Programme Director has yet to be appointed	Provision of narrative not possible due to prioritisation of Covid 19 response	The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, which has declined since last year’s Q2 1819 Amber, due primarily to the following factors; / - Water penetration at UCLH site on level B5, this required remedial action. / - Cyclotron cooling was delayed by technical issues, this in turn delayed "beam on". / Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; / - Remedial work to address the water penetration at the UCLH site. / - Specialist cryogenics team was secured and the cyclotron cooling completed.	Provision of narrative not possible due to prioritisation of Covid 19 response	The IPA Delivery Confidence Assessment (DCA) rating at Q2 1920 (30th September 2019) was Amber/Red, which has declined since last year’s Q2 1819 Amber, due primarily to the following factors; / - Capital cost assurance on the RIBA3 construction design identified significant cost pressures against the existing baseline. As at Q2 2019/20 the full implications of changes had not been resolved and significant work was still needed to re-assess the scale and profile of investment. / - Proposals from construction partners and cost professionals identified the need to revise and extend the programme schedule. This is to reflect additional phases of design; the complexity of the required construction; updated market intelligence and the need to re-align organisational transformation. / Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following non-project operating environment activities have impacted the original Q2 IPA DCA; / - With the advent of a new parliament, uncertainty in the timing and nature of the Spending Review planning process decreases confidence in the schedule for PBC approval. / Since the Q2 1920 (30th September 2019) Amber/Red IPA DCA, the following primary project actions have impacted the original Q2 IPA DCA; / - Additional residual cost and schedule movements driven directly by: construction design and planning; scope changes and refinements; and returns from early works tenders. Changes have been included in the draft PBC. / - Focussed efforts to develop business design and transition planning, in line with revised construction plans, such as the work on the Target Operating Model to ensure alignment of language and approach with the Future Operating Model (FOM)
Project - Start Date / (Latest Approved Start Date)	01/04/2016	23/02/2015	01/09/2016	29/03/2012	01/12/2014	31/03/2018	24/07/2007	01/01/2012	01/04/2016	28/06/2013
Project - End Date / (Latest Approved End Date)	31/03/2021	31/03/2020	31/03/2023	31/03/2021	30/06/2019	31/03/2022	30/09/2020	30/05/2018	31/12/2020	30/06/2025
Departmental narrative on schedule, including any deviation from planned schedule (if necessary)	Provision of narrative not possible due to prioritisation of Covid 19 response	The scheduled baseline project end date at Q2 1920 (30th September 2019) is 31/03/20, has not changed since last year's Q2 1819 date of 31/03/20, due primarily to the following factors; / - The baseline end date at Q2 1819 and Q2 1920 was 31/03/20, in line with the FBC.	The scheduled project end date at Q2 1920 (30th September 2019) is 31/03/23, due primarily to the following factors; / - There are currently no factors which are impacting the programme end date	The scheduled baseline project end date at Q2 1920 (30th September 2019) is 31/03/21, has not changed since last year's Q2 1819 date of 31/03/21, due primarily to the following factors; / - There has been no change to the baseline project end date primarily due to the fact that migration pace has been increasing month on month, with the programme still aiming to complete migrations by the externally published deadline of August 2020 (however the programme team continues to work on the basis that there will be a tail of migrations beyond this date). / Since the Q2 1920 (30th September 2019) baseline project end date of 31/03/21, the following non-project operating environment activities have impacted the original Q2 baseline project end date; / - There has been no change to the baseline project end date, however we are starting to see a negative impact on migrations following the COVID-19 outbreak. Despite this, HSCN is still an essential step for organisations to secure improved connectivity and therefore see no change to the baseline end date / Since the Q2 1920 (30th September 2019) baseline project end date of 31/03/21, the following primary project actions have impacted the original Q2 baseline project end date; / - There has been no change in programme scheduling, however a tail management strategy is in place which will help support those organisations most at risk of not migrating by August 2020 / - The signed Transition Network Year 4 extension also provides additional contingency to support the baseline project end date.	The scheduled baseline project end date at Q2 1920 (30th September 2019) is 30/06/19, has shortened by 184 days since last year's Q2 1819 date of 31/12/19, due primarily to the following factors; / - The scheduled baseline project end date had moved out to 31/3/20 to reflect the delays caused by the non delivery of the network to the agreed timetable. Provisional replanning in Q3, and reported in the Q3 report, moved the end date out to 30/10/2020; until the Covid 19 pandemic struck we were on target to achieve this revised date; we are exploring what can continue and what may be possible to reschedule to avoid further delays / - The delays required extensive replanning of the dependent elements of the programme. Every opportunity has been taken to mitigate the impact and re-ordering of work has been done with the other suppliers and within the NHSBSA business taking into account business critical processing including year end financial processes. / - Reports were provided to the DHSC Investment committee in November and January and as requested an addendum was prepared for the March 2020 investment committee. / Since the Q2 1920 (30th September 2019) baseline project end date of 30/06/19, the following non-project operating environment activities have impacted the original Q2 baseline project end date; / - The Programme has increased the frequency of all supplier meetings which now take place every week and have allowed for better supplier collaboration. This increases the programmes confidence and overall assurance in the delivery to the revised plan. / Since the Q2 1920 (30th September 2019) baseline project end date of 30/06/19, the following primary project actions have impacted the original Q2 baseline project end date; / - Escalation and involvement of both the Crown Rep Team and BSA Chief Executive to Managing Director level communications had a major impact and these handshakes are continuing until delivery of the end to end data network / - The revised plan agreed with all suppliers has been reviewed every week and to late March, when the Covid 19 pandemic began to impact, all delivery milestones on this revised plan had been achieved at that point	The scheduled project end date at Q2 1920 (30th September 2019) is 31/03/22, due primarily to the following factors; / - National deployment plan still envisages completion by that date / - Contingency built into initial timetable	Provision of narrative not possible due to prioritisation of Covid 19 response	The scheduled baseline project end date at Q2 1920 (30th September 2019) is 30/05/18, has not changed since last year's Q2 1819 date of 30/05/18, due primarily to the following factors; / - UCLH currently remain on track to open the centre to patients in 2020. / - The potential impact of changes to the schedule caused by water ingress and/or cyclotron cooling is still being assessed. / Since the Q2 1920 (30th September 2019) baseline project end date of 30/05/18, the following primary project actions have impacted the original Q2 baseline project end date; / - Mitigations are in place to address the water penetration. / - Updated milestone dates will be agreed and UCLH will provide NHS England with an updated programme plan.	Provision of narrative not possible due to prioritisation of Covid 19 response	The scheduled baseline project end date at Q2 1920 (30th September 2019) is 30/06/25, has lengthened by 181 days since last year's Q2 1819 date of 31/12/24, due primarily to the following factors; / - Construction design changes as a result of value management, value engineering, stakeholder needs and user-led requirements have affected the timelines of the programme. / - Robust challenge to our partners over declared durations and schedule risk allowances have affected the start of RIBA 4 (technical design) stage. / Since the Q2 1920 (30th September 2019) baseline project end date of 30/06/25, the following non-project operating environment activities have impacted the original Q2 baseline project end date; / - With the advent of a new parliament, uncertainty in the timing and nature of the Spending Review planning process decreases confidence in the schedule for PBC approval. / Since the Q2 1920 (30th September 2019) baseline project end date of 30/06/25, the following primary project actions have impacted the original Q2 baseline project end date; / - Pending changes (such as site-wide electrical supply and resilience requirements) will have a significant impact on the programme schedule / - Additional residual cost and schedule movements driven directly by: construction design and planning; scope changes and refinements; and returns from early works tenders. Changes have been included in the draft PBC.
Financial Year Baseline (£m) (including Non-Government Costs)	£9.71	£12.11	£35.99	£75.53	£19.40	£55.28	£38.00	£48.45	£9.20	£311.25
Financial Year Forecast (£m) (including Non-Government Costs)	£8.48	£12.84	£50.95	£71.10	£22.46	£28.83	£38.00	£66.61	£8.62	£188.94
Financial Year Variance (%)	-13%	6%	42%	-6%	16%	-48%	0%	37%	-6%	-39%
TOTAL Baseline Whole Life Costs (£m) (including Non-Government Costs)	£33.36	£69.50	£423.00	£392.76	£121.40	£763.93	£68.40	£1,247.24	£54.95	£2,656.32
Departmental narrative on budget/forecast variance for 2018/19 / (if variance is more than 5%)	Provision of narrative not possible due to prioritisation of Covid 19 response	The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of 6%, is due primarily to the following factors; / - At Q2 1920, there was an increase of £0.7m due to additional planned development work on the Data Processing Services.	The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of 42%, is due primarily to the following factors; / - Additional programme spend to complete procurement and deliver against the Secretary of State tech vision. Note that these were all reflected in the programme's Full Business Case which was approves by HMT and Cabinet Office in October 2019. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 42%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; / - There has been no non-project operating environment impact to the Q2 1920 baseline / forecast variance of 42%. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 42%, the following primary project actions have impacted the original Q2 19/20 in-year variance; / - There has been no further project operating environment impacts to the Q2 1920 baseline / forecast variance of 42%.	The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -6%, is due primarily to the following factors; / - A forecast underspend in 19/20 allowed HSCN to participate in the NHS Digital / NHS England Prioritisation exercise. HSCN funds were identified to be returned centrally to NHS Digital, in order to support cost pressures and fund other essential programmes and delivery for the wider organisation. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -6%, the following primary project actions have impacted the original Q2 19/20 in-year variance; / - The In-year forecast for Q3 increased by £3.3m, on account of monies provided by NHS Digital centrally for the Internet First initiative, a child item of the HSCN Programme / - The In-year forecast for Q4 reduced by £3.5m revenue (largely due to savings made centrally and then distributed locally to NHS England to support migration acceleration). / £1.9m capital was also released to other programmes within NHSD as part of the funding received for the Internet First initiative from NHSD centrally in Q3.	The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of 16%, is due primarily to the following factors; / - Spend totals forecast increased by £3.22m as a result of £0.6m supplier costs slipping into 2019/20 and increased costs from the incumbent for Transition Services, new suppliers for additional works required as a result of Virgin delays and additional resources required to run Programme for a longer period. / - Recurring new costs for new services have fallen as a result of not being able to bill the new suppliers because of delays on implementation of the Networks. One-off costs have increased for Exit charges from the incumbent as well as additional dual running costs. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 16%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; / - Incumbent supplier costs have increased as the NHSBSA has grown and taken on more services, this has impacted the cost of dual running with the incumbent. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 16%, the following primary project actions have impacted the original Q2 19/20 in-year variance; / - Spend totals forecast increased by £3.22m as a result of £0.6m supplier costs slipping into 2019/20 and increased costs from the incumbent for Transition Services, new suppliers for additional works required as a result of Virgin delays and additional resources required to run Programme for a longer period. / - Recurring new costs for new services have fallen as a result of not being able to bill the new suppliers because of delays on implementation of the Networks. One-off costs have increased for Exit charges from the incumbent as well as additional dual running costs.	The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -48%, is due primarily to the following factors; / - Delay in local programme mobilisation. / - Delay in national programme business case approval / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -48%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; / - NHSX recruitment progressed and new roles being taken up. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -48%, the following primary project actions have impacted the original Q2 19/20 in-year variance; / - Local programmes established across 12 out of 13 localities. / - Each local programme now has formal Funding Agreement in place with NHS England	Provision of narrative not possible due to prioritisation of Covid 19 response	The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of 37%, is due primarily to the following factors; / - Due to the reprofiling of capital works, in year the programme is over budget by £36.6m. At the end of 2018/19 the capital programme was underspent by £28.8m. This leaves the position as the end of 2019/20 as £7.9m overspent / - The recurring costs of the programme are £17.8m under budget in 19/20. This is because the service at UCLH has yet to commence. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 37%, the following non-project operating environment activities have impacted the original Q2 19/20 in-year baseline / forecast variance; / - The building works at UCLH are continuing based on the revised plan. / - UCLH continue to work on their ramp up for staffing. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of 37%, the following primary project actions have impacted the original Q2 19/20 in-year variance; / - The building works at UCLH are continuing based on the revised plan. / - UCLH continue to work on their ramp up for staffing.	Provision of narrative not possible due to prioritisation of Covid 19 response	The 19/20 in-year baseline / forecast variance at Q2 1920 (30th September 2019) of -39%, is due primarily to the following factors; / - Schedule delay due to in flight value engineering activities / - Reprofiled schedule has moved budgeted spend into future years. / Since the Q2 1920 (30th September 2019) 19/20 in-year baseline / forecast variance of -39%, the following primary project actions have impacted the original Q2 19/20 in-year variance; / - Continuing value engineering and risk profiling activities / - Schedule reprofiling activities moving funding requirements into future years
Departmental Narrative on Budgeted Whole Life Costs	Provision of narrative not possible due to prioritisation of Covid 19 response	The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £69.50 m, has decreased by £5.75 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £75.25 m, due primarily to the following factors; / - The Q2 1819 baseline cost is from the approved OBC, whereas the Q2 19/20 baseline cost is from the approved FBC and therefore reflects a later estimate of scope and costs.	The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £423.00 m, due primarily to the following factors; / - There are currently no factors which are impacting the programme whole life costs	The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £392.76 m, has not changed since last year's Q2 1819 (£m) baseline Whole Life Cost of £392.76 m, due primarily to the following factors; / - No change in programme budget. Forecast programme expenditure also remains within the FBC envelope. / Since the Q2 1920 (30th September 2019) £392.76 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; / - No change in programme budget. Forecast programme expenditure also remains within the FBC envelope.	The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £121.40 m, has decreased by £8.10 m since last year's Q2 1819 (£m) baseline Whole Life Cost of £129.50 m, due primarily to the following factors; / - Spend totals forecast increased as a result of £0.6m supplier costs slipping into 2019/20 and increased costs from the incumbent for Transition Services, new suppliers for additional works required as a result of Virgin delays and additional resources required to run Programme for a longer period. / - Recurring new costs for new services have fallen as a result of not being able to bill the new suppliers because of delays on implementation of the Networks. One-off costs have increased for Exit charges from the incumbent as well as additional dual running costs. / Since the Q2 1920 (30th September 2019) £121.40 m baseline Whole Life Cost, the following non-project operating environment activities have impacted the original baseline Q2 Whole Life Cost; / - Incumbent supplier costs have increased as the NHSBSA has grown and taken on more services, this has impacted the cost of dual running with the incumbent. / Since the Q2 1920 (30th September 2019) £121.40 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; / - Spend totals forecast increased as a result of £0.6m supplier costs slipping into 2019/20 and increased costs from the incumbent for Transition Services, new suppliers for additional works required as a result of Virgin delays and additional resources required to run Programme for a longer period. / - Recurring new costs for new services have fallen as a result of not being able to bill the new suppliers because of delays on implementation of the Networks. One-off costs have increased for Exit charges from the incumbent as well as additional dual running costs.	The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £763.93 m, due primarily to the following factors; / - Still as per Programme Business Case	Provision of narrative not possible due to prioritisation of Covid 19 response	The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £1,247.24 m, has not changed since last year's Q2 1819 (£m) baseline Whole Life Cost of £1,247.24 m, due primarily to the following factors; / - As the plan doesn’t change these comments are based on actuals. Between 2018/19 and 2019/20 the forecast outturn for the programme has reduced by £8.2m. This is due the actual costs of the service at The Christie in year being lower than the original plan. / - The capital forecast remained the same between the two years. / Since the Q2 1920 (30th September 2019) £1,247.24 m baseline Whole Life Cost, the following non-project operating environment activities have impacted the original baseline Q2 Whole Life Cost; / - Nothing external to the projects is impacting on costs. / Since the Q2 1920 (30th September 2019) £1,247.24 m baseline Whole Life Cost, the following primary project actions have impacted the original Q2 baseline Whole Life Cost; / - As the service is now live at The Christie we are now seeing real costs.	Provision of narrative not possible due to prioritisation of Covid 19 response	The baseline Whole Life Cost at Q2 1920 (30th September 2019) is £2,656.32 m, has not changed since last year's Q2 1819 (£m) baseline Whole Life Cost of £2,656.32 m, due primarily to the following factors; / - Construction design changes, value engineering activities and re-profiling of schedule and risk have been reflected in draft PBC but WLC will not be updated until re-baselining.
Annual Report Category	ICT	ICT	ICT	ICT	ICT	ICT	Government Transformation and Service Delivery	Government Transformation and Service Delivery	Government Transformation and Service Delivery	Infrastructure and Construction
The IPA Annual Report publishes the whole life cycle costs on projects, based on figures from their Business Cases, whilst the National Infrastructure and Construction Pipeline (NICP) focuses primarily on the upfront capital investment on a project. Where both documents refer to the same projects, this distinction will be the principal reason for any differences in the data sets published. Other government publications may use different methodologies to derive cost figures

## 'file:///C:/Data%20Team/GEMS%20Reports%20&%20Master%20Spreadsheet/Master%20Spreadsheet/Blank%20sheet%20V5.xlsx'#Sheet2
1. Governance		1.1 Robust Governance Structures & Processes
2. Stakeholder Management		1.2 Commitment & Engagement
3. Programme and Project Management		1.3 Approvals
4. Change Management & Transition		2.1 Engagement Strategy & Planning
5. Financial Planning and Management		2.2 Effective Engagement
6. Benefits Management and Realisation		2.3 Effective Across Organisational Boundaries
7. Commercial Strategy & Management		3.1 Planning
8. Context, Aim & Scope		3.2 Controls
9. Risk, Issues & Dependancy Management		3.3 Change Control
10. Resource & Skills Management		3.4 Quality Management
11. Knowledge Management		3.5 Information Management
12. Technology		3.6 Communications
		3.7 Methodology & Standards
		3.8 Requirements Definition
		4.1 Organisational Culture
		4.2 Organisational Capability
		4.3 Operational Readiness
		4.4 Customer Engagement
		7. 1 Sourcing Strategy
		7.2 Contract Management
		7.3 Supply Chain Management
		8.1 Vision, Aim & Objectives
		8.2 Scope
		8.3 Business Case
		8.4 Alignment of Delivery to Policy
		8.5 Critical Success Factors
		9.1 Robust Framework & Process
		9.2 Active Risk Mangement
		9.3 Contingency Planning
		10.1 Leadership and Capability
		10.2 Capacity Planning & Management
		10.3 Skills Assessment & Management
		10.4 Succession Planning & Management
		10.5 Organisation
		11.1 Best Pracitce
		11.2 Lessons Learnt
		12.1 Alignment to Strategy
		12.2 Integration
		12.3 Operational Readiness
		12.4 Not Used
		12.5 Security
		All

## 'file:///C:/Users/sebastien.polis/Desktop/Printing%20Spreadsheet%2020150209%20-%20test.xlsx'#Drop_down_list
1 Governance
2 Stakeholder Management
3 Programme and Project Management
4 Change Management and Transition
5 Financial Planning and Management
6 Benefits Management and Transition
7 Commercial Strategy and Management
8 Context, Aim & Scope
9 Risk, Issue & Dependency Management
10 Resource and Skills Management
11 Knowledge Management
12 Technology
13 Interfaces
14 Other

1.1 Robust Governance Structures & Processes
1.2 Commitment & Engagement
1.3 Approvals
2.1 Engagement Strategy & Planning
2.2 Effective Engagement
2.3 Effective across Organisational Boundaries
3.1 Planning
3.2 Controls
3.3 Change Control
3.4 Quality Management
3.5 Information Management
3.6 Communications
3.7 Methodology & Standards
3.8 Requirements Definition
4.1 Organisational Culture
4.2 Organisational Capability
4.3 Operational Readiness
4.4 Customer Engagement
7.1 Sourcing Strategy
7.2 Contract Management
7.3 Supply Chain Management
8.1 Vision, Aims & Objectives
8.2 Scope
8.3 Business Case
8.4 Alignment of Delivery to Policy
8.5 Critical Success Factors
9.1 Robust Framework & Process
9.2 Active Risk Management
9.3 Contingency Planning
10.1 Leadership Capability
10.2 Capacity Planning & Management
10.3 Skills Assessment & Management
10.4 Succession Planning & Management
10.5 Organisation
11.1 Best Practice
11.2 Lessons Learnt
12.1 Alignment to Strategy
12.2 Integration
12.3 Operational Readiness
12.4 Not Used
12.5 Security