ACTIVITY BASED BUDGETING

Activity-Based Budgeting (ABB) is a financial management tool that profiles the component costs of project activities against a timeline. By planning activities in this way an ABB can be used to assess:

- when activities will take place and the FCO becomes liable for payment
- whether all component costs of an activity have been considered
- what the total outcome cost of an activity is likely to be
- whether activities are affordable and good value for money

The ABB is also a useful tool for:

- planning and monitoring the financial performance and actual progress of a project
- assessing the impact on a project if adjustments are made to any of the three key project implementation factors (Purpose, Money and Time)

Please note that an ABB must be provided for each project proposal, attached as a separate annex.

Examples

Example 1: The following table is not an ABB. It provides little useful information about how the proposed project budget will be spent. There is no breakdown of costs within each Expenditure Category and no timeline to show when costs will be incurred or which particular activity they are assigned to. As such it is not possible to assess the cost of individual activities or whether the budget is realistic, justifiable or value for money.
Expenditure Category		Total Cost (CZK)
Personnel		11075
Travel		9000
Accommodation & Subsistence		6000
Capital		20000
Monitoring and Evaluation		1600
Admin/Mgt		9425
Other		9800
	66900

Example 2:
The following table is better. Although lacking any time-based considerations it does provide some insights into the component parts of each activity, namely, what they are and how much they will cost. It shows individual and comparative costs for each activity, allowing Project Teams to assess whether funds are being appropriately assigned. It can be used as a stepping stone towards a fully developed ABB.

Activity	Components	Total Cost (CZK)	Sub-Totals (CZK)		%age
Visit to UK by 8 Scientists	Flights	7,200	11,280		27%
	Subsistence	1,200
	Hotels	2,880
Develop written recommendations and methodology for local implementation, arising from visit	Scientists’ Fees	12,000	12,400		30%
	Books, materials and printing	400
Training on the Recommendations arising from the Visit / (4 x half-day training)	Venue and Catering	5,000	5,630		13%
	Trainer’s Fees	400
	Materials	230
Follow-up Training – Review Action Plan Implementation / (4 x one-day training)	Venue and Catering	4,000	5,030		12%
	Trainer’s Fees	800
	Materials	230
Project Management	Project Manager	3,500	4,500		11%
	Secretary	1,000
Evaluation	Local consultant fees	2,500	2,850		7%
	Travel costs	350
TOTAL		41,690	41,690		100%

(Please note: The yellow column on the right hand side of this table shows a breakdown of the sub-totals into percentages of the overall project cost (CZK 41,690). This is not included in the standard FCO form, but it is a useful method for identifying whether activities are providing good or poor value for money. For example, Evaluation costs at 7% and Project Management costs at 11% would be considered too high. This sort of calculation can help assess Value for Money).

Point to consider: Project Relationships

Although the Activity Based Budget in Example 2 links Money to the Project Purpose (via Activities, and therefore the anticipated Outputs from those Activities) it does not go far enough in relating the Money or Purpose to the Time of implementation.

Figure 2.1
Key Project Factors - “The Project Triangle”

# Purpose

Ac

##### Project

##### Management

Activity Based Budget

# Time
# Money

What we now need to know is

- When will activities take place (in order to achieve the project outputs and purpose)?
- When will the FCO become liable for payment (so project / programme expenditure can be profiled / tracked efficiently)?

The following examples illustrate how these questions can be answered using simple a GANNT chart.
Example 3:

Activities can now be assigned a date along a timeline to show when they will occur using a simple GANNT chart.

Example 3 identifies blocks of activities against particular months. This can be further broken down to show more detail e.g. more rows can be added under each activity in order to list all key tasks needed to achieve that activity, and more columns can be added to break down months into weeks and even days for tasks and activities that are time critical. The amount of detail shown depends on the timeline and complexity of the project and activities.

Activity	October	November	December	January	February	March
Visit to UK by 8 Scientists
Develop written recommendations and methodology for local implementation, arising from visit
Training on the Recommendations arising from the Visit / (4 x half-day training)
Follow-up Training – Review Action Plan Implementation / (4 x one-day training)
Project Management
Evaluation

Figures from Example 2 can now be transferred into Example 3, adding additional rows and columns as necessary.

Due to Resource Accounting principles, the FCO is liable for payment once an activity has taken place. Therefore, activity costs listed in a GANNT chart need to reflect the timing of the activity, not when payment will be made (actual payments may occur before or after the activity itself is completed).

See Example 4 below for a complete ABB.
Example 4: An Activity Based Budget

Activity	Details	April	May	June	July	August	September	October	November	Totals
Visit to UK by 8 Scientists	Flights-Economy		CZK 7,200							CZK 11,280
	Subsistence		CZK 1,200
	Hotels		CZK 2,880
Develop written recommendations and methodology for local implementation, arising from visit	Scientists’ Fees			CZK 12,000						CZK 12,400
	Books, mat. & printing			CZK 400
Training on the Recommendations arising from the Visit (4 x half-day training)	Venue & Catering				CZK 5,000					CZK 5,630
	Trainers’ Fees				CZK 400
	Materials				CZK 230
Follow-up Training – Review Action Plan Implementation (4 x one-day training)	Venue & Catering						CZK 4,000			CZK 5,030
	Trainers’ Fees						CZK 800
	Materials						CZK 230
Project Management	Project Manager		CZK 700	CZK 700	CZK 700	CZK 700	CZK 700			CZK 4,500
	Secretary		CZK 200	CZK 200	CZK 200	CZK 200	CZK 200
Evaluation	Local consultants’ fees							CZK 2,500		CZK 2,850
	Travel costs							CZK 350
Totals		CZK 0	CZK 12,180	CZK 13,300	CZK 6,530	CZK 900	CZK 5,930	CZK 2,850	CZK 0	CZK 41,690

This Example provides the minimum level of detail needed for Programme Teams to assess value for money, per activity, for this project.

Benefits of an ABB

A well drafted ABB can be used to:

Assess the quality of project planning, e.g. (list not exhaustive)...
- Has the implementer included the right range of activities that will achieve the project Outputs?
- Does the timeline meet overall project and programme schedule requirements? Is it realistic and achievable?
- Has the implementer considered the 3 key project management factors of Purpose, Money and Time?

Evaluate the costs of activities, linking value with the Project Outputs and Purpose and the wider strategic objectives of the Programme...
- Have the activities been properly costed?
- Are they necessary to achieve the Outputs and Purpose?
- Are they good value for money?

Identify waste and poor value in budgets, and respond to it...
- Are component costs realistic? Have any costs been duplicated or inflated?
- Are any component costs unnecessary?
- Might there be opportunities to reduce costs through synergies with other activities?

Profile the timing and value of project spend...
Is the payment schedule correct / realistic?
- When will payments be made?
- When and how much funding is required to make those payments?

Identify activity workload and any pressure points...
Is the implementer being under/over ambitious with its proposed range/timing of activities?
- Does the implementer have enough / the right resources to deliver the activities?
- Should activities be scheduled differently to e.g. avoid overload and work within an implementers available resources?

Correctly receipt activity on PRISM...
Following FCO Resource Accounting principles, when should activities be receipted on PRISM? (Activities should be receipted on PRISM once they have taken place. Do not wait for the implementer to submit an invoice).

The ABB as a Project Management tool

 An ABB is also an effective Project Management tool. For example, it can be used to

- Assess actual progress of a project against the forecast time line and costs
- Set milestones, identify project-critical events (i.e. those events that are essential for a project to proceed to the next stage) and agree key dates with an implementer and the Programme Teams for reviewing progress and submitting reports
- Highlight risks (allowing for early mitigation of those risks), as well as possibly indicate potential fraud (refer to separate guidance on Fraud and Programme Budgets on the SPF SharePoint site)
- Help clarify the range and level of interest of project stakeholders
- Manage and assess a project against the three key factors of Purpose, Money and Time (see Figure 2.1), including early indications of over / under spends (to aid decisions about requesting additional funds or returning unused funds)

An ABB is a key project management tool and a good investment of time.

Value for Money (VFM)

Always consider VFM when assessing and monitoring ABBs (refer to separate VFM guidance on the SPF SharePoint site).

In particular...

Flight Costs - look carefully at proposed flight costs, in particular at class of travel which should at the very least be commensurate with FCO travel policies (i.e. no business class travel for flights under 10 hours)

Per Diems – these should not be paid as an advance payment. Subsistence costs should be paid on an “actual” basis on production of receipts for actual costs incurred and for amounts not exceeding those set out in Post’s Geographical Expenditure Guidelines (GEG)

- Administration / Management Fees – (refer to separate Administration Costs Guidance on the SPF SharePoint site). Have these been set out in the ABB as separate charges? If so, are they reasonable / realistic? Or is the implementer “double charging” for Admin/Management fees? For example
  - Is the implementer making a separate (i.e. additional) charge for office rent and utilities which is already covered elsewhere, e.g. in their hourly charge-out rate?
  - Is the implementer assigning all of its admin/management costs to this project even though it is also running other (non-FCO) projects? If so, why is the FCO being charged for all these costs?
  - Is the admin / management charge proportionate to the size of the project and range of activities? Is part/all of it covered by other project donors?

Equipment – (refer to separate guidance on Equipment Costs on the SPF SharePoint site). Programme funds should not be used to buy equipment that the implementer is reasonably expected to provide themselves