## Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Global Future Cities Programme (Prosperity Fund)
Programme Value: £80m		Review Date: March 2020
Programme Code: GB-GOV-50-PF-21-FTCY (including GB-GOV-3-PF-FUT-911; GB-GOV-3-PF-FUT-912; GB-GOV-3-PF-FUT-913; GB-GOV-3-PF-FUT-921; GB-GOV-3-PF-FUT-922; GB-GOV-3-PF-FUT-923)	Start Date: 2019	End Date: March 2023

Summary of Programme Performance
Year	2020
Programme Score	A
Risk Rating	Moderate

Summary of progress and lessons learnt since last review
This is the first substantive annual review of the Global Future Cities Programme (GFCP).
Over the last year the programme has completed procurement processes to put in place private sector delivery partners in each of the geographies the programme operates in (Brazil, Nigeria, Turkey, South Africa and South East Asia) and completed inception phases in all but one of these geographies. The focus for the programme during these inception phases has been on further building relationships with key city authorities, deepening the design of interventions under the programme’s three pillars (transport, urban planning and resilience) and establishing appropriate monitoring, evaluation and learning and programme management structures.

List of recommendations for the next year
Review in-house technical resourcing: While there is strong technical capacity within Delivery Partners and programme management expertise within the Programme Team, the programme could significantly benefit from further in-house technical resourcing. The programme should explore scaling up current support it is getting from its Social Development and Secondary Benefits Advisors. The programme should also explore mobilising in-house urban development expertise to maintain effective technical assurance over its interventions, including drawing on existing resource elsewhere within HMG.

Better clarify and communicate roles and responsibilities, particularly between UN Habitat and Delivery Partners. Ensuring that interaction points between the two are clear and that work in country is aligned will be crucial moving forward. Of particular importance in this regard will be ensuring Delivery Partners are able to inform UN Habitat’s upcoming capacity building programme and that outstanding UN Habitat Strategic Advisor positions in SE Asia are filled.

Finalise country level results frameworks and revisit the programme level results framework as part of this process to ensure continued alignment. Establish clear data sources, baselines and reporting responsibilities. Ensure the programme is able to assess performance against its results framework at its next annual review.

Revise the programme level theory of change (ToC), paying particular attention to the contextual validity of assumptions underlying causal pathways and the interconnections between primary purpose and secondary benefit trajectories. Establish these ToC revisions as regular practice.

Establish stronger mechanisms for learning between Delivery Partners (DPs), Post and municipal stakeholders in GFCP cities. Consider building on the knowledge management role of UN Habitat in this regard and processes to facilitate dialogue across countries.

In each city analyse the barriers to programme supported spatial plans, sector strategies and systems designs progressing into implementation and delivery. This mapping should analyse political economy, institutional and financial barriers and identify measures for the programme and city reformers to navigate and address these. Work towards implementing such measures and use this knowledge to shape the design of potential follow on Future Cities programming.

In each city review and act on potential complementarities and synergies between interventions. Work towards an inter-sectoral approach that delivers a sum greater than the parts by ensuring interventions seeking to reform housing, transport and planning sectors are inter-linked and able to play off one another.

Embed engagement with beneficiaries, particularly poor and excluded city demographics, as a continuous process in programme interventions. This should involve building processes of consultation, public dialogue and participation in the processes of planning and service delivery the programme is supporting. Undertake this in a manner that is alive to any relevant contextual sensitivities to engaging these groups and questions around appropriate sequencing in relation to government engagement. Consider drawing on newly developed guidance on beneficiary engagement from DFID’s Better Delivery Department and short term advisory resource.

Develop a consistent approach to pilots across GFCP countries which sets clear criteria for initiating pilot projects, including their demonstration value, sustainability and potential to be scaled up. Consider drawing on models from UN Habitat or external experts for this.

Finalise a Secondary Benefits strategy and work plan that targets the full spectrum of secondary benefits the programme can contribute towards, including exports, outward investment and soft power. Better mainstream secondary benefit work with the programme’s core business, including better integrating primary purpose and secondary benefit pathways in the theory of change.

Establish VfM systems during implementation that track progress towards and line of sight to the economic returns projected in the business case at the intervention/sector level. Filter these down to DPs and ensure they are putting in place, and reporting on, appropriate efficiency measures.

SRO Commentary
“I have reviewed the Global Future Cities Programme Annual Review (AR) and agree with its findings. The overall score of A is a good reflection of the current status of the programme, which has just completed design and inception phases and is moving to full implementation. As SRO, I will be working with the team to consider how we take forward the recommendations made in this AR.”
JFU Commentary
This first full annual review takes place as the programme transitions between inception phase and implementation. The team has done well to navigate procurements delays and most cities are now ready to begin their interventions. There is good evidence that consultation and investment in relationships with local authorities has shaped the design of individual city plans throughout the inception phase. The programme should continue in this collaborative spirit and expand consultation to include more direct beneficiaries. The review suggests that the programme has a sense of where opportunities and challenges lie and this now needs to translate into clear theories of change and results frameworks for each city. As the recommendations make clear, revising theories of change in light of new evidence around assumptions is particularly important.
 This is a complex programme across 19 cities and five suppliers. The programme will need to demonstrate and articulate clearly that the benefits of configuring the programme in this way exceed costs. There must be a clear understanding of the pathway to outcomes in each city and of the milestones along the way, so that the portfolio can be managed for maximum value for money. The programme would benefit from an assessment of where results are most likely to be generated, to support prioritisation. This effort will be strengthened by the recommendations to increase access to expertise and improve internal processes and systems to enable portfolio management.
List of Acronyms
CO	Cabinet Office
DFID	Department for International Development
DP	Delivery Partner
DIT	Department for International Trade
FCO	Foreign and Commonwealth Office
GFCP	Global Future Cities Programme
HMT	Her Majesty’s Treasury
MEL	Monitoring, Evaluation and Learning
PP	Primary Purpose
RF	Results Framework
SB	Secondary Benefit
ToC	Theory of Change
VfM	Value for Money

## A. INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/prosperity-fund-global-future-cities-programme
DevTracker Link to Log frame:	Not yet published

The Global Future Cities Programme (GFCP) is supporting a select number of cities in middle income countries to generate greater and more inclusive local economic growth by improving the way their cities are planned and managed. This includes developing more sustainable and environmentally resilient cities, a reduction in levels of poverty and social inequality cities face and the creation of mutually beneficial two-way trade and investment opportunities for the UK and other international actors.
The programme has a total value of £80m and is led by the Foreign and Commonwealth Office (FCO), with an oversight structure that draws on resource from the Department for International Development (DFID) and Department for International Trade (DIT). It is delivering a set of targeted technical assistance interventions in 19 selected cities across ten countries (Brazil, Indonesia, Malaysia, Myanmar, Nigeria, Philippines, South Africa, Thailand, Turkey and Vietnam). These interventions are delivered across three inter-linked objectives and pillars of programme activity:
•	Increased access to safe affordable sustainable transport: Through support to the development of integrated multi-modal public transport systems.
•	Well governed, technologically innovative, inclusive, and integrated urban planning and management: Through support to the development and adoption of city master plans, inclusive spatial strategies, transparent planning instruments, improved processes and regulations.
•	Increased resilience and reduced socio-economic and environmental damage caused by natural disasters: Through the adoption and implementation of inclusive evidence-based resilience and risk mitigation strategies and plans.
Interventions in these pillars are delivered by a set of private sector delivery partners who have been contracted on geographic lines (including Adam Smith International in Nigeria, Arup in Turkey, Ernest & Young (EY) in Brazil, PricewaterhouseCoopers (PwC) in South Africa and Mott MacDonald in South East Asia) and are overseen on a day to day basis by the FCO as Post. Further oversight of work taking place in cities is undertaken by a programme management team housed centrally in the FCO and through UN Habitat, who have a ‘Strategic Partner’ role on this programme via an MoU held with the FCO. UN Habitat also played a central role in the project development process through leading delivery of the programme’s Strategic Development and Transition phases, during which the programme’s city level interventions were designed.
The Global Future Cities programme will run for a period of three years up until 2023 and it operates through the delivery of technical assistance to city authorities in processes of regulatory change, institutional design and evidence based policy making, as well as providing capacity development support to those authorities and the implementation of select pilot projects.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
The Global Future Cities programme (GFCP) is working towards sustainable urban environments that enhance inclusive economic growth, reduce social inequalities and are safer. It is doing this through contributing to three inter-connected outcomes: more affordable and accessible transport systems; better integrated urban planning and management; and increased resilience to environmental disasters.
The programme has completed inception phases in all but one of the geographies it will be implementing in. The main focus of these inception periods has been building relationships with key city authorities, deepening the design of interventions under the programme’s three pillars and establishing appropriate Monitoring, Evaluation and Learning (MEL) and programme management structures. Implementation of programme interventions is yet to begin and it is thus too soon to assess their contribution to achieving outcomes. The focus of this review has instead been on the systems, structures and approaches developed by the programme over the last year, and assessing to what degree they leave the programme set up to effectively deliver to its outputs and outcomes during implementation.
During GFCP’s Strategic Development Phase the programme undertook a rigorous process of identifying and crafting a portfolio of interventions within its targeted sectors in each city. This process involved a substantive assessment of technical viability, poverty/inclusion impact and traction amongst stakeholders in government, communities and excluded groups. These interventions tend to have good alignment with the programme’s theory of change and strong line of sight to Prosperity Fund objectives.
This review suggests the programme’s interventions are likely to effectively progress through the initial stages of the programme’s results chain. The continued relevance of these interventions and local ownership over them has been enabled through considerable work undertaken at Post in majority of GFCP’s cities to refine and adapt them to changing political and stakeholder dynamics during the inception phase. A well-functioning operating model to manage the delivery of programme interventions has been established across multiple tiers with effective programme coordination and accountability mechanisms across the programme and strong external expertise has been brought into the programme through procurements for delivery and strategic partners.
As the programme moves further into implementation it is, however, likely to face significant challenges in meaningfully contributing to its outcomes. The interventions the programme plans to deliver primarily focus on processes of spatial planning, sector/sub-sector strategy development or systems design. In many of the city contexts the programme works in the downstream delivery of these initiatives, however, face a number of institutional, financial and political barriers. The implementation of transport plans, for instance, requires significant project level investment or credit mobilisation mechanisms not in place in many cities. Similarly the operationalisation of open data platforms the programme is engaging in many cities requires systems and incentives for collaboration and information sharing that are often lacking in municipalities. While a number of cities are taking measures to address such barriers, there should be greater investment in this across the board and the programme’s theory of change should be revised accordingly.
As the programme progresses it is important that it takes full advantage of potential synergies between interventions and delivers an integrated inter-sectoral approach. The importance of working on interconnections between improved transport, planning reforms and resilience within a city are strongly stated in the business case and recognised as being important for the achievement of programme outcomes. A greater effort to build these synergies has taken place in some geographies, including in Turkey, which can be drawn upon in other locations.
Equally important is maintaining a strong line of sight towards the poverty impacts of the programme and making continued and purposeful efforts to identify and integrate the priorities of groups traditionally excluded from city decision making and management. The programme has made strong efforts to integrate standards around gender equality, women’s economic empowerment and is increasingly probing disability access issues. Achieving outcomes will, however, involve constant effort to ensure programme benefits are not captured by elite groupings and benefit a broader set of poor and excluded groups, including those living in informal settlements, women, migrant communities and small businesses in the informal sector. Ensuring these groups have sight and input into processes of regeneration, transport planning and resilience is key in achieving the programme’s poverty reduction outcomes and avoiding doing any harm. A greater emphasis on the consultation and participation of beneficiaries and the groups representing them (e.g.: civil society organisations, locally elected representatives) in the programme alongside its strong partnership with municipal administrations would be valuable to this end.

Annual outcome assessment (Secondary Purpose)
The programme aims to achieve secondary benefits to the UK and other international actors in the form of growth in exports, investment returns and soft power. The provision of services for city planning, infrastructure project development and climate resilience are areas the UK and other international actors play a strong role in. There is hence considerable potential for more dynamic transport, planning and housing sectors in the priority markets GFCP is working in to deliver these secondary benefits. Similarly the cultivation of a pipeline of more technically and financially viable infrastructure projects could create enhanced outward investment opportunities.
The realisation of these benefits are subject to the above point on processes of planning/systems design progressing into implementation, as well as the effective cultivation of market linkages between international businesses and cities. During the programme’s inception period the programme has focused on building relationships with international service providers in the future cities market and establishing systems for identifying and tracking export opportunities in the cities and sectors the programme is working in. This approach has contributed to early progress on select secondary benefit opportunities, including on e-ticketing in Istanbul and eco-tourism in Iskandar.
This progress has been driven by the work of GFCP staff at Post and the work of complimentary non-ODA funded resource through the Department for International Trade (DIT), including a part time Secondary Benefits Advisor with strong connections to the UK Future Cities market. The programme has also been able to tap into DIT’s in-country Smart Cities platforms in some cases, but these are only operational in two of the programme’s ten targeted countries (Brazil and Turkey). Given the considerable scale of the programme and the need to deepen market linkages across a large number of cities, it is questionable whether the programme has the appropriate level of resourcing to meet its Secondary Benefit outcomes. It would be valuable for the programme to explore increased mobilisation of non-ODA resource and enhancing the currently quite limited role many delivery partners play in secondary benefit pathways.
As the programme progresses and deepens its resourcing behind secondary benefits, a broader and more mainstreamed approach to secondary benefits should be explored. This should entail a greater focus on enabling outward investment opportunities, capturing the considerable soft power benefits the programme is contributing to and better integrating with the programmes primary purpose activities to generate mutually re-enforcing effects (such as facilitating international investment into the infrastructure/planning projects the programme is designing).

Overall output score and description
GFCP has developed a programme level results frameworks that will capture delivery against interventions across its three sectors and ten countries during its implementation phase. As the review period under question covered processes of procurement, mobilisation and inception, assessment has taken place on a process based results framework that captures key areas of programme work during this phase. Scoring per output is provided in Section B.

Key lessons
1. Roles, responsibilities and working arrangements are in need of further clarification, particularly related to the role of UN Habitat and how they best work together with in-country Delivery Partners.
2. Assumptions underlying causal pathways on progress to outcomes do not hold in many city contexts. This is particularly relating to assumptions around resources being allocated to finance plans, all stakeholders in partner governments being supportive of interventions and vulnerable populations being prioritised in funding allocations. Achieving programme outcomes will require dedicated engagement in these areas.
3. The programme’s theory of change is not in sync with its programme cycle. Pathways to outcomes in the programme’s theory of change are based on lengthy processes of institutional change and infrastructure delivery, but programme implementation takes place over a relatively short three year period.
4. There are important opportunities to share learning between GFCP teams working in different cities and to contribute to the global evidence base. Mechanisms to facilitate this are needed.

Key actions
1. In each city analyse the barriers to programme supported spatial plans, sector strategies and systems designs progressing into implementation and delivery. This mapping should analyse political economy, institutional and financial barriers and identify measures for the programme and city reformers to navigate and address these. Work towards implementing such measures and use this knowledge to shape the design of potential follow on Future Cities programming.
2. Embed engagement with beneficiaries, particularly poor and excluded city demographics, as a continuous process in programme interventions. This should involve building processes of consultation, public dialogue and participation in processes of planning and service delivery. Undertake this in a manner that is alive to any relevant contextual sensitivities to engaging these groups and questions around appropriate sequencing in relation to government engagement.
3. To better leverage the programme’s secondary benefits (SBs) potential pursue an increase in resourcing for secondary benefits work and better mainstream it with the programme’s core business, including better integrating primary purpose and secondary benefit pathways in the theory of change. Explore ways to enhance the role of Delivery Partners in secondary SB management in consultation with the PF SB Community of Practice.
4. Finalise a Secondary Benefits strategy and work plan that targets the full spectrum of secondary benefits the programme can contribute towards, including exports, outward investment and soft power.

Summary of changes to the logframe since the last annual review
N/A
## C: DETAILED OUTPUT SCORING

## DETAILED OUTPUT SCORING

Output Title	Procurement process is timely and delivers value for money.
Output number per LF			Output Score	A
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Procurements completed against estimated timeline.	5	5 procurements were completed January to August 2019. Largely due to approval delays there was a 5 week delay for 4 contracts and a 9 week delay for one (SE Asia).
Procurement processes deliver value for money.	5	All procurements undertaken competitively via Prosperity Fund framework and came under the expected amount.
Programme spend delivers against forecast.	Full spend against forecast.	Programme has come in around 18% lower than original budget (money handed back at 6 month and 9 month review points).

Key Points
After the programme completed its Outline Business Case (OBC), multiple approvals were required before the programme could proceed to tender. These approvals took longer than their target turn around due to staff shortages. This delayed the opening of tenders by around 5 weeks.

The Full Business Case (FBC) was approved by FCO’s Investment, Infrastructure and Operations Committee (IIOC) in June 2019. The South East Asia bid required additional scrutiny due to the value of the award. Delays in this approval process added a delay to the award of the SE Asia contract of 4 weeks.

Overall there was approximately a 5 week delay for Brazil, Nigeria, South Africa and Turkey against the original timetable, and a 9 week delay for SE Asia. However, the delay to the SE Asia contract had a positive impact as the Programme Team (P)T had more capacity for contract negotiations and were able to apply lessons learnt from other procurements.

The open tender undertaken via the PF framework should ensure VfM is achieved via the nature of competitive tenders and all tenders did come in under the expected amount. Day rates were checked to ensure they were under the allowed limit. For one bid (Brazil) only 1 response to tender was received – this was benchmarked against other bids in other regions to ensure it still met VfM requirements.

Original Budget for GFCP programme in FY19/20 was £13.7 million which was scaled down to £11.8 in December 2019. The reduction in the spend was due to delivery partners mobilising around 1-2 months later than originally planned.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A.
Recommendations
None.

## DETAILED OUTPUT SCORING

Output Title	Programme management and governance structures effectively mobilised and operational.
Output number per LF			Output Score	A
Risk:		Minor	Impact weighting (%):	35%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Key positions filled according to timeline.	17	All positions filled (17).
Programme internal governance arrangements established and functional.	At programme and country level.	Internal boards at programme level established and operational as of April 2019 and steering committees at country level established during inception phase.
Programme effectively consulted and partnered with host governments and beneficiaries.	In all 10 countries.	Strong partnership structure with city governments in each country and responsiveness of programme interventions to their changing needs and priorities. Limited engagement with beneficiary groups during inception in many cities.
Inception phase for delivery partners completed on time.	5	Inception for South Africa, Nigeria, Turkey and Brazil all completed on time and to plan (4/5). SE Asia due to complete on time. (To note that is the adjusted time plan after the procurements ran late).

Key Points
During the review period, the programme team has filled all key programme positions, creating effective teams both in London and overseas. Although two programme managers left during the year, they were quickly replaced. The role of DIT Sector Specialist (non-ODA funded) was filled in May 2019 and the incumbent spends 2 days a week on the Future Cities programme. Staffing levels of FCO teams and Delivery Partners seem right for now but this should be reviewed in a year’s time to check that current structures are still correct.

The programme team also successfully set up effective governance arrangements. Governance structures are operational and working well. The Strategic Board meets approximately quarterly or as programme timeline dictates. Monthly Programme Management Committees are held. The programme team have set out the basic approaches for assessing programme learning and evaluation.

The programme team successfully completed a complex set of procurements for the delivery partners and concluded the programme inception stage ready for full scale implementation in 10 countries. The inception phase for South Africa, Turkey, Nigeria and Brazil all completed to timetable. South East Asia are on track to complete by end March 2020. The review team noted that there was a lack of clarity between delivery partners and strategic partner over their roles, particularly with regard to capacity building. Early clarification is essential.

The programme team engaged with a wide array of stakeholders, both internal HMG (FCO, DIT, DFID etc.) and external (City Governments) while maintaining a close eye on the operating environment and effectively managing the risks arising from changing contexts. City Governments have been consulted and engaged throughout the programme as key stakeholders and beneficiaries. Prior to procurement in December 2018, validation workshops were held by UN Habitat which signalled the approval by each City of the Terms of References (ToRs) for projects/interventions planned in each city. These then formed the tender documents for procurement of the delivery partners. Cities were briefed throughout on the procurement process and on the results. The contract mobilisation period required delivery partners to engage with City partners at the start of their inception phase of work. The Sustainable Development Goals (SDG) workshops were convened by UN Habitat during December 2019 – February 2020 and involving the City partners and Delivery partners, marks the end of the inception phase.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A.
Recommendations
Review in-house technical resourcing: While there is strong technical capacity within Delivery Partners and programme management expertise within the Programme Team, the programme could significantly benefit from further in-house technical resourcing. The programme should explore scaling up current support it is getting from its Social Development and Secondary Benefits Advisors. The programme should also explore mobilising in-house urban development expertise to maintain effective technical assurance over its interventions, including drawing on existing resource elsewhere within HMG.

Now that the programme’s intense inception period is complete it should better clarify and communicate roles and responsibilities, particularly between UN Habitat and Delivery Partners. Ensuring that interaction points between the two are clear and that work in country is aligned will be crucial moving forward. Of particular importance in this regard will be ensuring Delivery Partners are able to inform UN Habitat’s upcoming capacity building programme and that outstanding UN Habitat Strategic Advisor positions in SE Asia are filled.

## DETAILED OUTPUT SCORING

Output Title	Appropriate MREL frameworks and processes at country and programme levels in place
Output number per LF			Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Programme level results framework and theory of change are developed and aligned.	At programme level.	A Programme level Theory of Change (ToC) and Results Framework (RF) were developed early during the inception phase to guide the work of delivery partners at the country level. These are now in need of revision based on RF’s and ToC’s developed at the project/country level and new learning developed during the inception phase. Particularly important is the development of baselines in the RF and revisiting of assumptions underlying the programme’s ToC.
Programme level results framework indicators well defined, clear and at the right level of ambition	At programme level.	The programme results framework is well structured and is set up to effectively capture the programme’s work across multiple countries and sectors in a succinct manner. It is, however, unclear how a number of indicators will be operationalised, including what data sources will be used, how baselines will be developed and milestones set.
Country level results frameworks and theory of change are developed and nested within programme level frameworks.	In each GFCP country.	Draft results frameworks for the country level were submitted at the end of inception by each Delivery Partner. These are yet to be finalised and alignment with programme level needs to be reviewed.
MREL frameworks are sensitive to social inclusion considerations.	At programme and country level.	The programme has committed to disaggregating some indicators at the outcome level by gender, age and income. Qualifiers around inclusion are built into some indicators at the intermediate outcome and output levels (e.g. Inclusive evidence based policies, strategies, plans and models developed).

Key Points
GFCP is a complex programme working at scale across multiple levels, sectors and geographies. The programme has progressed well in establishing an overarching programme level ToC and RF within which country and project level RFs and ToCs can be effectively nested. This is an important step in ensuring the coherence of the programme and aggregating its work. There is good understanding of these frameworks within the programme team and Delivery Partners and an active effort to align work to them.

Operationalising the programme’s MEL system and appropriately monitoring progress during implementation will, however, require significant work to finalise country level frameworks, develop data sources and baselines and check line of sight between the programme and country level TOCs/RFs. It will be important throughout this process for the programme to ensure MEL systems are maintained as simple and less labour intensive so as not to become too cumbersome during the programme implementation. Important as well will be the participation of City Governments and alignment with available municipal data sources and the ability to report against cross cutting priorities, such as adaptation to climate change and carbon impacts.

It would be important that the TOC and RF is regularly refreshed and closer oversight maintained to keep the linkage between outputs –> intermediate outcomes and ultimate outcomes under purview. An immediate term revision is needed in line with new learning that has emerged during the inception period. This includes revisiting assumptions underlying ToC causal pathways that do not hold for many city contexts (e.g.: assumptions such as “Vulnerable populations, especially the hard to reach will be prioritised and the funding allocated to ensure inclusion and true representation” and “Resources allocated to finance plans” that are places on the causal chain between output and outcomes).

Within the programme level ToC Secondary Benefit pathways are currently siloed of from causal pathways in the programme’s three pillars. This risks not fully reflecting the reinforcing nature of primary purpose and secondary benefit pathways.

The spread of programming across 10 countries and 5 Delivery Partners creates barriers to effectively leveraging learning between cities. There is considerable potential added value in establishing mechanisms for delivery teams, staff at Post and municipal actors in different cities to draw on learning from one another. This is particularly the case given the different shape GFCP has taken in each country based on the different areas of expertise of its Delivery Partner and contrasts in local contexts.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations
Finalise country level results frameworks and revisit the programme level results framework as part of this process to ensure continued alignment. Establish clear data sources, baselines and reporting responsibilities.

Revise the programme level theory of change, paying particular attention to the contextual validity of assumptions underlying causal pathways and the interconnections between primary purpose and secondary benefit trajectories.

Establish stronger mechanisms for learning between DPs, Post and municipal stakeholders in GFCP cities. Consider building on the knowledge management role of UN Habitat in this regard and processes to facilitate dialogue across countries.

## DETAILED OUTPUT SCORING

Output Title	Programme design is evidence based, fit for context and sustainable
Output number per LF			Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of projects validated for delivery by programme partners.	30	During the programme’s Strategic Development Phase 30 interventions were validated for delivery by stakeholders from government, civil society and expert communities. Due to procurement delays there was a significant time lag between this validation process and the inception phase of the programme during which city contexts and stakeholder needs and priorities have often shifted. In majority of programme cities there has, however, been a process of re-scoping or adjusting interventions to ensure their continued relevance and contextual fit.
Evidence base and relevant expertise effectively fed into development of projects.	30	In the programme’s Strategic Development phase potential interventions were identified and shortlisted through an assessment of city context and consideration of constraints and additionality. During the Transition Phase interventions were consolidated and designed through a process of scoping technical viability. / In inception, the approach Delivery Partners have taken to deepening the design of these interventions has varied. All interventions do, however, have causal pathways outlined, stakeholder mappings and considerations of impact on social exclusion.
Sustainability and exit considerations incorporated in programme design.	Across programme	Consideration of sustainability was incorporated into city and intervention selection processes and most delivery partners have developed basic exit strategies as part of their inception deliverables. Achieving and sustaining outcomes will, however, require better understanding, and contributing to addressing, the institutional and financial barriers to programme supported strategies and plans being implemented.
Programme design sensitive to gender and social inclusion.	Across programme	All Delivery Partners have conducted Gender and Social Inclusion (G&I) assessments to understand the G&I dimensions of project interventions and some have drafted G&I action plans. Engagement with groups representing the urban poor and excluded demographics took place during the programme’s Strategic Development Phase, but has taken place in only a limited manner during the programme’s inception phase.
Programme has a clear external communications strategy and approach.	At programme and country levels	Programme communication strategy developed and supported by delivery partner stakeholder and communications plans.

Key Points
As discussed above, the project has undergone a rigorous process of intervention selection that considered stakeholder traction, technical viability and strategic fit. Interventions selected tend to have a strong alignment with the programme’s theory of change and have the potential to play an important role in processes of city economic transformation.

Although GFCP has limited flexibility to drop existing interventions or take on new ones, it has worked well to enable the continued relevance of interventions to changing contexts and stakeholder priorities. Most cities have gone through processes of adjusting or reframing interventions in relation to changing contexts, as was the case after local elections in Turkey and in response to changing government priorities in South Africa.

The programme has the potential to take a powerful inter-sectoral approach through supporting inter-connected reforms in transport, land, housing and planning sectors. This requires designing strong connections and synergies between interventions within a city, as is the case in Bursa where interventions on establishing data-driven city management systems and urban transformation plans are being knitted together. Such an approach could be taken forward more systematically across cities.

As discussed in the section on progress towards outcomes, the interventions the programme plans to deliver primarily focus on processes of spatial planning, sector/sub-sector strategy development or systems design. In many of the city contexts the programme works in the downstream delivery of these initiatives, however, face a number of institutional, financial and political barriers. The implementation of transport plans, for instance, requires significant project level investment or credit mobilisation mechanisms not in place in many cities. Similarly the operationalisation of an open data platforms the programme is engaging in many city requires systems and incentives for collaboration and information sharing that are often lacking in municipalities. A number of cities are taking some measures to address these barriers (such as in South Africa where there is considerable investment in deepening political traction behind interventions and building institutional capabilities), but greater investment in this area over the coming year is likely needed.

This challenge is exacerbated by a lack of alignment between the programme’s theory of change, which involves working through lengthy processes of institutional reform and infrastructure delivery, and its programme cycle, which has a short three year implementation time frame.

A number of cities have begun undertaking pilot projects associated with the interventions selected within each city. These often involve directly funding small scale infrastructure or services in contrast to the focus of the programme’s core interventions on upstream planning and institutional reforms. While pilot projects could play an important catalyst role, it is important the programme develops a consistent approach to them that ensures they are aligned with the programme’s theory of change and are sustainable.

The programme has made strong efforts to integrate standards around gender equality, women’s economic empowerment and is increasingly probing disability access issues. Continuous efforts to ensure programme benefits are not captured by elite groupings and benefit a broader set of poor and excluded groups are crucial, including those living in informal settlements, migrant communities and small businesses in the informal sector. Ensuring these groups have sight and input into processes of regeneration, transport planning and resilience is key in achieving the programme’s poverty reduction outcomes and avoiding doing any harm. There has been strong initial work in this area in some cities the programme can draw on. This includes its work in Lagos, where there has been considerable effort in understanding actors in the informal transport sector and engagement with local civil society and community structures.

A broader and more mainstreamed approach to secondary benefits should be explored. This should entail a greater focus on enabling outward investment opportunities, capturing the considerable soft power benefits the programme is contributing to and better integrating with the programmes primary purpose activities to generate mutually re-enforcing effects (such as facilitating international investment into the infrastructure/planning projects the programme is designing).

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
In each city analyse the barriers to programme supported spatial plans, sector strategies and systems designs progressing into implementation and delivery. This mapping should analyse political economy, institutional and financial barriers and identify measures for the programme and city reformers to navigate and address these. Work towards implementing such measures and use this knowledge to shape the design of potential follow on Future Cities programming.

In each city review and act on potential complementarities and synergies between interventions. Work towards an inter-sectoral approach that delivers a sum greater than the parts by ensuring interventions seeking to reform land, transport and planning sectors are inter-linked and able to play of one another.

Embed engagement with beneficiaries, particularly poor and excluded city demographics, as a continuous process in programme interventions. This should involve building processes of consultation, public dialogue and participation in the processes of planning and service delivery the programme is supporting. Undertake this in a manner that is alive to any relevant contextual sensitivities to engaging these groups and questions around appropriate sequencing in relation to government engagement. Consider drawing on newly developed guidance on beneficiary engagement from DFID’s Better Delivery Department and short term advisory resource.

Develop a consistent approach to pilots across GFCP countries which sets clear criteria for initiating pilot projects, including their demonstration value, sustainability and potential to be scaled up. Consider drawing on models from UN Habitat or external experts for this.

Finalise a Secondary Benefits strategy and work plan that targets the full spectrum of secondary benefits the programme can contribute towards, including exports, outward investment and soft power. Better mainstream secondary benefit work with the programme’s core business, including better integrating primary purpose and secondary benefit pathways in the theory of change.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Drivers of cost for the GFCP programme are twofold: staff costs in the London/Singapore Hubs and for country programme managers (including platform charges, travel etc.), and delivery costs through contracts with the delivery partners and the programme’s strategic partner.
This year staff costs were as expected, though drops in spend took place during some periods due to delays in recruitment after staff leaving. Delivery partners’ costs were below what was anticipated this year as procurement opened approximated 5 weeks later than expected and then mobilisation and inception around 5-9 weeks later, which means less money was spent on delivery this year.
Initial allocation to the GFCP programme for this financial year was £13.7m. This was reduced to £11m when the impact of the late start of delivery partners was known. The programme has a high proportion of its annual expenditure forecast for the final quarter of the this FY, which reflects a broader backloading of the programme budget, with the first two quarters reflecting low spend during the procurement stage.
Financial spend in Financial Year 19/20
Programme:	Project Name:	Budget 19/20 (agreed March 19)	Actuals as of January 2020	Forecast to March 20
PF FUT 911001	PF FUT UKB staff	£350,000	£231,300	£332,174
PF FUT 911002	PF FUT LE Based staff costs	£320,000	£234,746	£325,554
PF FUT 911003	PF FUT Platform charge	£350,000	£362,435	£362,435
PF FUT 912002	PF FUT SA Big Data[1]	£10,000	£12,434	£12,434
PF FUT 913001	PF FUT Non staff admin UK[2]	£50,000	£28,206	£107,009
PF FUT 913002	PF FUT UN Habitat T Work	£450,000	£346,423	£816,423
PF FUT 913003	PF FUT LE Mobile Phones	£10,000	£3,389	£9,627
PF FUT 913004	PF FUT LE Travel & Subs	£100,000	£81,361	£97,163
PF FUT 913005	PF FUT All Staff Training	£10,000	£2,418	£2,418
PF FUT 913006	PF FUT Programme Support[3]	£90,000	£122,303	£185,583
PF FUT 921001	PF FUT Delivery Phase Brazil	£750,000	£81,220	£367,269
PF FUT 921002	PF FUT Delivery Phase SE Asia	£3,500,000	£423,094	£1,662,976
PF FUT 922001	PF FUT Strategic Partner[4]	£1,200,000	£1,808,704	£2,367,124
PF FUT 922002	PF FUT Delivery Phase Nigeria	£2,500,000	£413,701	£1,308,303
PF FUT 923001	PF FUT Delivery Phase South Africa	£2,000,000	£590,558	£1,591,796
PF FUT 923002	PF FUT Delivery Phase Turkey	£2,000,000	£342,938	£1,455,547
	Totals	£13,690,000	£5,085,230	£11,003,835
[1] Project supporting South Africa in using data to understand complex urban issues.
[2] Programme facilitation costs covering planning, implementation, resources
[3] Commercial contractor costs
[4] Strategic Partner costs for implementation phase

Major variances in spend are due to delivery partner costs being lower than originally expected as explained in above sections. UN Habitat work has increased in cost due to extra work being undertaken in South Africa. UK staff travel costs higher than originally costed due to trip to World Urban Forum planned later on in year. The GFCP team applied for a side event at the conference as part of their knowledge transfer work. This event was only approved in December for travel in February. The team also travelled to South Africa launch events that had not been accounted for at the start of the FY.
Admin costs are mostly made up of staff costs (including travel, phones etc.) and platform charges (Locally engaged staff are counted as 25% admin and 75% programme due to their implementation focused roles). Total for this financial year was high approx. 5.6% (£614K) but overall as a proportion this will fall as the programme enters full delivery and total admin for programme as whole will be under 3.5% cap.
Now that inception phase has passed and we have full programme work plans for FY 20/21, the budgeting should be more accurate and it will be easier to track delivery partner spend monthly through our reporting procedures.
The Strategic Board approve the overall budget for the programme. In year, delivery partners report their budget monthly to programme team so we can track and mitigate any variances. Performance will be monitored quarterly by the strategic board and any variances over +/-10% flagged to them. Any increase or decrease in the yearly budget for the programme is to be agreed by strategic board.

VfM performance
During the annual review period, GFCP programme successfully built on its previous relationships with city governments and reaffirmed their commitment to programme interventions, demonstrated by their active participation in programme activities and agreement of commitments through city level Memorandums of Understanding (MoUs) in each GFCP country. This took place with minor amendments in some cases (e.g. in Turkey and South Africa) to programme interventions.
Good progress has been made in procuring and mobilising the services of delivery partners for Brazil, Nigeria, Turkey, South Africa and South East Asia, and enabling them complete the inception phase for the programme. UN Habitat has continued to provide strategic support on quality assuring deliverables. This has put the programme on track to move into implementation as planned and on track to deliver the planned outputs and intermediate outcomes by December 2021. However, there is a moderate risk to the realisation of the envisaged primary and secondary benefits within the anticipated period, due to the dependency of programme interventions on local commitments, institutions and processes in partner countries to deliver GFCP interventions downstream (discussed further in the progress towards outcomes section). This risk has slightly increased due to outbreak of Covid-19, causing restrictions on free movement of professionals, possible restrictions on development finance and a probable global economic recession.
The key areas of expenditure as outlined in the business case for the programme are set-out below, together with their projected costs, as indicated in the BC.
Cost item	Cost (£m)
Phase 1 Strategy and Training (transition delivery funding including HMG programme Hub 2018/19)	4.1
Phase 2 strategy and knowledge management	4.0
Phase 2 intervention delivery	62.9
HMG programme hub over Phase 2 (London and Singapore hubs plus Posts)	5.0
Phase 2 intervention contingency	2.0
TOTAL	80.0

The breakdown of intervention delivery phase by pillar is as follows.
Pillar	Cost (£m)
Transport	27.1
Urban planning	26.3
Resilience	9.5
TOTAL	62.9

Economy and Efficiency
On economy and efficiency, programme expenditure has been managed successfully to budget over the Annual Review (AR) period whilst delivering expected progress against its milestones. The overhead cost (FCO staff costs + administration costs) has amounted to 5.6% of expenditure though this should come down to within the 3.5% cap as delivery expenditure increases. The FCO’s procurement framework was used for the procuring the services of delivery partners, which was a competitive process in which bids were assessed on cost, the quantity and quality of proposed deliverables and suppliers’ capability/capacity to deliver. Given the control over programme overheads at the PT level alongside the relatively timely delivery of procurement and the programme’s demanding inception period, it can be inferred that the programme is being managed to an acceptable level of efficiency. UN Habitat were originally selected to undertake transition development work through a bidding process with other multilateral organisations in 2017. Given their experience of transition work, they continued as strategic partner. The rationale for this is explained in the Business Case. UN Habitat put together a detailed work plan; day rates for staff are lower than those on the PF Framework so represent VfM.
In terms of areas for improvement on economy and efficiency, an action to monitor the potential for additional cost economies and efficiencies during the programme implementation stage will be particularly important as spend starts to increase in the remaining years of the programme. Delivery Partners should be encouraged to seek out these efficiencies during implementation and regularly report on them.
Effectiveness
The GFCP programme is still at a relatively early stage, so it is too early for effectiveness to be properly judged. However, the successful completion of procurements for professionally capable delivery partners and their mobilisation and completion of inception phases in a tight 3-4 month timeframe of reflects well on programme effectiveness. Furthermore, based on a review of key documentation and interviews with the programme team and delivery partners, the programme has appeared to establish strong project management systems and processes and a robust financial management system that demonstrates strong cost control. The initial foundations of an effective MREL system as well have been laid, though this requires further work.
Equity
The GFCP programme team has worked closely with delivery partners during the inception stage to ensure that Gender & Inclusion is effectively embedded in the programme’s methodology and agreed to by the city governments of beneficiary countries. The Social Development Advisor worked closely with the delivery partners and other members of the programme through this process and an update of the G&I scorecard assessed the programme as in alignment with the PF G&I policy.
The AR team found that the GFCP programme team is strengthening its G&I capability; delivery partners have G&I resource within their teams and the PF Social Development Advisor continues to play a crucial role over G&I. That said, the GFCP can do more by embedding stronger continuous engagement with groups representing programme beneficiaries (discussed above); seeking increased in-house technical inputs on social development and further monitoring G&I progress during the Programme’s implementation stage. Further, the GFCP team can draw on resources and lessons from major DFID infrastructure programmes and existing guidance on good practice on inclusive infrastructure.
Assessment of whether the programme continues to represent value for money
VfM performance compared to the original VfM proposition in the business case
The business case appraised the GFCP programme £80m investments (discounted at £73m for 2017). Over a 20 year period the total Primary Benefits accruing to the programme is £107m (having a BCR of 1.5:1) and Secondary Benefits accruing up to £23m (having a BCR of 0.30:1). The individual sectoral benefits projected as per the table extracted from the business case below.

Summary of Future Cities Programme Costs and Benefits. 2017 £m, discounted to 2018/19. Appraisal Period 2018/19 – 2037/38
Pillar	Costs	Primary Benefits	Primary BCR	Secondary Benefits	Secondary BCR
Transport	32	34	1.1 : 1	11	0.40 : 1
Planning	32	47	1.5 : 1	12	0.40 : 1
Resilience	9	26	2.8 : 1	0.3	0.03 : 1
Total	73	107	1.5 : 1	23	0.30 : 1

The benefits were forecasted on the basis of numerous assumptions made at the Business Case (BC) preparation stage to reflect the transition of inputs into outcomes. The Programme “intervention level outputs” are nested at “intermediate outcomes” in the programme level theory of change.
During the AR period, the team focused on setting up the governance processes for ensuring that clear line of sight is maintained between the inputs – outputs and intermediate level outcomes through an attention to the alignment between the various levels of theory of changes and logframes. Concerted effort was made during the inception stage in this regard and the AR team noticed enough level of awareness and attention on this subject during its interviews with the delivery partners and programme managers.

The programme team has adopted a VfM scorecard approach to measure the programme preparedness (on a traffic light scoring system) over the following areas:
Relevance and robustness of VfM measures in place
Approach to procurement and cost containment
Efficient use of resources and inputs by Prosperity Fund interventions
Validation of Prosperity Fund Theory of Change causal pathways (for primary & secondary benefits)
Sustainability of programme activities
Ability of leadership, management and oversight structures to support Programme delivery
Strategies and measures adopted to enhance delivery and mitigate risk
Equity of programme design and approach

The Review Team reviewed the Feb 2020 Score Card Assessment and broadly agrees with its recommendations made against the specific areas. However, based on interviews with key informants, the Review Team will rate the Programme performance during 2019-20 as follows (slightly different from the Feb 2020 scores):

VfM Scorecard Element	Rating by Review Team
1. Relevance and robustness of VfM measures in place	Amber
2. Approach to procurement and cost containment	Green
3. Efficient use of resources and inputs by Prosperity Fund interventions	Amber-Green
4. Validation of Prosperity Fund Theory of Change causal pathways (for primary & secondary benefits)	Amber
5. Sustainability of programme activities	Amber
6. Ability of leadership, management and oversight structures to support Programme delivery	Green
7. Strategies and measures adopted to enhance delivery and mitigate risk	Green
8. Equity of programme design and approach	Amber

Overall, the Review Team would assign the VfM scorecard status as Amber-Green (slightly improved from Amber status awarded by the Programme Team in Feb 2020).
The programme’s current scorecard approach is focused on assessing whether the programme has the correct systems and processes in place to deliver value for money. The review team would recommend that in addition to this the programme adopts more substantive and quantitative measures to track its delivery of VfM. This would entail assessing results and projected returns of interventions against their costs to establish return on investment and contribution towards the primary and secondary benefits envisioned in the business case.
Because of numerous extraneous factors at play, a regular (biannual / annual) refresh of this will provide an assurance that the programme is moving in the right direction and is aimed at achieving its promised returns. It will also help the programme identify the additional measures required to maintain a positive VfM on the programme.
More strategically, it is also required that during programme interventions’ implementation stage, sufficient downstream sustainability mechanisms are put in place to ensure that the programme “intermediate outcomes” progress towards the “outcomes”. As discussed elsewhere in this report, achieving outcomes in this programme will require greater attention to the financial, institutional and political barriers to programme supported spatial planning/sector strategy processes being implemented. Putting in measures to contribute towards sustained ownership and downstream financing are key and should be reflected in the programme’s theory of change.
Assessment of whether the programme continues to represent value for money
Based on the economy measures introduced to lower the cost of inputs, the project management systems adopted to drive efficiency and the strong level of city government satisfaction with the programme interventions, the AR team is of the view that the GFCP programme represents value for money and would be on track to achieve its stated outcomes provided it adopts the AR recommendations provided in this report.

Quality of financial management
Financial management frameworks vary for each supplier, but all are subject to oversight through the FCO’s Supplier Relationship Management system and clauses within, including those pertaining to regular reporting and internal audit. Each supplier has provided to the programme policies which certify they and their supply chain will comply with the provisions of clause 53 (Prevention of Fraud and Bribery) of Call-Off Contract. Fraud, bribery and safeguarding processes for the programme are set out in their operating manual (which was an inception phase output) and this document was cascaded to Delivery Partners supply chains for implementation. Fraud/corruption risks that are specific to the project and circumstances are identified in the delivery partner’s risks register and actively monitored. The programme takes the same approach with UN Habitat. All contracts and the UN Habitat MOU are overseen by the GFCP Contract Manager

All Delivery Partners have reported on time to a satisfactory quality to date (noting that this only covers a 4 month period). The programme has a service level KP that tracks reporting timeliness during implementation to track this in an on-going manner.

Date of last narrative financial report	March 2020.
Date of last audited annual statement	N/A

## E: RISK (1 page)

Overall risk rating: Moderate
Overview of programme risk
The Review Team observed that the programme has adopted a comprehensive Risk Management Approach and deployed it effectively at both HQ and Country levels. Various contextual, operational, delivery, reputational and fiduciary risks have been identified and mitigation strategies put in place. Some of the country offices are ahead of others in risk mitigation strategies and have established stronger processes for on-going risk management.
Key contextual risks identified by the programme include a lack of city level leadership and institutional capacity leading to low support and missed opportunities and delayed decisions by partner governments creating hurdles in programme delivery. Further risks the programme could factor in here include political change in municipalities and the impact of Covid-19 on programme operations and delivery, including the changes it will provoke in local economies and government priorities.
Delivery risks include opportunities for synergy being missed, the complexity of the programme being unmanageable, overlap of programme with other donors and UK companies not taking advantage of opportunities created. The mitigation for these risks could be further enhanced by encouraging delivery partners to map synergies across interventions, putting in place stronger mechanisms for learning between GFCP countries and mobilising greater resource from DPs and DIT behind secondary benefits work. Risks of the programme not achieving outcomes should include risks around downstream financing/institutional systems for the implementation of programme supported plans/sector strategies being implemented.
Fiduciary and Reputational Risks include contractors delivering poor VFM, negative press coverage of the programme and non-compliance with finance guidelines and local statutory regulations. Existing mitigation strategies for these risks are sufficient.
Operational Risks include the programme not benefiting the urban population experiencing poverty, exclusion or gender inequality. Mitigations identified include requirements for Delivery Partners to mobilise G&I expertise and social disaggregation of Monitoring and Evaluation (M&E) data. These are key steps, but this risks could be further addressed by integrating regular consultation with groups representing the urban poor (e.g.: civil society and community structures) into the programme’s interventions.
From the Risk Management Approach and the Risk Registers, it can be concluded that the Teams have a very good understanding of Risk Management and have been using it well. Appropriate mitigation measures have been put in place for the above (and other risks) identified at various levels. Continued use of this approach and monitoring of the Risk Register will be needed to ensure that any ensuing risks to the programme are adequately addressed. There is also a good opportunity to share and learn best practice from across the delivery partners on GFCP and to have effective risk management system at the delivery level

Outstanding actions and recommendations from risk assessment
1. Consider adding in contextual risks on political change in municipalities and the impact of Covid 19.
2. Better mitigate against Delivery Risks by assessing synergies between interventions, putting in place stronger mechanisms for learning between county teams and factoring risks around programme interventions not being delivered downstream.
3. To better address Operational Risks around the poverty impact of the programme, build stronger beneficiary engagement into programme interventions.
## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The Business Case envisaged contracts starting in August 2019. The Outline Business Case required multiple approvals before proceeding to tender, and after tender, the SE Asia bid required further CO and HMT scrutiny. This slipped by 5 weeks (for Brazil, Nigeria, South Africa and Turkey) and 9 weeks (for SE Asia), mainly due to delays in approvals from Cabinet Office and HM Treasury. Despite this, inception has been completed on time, although the short inception period proved challenging for Delivery Partners. All Inception Reports have been signed off, with the exception of SE Asia which is currently being finalised.
The open tender undertaken via the PF framework should ensure VfM is achieved via the nature of competitive tenders and all tenders did come in under the expected amount. Day rates were checked to ensure they were under the allowed limit. For one bid (Brazil) only 1 response to tender was received – this was benchmarked against other bids in other regions to ensure it still met VfM requirements. Robust programme governance structures with clear lines of responsibilities have been established and change management processes provide assurance that commercial consideration will be kept in close purview whilst programme changes are encountered.

Performance of partnership(s)
This is a complex programme with a Strategic Delivery Partner (UN Habitat) and five Delivery Partners (Ove Arup, PwC, Mott MacDonald, ASI and EY) covering 19 cities in 10 countries. Robust governance and management structures are in place to manage the relationships.
Initial teething problems are being overcome as programme teams learn how to work together. There is a need to clarify the different roles of the Delivery Partners and UN Habitat at an early stage to ensure each organisation understands its role.
There is also an appetite for more shared learning between Delivery Partners. We recommend that the programme team find an early opportunity to bring Partners together to share experience and best practice. UN Habitat’s Knowledge Management Platform will have an important role to play, but bringing the teams together in one place would be highly beneficial.

Changes in the Delivery Plan
The programme has just completed inception phase and delivery plans have been drawn up by delivery partners. Some changes to supply chains have taken place since procurement. In each case, the change control process has been followed and changes logged.

Asset monitoring and control
The programme is not generating any assets.

## G: BUSINESS ENVIRONMENT

How has the business community and business environment responded to the programme?
The UK houses well regarded private sector expertise in urban planning, built environment, smart cities and climate based adaptation. The programme has engaged in the UK and at Post with businesses working in this space to facilitate market linkages with cities and the uptake of export opportunities identified through the programme. Good practices of engaging the business community under the programme include the alignment of the Brazil programme’s launch with the visit of a trade mission and the cultivation of export opportunities for UK service providers identified through the programme, including in the development of smart-ticketing systems in Istanbul and eco-tourism strategies in Iskandar. Engagement with a broader set of business actors, including UK infrastructure investors, is still at an early stage and will be deepened during implementation.
(Where relevant) What role has non-ODA spending played in promoting programme objectives?
The programme uses non-ODA funds to resource a part time (2 days/week) Secondary Benefits Advisor from DIT. This is an important role that facilitates connections with businesses in the UK smart cities sector, the capturing and communicating of export opportunities and expertise for FCO project managers at Post on business engagement. Given the scale and geographic spread of the programme, increased non-ODA resource would greatly benefit the programme’s business engagement, as would exploring how programme delivery partners could play a stronger role in business engagement and secondary benefit pathways.

## H: MONITORING & EVALUATION

Evidence and evaluation
All Prosperity Fund programmes are required to undertake regular evaluation through a supplier managed independent evaluation service. GFCP is yet to undertake an independent evaluation due to the early delivery stage it is in. Its first evaluation is planned for to take place towards the end of 2020.
Monitoring progress throughout the review period
The review period has spanned the programme’s procurement, mobilisation and inception phases. Progress during this period was monitored through a set of key performance indicators and milestones, which have been aggregated up into the process framework used in this annual review.
The programme has made significant progress in establishing appropriate monitoring systems for its work during implementation. A programme level results framework was developed early in inception which set an overarching structure within which Delivery Partners drafted country level results frameworks. These country level results frameworks are well nested within the programme level framework and allow an effective aggregation of the programme’s work across countries and sectors.
To enable effective monitoring during the programme’s implementation period, results frameworks are in urgent need of finalisation. Programme and country level results frameworks should urgently establish clear data sources, ownership responsibilities, baselines and milestones. Alignment between country and programme levels should be reviewed at this point.