Memorandum of Understanding for Strategic Partner services related to the Prosperity Fund Better Health Programme

The Government of the United Kingdom of Great Britain and Northern Ireland (the Government) represented by the Foreign and Commonwealth Office (FCO)
and
Health Education England of the Government of the United Kingdom of Great Britain and Northern Ireland (the Implementing Partner)
(together the Participants)

WHEREAS the FCO requires the Implementing Partner to co-ordinate a consortium of NHS organisations acting as Strategic Partner for the Better Health Programme, thereby enabling the FCO to be an intelligent client during programme delivery;
WHEREAS the services required of the Implementing Partner (hereafter “the project”) are intended to support the Better Health Programme and maximise the benefits from the programme

Have reached the following understandings:

1. Purpose

The purpose of this memorandum is to enable the Implementing Partner to organise and implement support – in the form of technical health inputs and strategic advice – to the FCO during the delivery of the Better Health Programme, and carry out related activity in the UK, Mexico, South Africa, Brazil, Malaysia, Thailand, Vietnam, Myanmar and the Philippines. The objectives and activities of the Better Health Programme and the project are set out in Annex A – Prosperity Fund Better Health Programme Strategic Partner Terms of Reference.

The Implementing Partner will be awarded funding by the Government in line with the commitments set out in this memorandum.

The Implementing Partner accepts the funding on the basis that it will be used to implement the project activities as set out in Annex A - Prosperity Fund Better Health Programme Strategic Partner Terms of Reference.

The Implementing Partner will not carry out any activities as part of this project other than those described in Annex A without the prior written approval of the Government, and will use the funding from the Government solely for the purposes of achieving the Better Health Programme outcomes as outlined in Annex A.

2. Duration

This memorandum will come into effect upon signature by both Participants and provides funds for the period from 1st April 2019 until 31st March 2020. Its effect may be extended beyond this period with the written approval of both Participants.

3. Sub-contracting

Any sub-contracting of activities relating to the project will be the sole legal and financial responsibility of the Implementing Partner.

4. Financial arrangements

Summary of the financial arrangements.

The total amount of the cost of the project eligible for financing is not expected to exceed £ 886,062 in line with the budget provided at Annex B. In the event supplementary staffing is arranged, in line with cost estimates provided at Annex B, the participants will sign a variation of this arrangement, in the form of a revised version of this memorandum.

The Implementing Partner will submit all invoices relating to the project to the Government on a quarterly basis for payment to be made quarterly in arrears.

In order for the Government to provide funds to the Implementing Partner, the Implementing Partner will demonstrate to the Government, as required at paragraph 7(2), that it has satisfied the following provisions:

- All costs have been in strict accordance with the principles set out in HMT’s “Managing Public Money”, a publicly available guidance document;
- All costs have been clearly itemised in the aforementioned invoices;
- All costs have been properly attributed to activities set out in Annex A; and
- All personnel expenses in excess of day rates and in excess of those expenses set out in Annex B have previously been approved by the Government.

Financing by the Government for subsequent years of the project is not guaranteed and will depend on the availability of funding to the Government and satisfactory progress (as demonstrated via the reporting requirements detailed herein).

The Participants recognise the importance of procurement good practice when using funds provided by the Government for any procurement that is necessary to implement the project.

The Implementing Partner will maintain an accurate record of expenditure and will retain all invoices, receipts and accounting records for up to six years and make these available for inspection by the Government or an independent auditor as required.

The Implementing Partner will submit monthly expenditure forecasts to the Government, as represented by the Better Health Programme Manager (as defined in paragraph 10(1)), and inform the Government, in writing, of significant variations in the forecast costs. Any change in the expenditure profile is subject to the Government’s written approval.

The Implementing Partner will maintain records of significant exchange rate fluctuations (+/- 5%) which might lead to changes in the levels of resources required.

5. Travel arrangements

1. The Implementing Partner will co-ordinate the dates of any overseas missions with FCO diplomatic missions in the corresponding partner countries.
2. The Implementing Partner will consult these diplomatic missions on a proposed programme plan.
3. The Implementing Partner will provide confirmation of delegation and travel itinerary at least one week ahead of each visit, to enable FCO participation as appropriate.

6. Amendment of this memorandum

Any amendment to this memorandum will be decided upon by both Participants and will be made in writing.

7. Reporting

On the seventh working day of each month, the Implementing Partner will provide the Government with a written summary report. This report will cover the Implementing Partner’s activities undertaken under the project and an assessment of progress made by Suppliers on programme delivery, by reference to Annex A. This will be accompanied by the financial reporting referenced at 4(1) point (g), and an assessment of risks. The report will be presented to the monthly Better Health Programme Management Committee (PMC) in a format as agreed by the Participants. A report will also be submitted quarterly to the Better Health Quarterly Board, upon written request by the Government and in a format agreed by the Participants.

1. In each of their monthly reports, the Implementing Partner will submit a statement setting out how the project funds were spent, including details of consultant fees and travel expenses, where applicable.
2. Continuation of the project upon the conclusion of each stage of the project will be dependent on the Implementing Partner demonstrating to the Government, through the report and assessment, satisfactory progress against the original bid.

8. Termination

The FCO may end its participation in this arrangement by giving one month’s written notice to the Implementing Partner, in the following circumstances:

1. Upon the Implementing Partner failing to implement the project according to this memorandum
2. Upon a significant failure by the Implementing Partner to meet any of the commitments set out in this memorandum
3. Force majeure
4. Where any changes occur which, in the opinion of the Government, significantly impair the value of the contribution of the project towards the programme objective
5. Where the financial position of the programme changes significantly.

In the event of termination, all remaining funds other than those irrevocably committed in good faith before the date of termination, in line with project objectives and approved between the Participants as being required to finalise activities, will be returned to the FCO.

9. Dispute settlement

Any dispute that may arise as to the interpretation or application of this memorandum will be settled by consultation between the Participants.

10. Contact information and equipment at project end

The Implementing Partner will provide the Government with contact details for its representative with responsibility for addressing normal day-to-day enquiries.

The point of contact for the Government in relation to this MOU is the Better Health Programme Manager
The point of contact for the Implementing Partner in relation to this MOU is the Chief Policy Officer, Global Engagement
On completion of the project, any items of equipment with a value of over £1,000 will remain the property of the Government unless the Participants make an alternative arrangement.

11. Responsibility for Staff

1. The Implementing Partner will provide adequate supervision of and care for its staff, authorised agents and representatives, in line with its obligations as an employer or as a result of any other relationship.
2. The Implementing Partner will put in place a formal safeguarding policy (at an organisational level) which is communicated to, and accepted by, all staff and included in the induction packs.
3. All individuals involved in the project will be requested to confirm to the Implementing Partner by return of email that they have read and agree with the HEE anti-fraud, bribery, corruption and formal safeguarding policies ahead of travelling.
4. If the Implementing Partner’s staff or authorised agents and representatives are based in living or working accommodation owned, occupied or controlled by the FCO or using transport or other facilities provided by the FCO, these individuals will observe such instructions and requirements of accommodation and access to facilities as apply to FCO staff.
5. In the event of paragraph 11(4), including where Implementing Partner staff use FCO managed or controlled facilities in a manner that is consistent with the purposes for which funding is provided under this memorandum, it does not discharge the Implementing Partner’s more general and continuing obligations to these individuals in its role as an employer or as a result of any other relationship.
The foregoing record represents the understandings reached between the Government of the United Kingdom of Great Britain and Northern Ireland (represented by the Foreign and Commonwealth Office) and Health Education England upon the matters referred to therein.

Signed on behalf of the Government of the United Kingdom of Great Britain and Northern Ireland / Name: / Position: Date: / Signature:	Signed on behalf of Health Education England / Name: / Position: / Date: / Signature:

Annex A

Prosperity Fund Better Health Programme Strategic Partner Terms of Reference

Better Health Programme – Implementation Phase
Terms of Reference for the NHS Consortium as the Strategic Partner
Background
The £1.2bn Official Development Assistance (ODA) Prosperity Fund, of which £79m will be used to deliver the Better Health Programme (BHP), is a cross Government initiative to encourage economic growth in developing countries. The FCO Better Health Programme aims to support partner countries (Brazil, Mexico, South Africa, Malaysia, Myanmar, the Philippines, Thailand and Vietnam) in their health systems’ reforms with the goal of expanding Universal Health Coverage (UHC) and improve health and related economic growth outcomes. This multi-country sector programme is designed to improve health, increase life expectancy, improve productivity and deliver economic growth in middle income countries through interventions focused on reducing non-communicable diseases and improving patient safety.
A consortium of health-sector arm’s length bodies (ALBs) (“the NHS Consortium”) was commissioned by the Foreign & Commonwealth Office (FCO) to deliver the Strategic Development Phase of the BHP. A joint team, coordinated by Health Education England (HEE), delivered a programme of visits to the selected eight countries to better define priorities for the Implementation Phase of the BHP. The team produced output documents highlighting recommended interventions and submitted these to FCO for sign-off. A smaller team are providing transitional support for the tendering process until arrangements are in place to support the implementation phase.
Following feedback from the partner governments during the Strategic Development Phase, it has been agreed that the NHS Consortium will continue to provide support during the Implementation Phase of the programme, acting as a Strategic Partner. These Terms of Reference define this support.
Objective
The objective of the NHS Consortium as a Strategic Partner is to provide flexible, quality-assured health technical expertise and strategic advice to support delivery of the Better Health Programme aims and the strengthening of health system-to-system relationships.
Scope
This objective will be achieved by fulfilling four functions:
- Expert advisory input to Delivery Partners to support further programme design ahead of implementation and during delivery of the programme as needed;
- Expert high-level advisory input to the FCO to support ongoing monitoring and evaluation of the Implementation Phase by providing critical appraisal and facilitating cross-programme learning and building capacity at posts;
- Support to the FCO SRO and Programme Lead in programme level strategic decision-making through technical knowledge-based recommendations;
- Facilitation of UK Global Health Diplomacy, ensuring the BHP maintains a system-to-system dialogue, building on relationships developed during the Strategic Development Phase and complementing the FCO’s relationship with the Governments of partner countries to maximise the benefits of the programme.

These functions are expected to be performed by the combination of:
- The BHP NHS Joint Unit (“the Joint Unit”), including a specified number of UK health systems advisors (“the Advisors”).
- The NHS Consortium Technical Advisory Service (CTAS)

Roles and responsibilities are set out in more detail below in the relevant sections (Sections 9 to 10). The requirement to ensure these activities do not detract from the consortiums domestic responsibilities is outlined in section 13.
Secondary Benefits
The NHS Consortium as a Strategic Partner to the FCO BHP is funded through Official Development Assistance. All activity should be aligned to activity designed to maximise the primary benefits of the programme.
The NHS Consortium as Strategic Partner will also be expected to work closely with FCO and DIT to maximise the secondary benefits from the programme. In practice, this will mainly include intelligence gathering and sign posting of emerging activity.
Any non-ODA funded activity seeking to maximise secondary benefits through the consortium as a strategic partner must be agreed by the FCO, as well as meet the requirements set out in section 13 regarding the Consortium’s domestic responsibilities
Membership of the NHS Consortium
The UK health and social care sector organisations listed at Appendix 1 have agreed to be members of the NHS Consortium and participate in the active governance of the Strategic Partner activities through ALB Responsible Officer (SRO) representation on the BHP ALB Steering Group (see Accountability and Governance). They will also contribute to the pool of technical expertise accessible to the CTAS, by facilitating employees to be called upon for short-term input to the BHP, and may contribute to the Joint Unit by facilitating secondments to that team (see Section 9). Additional information on each organisation can be found in Appendix A. The Strategic Partner arrangements will be covered by a Memorandum of Understanding.
Any other UK health or social care sector organisation, including those of the devolved administrations, may choose to become an “Associate” of the NHS Consortium. This will allow individuals employed within those organisations to contribute to the pool of technical expertise by allowing employees to be called upon for short-term input, to the CTAS, and for the costs associated with this input to be reimbursed. The list of Associates will be maintained by the Strategic Partner as described in section 9 below.

External Stakeholders
External stakeholders critical to the effective functioning of the NHS Consortium as a Strategic Partner in supporting BHP Implementation Phase include but are not limited to:
- The FCO BHP team (Whitehall), who will manage the programme including responsibilities for strategic programme decision making, assurance and governance
- The Department of Health and Social Care (DHSC) colleagues and representatives of other government departments overseeing the Prosperity Fund, particularly the Department for International Development (DFID)
- Healthcare UK (HCUK) and the Department for International Trade (DIT)
- The FCO programme management and advisory colleagues in the relevant embassies, who are responsible for in-country government relations, monitoring supplier performance, and supporting contract management
- Relevant ministries and agencies of partner governments
- Civil Society organisations from those countries, as appropriate
- Delivery Partner organisations, who are responsible for the day-to-day delivery.

Relationship between NHS Consortium and External Stakeholders
External stakeholders will be able to call upon the NHS Consortium for expert advice and support when needed and as appropriate in accordance with the Roles and Responsibilities described in this document. The approach to the relationship will be characterised by:
- A partnership of equals, in which the NHS Consortium recognises that the UK needs the local perspective and gains from shared learning
- Objectivity, for example, ensuring that advice does not give preferential advantage to any specific organisation or supplier
- Assurance for External Stakeholders that the right expertise is being provided and used
- NHS values, including but not limited to ‘compassion’, ‘improving lives’ and ‘everyone counts’
- NHS principles, including but not limited to a patient-centred view and a system-wide approach
- Enabled learning, by contribution to monitoring, reporting, evaluation and learning from the BHP.

Timeline
The implementation phase for the Better Health Programme is expected to run from April 2019 to end of September 2022. Institutional and governance arrangements for the NHS Consortium as Strategic Partner are expected to be in place and fully functional from 1 April 2019.
Roles and Responsibilities: BHP NHS Joint Unit (“Joint Unit”)
The role of the Joint Unit is to coordinate, support and manage all the activities of the NHS Consortium as Strategic Partner to deliver the functions as outlined in Section 2. Please see Figure 1 for the structure of the Joint Unit and Figure 2 for an organisational systems map.

Figure 1: NHS BHP Joint Unit Structure

Figure 2: BHP organisational systems map

The Joint Unit will ensure that the overall programme supports, reflects and takes into account ongoing input from partners, and changing circumstances in partner countries.
This includes but is not limited to:
- Managing the Strategic Partner input within the budget agreed by the FCO
- Ongoing cross-programme management of its own activities and processes
- Providing first-line technical support to posts
- Supporting ongoing monitoring, reporting, evaluation and learning (MREL) - including by facilitating cross-programme communications to maximise the effectiveness of delivery, and building capacity of FCO colleagues to engage in health and MREL activities
- Maintaining a list of active Associates contributing to CTAS, ensuring new Associates are ratified at routine Steering Group meetings
- Coordinating expert inputs into the BHP from the UK necessary to ensure effective delivery - including, but not limited to, developing, maintaining and managing access to the CTAS
- Working with FCO, Delivery Partners, and advisory colleagues to gather insights into potential secondary benefits and help channel appropriately
- Preparation of reports to the FCO on its activities.
The Advisers in the Joint Unit will use their previous experience in the UK and other health systems, and network in the UK, to advise FCO colleagues in post, and the rest of the Joint Unit, on:
- Design and delivery of the BHP interventions
- Relationship strengthening
- Strategic direction

There will be a broad base of technical expertise within the NHS Consortium relevant across the scope of the BHP. The Advisers will recommend when it is necessary to escalate demands for technical inputs outside their areas of expertise. Each is expected to have specific responsibilities for providing advice to a subset of the partner countries, but also to provide cross-cutting advice to colleagues in line with their expertise.
The Advisers will:
- Support FCO colleagues at post in the effective engagement with government partners and Delivery Partners where required.
- Link to the colleagues in the Joint Unit and the wider consortium and feedback required information
- Provide strategic health guidance to FCO programme management and advisory colleagues in the relevant embassies as required, ensuring that delivery aligns to health policies in-country and international best practice
- Be the first port of call for content-specific questions from partner government, FCO post or Delivery Partners, feed up questions which they are not able to respond to and access the wider consortium expertise through the advisory service
- Work with FCO, Delivery Partners, and Joint Unit colleagues to gather insights into potential secondary benefits and help channel appropriately

Roles and Responsibilities: NHS Consortium Technical Advisory Service (CTAS)
The CTAS will consist of a database of subject matter experts from Member or Associate organisations who are willing and able to respond to a request for targeted technical expertise. The response will be in the form of focused, short inputs (either one off or in series) on specific areas identified for UK health sector input i.e. where experience is unique, particularly relevant, or particularly requested. Core principles of the operation of the CTAS are set out in a separate Terms of Reference and the portion of services that respond to commissions by FCO posts are covered by the same MOU as the Joint Unit.
Who can join the database?
Those who are employed by, or who hold a contract with, one of the six Member ALBs can join the database. Other UK health or social care sector organisations, including those of the devolved administrations, may choose to become an “Associate” of the NHS Consortium. This will allow individuals employed within those organisations to contribute to the pool of technical expertise by allowing employees to be called upon for short-term input, particularly to the CTAS, and for the costs associated with this input to be reimbursed. It is at the discretion of the NHS Joint Unit as to which organisations may become ‘Associates’; expressions of interest for this will be reviewed on a case-by-case basis. The list of Associates will be contained in a schedule to the MOU and be regularly updated through the life of the BHP.
How will CTAS provision be mobilised?
Resource from the CTAS will be mobilised as per the following steps.
Details of a request for support will be received from FCO Programme Management teams in country. The NHS will aim to deploy experts to support in-country activity in 10-12 weeks. A minimum of eight weeks’ notice is required ahead of any overseas deployment. For support provided remotely the NHS will work to deliver work in a timely fashion, reducing this turn around, while ensuring organisations are able to meet their domestic responsibilities.
- The CTAS team will first assess whether the request is appropriate for use with CTAS. If the expertise of the Health Systems Adviser is sufficient to address the request, they will be asked to provide direct support. If the request requires a certain area of expertise beyond the capacities of the Health Systems Adviser, the CTAS will be drawn upon to respond to the request. In a case where there are no Health Systems Advisers in post, CTAS will be drawn upon where appropriate.
- If more than ten contacts are eligible following the initial ‘areas of expertise’ filter, relevant ‘international experience’ will be used to further shortlist. If more than 10 contacts continue to be eligible, further criteria relevant to that specific request will then be used to reduce the list – e.g. appropriate job grading, ability to provide continuity.
- If a Technical Advisor is selected, they will be contacted via email and the deployment process – detailed outside of this MoU - will commence upon their acceptance. If there are no appropriate advisers on the database, this will be escalated to the ALB Steering Group via the NHS Joint Unit and attempts will be made, where possible, to fulfil the request through non-database contacts within Member organisations. FCO posts would be kept up-to-date regarding this process.

Expected Deliverables
Expected deliverables include:
- A work plan aligned to the BHP programme plan and country logframes: initial version to be in place ahead of implementation, and to be updated at least every 6 months
- An engagement plan across BHP countries and stakeholders
- A MREL plan aligned with the FCO Country and Programme logframe.
- High-quality technical advice provided through the Health System Advisors and the Service
- Early identification of risks and appropriate recommendations on mitigation
- Summary monthly reports to Programme Management Committees (including monthly finance forecasts); these reports will detail Supplier progress against their work plans, and the contribution to logframe outputs, including any call down on the CTAS or wider NHS engagement, and any potential secondary benefits identified
- Quarterly internal reports to the BHP ALB Steering Group (not FCO) of the progress against the work plan
- Quarterly updates to the FCO BHP strategic board (see below) which report on strategic trends and risks across the programme.
- Advisory input and recommendations which are non-enforceable
- Specific short-term deliverables as arranged per country e.g. participation in workshops etc.

Finances
The overall budget for the activities of the Strategic Partner, including salaries and any travel and subsistence costs of the Joint Unit, are set out in full in Annex B of this MOU Funding will be allocated from the BHP to HEE for allocation to the NHS Consortium. The Joint Unit will submit forecasts monthly and invoices to the FCO BHP team on a quarterly basis.
As set out in section 10, within the budget of the Strategic Partner there will be a ring-fenced minimum budget by country for the CTAS, to be managed and monitored by the Joint Unit to provide support ongoing monitoring and evaluation of the Implementation Phase by providing critical appraisal and facilitating cross-programme learning and building capacity at posts. Time commitment costs of the CTAS will also be covered by the Strategic Partner budget. This allocation excludes any additional requested activity via CTAS to cover gaps in Delivery Partner provision, which should be funded from the Delivery Partner’s budget.
Domestic Responsibilities
The NHS Consortium recognises that its primary goals and statutory responsibilities are focused on the NHS, service users, and the population of England. While the NHS Consortium believe that the NHS engaging globally is beneficial to individuals, organisations, the health system, the government, and UK PLC, no activity undertaken on behalf of the consortium or the FCO should be to the detriment of their domestic responsibilities.
Assurances to this effect include, but are not limited to, ensuring that all activities undertaken are fully funded, that domestic responsibilities are considered when decision on accessing UK expertise are taken, sufficient notice is given to ensure that domestic responsibilities are not adversely affected and that line managers and organisational leads are sighted on all such activity.
Accountability and governance
The relationship between FCO and the Hosting Member organisation, Health Education England (HEE), is governed by an MOU.
The relationship between all Members and Associates of the NHS Consortium will be governed by a separate MOU.
There are two governance bodies overseeing the NHS Consortium, each of which will have its own Terms of Reference:
The BHP NHS Joint Unit is accountable to the BHP ALB Steering Group. The ALB Steering Group will consist of Member SROs, which will provide governance and high-level management of the team and will be the first point of call for escalating and resolving issues in fulfilment of the Strategic Partner functions. This Group is chaired by the Head of the Joint Unit and meets quarterly.
The BHP ALB Steering Group is accountable to the existing FCO BHP Strategic Board. The BHP Strategic Board consists of representatives from FCO, DFID, DHSC, and DIT. They provide strategy and direction for the whole BHP. This Board meets quarterly.

The Head of the BHP NHS Joint Unit will attend both Boards to provide linkage between the two functions. Minutes from the BHP ALB Steering Group will be shared with the BHP Strategic Board.
Whilst being responsible for internal project management, the Strategic Partner is not responsible for BHP programme management, wider outcome delivery beyond agreed specific short-term deliverables, contract or financial management of Delivery Partners, or any activities to be carried out by the FCO programme team including those at post. The Strategic Partner does not own the relationships with Delivery Partners or in-country stakeholders as this will continue to be managed by FCO.

Appendix A
The NHS Consortium is constituted from the following Member organisations
- Care Quality Commission (CQC): CQC is the independent regulator of health and adult social care in England. CQC ensures that health and social care services provide people with safe, effective, compassionate, high-quality care and we encourage care services to improve.
- Health Education England (HEE): HEE supports the delivery of excellent healthcare and health improvement to the patients and public of England by ensuring that the workforce of today and tomorrow has the right numbers, skills, values and behaviours, at the right time and in the right place.
- NHS Digital: NHS Digital is the national information and technology partner to the health and social care system. It uses digital technology to transform the NHS and social care.
- NHS England: NHS England leads the National Health Service (NHS) in England. It sets the priorities and direction of the NHS and encourages and informs the national debate to improve health and care.
- NHS Improvement (NHSI): NHS Improvement is responsible for overseeing foundation trusts and NHS trusts, as well as independent providers that provide NHS-funded care. It offers the support these providers need to give patients consistently safe, high quality, compassionate care within local health systems that are financially sustainable.
- Public Health England (PHE): Public health expertise to protect and improve the health and wellbeing, and reduce health inequalities through world-leading science, knowledge and intelligence, advocacy, partnerships and providing specialist public health services.

Annex B
Financial Summary BHP NHS Joint Unit 2019/20

Date 25/02/2019