## Introduction
Risk based matrix
The good estate management for schools (GEMS) guidance sets out the principles of maintenance planning.
You should also read the relevant GEMS guidance and further information about prioritising maintenance before using this tool.
This tool will help you develop a risk based approach to prioritising maintenance to make best use of your resources. To do this, you will need to assess the condition of your estate along with risks and other factors that you consider important.
Methodology The methodology used in this matrix is based on as assessment of risk factors and their severity and the probability of failure. The risk factors in the matrix cover: • health and safety and statutory compliance • the impact on the operation of the school • the potential financial or reputational implications • the impact on the ongoing condition of the building or elements within it You could consider other risk factors to reflect your organisation's priorities. The probability of failure in the matrix is defined as: • unlikely • possible • likely • certain You will need to use your condition surveys or seek advice from your building professional to help identify the probability of failure.
This is an example only and is not intended to provide a prescriptive methodology. You should use a methodology that suits the needs of your school or organisation. This methodology can be adapted to meet your own needs.
By applying a consistent methodology, you will be able to rank different maintenance works against each other and ensure that you focus and prioritise your resources to minimise risks.

## Instructions
How to use the risk based matrix
We have included some example maintenance activity in the workbook. These are only examples and are not intended to describe the risk associated with particular maintenance. You should consider and assess the severity of the risk in terms of the consequences for your organisation. This matrix is based on as assessment of risk factors and their severity and the probability of failure. You can use the matrix to consider the risk factors and probability of failure of items if you don’t undertake the works, and rank them in order of priority. The simple numerical ranking can be used alone, or you could combine it with a simple colour ranking (red-amber-green approach). Once you have completed the assessment for each activity, complete the outcome/next steps section at the end to identify maintenance that should be carried out.
How to complete the risk based matrix
Instructions for comletely each section of the risk-based matrix are listed below but should also pop-up as you click into each cell.
Description:
Location - enter the location where the maintenance needs to take place Maintenance activity - enter the name of the maintenance activity that needs to take place - you can be as descriptive as is useful for you.
Risk areas - for each category, select the level of risk. Descriptons for each level can be found in the 'risk categories' tab, or by selecting a level.
Severity of risk - The tool will generate an overall risk level based on the levels identified in the 'risk areas' section. You can override this to suit your organisation and circumstances by entering a different overall risk level in the 'override overall severity risk' column. This will replace the auto-generated level with the level you have identified.
Likelihood of failure - Identify the likelihood of failure of the maintenance required is not carried out.
Priority - The priority level will be automativally generated here, based on your previous responses. If you edited the overall severity risk earlier, the formula will use the level you identified.
Outcome/next steps - you can use this table to help you plan out the next steps for this issue - you can fill in information such as actions to take, timeline and budget, to help you with planning and prioritisation.

## Risk based matrix
Risk based matrix
Before you start please read the accompanying document and 'how it works' tab
Description |  |  | Risk areas | [12 empty] | Severity of Risk |  |  | Likelihood of Failure |  |  | Priority |  |  |  | Outcome/next steps
Ref | Location | Maintenance activity | Health and safety/statutory compliance |  | Score | Operational/service interruption |  |  | Maintenance budget/business/financial |  |  | Building condition/deterioration |  |  |  | Overall severity score (auto-generated) | Override overall severity score | Value | Likelihood Score | Value | Description | Numerical Rating | Category | Action required | Reasoning | Estimated cost | Timeframe | Comments
Eg 1 | Main building | Boiler replacement | Insignificant | No risk of injury or breach of procedures | 1 | Moderate | Impact on large part of school, disruption to normal school operation | 3 | Minor | Possible impact on reactive maintenance budget, complaint or impact on reputation | 2 | Minor | Could develop into minor deterioration of building or services if delayed | 2 | Minor | Moderate | Please select | 3 | Likely | 3 | Signs of significant deterioration/damage. Estimated time to failure within a year. | 9 | Resource dependent | Replace boiler | Prevention of failure, it is reaching the end of its lifespan | £x | Autumn term
Eg 2 | Reception | Replace door | Moderate | Injury or illness resulting in absence, significant breach of procedures or legal requirements | 3 | Minor | Localised impact, little disruption or impact on school operation | 2 | Minor | Possible impact on reactive maintenance budget, complaint or impact on reputation | 2 | Minor | Could develop into minor deterioration of building or services if delayed | 2 |  | Moderate | Please select | 3 | Certain | 4 | Failure imminent or has already occurred. | 12 | Priority | Replace the reception classroom door | Risk of injury if it gets worse; potential that the classroom will be out of action | £x | This month
3 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
4 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
5 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
6 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
7 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
8 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
9 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
10 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
11 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
12 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
13 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
14 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
15 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
16 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
17 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
18 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
19 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
20 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
21 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
22 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
23 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
24 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
25 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
26 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
27 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
28 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
29 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
30 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
31 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
32 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
33 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
34 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
35 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
36 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
37 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
38 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
39 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
40 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
41 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
42 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
43 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
44 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
45 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
46 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
47 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
48 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
49 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select
50 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  |  | Please select | Please select | #N/A | Please select

## Risk Categories
Severity of Consequences
Please select
Insignificant
Minor
Moderate
Major
Catastrophic
Probability of Failure
Please select
1 | Unlikely | Operationally sound. Normal wear and tear. Estimated time to failure 5-10 years.
2 | Possible | Some signs of minor deterioration/ damage. Estimated time to failure up to 5 years
3 | Likely | Signs of significant deterioration/damage. Estimated time to failure within a year.
4 | Certain | Failure imminent or has already occurred.
Probability of failure
[8 empty] | 1 | 2 | 3 | 4
| Severity |  |  | Health and safety/statutory compliance | Operational/service interruption | Maintenance budget/business/financial | Building condition/deterioration | Unlikely | Possible | Likely | Certain
|  | Please select | 0
| 1 | Insignificant | 1 | No risk of injury or breach of procedures | Minimal or no impact on school operation | Minimal or no impact on reactive maintenance budget or reputation | Work can be delayed without affecting condition of building or services | 1 | 2 | 3 | 4
| 2 | Minor | 2 | Minor injury, trivial breach of procedures or minimal breach of legal requirements | Localised impact, little disruption or impact on school operation | Possible impact on reactive maintenance budget, complaint or impact on reputation | Could develop into minor deterioration of building or services if delayed | 2 | 4 | 6 | 8
Severity of consequences | 3 | Moderate | 3 | Injury or illness resulting in absence, significant breach of procedures or legal requirements | Impact on large part of school, disruption to normal school operation | Significant impact on reactive maintenance budget, reputational impact, financial penalty | Will result in significant deterioration of building fabric or services if delayed | 3 | 6 | 9 | 12
| 4 | Major | 4 | Major injury, notifiable breach of legal requirements or procedures, litigation likely | Major impact and disruption to whole school operation | Major impact on reactive maintenance budget, loss of reputation, financial penalty | Serious deterioration of building and services and drop in overall condition category if delayed | 4 | 8 | 12 | 16
| 5 | Catastrophic | 5 | Fatality, prosecution from legal breach | Failure results in closure of whole school operation | Extensive impact on maintenance or capital budgets, reputational impact, significant financial penalties | Will result in complete building failure, unsuitable for occupation if delayed | 5 | 10 | 15 | 20