BRAZIL PROSPERITY FUND
BILATERAL PROGRAMME FULL BUSINESS CASE

UK-Brazil Prosperity Partnership – poverty reduction and productivity gains
Programme Purpose: To support increased productivity in Brazil for renewed economic growth and poverty reduction, by reducing transaction costs and stimulating competition and innovation.
Programme Value: £56.45M
Start Date: April 2018	End Date: March 2023
Overall programme risk rating:	Moderate

*Note to reader: This Business Case was written between 2017-18 and information reflects thinking from this period. Despite some contextual changes, the analysis, main problem to be addressed and proposed solutions remain valid. Economic metrics predate the COVID-19 global outbreak. This document was also written before the merger between the FCO and DFID into FCDO, and therefore may contain reference to these organisations as separate. A list of acronyms is included in Annex A for reference.

## INTERVENTION SUMMARY

Brazil finds itself at a crossroads – what we term an inflection point. It could remain a middle income country, growing old before it becomes rich, with millions of its citizens still poor.[1] Or it could improve its productivity, attain a higher growth trajectory, continue its social inclusion policies, lift further millions out of poverty and, by 2036, become as rich per capita as Portugal is today.[2]
[1] “Over the 20 years to 2031 Brazilians aged 65 and above will rise from 7% to 14% of the population. That change took a century in France” World Bank (2011), Growing Old in an Older Brazil, page XXVII
[2] Simulation based on GDP per capita levels at purchasing power parity IMF World Economic Outlook Database, April 2017, International Monetary Fund. Database updated on 12 April 2017. Accessed on 21 April 2017. Data on ageing taken from World Bank (2011) Growing Old in an Older Brazil, p10.

Brazil made world-leading progress coupling economic growth with poverty reduction. But, in 2015, Brazil had experienced the most severe recession in its history, meaning that progress on poverty and inequality now faces stagnation and reverse. Brazilians who were recently lifted out of extreme poverty now face a complex scenario of slow economic growth and rising unemployment.

Structural barriers to Brazil’s productivity must be urgently addressed through significant changes to the status quo, without which further sustainable and equitable growth in Brazil will not be achieved. Brazil can no longer afford be 124th for ease of doing business globally and 22nd in Latin America. High transaction costs, and challenges related to competition and innovation, quality infrastructure and access to finance for essential infrastructure investments are summed up collectively as “custo Brasil” – the cost of doing business in Brazil. Brazil’s traditional industrial policy, backing national champions, should be updated and upgraded to allow market forces to drive efficiency.

The Prosperity Fund in Brazil deliberately targets the areas where UK strategic expertise and existing strong partnerships add value to help reduce structural barriers to productivity and create the conditions for growth in key sectors. Brazil’s determination in moving forward on its reform agenda gives confidence that Prosperity Fund support is timely and can help Brazil achieve a higher growth and poverty reduction trajectory during this inflection period.

Through the UK’s £56m investment over three years, we will:
- Provide technical assistance and capacity building to support Brazil to align with OECD standards (£2m);
- Provide a tailored package of training, mentoring, and technical support to an existing Brazilian Development Bank to establish Brazil’s first Green Investment Vehicle (£4m);
- Design a market framework for capital market and policy instruments for sustainable infrastructure investments (£1m);
- Stimulate investment in innovative technologies to enable Brazil to diversify energy production from a wider range of renewable sources (£16.5m);
- Improve energy policy, regulation and planning, increase competition, share international best practice and business models, creating an open and transparent business environment and encouraging vital investment (£8.5m);
- Pilot innovative Smart Mobility technologies in São Paulo to improve traffic flows, improving the quality of life for poor communities, reducing negative impacts on Brazil’s economic development (£5m)
- Pilot innovative Smart Water technologies in Recife to reduce water lost by leakages, improving the efficiency of water management, and increasing access of the poorest to potable water within integrated urban planning (£5m)
- Pilot advanced electronic systems (a Port Community System) to improve the efficiency of ports which handle principal trade flows (including those of the UK), supported by technical assistance and capacity building to improve ports management (£8m);
- Provide a tailored package of training, mentoring, and technical support to enable targeted sectors of Micro, Small and Medium Enterprises (MSMEs) to participate in global and UK supply chains. (£6m)

Successful UK-funded interventions will demonstrate ‘what works’ for productivity growth and improved market efficiency, giving Brazil and others the confidence to replicate this at scale to unlock more of Brazil’s economic potential.

If the UK can partner Brazil through its return to growth, the potential for shared prosperity gains is significant. Brazil’s economic growth to-date has demonstrated significant regional spillover to the South America region. If Brazil makes the essential structural changes needed to return to growth, the benefits are likely to reach far beyond Brazil’s own population of 208m people. More efficient and less costly trade operations, as well as an increased pool of companies trading in different sectors, are beneficial for both the UK and Brazil, as well as the international market.

The proposed programme supports UK policy objectives. As the UK National Security Strategy and Strategic Defence and Security Review 2015 states: “As the largest economy in Latin America, Brazil is increasingly an important partner for the UK. We have chosen to strengthen our economic relationship with Brazil through an Economic and Financial Dialogue, with the inaugural meeting in October 2015 paving the way for closer cooperation on infrastructure and financial services.”[3] If Brazil’s huge market can be orientated towards the UK’s internationally renowned standards and best practices – for example in regulatory reform, green finance and trade facilitation – and through driving demand for greater innovation in areas of world-leading UK expertise, Brazil can be set on a path to renewed growth to the benefit of both its own citizens and those in the UK.
[3] UK National Security Strategy and Strategic Defence and Security Review 2015 (page 72. Section 6.24)

## STRATEGIC CASE

A. The opportunity: Brazil’s return to inclusive economic growth to lift millions more out of poverty

Brazil has a globally leading track record in economic growth coupled with effective public policy, which drove tremendous reductions in poverty and inequality. More than 29m people were lifted from extreme poverty between 2004 and 2014 (Annex B Figure 1) and inequality dropped from 58.1 in 2001 to 51.5 on the Gini index by 2014.[4]
[4] The Gini index measures the degree of inequality in a country’s distribution of family income; the more unequal a country’s income distribution, the higher it will be on the index.

The combination of economic growth and effective social policy significantly reduced extreme hunger and improved health and school attendance. Enormous improvements were made in nutrition, with stunting rates declining from 19% in 1989 to 7% in 2007.[5] Total life expectancy increased from 65 to 75 years between 1989 and today, while infant mortality rates fell from 53 to 15 per 1000 live births.[6] Illiteracy rates for women 15 years old and above fell from 20.3% in 1991 to 9.8% in 2008.[7]
[5] 10 Facts About Food and Nutrition in Brazil
[6] World Bank - Contraceptive prevalence, any methods (% of women ages 15-49)
[7] Gender Equality Pays Off in Brazil

While GDP grew on average 4.5% per year from 2000-2010, incomes of the bottom 20% rose at rates above 7% per year.[8] Formal jobs were created rapidly, with unemployment rates falling from 11% at the beginning of the decade to 5% in 2010. Income growth meant an increased middle class and a rapid reduction in the proportion of the Brazilian population classified by the World Bank as extremely poor, moderately poor and vulnerable to poverty.[9] Annex B - Figure 2 shows that the proportion of the population in these categories nearly halved from 45% in 2004 to 23% in 2013. The biggest improvements were to the extremely poor category of people.[10]
[8] Otaviano Canuto, World Bank: What’s Ailing the Brazilian Economy?
[9] According to Brazilian government definitions the extreme poor in Brazil live on under £25 per person a month, the poor between £25 and £46 and the vulnerable between £46 and £88 a month. Boundaries taken from World Bank http://documents.worldbank.org/curated/en/567101487328295113/pdf/112896-WP-P157875-PUBLIC-ABSTRACT-SENT-SafeguardingBrazilEnglish.pdf p. 5. Purchasing Power Parity conversion rates for 2017 taken from the IMF World Economic Outlook 2017
[10] World Bank (2016) Retaking the Path to Inclusion Growth and Sustainability, Report no. 101431-BR Brazil Systematic Country Diagnostic, page 9

Progress was also reflected in reduced race gaps in income. Annex B - Figure 3 shows that, in 2003, only one third of the afro descendant population earned at least half of the minimum wage, compared to just over two thirds of whites; by 2012, over two thirds of the afro descendant population earned at least half of the minimum wage. This was echoed in other income brackets.

These positive trends were linked to two major factors: first, the improved performance of the economy and the labour market, leading to job creation; and secondly the successful introduction of active social programmes for redistribution, including the Bolsa Familia, the world’s largest conditional cash transfer scheme. Brazil’s social transfer system began in 1995, initially with DFID bilateral programme input, and advanced significantly both in 2001 and from 2004 onwards, reaching some 50m low-income Brazilians – a quarter of the total population.[11]
[11] http://www.worldbank.org/en/news/opinion/2013/11/04/bolsa-familia-Brazil-quiet-revolution

The most important cause of poverty reduction for those categorised as both poor and extremely poor was changes in household income, from both labour and non-labour source (Annex B Figure 4). This was even more important than the demographic changes (captured as the ‘dependency ratio’ in figure 4) that increased the proportion of people at economically productive ages. Importantly, for the extreme poor, non-labour income (green) – government social transfers – was the most important cause of poverty reduction, whereas labour income (yellow) was more important for those categorised as poor.[12] An OECD study shows the same holds true for an earlier period from the mid-1990s to 2010 during which 63% of the fall in poverty in Brazil was due to income growth. This shows that this pattern is deeper than just the duration of the previous economic boom cycle.
[12] World Bank (2017). Safeguarding against a reversal in social gains during the economic crisis in Brazil, p.3

Recent recession means poverty and inequality gains face stagnation and reverse

Despite this tremendous progress, Brazil’s success in achieving growth with poverty reduction risks being reversed. Since late 2014 with the worst recession in the country’s history, GDP per capita has decreased by almost 9%.[13] 17m people in Brazil are poor and nearly 7.6m (3.7% of the population) still lives in extreme poverty.[14] Factoring in the effects of the recession that Brazil is just exiting, the World Bank estimate that 8.3m Brazilians live on less than £25 a month, 19.6m live on between £25 and £46 pounds a month, and approximately 51m live on between £46 and £88 a month. As a comparison the relative poverty line in the UK is approximately £130 per person a month.[15] All 79m people in Brazil counted as extremely poor, poor and vulnerable would count as extremely poor in the UK. The contraction hit all sectors hard, in particular industry, now 21% below its historic output peak in June 2013. Extreme poverty increased from 2.8% to 3.4% between 2014 and 2015; while the overall poverty rate increased from 7.4% to 8.7%.
[13] Data from IBGE, Brazilian statistical institute.
[14] People living on less than USD $1.90 a day, World Bank Development indicators 2016.
[15] Dept of Work and Pensions, Households Below Average Income: An analysis of the UK income distribution: 1994/9 -2014/15, p.12

Brazil now ranks 80th in the world in terms of income per capita, at USD $15,200 per capita, roughly the same as China and 7% below the average world income. Food insecurity remains a problem in some communities.[16] In the North and Northeast regions, about a quarter of children under the age of five suffer from chronic malnutrition. Half of Brazil’s 60 million children live in poverty.[17] The participation of children in the labour force in Brazil is at least twice as high as in any other country in Latin America.[18]
[16] 10 Facts About Food and Nutrition in Brazil
[17] Save the Children - Brazil
[18] Word Bank - Brazil: A Poverty Assessment

Since 2015, Brazil has seen falling employment, rising inflation and fiscal pressures. The recession has caused the unemployment rate to double to over 13% and 2.9m formal jobs have been lost since the beginning of 2015.[19] Youth unemployment in 2017 increased to nearly 29%, which can significantly reduce long term wages and increase odds of future joblessness.[20] Between 2.5m and 3.5m more people –- mainly in urban areas in the southeast – are at risk of slipping back into poverty.[21] The World Bank suggests that these “new poor” are likely to be slightly younger, skilled, and located in urban areas in the southeast.[22] They are a group that can more easily be lifted back out of poverty again through resumed economic growth and a strengthened domestic labour market. In spite of the fact that 85% of the population live in urban areas, rural and urban areas contribute equally to national poverty, especially in the Brazil’s Northeast.[23] The proposed Prosperity Fund programme in Brazil will target the geographical spread of the interventions to reach both the “new poor” and the North and Northeast, where poverty has traditionally been concentrated.
[19] IMF Country Focus, 2016. Fiscal Discipline Critical to Restoring Growth in Brazil
[20] The World Bank Data - Unemployment, youth total (% of total labor force ages 15-24) (national estimate)
[21] World Bank Latin America – Protecting the “new poor” during Brazil’s economic crisis
[22] World Bank (2017 )– Poverty and Inequality Monitoring:Latin America and the Caribbean. Safeguarding Against a Reversal in Social Gains During the Economic Crisis in Brazil, p.10htp:w.worldbank.org/en/nen/news/ition to lre.l and redistributive mechanisms to
[23] Word Bank - Brazil: A Poverty Assessment

Climate change is an additional negative factor that affects Brazil’s poor disproportionately and impedes social and economic development. The reliance of Brazil’s economy on natural resources and commodities intensifies the potential impacts of climate change on its population and economy. Brazil is severely susceptible to extremes of droughts and flooding. Reduced water in reservoirs in the South and South East have put at risk Brazil’s hydroelectric power generation, which is responsible for over 70% of all the country’s electricity. Brazil has made ambitious commitments under the UNFCC Paris Agreement 2016 (COP 21) to reduce greenhouse gas emissions by 37% by 2025 and 43% by 2030. As the 7th largest emitter of greenhouse gases (GHG), global efforts to address climate change depend upon Brazil’s ability to meet COP 21 targets.

Economic difficulties are increasing conflicts over land and other natural resources, putting Brazil’s environmental achievements at risk. Forests and global food supply chains are at risk without sustainable investments in low carbon development.[24] The worst effects of climate change will affect the North and North East regions, the poorest regions in Brazil, and exacerbate regional and income inequalities. Without immediate action, climate change in Brazil will result in an estimated annual average loss of between 0.5% and 2.3% of GDP per capita by 2050.[25] Women and girls are disproportionately affected; in Brazil, many women’s livelihoods are dependent on climate-sensitive sectors such as subsistence agriculture, forestry and water. Women and girls can typically have less economic capacity and access to resources than men and boys to enable them to adequately prepare for and adapt to climate change.[26]
[24] In December 2015, 193 countries signed the Paris COP 21 agreement to keep global warming below the 2 degrees centigrade limit. It will require that global net GHG emissions approach zero by the second half of the century (IPCC 2014).
[25] The Economics of Climate Change in Brazil:Costs and Opportunities
[26] Coêlho A., Adair J., Mocellin J. Psychological responses to drought in northeastern Brazil. Interamerican J. Psychol. 2004;38:95–103

Brazil remains one of the most unequal countries in the world: inequality is around five times greater than in OECD countries and progress has halted (Figure 1). Brazil scores 51.9 and ranks 129th of 145 countries on the Gini Index. Before fiscal transfers, Brazil is the 23rd most unequal of the world’s 26 upper-middle income countries; after fiscal transfers, it only improves to 18th.[27] Inequality in Brazil is compounded by lack of competition, high levels of corruption[28] and unequal access to education and health – Brazil scores next to last in terms of the quality of its health services compared to the other 26 upper-middle income countries globally.
[27] World Economic Forum, Inclusive Growth and Development Report 2015
[28] Brazil is ranked 76 in the Transparency International’s corruption perception index (CPI).

Brazil ranks 79th out of 144 countries in the 2016 World Economic Forum Gender Gap Report.[29] Brazilian women have close parity to men in terms of educational attainment and health. However in terms of economic participation and political empowerment, there is significant disparity. Brazil has the largest gender gap in salaries in Latin America – 29.7%[30] and also the lowest percentage of seats held by women in parliament in the region – 9.9%.[31] Global evidence confirms a correlation between gender equality and GDP per capita, the level of competitiveness and human development.[32] This programme will seek to create opportunities for women’s economic empowerment and access to job opportunities and ensure that gender inequality in Brazil is not worsened.
[29] Global Gender Gap Report 2016. World Economic Forum
[30] IADB, New Century, Old Disparities – Gender and Ethnic Wage Gaps in Latin America IDB Working Paper Series 109. Note: The gap increases to 31.4% when there are children on the household, much greater than in Chile [18.6%], Mexico [10.5%] or Colombia [6.3%]).
[31] World Bank - Gender Data Portal.
[32] World Economic Forum - The Case for Gender Equality
### B. The need: reduce “custo Brasil”, the structural barriers to Brazil’s productivity which are preventing growth and continued poverty reduction

The recent economic crisis has unveiled critical structural deficiencies in Brazil’s economy

Brazil cannot replicate the sources of its earlier economic growth, driven by rising commodity prices, increased official participation in labour, demographic changes creating a sizeable young workforce and wide extension of credit.

Productivity per worker in Brazil remained at roughly the same levels between 1950 and 2010. World Bank analysis states: “It is now widely accepted that a systematic increase in Brazil’s labour productivity and Total Factor Productivity will be needed if the growth-with-social-inclusion that prevailed in the 2000s is to return”.

Brazil must increase productivity by reducing ‘custo Brasil’

Reduced labour outputs means that Brazil can only raise productivity by improving industrial efficiency, but Brazil’s closed industrial policy of protectionism, backing national champions, has traditionally supported and protected less efficient industries, stifling competition and reducing the need for firms to innovate. Structural barriers to Brazil’s productivity must be urgently addressed through significant changes to the status quo.

Brazil also faces a massive energy infrastructure challenge, requiring an estimated cumulative investment of £365bn by 2030. Brazil’s future development depends on sufficient energy to power its economic growth. Total energy demand is expected to increase 60% by 2030.[33] Electricity demand is expected to increase by 80%, requiring 349TwH[34] of further generating capacity (equivalent to that of the UK and Portugal combined). Despite relatively high levels of access to energy overall, more than 6m people still do not have access to electricity.[35]
[33] National Energy Plan 2030
[34] The most recent forecast of electricity demand in Brazil is that it will reach 535TwH by 2021. We assume the same average growth rate for electricity demand for the remaining years after 2021 up to 2030 as applied in the National Energy Plan, i.e. 4.3% (CAGR) giving an estimate of 781 TwH in 2030, or 67% more than in 2017. Assuming 3.5% (CAGR) electricity demand growth 2022-2030 implies a 56% growth in demand over 2017 levels. A middle estimate, which we adopt in this business case, implies a 60% growth in demand or 290 TwH roughly equal to the entire generating capacity in 2016 of Italy. 1ª Revisão Quadrimestral das Projeções da demanda de energia elétrica 2017-2021 p. 9 and National Energy Plan 2030 p.180.
[35] Newspaper G1: Milhões de brasileiros ainda não têm energia em casa, diz Aneel

Brazil’s energy matrix is already one of the most diverse in the world with over 40% coming from renewable sources compared to a world average of 15%. Despite this, the energy sector is the highest emitter, contributing 36.6% of Brazil’s CO2; emissions from energy more than doubled between 2005 and 2012 from 16% to 37%.[36] Brazil must therefore meet its future energy needs from a wider range of renewable technologies, managing its power network effectively to integrate these.
[36] MCTI (Ministry of Science and Technology)

Measures to cut energy emissions include sourcing 33% of energy from non-hydro renewable sources by 2030, including 27% of electricity from solar, wind, and biomass by 2024. To absorb intermittent generation and integrate renewables onto its electricity grid, a wider range of technologies – such as battery storage and smart grids – need to be demonstrated and deployed at scale.

To attract the vital investment needed to maximise potential, Brazil will first need to address its complex regulatory environment. In May 2017, signalling its ambition to adopt international best practice, Brazil announced its formal application for accession to full membership of the OECD. The OECD has analysed the negative impact of local content requirements to industrial competitiveness and long term growth.[37] Membership requires members to adhere to its core value of an open and transparent market-economy. Brazil’s accession offers a window of opportunity for sustained engagement on improving the effectiveness of local content and creating a more open and transparent energy sector. Brazil’s electricity sector reforms – which to date have been modelled on the UK’s – will further benefit from adopting UK approaches.
[37] The economic impact of local content requirements - OECD

The lack of long term liquidity in Brazil’s capital markets is one of the biggest challenges to tackling Brazil’s critical infrastructure gap – particularly for the sustainable investments that are essential if Brazil is to meet its COP 21 commitments.[38] Despite the Government’s best efforts to attract international investment into infrastructure over the past years, there is still the need of capital flow to Brazil from domestic or international markets.[39] While the standard of financial markets and banking are of a very high standard in Brazil, a history of hyperinflation, high real interest rates and unsustainable public-sector subsidies has crowded out private finance and meant that Brazil’s capital markets remain underdeveloped. At 37% of GDP, Brazil’s capital market liquidity levels compare unfavourably to the UK (95%) and are identified by Brazilian business as outweighing negative impacts of corruption, political instability and tax rates.[40]
[38] Sustainable and resilient infrastructure integrates Environmental and Social Governance (ESG) aspects into a project’s planning, building and operating phases while ensuring resilience in the face of climate change or other shocks such as rapid migration, natural disasters or economic downturns. Service needs will be met in a manner that minimizes or reverses environmental damage, improves social equality and does not waste resources. The United Nations include the potential of infrastructure in their proposal for the SDGs by directly mentioning sustainable and resilient infrastructure in two of the 17 SDGs (UNEP, 2016)
[39] Projeto Crescer
[40] World Bank survey 2014

Brazil is one of the most closed economies in the world with trade to GDP at 26.9%, and is the most closed economy among G20 countries.[41] Historical imports substitution policies, incentivising internal production of most goods and applying high-tariffs on imported products, mean imports have commonly been seen as a threat. Although protectionist policies generated growth in Brazil for some time, long-term, it fostered the lack of competition which now puts Brazil behind in global trade chains. Reforms to increase trade openness are underway but could go further.
[41] Openess to International Trade Index 2016 – International Chamber of Commerce
### C. Why should HMG intervene?

Critical areas of Brazil’s reform agenda can be amplified by targeted support from its partners, including the UK. An example is Brazil’s application for accession to the OECD, which is potentially transformational in terms of embedding microeconomic reforms, providing a self-enforcing reform mechanism and orientating Brazil towards more outward facing global relationships. Other reform areas where UK support can add value include implementation of a trade facilitation strategy; measures to increase private investment in long term infrastructure financing; and opening up Brazil’s energy markets.

Other critical areas of the government’s current focus lie beyond the scope of influence of Prosperity Fund cooperation, e.g. macroeconomic imbalances, labour market and pension reforms. These primarily require domestic political negotiation rather than simply technical cooperation.

The UK has the right strategic expertise to demonstrate success

The proposed Prosperity Fund in Brazil deliberately targets the areas where UK strategic expertise and existing strong partnerships add value to help reduce structural barriers to productivity and create the conditions for growth in key sectors. Brazil’s determination in moving forward on its reform agenda gives confidence that Prosperity Fund support in the areas where Brazil has expressed demand for UK cooperation is timely and can help Brazil achieve a higher growth and poverty reduction trajectory during this inflection period. Successful UK-funded interventions will demonstrate ‘what works’ for productivity growth and improved market efficiency, giving Brazil and others the confidence to replicate this at scale to unlock more of Brazil’s economic potential.

The UK has a strong track record in supporting Brazil’s reform agenda, including investments via the previous Prosperity Fund of over £14m from 2011 to 2016 which showed effective results.

The scale of Brazil’s economy and its global political influence makes it of significant strategic global importance, including to the UK. Brazil is a driver of both regional and global economic growth and an important like-minded partner for the UK in the multilateral arena, amplifying the UK’s voice in fora where Brazil’s influence is stronger. Brazil has the potential to play an even greater role in international cooperation and promotion of shared norms and standards, including in trade.

The programme supports HMG priorities in Brazil to ensure that the bilateral trade and investment relationship fulfils its potential; that structural reforms result in a more open, competitive environment; and that the UK’s prosperity is promoted by opening markets, driving economic reform, and championing British business and sustainable economic growth. Cooperation with Brazil on trade issues is becoming increasingly important in the context of Brexit and our relationship through the WTO. Our Prosperity Partnership lays the foundations for further positive working relationships on trade, of which more efficient and less costly trade operations as well as an increased pool of companies trading in different sectors are important areas.

The UK is well-placed to respond to the expanded opportunities that are likely to emerge if reforms in these sectors in Brazil are successful. Brazil and the UK have long historic trade and investment ties across diverse sectors of the economy. Brazil is the top destination for UK exports to Latin America and the UK is Brazil’s 14th top supplier.[42] UK goods exports to Brazil more than doubled between 2005 and 2015. UK services exports to Brazil have also increased significantly, 59% higher in 2014 than in 2009. The UK is also the 15th largest market for Brazilian exports and the 14th immediate destination for Brazilian direct investment.
[42] 37% of UK exports to the region.
### D. What are the main programme activities?

Selection of sectors for bilateral Prosperity Fund activity in Brazil

This business case focuses specifically on reducing “custo Brasil” – the cost of doing business in Brazil.

Working in the Prosperity Fund sectors of Energy, Green Finance, Future Cities, and Trade is likely to lead to the greatest overall primary benefits to Brazil and potential secondary benefits to the UK. These sectors are therefore considered to demonstrate the most efficient allocation of Prosperity Fund resources in Brazil.

Within each identified sector, scoping was undertaken to determine a range of possible interventions to address productivity barriers.

Trade: reducing transition costs and diversifying market opportunities

This programme builds on Brazil’s efforts to facilitate trade and integrate into global markets as a source of growth. It aims to supports Brazil’s economic development by reducing the costs of trade and time of transactions, and increasing participation of Brazilian MSMEs in global value chains, in turn creating jobs. The UK Investment of £16m will:

1. Provide technical assistance and capacity building to support Brazil to align itself with OECD standards. (£2m)
2. Pilot advanced electronic systems (a Port Community System) to improve the efficiency of ports which handle principal trade flows (including those of the UK), supported by technical assistance and capacity building to improve ports management (£8m);
3. Provide a tailored package of training, mentoring, and technical support to enable targeted sectors of MSMEs to participate in global and UK supply chains. (£6m)

Future Cities: sustainable urban development through smart city technologies

This intervention seeks to advance sustainable urban development in Brazil through the development of smart city technologies in mobility and water, areas in which the UK excels.[43] The programme will support innovations in transport and efficient water management through a smart city approach[44] in order to reduce poverty and boost sustainable economic growth. The programme will pilot innovative technologies for sustainable urban management to demonstrate the benefits of international expertise to address the negative impacts of critically inadequate urban infrastructure, particularly on the urban poor, paving the way for these technologies to become commercially viable and implemented at scale in Brazil. Interventions will aim to improve safety and access to basic infrastructure to the most vulnerable groups, such as the marginalised, informal workers, and women. There is a current demand from city governments for smart city solutions, yet they lack the expertise to do so by themselves. Cities are seeking international partnerships, and the UK could be one of the leading global partners in piloting successful smart city technologies in Brazil. The UK Investment of £10m will:
[43] ICF, 2017. Scoping Study for a Global Future Cities Programme. 18 April 2017. Pg, vii.
[44] UN Habitat III, The New Urban Agenda. https://habitat3.org/the-new-urban-agenda. “We commit to adopt a smart city approach, which makes use of opportunities from digitalization, clean energy and technologies, as well as innovative transport technologies, thus providing options for inhabitants to make more environmentally friendly choices and boost sustainable economic growth.” UN Habitat III, The New Urban Agenda. https://habitat3.org/the-new-urban-agenda.

1. Pilot innovative Smart Mobility technologies in São Paulo to improve traffic flows, improving the quality of life for poor communities, reducing negative impacts on Brazil’s economic development (£5m)
2. Pilot innovative Smart Water technologies in Recife to reduce water lost by leakages, improving the efficiency of water management, and increasing access of the poorest to potable water within integrated urban planning (£5m)

Energy: supporting Brazil’s renewable energy transition

The programme will be delivered via a single UK-Brazil energy partnership, providing a focal point for the entire UK offer on energy regulation, policy making, R&D and innovation. This proposal is unique – there currently is no dedicated energy resource in Brazil able to tackle both regulatory and technology barriers and provide the coordination needed to deliver the proposed impacts. The will support Brazil to meet international standards and best practices; make regulatory reforms to enable the transition to a low carbon economy; promote diversification and tackle market failures to boost investment. It will increase institutional capacity of regulators, policy makers and operators and improve interagency integration. The UK Investment of £25m will deliver the following outputs:

1. Policy and regulation: Improve energy policy, regulation and planning, increase competition, share international best practice and business models across the energy sector, creating an open and transparent business environment and encouraging vital investment (£8.5m);
2. R&D and Innovation: Stimulate investment in innovative technologies to enable Brazil to diversify energy production from a wider range of renewable sources (£16.5m);

Green finance: building the path a low carbon economy through investments in sustainable infrastructure

The proposed Green Finance programme will support the establishment of Brazil’s first ‘green investment vehicle’ within an existing Brazilian development bank, based on the model of the UK’s Green Investment Bank (GIB). A key outcome will be to develop a new comprehensive standard framework for Environmental Social and Governance (ESG) which can be used by the target institution and other development banks in Brazil to design sustainable infrastructure projects which are capable of attracting essential private investment. This ESG methodology will also be used more widely by financial organisations, including pension funds and insurance firms, enabling them to allocate investments to the ‘green’ portfolio in Brazil. To support the Green Investment Vehicle and help consolidate the green finance market in Brazil, the programme will provide capacity building by designing new and improving existing policy and capital market mechanisms, such as green bonds and mezzanine finance. This will increase investment into sustainable projects by balancing the risk profile and improving the investment climate. The UK Investment of £5m will:

i. Provide a tailored package of training, mentoring, and technical support to an existing Brazilian Development Bank to establish Brazil’s first Green Investment Vehicle (£4m);
ii. Design a market framework for capital market and policy instruments for sustainable infrastructure investments (£1m).

The programme is consistent with relevant UK legislation, in particular the requirements of the International Development Act 2002, the International Development (Reporting and Transparency) Act 2006 and the International Development (Gender Equality) Act 2014).[45] It directly contributes to the UK Aid Strategy, specifically the objective to use Official Development Assistance (ODA) to promote economic development and prosperity in the developing world. This will contribute to the reduction of poverty and strengthen UK trade and investment opportunities around the world.[46]
[45] Legislation.gov.uk - International Development Act 2002; International Development (Reporting and Transparency) Act 2006; International Development (Gender Equality) Act 2014
[46] UK AID: Tackling Global Challenges in the National Interest (2015). Action Aid, Women Harrassment Poll. www.actionaid.org.br/news/pesquisaassedio. Folha de Sao Paulo, Nov 8th, 2015. Metropoles, Combat to Harrassment in Public Transport Empowers Women. www.metropoles.com/materias-especiais/combate-ao-assesdio-no-transporte-publico-empodera-as-mulheres

Gender Act:

The Trade programme will seek to ensure that opportunities to support women’s economic empowerment and access to job opportunities are harnessed and that unequal gender access to international markets is not worsened. It will explicitly aim to create jobs and opportunities for more women to participate in international trade. By supporting Brazil to diversify the export base with different types of goods, especially those produced by MSMEs, we will seek to create a more balanced participation between men and women in international trade. The programme will support Brazil’s efforts to reduce gender inequality in trade, guided by the UN High Level Panel on Women’s Economic Empowerment and in consultation with the Brazilian Trade Promotion Agency (Apex). Selection of ports and MSME sectors/geographical locations will be based on a thorough assessment of the potential for job creation, poverty reduction, equitable access and social inclusion and women’s economic empowerment.

The Future Cities programme will seek to promote gender equality in the provision of programme interventions by promoting integrated urban planning towards inclusive growth, combating gender violence with safer urban environments; and by increasing opportunities for women’s economic empowerment. Shorter journey times and improvements to safety will improve the well-being of the poorest and most vulnerable residents, including increasing the economic empowerment of women, for example by making longer, more complex journeys arising from caring responsibilities easier. Access to better transport and safe water increases the possibility of women having better jobs and improves productivity for home-based workers, which in Brazil are mostly women

The Energy programme will work on mainstreaming women’s participation in the energy sector, acting on their role in energy provision and use. It will seek to assess the economic and social costs of energy poverty, particularly on women and girls, including time constraints, allowing women more time for social, economic and civil activities.

The Green Finance programme address gender equality by boosting investment in sustainable infrastructure, positively impacting women and girls, who are disproportionately affected by the impacts of climate change, especially in regions that are the poorest and most lacking in infrastructure, where livelihoods are more dependent on climate-sensitive sectors such as subsistence agriculture, forestry and water.[47] Furthermore, the improvement of gender equality in Brazil depends widely on the positive externalities from increased infrastructure on time allocation and bargaining power of women at home.[48] A World Bank study illustrates that improvements in infrastructure (e.g. rural roads and power grids) diminish the time women spend on family chores, and thus help to increase gender equality across Brazil. [49]
[47] https://www.oecd.org/dac/gender-development/Making-Climate-Finance-Work-for-Women.pdf
[48] (http://siteresources.worldbank.org/EXTPREMNET/Resources/EP109.pdf)
[49] (http://siteresources.worldbank.org/EXTPREMNET/Resources/EP109.pdf)

Sustainable Development Goals:

The UK’s partnership with Brazil on this programme supports UK Implementation of the Sustainable Development Goals (SDGs), in particular SDG 17 – Partnerships for the Goals.[50] The four programme areas address the following SDGs.
[50] House of Commons, 2016. UK implementation of the Sustainable Development Goals: Government Response

Programme Area	UN 2030 Agenda for Sustainable Development[51]
Trade	SDG 1 – Equal rights to Economic Resources / SDG 8 – Decent Work and Economic Growth / SDG 9 – Industry, Innovation and Infrastructure
Future Cities	SDG 11 – Sustainable Cities and Communities / SDG 3 – Good Health and Wellbeing / SDG 6 – Clean Water and Sanitation
Energy	SDG 7 – Affordable and Clean Energy / SDG 13 – Climate Action
Green Finance	SDG 7 – Affordable and Clean Energy / SDG 9 – Industry, Innovation and Infrastructure / SDG 13 – Climate Action / SDG 17 – Partners for the Goals
[51] United Nations - Sustainable Development Goals.

Secondary Benefits:

Removing specific market barriers will increase business opportunities in Brazil, including for the UK. UK business has the appetite, capability and capacity to respond to resulting new opportunities. In summary:
- Less costly and more efficient trade operations in Brazil should create increased trade flows of goods between UK and Brazil.
- An increased and diversified pool of companies trading will also create more opportunities for investment and diversify supply chains, increasing trade flows in different sectors – such as services – where the UK has a competitive advantage, as well as reducing market access barriers.
- Brazilian companies will be integrated into British supply chains in key sectors for economic growth.
- Service exports from the UK will increase and the return on investment to UK and international investors accessing UK capital markets will deliver secondary benefits. They will also be derived from the infrastructure value chain.
- Energy companies will be able secure contracts for innovative products and services or increase their margins through efficiency gains.
UK cutting-edge companies will be able to secure business wins in a scaled up smart city technology sector resulting from increased collaboration and internationalisation.
### E. What are the expected results from the programme?
Sector	Interventions	Cost	Primary Benefits NPV £m	Secondary Benefits NPV £m	Indicative Key Performance Indicators
Trade (£16m)	Provide technical assistance and capacity building to support Brazil to align itself with OECD standards (£2m);	£2m	408.6	52.8	Brazil adheres to 5 selected binding OECD instruments
	Pilot advanced electronic systems to improve the efficiency of ports which handle principal trade flows (including those of the UK), supported by technical assistance and capacity building to improve ports management (£8m);	£8m			Reduce the time for goods to be imported to Brazil by 2 days, and for goods to be exported from Brazil by 1 day in the selected Brazilian ports
	Provide a tailored package of training, mentoring, and technical support to enable targeted sectors of Micro, Small and Medium Enterprises to trade and participate in global and UK supply chains (£6m);	£6m			Double participation of targeted Brazilian MSMEs in international trade from 1% to
Future Cities (£10m)	Pilot innovative technologies to improve traffic flows and the quality of life for poor communities	£5m	74.5	63.6	Reduce traffic congestion in project targeted areas by 10%.
	Pilot innovative technologies that, improve efficiency of water management, and enable the poorest to have proper access to drinking water and sanitation	£5m			Reduce water lost to leakages in project targeted areas by 20%.
Energy (£25m)	Stimulate investment in innovative technologies to enable Brazil to diversify energy production from a wider range of renewable sources	£16.5m	321	52.6	20% growth in renewable energy integrated to the grid; 50% reduction of gas flared and 50% reduction of gas reinjection within the period of the programme
	Improve energy policy, regulation and planning, increase competition, share international best practice and business models, creating an open and transparent business environment and encouraging vital investment	£8.5m			3 key policy changes in the following areas: energy storage; local content in wind, solar and oil and gas; and natural and bio gas
Green Finance / (£5m)	Provide a tailored package of training, mentoring, and technical support to an existing Brazilian Development Bank to establish Brazil’s first Green Investment Vehicle	£4m	1158	109.5	Additional pension fund allocation on renewable and energy efficiency from current 2% to 8% by 2027
	Design a market framework for capital market and policy instruments for sustainable infrastructure investments	£1m			Increased green bond issuance by 7.1% and the percentage of certified green bonds (relative to non-labelled) from current 23% to 62.5% in 2027.

Brazil Prosperity Fund – Theory of Change

## APPRAISAL CASE

INTRODUCTION

This appraisal of interventions builds on the rationale outlined in the strategic case for reducing poverty in Brazil by boosting productivity - working in partnership with Brazilian authorities, industry and communities in trade, energy, future cities and green finance.

A detailed appraisal of interventions can be seen in the attached Annex. We evaluate 11 specific interventions across these sectors which, when combined, amount to our programme. Our economic appraisal uses customized approaches to evaluate both the primary and secondary benefits of interventions planned in each of our four sectors: trade, energy, future cities and green finance. We also appraise the unquantified benefits.

The Programme will boost medium and long term productivity by:
  1. lowering the cost of doing business: reducing time to trade, increasing competition in supply chains, improving long-term green financing and reducing transit times and utility costs.
  2. boosting innovation through more openness to international best practice, attracting more inward investment, seed funding new research and development in sustainable energy, creation of new financial instruments, and introducing new technologies. This dimension features in unquantified benefits.
  3. boosting sustainability through green finance, promoting sustainable energy, and promoting more sustainable cities.

While the interventions we have appraised represent our preferred portfolio, it should be noted that as the political landscape changes and we undertake further inception work and engage the market, we may dial up and down different interventions or adopt new interventions where they can be demonstrated to deliver greater benefits.

Our approach

This programme presents a complex interplay between interventions that aim to:
- assist Brazil to open up its economy to trade and investment and to participate more successfully in global supply chains
- finance and design green development solutions in solar energy, use of gas as a transition fuel, water distribution and transport corridors.

We have categorised three types of primary benefits for Brazil from the programme: monetised benefits, non-monetised benefits and pro-poor benefits (which are subset of non-monetised but important to distinguish given the programme’s focus on poverty reduction). It will also generate two types of benefit to the UK (monetised and non-monetised). We cover all these benefits in this economic case with numerical assessments where possible; for the pro-poor and the non-monetised benefits we have followed an evidence-based approach drawing on economic theory where the robustness of quantitative analysis was especially uncertain or challenging.

We discount these monetised benefits by three factors:
  1. Additionality: the UK Prosperity Fund impact varies according to the various factors described in the do nothing scenario.
  2. Risk: chances of success fall as intervention complexity and the power of groups that perceive that they may lose rise.
  3. Time value of money: we use a 10% discount rate for primary benefits and a 3.5% discount rate for secondary benefits.

The key primary benefits monetised in this Economic Case are:

Opening Up:

The increase in Brazilian exports through
    1. reduced time in transit of goods in key Brazilian ports.
    2. capacity building of Brazilian MSMEs to export.

The increase in investment in Brazil and/or income and more efficient allocation of capital through
    1. Brazil signing more double taxation agreements (which allow companies to move goods between different countries without paying tax twice) as a result of OECD accession.
    2. Brazil improving its ranking on the OECD services competitiveness index.
    3. more green infrastructure built
    4. more competitive energy supply chains.

Sustainable Development:

The increase in investment and/or income through
    1. regulation and roll out of energy storage coupled with solar power installations
    2. reduced water leakages due to adoption of better technology
    3. reduced transit times through transport corridors with better traffic light control technology that prioritises public transport
    4. a Green Investment Vehicle at Brazilian State Development Bank BNDES
    5. Green Mezzanine Finance instruments at BNDES.

We add up the total estimated benefits as contributions to Gross National Income (GNI). Counting the value of additional exports, or reduced imports or increased physical capital formation we focus on spending that generates the national income. At other times we look directly at increased profits, wages, rent or interest payments – the income perspective. These are alternative points from which to measure the flow from production of final goods and services to sale/spending to income.

The key secondary benefits monetised in this Business Case are:

Opening Up:
  1. The increase in UK exports to Brazil through reduced trading costs at key Brazilian ports.
  2. exports of intermediate goods to Brazilian MSMEs for their use in production of goods to export (re-exporting the intermediates.)
  3. Brazil’s improvement on the OECD services competitiveness index.
  4. Selling into more competitive energy supply chains.
  5. higher demand for UK exports due to the overall impact of the combined interventions on Brazilian GNI.

The increase in investment and income through
  1. Increased FDI flowing from Brazil to the UK due to Double Taxation Agreement
  2. Higher repatriated profits on increased UK ODI flowing to Brazil due to Double Taxation Agreement

Sustainable Development:

The increase in UK exports to Brazil due to
  1. Supply of energy storage technologies
  2. supply of better technology to reduce water leakages
  3. supply of traffic light control systems to enhance transport corridors

The increase in UK Investment and/or Income through
  1. Returns on investment to UK investors in assets developed through a Green Investment Vehicle
  2. UK investment returns, or UK insurance or reinsurance receipts, on investments financed through Green Mezzanine Finance.

The recommended option achieves a Primary Benefit-Cost Ratio (BCR) of £37 for every £1 spent, which falls in the high value for money category and a Secondary Benefit-Cost Ratio of just under £7.90 for every £1 spent medium to high value for money.

The alternative option Primary BCR is lower at £36 per £1 spent. While the Secondary BCR is higher at just under £8.30 per £1 spent.

We choose the recommended option because

  1. it delivers higher primary benefit and therefore is more justifiable on ODA criteria
  2. it promises more pro-poor and pro-women unquantified primary benefits
  3. it fits better in terms of mutually reinforcing components
  4. expansion of the Future Cities programme within the bilateral programme does not consider the reinforcing effect of the Global Future Cities programme in spreading the innovations of the bilateral programme to other Brazilian cities.

The sensitivity analysis varies between a low Primary BCR of £19 for every £1 spent, and a high BCR of £80 for every £1 spent. Rates of return are positive even in the low scenario (lower undiscounted benefits, lower additionality, higher risk) showing that the economic case for the recommended option is robust.

In terms of secondary benefit, the low Secondary BCR is just under £2 per £1 spend, while the high Secondary BCR is just under £14 pounds per £1 invested. Our central Secondary BCR is just under £6 per £1 spent. This is a medium level BCR.

OPTIONS APPRAISAL
OPTIONS APPROACH

The approach for options analysis has the following three scenarios:
1. Do nothing: In this scenario, the UK Prosperity Fund does nothing for poverty alleviation in Brazil, implying the costs and the associated benefits are zero.
2. Central Scenario: In this scenario, the UK Prosperity Fund spends a total of £56 million in Brazil across six interventions, where the costs and the associated benefits are such as proposed in the business appraisal case.
3. Options Scenario: In this scenario, the UK Prosperity Fund spends a total of £56 million in Brazil, however the costs and the associated benefits are different across the six interventions to the ones proposed in the central scenario.

Options Scenario

Options analysis is conducted to provide the UK Prosperity Fund with an alternative portfolio of expenditure on the six interventions in Brazil, based on their scalability, initial costs and associated risks and the primary benefit-cost ratio in the central scenario. The main assumption is that the total funds available from the UK Prosperity Fund is fixed at £56 million for expenditure in Brazil under the bilateral programme. A major limitation of this approach is that it is not able to capture non-monetary benefits in the assessment.

The following approach entails how the decisions to scale costs of interventions is arrived at:

Scaling down approach gives interventions likely to be scaled down

Selection of interventions for scaled down costs and benefits in the options scenario

Source: Vivid Economics
- Step 1: Choose interventions that are fully scalable or partially scalable based on the nature of the intervention. For example, an intervention is scalable if it is around proving technological support or capacity building but is not scalable if it is a regulatory or market-design intervention, which is viewed binary that either delivers or fails.
- Step 2: Choose interventions which have present value of costs is more than 25% of the entire portfolio as well as a risk factor of more than 50%. This step captures high-costs, high-risks interventions.

Scaling up approach gives interventions likely to be scale up

Selection of interventions for scaled up costs and benefits in the alternative portfolio

Source: Vivid Economics
- Step 1: Similar to step 1 in the scaling down approach, choose interventions that are fully scalable or partially scalable based on the nature of the intervention.
- Step 2a: Choose interventions with primary benefit-cost ratio of greater than 50, which is considered highly beneficial to the Brazilian economy.
- Step 2b: Choose interventions with risk lower than 25%, which implies scaling up has higher likelihood of success.

We assess the total costs and associated risks, as well as the benefit-cost ratio for the four sector interventions: trade, finance, future cites and energy to arrive at a different portfolio of costs for the options scenario.

Summary of total costs, primary benefits, BCRs and risk factors proposed for the UK Prosperity Fund Intervention
Intervention	Total costs (£ million, present value)	Total primary benefits (£million, present value)	Primary Benefit-Cost Ratio	Aggregated risks*
Trade	15	409	27	54%
Finance	5	1,158	232	63%
Future Cities	9	75	8	23%
Energy	23	321	14	48%

Note:	Aggregated risks are a simple average of risks for all interventions within a sector, which is why it might fail to reveal the true risk of intervention in that sector
Source: Vivid Economics
Based on criteria set out to scale up or down interventions and figures above, we propose the following diversion of funds to optimise total benefits and the expenditure in Brazil:
- fraction of funds from trade interventions are diverted due it its high-cost and high-risk nature; costs make up around 30% of the total funds for trade when the risk of success is more than 50%.
- fraction of funds from energy interventions are diverted due to similar reasons to trade; costs make up around 45% of the total funds available when the risk of success is quite high[52].
  [52] Although the aggregated risk for energy intervention is less than 50%, it is important to note the simple aggregation is misrepresenting the high-risk nature of this intervention as the aggregated risk factor is made of four individual risk factors
- the diverted funds from the above two interventions received by future cities, due to ease of scalability as well as low-risk involved at 23%.
- the diverted funds from energy and finance also received by finance interventions, that have a very high potential to generate greater primary benefits to Brazil, evidenced by the high benefit-cost ratio.
The exact change in the portfolio of costs is given in the Figure above.

Differences in portfolio in the central and options scenario

Source: Vivid Economics
Benefits assessment in the options scenario

The primary benefits in the options scenario is estimated for each intervention that undergoes a change in costs in the options scenario:

- Trade: benefits from trade intervention are reduced:
    - Ports: benefits same as the central scenario
    - MSMEs: benefits are reduced from reduced outreach in the form of number of MSMEs targeted by the intervention, specifically one-third of the number assumed in the central scenario
    - OCED: benefits are unchanged
- Future Cities: benefits from future cities intervention go up:
    - Mobility: increased benefits from inclusion of two additional cities in the programme, specifically primary benefits from additional 440 junctions informed by Recife and Fortaleza traffic statistics
    - Water: increased benefits from increase in the population from three additional cities benefited by intervention, specifically from Recife, Fortaleza and Teresina.
- Energy: benefits are reduced in the options scenario:
    - Natural gas: quantified primary benefits remain the same even as costs are reduced, as costs reduction is done to the proportion of funds accruing to R&D, the benefits from which are not quantified in the primary benefits analysis[53].
      [53] R&D will leverage the 1% oil and gas R&D levy into key areas to make natural gas distribution carbon neutral e.g. carbon capture and methane leak detection and reduction. The consequence of reducing funds for R&D is that some new areas of research to ensure a clean gas transition that the Prosperity Fund would fund will not happen.
    - Energy storage: reduced benefits from increase in the risk profile of the intervention due to reduced funds from the Prosperity Fund, captured by decreased installed energy storage capacity for total electricity output, specifically assuming it to be 2%
    - Competitive supply chain: reduced benefits as the intervention is only able to target oil & gas sector with the available funds, so primary benefits from renewables sector is zero .
- Finance:
    - GIV: increase in benefits from capacity building and training support on additional municipal waste projects
    - Mezzanine: benefits stay the same

The direct secondary benefits in the options scenario is estimated for each intervention that undergoes a change in costs in the options scenario:
- Trade: benefits from trade intervention are reduced.
    - Ports: benefits same as the central scenario.
    - MSMEs: benefits reduction proportional to decrease in primary benefits.
    - OCED: benefits are unchanged.
- Future Cities: benefits from future cities intervention go up
    - Mobility: benefits increase from additional 440 junctions.
    - Water: benefits proportional to increase in primary benefits.
- Energy: benefits are reduced in the options scenario
    - Natural gas: benefits stay the same.
    - Energy storage: reduced benefits are proportional to decrease in primary benefits.
    - Competitive supply chain: secondary benefits only from the oil & gas sector considered.
- Finance:
    - GIV: increased benefits proportional to increase in primary benefits
    - Mezzanine: benefits stay the same

The indirect secondary benefits in the options scenario is estimated for energy and finance interventions that undergo change in costs in the options scenario:

- Finance: increase in indirect benefits proportional to increase in primary benefits.
- Energy: decrease in indirect benefits proportional to decrease in primary benefits.
- Future Cities: increase in indirect benefits proportional to increase in primary benefits.
- Trade: decrease in indirect benefits proportional to decrease in primary benefits.

Summary table Central Scenario
Intervention	PV of costs (£m)	PV of primary benefits (£m)	PV of secondary benefits (£m)	BCR Primary Benefits	BCR Secondary Benefits
MSMEs	6	80	28	13	5
OECD	2	111	2	56	1
Ports	7	208	10	28	1
GIV	4	38	2	10	1
Mezzanine	1	1,083	105	1,083	105
FC Mobility	5	62	62	14	14
FC Water	5	18	2	4	0.3
Natural Gas	10	106	2	10	0.2
Energy Storage	10	82	47	8	5
Competitive Supply Chain	3	188	15	68	5

Source:	Vivid Economics
Summary table Options Scenario
Intervention	PV of costs (£m)	PV of primary benefits (£m)	PV of secondary benefits (£m)	BCR Primary Benefits	BCR Secondary Benefits
MSMEs	4	66	23	18	6
OECD	2	111	2	56	1
Ports	7	208	10	28	1
GIV	6	75	4	13	1
Mezzanine	1	1,083	105	1,083	105
FC Mobility	9	84	105	9	11
FC Water	9	37	3	4	0.32
Natural Gas	6	106	2	16	0.32
Energy Storage	6	66	47	10	38
Competitive Supply Chain	1	74	15	80	4

Source:	Vivid Economics
We recommend the central scenario estimates over the options scenario. In the options case, primary benefits are lower than the central scenario, but secondary benefits are higher. However, the options analysis only considers quantified primary benefits and fails to capture the change in unquantified benefits coming from change in the distribution of resources across the portfolio. Unquantified benefits represent high growth impacts to Brazilian and the UK economies and therefore are important to consider, such as:
- diverting funds from MSMEs intervention in the trade sector will slow down the development of women and minority-led small businesses, impeding progress on reducing inequality. The target number of 10,000 MSEs is deliberately scaled so as to attain scale for women, poor and minority-led businesses (e.g. led by entrepreneurs with disabilities).
- diverting funds from natural gas intervention in the energy sector endangers the development of low carbon research and infrastructure in the gas sector. In particular, we need a certain scale of funds to effectively leverage the 1% R&D levy into sectors that individual oil and gas companies do not automatically tend to go. For example, in natural gas, for it to be even cleaner, research is needed in how best to strip out carbon dioxide and how to detect and reduce methane leaks in distribution.
- diverting funds from competitive supply chain in the energy sector reduces the likelihood of renewables development in Brazil, which negatively impacts Brazil’s ability to reduce GHG emissions. In particular, if solar sector development remains constrained by an uncompetitive supply chain it will likely constrain the roll out of distributed energy storage and the development of the Green Investment Vehicle in this sector.

SENSITIVITY ANALYSIS

As the economic models used to determine the primary and secondary benefits are based on numerous assumptions, which introduce uncertainty, a sensitivity analysis was carried out for all interventions to understand the effects on the results of the model of varying the inputs.

For each intervention, we tested three scenarios in the sensitivity analysis:
Low Case: In the low scenario, we estimated the impact of the programme using conservative estimations for the inputs. The activities implemented were assumed to have a limited impact; and assumptions surrounding projections, additionality and risk were set to pessimistic values (for example, using IEA “Current Policies” projections)

Central Case: The central scenario sets out a realistic and achievable impact that has a high chance to be sustainable after the programme duration. The activities implemented were assumed to have a realistic impact; and assumptions surrounding projections, additionality and risk were set to realistic values (for example, using IEA “New Policies” projections)

High Case: The high case sets out what impacts could be attained if the programme achieved its most ambitious aims. The activities implemented were assumed to have a strong impact; and assumptions surrounding projections, additionality and risk were set to optimistic values (for example, using IEA “Sustainable Development” projections)

For simplicity, only inputs for the assumptions considered to be the most important or uncertain have been varied and tested in the sensitivity analysis. These variables are summarised in the tables below, and are explained in greater detail in the technical annexes for each individual intervention, with a rationales given for their selection and the values used.

The results of the sensitivity analysis for primary and secondary benefits are summarised below:

Primary Benefits
Results of Sensitivity Analysis for Primary Benefits by Programme/Intervention
Programme/Intervention	Primary PV (£m)			Main Assumptions varied in Sensitivity Analysis / (see Technical Annex X for details of values / rationale)
	Low	Central	High
Total - Primary Benefits	1,107	2,088	4,280	See below
Trade Programme	140	561	2,007
OECD accession	16	273	1452	Added GDP; Increase in FDI; Additionality; Risk
Port Management	93	208	436	Import/Export times; Additionality; Risk
MSMEs in Int'l Trade	31	80	118	MSE growth; Export growth; MSE Export Share; Additionality; Risk
Future Cities Programme	27	68	179	X% water saved. Roll out of system by number of pressure management zones.
Traffic Flow	13.8	49.7	132.7	Impact on traffic by X%. Roll out by number of junctions. Additionality.
Water Management	14	18.5	47	Impact on water leaks by X%
Energy Programme	246	331	611
Energy Storage	37	37	198	Rollout to X% of system; gain from deferred transmission investment
Natural Gas	54	106	175	Volume of additional gas sold and increase in gas net exports / Number of new onshore gas pipelines built
Competitive Energy Supply Chains	155	188	238	Gross value added in additional investment. / Productivity impulse.
Finance Programme	690	1,121	1,511
Green Investment Vehicle	37	38	43	Finance market for energy storage (based on projected solar PV capacity)
Mezzanine Finance	652.3	1,083	1,468	% infrastructure projects supported by private finance

As the table above shows, although there is some variability in the results of the model depending on the inputs used, all four programmes are expected to give strong, positive primary benefits under all scenarios. In all cases, including all Low scenarios, the expected benefits of the interventions at least outweigh the costs of the programme; in most cases greatly exceeding that.

Over the 10 years of the programme, the overall Net Present Value of the primary benefits of the Brazil programme are expected to be between £1.2bn and £3.4bn, representing a very strong return on investment.

Overall Results of Sensitivity Analysis for Primary Benefits (NPV)
	Net Present Value (£m)
	Low	Central	High
Total Primary Benefits (Net)	1,024	2,010	4,230

Overall Results of Sensitivity Analysis for Primary Benefits (NPV)
Secondary Benefits
Programme/Intervention	Secondary PV (£m)			Main Assumptions varied in Sensitivity Analysis / (see Technical Annex X for details of values / rationale)
	Low	Central	High
Total - Secondary Benefits	154	364	796	See below

Trade Programme	21	159	440
OECD accession	5	115	367	Increase in FDI; UK Share of FDI; Additionality
Port Management	5	10	31	UK Exporter Reduced Trading Costs; Risk
MSMEs in Int'l Trade	11	34	42	Linked directly to assumptions in Primary Benefits calcs

Future Cities Programme	37	37	37
Traffic Flow	31	19	93	Roll out by number of junctions
Water Management	1	18	3	Roll out by number of pressure management zones

Energy Programme	35	57	107
Energy Storage	24	47	94	Linked directly to assumptions in Primary Benefits calcs
Natural Gas	0	2	4	Linked directly to assumptions in Primary Benefits calcs
Local Content	11	8	13	Linked directly to assumptions in Primary Benefits calcs

Finance Programme	68	107	150
Green Investment Vehicle	2	2	2	Linked directly to assumptions in Primary Benefits calcs
Mezzanine Finance	66	105	148	Linked directly to assumptions in Primary Benefits calcs

As the table above shows, although there is some variability in the results of the model depending on the inputs used, all four programmes are expected to give strong, positive secondary benefits under most scenarios. In almost all cases the expected benefits of the interventions at least outweigh the costs of the programme, with the exceptions being
  1. the low scenario cases for Natural Gas (however, the central and high scenarios for this intervention do show positive net benefits to the UK, and the intervention has a strong expected primary benefits, so it still represents good value).
  2. the secondary benefits from intervention in Water in Recife but these assume conservative roll out and do not take into account the synergy in terms of roll out in other cities that will exist between this intervention and the Global Future Cities programme working on planning in other cities. The primary benefits here, especially the unquantified benefits for the poor make this a good value for money intervention.

Over the 10 years of the programme, the overall Net Present Value of the secondary benefits of the Brazil programme are expected to be between £84m and £705m, representing a strong return on investment.

Overall Results of Sensitivity Analysis for Secondary Benefits (NPV)
	Net Present Value (£m)
	Low	Central	High
Total Secondary Benefits (Net)	76	286	718

APPRAISAL OF SOURCES

The estimates in this Appraisal Case use a mix of sources.

  1. Official data in Brazil is rich and of high quality and has been used throughout. We have also used official UK data and internationally available data from reliable sources like the international financial institutions.
  2. We have also used research output of a variety of Brazilian industrial and professional associations. These are long-standing groups that represent sectors and benefit from tax revenue allowing them to develop research capacity.
  3. To determine parameters we have used peer reviewed academic articles and academic work by international financial institutions like the World Bank, the IADB, the IMF and others like the WTO.
  4. Where we have had questions we have corresponded directly with the academics who have completed these studies, notably in Energy Storage and competitive supply chains.
  5. We have contacted companies directly to discuss parameters relating to specific technologies e.g. transport and water.

Wherever possible we have tried to use studies that relate directly to Brazil. This was not always feasible, e.g. studies on benefits from energy storage (not yet implemented in Brazil) and a study on the productivity effect of more competitive energy supply chains.

In several interventions, we have approached the estimates from more than one academic angle to cross check. e.g. Green Investment Vehicle using anchor sector bottom up approach and cross checking using a top down scaling by UK Green Investment Bank experience, or ports using Latin American case study results and also the results from a computerized general equilibrium model of Brazil. Triangulating using a variety of sources strengthens our confidence in our estimates.

Where the academic work we use employs a specific economic technique we have endeavoured to be explicit about that technique and to highlight any issues that might affect the parameters substantially. So for example we note that,
    1. tax havens are not taken into account in studies of the effects of double taxation on investment flows.
    2. the computerized general equilibrium model used in the ports estimates has no internal frictions - unlike Brazil.

When doubt about the accuracy of a source or its applicability to Brazil we have used sensitivity variance to allow for plausible ranges or confidence interval around the estimate. For example we do not know:
    1. future Brazilian export growth so we take an estimate by Oxford Economics and HSBC and scale it within plausible ranges as a baseline for the MSE intervention.
    2. the investment and productivity effects of more competitive energy supply chains. So, we scale our central estimates for high and low scenarios.

Reports and studies generated under the former Prosperity Fund have been important inputs into this Business Case, for example,
          1. estimates of the impact of improvement in services competitiveness (Arbache study);
    2. estimates of the impacts of more double taxation agreements in Brazil (EY study);
    3. estimates of the economic case for energy storage (ABRADEE study).

Economic consultancy has also greatly assisted the iterative process in generating these estimates. Various reports including by Oliver Wyman, KPMG and more recent work by Palladium and Vision Economics have all enriched the analysis in this Appraisal Case.

An extensive set of footnotes are provided throughout which give access to these sources.

In many cases, the sources are in Portuguese. Given the richness of the empirical and academic work available in Brazil this Appraisal Case would have been severely limited if we had restricted ourselves to English language sources only.

COMMERCIAL CASE

Commercial Requirements Overview

Overview of each Strand

The Appraisal Case identified the preferred options for the Brazil Prosperity Fund portfolio working across each of the thematic areas of: Trade, Green Finance, Energy and Future cities.

Summary of procurement model for each strand:
- Trade: One Memoranda of Understanding (MoU) with the OECD (already finalised) to deliver support for Brazil’s reforms to meet OECD accession criteria, and, one contract procured via the PF framework to deliver i) support to MSMEs and ii) port efficiency. Based on recent market feedback, while our preference is for one supplier to programme manage both strands,
- Green Finance: One contract through the PF Framework to deliver all interventions.
- Energy: One contract through the PF Framework, with the expectation that there will be sub-contractors or a consortia delivering the different strands of the programme given the varied skillsets required on regulation and running a grant competition required and the level of local knowledge, expertise and and networks necessary.
- Future Cities: One MoU with the World Bank to deliver the programme with the first year of transitional activity covered by an EFO (Externally Financed Output). The EFO has already been finalised and we expect the MoU to be completed within the next 6 months.

To deliver the outputs outlined above, the following types of supplier services will be required. Examples of each are illustrated below:

Brazil Prosperity Fund Sector	Type of Supplier Services Required
Energy – Delivered through Framework	Management services / Advisory services / Delivery services
Green Finance – Delivered through Framework	Management services / Advisory services / Delivery services
Future Cities – Delivered through MOU with World Bank	Management services / Delivery services
Trade – OECD strand delivered through MOU with OECD. Other strands (e.g. SMEs and Ports) through Framework	Management services / Advisory services / Delivery services

Given the complex operating environment, we expect that implementers will need to bring together a diverse skillset to effect real and lasting change in Brazil by delivering the outputs outlined above. This will include expertise in delivering large-scale, mulit-year aid programmes, the ability to operate in the, at times, bureaucratic regulatory and legislative Brazilian landscape in partnership with Brazilian authorities and institutions, knowledge of Brazilian market operation to tailor innovations to have maximum impact and expertise in the UK’s commercial strengths to foster productive partnerships.

Implementing partners will each be responsible for coordinating participation of non-commercial partners in the programme, where needed. The implementers are likely to need to engage with Other UK Government Departments (OGDs) and arm’s length bodies (ALBs) who can provide technical expertise to support the detailed design and implementation of the portfolio. The implementers will also need to know the UK’s strengths in innovation and will want to construct this from commercial, semi-commercial (such as the UK’s network of catapults, incubators and innovation support and grant programmes) and academic sources. For specific interventions within some sectors of the Brazil programme, e.g. Energy, Green Finance and Trade, we will underpin partnerships with MOUs signed by the Brazilian and/or ML institutions to leverage greater impact, secure additional funds from partners and create lasting institutional links.

Delivery model and Procurement

Procurement for the majority of our portfolio will be via the Prosperity Fund Framework Agreement, which offers the following advantages compared to a direct procurement approach:
  1. Access to pre-qualified suppliers with the proven experience and capacity to implement large-scale programmes and on whom due diligence has been carried out centrally, significantly reducing procurement timescales;
  2. Prior agreement of key contractual terms for local delivery and central management of performance by FCO’s Procurement Group, reducing transaction costs at Post;
  3. Flexibility for suppliers to meet specific requirements through subcontracting or forming consortia with other suppliers that have proven technical expertise and a track record of working in Brazil.

We intend to deviate from the procurement of private sector services in two areas: future cities and the OECD workstream. The detailed justification for this different approach to procurement is based on the specifics of the interventions and the market, set out in more detail below.

In summary, on future cities, we believe our programme will be more sustainable and likely to have a more widespread impact if we partner with a multilateral organisation who can amplify the interventions and increase the likelihood of their uptake across Brazil by providing cost effective finance for the interventions to be rolled out more widely. From our market engagement, the World Bank has relevant expertise, institutional relationships with both city and state actors in priority states (in particular on water in Recife and urban mobility in Sao Paolo) and significant capacity to provide low cost finance to follow up what works in the programme with significant replication at scale. For our trade workstream to support Brazil to meet the high standards of the OECD, our engagement with Brazilian authorities, the OECD and the market has identified the OECD itself as the ideally placed implementer. The OECD can provide an extremely high quality of expertise to support Brazil’s economic reforms needed to drive productivity given its role in setting global best practice; it has the added bonus of adding weight and credibility to Brazil’s readiness to start the OECD accession process.

Alternative delivery route justification

World Bank Delivery for Future Cities:

We have had informal and structured engagement with the World Bank at both a technical and senior level. The feedback attests to the fact that their capacity, ability to deliver and strategic approach are in line with what we are trying to achieve through the PF programmes. We believe that they would be the best delivery vehicle for the programme for the following reasons:

  1. Programme fit: The World Bank already has a pipeline of projects on water in Recife and mobility in Sao Paulo, which matches our focus and complements our efforts. As part of this they already have developed relationships and trust with all levels of government in this sector.
  2. Experience: The World Bank provided the most solid case and track record among the multilaterals, considering staff expertise, experience in the sector and established network
  3. Spillover effect: leveraging the Bank’s projects in areas of water and mobility creates future opportunities for pilots to be replicated and/or financially supported in later stages
  4. Willingness: the World Bank has been the most proactive, providing extensive analytical support to date and showed preparedness to accommodate the PF needs.
  5. Capacity: the World Bank in Brazil has the footprint to deliver the programme and the ability to scale up the supported pilots.

Implementation
- Due to their extensive due diligence processes, decades long experience with local authorities in Brazil and numerous projects in area of infrastructure, the World Bank can be seen as a trusted partner to the UK, making additional assurance that the works in those selected cities and areas are mitigated against the risk of the UK being dragged into ongoing corruption scandals.
- Relatively low management fee (17% is an indirect non-negotiable charge, other charges like programme management are negotiable).
- The World Bank has a track record of taking on innovative work and scaling it up
- Strong internal capacity to develop policy and research support
- High quality assurance, checks and processes
- Extensive experience working with grant management

An overriding added benefit for the World Bank, given the scale of the urban challenges in Brazil is that if the interventions are successful then the World Bank could provide finance for cities all over Brazil to adopt these same technologies, thereby maximising the opportunity for the UK innovations outside the scope of the PF programme.

Risks of working with the World Bank
There are risks of working with a multilateral, but we feel that the risks can be adequately managed given the conversations we have had with them. The main risks include:
UK Visibility/Branding
Delivery of Secondary Benefits
Delays due to bureaucracies of agreements

Trade Programme – OECD as delivery partner for OECD workstream:

Why the OECD

Contracting the OECD to deliver one trade intervention would result in:
- Assurance of OECD standards included in all projects which would not be guaranteed if the delivery route was through the procurement framework or other multilateral organisations;
- Faster delivery of the intervention, as the OECD are already partnering with Brazilian authorities funded through the transitional funding. This is important as it capitalises on the current political climate (ahead of elections at the end of this year) and makrs sure the UK maintains political leverage with the Brazilian Government in an arena that is developing quickly;
- Being able to draw on this existing relationship also offers, value for money with reduced overhead costs and better coordination (given that the OECD is already involved in the Brazilian accession process);
- Improved dialogue between Brazil and the OECD, which would support the ultimate objective of the intervention.
- Internal checks and balances, given transparent OECD’s processes and UK’s experience in working with OECD in similar projects and permanent oversight of the UK Delegation at the OECD.
- Expertise in diversity, gender and inclusion, given that this is already part of the OECD regular process for projects.

We have considered other multilaterals and approached the World Bank to discuss possible collaboration but none would offer the same benefits and would carry more risks when compared to the OECD option.

Risks of the OECD route

There are also risks in contracting the OECD to do this work. However, we believe that these can be effectively mitigated using appropriate controls:
- High delivery costs
- UK visibility

Procurement Plan

Where using the procurement framework, a competitive tendering process will be used to select suppliers from the PF framework. In parallel, we expect to sign MoUs with the OECD and World Bank to deliver these programmes. For the World Bank, the first year of inception activity will be covered by an EFO while we finalise terms of the full scale implementation partnership.

The detailed scope of services required from suppliers will be defined in a Statement of Requirement (SoR), drafted by the Brazil Programme Team in consultation with the central procurement teams. Beyond minimum programme requirements, the SoR will not specify how suppliers should deliver the services. The SoR will set out programme requirements, target outcomes, maximum budgets and and standards/ key criteria that the supplier will need to adhere to, including relating to:
- Programme value;
- Start and end dates;
- Indicative payment schedule, conditions for such payments to be made, payment by results/milestone achievements where possible, provisions for claw-back of funds, and payment request procedure, based on status of delivery and spend statements;
- Arrangements for separate management of funds;
- Financial and impact reporting schedules, and monitoring and evaluation requirements;
- Responsibility for due diligence and management of subcontractors/grantees;
- Governance arrangements;
- Procedures for making changes to project documentation or agreements;
- Independent annual audits;
- Accountability and indemnity;
- Consultation, communications and branding for programme activities;
- Intellectual property;
- Fees and charges;
- Payment mechanisms;
- Basis and process for full or partial termination and dispute resolution, including initial and mid-programme review points;
- Quality, oversight and sustainability of services;
- Total costs and risks.

Expected timeline and process

We anticipate that contracts for the Brazil Prosperity Fund programme will be awarded by April 2019 and the programme will end on 31 March 2023. The table below illustrates high-level timescales of different procurement stages.

High-level procurement timeline
	Q3 / FY17/18	Q4 / FY17/18	Q1 / FY18/19	Q2 / FY18/19	Q3 / FY18/19	Q4 / FY18/19	Q1 / FY19/20
SoR drafting and approval
Invitation to tender
Evaluation of bids
Contract approval
Start of work

Evaluation, Contracts and Risks

Suppliers will be expected to demonstrate in their proposals how they will target programme interventions to meet specific Prosperity Fund outcome criteria, including how these will:
  1. Have the greatest impact on the poorest residents, taking particular account of gender differences,
  2. Generate largest primary benefits to Brazil;
  3. Align with UK comparative advantage and expertise.
Additional factors that suppliers will be required to demonstrate have informed the specific geographical and beneficiary focus of interventions will include:
- Complementarity with HMG and other donor programming;
- Opportunities to improve legal-regulatory environment and social norms.

Before contracting services, suppliers will be required to make an evidence-based assessment of the differentiated impacts of UK-funded interventions on gender equality and women’s economic empowerment and will also be required to report on differentiated impacts as part of ongoing reporting. No work will be taken forward should initial or ongoing assessments indicate that there will be a subsequent negative impact on gender equality.

Payment model

Pricing may vary at different stages of the project but in all cases it will reflect the following characteristics:
- Practical;
- Measurable deliverables;
- Incentives for the supplier to perform;
- Appropriate risk transfer;
- Flexibility;
- Affordability;
- Transparent and auditable payment by results (linked to milestones and Key Performance Indicators (KPIs). Contracts will be output-based as a minimum but linked to impacts where possible).

A Payment By Results (PBR) approach may be used to incentivise the achievement of impacts identified in the programme log frame but only (in light of the complex and often long-term nature of the projects being undertaken) where impacts can be defined, attributed to the supplier and meaningfully measured in a workable timescale and allowing for some pre-payment and milestone payments for some elements of the programme where appropriate (para. 256). Critical Performance Indicators (CPIs), KPIs and Service Level Agreements (SLAs), linked to PBR, will be developed and applied to performance areas.

Contract management

Contract and supplier performance will be managed through the life of the programme via regular contractual performance and logframe reviews, annual reviews, in line with Cross-Prosperity Fund MREL Strategy, reporting from the third party monitoring and verification agent, strong and relevant Key Performance Indicators and Service Level Agreements where necessary. Risk assessment and reporting of savings and efficiencies will be embedded into the contractual review meetings as business as usual on a quarterly basis.

Subcontractors will be responsible for delivery of discrete projects linked to their contract and will be managed by lead supplier(s), not by the FCO. The FCO’s contractual relationship would be with the lead supplier, though the contract will provide for an appropriate level of oversight of downstream partners. The Brazil Programme Team will maintain final authority on selection of subcontractors. Any supplier wishing to subcontract must carry out due diligence checks on downstream potential partners before entering into a contractual arrangement for use of UK taxpayer funds. To help ensure effective delivery, SoR will require any consortia to demonstrate how they will work together in a coherent and efficient way.

The Programme Team will apply best practice programme management principles and the National Audit Office criteria for VfM throughout contract planning and implementation processes. In delivering VfM, the team will ensure economic, efficient and effective use of funds to achieve agreed outcomes.

Commercial risks

Risk Transfer approach

The broad delivery approach is to transfer risks to the party best able to manage them and to minimise risks to the UK Government (HMG), thus safeguarding taxpayers’ funds as far as possible. The Brazil programme team will work with legal advisors and stakeholders across HMG and, where appropriate, with suppliers, to address all risks.

Delivery Partners

Trade Strand

The trade strand launched procurement process to select one delivery partner to deliver on the i. MSMEs and ii. Ports interoperability objectives on 17th September 2018 to Prosperity Fund Framework supplier as per our preferred delivery route.

After completion of the processes, Palladium International was the selected delivery partner based on their technical and commercial competencies. Palladium will lead a consortium composed of the following companies: EY, Procomex, OCO, Edeavor Brasil, Inter-American Development Bank, Next Trade Group, São Paulo University and Hambourg Port Consulting. The total cost of the contract will be £13,214,968 including all fees, which within the budget available for the programme.

The contract period will be from March 2019 to March 2023, with a six-month revision in the beginning after completion of the Inception Phase and another one in March 2021 to align with the Spending Review. The delivery partner’s services and contract will be monitored according to expectations and parameters established in the Statement of Requirements (SoR) for this programme.

Green Finance Strand

The Green Finance strand launched procurement process to select one delivery partner to deliver the full strand on 8th November 2018 to Prosperity Fund Framework supplier as per our preferred delivery route.

After completion of the process, EY was selected as the preferred delivery partner based on their technical and commercial competencies. EY will lead a consortium composed of the following companies: Sitawi and Carbon Trust. The total cost of the contract will be £4,403,115.36 including all fees, which is within the budget available for the programme.

The contract period will be from April 2019 to March 2023, with a six-month revision point after completion of the Inception Phase and then another revision point in March 2021 to align with the Spending Review. The delivery partner’s services and contract will be monitored according to expectations and parameters established in the Statement of Requirements (SoR) for this programme.

Energy Strand

The Energy strand launched procurement process to select one delivery partner to deliver the full strand on 1st February 2019 to Prosperity Fund Framework supplier as per our preferred delivery route.

After completion of the process, Adam Smith International (ASI) was selected as the preferred delivery partner based on their technical and commercial competencies. ASI will lead a consortium composed of the following companies: Carbon Limiting Technologies, Fundação Geútlio Vargas, Instituto 17 and Hubz. The total cost of the contract will be £22,135,905.90 including all fees, which is within the budget available for the programme.

The contract period will be from December 2019 to March 2023, with a six-month revision point after completion of the Inception Phase and then another revision point in March 2021 to align with the Spending Review. The delivery partner’s services and contract will be monitored according to expectations and parameters established in the Statement of Requirements (SoR) for this programme.

FINANCIAL CASE

What are the costs and how are they profiled?

The £56m budget for interventions proposed under the Prosperity Fund programme in Brazil will be Official Development Assistance (ODA) eligible and come from the central Prosperity Fund budget held by the Cabinet Office. The programme budget in Brazil will be controlled locally at Post by the FCO within central Prosperity Fund governance arrangements and in accordance with FCO financial management systems and processes.

The table below provides the indicative spending profile for the programme over its five year lifespan against each of the four priority sectors of the preferred option identified in the Appraisal Case and the independent monitoring contract. Programme Management costs are identified separately and currently refer only to internal FCO staff costs and associated overheads, such as travel, training and platform costs, detailed in the table ‘Prosperity Fund Brazil Annual Staff costs’ below. A full, detailed forecast will be developed during the procurement process, including separate identification of management and other associated administration costs within supplier budgets.

Prosperity Fund Brazil indicative spending profile (£m)
*Budget by sector including staff and transition costs
Sector	TOTAL		17-18	18-19	19-20	20-21	21-22	22-23	TOTAL
Green Finance	4.95			0.2	0.75	2	2		4.95
Trade	14.5	OECD		0.5	1	1	1		3.5
		Ports		0.3	1.5	2.5	2	0.5	6.8
		MSME		0.2	1	2	1		4.2
Energy	22.05	Centre		0.15	0.75	0.75	0.75	0.75	3.15
		Reg/training		0	1.25	1	1	1	4.25
		Innovation		0	5.15	5	4.5		14.65
Cities	9			1	2	2	2	2	9
Outreach/ capacity building				0.05	0.05	0.05	0.05		0.2
Gender				0.1					0.1
Staff	7%			0.9	0.9	0.9	0.9	0.65	4.25
TOTAL			1.4	3.4	14.35	17.2	15.2	4.9	56.45

Staff costs
Staff costs for the programme are calculated on a Full Economic Cost (FEC) basis at the corporate exchange rate and comprise 7% of the total programme budget. Staff costs are budgeted for resource to manage Brazil’s bilateral programme only and do not include staff resources dedicated to Prosperity Fund centrally managed ‘global’ programmes. The proportion of staff costs to programme budget is twice the indicative 3.5% ‘benchmark’ for programme administration set by the PFMO. This reflects the significantly higher employment costs in Brazil than in the two other Prosperity Fund posts in the region, Mexico and Colombia. At many FCO grades, local staff costs (FEC basis) are around twice the cost of equivalent staff at these posts.

Brazil’s proposed annual staff profile and costs are set out below. Costs are presented on a FEC basis, recalculated at the corporate (not budget) exchange rate as agreed between Post and PFMO in line with other programme spend.

Prosperity Fund Brazil annual staff costs
	GRADE	FTE (MINUS GLOBAL)	JOB TITLE	FULL ECON COST TO PF*
MANAGEMENT TEAM	D7	0.5	PROSPERITY COUNSELLOR	50,522.27
	D6	1	PROSPERITY FUND PROGRAMME MANAGER	101,044.54
	D6	0.4	INFRASTRUCTURE STRATEGIC PROGRAMME MANAGER	33,320.17
	C4	0.4	REGIONAL STRATEGIC PROGRAMME MANAGER	31,003.86
PROGRAMME SUPPORT TEAM	D6L	0.5	ECONOMIST	60,912.16
	C4	1	PROCUREMENT SPECIALIST	77,509.65
	C5	0.4	COMMERCIAL LEAD
	B3L	1	RESULTS ADVISER	66,388.95
	B3L	1	FINANCE MANAGER	66,388.95
	A2L	1	PROGRAMME ASSISTANT	66,388.95
PROGRAMME SECTOR TEAMS	C4	0.7	PROGRAMME MANAGER - TRADE (PORTS, MSMES)	54,256.76
	C4	0.7	PROGRAMME MANAGER - INFRA/REGULATION (CITIES)	54,256.76
	C4	1	PROGRAMME MANAGER - GREEN FINANCE (GF)	77,509.65
	C4	1	PROGRAMME MANAGER – ENERGY	77,509.65
	B3L	1	PROGRAMME OFFICER	66,389.25
	B3L	1	PROGRAMME OFFICER	66,389.25
	B3L	0.7	PROGRAMME OFFICER	46,472.48
	B3L	0.7	PROGRAMME OFFICER	46,472.48
	TOTAL	13.6		1,042,735.79
				7%

*FEC costs converted at corporate exchange rate

How will the programme ensure accurate forecasting?

Key cost drivers for delivery of the portfolio are:
  1. Administrative – FCO programme team staff costs; travel, training; overheads
  2. Strategic – Management services; policy advice; capacity building;
  3. Technical – Technical expertise; delivery of technology pilots/ testing.

Suppliers will be expected to provide accurate financial forecasts against activity based budgets when bidding for the work and on both a monthly and annual basis thereafter. These detailed spend forecasts will be used by the Brazil team for accurate forecasting and financial reporting to the FCO and Cabinet Office. Forecasts should be free of optimism bias, with suppliers informing the FCO of potential slippages or overspends immediately when identified.

Financial Management

Funds will be disbursed to the Delivery Partners described in the Commercial Case – up to five for the main delivery of the programme in each sector. Contracts, MoUs and Administrative Arragements will outline how funds will be disbursed, agreed beforehand with the suppliers and will be partially tied to payment by results, though allowing for some pre-payment and milestone payments as appropriate.

Payments will be disbursed on the basis of results reported quarterly and spend reported on a monthly basis in narrative and financial reports. Invoices will be paid monthly or quarterly in arrears after satisfactory completion of activity and project spend as set out in the agreed work plan and financial forecasts. This will be important as a tool for monitoring/ managing performance against the calendar year ODA target, and for actively managing portfolio budgets. Third party monitoring will be used to verify results achieved. Receipting against resource-based activity will be carried out monthly at Post.

Reporting requirements for implementers will be set out in contracts with suppliers (detailed in the Commercial Case), and will specify the need for compliance with agreed conditions of funding in addition to HMG requirements. Forward-looking budgets, delivery plans and milestones will be agreed following submission of the inception report under each contract, and annually thereafter. Full financial reports will be provided annually in advance of programme annual reviews. Annual reports will be supplemented by quarterly reports, including a record of activity over the previous quarter, progress against the work plan and log frame outputs, a risk register, and any expected deviations from the agreed forward-looking budgets and delivery plans. Suppliers will also be required to provide annual audited accounts, signed by the Finance Managers on behalf of the implementing partners and certified by their auditors that separately identify FCO funds, associated disbursements and unspent funds. The programme may also finance independent audit of partners if required.

Internal reporting beyond monthly receipting, will include the Brazil programme management team providing financial and management reports (including on financial risks) on a quarterly and annual basis to the PFMO, PFDU and Americas Directorate in London. The Brazil Programme Management team will work together with the independent monitoring contractor and PFMO’s MREL team to gather data and evidence on milestone targets, outputs, outcomes and impact being produced by the programme and take responsibility for assuring accuracy of data on FCO internal financial management systems, Hyperion and OBIEE.

Payments in advance of activity will not be made routinely, as they carry a significantly increased risk of loss of public funds. It is not expected payments in advance will occur and these will be avoided, however according to HMT guidance, there might be acceptable circumstances for an exception approval of advance payments, e.g. where the recipient needs working capital to carry out the commitment for which the grant is being paid. To demonstrate that need an implementer/supplier must submit a strong and compelling business case explaining why an advanced payment is necessary and make it clear why an advance payment would be a good use of public funds. Requests for advance payments will be heavily scrutinised by the programme team to ensure that they are absolutely necessary and not in advance of need. Payments in advance of need will not be made.

Innovative financing and programme scalability

The Brazil Prosperity Fund programme will adopt an innovative approach to financing to increase the value of UK investments in the Energy and Future Cities sectors through attracting additional external funding. The Future Cities programme will be phased so that early, demonstrable success attracts ‘matched-funding’ for subsequent UK investments in the later phases. The Energy programme aims to use the UK’s investment to leverage additional private sector funding. These two sectors both offer considerable opportunities and could absorb significant additional funds to those being proposed in baseline budgets. We will also remain open to securing co-funding from external stakeholders, where this aligns with programme aims.

Actions to mitigate financial risk and fraud

Risk of under/overspend – The main financial risks to programme spend are delays to delivery (including business case approvals and procurement processes). Monthly expenditure reports and forecasts, quarterly financial reports and frequent meetings with partners will mitigate the risk of large over or under spends in this programme. Performance targets under payment by results contracts with suppliers will be set on a sector-wide basis, whereby underperformance in a single programme intervention will not prevent payments being made if strong results have been achieved elsewhere. Spend and results targets will also be balanced via a flexible funding approach that allows funding to be moved between programme sectors and interventions (potentially including those managed via ‘global’ programmes operating Brazil) with funds targeted towards highest-performing interventions. Logframe targets will be reviewed after each annual review and if circumstances change.

Exchange rate risk: The Prosperity Fund operates using the corporate rate of exchange, which is subject to foreign exchange (FX) fluctuations. In order to manage the FX risk caused by spending in local currency, delivery contracts will be in sterling so that risk is passed on to the supplier, who will be able to use commercial methods unavailable to HMG (e.g. hedge accounting) to offset FX risk.

Risk of fraud by suppliers – Lead suppliers and third party monitoring supplier will both be required to set out their fraud mitigation strategies including internal risk management systems and reporting systems. FCO will further require that annual financial audits include spot checks of high risk areas of programme activity (e.g. procurement), and – if any causes for concern arise – will reserve the right to conduct a full forensic audit. Due diligence on potential implementers will have been carried out as part of the Prosperity Fund Framework Agreement.

Risk of fraud through downstream suppliers or with partners in country – this risk will be partly mitigated through lead suppliers’ due diligence of downstream suppliers, ensuring acceptable levels of financial control and reporting before granting funds. The lead supplier will be required to set out how they will monitor the performance and financial management of downstream suppliers and national partners supported through the programme, e.g. ‘spot’ field visits to verify services, quality control checks to ensure partners are delivering services to the required standard and data tracking mechanisms. We recognise that where programme interventions have longer ‘chains’ of suppliers, fraud through downstream partners is likely to be greater, so will focus greater effort towards mitigating measures in these cases.

If fraud is detected, the FCO will demand full remedial action including repayment in full if the fraud involves diversion of UK funds. Continued disbursement of funds will be contingent on adequate financial oversight.
MANAGEMENT CASE

Management arrangements for implementing the intervention

The Prosperity Fund programme in Brazil will comprise one main component of Supplier services. Up to five lead suppliers or consortia will be managed through up to three separate commercial contracts via the Prosperity Fund Procurement Framework (Energy, Green Finance and Trade), and two MoUs/Administrative Arrangements (Future Cities and Trade-OECD).

Portfolio Governance
The FCO is the appointed lead department and will hold the budget for the Brazil Prosperity Fund Programme. The SRO for the Prosperity Fund Programme at Portfolio level is the Permanent Under Secretary who may delegate SRO responsibility to Posts. The SRO for the Brazil programme will be Her Majesty’s Ambassador to Brazil who will have overall responsibility for the delivery of the programme’s objectives. The SRO for the Brazil programme will report to the FCO Director who sits on the Cross-Whitehall Portfolio Board, creating a reporting line into the overall portfolio.

The FCO Americas Directorate will delegate authority for the allocated funds to Post, both in terms of management of public money and ensuring compliance with the International Development Act. The Brazil network has already instigated an ODA committee at post chaired by the Deputy Head of Mission to help monitor compliance, evaluate strategic direction and implementation. This committee will work to join up a cross government narrative on ODA in Brazil (across the BEIS and DEFRA International Climate Fund projects, the joint BEIS-FCO Netwon fund projects and the Prosperity Fund) to ensure synergies and sharing of lessons and best practice. The Committee will provide advice to the SRO.

Post will liaise with Other Government Departments (OGDs) to ensure that the programme remains aligned with HMG policy priorities, however OGDs are not responsible for the delivery of the fund. We will continue to consult HMT, DIT, CO, BEIS, DfT, DFID, amongst others. The Cross-government Ministerial Board for the Prosperity Fund has already agreed in principle to allocate the required funding to this programme. Business Case sign-off will therefore be carried out through the FCO Investment, Infrastructure and Operations committee (IIOC) following Cross-Whitehall engagement throughout the drafting process. The detailed Governance and Management structure is annexed.

Functions of Governance and Management Groups

Senior Reporting Officer (SRO)
The Senior Budget Holder for the Brazil programme will be Her Majesty’s Ambassador to Brazil who will be accountable through their annual appraisals for their fiduciary responsibilities including spending money in the public interest and ensuring value for money. The SRO will also complete our Annual Consolidated Certificate of Assurance every year to give assurances to the PUS that as a network we are compliant with policy and best practice on many different  areas (and highlight any areas we are not).

PF Brazil Board
The SRO will be supported by a senior-level Prosperity Fund Brazil Board. This will be chaired by the HMA and the secretariat will be provided by the PF team in post. Its attendee will include Brazil post senior management and relevant HMG representatives (including PFMO). This will review programme progress and performance and advise the HMA as SRO to shape strategic priorities on at least a quarterly basis. This group will ensure there is strategic oversight of the programme.

ODA and Secondary Benefits Committee
The Committee will act in an advisory capacity only as responsibility for decision-making lies with the HMA as SRO. However, the Committee will offer advice and recommendations on programme strategies including, but not limited to, the yearly strategy refreshes of each programme. The members will also offer advice on mitigation of risks and maximising impact, particularly on the delivery of Primary Benefits.

Programme Management Team (PMT) and Programme Delivery Team (PDT)
The management team is responsible for managing the team and ensuring the implementers work to fulfil the strategic agenda of the PF. They will help the sector teams capitalise on the opportunities the portfoilio creates for leveraging UK influence. The team will maintain a high-level programme timeline incorporating key milestones for various workstreams and develop and monitor detailed programme delivery plans for each set of sector interventions, including actions, risks, financial and contract management and compliance with internal governance requirements.
Programme Sector Teams
The sector teams are responsible for day-to-day management of the programmes, including delivery against financial and operational targets and managing risks. They will also liaise with suppliers, internal and external stakeholders with a stake in the programmes, as well as provide overall coordination of programme communication and delivery.
Global Programme Sector Teams
We intend to run the bilateral and global programmes as seamlessly as possible and want our Brazilian and UK stakeholders not to see a difference. The management of the global programmes is their responsibility but we are working to encourage them to adopt the above model. The responsibilities of the global programme sector teams should be the same as the bilateral sector teams except that the programme management function is carried out by the relevant teams in the Prosperity Fund Department. Even though the Governance structures will be more London-based, they should mirror the Technical advisory committees for the local market as well as feed into the ODA Committee to ensure that the programmes have local senior oversight and challenge.

Programmes Advisory Committee
The team will engage extensively with stakeholders and experts. This will include using the working-level programmes advisory committee whose participants will include key delivery partners in each of the programme areas, such as relevant HMG representatives, Federal and State Governments, Implementers, and NGOs/Civil Society and Multilaterals. They will meet on at least on a quarterly basis in meetings chaired by the relevant programme lead and will maintain technical oversight of the programme activity offering technical sector-based advice while, including ensuring coherence with existing donor and recipient activities. There will be one Advisory Committee for each programme.

Business Advisory Groups

The Business Advisory Groups will be formed of interested UK companies in each of the sectors. DIT teams will identify the private sector members and the relevant DIT officer will ensure regular communication on the opportunities that arise through the Prosperity Fund programmes. The DIT officer will update PF programme managers through the Internal Coordination Groups, who will then discuss how to maximise non-ODA activity in support of securing Secondary Benefits. They will provide quarterly activity reports to the ODACom.

Staffing structures for programme, Prosperity funded staff, are set out in the table below. The programme team consists of a programme management team, a delivery team and a programme and policy sub-team for each of the strands of the business case.

The primary focus of all of the above staff will be to secure the primary programme objective (poverty reduction). All staff will also have a role in ensuring both secondary (indirect UK commercial benefits) and tertiary (public diplomacy) benefits of the programme are realised. This will include representational work – leading on Government to Government engagement to support delivery partner’s work, ensuring UK presence and branding of programme activities and liaising with UK companies and DIT teams regarding potential commercial opportunities.

The substantial investment of UK funds proposed, the complexity of programme design and the need for a range of specialist expertise will require a commensurate level of programme management resource. The Brazil programme team will also provide adequate staff resources for ongoing supervision funded from Prosperity Fund programme budgets, recognising that the flexible and adaptive model that we are seeking to implement can be intensive on staff time.
Staff resource is budgeted to manage Brazil’s bilateral programme only and does not include staff time dedicated to Prosperity Fund centrally managed ‘global’ programmes. Where this is required, a proportionate financial contribution will be expected from ‘global’ programme budgets, to be agreed with these teams and PFMO/PFDU. A detailed description of each role is included in Annex D.

Additional resource to be considered at programme resource reviews is specialist social development and gender expertise, where this is not available centrally. Capacity building will be provided across the Programme Team, including to management and sector teams, to build awareness of gender, poverty, social development and inclusion in programme design, adaptation and delivery.

Global Programme Management
Seven Prosperity fund ‘global’ programmes propose to work in Brazil: Future Cities, Trade, Business Environment, Digital Access, Better Health, Skills and Infrastructure. The Brazil Programme team has initiated a Brazil Portfolio Steering Group to drive efficiencies and maximise synergies between bilateral and global programme objectives. This management approach aims to pool procurement, MREL, risk management and external engagement strategies to achieve coherence and maximise efficient management of resources. Flexible programming tools and shared lesson learning will enable resources to be reallocated to the highest performing components of each programme throughout implementation.

Supplier management
Delivery of the programme will be outsourced to external suppliers. The Brazil Programme Team will deal primarily with the lead contractors (with whom we will contract) or consortium partners only, interacting with sub-contractors as needed, including having final oversight of their selection. Close coordination, clear lines of reporting and levels of authority, and clear governance arrangements will be required.

Within the lead supplier teams a Programme Director and a Programme Coordinator will be appointed for each contract. These will be the key points of contact between the Brazil Programme team and the suppliers. We will expect to be closely involved in the selection of these individuals, including contributing to job specifications and chairing or sitting on any panel to appoint them. They will be the key day to day point of contact for the Brazil Programme team. Meetings at a minimum of every four to six weeks will be expected between the Brazil Programme team and each Programme Director. Contact between the Brazil Programme team and each Programme Coordinator is expected at least weekly.

Details of organisational structures, operating systems, processes and reporting lines between lead contractors and any consortia partners or sub-contractors will be a requirement in all appropriate Terms of Reference and included in the technical evaluation of bids. Whilst the Brazil Programme team will deal primarily with the lead contractor or lead consortium partner, they will also have regular, structured contact with suppliers/sub-contractors/consortium partners on a quarterly basis. This will be organised through the lead contractor, who will also be invited to attend to avoid any risk of miscommunication.

Monitoring and evaluation
The monitoring, reporting, evaluation and learning (MREL) for this programme will be consistent with the central Prosperity Fund approach to MREL led by PFMO. We will report expenditure monthly and impacts (results) quarterly and annually to PFMO in line with reporting requirements. Brazil programme monitoring will be consistent with the programme Theory of Change. Results frameworks will be developed in consultation with stakeholders central MREL providers flowing from this.

Programme data baselining, data capture and reporting to central MREL systems will be the responsibility of the Brazil Programme team and its implementers, who will have formal contractual responsibility for reporting on results delivered in a prescribed format. The main monitoring tool for the programme is the logframe. We will adopt a ‘nested’ logframe model (individual results frameworks for each intervention aggregated at portfolio-level). A draft will be developed following the commercial tender and selection of successful bidder, based on their proposed indicator approach. During inception there will be a process of defining ‘methodology notes’ and each of the logframe indicators will be refined. The programme will be monitored through data generated by implementers, the third party monitoring supplier, national and global data.

The programme will seek to promote gender equality in the provision of programme interventions. Project data will be disaggregated by gender in all sectors wherever possible. Before contracting services across all sectors, suppliers will be required to make an evidence-based assessment of the differentiated impacts of UK-funded interventions on gender equality and will also be required to report on differentiated impacts to as part of ongoing reporting. No work will be taken forward should initial or ongoing assessments indicate that there will be a subsequent negative impact on gender equality.

#### Communications and branding
Success of Brazil’s Prosperity Fund programme will be supported by an effective communication strategy that clearly demonstrates how the programme is delivering economic development and poverty reduction benefits in Brazil, as well as secondary benefits to the UK. We will explore branding options to maximise awareness and understanding of the programme, and raise the profile among beneficiaries and partners that this is a British government initiative. Key communications objectives include:
- To tell a positive and confident story about the effectiveness of ODA spend in Brazil, demonstrating how HMG resource can deliver economic development for Brazil and opportunities for UK business, building support with UK public, press and Parliament.
- To ensure UK companies are aware and able to take advantage of opportunities and access resulting from programme activities;
- To influence national and local decision-makers to support effective implementation and delivery of the programme;
- To use the programme to raise the profile and reputation of the UK in Brazil while facilitating access to stakeholders in government and in the private sector;
- To raise the programme’s profile through reporting of success/impact.

Communications activities will be co-led by the Programme Management team and implementing partners.

Risk Management

Risks for each intervention have been assessed by the programme and teams across the embassy against the following six categories of risk: external context, reputational, fiduciary, delivery, safeguards and operational. In assessing the risks, a number of important assumptions have been made. Each intervention within each sector was assessed against the likelihood of the risk occurring and the severity of the impact and given one of the following four ratings described below: Minor, Moderate, Major and Severe (Gross risk rating). Mitigation measures were then applied and the risks were rated again (Net risk rating). Finally, an aggregated gross and net risk rating has been provided for the overall programme based on the risk analysis by intervention.

Description of risk ratings

The gross risk assessment for the overall Prosperity Fund programme is assessed to be ‘major’. The key driver for this rating is External risk, i.e., political and economic uncertainty, which remains our biggest concern across all four sectors. The uncertain environment impacts on the delivery of the programmes and consequently impacts on our reputation. Fiduciary risk is a moderate concern given the level of bureaucracy inefficiency and opportunity for misuse of funds.

Applying mitigation strategies across the 4 programmes lowers the overall net risk rating to ‘moderate’. We have little influence against external factors, but our focus on key sectors, which will remain a priority for any future government, gives a degree of certainty that the programme will continue to be supported. Fiduciary, delivery and sustainability risks will be mitigated by ensuring suppliers provide sustainable/strong legacy planning in their proposals, with teams taking remedial action as necessary to ensure sustainability/strong legacy of programme. The full aggregated programme risk assessment will be developed during programme implementation and updated at least quarterly.