Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme

Title: China Prosperity Fund Phase One
Programme Value: £85m		Review Date: 30 June 2019
Programme Code: GB-GOV-50-PF-02-CHP (including GB-GOV-3-PF-CHP-912; GB-GOV-3-PF-CHP-913; GB-GOV-3-PF-CHP-911; GB-GOV-3-PF-CHP-924; GB-GOV-3-PF-CHP-921; GB-GOV-3-PF-CHP-923; GB-GOV-3-PF-CHP-922)	Start Date: 2017	End Date: March 2022

Summary of Programme Performance
Year	2018	2019
Programme Score	n/a	A
Risk Rating	n/a	Major

Summary of progress and lessons learnt since last review
The China Phase One programmes have, collectively, made tremendous progress and are on the right trajectory, with an overall score of “A” denoting the portfolio has met expectations. The portfolio is now satisfactorily set up, for the most part, to deliver a complex and potentially impactful set of programmes on Energy & Low Carbon, Infrastructure in partner countries, financial services and business environment reform, along with secondary benefits, including for UK businesses. As the portfolio moves from procurement into inception and implementation of multi-year programmes, we want to recognise that this has not been an easy process. In particular, we recognise strong leadership by the outgoing Prosperity Fund Counsellor, the extremely hard working and eager programme team, the beneficial restructuring driven by the new SRO, the growing confidence, sense of purpose and critically, ownership by the team, and an important emerging narrative around contributions to global good, as well as secondary benefits & opportunities for business.

We note a number of major challenges to this programme. The China context is difficult, not least because of the unique political & economic environment & relationship challenges. There are many stakeholders, with the result that the programme team can be pulled in different directions. It is important that as far as possible they are given a clear mandate/cover under which to operate. From the China Programme Teams’ (CPT) perception, Central structures (PFD, JFU and CPG) have not always offered clear, consistent and timely guidance that the CPT needs. Coherence and VfM of transition funded programmes has not always been clear. This has contributed to significant delays in programme initiation. The potential for reputational risk from the China portfolio requires a smart & proactive internal communications approach to address this. Such risks are reflected in the recommended higher risk rating for this programme (Major).

List of overarching recommendations for the next year

SRATEGIC ISSUES:

1. Develop coherent narrative: We recommend the development of an agreed narrative on the overall purpose of the China programme and what this means in practice. The agreed narrative should give programmes a clear mandate to operate. This is not just a question of the centre issuing guidance but requires a process involving consultation with the centre and China policy leads & programme SROs, and guidance, training and capacity building. It should include a stronger narrative on contribution to global good, which should also be captured in programme logframes.
2. Improve coherence of approach: This narrative then needs to drive a coherent approach across the portfolio on delivering development impact, as well as secondary benefits, based on an assessment of how each intervention area contributes to primary purpose and to secondary benefits; and gathering evidence as to which interventions contribute most to improving conditions for sustainable and inclusive growth. This should be supported by programme evaluation(s).
3. As part of delivering on the primary purpose, the portfolio could integrate stronger mechanisms for identifying, monitoring, and responding to gendered risks and potential harm arising from project activities. There is some excellent situational analysis in the business case, including strong considerations of G&I at a national level.
4. Improve Strategic Oversight: It is important that the overall Strategic Board sits on a regular basis. We suggest at least once in the next six months to ensure that all Phase One programmes have commenced Inception satisfactorily, and thereafter at least twice a year, especially as the overall value of programme activities rises progressively.
5. Development of a Secondary Benefits Strategy: Development of programme wide secondary benefits strategy, in accordance with new JFU guidance and with support from JFU.
6. Steering Board effectiveness. Steering boards for strands are a welcome initiative. However, it is important that steering boards have clear TOR, including role and clear expectations of members, and that members adhere to these. In terms of membership, all Steering Boards should include at least one development expert, who can advise on development impact. These representatives could be drawn from DFID China, PFDU or JFU.

OPERATIONAL MATTERS:
1. Update Risk Matrix: The risk matrix should now reflect risks relating to the implementation stage. There is also a need to revisit how we treat political risk in the programme across the PF portfolio.
2. Update and Complete all Logframes: We welcome the fact that the over the last six months, the programme has moved from having no logframe, to having a working logframe. We recommend that this is now amended & updated to include 1) completion of logframes 2) quality check and improvement of indicators & milestones; and 3) check that level of stretch is appropriate and consistent across the logframe.
3. Development of VfM strategy & indicators: The China programme should develop an overarching VfM strategy, using the VfM scorecard as a tool, with a strong focus on lessons learned, with regular reporting on progress to the relevant Board. Under this, each strand should develop a strand specific strategy with implementing partners. The MREL team should support the development of this strategy & FCO economics unit will be consulted in its development.
4. Improve dialogue and understanding on Commercial & Procurement matters: The forthcoming visit to Beijing by the Head of CPG should be used as an opportunity to review commercial risk, capability, roles and responsibilities and to develop a clear service-level agreement.
5. Develop a Financial Operations Manual: The finance team needs to continue to build on its growing involvement with procurement and monitoring of all budget lines.

MONITORING, EVALUATION AND LEARNING:
1. Better integrate Monitoring, Results Evaluation & Learning (MREL): With ongoing support from the Centre, China teams can plan & own the China MREL strategy.
2. A recommendations matrix should be developed by the China Programme Team, putting all recommendations into a matrix, with clear timeframe & responsible owners to be reviewed on a quarterly basis.

LIST OF ACRONYMS

AML	Anti-Money Laundering
AR	Annual Review
BC	Business Case
BE	Business Environment
BEIS	Department of Business, Energy and Industrial Strategy
CDR	Commercial Dispute Resolution
CTSG	China Technical Support Group
DFID	Department for International Development
DIT	Department for International Trade
E&L	Evaluation & Learning
ELCE	Energy and Low Carbon Economy
FATF	Financial Action Task Force
FCO	Foreign and Commonwealth Office
FDI	Foreign Direct Investment
FS	Financial services
G&I	Gender & Inclusion
IFC	International Finance Corporation
IIOC	FCO Investment Committee
IP	Intellectual property
JFU	Joint Funds Unit
KPI	Key Performance Indicator
M&R	Monitoring & Reporting
MoU	Memorandum of Understanding
MREL	Monitoring, Reporting, Evaluation & Learning
OBC	Outline Business Case
ODA	Official Development Assistance
PDP	Primary Delivery Partner
PF	Prosperity Fund
PFDU	Prosperity Fund Delivery Unit
SBs	Secondary Benefits
SDA	Social Development Advisor
SDGs	Sustainable Development Goals (SDGs)
SRO	Senior Responsible Owner
ToC	Theory of Change
VfM	Value for Money

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	To be inserted
DevTracker Link to Log frame:	Not Yet Available

The China Prosperity Fund (2017-2022) Phase One has a budget of £85 million for ODA activities, and comprises four programme strands: China Business Environment (previously called Rule of Law for Business), Financial Services, Energy and Low Carbon Economy and Infrastructure. The portfolio is expected to lead to:
- an improved business environment through enhanced legal and regulatory framework and its implementation;
- a more efficient and inclusive financial system, less exposed to significant shocks;
- China making a quicker transition to a low carbon economy; and
- increased and more sustainable investment in China and ODA-eligible partner markets in higher quality infrastructure projects.

The Outline and Full Business Cases for Phase One have been approved. The China portfolio is led by the FCO and managed by the Prosperity Fund team within British Embassy Beijing. For Phase One outcomes, see below:

- Outcome 1 New policies issued that facilitate China’s transition to low carbon economy and an improved multilateral governance.
- Outcome 2 Strengthened policy environment and successful pilot infrastructure projects developed and integrated leading to increased project quality and bankability.
- Outcome 3 Increased international expertise and private capital investment in Chinese outbound infrastructure projects.
- Outcome 4 Financial resilience for underserved populations through increased access to financial services for underserved populations following regulatory innovation and increased market competition.
Outcome 5 inclusive growth and poverty alleviation globally through more robust commercial dispute resolution mechanism, stronger controls on money laundering, improved investment environment and intellectual property right protection; and increased trade and investment cooperation between Chinese and UK/international business.

Annual Review

Since this is the first China Phase One Annual Review, the review covers the period from the receipt of transition funding in May 2016 to June 2019, with a particular focus on the period following 1 June 2018, after final business case approval and the full funding moved over to departmental baseline. This was a period of programme mobilisation and procurement, as well as transition funded project delivery.

In terms of limitations, the review covers a complex programme, including four substantial strands at different stages of procurement and transition to multi-year programmes.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Outcome assessment (Primary Purpose – SDGs and global goods in inclusive growth, gender equality, women’s economic empowerment and poverty alleviation)
Overall, we consider that the portfolio is well set up to contribute to the outcomes as set out below, though there are risks to delivery. On ELCE, the programme is in a good position to contribute to China’s transition to a low carbon economy. UK expertise in key areas appears to be recognised, though we must be realistic about attributing changes to our intervention. On infrastructure, the programme has made substantial progress but there is a protracted line of sight to ultimate beneficiaries. Nonetheless, the potential benefits of influencing more sustainable and inclusive approaches in China’s infrastructure investments make this a worthwhile endeavour. The Financial Services strand includes some promising interventions. For the Business Environment strand, further work is required to clarify how the outcome of inclusive growth will be achieved through current plans. Overall, there have been considerable delays to approvals and pre-procurement in particular.

Our advice is that programmes actively and continually focus on maximising development effects and ensuring that they do no harm throughout the programme cycle. A strong and consistent focus on gender & inclusion is one way of mitigating this risk. G&I is an integral element of the Primary Purpose & it is important that this understanding/capability is built through ongoing support by PFD SDA and MREL consultants. The Prosperity Fund G&I thematic evaluation assessment of China Phase One rates amber overall, although has scored a green on internal capability. The work that the programme team has done in terms of developing a G&I action plan is recognised. To progress further, we recommend that:

- The programme integrate stronger mechanisms for identifying, monitoring, and responding to gendered risks and potential harm arising from project activities. The response measures should identify how risks will be mitigated and what actions are to be taken to tackle potential harm.
- There is some excellent situational analysis in this business case, including strong considerations of G&I at a national level. Projects could articulate in future ToCs and project plans how they aim to design interventions which are mindful of such issues, and where potentially they may seek to have a positive impact on advancing gender equality and WEE.

Monitoring & review of the G&I action plan should be integrated into programme management structures, routine review by oversight Boards, and primary purpose concerns need to be threaded through the logframe & included in the risk matrix.

Annual outcome assessment (Secondary Purpose)
China Phase One does not have a Secondary Benefits Strategy, so it is difficult and too soon to judge progress, although Infrastructure strand has developed one as part of its inception. Development of a Secondary Benefits Strategy has been included in the Strategic Recommendations.

Overall output score and description
There are four programme strands with 16 Outputs that have been scored in this first Phase One Annual Review. Overall, an “A”, with caveats, is proposed as an integrated total Outputs score (Met Expectations). This recognises the progress made by programme teams, despite delays for a multiplicity of programme development, procurement, contract negotiation and contractor appointment reasons elaborated upon in the Outputs (Section C). The AR Team concluded that exceptionally and for Year One only, outputs without milestones will be scored on the basis of progress made.

Summary of changes to the logframe since the last annual review
None. First annual review

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

	1..Procurement: Procurement procedures finalised and completed by the programme to secure the right expertise to deliver the interventions and Value for Money
Output number per LF		1	Output Score	B
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator	Milestones	Progress
1.1 Qualitative: the status of an assurance procedure in place to ensure that the programmes have gone through proper internal/external discussion and debate to identify and select ideas that will best support the multi-year programme design and delivery	1. There is an internal assurance process in place that involves all key stakeholders in China and in London / 2. There had been robust discussions during the assurance process about the project design, VfM, project objectives etc. that would support multi-year programme delivery.	In FY16/17, internal Prosperity Fund Boards held attended by the Prosperity Fund Counsellor, Economic Counsellor, Political Counsellor, UKTI (now called DIT) DFID, RCUK (now UKRI) and other senior management within the embassy to challenge and debate project ideas, budget, VfM, risk etc. / In FY17/18, due to restructuring of the team, PFMO bidding processes used as the first step to ensure competition. Then Central Team and procurement process worked as a dual process to ensure quality of project design, VfM and links with the multi-year programme. / In FY18/19, due to the reduced number of project ideas proposed, a new system was adopted as the assurance procedure: A “Challenge Session” to allow more in-depth discussion on each programme. Four Challenge Sessions were held among all the teams inviting relevant stakeholders, e.g. SROs, Prosperity Fund Counsellor, relevant policy team and the DIT team to allow robust debate on each project proposal, budget, VfM, link to the multi-year programme, procurement route etc.
1.2 Qualitative: the status of the procurement process through a fair process run according to Government procurement rules and achieved VfM	1. FCO procurement guidance is strictly followed to ensure China Prosperity Fund is open and transparent / 2. Procurement procedures have achieved VfM	Starting from FY17/18, the team started to use the Manila procurement hub as the main procurement route for Prosperity Fund projects instead of a call for bids approach. / Due to limited capacity in the Manila procurement hub and the introduction of the Prosperity Fund framework, the team then switched to London CPG as their main procurement resource in the next financial year. / In the past 3 years, with guidance and support from Manila and London CPG, FCO procurement guidance were strictly followed, using HMG’s procurement platform BRAVO, PF framework for transitional projects and multi-year programme. / Technical evaluations and commercial evaluations were done separately and individually to ensure fairness. All communications with the potential bidders were through the online system and open to all bidders.
1.3 TF: Number of transitional projects procured which supported the multi-year programme design and maintain relationship with key stakeholders	FY 18/19 Q2: 1 / FY 18/19 Q3: 8 / FY 18/19 Q4: 5 / FY19/20 Q1: 0	In FY16/17, 15 transitional projects were delivered between Phase One teams. (ROLB 4, Infra 5, FS 5, ELCE 1) / In FY17/18, China Prosperity Fund had delivered 24 transitional projects. (ROLB 7 Infra 6, FS 5 and ELCE 6) / In FY18/19, 14 “transitional projects” had been procured. Some are still delivering. (BE 3, Infra 1, FS 3 and ELCE 7)
1.4 Multi-year Programme: Number of one-on-one consultations for testing market interest/demand	FY 18/19 Q2: 16 / FY 18/19 Q3: 11 / FY 18/19 Q4: 0 / FY19/20 Q1: 0	After Phase One team’s OBC approval in May 2018, all Phase One teams started to prepare for the multi-year programme procurement. / One-on-one consultation was adopted to test market’s interest among and outside PF framework suppliers and collect feedback to the published Green SOR. / Infrastructure attracted 9 companies in July; ELCE attracted 7 in July; Business Environment attracted 6 among the framework suppliers and 2 outside framework suppliers in September and FS attracted 5 in November 2018.
1.5 Multi-year Programme: Number of multi-year SoRs/Tendering documents released to the market which clearly set out our programme requirement, primary purpose, secondary benefit, G&I requirement.	FY 18/19 Q2: 1 / FY 18/19 Q3: 2 / FY 18/19 Q4: 2 / FY19/20 Q1: 1	All Phase One teams went out to the market using the PF framework. On 12 September 2018, Infrastructure put out its SOR for the main multi-year programme, followed by ELCE in Oct 2018. Business Environment put out both its main procurement SOR and Standards Pillar SOR in December. Financial Services issued their tender in January 2019 due to several rounds of internal discussion on the programme design. The scope of the BE tender requirements has altered as the programme evolved, thus went out to re-tender in March 2019. / The SORs all have clearly set out the programme objectives, programme design, primary purpose, secondary benefit, G&I requirements.
1.6 Multi-year Programme: Number of bids received of which our programme has attracted sufficient interest from the market and generated competition.	FY 18/19 Q2: 0 / FY 18/19 Q3: 8 / FY 18/19 Q4: 8 / FY19/20 Q1: 0	After several rounds of stakeholder engagement, one-on-one consultations, China Prosperity Fund Phase One teams attracted the following number of bids: / Infrastructure programme received 5 bids. ELCE received 3 bids. BE main programme received 4 bids and Standards received 2 bids. FS received 2 bids.
1.7 Multi-year Programme: Number man days spent on evaluating bids which have involved colleagues from DIT, policy team, programme team and ensured fair, transparent and in-depth evaluation.	FY 18/19 Q2: 0 / FY 18/19 Q3: 129 / FY 18/19 Q4: 100 / FY19/20 Q1: 0	Due to the complexity of programme design and different approaches to assessing bids, the evaluation process involved more person- days within the embassy and HMG system than expected. However, by involving experts from all sectors, the selection process was fair, transparent and involved robust debate and in-depth discussion.

Key Points
Assurance Process
Before commencing procurement, the China Programme team adopted a comprehensive and robust assurance process within the China network and with London. The Phase One multi-year programme Business Case went through multiple approvals including FCO IIOC and the PF Portfolio Board. Board comments were addressed before final Outline Business Case approval.

In terms of transitional year projects, ideas from all Phase One teams were collected and submitted to the London PFMO JFU for approval. 15 transitional projects were approved and delivered in FY16/17. Once allocations were made, an internal challenge board was established in China, where senior officials from DIT, FCO Economic & Political sections reviewed and challenged project ideas. In FY17/18, due to restructuring of the team, the PFMO (now JFU) bidding process was adopted as a first step; then, in China, Central Team and procurement processes ensured quality and VfM of the projects and their link to multi-year programmes. 24 transitional funding projects were approved and procured in FY17/18. During FY 18/19, OBC assurance followed by internal challenge sessions were used.

Procurement Process
Due to the change from call for bids to tendering process in FY17/18 as required by PFMO (now JFU), the China Programme team had to quickly learn new procurement practices in order to achieve VfM in multi-year programme development and design. To close the knowledge gap, the China Prosperity Team invited the Head of the Manila procurement hub to deliver training in June 2017. This established a good foundation in terms of procurement knowledge and capability.

The Central Team has created a specific procurement role. Because of long drawn out assurance processes for multi-year programmes, teams have used transition funded projects to maintain relationships with key stakeholders in China, and to identify key areas where programmes could achieve tangible impact within the Prosperity Fund timeframe while achieving both primary purpose and secondary benefits. Between FY 16/17 to the end of FY18/19, Phase One teams have delivered 53 transitional projects using different procurement routes.

The four strands entered multi-year programme procurement at different times during September 2018 to January 2019 after several rounds of market engagement. Strands attracted different numbers of bids, but all have ensured sufficient market competition. Based on the procurement knowledge gained through transitional projects, most teams progressed swiftly through the evaluation and moderation process. Teams have engaged different parts of the China network, for instance policy team, DIT team, Central Team in bid evaluation.

However, delayed procurement timelines mean that this output merits a B grade. After identifying the successful bidders, London CPG undertook contract negotiations which took longer than expected, shortening the programme delivery timescale and potentially restricting impact and adversely affecting overall VfM (discussed in Section D).

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review.

Recommendations
PROC 1: As China Prosperity Fund Phase One Teams gradually move into inception and delivery stage, it is recommended that teams (in conjunction with CPG) undertake additional programme and contract management training for multi-year programmes, learning from DIFD and other donors’ experience in the country. At the same time, peer learning, which teams already do, is another useful way to learn which can be strengthened.
PROC 2: Set up a mechanism to improve closer working relationships with CPG (including through staff attending commercial bid reviews and short two-way secondments). This would greatly support future programme/contract management work, particularly when disputes happen.
PROC 3: In the Phase Two and Three procurement stages, the finance team needs to be more closely involved and informed throughout the process to better track information required for financial management and to provide key inputs to VfM assessment.

Output Title	2.. Governance & Capacity Evidence that the China Prosperity Fund Programme team’s capabilities and capacities sufficiently support management of the Primary Delivery Partners (PDP) to deliver the outcomes and outputs as set out in the Business Case
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
2.1 Qualitative: the status of CPF team structure and governance to sufficiently support the programme procurement, communication, delivery and decision making through proper integration into relevant departments in the China network	1. Set up of CPF team structure, reporting lines, decision making process procedure in place / 2. Sufficient communication between programme teams and Central Team, between programme teams and the China network	The China Prosperity Fund team structure was relatively stable with a Central Team providing service and/or guidance to teams on finance, procurement, communication and MREL; and three people programme teams working on specific thematic areas. / The programme now benefits from the full time employment of a dedicated Communications Officer, who has been in place since May 2019. / Programme teams are now sitting more seamlessly with the policy/DIT teams; Central Team has been working with the programme teams on daily basis; weekly team meeting and monthly programme manager meetings are set to promote internal communication and peer learning.
2.2 Qualitative: the PDP's team structure has clearly outlined that and experts recruited have sufficient capacity to ensure programme delivery, VfM, G&I, subcontractor management, communication and impact	1. PDP has a clear structure on programme management, communication and clear roles & responsibilities / 2. PDP have hired experts with sufficient knowledge and experience to manage large multi-year programmes	ELCE included the detailed requirement of PDP’s team structure and expertise in to the SoR; ELCE team formed an evaluation panel in the Embassy and evaluated all the bids for PDP / FS: A clear team structure with strong capability on procurement and contract management, a comprehensive communication plan as well as VfM strategy were demonstrated in the proposal of the successful bid winner. Designated lead on G&I was also recruited for the entire cycle of the programme. / Infra: The PDP of infrastructure programme has formed up a team of experts on primary benefit, secondary benefit and gender inclusion, and has developed a comprehensive VfM plan, procurement manual, and stakeholder engagement plan.
2.3 Qualitative: status of portfolio level risk register and programme level risk register with proper mitigation plans, endorsed by Board and Steering Committee Meetings	1. First Portfolio level risk register & programme level risk register developed. / 2. First Portfolio level risk register & programme level risk register revised. / 3. First Portfolio level risk register & programme level risk register endorsed by Board(s)	Since early Q4 FY17/18, all Phase One teams started to set up their own programme level risk register updated quarterly. / At the same time, the first China Phase One portfolio risk register was also created drawing from the programme level risk register. / After the programme and portfolio risk register were created, the team has revised the risk register quarterly and this has been endorsed by the Board and Steering Group committee on the occasions they have met. Overall, the AR Team considered risks to have been understated, particularly where externalities play a role.
2.4 Qualitative: status of training have been identified and attended by team members to mitigate skills and knowledge gap, e.g. RedR programme management, on-line contract management; trade policy training, G&I training etc.	1. Training courses have been identified. / 2. Training courses have been identified; and at least one course has been run. / 3. Training courses: all relevant courses have been run at least once.	China Prosperity Fund Team has identified programme management training delivered by RedR as the basic and mandatary training among all team members. Other training has been actively identified by the L&D champion and other team members, e.g. contract management training, trade policy training, and gender & inclusion workshop have delivered and attended by team members. Contract management training and G&I training events are scheduled in the next two months. / One L&D Champion has been identified in the team and drafted an L&D plan.
2.5 Qualitative: Level of engagement by teams with MR and EL suppliers, to better shape the programme delivery model, TOC, logical framework, G&I aspect, primary purpose & secondary benefit.	1. Teams have begun work with MR and EL suppliers to produce programme delivery model, TOC, logical framework. / 2. Teams have revised programme delivery model, TOC, logical framework, with MR and EL suppliers	In December 2018 and March 2019, the MR and EL supplier paid two visits to China and met with all Phase One teams and explained the support they can offer, such as designing the programme delivery model, drafting of ToCs and logframes etc. / MR and EL teams continued to provide support afterwards, such as during AR preparation, and offered VfM scorecard tool and PF Learning platform support.
2.6 China portfolio advisory group and programme steering group meeting held regularly to provide strategic guidance and operational instructions to China portfolio and each programme respectively.	FY 18/19 Q2: 3 / FY 18/19 Q3: 3 / FY 18/19 Q4: 1 / FY19/20 Q1:	China Portfolio advisory board held every quarter or four month between Sep 2016 and Sep 2018. However, the last advisory board chaired by HMA was stopped ever since Sep 2018 due restructuring of board meetings. Some of the functions have been taken by each programme’s steering group committee meeting while the advisory board has been proposed to split into an Operational board and Strategic board, but arrangements are not yet finalised. / All Phase One teams have gradually adopted the quarterly steering group committee mechanism inviting policy team, DIT team, DIFD, outreach team etc. in the China network to keep relevant stakeholders informed and seek operational instruction from board members.

Key Points
Governance Structure
China Prosperity Fund Team’s structure has not changed over the last three years with a Central Team, and three people per programme. The Central Team’s role evolved from managing a large number of small FCO Prosperity projects into supporting fewer, large-scale multi-year programmes. The two Central Team programme manager roles evolved into Head of Procurement and Head of MREL role. The Central Team acted as the liaison between JFU, PFDU and other stakeholders in London and all strand teams. Apart from providing support and guidance on procurement, finance, communication and MREL, Central Team also ensures consistency among the Phase One, Two and Three teams. Programme teams on the other hand, hold and manage the relationship with key Chinese and UK stakeholders and are responsible for programme delivery and intended impact. Programme teams work closely with the programme suppliers on a daily basis.

MR & EL, Risk Register
MR and EL providers started to approach the team in late 2018. During the two visits of MR and EL teams, they offered support in development logframes, theory of change, as well as evaluation and learning processes. There is now a much better understanding of need on the part of China Programme Team of the MR & EL offer. We recommend the development of a clear MREL strategy that will enable the CPT to drive and manage the MREL resources at their disposal, including but not limited to MREL consultants, suppliers, and support from PFD and JFU.

Teams had a comprehensive risk register at both programme level and portfolio level which has been updated on regular basis. Teams reported to boards for endorsement as well as proposing risk mitigation plans.

Capacity building
As the China Prosperity Fund moved from one year small projects into a large multi-year programme, teams have identified and secured training through many channels, including formal FCO training, experience sharing by internal and external experts, online training, peer learning (e.g. programme manager meetings) etc. Teams have nominated an L&D champion to help identify and plan formal and informal training and have drafted an L&D plan.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review.

Recommendations
G&CE 1: Along with the team’s restructuring and recent line management changes, it is suggested that some co-countersigning responsibility should be set within the Central Team in order to help the balance between programme teams’ integration into other DIT/Policy teams as well as helping ensure consistency within China Prosperity Fund programme teams.
G&CE 2: As suggested by JFU and PFDU, China Prosperity Fund teams should have regular reviews to see whether the staff number, grade and knowledge fit current programme cycles and requirements.
G&CE 3: China PF programme teams and the MR & EL team should agree more effective communication channels. MR and EL content should be better adapted to China’s context and the MR & EL teams should work with the programme teams to better tailor existing and help develop any new required tools.
G&CE 4:The Board(s) mechanisms needs to be adopted as a matter of urgency to keep the new portfolio SRO informed about programme progress, risks, and to endorse programme decisions that are beyond the remit of programme steering group committee meetings. The nature and quality of material required for Board(s) should be reviewed.
G&CE 5: It would be helpful to set up more frequent and appropriately structured peer learning sessions for team members.

Output Title	3..Infrastructure: Policy reform reports and capacity building delivered for officials and programme stakeholders through international expertise and methodologies adapted to the China and partner countries context
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	6.65%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Technical assistance products delivered (including reports, guidelines, methodologies and policy papers) on best practice for delivering sustainable infrastructure to Chinese officials and programme stakeholders	TBC / (milestones for the Infrastructure Programme logframe indicators are currently being finalised with the Lead Delivery Partner)	(Transitional): Developed 2x PPP project implementation methodologies referring to UK 5-Case Model for Chinese central government (NDRC) to learn from and apply UK experience when drafting PPP law (Mar 2017). / (Transitional): Developed 1x value for money evaluation methodology drawing from UK experience of PPP projects for Ministry of Finance (Mar 2017). / (Multi-year): 10x TA workstreams have been prioritised and 2x TA products focusing on project preparation funds and credit enhancement facilities will be produced in next quarter.
Officials and programme stakeholders trained in best practice methodologies for sustainable infrastructure delivery	TBC	(Transitional): 1x large scale training to 350 Chinese government officials and practitioners about UK’s PPP methodology and best practice (Mar 2017) / (Transitional): 1x study trip to the UK including 1 DG and 5 directors from Ministry of Finance to learn VfM best practice (Mar 2017). / (Transitional): 1x working session to 15 officials of Chengdu government to help them better implement a water treatment project (Dec 2018). / (Transitional): 1x sharing session by UK experts from DFID, Standard Chartered Bank and KPMG with NDRC, PBOC and MOF about encouraging international private capital participation into infrastructure projects in developing countries (Dec 2018).

Background
Delivery of technical assistance products and associated training supports development and embedding of best practice policies, processes and methodologies for infrastructure delivery across the project life cycle facilitates more sustainable, commercially viable and higher quality infrastructure projects leading to inclusive growth and poverty alleviation (where Primary Purpose is taken into consideration in design).

Key Points
Credit should be given to the Infrastructure strand for being the first to get Phase One Inception underway. This has required significant effort by the team, and should be recognised and clearly acknowledged.

During the review period, the Infrastructure Programme delivered transitional technical assistance and training projects focused on sharing UK expertise in Public-Private Partnerships (PPPs), infrastructure delivery and private financing. The Programme supported key Chinese ministries, the NDRC and MOF, to draw on UK best practice in Value for Money assessment and broader UK experience with PPPs and concessions, to feed in to the development of China’s Comprehensive PPP Law, expected to be proposed to China’s parliament in 2019, and VfM methodologies. The projects also provided a platform for UK policy and commercial experts to present to key Chinese stakeholders and potential commercial clients and established the UK as a key source of infrastructure expertise and best practice for China as it continues to rapidly develop its institutions, policy framework and market.

These projects also successfully supported the transition from the previous PF model of small, one-year projects to multi-year programming through informing the programme strategy and relationship handling with key Chinese government partners. NB: The project experience resulted in the Programme team deciding to focus more on the Chinese overseas rather than domestic infrastructure sector, concluding this had greater scope for primary purpose and secondary benefit impact within the budget available. This continues to build on existing learning and relationships developed through transitional projects.

The multi-year programme is now underway and in its Inception Phase. Ten TA work stream areas (including project preparation, risk management, and community engagement) have been prioritised, with plans to deliver two ‘quick win’ TA products (online tools to access project preparation funds and credit enhancement facilities) in the next quarter while continuing to scope and align on the broader ten.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review.

Recommendations
INF.1:	Because of the need to engage across a wide spectrum of actors, the (new) Delivery Partner will need to ensure it has sufficient China policy expertise internally or within its supply chain, and that it is plugged into key policy influencers in China in order to ensure the TA work achieves maximum impact.
INF.2:	New Programme Logframe indicators and Key Performance Indicators (KPIs) with units that include metrics of Quality, Quantity and Time for both process activities and hard outputs need to be developed in the next quarter.

Output Title	4..Infrastructure: Pilot infrastructure projects identified and project preparation technical assistance delivered
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	5.7%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Pilot infrastructure projects jointly identified and agreed with programme stakeholders	TBC	MoU on third market cooperation signed by DIT and NDRC ministers at 10th UK-China EFD (Jun 2019). / NDRC sent preliminary inquiry to Chinese businesses collecting projects with potential for collaboration with UK. 18 projects were collected from Chinese businesses (2018). / NDRC are consulting with Chinese businesses to put forward a new ODA-eligible list of projects (Jun 2019).
Project preparation interventions delivered (including feasibility studies, business plans, environmental, G&I and poverty impact reports, funding plans etc.)	TBC	(Transitional): Delivered 1x technical advisory engagement by UK experts to Chengdu municipal government for a municipal PPP water project (Mar 2018) – part of credibility & relationship-building. / (Transitional): 2x scoping studies undertaken to assess interventions to jointly deliver sustainable and quality infrastructure projects in developing countries to maximize positive social impact and private-sector participation (2017, 2018).

Background
Delivering project preparation interventions on live pilot infrastructure projects ensures work on policy and best practice development is practically applicable and allows for demonstrator projects and case studies which can be replicated and scaled-up. Delivery of high quality, sustainable infrastructure projects can directly facilitate job creation and access to markets for local communities.

Key Points
During the transitional period, the Programme Team established a strong relationship with the key Chinese ministerial counterpart with oversight of Chinese outbound infrastructure projects, the National Development and Reform Commission (NDRC). As a result, the NDRC agreed to be the Chinese ministerial lead for the programme. The NDRC also conducted a preliminary consultation with leading Chinese businesses to identify overseas projects for collaboration. An initial list of 18 projects was identified, which has also provided opportunities for secondary benefit.

Very positively, two scoping studies for the multi-year programme clarified the complementary strengths of the UK and China to work together on projects in partner countries, and identified the barriers and challenges to more sustainable, bankable projects which would need to be addressed by the programme. These two reports were presented to the NDRC at the 9th UK-China Economic and Financial Dialogue and have been drawn on as a template for developing China’s own approach to third market cooperation with developed country partners.

During the Inception Phase for the multi-year programme, the team finalised a MoU on Third Country Cooperation, which received high-level endorsement from both countries, signed by DIT and NDRC ministers at the 10th UK-China Economic and Financial Dialogue and witnessed by the Chancellor and Vice Premier of China. The agreed text secured the strongest ever language on development standards achieved in a third country cooperation MoU with China, and included for the first time reference to the G20 Principles for Quality Infrastructure Investment. Following the MoU signing, the FCO and NDRC agreed a G2G steering group to oversee the Programme, and the NDRC circulated a formal notice to 30 leading Chinese firms to collect proposed pilot projects with defined sustainability and local impact criteria.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review.

Recommendations
INF.3:	The link between outputs and primary beneficiaries should be clear through Indicators in the Logframe.
INF.4:	The success of the programme is dependent on positive key relationships being maintained between British Embassy programme staff, the Prime Delivery Partners and a relatively small number of key Chinese interlocutors, who provide access to and facilitate dialogue with various parts of the Chinese Government. As a broad strategic thrust, the programme should actively seek multiple lines of communication and dialogue as part of a general risk-management strategy for the portfolio. The AR Team does, however, appreciate the sensitivities involved and the hierarchical nature of the Chinese government.
INF.5:	RISKS: Overall the Risks identified for all three sub-components are self-assessed as Moderate. Given the limits to Year One indicators & activities, this is acceptable. However, for Year Two, when attempts to start to design & implement Pilots Infrastructure in partner countries are to be initiated, then the overall risk for this strand should be revised to Major.

Output Title	5..Infrastructure: Partnerships and collaborations formed and consolidated to support programme design and the establishment of a platform for pipeline development, investment facilitation and business matching
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	6.65%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Pipeline development, investment facilitation and business matching platform/mechanism activities delivered	TBC	Regular (8x) B2B events to increase British profile in delivering sustainable infrastructure projects in front of Chinese and partner country stakeholders (2x DIT events in Macau, 1x Private Infrastructure Development Group (PIDG) workshop to 60 Chinese companies, 1x UKEF & Standard Chartered Bank joint workshop to 40 Chinese companies, 1x working session with PowerChina, 3x UK-CN events in Ethiopia, S.A., Egypt)
Key China, UK and partner country stakeholders engaged to support multi-year programme development and secure high-level buy-in	TBC	Identified and established relationships with over 20 core stakeholders (government, policy banks, commercial banks, insurance, EPCs), increasing buy-in for the programme and wider interest in commercial collaboration with the UK. Supported scaling up of UK-China engagement across numerous partner countries (incl. South Africa, Egypt, Malaysia, Indonesia, Kenya and Ethiopia)
High-level visits and dialogues supported by programme team and endorsing the PF programme	TBC	Participated in / supported 7x high-level events/visits and secured endorsements for the programme: / 1x JETCO (Ministry of Commerce) / 2x EFD (NDRC, Vice premier) / 3x HMT BRI Envoy visit to China / 1x PM visit (PBOC-DIT roundtable)

Background
Given the complex strategic environment of the Programme and political economy in China, securing buy-in and contribution from key stakeholders in China, UK and partner countries is vital to the success of programme delivery. Pipeline development, investment facilitation and business matching will be important tools to identifying and supporting new private capital investment into infrastructure projects to raise standards and drive commercial opportunities. High-level visits and dialogues are key moments in the bilateral calendar which can be leveraged to secure programme progress. It is important that time and resource requirements to support these activities are adequately understood and recorded.

Key Points
The Programme team has delivered and supported numerous partnership activities, events, visits and high-level dialogues throughout the review period across China, partner countries and the UK, to raise awareness of the programme, secure buy-in, and scale up the engagement with China needed to successfully deliver the programme outcomes.

The relationships and partnerships the Programme team has developed throughout the review period across government and business has supported wider HMG work led by DFID, HMT and DIT. The work of the Programme team has played an important role in the development of the China strategies of PIDG, UK Export Finance and DIT.

The importance China places on collaboration in third markets and on high-quality infrastructure with the UK is evident from numerous statements by Chinese leaders, including Premier Li Keqiang, Foreign Minister Wang Yi, NDRC Minister Ning Jizhe, Commerce Minister Zhong Shan etc. to UK Government counterparts over the past two years.

The UK and China governments also welcomed the launch of the programme in the Policy Outcomes Paper of the 10th EFD in June 2019 and agreed to undertake technical cooperation, joint research, pilot projects, investment facilitation and pipeline development with the aim of delivering sustainable, bankable infrastructure projects in third markets. Both sides also agreed to develop a three-year work-plan to promote the practical cooperation needed to improve the sustainability, quality and commercial viability of growth-enhancing infrastructure in Africa and Asia.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review.

Recommendations
INF. 6:	Ensure programme of High-Level Visits/MoU signing and landmark events continue to be tied to clearly articulated programme output and outcome achievement markers/milestones.

Output Title	6..Financial Services: Evidence that FS Programme transitional activity and initial engagement contributed to programmes outcomes, both in terms of primary purpose and secondary benefit, and the design of the main delivery phase of the programmes
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	4.5%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Evidence that scoping studies/pilots/transition year projects have defined the focus areas for the multi-year programme, and been incorporated into the MoU with Chinese Government	Scoping studies formulated (2016/17)	Five scoping study reports were completed in year 16/17. Three areas of focus have been identified and incorporated in the multi-year programme business case. They are also incorporated in the MoU signed with Chinese government.
No. of policy papers, roadmaps, approach papers, reports (including inception reports) etc. produced that have contributed to the reform of targeted areas in the multi-year programme	Policy papers completed (2017-2019)	Two policy papers on Fintech and regulatory reform have been produced in 17/18 respectively. Another one on a workplace pension scheme is now being drafted. All the three have significantly contributed to the reform landscape with key decision makers at Chinese government ministries and regulatory institutions
Evidence that the business case and programme design evolved through each stage of the approvals process, and took on relevant feedback from key stakeholders in the FCO and cross-Whitehall governance chain	Key comments from stakeholders were incorporated in the business case.	Key comments from suppliers and internal stakeholders such as IIOC were incorporated in the business case.

Key Points
Scoping studies were undertaken in order to explore areas within the financial services sector that have the greatest potential to serve the primary purpose and secondary benefit for Prosperity Fund. These five areas include Capital Markets, Asset Management, Green Finance, Insurance and Fintech. Out of them, three were subsequently selected as areas of focus for the multi-year programme, including insurance, pension and Fintech.

A number of policy papers were produced on regulatory reform, fintech and pensions. These laid the groundwork for the multi-year programme in terms of relationship building and knowledge sharing. For example, the regulatory reform policy paper laid out specific areas that UK can share experience with China. During the drafting and finalising stage of the report, a group of prominent experts and policy makers was formed as the “Advisory Group” and “Consultation Group” of UK-China Financial Policy Initiative. The initiative and groups under it enabled in-depth dialogues between UK and China on this topic, in particular between the programme and policy team and Chinese regulators. The project deepened the UK relationship with the most influential academic institute in China’s financial policy area, the PBC School of Finance, now a member of the implementing consortium.

It is clear that the approvals process led to positive changes in the approach. The programme adopted a “Fund Manager” model to accommodate risks related to the unique characteristics of China’s political economy. There is a break clause at the end of the Inception Phase and a detailed Annual Review process (along with more regular governance checks) to ensure the work is on track and risks are identified, mitigated and responded to where necessary. The programme also set up a robust governance structure (more details under Output 4) as proposed by IIOC.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review.

Recommendations
FS1: Programme has met its expectations, though it could improve its articulation of how the engagement has addressed, and where relevant, improved the design of programmes - from both a primary purpose and secondary benefit perspective.

Output Title	7..Financial Services: Evidence that the China FS Programme procurement approach, processes and delivery model design, as well as guidance and support received from London resulted in robust tendering and contracting which has set the programme up for success
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	4.5%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Qualitative: evidence based on independent consultant reviews (Palladium, YS, CW) and stakeholder engagement (e.g. green SoRs) that shows the programme design (interventions, themes, ToC, procurement plan) has improved significantly over time before the final tender was issued	Programme design has taken comments from consultations and stakeholder engagement during inception stage

Key Points
The Programme Team has had extensive engagement with Framework suppliers in the run up to the tender being issued. The procurement of the design, inception, implementation and closure phases of the Programme also contains substantial engagement with external stakeholders. To assess whether the market had the capability, capacity and motivation to deliver the services required, the Programme engaged with over twenty potential implementing partners and beneficiaries since September 2016. This included, for example, workshops for suppliers in London and Beijing in late 2017.

The market engagement indicated that there was sufficient private sector interest in delivering the services required to achieve the outcomes and outputs set out in the Strategic Case. This interest was both at a global (Framework Agreement) level and at local supply chain level. Recommendations that arose from the market engagement events were incorporated into the SoR, where applicable.

However, this output score reflects the significant delays that have occurred in the process of approval and preparation for market, and that as a result, the procurement process has been delayed with different perceptions between Post and CPG. Recommendation FS2 proposes a way forward to resolve issues.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review.

Recommendations
FS2: Procurement, contract and programme management processes and guidance need to be further refined and tailored for Prosperity Fund China and conduct regular dialogue.

Output Title	8..Financial Services: Evidence that the current China FS Programme team’s capabilities and capacities sufficiently support management of the Primary Delivery Partners (PDP) to deliver the outcomes and outputs as set out in the Business Case
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	3%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Training in relevant policy areas and programme management skills is completed by the programme teams via workshops, self-study, conferences and formal training seminars	Relevant policy and programme management training is identified and participated in by FS team members.	Programme team has attended formal training Programme Management, Contract Management and a number of events/seminars on subject matter and their knowledge on relevant issues have been strengthened.

Key Points
It is clear that the FS strand is on a steep learning curve and that knowledge and capacity has been built, through both formal training (e.g. PF REdR Programme Management training) as well as through attending workshops and policy events., e.g. a Global Finance Summit in June 2018 at Tsinghua University. The team is meeting expectations on management of the programme, and has attended the relevant training to strengthen their skills in this area.
Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review

Recommendations
FS 3: For the future, the team could increase its expertise in monitoring progress with its projects and holding implementing partners to account.

Output Title	9..Financial Services: Evidence that the existing governance arrangements for the individual programmes support the control processes and make implementation more effective.
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	3%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Effective structures for Programme design and management that integrate Prosperity Fund team, Policy team and DIT teams	Well defined roles & design of programme team with deep integration into the China network	A Steering group was set up early 2018. It comprises a good balance between programme, policy and DIT teams. Three steering group meetings have been held so far and have contributed to the programme design. The Programme SRO is the overall lead for FS in China meaning strong alignment including throughout consulates and significant cross-team working to increase secondary benefits. A Deputy Programme SRO (Rhys) ensures regular senior engagement

Key Points
It is clear that a steering group has been established, and is providing input into work plans, risk management & policy relevance. As per overarching recommendations, however, it will be important to ensure that the steering committee includes development expertise.

There is evidence that the programme team works closely with policy and DIT colleagues. The Programme SRO is the overall lead for FS in China meaning strong alignment including throughout consulates and significant cross-team working to increase secondary benefits.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review.

Recommendations
FS 4: Consider adding development expertise to the skills and knowledge base of the Steering Group.

Output Title	10..Financial Services: Partnerships and collaborations formed and consolidated to support programme design, alignment with host government priorities as well as emerging initial outcomes achieved
Output number per LF		5	Output Score	A+
Risk:		Moderate	Impact weighting (%):	4%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of stakeholder engagement with China, UK (and third countries) held or supported by PF programme to support multi-year programme development and ensure government/key stakeholder's buy-in (exclude project activities)	21 direct engagement occurred	Programme team has engaged directly with Chinese government 18 times within reviewed period and laid ground for bilateral agreement on multi-year collaboration; / 3 seminar/events organised under transitional year projects;
Number of outcomes from meetings and engagement to support programme development and delivery (If there is clear evidence of working progress towards G2G agreement, government endorsement etc.)	MoU signed between two governments to endorse FS programme	MoU signed on 17th June 2019 in the margin of UK-China Economic and Finance Dialogue
Number of successful stories and description of initial primary outcomes and secondary benefits achieved with a verifiable contribution from the programme (ODA and Non-ODA projects)		A UK-China joint venture insurance company gained its pension license first of its kind through work related to transitional year project. / A total of £110 million export win achieved by two Fintech companies from M2020 (non-ODA) / Strengthened mutual recognition on accounting standards which contributed to the successful launch of London-Shanghai Stock Connect / New insurance product for poor farmers to be introduced (work started last FY)

Key Points
Underdeveloped pension provision poses a significant risk to the financial security of China's ageing population, particularly among poorer sections of society. Through a non-ODA project in 2017/18, the programme supported dialogues, events and joint research pieces between China’s Ministry of Human Resources and Social Security (MOHRSS) and Department of Work and Pensions (DWP) on workplace pensions. Through this work, the programme has played a key supporting role for UK-China Joint Venture (JV) organisations looking to develop the private pensions market in China. A combined and sustained effort with DIT and FCO colleagues has recently resulted in one such JV firm becoming the first part-foreign company to obtain a license for pensions insurance business in China (March 2019).

In 2017/18, a project involving the UK Financial Reporting Council and the Chinese Ministry of Finance has led to the issuing in early 2018, of a report on an auditing regulatory framework between UK and China. This should lay the foundations for am MoU to work towards recognition of respective audit regulations, which would be a significant step to reduce reporting burdens for UK companies, which until now have acted as a barrier to British business. Through a transitional year project in 2017/18 named “Strengthening UK-China Cross-border Audit Regulatory Cooperation to Support Foreign Participation in China’s Bond and Equities Market”, China’s Ministry of Finance and UK’s Financial Reporting Council signed a MoU to strengthen the mutual recognition of auditing document with regard to panda bond issuances. This largely reduced the cost and simplified the procedures for future panda bond issuance of UK companies. The project also deepened the cooperation between the accounting authorities on both sides, which contributed to the negotiation of a relevant part in the MoU for the forthcoming London Shanghai Stock Connect.

Through a non-ODA project in 2018/19, an event held for policy makers and private sector players on Fintech contributed to commercial contract worth approx. 110 million GBP of export win gained by two UK fintech companies. The programme team has arguably exceeded expectations. To have both a MoU signed by the two governments, and export (notional) wins totalling £110M are exceptional events.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review.

Recommendations
FS 5:.Complete & review milestones.
Output Title	11..ELCE: The evidence of ELCE Programme transitional activity and initial engagement contributed to programmes outcomes, both primary purpose and secondary benefit, and the design of the main delivery phase of the programme
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10.5%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Evidence from scoping studies/pilots that form the focus areas for multi-year programme, which have been incorporated into the MoUs with Chinese Government.	Completion of the Scoping Report / Signing of the Action Plan and Work Plan that implement the UK-China Clean Energy Partnership MoU.	The Programme Scoping Report has been completed and laid out prioritised areas for UK-China collaboration, which were finalised into Four Pillars, defining the scope of the Programme. These were incorporated into the UK-China Action Plan (signed in 2017) and Work Plan (signed in 2019) for implementation of the high-level MoU for the UK-China Clean Energy Partnership.
No. of policy papers, roadmaps, approach papers, reports (including scoping reports) etc. produced that address the needs for China's low carbon transition	The Power Sector Reform expert exchange forum has contributed to new policy guidelines issued in China. / Climate Risk Indicator Assessment (CRIA) Report completed and disseminated during the high-level COP 24 event in Katowice in 2018	There were over 15 policy papers developed through 2016 to 2019. These papers have all targeted key areas and needs for China’s low carbon transition. The Power Sector Reform expert exchange forum in London has brought together high-level policy decision makers, top experts, and grid operators from China and the UK to discuss the needs for China’s power sector reform moving forward, which contributed to new policy guidelines issued in China. / The CRIA Report was delivered and disseminated on time and appears to have impressed Chinese interlocutors.
Improved capacity of / stakeholders and policy makers in the focus areas of the multi-year programme	High-level officials from Chinese central government including NDRC, NEA, and local provincial governments participated in workshops, seminars that received the UK knowledge and experiences	The Programme supported various projects that led to improved capacity of key stakeholders and policy makers in focus areas. The programme milestones were successful in delivering capacity building outcomes. The PSR expert exchange forum has contributed to new policy guidelines
Stakeholders in the Climate Risk remit accept the proposed Climate Risk indicators (we can arrange interview with key stakeholders)	Climate Risk indicators accepted by relevant stakeholders	The Climate Risk indicator work has been implemented continuously between influential partners in the UK and China from 2017 to 2019. A Climate Risk Indicator Assessment Report has been completed and disseminated at various high-level events in 2018 including COP 24, which led to wide recognition of the work from Chinese policy decision-makers. International organisations including UN Agencies expressed interest in incorporating the indicator system into UN systems.

Key Points:
Transitional Funding was designed and used to support necessary projects that: a) maintain important relationships with key stakeholders; b) explored interventions for the multi-year programme; and c) keep disseminating information about the Prosperity Fund. The approval and procurement of the programme was significantly delayed between 2016 and 2019, and transitional funding was particularly critical to fill in this intermission.

The Output and activities of those transitional projects seek to secure Chinese government stakeholder’s endorsement, build the capacity of research institutions and policy-makers, and deliver the UK’s soft power. These efforts aim to address China’s urgent needs for low carbon economy transition, emission reduction, and inclusive economic growth. The China Energy cluster (Prosperity Fund programme team, Policy, DIT) steered the project design and approval process through a joint decision-making process, optimising the potential for secondary benefits to be realised.

The Beijing team was keen to highlight two projects in particular: a) Expertise for China’s power sector reform and b) The Climate Risk Indicator Assessment Report. The expertise exchange enabled substantial improvement in the capacity of China’s policy decision-makers and led to a new policy guideline for power sector reform that aims to speed up the country’s low carbon transition effort. The finalisation of the Climate Risk Indicator Assessment Report has attracted high-level political attention through well-designed dissemination events. Not only Chinese but also international governmental organisations were aware of this product and seem to have accepted the indicators proposed.

Lessons Learnt:
Close connection between the Energy Group and the Chinese government’s strategy will help ensure that projects address the most urgent reform needs. High-level Chinese government buy-in is very important. An MoU with the National Energy Administrative is critical to deliver multi-year interventions and secure enabled participation of Chinese officials.

Some projects were implemented by third-party entities. They demonstrated a good understanding of ODA rules and strong knowledge and linguistic capacity in following FCO contract and financing guidance. However, the lack of strong relationships with China’s key stakeholders prevented them from getting access to high quality data, information, setting-up meetings, and transferring the reports and recommendations to Chinese policy decision-makers.

Chinese implementers are good at delivery outcomes due to their generally close relationship with the Chinese government, but lacked ODA knowledge and competent language capacity to complete relevant FCO paperwork. This shortage of capacity has created barriers for some implementers to bid for projects, and consumed quite an amount of the Programme team’s resources throughout certain projects. In the multi-year Programme, it is anticipated that the Delivery Partner will provide assistance wherever necessary to Chinese implementers to fulfil programme requirements.

Recommendations
ELC. 1:	A more clearly articulated line of sight to achievement of Primary Purpose could be developed. The programme needs to articulate and demonstrate how it contributes to poverty alleviation. Logframe indicators to show this a little more clearly should be developed.
ELC. 2:	Now that the programme is moving steadily into Inception and thereafter Implementation, construction/formulation of the Output should be modified to take account of that changed situation. The Strand team is encouraged to revise the Logframe and indicators appropriately. Risks of non-attainment of the overall programme objective are probably Major, rather than moderate (discussed in ELC 6).
Output Title	12..ELCE: The evidence of the current China ELCE Programme team’s capabilities and capacities sufficiently support management of the Primary Delivery Partners (PDP) to deliver the outcomes and outputs as set out in the Business Case and recommendations to close the gaps
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	2.25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Training in relevant policy and subject matter is completed by the programme teams via workshops, in-door or online training	All team staff have completed RedR training organized by JFU / ELCE team members participated relevant workshops to better understand relevant policy and subject area	The Programme team members have completed relevant training through various formats, including through RedR, to learn about ODA rules, programme management, development, and implementation. The capacity gap resulting from personnel changes to the Programme team in December 2018 was subsequently filled by staff that are more experienced in FCO programme and contract management. The team continues to develop through attending workshops, meetings and conferences.

Key Points:
The right skill set and knowledge that the Programme team has developed will greatly facilitate the delivery of programme outcome and impact. Continuous development in knowledge is useful and necessary to keep the knowledge and experience in the team and cope with unexpected capacity volatility. The current Programme team members have all participated in RedR, FCO online Contract Management, and the PF Learning pilot programme.

Peer-learning is also a very useful way for knowledge sharing among colleagues in the same or different sections that benefit all. Prosperity Fund maintains all strand Programme Managers monthly meetings to meet this demand.

Lessons Learnt
Good learning resources are needed for the Programme team members to catch-up with the different knowledge that suits the changing phases of the Programme. Systematic training on integrating gender and inclusion indicators into the project design has not been undertaken. A fair amount of knowledge in this area can be learnt through peer-learning. However, good external training resources have not been identified yet.

Recommendations
ELC 3. Building on the Transitional Phase achievements, this output should be reviewed and modified. The programme team should look at what it is that the Delivery Partner(s) are going to deliver – those are the new outputs, and then construct a supporting set of metrics than ensures that they can and do deliver. The identification and procurement of suitable additional training resources is part of that requirement.
Output Title	13..ELCE: The evidence of the existing governance arrangements, both for individual programmes and the China portfolio support the control processes and making the implementation more effective.
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	2.25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Effective structures for Programme design and management that integrate Prosperity Fund team, Policy team and DIT teams	Energy Policy team and DIT Energy team formed up the China Energy cluster / Programme team restructured (Head of Energy Policy becomes the SRO of ELCE; management line of Programme team changed from Central Team to Energy Policy team) / Climate Change team transferred to Political section to reflect the Chinese government’s perception on Climate Risk.	The Embassy has setup an Energy group where people from Policy, DIT, Prosperity share information and ideas about general UK-China energy cooperation, and specifically on ELCE Programme design. The management line for the ELCE Programme team has been adjusted from being within the Prosperity Fund Central Team to being under the Policy SRO. The change is aimed to streamline the programme decision making and optimise programme outcomes.

Key Points:
The Embassy has set-up up an Energy Group that brings people from different sections together to share information and discuss the programme. This diversity reflects the interests of energy from multiple HMG sections, as well as addressing the achievement of Primary Purpose and Secondary Benefits from the Programme.
The SRO for Energy is now line-managing the ELCE Programme to streamline the decision-making process. Sectoral knowledge and the capability of coordinating with BEIS has strengthened the SRO’s capabilities to steer the Programme and optimise the Secondary Benefit potential, permitting the Programme team to focus on the Primary Purpose. The policy lead for the Climate Risk component has moved from the Energy Group to Political Section which will benefit the component work with bigger political awareness and support.

Lessons Learnt:
The new structure has enhanced the SRO’s authority over programme steering. It requires a solid understanding of ODA funding rules and skills to design programmes that will achieve Primary Purpose, so that ODA funding will not be overly driven by Secondary Benefit objectives.

Recommendations
ELC.4:	The formation of a fully functioning Energy Expert Exchange is a typical and highly desirable output. Transitional Phase focus of this section on internal governance arrangements as a measure of the success of that kind of Forum can now be built-upon to provided additional programme objective “stretch”. It is recommended that the team look outwards to what it is that adequate governance processes and structure are trying to achieve in China and with international counterparts and set those metrics as outputs.

Output Title	14..ELCE: Partnerships and collaborations formed and consolidated to support programme design, alignment with host government priorities as well as emerging initial outcomes achieved
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	4%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of stakeholder engagement with China, UK (and third countries) held by programme staff to support multi-year programme development and ensure government/key stakeholder's buy-in (exclude project activities)	18 meetings held with Chinese and international government and stakeholders	Programme team has led or participated in a good number of meetings with government or non-government stakeholders for information exchange and programme development.
Number of outcomes from meetings and engagement to support programme development and delivery (If there is clear evidence of working progress towards G2G agreement, government endorsement etc.)	Chinese government’s support for the Programme	China’s NEA endorsed the Programme and launched the programme with Minister Skidmore during the Energy Dialogue 2019.
Number of high-level visits and dialogue PF support and get endorsed	NEA DG level delegation to the UK for power sector reform knowledge exchange / The Embassy’s Deputy Head of Mission and NEA Deputy Director General (on behalf of the DG) opened the UK-China Clean Energy Conference in March 2019.	The programme team supported high-level events that showcased the UK expertise and knowledge to Chinese key stakeholders. The high-level presence from the Chinese side is indicative of their clear awareness of the UK’s strengths and implies political will to work closely with the UK. This awareness and willingness is critical to the success of interventions in Programme design.
Number of successful stories and description of initial primary outcomes and secondary benefits achieved with a verifiable contribution from the programme (ODA and Non-ODA projects)	Successful influence on the new policy of China power sector reform. / Successful launch of Climate Risk Indicator Assessment Report. / The Climate Risk work to be accepted by the UN.	The Outcome of some projects in 2018-2019 should be highlighted: The expert exchange in London has brought the right expertise together to address China’s need to reform its power market. The knowledge gained from this event contributed to the new policy issued a few months later. The Climate Risk Indicator Assessment Report was completed and launched at various high-level events including the COP 24 in Katowice. That report was well recognized by Chinese policy-makers. UNEP invited the UK (BEIS) to brief a meeting of UN agencies on the work, which could ultimately lead to UN adoption of the UK approach.

Key Points:
There were 7 ODA projects in 2018-2019. Those projects were designed to achieve the Primary Purpose and the Secondary Benefits. The Transitional projects in 2018-2019 successfully bridged the gap before the multi-year Programme start by engaging with key Chinese stakeholders, developing interventions that align with the multi-year Programme priorities, and delivered policy outcome & outputs. Outputs/outcomes include the contribution to the new policy guidelines for China’s power sector reform, and a key Output was the Climate Risk Indicator Assessment report launched and accepted by Chinese and international governmental organizations.

Lessons Learnt:
The significant delay of the multi-year Programme start caused by the contracting process with the Delivery Partner resulted in negative impact on the Transitional projects’ outcome. The uncertainties prevented accurate and timely information to be released to the market.

Recommendations
ELC.5:	Partnerships, with suitable defining metrics are perfectly sound output(s). The approach to work being undertaken is strongly endorsed (subject to caveats on “line of sight” to Primary Benefits).
ELC.6:	RISKS: Overall are Major. Contracting & Procurement delays, need for better understanding and dialogue, and vulnerability to relationships with key Chinese interlocutors all combine to increase risk. There are additional significant geopolitical external potential threats to relationships (Hong Kong, maritime waters, USA-trade etc.) that cannot easily be mitigated for within the programme.
Output Title	15..Business Environment: The capability of targeted Chinese government departments and private sector organisations are enhanced, to support China's progress towards improved business environment
Output number per LF		1	Output Score	A+
Risk:		Major	Impact weighting (%):	14%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of Chinese stakeholders trained in IP, CDR, AML, IE and standards (supported by evidence of uptake of training knowledge and skills)	Achieved: 195	IP: Trained 10 officials of General Administration of Customs on IP enforcement (Apr 2019). / CDR: Trained 35 judges and legal practitioners (Nov 2018). / AML: Trained 150 people from PBoC, government departments and industry practitioners on the FATF MER assessment methodology.
Number of events (incl. conferences/ workshops/seminars/roundtables) delivered	Achieved: 8	IP: Organised 2 roundtables on IP enforcement, protecting branding and tackling infringement. / CDR: 2 workshops on resolving international commercial dispute and implications for Chinese legal reform (Nov 2018 & Mar 2019) and 1 UK-China Judicial Expert Working Group. / AML: Organised 4 workshops with PBoC and cross government departments to assist China to prepare MER assessment for 2019 FATF Plenary.
Number of technical assistance products (including policy/recommendation papers, research reports, roadmaps) that inform the business environment reform agenda	Achieved: 7	IP: Produced a consultation response paper on the draft E-commerce law and later a position paper to advocate improvement in the implementation of the E-commerce law (Aug 2018 & Feb 2019). / CDR: Produced a scoping report examining the CDR framework and proposed priority areas. / AML: 4 technical recommendation reports to support China to prepare MER assessment.
Number of adoption of programme recommendations, demonstrating improvement in the business environment legal/regulatory framework and its implementation, enforcement and compliance	Delivered: 35	IP (2): Adopted recommendation on specific provisions of the draft E-commerce law. A systemic link established between online infringement and offline enforcement. / AML: Delivered a major early policy impact, involving on-going uptake of technical recommendations which contributed to China achieving an optimal result in its MER and established a clear road map for the country's continued development of its AML regime. 33 laws, administrative and departmental regulations on AML provisions were updated and introduced (2016-2019).

Key Points
The Business Environment strand has substantially exceeded expectations in terms of building capability of key Chinese government departments.

For example on IP, implementers had delivered 11 roundtables, a large number of events and meetings, established 11 e-commerce partnerships, and delivered 2 position papers. In practice, this delivered concrete primary purpose benefits, the benefits for rights holders are clear. On commercial dispute resolution, officials of the Supreme People’s Court (SPC) confirmed that PF financed projects since 2016 had supported their participation in nine roundtables or working groups. Court officials recognised that the programme can facilitate cooperation and improve the business environment in China, including people’s access to justice.

On anti-money laundering, PBOC officials confirmed that PF support (through govrisk) has been instrumental in supporting China’s assessment by the Financial Action Task Force (FATF) with the result that China demonstrated its reform effort and was put under “‘Enhanced Follow-up”. On Investment Environment, the team is considering World Bank proposals to carry this work forwards. Finally, on standards, a project to support standards reform has just commenced inception.

This indicator reflects the fact that this strand has undergone a thoughtful refresh of priorities, with wide consultation & a sensible decision-making process endorsed by steering board, and a renewed focus on business environment improvement and secondary benefits. While on this indicator the programme has exceeded expectations, it unfortunately does not include an assessment on primary purpose & development effects of the programme, which are in need of strengthening across the strand.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review.

Recommendations
BE.1: Undertake a thorough review of this strand approach to primary purpose and gender and inclusion during the visit of PFD’s Social Development Adviser in August 2019. A strand specific G&I action plan should be the outcome.
BE.2: Strengthen development advice on steering board
Output Title	16..Business Environment: Programme partnerships with government, non-government stakeholders and supply chain are developed and strengthened, to support effective multi-year programme design and delivery.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of newly established and strengthened institutional relationships with the Chinese government and non-government stakeholders	Achieved: 90 (accumulated number)	MoUs (2): HMT-PBoC MoU (for Financial Service Programme and AML strand) signed at the Economic and Financial Dialogue and MoU signed between the British Standards Institute and the Standardisation Administration of China. / IP (10); CDR (23); AML (50) / IE (3): Secured high-level buy-in from NDRC. / Standards (2): Secured high-level buy in from SAMR.
Number of projects awarded, delivered and performance effectively managed (via the CBE team or PDP).	Achieved: 3	Delivered 3 transition year projects on IP, CDR and AML.

Key Points
The Business Environment strand has met expectations on partnerships to support effective multi-year programme design and delivery, although milestones are insufficient and require revision.

Meetings with Government of China stakeholders (PBOC, SPC) implementers (BSI, CBBC, GovRisk) demonstrated that the Programme Team is building on long-established and effective partnerships in shaping this strand and moving towards multi-year programming. PBOC officials pronounced themselves ‘very satisfied’; PBOC officials welcomed the prospect of longer-term engagement & the potential to focus on improved systems, structures, capabilities. Implementers were positive about engagement & the procurement process.
The one question mark is the extent to which partnerships can be considered effective without the strong, clear, agreed approach on delivering development effects, as well as secondary benefits and business environment improvement. We would like to see a much more consistent and clearer narrative for this programme in terms of how improvements to the business environment (including, but not limited to, opportunities for UK companies) also deliver development effects.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key Cost Drivers and performance
All strands have had substantive pre-transitional and Transitional Phase activities underway, and the pattern of disbursement can be seen in the summary of actual versus forecast expenditure date presented in Table D1 below.
There is a history of generally high programme staff cost with respect to programme portfolio size prior to 2019/20, thereafter the ratios start to fall substantially and it is anticipated that over the lifetime of the portfolio, staff and administration costs will fall to ~3.87% of the overall funds available. Higher General Administration costs and programme development costs are not unexpected for this type of set of development activities.
Table D1: PF China Budget v. Actual Expenditure 2016-2019

i.e. Overall expenditure was 85% of forecast budget.
VfM performance compared to the original VfM proposition in the Business Case
The programme commenced inception with the Infrastructure strand in early 2019. Three other Phase One programmes (ELCE, Financial Services & Business Environment) are also about to commence inception phases this year, albeit later than originally expected. It is anticipated that overall outcomes and related impact primary and possibly secondary benefit realisation will be delayed by between six and 12 months but should not significantly affect the outcomes designed in the Business Cases. Records of transitional project primary purpose and secondary benefit impacts/achievements have been maintained, and these will be subject to further detailed attribution analyses in September 2019.
Economy (are we getting inputs at the right price and quality?)
To ensure inputs were procured at the right price and quality, a competitive tender process was implemented. After several rounds of stakeholder engagement and one-on-one consultations, the Infrastructure programme received 5 bids, ELCE received 3 bids, BE main programme received 4 bids, Standards received 2 bids and FS received 2 bids.
Due to the complexity of programme design and different approaches to assessing bids, the evaluation process involved more interactions within the embassy and HMG system than expected. Although involving experts from all sectors led to a fair, transparent and robust discussions in the selection process, we recommend this substantial staff resource is factored into the efficiency assessment once the programme starts delivering outputs.
Efficiency (how well are we converting inputs into outputs?)
Overall, planned timetables have slipped, as a result of a general unfamiliarity with multi-year contracting and procuring processes. The Programme Team identified the need to upskill and better tailor guidance from the Centre/ London. As such the review team recommend scaling up capabilities in multi-year contracting and procuring processes. The London team will work on developing mutually agreed acceptable service level agreements. This will ensure efficiency when the programmes start to deliver outputs.
Effectiveness (how well are out outputs delivering the desired outcomes?)
At this early stage, programme activity supports the overall thesis developed in the Theory of Change. Notwithstanding the likely technical and data-set challenge of contribution and attribution analyses in a substantial Chinese resource pool with many externalities, the portfolio has significant potential to achieve a mix of Primary and Secondary Impact benefits. For example:
The Infrastructure programme, in collaboration with DIT, has helped facilitate cooperation agreements between UK and Chinese businesses, and the UK-China Infrastructure Academy project, using non-ODA funding, has trained Chinese investors making major investments in infrastructure and regeneration projects across the UK on best practice approaches to UK market entry, standards and regulatory requirements.

The Energy and Low Carbon Economy programme has expanded bilateral collaboration in this sector with China. More strategically, and with potential global benefit, a recent PF-supported high-level bilateral report on Climate Risk Indicators is influencing Chinese policy discussions, including Chinese decisions on 2030 and 2035 emissions targets.
The China Business Environment programme has supported better IP protection policies of China’s Amazon equivalents, leading to a more level playing field for SMEs, a first UK company has made a £4 million claim. Programme recommendations for China’s e-Commerce Law have been adopted; and the PF team through GovRisk are supporting China’s Central Bank on strengthening Anti-Money Laundering (AML) standards. Chinese leadership, enthused by its 32-place rise in the World Bank’s Ease of Doing Business rankings, has stepped up business environment reform and wants to work with the PF on next steps needed.
Financial Services programming has supported a UK pensions provider to become the first foreign company to receive permission to open a pensions business in China, a market worth over £10bn a year; expected annual revenues for UK companies in this market will exceed £100million by 2025. Programming has also helped establish a UK/China fintech bridge to improve fintech regulation and commercial ties including multiple export wins and FDI wins in the sector; deepened cooperation between UK/China auditing authorities; optimised ‘Panda Bond’ issuance for international issuers; contributed to the negotiation of a relevant part in the MoU for Shanghai-London Stock Connect; supported growth in offshore RMB in London; and widened the market access of private fund management.

Recommendation D1. Valid causal pathways: while programme level ToC have been drafted, further work is needed to develop the narrative on how change is expected to happen as a result of PF support. A clearer articulation of how the programmes will deliver primary purpose and secondary benefits is needed, although it is also worth noting that some programmes e.g. FS and Infrastructure are developing /have developed dedicated primary purpose and secondary benefits action plans.
Equity
On Gender & Inclusion specifically, the Programme Team’s G&I assessment rates amber (insufficient evidence of alignment with PF G&I policy) overall, although has scored a green on internal capability. The work that the programme team has done in terms of developing a G&I action plan is recognised. Overall, there is work to do to ensure that Primary Benefit Impacts are targeted at poorer and more disadvantaged beneficiaries, both in China and in third-countries. Key recommendations and conclusions were stated in Section B previously.
Assessment of whether the portfolio continues to represent value for money
This is the first full year of implementation. Subject to the risks inherent in portfolio commencement delays and the probability that the end date is likely to need extension for all programmes, the portfolio is taking steps to ensuring good VfM practises.
Recommendation D2. Sustainability: Although rated in the self-assessment as an area of improvement the validation of the findings reported in the scorecards indicated that sustainability was in active consideration by teams in the delivery of their programmes. Infrastructure required bidders to develop a sustainability plan, noted also the scope for replication of pilot projects thereby enhancing the sustainability of the PF support, as well as the commitment of the Chinese stakeholders to sustaining results beyond the life of the programme. Similarly, ELCE, BE and FS require the development of a sustainability plan by bidders in their SoR. This indicates that this criterion could be scored higher (to 4) after the validation of the results of the self-assessment by programmes.
Overall VfM Assessment
Based on the moderated results of the VfM assessment, the China Phase One portfolio can be broadly rated as “good” in terms of value for money. This assessment is based on a wide range of elements, including the 4Es, as are articulated in summary form in the key elements of the Balanced Scorecard. Each of the four Phase One strands has utilised a wide range of input measures based on Transitional Phase project data; procurement experience and inception (where commenced). The programme will underspend as a whole in Year 1, primarily due to inception delays. Therefore, outcomes will not be achieved by end Year 3 and will probably require (at no/limited cost) an extension to programme timetables. This raises VfM and programme performance flags requiring careful monitoring and corrective action by end 2019 if programme trajectories are not positive (see D3-D5). Further work on putting in place VfM measures and indicators is needed as well as articulation of the ToC, assumptions and causal pathways in more detail for each of the programmes is recommended to strengthen management of the VfM dimensions of the programme.
Quality of Financial Management
A comprehensive Learning and Development (L&D) Plan (3rd May 2019) was proposed for all PF Staff in China, and this includes financial and contract management mandatory training, and tailored needs-based programme and competency-based support. This is supplemented by ad-hoc opportunistic training as required. Each programme team is led by an experienced and suitably qualified staff member who has undertaken basic financial management and Prospero system training, with more scheduled in August 2019. A former senior DFID statistician has been appointed to take over as the Prosperity Fund Counsellor, strengthening overall capability and oversight. Furthermore, the Central Team has a good grasp on the overall programme portfolio activities and budget.
Recommendations continued:
 D3. Additional Support for Commercial Negotiations (at post and in consultation with London) and the provision of additional guidance material is imperative.
D4. Programme Inception and Implementation Tables require rigorous monitoring and the likelihood of timetable or budgetary under- or over-utilisation should be part of systematic internal Standard Operating Protocols.
D5. High-level Management action is required to address the probable likelihood of overall timetable slippage – probably through agreement on programme end date extension (at no or limited cost).
E: RISK (1 page)
Overall risk rating: The overall risk rating for this portfolio should be major. The logframe requires updating to reflect this. The reasons for this assessment are outlined below.

Overview of programme risk
We judge this portfolio to be relatively high risk (both internal and external). The risk register for this portfolio was revised in April 2019. It comprises 13 risks, 8 green, 3 amber, and 1 yellow.

We believe that the current risk matrix significantly underplays the risks to the portfolio and requires revision, both in terms of the type of risk, their impact and mitigation actions, as well as overall assessment. This is not a negative reflection on the portfolio or the design, but will enable strengthened monitoring and support systems to be put in place.

Key operational risks identified focus on approval delays, capacity at post & in London, procurement, and failure of wider support. While we agree that these are some of the key risk areas, the following amendments are proposed:

Risk 2 (failure of wider UK community, including OGD, to engage, understand & support policy objectives of the programme). We do not agree that the risk is failure of understanding; rather that the PF as an instrument of overall HMG prosperity policy is not well embedded with other elements of the policy. We would also note that capability is not the whole picture in terms of operational risk; team structure & size and key skills areas (programme management, financial management, MREL, development expertise including but not limited to G&I should also be considered here.

Key delivery risks are currently focused on the market, suppliers and primary purpose/secondary benefit impact. While market & supplier availability are important, this section requires an overhaul as we move into implementation of multi-year programmes. Key risks for consideration should including delivery of VfM, supplier/contract management, MREL. Delivery of primary and secondary benefit are key risks, as well as coherence between primary purpose and secondary benefits (both should contribute to the overall purpose of the programme).

Reputational risks are significant – this requires internal as well as external management. While we agree that the comms strategy has led to progress, there is more work to be done here, in terms of crafting & embedding a clear narrative for the portfolio. We think that post-mitigation, the risk remains relatively high & this should be primarily addressed through the revised comms strategy that is recommended.

In terms of fiduciary risk, the Programme team has done well to develop its own guidance but this risk should be monitored.

In terms of contextual risk, we agree that GoC policy & buy-in are key risks, but that other contextual risks should be taken into account including, but not limited to, China – UK relations and their trajectory, and China’s ODA eligibility status, and human rights/political risk.

A key risk that will require mitigation is that ODA funding will come to an end by 2025 & all programmes should anticipate this, through having a strong focus on sustainability.

Outstanding actions and recommendations from risk assessment
A review of the draft programme financial guidance for implementers by PFD finance lead is recommended to ensure that they are robust, particularly in terms of their approach to fraud or corruption.

F: COMMERCIAL CONSIDERATIONS (1 page)
Delivery against planned timeframe
Solid momentum has been built-up during the Transitional Phase activities in anticipation of the launch of Inception Phases for the four programmes. However, all have been challenged by the complexity of international competitive tender for multi-year programme delivery, and all four are behind schedule against planned timeframe. Many of these issues were flagged in JFU’s March 2018 monitoring visit.

Performance of Partnership(s)
In general, and with respect to the trajectories developed during Transitional Phases, partnerships have been strong and perform well.

Changes in the Delivery Plan
It is a little too soon to tell for programmes that have yet to fully launch Inception Phases. For Infrastructure, there is already some evidence of “agile and adaptive” delivery planning with respect to the decision to move from a sequential TA then Pilots to a more parallel process with results from the first pilot being used to better guide TA requirements.

Asset monitoring and control
Too soon to tell, but the development of solid guidance and systems, coupled with training should be the focus throughout Year One and into Year Two.

G: Business Environment (½ page)
How has the business community and business environment responded to the programme?
Overall, the UK Business Community has responded well to the Prosperity Fund Phase One initiatives/strands. Relevant UK commercial entities, trade & commerce bodies and academic think-tanks responding to calls for commercial or appointed/nominated tender have been of high quality and appropriate skills, qualifications and with good contacts with counterpart Chinese institutions. Transitional activities have contributed greatly to the strengthening of relationships and the development of understanding on both UK and Chinese counterpart sides, and as Inception Phase activities start to get underway, they are building on generally positive trajectories of development progress. Relationships remain potentially fragile at this stage, with scope for misunderstanding and an over-reliance on key counterparts provided by Chinese interlocutors. Broadening those points of contract will be desirable for risk-management as relationships deepen and programmes move from Inception to Implementation. Whilst science-based and professional skills strengthening engagements are particularly likely to develop understanding faster, there remain underlying barriers to entry in Chinese markets. These include a decrease in optimism, perceptions of unfair competition and increasingly “fierce” competition from indigenous firms, concerns over policy complexity and unpredictability, and concerns over competitive neutrality of government actions.

What role has non-ODA spending played in promoting programme objectives?
In Q4 F/Y 2018/19 there were 11 non-ODA projects designed to support objectives for five PF programmes:
1. Energy and Low Carbon Economy: energy data/market engagement events.
2. Skills (Phase Two) : education technology/primary and secondary school teacher training.
3. Financial Services: insurance asset management/fintech.
4. Future Cities (Phase Three): Smart Cities Expo showcase.
5. Rule of Law for Business: China International and Import Expo side event, trade facilitation policy.

These projects spent £505K of £522K planned expenditure. Underspend was due to a combination of: projects securing some co-funding, scaling down of activities, self-implementation and exchange-rate fluctuation. Secondary benefits have been generated through the project activities through policy research, market engagement, expo, conferences, networking, B2B meetings, UK/site visits etc. Non-ODA funded projects have played an important role to realise secondary benefit for UK companies by identifying and matching the businesses in the areas where China Prosperity Fund have focused on.

Wider qualitative outputs have also been achieved, such as improved relations between UK/China and university partnership agreements; creating an enabling environment for UK and Chinese teacher training departments to gain insights on international market and explore further education cooperation opportunities; UK and Chinese, and academic research and partnership agreements.
H: Monitoring, Results, Evaluation & Learning (MREL)
Monitoring
The shift from transitional funded projects to multi-year programmes has required a step change & significant upskilling and changes in practice from the China Programme team. With support from MR team, the programme team has made good progress in terms of developing a first logframe, theory of change, indicators and milestones. As well as facilitating and accompanying this process, the MR team have trained programme teams in various aspects of monitoring and reporting.

As stated in the output above, Phase One teams have been closely working with MR teams to work out the ToC and logframe as programme monitoring tools. The teams have developed interim logframes, as well as logframes that cover the outputs that each programme intends to deliver. This has been a considerably steep learning curve that the teams have gone through; and they are prepared for further refinement as the programmes move from inception to implementation.

Prospero and PF Learning have been created and introduced as the online monitoring and learning platform.

Reporting

Reporting is commissioned and managed by the Central Programme team on behalf of the China Programme team. Monthly progress reports are issued to PFDU, and quarterly reports to JFU and PFDU. There has been rapid progress and learning on quarterly reporting during the period under review.

Evaluation & learning

The E&L team’s key focus is to work with the China Programme Team to generate understanding of and learning on what works, what does not work and why. The E&L process will also support the China Programme Team in programme adaptation and improvement, as well as contributing to wider learning across the Prosperity Fund, in particular feeding into the ‘family’ evaluations, where learning from projects in similar sectors in different parts of the world can be assessed.
The evaluation process had not fully started at the time of the AR, and the main evaluation mission will be in September 2019.  The work to date has focused on the one-off process of developing the initial Approach Paper. The E&L team also joined the AR visits in order to reduce demands on Chinese stakeholders, who would otherwise be asked to meet two separate missions within a three month period.
The focus of evaluation will evolve over the coming three years, with the first evaluation in September 2019 having a formative focus - assessing the quality of design and ToC at programme and strand level, assumptions, causal pathways, narratives on how change is expected to happen and how leadership and governance arrangements, as well as institutional capacity impact on the programme. It will also define the policy and institutional contexts in which the programme and its strands operate, as well as examining what other interventions are being implemented in these areas. Over the evaluation life cycle, the approach will shift from formative in this initial year to process-oriented and summative evaluations.

At present the E&L team are not contracted to or resourced for provision of technical assistance to the programme team (unlike the MR provider), but this may change in Q2FY19/20 onwards as a result of the current review of the MR and E&L provision by PFDU and JFU.

Overall, the China Programme Team has demonstrated a strong interest in E&L and is keen to promote programme improvement. In the past several years, programme teams have closely monitored the transitional projects’ activities and outputs to ensure quality delivery of the projects and compliance with FCO rules and China Prosperity Fund Guidelines. The results in the previous FCO audits were satisfactory.

Evidence and evaluation
Programmes collectively have commissioned and funded a significant amount of scoping and research.