CHINA PROSPERITY FUND PORTFOLIO – PHASE ONE BUSINESS CASE / (China Business Environment Financial Services; Energy and Low-Carbon Economy; Infrastructure)
Project Purpose: / To reduce poverty, in line with UK commitments to the Sustainable Development Goals, as well as increased bilateral UK trade and investment in China.
Programme Value:[1] £85 million		Country/ Region: China
Project Code:	Start Date:	End Date: 31 March 2022 (previously 2021)
Approval by Prosperity Fund Portfolio Board	Submitted: / 28 March 2017	Approved: / 04 April 2017
Approval by IIOC at SBC	Submitted: / 14 June 2017	Approved: / 21 June 2017
IPA SOC Critical Friends Review	22 June 2017
Approval by IIOC at OBC	Submitted: / 04 April 2018	Approved: / 18 April 2018
Approval by FCO Management Board (write round)	Submitted:	Approved:
Approval by EXCO	Submitted: / 24 April 2018	Approved: / 27 April 2018
Approval by FCO Ministers	Submitted: / 30 April 2018	Approved: / 04 May 2018
Approval by HMT / Approval by CO (+£10m)	Submitted:	Approved: / 20 July 2018
[1] Some of the programmes referred to in these documents have been affected by the ODA reprioritisation exercise in the first half of 2020 due to the reduction in GNI during the early stages of the Covid-19 crisis. As a result, documents which pre-date that reprioritisation may not accurately reflect the programmes in their current form. As announced in the 2020 Spending Review, the UK will temporarily reduce how much we spend on Official Development Assistance (ODA). We will spend 0.5 per cent of our national income (GNI) on ODA, rather than 0.7 per cent. This may further impact spend on programmes.

TABLE OF CONTENTS

LIST OF ABBREVIATIONS

AML	Anti-Money Laundering
CDR	Commercial Dispute Resolution
DFID	Department for International Development
DIT	Department for International Trade
FCO	Foreign and Commonwealth Office
FDI	Foreign Direct Investment
GEA	Gender Equality Act
GHG	Greenhouse Gas
HMG	Her Majesty's Government
HMT	Her Majesty's Treasury
IDA	International Development Act
IMF	International Monetary Fund
IP	Intellectual Property
MNC	Multinational Company
MOFCOM	Ministry of Commerce
MOF	Ministry of Finance
MREL	Monitoring, Reporting, Evaluation and Learning
NDRC	National Development and Reform Commission
NPV	Net Present Value
ODA	Official Development Assistance
OECD	Organisation for Economic Co-operation and Development
PBOC	People's Bank of China
PF	Prosperity Fund
PFDU	Prosperity Fund Development Office
PFMO	Prosperity Fund Management Office
SDG	Sustainable Development Goals
SME	Small and Medium-Sized Enterprises
SoR	Statement of Requirements
SRO	Senior Responsible Officer
ToC	Theory of Change
UN	United Nations
UNDP	United Nations Development Programme
UNFCCC	United Nations Framework Convention on Climate Change
VFM	Value for Money

CHINA PROSPERITY FUND PORTFOLIO (PHASE ONE)
EXECUTIVE SUMMARY
Rationale / China is the world’s second largest economy and largest trading nation. But, despite progress over the past decade, significant challenges remain; for example higher levels of inequality and environmental degradation. The China Prosperity Fund portfolio will contribute to the UK’s commitment to achieving the Sustainable Development Goals, for example, particularly SDGs 5 (Gender inequality), 7 (clean energy), 13 (climate action), 11 (sustainable cities and communities), 9 (infrastructure) 16 (justice and institutions) and 12 (responsible production & consumption). Without the Prosperity Fund (PF) China programme, the UK’s ability to achieve “Global Goods” such as greater global economic and financial stability, and a cleaner environment, are severely diminished. / The China Prosperity Fund Portfolio (Phase One) will provide up to £85m to also address market failures and weaknesses - unlocking increased prosperity for the UK and partner countries, through greater export and investment opportunities, estimated at £240m. / This Portfolio will play a key role in delivering the UK government’s strategy for China. It will employ UK expertise to shape China’s reform. / What will we deliver? / The four programmes that make up Phase One, together with those we will submit separately (Health, Global Partners, Urban Climate Change), are strongly complementary – an improved business environment for UK firms to compete in; financial services reform that align to our strengths in this sector, and also bring about greater financial inclusion; UK/international standards of infrastructure in Asia and Africa; and a low carbon economy that reduces global emissions. They will also support economic development in other developing countries. Bilateral partnerships in these areas have been endorsed at the highest level, including during President Xi’s State Visit to the UK in 2015, and former PM May’s visit to China in 2018. The proposed areas are well aligned with UK commercial strengths, as identified by DIT, and where the FCO China network’s extensive previous programming. These are: / China Business Environment (previously called Rule of Law for Business) (£27.5m) - UK/international businesses face significant challenges in working in China, that diminish confidence to export and invest; China ranks only 84th in the world for ease of doing business, and 80th on a rule of law index. The programme will support progress towards a stronger rule of law including clearer judicial processes, dispute resolution and protection of intellectual property - ultimately leading to an improved, fairer business environment for UK firms to operate in. / Financial Services (£22.5m) - This programme will work in areas where the UK has expertise to promote financial sector reform, employing policy and private sector expertise to better regulate the Chinese financial sector, build a more gender and socially inclusive economy, and enable UK/international businesses to enter the growing Chinese pensions and insurance markets. / Energy & Low Carbon (£20.5m) – China is the world’s largest emitter of greenhouse gasses and largest energy consumer and producer. The programme will match China’s specific reform needs with UK energy and low carbon strengths, reducing global emissions by accelerating China’s energy transition. / Infrastructure (£14.5m) - With an enormous global infrastructure gap, this programme will promote UK/international best practice in design, engineering, financial, professional and legal services; and environmental and social standards raising standards in growth-enhancing infrastructure projects in China and developing countries in Africa and Asia. / Four broad types of activity come under each strand: (i) Policy Reform of market regulations, frameworks and standards; (ii) Market Development via demonstrating new technologies / commercial models and project/investor pipeline development; (iii) Partnership Coordination including commercial ventures; and (iiii) Capacity Building of government and institutions. / Programmes covering Health, Global Partners and Urban Climate Change will complete the China Portfolio. / What are the expected results? / This Portfolio builds on past successes and targets areas where there is political will to maximise impact. But experience tells us that change will not happen overnight. Development (primary) benefits over the next ten years are expected to be worth £843m. They will include: / Improved rule of law and business environment for all firms; / A more efficient and inclusive financial system; / China making the transition to a low carbon economy; / Increased, sustainable investment in China and partner countries in higher quality infrastructure projects. / Commercial benefits to the UK of around £240m are also expected during the same period: / Improved business environment in China for UK/international firms and investors; and / Additional UK-China trade and investment opportunities. / How will the programme be delivered? / It will be delivered primarily through a small number of large multi-million-pound multi-year contracts using suppliers with relevant expertise (single firms or consortia) procured through a competitive tender process. Separate contracts will be required for each programme. The programme will also be aligned with and complementary to the wider Prosperity Fund global programmes, in order to share learning and maximise impact.

STRATEGIC CASE

CONSTRAINTS AND OPPORTUNITIES
China faces a number of broad, existing challenges. These have been highlighted by the World Bank Group (WBG)[1] and other partners as including: the environmental cost of growth and the significant inequality of growth across society. For economic development to continue, there are a further challenges that will also need to be actively managed, including rapid urbanisation and an ageing population.
[1] World Bank (IBRD, IFC, MIGA) (2012), Country Partnership Strategy for the PRC, for the period 2013-2016: http://documents.worldbank.org/curated/en/303351468242963292/pdf/NonAsciiFileName0.pdf

Tackling these will require cross-cutting measures including improving transparency, cutting corruption, addressing other political challenges and improving financial sector stability. These underpin, and are the focus of, the programmes set out later in this document.

THE CASE FOR ODA SPEND IN CHINA

The approach we are taking through this Prosperity Fund programming in China marks a transition to a new development landscape. It is in the UK’s and the rest of the world’s interests that we engage with China to steer its investments, and to embed it in the global development system

Engaging China is a top HMG priority, particularly in relation to the rules-based international order. The UK’s ability to influence China’s engagement within this system will have an important role in defining its future integrity and shape.

China is gaining increasing influence over regional and global economic progress and is forecast to be the world’s largest economy by 2030. China’s progress will impact not only its own development, but development outcomes around the world. China will go ahead with development work and approaches to rules-based governance/standards whether or not we engage it. Engaging China through practical programmes, and matched funding will enable us to steer China to benefit the wider global system.

UK ODA spend in China supports progress towards the UN’s Sustainable Development Goals (SDGs) resulting in global good impact. We only collaborate where the UK has clear policy and commercial expertise and where it doesn’t compromise our values or national security. Our activity, alongside making a tangible difference to China’s contribution to global development, also demonstrates a clear secondary benefit to international business, including UK companies.

This means delivering real prosperity gains for UK/international companies and workers, consistent with our Industrial Strategy, advancing our foreign policy objectives and promoting Global Britain in a large and growing market. Given its size, China’s progress on global challenges is crucial to progress on global goals overall.

PROGRAMME FOCUS
To build a Prosperity Fund portfolio in China that is impactful, our approach is to identify key problems (market failures). In doing so, we seek to steer China towards becoming an environmentally sustainable economy – while at the same time opening up opportunities for UK/international business.

In order to do this in the Chinese context, programme activity must satisfy two conditions:
Primary purpose: Sustainable economic development and poverty reduction in line with SDGs – this first condition is essential, and activity could not progress without it being met. The challenges set out above are a more detailed articulation of this condition;
Secondary benefit: Opportunities for UK/international business.

A careful, methodical and evidence-based approach was taken to developing the China Portfolio, which will ultimately consist of seven separate, mutually-reinforcing, sector-focused programmes.

The China portfolio, if all components are fully approved, will consist of:
- Phase One: China Business Environment, Infrastructure, Energy and Low Carbon Economy, and Financial services;
- Phase Two: Health, and Global Partners;
- Phase Three: Urban Climate Change.

A Theory of Change (ToC) is presented by this business case to map the efforts of each to the overall China portfolio objectives. It should be noted that the ToCs for each programme also interact with and reinforce each other. Once fully operational, the portfolio will seek to maximise positive spill overs.

China Business Environment (previously called Rule of Law for Business)
Primary purpose and gender equality
The China Business Environment programme will provide a fairer business environment for UK/international/domestic businesses in China. To flourish, businesses need a predictable and stable environment that provides the certainty needed for decision making and wealth generation. The World Bank sets out the core elements of a strong environment for business: macroeconomic stability, supporting business infrastructure and effective governance and institutions[2]. Key to this is the “rule of law”[3] [4].
[2] Xu (2010) The Effects of Business Environments on Development http://businessenvironment.org/dyn/be/docs/204/WB_Effects_of_BE_on_development.pdf
[3] ‘The Importance of the Rule of Law in Promoting Development’ Bingham Centre lectures (2014) http://binghamcentre.biicl.org/newsitem/6072
[4] Xu (2010) The Effects of Business Environments on Development http://businessenvironment.org/dyn/be/docs/204/WB_Effects_of_BE_on_development.pdf

China currently faces significant challenges in some legal and regulatory areas of its business environment, which the programme will seek to address. These factors reduce business confidence, particularly for the UK/international business community. Generally, poor rule of law in the business environment is characterised by: inconsistent and ill-informed laws and law-making procedures; opaque, unfair and unpredictable legal/regulatory enforcement that offers few mechanisms for protecting rights; ineffective legal remedies provided through the court system to seek redress; untrained and or ill-equipped legal and judicial institutions; and limited access for companies to qualified legal representation.

The macro-economic impact of improving the China Business Environment is also borne out in individual indicators of economic performance. As summarised in a recent DFID business case[5], income inequality across countries is closely associated with investors’ perceptions of the likelihood of expropriation of property; differences in legal environments are correlated with performance variations across countries in several areas, including financial systems, entrepreneurship dynamics, firms’ growth prospects and investment decision-making; and FDI tends to be greater where the cost of contract enforcement is lower, particularly if host economies are more indebted.
[5] https://devtracker.dfid.gov.uk/projects/GB-1-202647/documents

The macro-economic effect of improving the China Business Environment is the result of the impact that improved rule of law has on individual businesses, making them more productive and efficient, and incentivising their economic activity. A vibrant private sector is an important engine of growth in modern economies[6]. In a more predictable operating environment, UK/international businesses are more confident when making decisions, including decisions to invest and innovate. A 2015 survey of senior decision makers in the world’s leading companies[7] showed that strong rule of law in a host country is one of the most important factors to FDI decision-making. Specific factors that affect decisions to invest include: lack of transparency in regulatory / legal rule-making processes; lack of effective courts; risk of expropriation of investment; unexpected changes to regulatory and legal measures; and lack of recognition of intellectual property rights.
[6] See the World Bank Investment Climate brief for further details: http://www.worldbank.org/en/topic/competitiveness/brief/investment-climate
[7] ‘Risk and Return – Foreign Direct Investment and the Rule of Law’ A survey conducted by the Economist Intelligence Unit on behalf of Hogan Lovells, the Bingham Centre for the Rule of Law and the Investment Treaty Forum

Due to several factors, including its disproportionate impact on SMEs, improving the China Business Environment will be particularly beneficial to the poorest and most fragile members of society. Less well-educated members of the Chinese workforce are disproportionately likely to be employed in the SMEs sector (c. 50% of the SMEs workforce, in 2008, had junior high school education or lower[8]). Poor people are also at a particular disadvantage from a weak legal system and weak business environment as they are more vulnerable to corrupt and unfair practices and may be less well-informed of their rights. They come into conflict with government more often than other groups – for example through disputes around land rights and relocation, or ability to operate a small business. As such, they need a strong, impartial judicial system to protect their rights[9]. There is strong evidence that legal empowerment programmes work to alleviate poverty[10].
[8] p117, “Inclusive Growth And Development In The 21st Century: A Structural And Institutional Analysis Of China And India” (Volume 9 of Series On Economic Development And Growth), Ed. Dutta Dilip, World Scientific, 2014
[9] https://reinventingtherules.com/2013/10/25/the-impact-of-rule-of-law-on-poverty-and-development/
[10] https://reinventingtherules.com/2013/10/25/the-impact-of-rule-of-law-on-poverty-and-development/

To ensure that the China Business Environment programme contributes positively to female economic empowerment, project data will be disaggregated by sex wherever possible. Moreover, before contracting services, suppliers will be required to make an evidence-based assessment of the differentiated impacts of UK-funded interventions on gender equality and will also be required to report on differentiated impacts to as part of ongoing reporting. Finally, no work will be taken forward should initial or ongoing assessments indicate that there will be a subsequent negative impact on gender equality.

Examples of key market failures/constraints and areas for reform

If China is to transition successfully to a more open, inclusive and sustainable economy, this will need to be underpinned by an improved business environment. For this to happen, businesses, particularly UK/international businesses must be confident that their and others’ operations are subject to laws that are uniformly and fairly enforced, which protect their legitimate interests.

In addition to directly promoting growth, improvements to the China Business Environment will also indirectly affect consumer pricing and other areas currently adversely affected by issues in the regulatory environment. A recent analysis of the impact of various barriers to European firms’ performance in China concluded that regulatory barriers were second only to market access as a cost.

The China Business Environment programme could also have significant positive implications for developing nations beyond China. It has been noted that many of the same difficulties currently encountered by businesses in China have also reared their heads as Chinese companies increasingly “go out” to do business in third markets and affecting less developed economies. By addressing these issues in China, difficulties for UK/international businesses may be prevented elsewhere.

The China Business Environment programme in China will seek to address those legal and regulatory issues that are simultaneously impeding China’s domestic growth, and its engagement with the global market. By working alongside the Chinese government and business to address these issues, the programme will efficiently deliver on the Prosperity Fund’s two objectives, in a way that is impactful and additional. Some examples of these cross-cutting issues are:

Unclear rules – Laws and regulations underpinning certain kinds of business activity are unclear, outdated or contradictory. Complying with these rules is therefore costly, difficult and risky for businesses. China is seeking to address some of these areas (for example by revising certain crucial laws: Copyright Law, Foreign Investment Laws, Commercial Banking Law, etc.) but will require help from the international community to do so effectively.

Inconsistent/inexpert administration – Administrators of China’s business environment often apply the rules inconsistently, even when the rules are clear. Different provincial authorities interpret laws differently; guidance for interpretation is often patchy; administrators are inexpert in certain technical and legal areas. This compounds the risks and problems associated with the unclear rules on which the system is founded.

Inconsistent/inexpert enforcement – Courts, regulators and intermediaries are ill-equipped to monitor and enforce certain types of legal infringement in the business environment. IP infringements are a common problem and are difficult to address; commercial disputes are often poorly overseen; illicit capital flows are significant. This constrains real investment, dampens business confidence, and hampers innovation by domestic companies.

Addressing these areas will promote greater predictability in the market, increasing confidence amongst firms, who will then be more likely to enter the market or expand – creating employment and growth.

What opportunities are there for UK business?

The UK is in a strong position to promote the China Business Environment internationally, at the national and institutional level. The UK has one of the highest levels of rule of law worldwide, according to analysis by the World Bank[11], and the UK’s judiciary, legal and legal academic sectors are all very strong. The UK is recognised as the home of the ‘original’ common law system, and English common law is also often chosen by non-UK businesses for international trade and investment because it is user-friendly and offers remedy in UK commercial courts which have a reputation for fairness, efficiency and cost-effectiveness. In about 40 per cent of all global corporate arbitrations, English common law governs[12]. China is therefore keen to work with the UK on improved legal education and law-making processes.
[11] The UK was ranked 13th out of 215 economies surveyed on its strength of rule of law in 2015 (source: http://info.worldbank.org/governance/wgi/index.aspx#home) . China was ranked 71 out of 102 countries on the World Justice Project rule of law index (2015). http://worldjusticeproject.org/rule-law-around-world - [1 - strongest rating; 102 – weakest rating]
[12] Global Survey Reveals Corporate Choices in International Arbitration (2010). Available at: http://www.qmul.ac.uk/media/news/items/hss/38048.html

The UK also stands to benefit from business environment improvements where they occur in areas of UK comparative strength. Stronger rule of law in China would lead to an improved environment for all firms, British, foreign and domestic. There are areas in which UK business would particularly benefit, given the make-up of British business in China, the sectors in which they operate and the kinds of legal issues they most commonly experience.

Improvements made to the China Business Environment will also likely benefit the UK due to the impact that these improvements will have on SMEs. Surveys suggest that UK SMEs are reluctant to launch into new markets with poor legal environments. According to a survey of 1,100 UK SMEs by KPMG and YouGov, more than one third (36 per cent) said that they have no interest in exploring overseas markets, citing complex legal regimes as the main barrier[13]. Regulatory requirements, different standards, and difficulty accessing trade finance have also been cited as among the top ten barriers to exporting in the Asia-Pacific region[14]. The potential gain here is significant. SMEs generate more than half of the UK’s GDP, yet are underrepresented in exports. The UK ranks in the bottom five European economies for the share of SMEs among exporters and only 18 per cent of UK SMEs currently export to China[15]. Given that SMEs account for around 60 per cent of all private sector employment in the UK and just under half of the overall turnover in the UK’s private sector, there is considerable scope to boost the number of SMEs selling goods and services in China and, as a result, raise the overall level of exports across the UK economy[16].
[13] KPMG (2015) Export Week News: 36% of UK small businesses shun overseas expansion. Available at: https://www.kpmgenterprise.co.uk/our-resources/news/export-week-36-of-uk-small-businesses-shun-overseas-expansion
[14] World First (2016)
[15] World First (2016) Thinking Global: The route to UK exporting success. Available at: https://www.worldfirst.com/downloads/Think_Global_WorldFirst.pdf
[16] Ibid.

1. The China Business Environment programme will focus on addressing the cross-cutting issues listed above – regarding unclear rules and inexpert administration/enforcement – in five specific areas: Intellectual Property; Investment Environment; Anti-Money Laundering; Standards; and Commercial Dispute Resolution. These thematic “strands” have been chosen based not only on their importance for UK businesses, but on the fact that they meet other criteria for good programme design too. The criteria are:
  1. The degree to which the UK has expertise to contribute to improvements
  2. The political risk associated with engaging with the strand
  3. The degree to which the Chinese have agreed to work with the UK on the strand
  4. The degree to which success is likely regarding the strand
  5. The additionality of programme work on this strand
  6. The coherence of the programme.
  7. The evidence that rule of law issues, in this strand, are damaging to UK businesses
  8. The evidence that rule of law issues, in this strand, threaten stable Chinese economic development

These have been tested extensively through a detailed scoping study commissioned by the British Embassy in partnership with a wider range of legal and commercial experts.

“Rule of Law”-based thematic strands which were deemed to be “out of scope”, as having significantly failed against one or several of the above criteria, include: government procurement (no Chinese buy-in to work with the UK; little sense that reform would be of particular benefit to either poverty alleviation or UK business; anti-corruption (no Chinese buy-in; huge political risk for UK involvement, due to the particular nature of the current Chinese anti-corruption campaign); anti-monopoly (no Chinese buy-in; very limited prospect of success due to heavily state-influenced nature of Chinese economy); tax (no clear sense of likely UK company benefit from improvements to tax regime); insolvency (short term risks to Chinese poverty alleviation goals; lack of additionality due to multiple international efforts to improve the way Chinese companies, especially SOEs, are allowed to go insolvent; not aligned with other strands of programme activity).

The five strands that met all criteria, are listed below, along with the benefits success may bring to UK business:

Intellectual Property – British businesses currently lose hundreds of millions of pounds a year due to infringement of IP rights. The lack of regulatory certainty in the IP regime, and lack of enforcement, cause fundamental problems which are exacerbated by the fact that Chinese firms engaging in IP infringement often have global exporting capacity, with wide-ranging impacts for UK exports[17]. Improving the IP regime is also a crucial part of China’s strategy for transitioning to a more sustainable, higher-end manufacturing economy, ending domestic poverty in the process. The UK has a long history of engagement with China on IP issues, and other countries are significantly less engaged, meaning that work in this area is hugely valuable.
[17] https://www.gov.uk/government/publications/overseas-business-risk-china/overseas-business-risk-china

Investment Environment - Many UK businesses have emphasised particular problems that dissuade them from expanding their in-country operations, collaborating with Chinese business or even entering the market; and a study of bilateral investment flows commissioned by the British Embassy in 2017-18 showed that UK investment into China is slowing. This has obvious implications for the revenue generation opportunities for UK companies in China. China has expressed willingness to work with the UK on this issue, and workshops laying the groundwork for future engagement have already been held.

Commercial Dispute Resolution (CDR) – China’s approach to dispute resolution is inconsistent, and the quality of dispute oversight within China is variable. Problems range from a lack of expert judges/arbitrators, overseeing complex disputes, to a lack of clarity over procedures such as those regarding evidence. Greater stability in the CDR landscape would lead to increased UK business confidence in the commercial environment generally. It would also, of course, provide clarity for Chinese businesses, particularly small businesses, and this is an area in which China is keen to learn from the UK’s extensive and world-leading experience.

Standards – The use of China-specific, or even province-specific, standards in China are a barrier to trade both in and out of China, as it means that mutual recognition of goods/services quality is hard to come by. Where UK suppliers need to meet the equivalent Chinese standard for a product or service, this imposes an extra burden on UK suppliers potentially dissuading them from attempting to enter the Chinese market. Even where Chinese companies do use international standards, conformity assessment is of variable quality, and international confidence in Chinese standards adherence is low. Supporting Chinese standards bodies to align their standards content and processes more with international best practice will facilitate trade into and out of China, as well as making it easier for businesses to comply with Chinese regulations. UK businesses use international standards widely and would stand to gain significantly from an improved standards environment in China. The British Standards Institute (BSI) estimates that the use of internationally acceptable standards contribute around £6.1bn in additional exports to Britain each year[18].
[18] BSIGroup.com (2015) The Economic Contribution of Standards to the UK Economy. Available at: https://www.bsigroup.com/LocalFiles/en-GB/standards/BSI-standards-research-report-The-Economic-Contribution-of-Standards-to-the-UK-Economy-UK-EN.pdf

Anti-Money Laundering (AML) – China recognises strengthening its anti-money laundering infrastructure and ecosystem is a priority. This is a deterrent to foreign investment and is a factor that leads to a legal outflow of domestic capital to more stable investment opportunities overseas – undermining socio-economic growth and social stability. It also feeds other corrupt practices in China, which are hurting domestic businesses. The World Economic Forum estimates that corruption on average increases the costs of doing business by up to 10% and adds up to 25% to procurement costs in developing countries. China has wider issues with corporate governance, too, which work on AML could help to solve. Since 2005, and following the London Stock Exchange’s (LSE) efforts to promote London as a market for Chinese Small and Medium Enterprises (SMEs)[19], more than 80 Chinese firms have listed on the Alternative Investment Market (AIM, a sub-market of the LSE), with each of these using UK financial, legal and professional services. However, only half remained by 2015, with poor corporate governance and failure to meet the standards required to trade in London resulting in their delisting[20]. This is of real concern given HMG aspirations to continue to grow the London stock market including new work to connect the London and Shanghai stock exchanges. This area also, however, provides a significant opportunity, particularly regarding AML, given that China is due to implement the Common Reporting Standards for financial activity in 2018.
[19] FT.com (2015) Aim’s Chinese disasters offer cautionary tale for chancellor Available at: https://www.ft.com/content/a4b710f2-61f8-11e5-9846-de406ccb37f2
[20] FT.com (2015) London Stock Exchange clamps down on Aim-quoted Chinese companies Available at: https://www.ft.com/content/0eee474a-6e8f-11e5-aca9-d87542bf8673

Indirectly, several of these strands would also contribute to reducing corruption in China, to the benefit of UK businesses. UK businesses are also particularly sensitive to corruption related risk: 43 per cent of UK businesses surveyed decided not to conduct business in a country because of corruption, compared to 38 per cent for France and 29 per cent for the US[21]. Our scoping study pointed consistently to businesses’ concerns that “normal practices in China” laid them open to charges under the UK Bribery Act.

What commitment to partnership is there to build on for this programme?

The Chinese government has made a strong commitment to reforms to improve business predictability. Rule of law and anti-corruption were the key topics of the 4th (2014) and 6th Plenums (2016) respectively. These also featured heavily in the 13th Five Year Plan.

There is also evidence of Chinese political will and appetite to work with the UK. During President Xi’s State Visit to the UK in 2015, the UK and China signed a joint statement which included commitments to enhance and continue co-operation on rule of law. Since then the UK has further strengthened relations with key securing senior level support from the party, government and judiciary. Enhanced dialogue and exchanges have included reciprocal visits of the Presidents of our respective Supreme Courts and the establishment of a formal relationship between the Great Britain China Centre and the China Law Society. In 2017, the Lord Chief Justice of England and Wales was hosted in China. Following this, Vice President of China’s Supreme People’s Court took part in the 4th UK-China Judicial Roundtable and attended the first Standing International Forum for Commercial Courts, an initiative led by the UK Commercial Court. Talks have also begun with the National Development and Reform Commission (NDRC) and the Ministry of Commerce (MOFCOM) to embed our rule of law work more formally within the UK-China Economic and Financial Dialogue and Joint Economic and Trade Committee. At the individual strand level, work has been done to secure significant buy-in from key political players:

- IP – longstanding project work with the State Intellectual Property Office, and an annual judicial exchange on IP issues, have paved the way for multi-year programme work.
- Investment Environment – building on work done by DIT and FCO stakeholders, the programme team has engaged with China’s MOFCOM, NDRC and relevant legislators to secure buy-in for the multi-year programme.
- Commercial Dispute Resolution – the programme has secured buy-in from the Supreme People’s Court, the Shanghai Higher People’s Court, arbitration institutes such as CIETAC and the China Law Society to work on Commercial Dispute Resolution issues under the multi-year programme.
- Standards – The UK, via the British Standards Institute, is the key international partner to the Standards Administration of China (SAC), China’s main standards body. Other relevant ministries, such as the Ministry of Industry and Information Technology, and the Ministry of Science and Technology, have also either worked with, or expressed a clear interest in working with, the UK government on standards.
- Anti-Money Laundering – The UK has worked with the People’s Bank of China (PBOC) (China’s key anti-money laundering regulator) on improving the AML regime in China for several years. This has primarily been focussed on preparing China for the Financial Action Task Force’s Mutual Evaluation. The PBOC has expressed a keen interest in continuing to work with the UK on AML issues.

What results should the programme focus on and how might these be achieved?

Based on the reasoning given above, the programme will seek to deliver outcomes in five thematic areas:
- Intellectual property (IP)
- Investment environment
- Commercial dispute resolution (CDR)
- Standards
- Anti-Money Laundering (AML)

Desired outcomes in each of these strands are as follows:

Policy area	Outcome	Intermediate outcomes
IP	Improved IP outcomes for Chinese and UK companies	IO1 Improved legislative framework for IP
		IO2 Improved implementation of China’s IP legal framework by government and non-government bodies

		IO3 More efficient IP administration
CDR	Improve predictability, accuracy and enforceability of CDR results	IO1 Improve quality of Chinese CDR outcomes
		IO2 Improve enforceability of Chinese CDR outcomes/international CDR in China
Anti-Money Laundering	Less money laundered in China, reduced illicit capital flows	IO1 Enhanced capacity in Anti-Money Laundering and Counter the Financing of Terrorism in PBoC, other competent authorities, financial institutions and DNFBPs
		IO2 Better AML legislative framework and judicial enforcement.
Standards	Standards of Chinese products/projects raised	IO1 Improved quality of Chinese standards development, to be more closely aligned with international standards and best practices.

		IO2 Chinese companies use SAC-adopted internationally recognised standards
Investment Environment	Make investing into China less risky and easier for foreign companies.	IO1 Develop a clear legislative and regulatory framework for Foreign Investment into China
		IO2 More effective approvals process for foreign investment

Intermediate outcomes in all strands will rely on outputs of three kinds:
- More UK-China collaboration: ensuring the long-term sustainability of impacts by institutionalising UK-China legal and judicial relationships, enshrining the UK as China’s partner of choice for this work.
- Improvements to processes: providing assistance to Chinese regulators, courts and administrators to streamline processes and coordinate institutional structures.
- More expert personnel: providing training and expert exchanges to improve the capability of crucial operators within the Chinese system, either in the drafting of legislation, legal enforcement, or legal administration.

The supplier will design specific activities during the programme’s design/inception phase, to deliver the outputs specified. Specific activities may include:

Activity type	Programme activities
Build new (and expand scope of existing) high-level exchange e.g. UK-China judicial expert working groups	Support and expand Expert Working Groups between UK and Chinese judiciary to build consensus and influence politics and practice in key areas like IP, commercial dispute resolution etc.
Expertise sharing through establishing UK-China Centres of Excellence, workshops, joint initiatives and secondments.	Formalise exchanges between UK and Chinese legal communities, supporting secondments to key institutions
Generation of highly relevant and high-quality research, analysis, case studies, policy & draft law recommendations	Bring together group of UK and Chinese investment law experts to put forward recommendations for draft foreign investment legislation / Work with Supreme People’s Court to develop relevant Guiding Cases / Produce detailed reports to evidence economic case for reforms
Training and capacity building programmes with judiciary, law enforcement, regulators, practitioners and lead law-drafting bodies	Programme building Chinese judiciary understanding of IP law and its application / Training Chinese legislators regarding best practice in drafting laws/regulations, and guidance relating to substantive laws / Work with standards bodies to build provincial level capacity to investigate and enforce standards compliance
Outreach activities to engage international, including UK businesses, with opportunities in China	Support roundtables with leading Chinese e-commerce platforms to support development of/compliance with e-commerce and IP law / Engage with foreign and Chinese businesses to involve them in standards development and to advise on AML compliance
Support and advise HMG policy teams; engagement with DIT and private sector to ensure benefits of programme fully realised	Work with policy and commercial teams across the China Network on preparation for high-level Ministerial dialogues with China to effect policy changes and the removal of market access barriers needed for primary and secondary benefit. / Follow-up with DIT and private sector partners to advise on opportunities for export wins and investment projects.

FINANCIAL SERVICES
Primary purpose and gender equality

Ensuring the stability of China’s financial system is a global public good. The country’s giant banking system has tripled in size since 2008 and now has assets worth an estimated 40 per cent of global GDP[22]. China has the world’s second and third largest equity and bond markets, albeit in comparative terms are still dwarfed by the banking sector[23]. The rapid expansion in credit post the global financial crisis has seen China’s debt to GDP expand from 160 per cent in 2008 to 260 per cent in 2016[24]; threatening the stability and global system. Instability or a crisis would exacerbate poverty and undermine progress towards development goals.
[22] Rabinovitch, S. (2016) Big but brittle - Special Report on China’s Financial System. The Economist Available at: http://www.economist.com/news/special-report/21697983-china-needs-free-up-its-financial-system-even-if-it-hurts-says-simon-rabinovitch-big
[23] Rajadhyaksha, A (2016) China enters zugzwang Barclays Cross Asset Research. Available at: http://www.thebondbeat.com/bondbeat/wp-content/uploads/2016/02/barcap-TM1.pdf
[24] Keyu Jin, Lecture on China’s Financial System at the London School of Economics 8th April 2016

The development of the financial services sector, thereby, impacts poverty reduction through two channels: indirectly through growth and system stability; and directly through providing access to credit and other financial services. Well-functioning financial markets improve access to finance for productive investment that supports inclusive economic growth, gender equality and women’s economic empowerment, climate resilience and poverty reduction. Cheaper and more accessible finance can spur the development of crucial infrastructure that can boost sustainable and inclusive economic activity and improve women’s and men’s lives. More effective and efficiently functioning markets for insurance, pensions and FinTech products will also support financial inclusion, for SMEs, the informal sector, poorer women and men and excluded groups, including the unbanked.

Financial services though banking, savings, pensions and insurance, debt help private citizens save money, guard against uncertainty. Such direct mechanisms to poverty reduction require careful management by regulatory bodies, national and local governments to ensure financial services providers act in the interest of female as well as male consumers and provide them with the chance for individual betterment.

Through the indirect channel, there is strong empirical evidence[25] of financial markets’ role in allocating capital to fund productive investments that manage risk. The IMF argues that reforms to depth, access and efficiency of financial markets help stability[26]. Imperfections in financial markets can affect their efficiency, effectiveness and equitable access – so carefully designed markets, regulations and supervision are required. The globalised nature of financial markets means they can affect domestic macroeconomic conditions and have spill-over effects in other economies. Inclusive, transparent and resilient systems, and global coordination, are crucial for financial markets to deliver inclusive growth benefits without excessive risk[27]. Thus, the regulatory environment has a role to play in poverty alleviation and improving the way it functions can help deliver economic value throughout society.
[25] Studies, for example, by R. Levine “Financial Innovation and Endogenous Growth 2010, M. Gertler “Financial Structure and Aggregate Economic Activity: An Overview” 1998, J. Gurley & E. Shaw “Financial Aspects of Economic Development” 1955,
[26] IMF “Rethinking Financial Deepening: Stability and Growth in Emerging Markets” , May 2015. Available at https://www.imf.org/external/pubs/ft/sdn/2015/sdn1508.pdf
[27] IMF “Rethinking Financial Deepening: Stability and Growth in Emerging Markets” , May 2015. Available at https://www.imf.org/external/pubs/ft/sdn/2015/sdn1508.pdf

In the past, the poor in developing countries – including the elderly, and small and micro enterprises – faced major challenges in accessing existing financial systems – for instance the absence of credit history, property ownership etc. In China, now just over 2 in 10 adults do not have a bank account. This represents a 15 per cent improvement since 2011[28]. In recent years, two major developments have made a difference to poorer populations otherwise locked out of banking.
[28] Duflos, E., and Klapper, L. (2015) New Accounts in China Drive Global Financial Inclusion Figures Available at: https://www.cgap.org/blog/new-accounts-china-drive-global-financial-inclusion-figures

The World Economic Forum has assessed that 76.4% of women in China hold an account at a financial institution; compared with 81.4% of men. Recent estimates from the same study suggest that China could close the gender gap in economic participation by 25%, by 2025[29].
[29] The World Economic Forum ‘Global Gender Gap Report 2017’. Available at: http://www3.weforum.org/docs/WEF_GGGR_2017.pdf

First, microfinance institutions[30]. Evidence from the past twenty years has shown that micro finance institutions have better repayment rates than their commercial counterparts[31]. In China, microfinance was introduced in pilot form from 1994 onwards. Now there are over a thousand microfinance or village banks. Up to 2014, they have disbursed over US $78 billion to households and enterprises[32], helping to smooth incomes, though there is still work to be done and access to credit is hardest for the poorest sections of society
[30] N Bateman “Microfinance as a development and poverty reduction policy” ODI 2011
[31] C. Sutton & B. Jenkins “The role of Financial Services Sector in Expanding Economic Opportunity” Harvard University 2011
[32] http://www.cn.undp.org/content/china/en/home/library/poverty/sustainable-financing-for-poverty-alleviation-in-china.html

Second, mobile banking. In China, 19 per cent of adults with an account make payments from their account using their mobile phones. China is ahead of certain high-income OECD economies on this score, including Germany, where just 15 per cent of adult account holders make bank transactions on their mobiles. Expanding these types of models has the potential to address financial access inequality across China. Of the 234 million remaining unbanked Chinese adults: 55 per cent are women; 71 per cent live in rural areas; 54 per cent live in the poorest 40 per cent of households; about 80 per cent have only an elementary school education or less[33]. There is a body of evidence that suggests that expanding financial access requires diversified products beyond micro-credit, such as remittances, micro-insurance, savings accounts and other financial instruments.[34] In turn, evidence also suggests that to deliver such products at scale, especially to poor people, regulated and self-sufficient financial institutions are needed, which in turn require commercial sources of finance to grow[35].
[33] Duflos, E., and Klapper, L. (2015).
[34] Collins D, Murdoch J, Rutherford S, & Ruthven O (2009) “Portfolios of the Poor: How the World’s Poor Live on $2 a Day” Princeton University Press
[35] Robinson M (2001), “The Microfinance Revolution: Sustainable Finance for the Poor, Lessons from Indonesia

Further improvements to the financial system can help accelerate poverty reduction efforts. Fintech can transform people’s access to financial services, as shown with the success of WeChat, however Chinese authorities have struggled with regulating the sector, often squabbling over which body should regulate which aspect of the industry, resulting in gaps in regulation and inefficient rules which have stifled innovation. Regulating in a more open way can help foster growth and poverty reduction through product and service innovation in the financial sector.

In addition, financial sectors which promote good financial behaviour such as buying insurance and saving in a pension have struggled to get off the ground in China. Health care and access to/take up of health insurance illustrates this point. Supporting strong health systems improve the health status of the whole population, but especially of the poor among whom ill health and poor access to health care tends to be concentrated, as well as protect households from the potentially catastrophic effects of out-of-pocket health care costs. Of the estimated 55.75 million people living in poverty in China in 2015, 44 per cent were impoverished because of expenses related to health[36].
[36] 2020 health plan to ease burden on people in poverty: http://www.chinadaily.com.cn/china/2016-06/22/content_25797364.htm

Regulators struggle to appropriately govern and incentivise such markets, which enjoy nearly total penetration in developed economies such as the UK. The regulator has a key role to play in ensuring China’s ageing population does not cause it to fall into the middle-income trap, which would have a drastic negative impact on poverty reduction. It must move to build a regulatory environment for financial services that encourages useful product growth on both supply and demand sides.

What opportunities are there for UK business?

Sustaining economic growth and poverty reduction requires a shift from a reliance on quasi-state banking to a more market oriented financial system. Such markets presuppose the development of an elaborate apparatus of underwriters, rating agencies, custodians, actuaries, clearing and settlement platforms – key areas of UK comparative advantage.

The UK is a global leader in cross-border bank lending, foreign exchange operations, interest rates OTC derivatives, insurance, financial services technology (Fintech), investment management, and green bonds. A good business environment, skilled workers, competitive tax regime, advantageous time-zone, English as the world’s key business language, strong legal/regulatory environment and support for innovation mean international firms benefit from a presence in the UK. Financial services attract more FDI into the UK than any other sector. Foreign firms invested around £100 billion in the UK financial sector between 2007 and 2015[37]. The sector generated a net trade surplus in 2015 of £72 billion, more than all other industries combined[38].
[37] The City UK (2016) Key Facts about UK Financial and Related Professional Services Available at: https://www.thecityuk.com/research/key-facts-about-uk-financial-and-related-professional-services-2016
[38] Op. cit.

Further opportunities in China would help to grow the sector further. Particular opportunities are presented by currency trading, with London now the largest offshore centre for clearing Renminbi outside of greater China[39], in 2015 $1.8bn worth of RMB was settled in London[40]. By 2020, UK financial services to China could represent a £6~9bn annual market, up from £350million in 2012[41].
[39] FT “UK becomes the second largest offshore RMB hub” April 26th 2016
[40] Bank of England 2015 foreign currency settlement report
[41] FCO Economics Unit “UK exports to China now and in the future” January 2013. Available online here: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/211157/UK_Exports_to_China_-_Now_and_in_the_future.pdf

A handful of UK financial sector firms have broached the Chinese market with success, notably HSBC and Standard Chartered in the banking sector. Other sectors including pensions, insurance, asset management and venture capital and private equity investment have seen collaborations and joint ventures between British and Chinese companies, though these have been hamstrung by licensing issues, with Chinese authorities loath to grant licences to foreign firms with much greater experience and a more diverse product offering than nascent Chinese competition. However, this protectionist stance is changing and in late 2017 China announced the opening of certain financial subsectors to foreign ownership over the next few years. International firms should be planning now to bring their products to market as China opens up previously protected financial sectors and seeks the dual benefits of international participation: improved resilience through capital diversification and foreign expertise and insight.

This increasing role of foreign players in the Chinese financial sector presents distinct opportunities for UK businesses in a number of subsectors where the UK has a competitive advantage. Chief among those are Fintech, insurance and pensions. Venture capital investment in the UK’s Fintech industry surpassed that of China last year, second only to the USA, indicating the strength of innovation the UK Fintech sector. UK Fintech firms are world leaders in areas such as cross-border payments, regtech and digital lending. Insurance penetration is on course to more than double over the next five years in China, set to make it the world’s largest insurance market, yet UK insurance firms hold a paltry 0.3 per cent share of that market, versus a 6.4 per cent share for UK insurers globally and a 21 per cent share in Europe. A commercial pension industry is a major aim of the Chinese government, and they frequent look to UK expertise for advice in this sector.

Examples of key market failures/constraints and areas for reform

There are six fundamental market failures constraining the further development of China’s financial services sector and its ability to support inclusive growth and poverty reduction. Through the two channels described above (i.e., indirectly through growth and system stability; and directly through providing access to credit and other financial services). These are outlined in the table below:

Market constraint	Constraint description	Secondary benefit opportunities	Scope for external/international involvement
Indirect constraints on poverty reduction: financial stability and efficiency
Over-reliance on debt	China’s financial markets are skewed to its large banking sector which provides 70 per cent of total credit in the economy[42], having a disproportionate effect on poorer communities and women. The Chinese government is committed to building a multi-level capital market to address this over-reliance on debt markets and instead support development of other efficient markets including equity and venture capital. Reform in this area would help to increase the range of financial products serving smaller borrowers – including SMEs – allowing them to invest, expand and create jobs, including in less wealthy provinces across China	This is a structural debt problem and so there are no opportunities for any international firms in this area.	China’s over-reliance on debt is a top-level national priority given the threat it poses to global financial stability. Managing the national debt is a highly politicised issue in any country and whilst international agencies such as the IMF periodically offer analysis and advice on such situations, foreign governments do not.
Limited financial products available in secondary markets	Comparatively underdeveloped futures and bond derivative markets hinder the development of a more complex and efficient market mechanism in China. Reform in this area would impact on China’s poor by, for example, helping them hedge against market-related risks, including natural disaster risks (droughts, floods etc).	The UK’s advanced market for origination of derivatives contracts and complex products, plus active secondary markets, means there are potential gains for UK firms in this sector, and the USA would also similarly see a benefit. The UK being an offshore RMB hub should help it edge ahead in this respect. Specialised firms such as the London Stock Exchange Group may also find opportunities.	The sophisticated financial markets in the UK and USA which have developed in recent decades mean we have unparalleled expertise in the regulation and innovation required in this space. This is a frequent request from bilateral UK-China dialogues for further co-operation and knowledge sharing. Excessive regulatory controls are one of the main impediments for innovation and the market’s further development.
Lack of foreign participation	Barriers to foreign participation in China’s financial markets remain extremely high. Greater foreign participation would diversify the capital base, thereby reducing liquidity risk, bringing down borrowing costs and improving efficient of capital allocation so as to support those in poor regions and enable greater inclusive growth.	The only foreign financial sector firms in the Chinese market at present are mostly joint ventures. There is room to grow in this space as foreign ownership rules are gradually relaxed in China, though the biggest untapped and undeveloped markets are in pensions and insurance sectors.	China recognises the benefit of a diversified capital base and is therefore attempting to open its financial markets through legal and regulatory reform and a programme of RMB internationalisation. As a global financial sector leader, the UK has an important role to play in ensuring the Chinese financial environment opens in a constructive way that has a positive impact on financial stability and for the benefit of UK firms in these sectors.
Market constraint	Constraint description	Secondary benefit opportunities	Scope for external/international involvement
Both indirect and direct constraints on poverty reduction
Regulatory coordination	Regulation of China’s financial system is split over four different regulators (The People’s Bank of China, and the Securities, Insurance and Banking Regulators) with government oversight equally convoluted but dictated primarily by the ministerial level Financial Stability and Development Committee. Overlapping and cross-cutting responsibilities makes it difficult to regulate risks in a holistic and coherent manner. As Chinese firms also diversify their range of business lines, there is pressing need for greater regulatory coordination. Reform in this area would not only contribute to better risk management, but also has the potential to increase the protection offered to consumers/financial service users against losses, especially for the poor and women.	Transforming the Chinese approach to regulation, particularly for foreign market participants, has the potential to open the floodgates in terms of opportunities for UK/international companies Helping open and shaping the market regulation in a way that resembles what international firms are used to in terms of standards, compliance, reporting and more can be a game changer for foreign firms trying to enter the Chinese market.	China is eager to learn from Western countries, notably the UK and USA, on how best to reform its regulatory environment. It knows that regulation is the key to both financial stability but also to economic growth and efficiency. It recognises the role regulatory authorities must play in ensuring the economic boom is not disproportionately benefitting a select few and it welcomes outside guidance in how to approach changes to regulatory capacity and development.
Non-traditional finance	The failure of the traditional banking system to provide financial services to the non-state-owned sector has catalysed rapid growth in non-traditional finance including Fintech and wider shadow finance. Whilst the non-traditional sector is an important source of finance, the growth of both sectors in China is unsustainable and opaque. A number of platforms have failed due to fraud and poorly managed risks with significant impacts for consumers, but also contagion risks for the wider financial system. These unregulated companies are relied upon proportionately more by poorer people who are more vulnerable to financial shocks and mismanagement.	Payments technology and credit scoring analytics are just two areas that could help restrict the excessive reliance on the shadow banking sector in China. International expertise in this area can help China manage the transition away from non-traditional finance and in doing so present market entry opportunities for UK/international companies and financial providers.	Authorities often seek advice as to how the regulatory and oversight regime in the UK is able to so effectively reach and permeate throughout the financial system, thereby improving financial stability and consumer confidence, particularly amongst poorer communities. Knowledge sharing and research in this area is a common goal for both sides.
Market fragmentation	Efforts to develop stronger capital markets have resulted in significant fragmentation leading to poor efficiency of capital allocation, resulting in a pooling of capital in comparatively wealthy cities and among large State-Owned Enterprises (SOEs), exacerbating inequality. By facilitating greater efficiency of capital allocation this could enable greater distribution of capital across a wider range of cities, promoting more inclusive growth in less developed areas of China.	International lenders and investors have taken an increasing interest in Chinese markets as they become an increasingly large proportion of the global market. If capital allocation is improved particularly to MSMEs, there will be a growth in direct lending and product selling opportunities.	International connectivity for Chinese markets including stock and bond connects to London have been proposed in recent high-level dialogues and should be promoted to keep the UK in the lead position for China’s interface with the west. Some appetite for discussion and collaboration on how regulators can effectively manage this important sector of the economy.
Market constraint	Constraint description	Secondary benefit opportunities	Scope for external/international involvement
Direct constraint on poverty reduction: access to credit and other financial services
Limited access to and understanding of financial services	China’s economic development has disproportionately benefitted cities over rural areas and the wealth gap is widening. Unequal education and lack of access to suitable financial service providers and products has put many of China’s most vulnerable communities of development opportunities and thus the financial services sector does not work for all.	Improving access to financial services may have a secondary benefit for international firms if they are well positioned in the service supply chain.	Poverty alleviation is one of the top three government priorities and financial inclusion is a key mechanism for regulators and authorities to drive economic change from the bottom up. China is eager to make sure that the entire population feels the benefits of economic growth and welcomes foreign involvement in certain areas around this theme, particularly for women.
[42] Elliot & Yan, The Chinese Financial System, The Brookings Institution 2013

What commitment to partnership is there to build on for this programme?

There is strong consensus in Chinese policy circles of the need for the further development of the country’s financial markets. The 13th Five Year Plan prominently features the need for proactive market opening including the implementation of a macro prudential regulatory framework. This was reiterated recently, notably in the PBOC’s 2018 work plan, which highlighted the need for “strengthened financial risk prevention and control”, including in the internet banking, Fintech and insurance spaces.

There is also consensus on the need for poverty alleviation work in China. The Central Economic Work Conference, which outlined the Chinese government’s top priorities for 2018-2020, highlighted “poverty alleviation” as one of three major tasks for authorities in the coming years.

In the 2015 UK-China Economic and Financial Dialogue (EFD), led by then Chancellor George Osborne and Vice Premier Ma Kai, as well as during the State Visit to the UK by President Xi Jinping, the UK and China it was declared that the UK and China have an “unparalleled long-term partnership on financial services… [which is] a leading area in the bilateral relationship”[43].
[43] UK-China Joint Statement on building a global comprehensive strategic partnership for the 21st Century, 2015. Available at: https://www.gov.uk/government/news/uk-china-joint-statement-2015

This commitment was further strengthened in the 2016 EFD, where both sides agreed on a strategic plan for financial services to diversify and deepen cooperation on asset management, insurance, capital markets, Fintech and green finance[44]. The 2016 dialogue also saw the establishment of an annual UK – China Financial Industry Summit as part of the EFD.
[44] UK-China 8th Economic and Financial Dialogue: policy outcomes, 2016. Available at: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/567521/UK-China_8th_EFD_policy_outcomes_paper.pdf

The 2017 EFD further built on UK-China bilateral cooperation in the financial sector, including plans to link both countries equity and debt markets. UK banks are continuing and strengthening their relationships in China and there is increased demand for knowledge sharing between the UK and China, particularly on regulatory and oversight matters.

What results should the programme focus on and how might these be achieved?

1. Based on the above analysis of the constraints facing the development of the financial sector in China, those areas of particular interest to the UK and the direction of Chinese policy, the following focus areas (outcomes) have been identified:
  1. A more robust and innovative regulatory environment which supports the introduction of efficient and resilient products and services, including in the Fintech space
  2. Greater transparency and a more predictable regulatory environment which treats new entrants (including UK/international ones) equally
  3. Greater capacity for oversight supporting stable, responsible lending and investment, and fostering inclusive financial products such as insurance and pensions
  4. More inclusive financial system that educates and provides access for the underserved and poorest in China’s society, including disadvantaged groups, such as women and ethnic minority groups

Activities are likely to include those set out in the table below:

Activity type	Programme activities
Provide technical assistance that draws from the UKs areas of comparative and technical advantage / Host and lead practical workshops to share UK experience and expertise / Support and advise policy teams; engagement with DIT and private sector to ensure wider benefits of programme fully realised Provide support to Chinese and UK delegates and stakeholders / Develop high quality tailored research / Undertake high quality and focused analysis / Provide policy advisory and support that draws from international experience and expertise / Demonstrate research results with pilot initiatives / Actively advocate better standards for regulation, consumer protection and lending and investment practices / Generate financial education and training for the poorest sections of Chinese society, including women / Encourage the growth and development of financial services for the unbanked population, with new products and extensions of existing ones, including for poorer communities and women / Develop detailed insightful case studies / Develop and lead joint initiatives / Manage secondments to provide long-term skills and expertise building	A UK-China Fintech Regulatory Sandbox to remove barriers to innovation in the Fintech space and ensure appropriate safeguards, regulations and consumer protection mechanisms are built into new products and services. The Sandbox may have both national and regional hubs and may link into broader public and private sector UK-China efforts in the Fintech space, and will be reinforced with wider research pieces to inform policy and Sandbox development.
	Research, dialogues, conferences and experimental dialogues on financial regulatory policy and architecture, and other ad-hoc events on targeted areas of UK-China economic co-operation, delivered through working groups and a flexible projects fund. / A comprehensive training programme targeted on China’s regulatory authorities and central bank, leveraging UK expertise. Delivering bespoke training and capacity building on the regulation of China’s fast growing and increasingly complex financial markets. Leverage private sector partnerships to provide investor education programmes including technical assistance, workshops, joint initiatives and secondments.
	Multi-year pilots and innovative programming in the pensions and insurance spaces, as a proving ground for new policy ideas and evidence for research work. This will provide a way for innovation in insurance and pensions, which are naturally inclusive financial products, to demonstrate functionality and evaluate risks before they are implemented on a wider scale.
	A targeted financial education programme to educate underserved communities on how financial services can help them save money, grow business and better their lives. / Supported by a progressive series of pilot initiatives that help improve access to financial services for underserved communities/businesses

ENERGY AND LOW-CARBON ECONOMY
Primary purpose and gender equality

From early in the 21st century, China has represented the growth engine for global energy demand. Fiscal and monetary expansions through state-related entities made growth investment-intensive and strongly oriented towards heavy industry and infrastructure. This development path has more than tripled energy demand relative to 1990 levels with more than 90 per cent of the increase in energy demand met by fossil fuels[45]. China is now the world’s largest consumer and producer of energy, and produces more greenhouse gas emissions than the US and EU combined. Its consumption patterns and economic structure are critical to global emissions reduction.
[45] International Energy Agency (2016) World Energy Outlook Special Report: Energy and Air Pollution

This energy and carbon-intensive growth has given rise to natural resource constraints, environmental deterioration, rising dependence on imported energy and risks of asset stranding from overcapacity. The health impacts of pollution and environmental degradation have created social pressures to control and mitigate pollution.

Under China's current energy mix, greenhouse gases and common atmospheric pollutants are primarily caused by the burning of fossil fuels; therefore, they are of the same origin and occur synchronously[46]. Climate change response measures such as significantly reducing the dependency on fossil fuels and increasing the portion of clean and renewable energies have synergy with environment protection and public health[47]. The 13th Five Year Plan prioritises action to put China on a more sustainable and “green” growth path.
[46] Gao, 2016, China's response to climate change issues after Paris Climate Change Conference, Advances in Climate Change Research.
[47] IPCC, 2014, Summary for Policymakers//Climate Change 2014: Mitigation of Climate Change Contribution of Working Group III to the Fifth Assessment Report of the Intergovernmental Panel on Climate Change Cambridge University Press

In November 2014, President Xi announced that China would peak its CO2 emissions around 2030, with the intention to try to peak early, and to increase the non-fossil fuel share of all energy to around 20 per cent by 2030. The 13th Five Year Plan is guided by five key principles of “innovative, coordinated, green, open, and shared development” and sets peak targets for carbon emissions and energy and water consumption, as well as goals for increasing efficiency of industries and eliminating outdated or overcapacity production facilities, increasing energy production from renewables, and developing green infrastructure. The final plan shows the importance attached to this agenda in China’s overall development: 10 out of 25 numerical targets in the 13th Five Year Plan are related to the environment. This commitment was re-affirmed by the identification of “three battles” (risk prevention, poverty alleviation, and environmental protection) for 2018-2020 at the 19th Party Congress. The March 2018 government re-organisation and the newly-established Ministry of Ecology and Environment signalled further commitment to ambition addressing climate change and environmental risks.

China’s continued long-term growth potential and, by association, its continued capacity to alleviate poverty, are now linked to its ability to transition towards a more sustainable, low carbon economic growth model. Girls and women are more vulnerable to climate-related disasters[48]. The UNDP reports that, “women are more vulnerable to the effects of climate change than men --- primarily as they constitute as the majority of the world’s poor and are more dependent for their livelihood on natural resources that are threatened by climate change. Women and men in rural areas in developing countries are especially vulnerable when they are highly dependent on local natural resources for their livelihood”[49]. China’s poorest live in areas prone to extreme weather and various forms of pollution. Children from poorer families are the most vulnerable to respiratory infections and vector borne diseases[50].
[48] World Bank, 2011, “Gender and Climate Change, 3 Things You Should Know”.
[49] http://www.undp.org/content/dam/undp/library/gender/Gender%20and%20Environment/PB1-AP-Overview-Gender-and-climate-change.pdf
[50] http://www.worldbank.org/en/country/china/overview

A low carbon transition also has the potential to yield significant economic growth potential through potential industrial productivity gains and inducing innovation in clean technologies, with knowledge spill-overs into other sectors, which are likely to drive higher GDP growth than otherwise[51]. Meanwhile, China’s primacy as a manufacturing centre means that scale-effects could lower international technology costs.
[51] Aghion, Hepburn, Teytelboym and Zenghelis, 2014. Path-Dependency, Innovation and the Economics of Climate Change. Policy Paper. Centre for Climate Change Economics and Policy, Grantham Research Institute on Climate Change & the Environment, and New Climate Economy.

While extractive and resource-intensive industries such and coal mining and thermal power generation will be negatively impacted by a move to a greener growth model there are likely to be significant economic upsides. Industrial power prices are currently 50 per cent higher than in the US, largely as a consequence of non-economic thermal generation dispatch rules linked to the dominance of the coal capacity base. Power sector reforms are needed to help alleviate issues around high renewable energy curtailment rates and to promote investment in renewables and energy storage technologies. High industrial power prices and industrial energy efficiency are important components of international competitiveness.

Examples of key market failures/constraints and areas for reform

China’s energy and low-carbon reform agenda is ambitious and entails risks that could slow or stall progress. The fundamental reforms, rebalancing and shifts required to complete a successful low carbon transition cut across multiple sectors and decision making actors. There are no individual constraints or barriers to China’s low carbon ambitions but instead a set of inter-connecting and interacting constraints that include:

Capacity constraints: The number of Chinese officials dealing with energy and climate change policy within the central and provincial governments is less than in the UK. The limited institutional capacity has meant policy formulation and implementation has been often been inadequate and incomplete, lacking the resource to consider wider growth and social impacts of energy policy. An example of the impact of this is the delay to the introduction of China’s national emissions trading scheme from 2015 to late 2017, with the final scheme only covering large thermal power generation facilities rather than the planned eight industrial sectors.

Misalignment of incentives: Provincial officials tend to be measured by absolute macroeconomic growth targets, rather than taking into account a wider range of factors that matter for inclusive growth such as access, sustainability and externalities. They oversee heavy industry and China’s booming cities. When compounded by poor data and reporting, this has meant enforcement of low carbon policies has been inconsistent or insufficient.

Vested interests: Market reform in the fossil fuel and power sectors is limited by powerful government-linked business interests. State Owned Enterprises, especially State Grid, the National Oil Companies and the coal lobby fear losing their near-monopoly positions. Provinces reliant on heavy industry resist reforms that have contributed to job losses and social instability.

Poor management of new technology deployment: Inefficient subsidy policies, poor management, technical practices, and constraints on new tech innovation hinder clean energy deployment[52]. Reform in this area has the potential to benefit communities affected by the negative externalities (pollution, poor supply) of current energy policy and at the same time, bring new and more affordable products to market to meet the needs of underserved groups.
[52] 15% average curtailment rate of wind energy across China in 2015, National Energy Administration February 2016, http://www.nea.gov.cn/2016-02/02/c_135066586.htm

What opportunities are there for UK business?

Transitioning from energy and carbon-intensive growth to a low carbon pathway will require enhanced policies and measures to improve energy efficiency; continued efforts to manage an increasingly complex energy grid; the electrification of passenger transport (as well as other processes); a strategy for managing the phase-out of coal-fired power (unless equipped with carbon capture and storage); avoidance of new (unabated) coal; the incorporation of climate risk into decision-making; and the implementation of measures to shift China’s financial sector towards a system that can finance low-pollution, low-carbon, resource-efficient infrastructure.

It has been estimated that China’s future green growth plans will require an annual investment of USD $320 billion[53]. Senior Chinese officials believe China’s low-carbon market will be cumulatively worth USD $6.7 trillion by 2030[54]. The UK’s deep experience, institutional and commercial expertise and areas of relative comparative (export), technology (patent holding) and service sector advantage means it is well-placed to support China’s energy and low-carbon economy ambitions, with particular strengths in:
[53] PBOC UNEP report: Establishing China’s Green Financial System, 2015
[54] Chinese official personal comment 2016
- Innovating and commercialising clean technologies
- Applying carbon budget theory to drive public policy
- Creating institutions that provide independent and impartial recommendations to policymakers
- Planning and executing low-carbon transition bridging strategies, including:
  - Developing and regulating unconventional gas recovery
  - Committing to and managing a shift away from base-load coal power, including socio-economic impacts
- Planning and undertaking complex successive power sector reforms
- The development of innovative and robust public and private green finance
- Mainstreaming of climate risk into financial and political decision making processes

Realisation of commercial opportunities represents significant opportunity and challenge for UK business. Large parts of the relevant low carbon sectors are still closed to full foreign participation and there is strong competition from well-resourced and positioned state-owned enterprises. There is also strong competition from incumbent international competitors.

What commitment to partnership is there to build on for this programme?

Domestically, the Chinese leadership has put “green development” at the heart of China’s 13th Five Year Development Plan. The leadership sees low-carbon development as an opportunity to tackle pollution and move up the technology value chain. President Xi’s announcement that China would peak its CO2 emissions around 2030 was an important signal to the international community ahead of the successful Paris climate negotiations. Supporting green growth in poorer countries through south-south cooperation is now an important component to China’s new engagement in international climate negotiations through the UNFCCC process[55].
[55] See this UNDP report on China’s south-south cooperation on climate change to date: http://www.cn.undp.org/content/china/en/home/library/south-south-cooperation/more-money--more-impact--china-s-climate-change-south-south-coop.html

The top Chinese leadership considers the UK to be a world-leader in low-carbon policy and energy reform. This belief has been demonstrated through more than five years of engagement through the existing Prosperity Fund, and government-to-government partnerships including the Secretary of State level UK-China Annual Energy Dialogue, UK-China Clean Energy Partnership, Climate Change Working Agreement and co-chairmanship of the G20 Green Finance Study Group.

In December 2017, UK Secretary of State for Business, Energy and Industrial Strategy and the China National Energy Administrator signed an Action Plan for Clean Energy detailing the areas the two countries would cooperate through under the Energy and Low Carbon Economy Prosperity Fund programme. The British Embassy in Beijing is also working with the Ministry of Ecology and Environment on a MoU to underpin the China-UK cooperation on climate change. These agreements will provide a high-level buy-in and engagement for the upcoming Energy and Low Carbon Economy Programme.

What results should the programme focus on and how might these be achieved?

It is proposed that the overall impact from the programme is that:
- China reduces emissions below its Nationally Determined Contribution to the UNFCCC;
- Global costs of clean energy technologies fall, with international and UK companies winning business in partnership with Chinese firms in China and third countries.

These impacts will be supported by the following suggested intermediate outcomes. By the end of the programme, drawing on UK research, policy and commercial expertise, China will have:
- Made progress towards the formation of a stable and long term clean technology policy and regulatory environment;
- Increased the use of natural gas within domestic energy system and made progress in liberalising natural gas markets
- Commenced structural reduction in coal use in energy system
- Made progress in liberalising national and provincial power markets informed by international experience
- Started to adopt system thinking-informed decision making in energy sector
- Increased recognition of climate risk by decision-makers and in decision-making process
- Made progress in transparent engagement with international climate change and energy governance structures

Programme activities may include those set out in the table below:

Activity type	Programme activities
Provide technical assistance that draws from the UK’s areas of comparative and technical advantage / Host and lead practical workshops to share UK experience and expertise / Support and advise policy teams; engagement with DIT and private sector to ensure wider benefits of programme fully realised Provide support to Chinese and UK delegates and stakeholders / Develop high quality tailored research / Undertake high quality and focused analysis / Provide policy advisory and support that draws from international experience and expertise / Develop detailed insightful case studies / Develop and lead joint initiatives / Manage capacity building trainings and secondments to provide long-term skills and expertise building	PF programme management office to support delivery of research, case studies, analysis, policy advice and support, training, technical assistance, workshops, joint initiatives and secondments. / Senior Advisory Group of Business, Academic and Government expert quarterly meetings.
	Regulatory exchanges and two-way secondments
	Joint study group to gather latest research on climate risks to infrastructure, finance, and economic systems, reporting to planning Ministries building on China Climate Change Expert Committee and UK Climate Change Committee cooperation. / Business Advisory Group on climate risk and resilience.
	Activities linking with existing University and Industry partnerships to leverage existing UK-China collaboration.
	Alumni/expert audit to match UK and Chinese expertise, and maintain engagement from UK specialists with China knowledge.
	UK-China Clean Energy Partnership Action Plan annual Work Plan development / A horizon scanning research to review emerging issues, and provide responsive and flexible engagement to emerging issues and trends.
	Climate change working group established, with supporting analytical capacity, to raise ambition for UNFCCC negotiations.
	Work with policy and commercial teams across the China Network on policy advocacy and preparation for high-level Ministerial dialogues with China to effect policy changes and the removal of market access barriers needed to generate primary and secondary benefit; Follow-up with DIT and private sector partners to realise export wins and investment projects.

INFRASTRUCTURE IN AFRICA AND DEVELOPING ASIA

Primary purpose and gender equality

The stock of roads, ports, energy, telecoms, water and sanitation networks and buildings is vital for any country’s economic growth and development. Better quality and quantity of infrastructure increases connections, increases trade, reduces costs, facilitates investment and facilitates access to public services like education and health. Transport networks connect producers and consumers to markets, utilities help provide essential inputs of production and consumption like power and water, and communications networks facilitate the exchange and dissemination of information and knowledge. Inadequate infrastructure can lead to power or water shortages, congestion or public health risks that can create significant costs (including social) to economies.

Many studies estimate that the multipliers (or return on investment) to infrastructure investment are significant. The OECD find infrastructure investment can have a positive effect on growth that goes beyond the effect of the capital stock because of economies of scale, the existence of network externalities and competition enhancing effects[56]. The IMF highlighted now is a good time for public infrastructure investment to boost short-run demand and long-run supply potential[57], given weak global growth and low interest rates. They argue output multipliers can range from 0.4 in the short run to 1.4 in the long-run. Bom and Lighthart (2009)[58] found a 1 per cent increase in the stock of public capital in general could raise GDP by 0.08 per cent on average and can be 2.5 times higher for infrastructure. Straubb (2009)[59] and Estache and Garsous (2011)[60] find similar order impacts.
[56] ## OECD (2009) Infrastructure and Growth - Empirical Evidence. Discussion Paper. Available at: http://www.oecd-ilibrary.org/economics/infrastructure-and-growth_225682848268
[57] World Economic Outlook (2014) Legacies, Clouds, Uncertainties. Available at: http://www.imf.org/external/pubs/ft/weo/2014/02/
[58] Bom, P. and J. Ligthart (2009) How productive is public capital? A meta-regression analysis, Andrew Young School International Studies Program Working Paper 09-12.
[59] Straub, S. (2008) Infrastructure and growth in developing countries: recent advances and research challenges, World Bank Policy Research Working Paper 4460.
[60] Estache, A, and G. Garsous (2011) Drivers of the impact of infrastructure on growth: a meta-analysis ULB, ECARES working paper, Brussels.

Public infrastructure can often be disproportionately good for development and for the poorest. As it can facilitate access to markets, technology, finance or public services (health, education, water and sanitation), infrastructure can be extremely beneficial for poverty reduction and development. Transparency in infrastructure that improves its efficiency and reduces risks of corruption can also help ensure the benefits of infrastructure investment are distributed evenly.

There is currently a global deficit in infrastructure investment. In 2013 McKinsey estimated that US$ 57 trillion of infrastructure investment was needed globally over the next 18 years. The current infrastructure gap in low and middle income economies is estimated to be around $1trillion[61] annually. Asia itself requires an additional US$ 750 billion annually in infrastructure investment to 2020 (about 6.5 per cent of its GDP), with over 80 per cent of demand to come from energy and transport, the sectors most critical to supporting heightened economic activity. This issue has now been widely recognised at the multinational level with Europe, the G20, emerging markets and multilateral development banks prioritising infrastructure investment as a strategy for growth.
[61] Bhattacharya, A., Romani, M., and Stern, N. (2012). Infrastructure for development: meeting the Challenge Grantham Institute. Available at: http://www.lse.ac.uk/GranthamInstitute/wp-content/uploads/2014/03/PP-infrastructure-for-development-meeting-the-challenge.pdf

At the same time, some economists now argue that China has inefficiently delivered infrastructure, which has led to a significant build-up of central and local government debt[62]. As marginal returns decline, this infrastructure is now not expected to generate enough additional value compared to the cost (interest rate) of debt. As a result, the Chinese authorities are increasingly interested in Public-Private Partnership models as a means of financing large infrastructure programmes and driving value.
[62] E.g. see Pettis, M. (2016) China: Choosing More Debt, More Unemployment, Or Transfers. Available at: http://carnegieendowment.org/chinafinancialmarkets/66221

There is therefore a clear interest within China to ensure infrastructure built overseas is as productive as possible, into the long-term. Indeed, Chinese businesses have expressed interest in accessing UK expertise for building third country projects.

Capabilities in infrastructure make it possible for China to not only offer construction services globally, but to extract trade benefits from global markets. At the turn of this century, China had no major presence in the global construction market. Now, within Engineering News Record (ENR) top twenty global contractors (by revenue), four are Chinese companies'[63]. Since 2012, ENR has been publishing a special list of the top eighty Chinese contractors[64]. In 2012, Chinese contractors earned US$67 m from overseas infrastructure projects. By 2014, this had increased 117 per cent to US$191.7m[65]
[63] See the full list here: http://www.enr.com/toplists/2016-Top-250-International-Contractors1
[64] See the full list here: http://www.enr.com/toplists/2015_Top_Chinese_Contractors
[65] H. Li, Chen, & Martek, 2015

China extending its rapid and efficient infrastructure services to other countries has the potential to drive transformational change for global connectivity and trade. On the other hand, many Chinese infrastructure projects overseas to date have been sub-optimally delivered due to lack of international experience, poor understanding of local conditions and requirements[66]. There are few incentives in the Chinese system to deliver high-quality, commercially-viable or pro-poor projects, at home or abroad[67].
[66] For example, see the results/conclusions from this 2015 UN and Chinese government-led self-perceptions survey of over 250 Chinese firms operating overseas: http://www.cn.undp.org/content/china/en/home/library/south-south-cooperation/2015-report-on-the-sustainable-development-of-chinese-enterprise.html
[67] As discussed in earlier sections, Chinese banks, local governments are ranked by how much they have stimulated economic growth, therefore firms will respond to these incentives accordingly and build as much and as quickly as they can.

Therefore, there is an interest within China and in poorer countries in engaging with infrastructure projects to ensure they are pro-poor, high-quality (for example meeting social and environmental safeguards) and commercially-viable. In Uganda for example, where recent road projects have had to be cancelled due to failure of social safeguards, the partner government has requested UK support to Chinese-led projects. Tanzanian officials have similarly expressed a desire to involve UK companies in projects for quality assurance.

Effective infrastructure can have a positive impact on the lives of women and promote women’s economic empowerment; access to infrastructure is an important prerequisite for Women’s Economic Empowerment and has important implications for women’s access to jobs. It is also a significant enabler for improving gender equality for women and girls[68]. The IFC notes electrification of rural communities of South Africa led to a 13.5 per cent increase in female empowerment in those communities. Women’s economic empowerment is “about economic equality: such as closing the gender pay gap, increasing job opportunities, or access to loans. But it's also about breaking down barriers that hold women back: from discriminatory laws to an unfair share of home and family care. And it's a game-changer for development: because when more women get the chance to work, it makes their families, communities & countries wealthier”[69].
[68] IFC Jobs Study, 2013
[69] UN High Level Panel

Due to rapid rates of urbanisation combined with the long-term lock-in effects of getting infrastructure investments wrong, there is a limited window of opportunity to act[70].
[70] World Bank (2013) Planning, connecting and financing cities now. Available at: http://siteresources.worldbank.org/EXTSDNET/Resources/Urbanization-Planning-Connecting-Financing-2013.pdf

Examples of key market failures/constraints and areas for reform

There are three key market failures that affect infrastructure completion by China at home and overseas:

  1. Missing markets: China’s domestic infrastructure market suffers from incoherent legislation, hindering the expansion of private finance. For example China lacks a unified Public Private Partnership (PPP) Law to provide predictability to market participants, and there is a lack of consistency between current policies. We are currently supporting early stage work advising the Chinese government on the drafting of PPP legislation.

  1. Misaligned incentives: China’s approach to a number of aspects of the project lifecycle including project selection and preparation, feasibility analysis, social and environmental sustainability, risk and contracting frameworks, and financing are often not sufficiently detailed. This constrains its firms’ ability to deliver infrastructure overseas in a more sustainable and commercially-viable way, which would deliver additional benefits to partner countries.

  1. Asymmetric information: China’s businesses have not been operating overseas for long. They suffer from incomplete information about the legal and other frameworks of other countries, as well as risks. This constrains their appetite to invest overseas (as opposed to simply take pre-financed contracted projects). By addressing these constraints, reforms have the potential to improve China’s contribution to infrastructure globally, including in developing countries where China is stepping up its engagement.

  1. Reforms in these areas have the potential to encourage further investment in public infrastructure and improve its quality – helping it to better meet the needs of communities and strengthen standards (including safety and environmental).

What opportunities are there for UK business?

The UK has particular breadth and depth of expertise in best practice methodologies for infrastructure delivery (e.g. Five Case Model, Project Initiation Routemap) and public-private partnerships (PPPs), from both the public and the private sector. This has enabled the UK to position itself as a recognised world leader. Leading engineering and construction companies, facility management operators, technical, legal and financial advisers are active in the UK market, and apply the lessons learned and experience gained in this market to design, build, operate, and maintain infrastructure assets around the world.

The demand for infrastructure finance outstrips the capacity of the bank loan market, which is the tradition source for infrastructure finance. The UK’s financial sector is well placed to explore solutions to this challenge and help to facilitate the development of infrastructure around the world while providing opportunities for UK financial services. Infrastructure engagement could also support the UK’s position as a leading financial centre, by strengthening the attraction of the UK as a location to raise and structure RMB and green finance – either for China’s domestic or overseas projects.

Investment in other countries’ infrastructure is important to the UK. Infrastructure projects provide direct commercial opportunities for UK businesses and exporters in the short-run who can capitalise on overseas demand for our expertise in areas like PPP, infrastructure financing and investment and downstream services needed for infrastructure construction, operation and maintenance.

1. Infrastructure investment will also have positive spill over effects for the UK, improving trade routes/efficient and reducing UK business costs in the long-run. Indirectly, if infrastructure improves the business environment and strengthens growth in economies, this should raise demand for UK exports and investment.
2. The UK also has experience of working with businesses and contractors on sustainability. For example, the Ethical Trading Initiative[71] is a DFID-supported alliance of businesses, trade unions and NGOs committed to set and uphold labour standards in the supply chains of its corporate members, or the Responsible and Accountable Garment Sector Challenge Fund (RAGS). The UK has also supported international initiatives that set environmental standards for MNCs such as the UN Global Compact and the OECD Guidelines for Multinationals.
  [71] See http://www.dfid.gov.uk/Working-with-DFID/Funding-opportunities/Business/Ethical-Trading-Initiative-ETI/.

One element of the programme, the UK-China Infrastructure Academy, funded by the non-ODA element of the Prosperity Fund, is already up and running. This Academy is intended to provide training and guidance for senior executives from leading Chinese state-owned and private infrastructure businesses, as well as Chinese policymakers. In the initial phase of the Academy, courses are focused on entering and investing in the UK infrastructure and regeneration markets, and will be located in the UK. Participants are learning from HMG and UK industry experts about all aspects of doing business in the UK (planning, policy, legal regimes, regulation, procurement, finance, standards, roles of government, business norms etc). However as up to 25 per cent of attendees will be government officials, the Academy will also build capacity for Chinese policymakers to support them in developing policy for the domestic Chinese infrastructure sector, and for Chinese firms investing overseas (including in ODA-eligible countries).

The relationships built with the participants will be powerful tools to leverage to secure buy-in and collaboration both in China domestically and with Chinese businesses in (ODA-eligible) partner countries, thus supporting the wider objectives of the Infrastructure Alliance. Moreover, relationships established through the wider Alliance work can be leveraged for greater commercial opportunities, in terms of increasing Chinese interest in participating in the Academy, thereby facilitating greater and high quality inward investment into the UK.

What commitment to partnership is there to build on for this programme?

China’s 13th Five Year Plan (2016-2020) emphasises the importance of infrastructure development for China’s reform and opening. Specific targets outlined by the Plan include building or upgrading 20,000 kilometres of rural roads, expanding the high-speed rail network from 20,000 to 30,000 kilometres, covering 80 per cent of major cities, building over fifty new civilian airports, and upgrading numerous existing airports into international hubs. With green development a key priority, the Plan also proposes the development of low carbon transportation, stronger infrastructure energy standards, and the use of modern, green technologies to upgrade China’s transportation systems to be more energy efficient.

The 2015 UK-China Economic and Financial Dialogue saw agreement between the two countries to establish the ‘UK-China Infrastructure Alliance’ to, among other things, promote UK-China co-operation in each other’s markets and in partner countriess, and to provide training on public-private partnerships for Chinese central and local government officials. NDRC, MOFCOM, the Ministry of Finance (MOF) and the China International Contractors’ Association (CHINCA), key beneficiaries of the project, all have shown great interest, and HM Treasury signed MoUs on infrastructure and PPP collaboration with both NDRC and MOF in 2015. They strongly believe that this project will add value to both Chinese growth and the sustainability of China’s contribution to economic growth in developing partner countries, and will provide opportunities for UK businesses. The involvement of UK expertise in infrastructure development in China and in other ODA-eligible country will contribute to ensuring that such development is carried out in an environmentally and socially-responsible way.

What results should the programme focus on and how might these be achieved?

1. Based on the above analysis of the constraints facing the development of the infrastructure sector in China, those areas of particular interest to the UK and the direction of Chinese policy, the following focus areas (outcomes) have been identified:
  1. Improved standards for Chinese outbound infrastructure investment implemented by the Chinese government;
  2. Policy reform in China that facilitates international investment and expertise for delivery of infrastructure in partner countries in Africa and Asia;
  3. Increased cooperation between China and international partners on infrastructure projects in partner countries;
  4. Supporting Chinese-led infrastructure projects to access international financing and expertise.

Programme activities may include those set out in the table below:

Activity type	Programme activities
Supporting Chinese-led infrastructure projects to access international financing and expertise	Developing a robust pipeline of infrastructure projects with high potential to be delivered through UK-China partnerships / Providing funding for project preparation of prioritised projects, leveraging UK methodologies and best practice / Advising and supporting project sponsors to bring projects to market and secure financing, including from the London market
Generation of policy reform products, skills sharing and international best practice	Commission a number of in-depth evidence synthesis documents relevant to specific reform interests of Chinese authorities. / Identifying and leveraging UK expertise and best practice to deliver capacity building / Delivering capacity building for project sponsors, project stakeholders and/or partner government authorities to manage and deliver prioritised projects / Supporting policy officials in drafting regulations and working through technical aspects of reforms
Coordination to support increased UK-China collaboration	Government to government (G2G) and business to business (B2B) mechanisms and platforms established / Possible establishment of Infrastructure Hubs located in key regions in Asia and Africa to accelerate international (including UK)-China cooperation in partner countries / Organising events, seminars, training sessions, workshops and platforms to bring together key stakeholders and facilitate international best practice sharing
Support and advise policy teams; engagement with DIT and private sector to ensure wider benefits of programme fully realised	Work with policy and commercial teams across the China Network on policy lobbying and preparation for high-level Ministerial dialogues with China to effect policy changes and the removal of market access barriers needed to generate primary and secondary benefit; Follow-up with DIT and private sector partners to realise export wins and investment projects

A substantial proportion of this programme will be focused on developing partnerships with China in ODA-eligible partner countries to support increased infrastructure investments delivered with international expertise and incorporating best practices. A scoping study commissioned by McKinsey evaluated the potential for UK-China infrastructure collaboration in 15 countries across four regions (East Africa, Central Asia, South Asia and Southeast Asia) which have seen significant flows of Chinese infrastructure financing. The study assessed countries based on a number of metrics including market sizing and infrastructure spend forecasts, linkages with the UK and China, development impact and commercial potential, and through this process recommended prioritisation of East Africa and Southeast Asia. A focus on these regions would also have potential for synergies with a range of other HMG activity including planned IPA (Infrastructure Projects Authority) infrastructure programmes in Indonesia and Vietnam as well as DFID programming in East Africa. The final selection of focus countries for this programme will be determined following further evaluation and consultations with stakeholders including Posts, Chinese partners and market participants over the coming months.

A second element to the programme will focus on support for implementation of policy reforms, standards and guidelines in China to incentivise more commercially focused infrastructure investments, incorporating industry best practices, and delivered in collaboration with local and international partners.

PRIMARY PURPOSE AND SECONDARY BENEFIT APPROACH

Our approach to primary purpose

1. As outlined above, the four programmes each have significant potential to further sustainable economic development globally and contribute to the reduction of overall poverty and inequality to achieve the UN SDGs. The programmes overall are expected to impact a wide range of development indicators, likely to include the channels below. Comprehensive indicators will be developed in conjunction with programme partners, in line with the Fund-level monitoring and evaluation strategy (see the Management Case for more detail). Poverty and inequality will be reduced through:
  1. Indirect income increases (through job creation, increasing productivity, rising wages)
  2. Price reductions (through greater competitiveness, improved market access)
  3. Improved access to basic services (more reliable and sustainable energy)
  4. Higher quality products and services (including from public sources)
  5. Strengthening resilience and protection from shocks (stable macro economy, greater transparency and predictably in public policy)

Working with suppliers, the programmes will be informed by gender and inequality assessments, ensuring that opportunities are taken to shape activities to further inclusivity aims. See Management Case for more detail.
Furthermore, tackling the challenges outlined above through the four programmes will make an important contribution to China’s efforts to meet the UN Sustainable Development Goals (SDGs). As the programmes are sectoral and interact, their impact on the SDGs is cross-cutting.

As set out above, each programme will contribute, by design, to direct or indirect poverty reduction, gender equality and reduced inequalities – Goals 1, 5 and 10.

The table below highlights which additional SDGs the portfolio as a whole will further. It should be noted that the categorisations below are not exclusive – the portfolio is designed to be cross-cutting, so that programmmes contribute across the challenges and across the SDGs.

Challenges	Cross-Cutting Programmes	SDG contribution / (in addition to 1, 5 and 10, which all contribute to)
Transition to a new growth model	China Business Environment / Infrastructure / Energy and Low-Carbon Economy / Financial Services	4 (quality education) / 8 (jobs and economic growth) / 9 (industry, innovation, infrastructure) / 16 (justice and institutions) / 4 (quality education)
Remaining Poverty		2 (no hunger) / 16 (justice and institutions)
Inequality		16 (justice and institutions)
Environmental Damage		7 (clean energy) / 12 (responsible production & consumption) / 13 (climate action) / 15 (life on land)
Rapid Urbanisation		11 (sustainable cities and communities)
An ageing population		(good health and wellbeing)

Our approach to secondary benefits – UK business

Both the UK Aid Strategy[72] and DFID’s Economic Development Strategy[73] point to the importance of the private sector in driving growth and wider economic development. Alongside building the capacity of the public sector, the China Prosperity Fund Portfolio will seek to open up markets and remove obstacles to structural reform that make it easier for businesses to operate, provide employment and generate wealth.
[72] UK aid: tackling global challenges in the national interest (2015). Available at: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/478834/ODA_strategy_final_web_0905.pdf
[73] Economic Development Strategy: prosperity, poverty and meeting global challenges (2017). Available at: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/587374/DFID-Economic-Development-Strategy-2017.pdf

By engaging in dialogue with the domestic and international business community, the constraints facing private sector growth will be better understood. The programmes will focus particularly on those constraints that matter most for UK business.

APPRAISAL CASE

INTRODUCTION

In recent years, FCO prosperity programming has supported China’s poverty reduction, and facilitated a number of partnerships with UK businesses. As set out in the Strategic Case, this business case proposes to build on that experience by establishing a multi-sector portfolio with four key focus issues in this first phase – China business environment , financial services, a low-carbon economy, and better infrastructure - that have been identified as being high potential both in terms of growth and poverty reduction, and opportunities for UK/international businesses.
QUANTIFYING BENEFITS
The overall purpose of the Prosperity Fund programmes in China is to steer its progress towards the UN’s SDGs that will result in global good impact both economically and environmentally. Our activity, alongside making a tangible difference to China’s contribution to global development, also demonstrates a clear secondary benefit to international business, including UK companies.

The Strategic Case identified key constraints and opportunities in four areas that Prosperity Fund programming can best address. The strategic case also identified a number of particular concrete results across those four areas.

In the Strategic Case, evidence was presented in each area that demonstrates the contribution of these areas to growth and inequality reduction. In some places the evidence was incomplete or difficult to quantify. Therefore the overall Theory of Change for this programme is based on medium evidence. It is also subject to a range of assumptions, set out in later sections.

However, it is also possible to attempt to estimate specific benefits of each programme, based on key expected outcomes, which are summarised in the table below.

SUMMARY OF PROGRAMME OBJECTIVES
Programme	Outcomes supported
China Business Environment	Greater protection for company Intellectual Property rights, leading to less IP abuse/theft / A more transparent, speedier process for UK/foreign investment into China / An approach to commercial dispute resolution resulting in more predictable and enforceable outcomes for UK/international firms. / An improved national approach to corporate compliance, particularly in anti-money laundering / An improved approach to the drafting and monitoring of standards, in line with international best practice
Financial Services	Market-driven regulatory environment which supports efficient and resilient products and services / Greater transparency and a more predictable regulatory environment which treats new entrants (including UK/international ones) equally / Greater capacity for oversight supporting stable, responsible lending and investment / More inclusive financial system that educates and provides for the poorest in China’s society
Infrastructure in Africa and Developing Asia	Policy environment that facilitates international investment and expertise for Chinese-led infrastructure / Chinese-led infrastructure projects supported to access UK/international expertise and financing / Increased cooperation between China and UK/international partners on infrastructure projects in partner countries / Improved standards for Chinese outbound infrastructure investment to UK/international levels
Energy and Low Carbon Economy	Adoption of market, finance and technology policies and regulations that support the transition to a low carbon growth model, level the playing field, and manage related systemic risks / Introduction of more cost-effective development and deployment of clean energy technologies and infrastructure to reduce GHG emissions / Implementation of ambitious actions for more transparent engagement with international climate change and energy governance structures

However, the development factors we are attempting to influence (productivity of capital, the rule of law, infrastructure investment optimisation and de-carbonisation) through the Prosperity Fund have economy-wide implications which are inherently difficult to model using the simple techniques.

Furthermore, it must be noted that in dealing with an economy with the scale ($11.063 trillion in 2016) and growth rate of China (6.9 per cent in 2017), small deviations in the input variable to our models can result in a highly significant output change which would appear unrealistic in any other economy. Estimates have been adjusted to take account of the amount of benefit that is reasonable for the UK to claim, given the activities of wider players and the extent to which UK support is critical in achieving a given result.

However, based on detailed modelling and estimation, we can estimate possible benefits from the programmes, of the magnitude shown in the below:

	10 Year Primary NPV (£m)	10 Year Secondary NPV (£m)
Conservative central estimate	£843	£240

The tables below provide a further breakdown of these figures.

In keeping with HMT guidance, a discount rate of 10 per cent has been applied to primary benefits and a discount rate of 3.5 per cent applied to secondary benefits and programme costs (see Section C). This appraisal period is ten years from the start of the intervention (2018), with results given after both five and ten years. It should also be noted that in order to give figures in pounds sterling, exchange rates have had to be used. This appraisal has taken $1 as equal to £0.77 (over 10 years), which are reasonable at the time of writing.

The estimated benefits quantified here are based on the objectives of each of the programmes. Key outputs are replicated here for reference.

ESTIMATES OF PRIMARY BENEFITS
Activity	Programme Cost	Do nothing counterfactual	Intervention Variable & Result	Impact	NPV Over 10 Years
China Business Environment	£27.5m	According to historical trends of improvements in the World Justice Index[74] (WJI), China will continue to improve in this area and (according to the data) is required to do so in order to achieve a high-income status. We have modelled the baseline rate of change of overall WJI on a projected pathway using historic growth in GDP/Capita.	The speed (rate of change) is increased.	Through modelling the relationship between GDP and WJI, we have simulated the effect of achieving an improved WJI score at the end of 2027. / This has an impact on GDP either through enabling the creation of additional GDP, or through not placing a limit on GDP (we cannot prove causation)	£389m
Financial Services	£22.5m	China has showed some willingness to open its financial markets, but according to the OECD[75] has still one of the most restrictive capital markets of major economies. China is experiencing an increase (less efficient) in the Incremental Capital Output Ratio (ICOR) leading to a decrease in the level of GDP growth achieved for each unit of capital employed. Our baseline model assumes no improvement in the ICOR ratio over the next decade.	An improvement in the ICOR ratio through increased competition provided by foreign firms. / Our assumption is that the prosperity programme drives reforms which improve the ICOR ratio by 0.1% between 2023-2027. / Our model also assumes that the same amount of capital is being invested in the years 2023 – 2027 as in the baseline.	The impact of this change is significant as 60-70% of all China’s GDP growth is as a result of capital investment. / A 1% improvement in the output from this level of capital investment has a significant impact on GDP growth.	£153m
Energy and Low Carbon Economy	£20.5m	In line with the 12th Five-Year Plan outcomes, China will achieve its 13th Five-Year Plan targets. The targets will look increasingly unambitious relative to the potential of non-coal pathways and the increasing systemic risks linked to over-capacity of high-emissions technologies.	The speed (rate of change) is increased. China achieves the 13th Five-Year Plan energy and low carbon targets two months earlier than in absence of the programme.	By the end of the programme period China will be two months ahead of 13th Five-Year Plan targets for energy and low carbon for the specific energy technologies covered by the programme. The two-month acceleration is carried forward in time as enhanced ambition in future Five-Year Plan’s and as China makes progress towards its UNFCCC Nationally Determined Contribution and 2030 emissions targets.	£218m
Infrastructure in Africa and Developing Asia	£14.5m	China’s overseas infrastructure investment plans will go ahead, with an estimated spend of US$1trn over a 10-year period. This has two effects on partner country GDP (i) Construction will add directly to GDP (ii) Post completion there will be an increase in GDP due to the elasticity (benefits) of the new infrastructure. / However, these GDP effects will be felt whether the Prosperity Fund is involved or not and have been modelled as such.	The intervention improves the planning and design of the partnered projects (projected $6.6bn). This reduces the required investment by 4% thereby enabling the construction of additional infrastructure with the same overall level of investment.	Overall, the same amount of investment will be made ($6.6bn), and as such no additional GDP will be derived from the construction phase. / However, this additional infrastructure will result in an increased in the associated spill over benefits. / It is the effect of this additional spill over we have modelled.	£83m
Overall Primary Benefit (NPV):					£843m
[74] http://worldjusticeproject.org/rule-of-law-index
[75] https://data.oecd.org/fdi/fdi-restrictiveness.htm#indicator-chart

ESTIMATES OF SECONDARY BENEFITS (FOR UK)
Activity	Programme Cost	Intervention Variable	Calculation	NPV Over 10 Years
China Business Environment	£27.5m	Improvements in the China business environment in-directly benefit the UK through increasing the wealth of potential customers. / Increasing overall GDP (derived from primary benefit) leads to a larger market for UK goods and services, plus additional capacity for Chinese investors to invest in the UK	The ratio of China’s GDP to UK exports and FDI was calculated over the past 4 years. This gave a figure of 0.284% of China’s GDP. / The calculation also assumed 0.06% growth in the ratio of UK exports/China GDP as this would be expected with an improved Rule of Law. / The impact of an increase in GDP (primary benefit) was then modelled using this ratio.	£17m
Financial Services	£22.5m	Improvements in access for foreign firms to the Chinese financial markets (insurance, pensions and Fintech) leads to an increase in the overall market share of UK firms.	Z-Ben consultancy provided estimates for current UK firms’ market share which was used as baseline. Estimates of market size and growth were also provided by PWC and Z-Ben and used in the model. / They also provided estimates for the improved market share through the reform of individual laws and barriers. An average was taken of these impacts to calculate the potential increase in market share, both in insurance and banking, of a single reform as a result of the proposed Prosperity programme. This increase in market share was projected from 2023 onwards (in both insurance and banking) thereby increasing access to the market. / We have considered the secondary benefit to be the return on this additional market share (1% rate of return (RoR)) in order to provide equivalence to an infrastructure investment.	£34m
Energy and Low Carbon Economy	£20.5m	Accelerated investment in energy technologies to meet and surpass 13th Five Year Plan targets for 2020 and a deeper understanding of and preference for UK supply chains and expertise leading to an increase in the overall market share of UK goods and services in China from 2020.	13th Five-Year Plan targets are converted into megawatt-hours of specific technologies using a 2015 baseline and curve-fitting. Costs per megawatt-hour-equivalent are derived for offshore wind, nuclear, natural gas, smart grid, energy storage and new energy vehicles. Costs follow international and China-specific cost curve projections. / An additional two months of growth in the technologies is applied. A 10% increase in UK goods and services related to the technologies is calculated relative to the current baseline and applied from 2020.	£47m
Infrastructure in Africa and Developing Asia	£14.5m	Increased access to Public-Private Partnerships (PPP) financing opportunities on overseas infrastructure projects leading to increased returns. Additional service export wins in planning, design and programme management.	Focusing on an estimated $6.6bn of project partnerships developed we assumed this would lead to a 10% share of PPP financing partnerships for UK companies on an annual RoR of 6%. / Additionally, we assumed 7.5% of the $6.6bn of partnerships was to be spent on planning and design, and that 20% of this would be secured by UK companies.	£141m
Overall Secondary Benefit (NPV):				£240m

QUANTIFYING COSTS

The programme budget allocated to the China bid was up to £85m. We have designed a portfolio across the four priority sectors accordingly. The table below sets out the cost profile (up to 2021 based on original timeline):[2]
[2] Some of the programmes referred to in these documents have been affected by the ODA reprioritisation exercise in the first half of 2020 due to the reduction in GNI during the early stages of the Covid-19 crisis. As a result, documents which pre-date that reprioritisation may not accurately reflect the programmes in their current form. As announced in the 2020 Spending Review, the UK will temporarily reduce how much we spend on Official Development Assistance (ODA). We will spend 0.5 per cent of our national income (GNI) on ODA, rather than 0.7 per cent. This may further impact spend on programmes.

Year	Y1 (2017/18)	Y2 (2018/19)	Y3 (2019/20)	Y4 (2020/21)	Total cost	Discounted cost (3.5%)
Cost (£m)	4	9.1	40.4	31.5	85	78

Therefore, given the estimate of primary benefit (£843m) and secondary benefit (£240m) over ten years, the programme, at a cost of up to £85m (£78m discounted) still delivers a significant return on investment and excellent Value for Money. It should be noted that no benefit is derived during the live programming period. This is due to conservative assumptions that the impact of the policy reform we are seeking to achieve through the programme will take several years to materialise. In reality, we expect to derive some benefit, including commercial, earlier than this, based on the China network’s previous programming experience.

UNQUANTIFIED BENEFITS

To ensure the viability of the primary and secondary benefits of the programmes, most of the benefits were quantified based on robust modelling including calculations, available statistics and assumptions. However, some of the benefits resulting from the programmes may be unquantifiable due to the lack of data or due to their complexity to quantify. These benefits are described below:

China Business Environment – In the appraisal above, the primary and secondary benefits arising from the programme (by reducing legal and regulatory uncertainty and improving the transparency of conducting domestic and international business) were quantified as far as possible. Additional primary or secondary benefits, such as those that may arise from wider systemic improvements to the regulatory and legal environment, or opportunities for UK professional and legal services firms, have not been included in the quantitative analysis due to the difficulty of proving causality between the outputs and impacts, lack of available data in this area.

Financial Services - In the appraisal above, the primary benefits (transition to a more effective regulatory environment for financial services to promote sustainable growth) and secondary benefits (increased access to the Chinese financial market for UK and international companies) arising from the programme were quantified. Other primary benefits from the programme that have not been quantified include increased financial inclusion, increased access to finance for SMEs, and improved transparency. Additional secondary benefits include improved access for international/UK firms to other sectors due to an improved general business environment in the financial sector, and opportunities for international/UK professional services and financial services firms. These have not currently been included in the quantitative analysis due to the difficulty of proving causality between the outputs and impacts, and the lack of available data in this area.

Energy and Low Carbon Economy – In the appraisal above, the primary and secondary benefits arising from increased uptake of clean and bridging technologies in China were quantified. The other strands of the low carbon programme relate to reform of the power sector, incorporating climate risk into decision making, improved low carbon standards and governance for investments, and more ambitious climate policies. This strand of the programme will also bring both primary benefits (including avoided CO2 emissions, improved air quality and public health) and secondary benefits (including reputational benefits for UK energy firms/experts from being able to showcase UK leadership in complex energy problem-solving), but these were not included in the quantitative analysis due to the difficulty of proving causality between the outputs and impacts, and the lack of available data in these areas.

Infrastructure – In the appraisal above, the primary and secondary benefits arising from increased efficiency China’s overseas construction projects and increased trade/bilateral relations between the UK were quantified. Other benefits from this strand of the programme that have not been quantified include higher safety and welfare standards for construction workers, better quality infrastructure delivered in partner countries, and improved environmental sustainability in partner countries.

The other strands of the infrastructure programme focus on policy reform and PPPs in domestic China. These strands of the programme will also bring both primary benefits (including increased job creation due to a more open and efficient construction sector, and higher standards for construction projects in China which will have benefits for the welfare and safety of employees) and secondary benefits (including increased opportunities for international and UK construction firms and consultancies due to a more open construction sector and improved international business links) was not included in the quantitative analysis due to the complexity of quantifying these benefits, and the lack of data available in these areas.

ANALYSIS OF OPTIONS

So far, this appraisal case has quantified the likely benefits and costs of the proposed programme. This quantification is a base-case. The final benefit and cost levels are likely to be influenced by the delivery mechanism chosen and the associated control and risk level. As such, this options appraisal assesses a number of plausible delivery options below based on a set of additional criteria, and an assessment of whether the option is likely to lead to benefits above/below/in line with the base case.

1. The additional criteria are:
  1. Value for Money – Delivering the required quality services at the best value.
  2. Adaptability - Retaining the ability to be flexible, move quickly to grasp opportunities and respond to emerging priorities/learning
  3. Capability and capacity – Ensuring access to supplier(s) with the correct mix of expertise, contacts and networks to meet requirements. FCO having the right contract management plans, skills, resources and management information to manage contracts when they are let
  4. Control over risk and delivery – level of control retained by Embassy/HMG over the delivery and direction of the programme

Delivery Options

1. Option 1 – Do Nothing
  1. A base-case which assumes business as usual in China and beyond. Specifically, this means that China will meet its target to achieve some degree of internal structural reform to meet major challenges outlined in this business case, as well as continue external investment in other poorer countries.
  2. Under this option, the pace of inequality reduction in China and beyond; the pace and direction of domestic structural reform (e.g. the degree to which financial markets are liberalised would be slower); and the long-term sustainable impact of external investment would all differ from the other options set out below. The growth of the economy would be in line with IMF forecasts.
  3. From a UK perspective, we would expect export and investment levels to China to remain broadly on-trend in the coming years, with UK market share remaining stable.
  4. All the results set out in the Appraisal Case are additional to this business as usual, status-quo scenario. Put another way, for the purposes of estimation and comparison, we assume zero results from this option.
2. Option 2 – Fully Contracted-Out Model
  1. This option would involve allocating £85 million to external implementers who would be tasked with developing programmes to target the key results outlined in this business case. Existing FCO China programme teams would develop statements of requirements for these contracts and procure services through a small number of competitive tenders (one per programme), with the supplier for each programme able to sub-contract as appropriate. In line with the UK’s commitment to untied aid, suppliers could be British, Chinese or from another part of the world – the strength of their bid would be key.
  2. Existing teams would maintain focus on their other programmes, limiting their engagement with stakeholders, and have minimal involvement in programme delivery.
3. Option 3 – HMG Partnership Model (Preferred Option)
  1. This option would involve allocating up to £85 million to the FCO in China to deliver bespoke new programmes for China Business Environment, Financial Services, Energy and Low Carbon Economy and Infrastructure through a private and third sector partnerships model. The programme teams would be responsible for designing the programmes and would lead the competitive procurement processes for appointing the lead supplier. It is envisaged that there would be a single overall supplier per programme, who may lead a consortium, or a group of sub-contractors, to deliver the requirements of the programme.
  2. In contrast to Option 2, HMG would be closely involved in the day to day management of the programme – setting strategic direction, consulting with stakeholders in government and business and making operational decisions. This role would involve working alongside a lead supplier (programme manager) who would be responsible for the resourcing and oversight of frontline activities and the delivery of programme results.
  3. The China Network would provide wrap-around diplomatic and commercial support for each of the programmes, meaning links to the UK would be emphasised strongly. China Network staff would play a strong role in engagement with key stakeholders, in particular the Chinese authorities, as well as programme delivery and reporting. Based on the China network’s experience, providing significant wrap around support is the best way of maximising the programme’s chances of success, since the Chinese authorities are not accustomed to working with third parties acting on behalf of HMG.
  4. A proportion of the funding (as set out in the Commercial Case) would be retained by the Embassy teams to be deployed more flexibly - in order to respond to changing circumstances or emerging priorities, and to allow for funding that is outside the capabilities or responsibilities of the lead suppliers. This would primarily be procured via competitive tendering, although grants and MOUs may also be used on occasion.
  5. The unique political-economic environment of China means that the ability to respond flexibly will be key. Equally, the policy-facing nature of these programmes means there will be significant elements of these programmes that we simply cannot channel directly and solely through commercially procured private sector companies.

1. Option 4 – Multilateral Delivery Model
  1. This option would direct up to £85 million to an appropriate multilateral partner such as the World Bank or UNDP (in China) to deliver results in the four programmes.

Comparison of Options

As noted above, four criteria have been used to score the various options ­ - value for money; adaptability; capability and capacity; and control over risk and delivery.

With regards to Option 1 – the ‘do nothing’ scenario – as has been noted before, while it is likely that China would achieve some degree of structural reform to meet major challenges, several future challenges – such as urban poverty and improvement of Chinese business activities in poor countries – may not be addressed for a great deal of time, both due to their complexity and difficulty in management and enforcement. In addition, it is less likely that China would utilise UK models or ideas to solve major challenges, or that UK businesses would link into or benefit from these reforms.

It is therefore clear that Option 1 would not deliver the primary or secondary results which these programmes are pursuing. UK may then be able to focus resources on addressing China’s challenges through other instruments. However, currently there are no such alternative instruments beyond those discussed in this business case. Scoring low against all four criteria, Option 1 is rejected.

Value for money. From an economy perspective, Option 4 (Multilateral) is likely to be the lowest cost, using existing multilateral infrastructure, networks and services to deliver the programme and with a small HMG requirement. However, in terms of the primary and secondary objectives of the Fund and the efficiency and effectiveness of the instrument, option 4 is likely to be the weakest, with limited ability to deliver on UK priorities in particular. Option 3 (HMG Partnership) is likely to be more costly than Option 2 (Fully contracted out), as more HMG staff will be required to support this route, but it holds higher potential to be effective, as HMG experience will be much more closely involved in shaping and operating the programme.

Adaptability. Option 2 (Fully contracted out), offers the lowest potential to respond to changes in the operating environment. Whilst this could be addressed to some degree by incentivising the flexibility of suppliers, without strong HMG direction and involvement, this may be difficult to secure. The assessment is similar for the multilateral Option 4 (Multilateral), which would need to be governed by a well-defined terms of reference that may take time to adjust and consider resourcing implications. Option 3 (HMG Partnership) is the most adaptable, due to the close involvement and direction of HMG.

Capability and capacity. In all options, the access to skills relevant to the primary purpose is likely to be very good. By design, it will be a requirement of any contracting arrangement that the global good capacity is top quality. Option 4 (Multilateral), in particular represents strong opportunities to benefit from international lessons and experience. From a secondary benefit perspective, experience relevant to UK business in particular is likely to be weaker in Option 4 (Multilateral). Indeed, it is not common practice for multilaterals to pursue objectives outside of the development of the host country or the generation of global public goods. Option 2 (Fully contracted out) and 3 (HMG Partnership) offer more scope to build in an international business, including UK, element through contracting mechanisms. However, the greater involvement of HMG under Option 3 (HMG Partnership) would strengthen this capability, bringing a government perspective – particularly important in the Chinese context.

Control over risk and delivery. Option 3 (HMG Partnership) offers more control over risk – both its realisation and a changing HMG appetite for risk – and delivery than other options. Option 2 (Fully contracted out), and 4 (Multilateral) are more arms-length, reducing scope for HMG to shape direction on a regular basis and with less oversight of potential risks such as problems with sub-contractors, finance being spent badly.

A summary of these comparisons against the criteria is shown in the table below:

Option	Value for money	Adaptability	Capability/ capacity	Control over risk
1 – Do nothing	Low	Low	Low	Low
2 – Fully contracted out	Medium	Low	High	Low
3 – HMG partnership	High	High	Medium	High
4 – Multilateral	Medium	Low	High	Medium

This comparison clearly suggests that Option 3 (HMG Partnership) is preferred and should be selected.

Consideration of Other Approaches

Contracting a single supplier for the entire £85m programme has been ruled out for a number of reasons. The scope of the programme is too complex for any one supplier to adequately manage and deliver. There is a need to maintain an element of control and direction in order to maximise impact given the secondary benefit sought, which is less suited to a single contract. Precise expertise and therefore precise consortia will be required for the different programmes. Splitting implementation by programmes limits our exposure to any single organisation, avoiding an unnecessary level of implementation risk.

FCO-led delivery of the whole programme was judged not to be practical, as the FCO does not have sufficient capacity, experience or expertise to deliver a programme of this scale and complexity. It would also not be in line with the Ministerial steer towards the programme being outsourced.

Consideration was also given to the FCO managing multiple sub-contractors. This approach would bring with it the advantage of giving us a greater say in who would be delivering each element of the programme, and greater control over its delivery. However, the Prosperity Fund Management Office’s (PFMO) firm view ahead of submission was that avoiding ‘fragmentation’ and keeping HMG head count low was paramount. They judged that managing a series of sub-contractors would be difficult and would require additional HMG staff resources, which in their view would not represent sufficiently good VFM. It would also place greater delivery risk on the FCO. As such, the preferred HMG partnership option outlined above seeks to allow us the flexibility to manage a small number of projects and activities separately, whilst still outsourcing the vast majority of the management and delivery burden onto our suppliers.

Consideration was given to the option of delivering the programme through a large portfolio of small projects. The China network has extensive experience of taking this kind of approach to deliver programmes of up to £12 million per year, with excellent impact achieved. However, the high ratio of staff needed to manage it makes it impossible to manage within or even close to the existing bench mark on staffing. Nonetheless, this approach does have significant benefits in terms of what can be achieved with a relatively small investment in the right intervention and with sufficient HMG support. Our preferred option aims to capture these benefits whilst still achieving VFM.

THEORY OF CHANGE FOR THE PREFERRED OPTION

The Figure below sets out the full theory of change for the preferred Option 3. To note, that the Theory of Change also presents how Phase Two (Health, Global Partners) and Phase Three (Urban Climate Change) of the China programme would contribute and complement overall prosperity objectives in China.

PORTFOLIO THEORY OF CHANGE SUMMARY DIAGRAM

Global economic/financial stability; greener environment
APPROACH TO INTEGRATING GENDER AND INEQUALITY INTO THE PORTFOLIO

The potential to address issues of gender inequality is set out in each of the sectoral summaries in the Strategic Case.

In addition, each of the programme teams will work with all suppliers and partners to ensure that activities supported by the programmes are gender and equality sensitive, and in compliance with the Gender Equality Act (GEA), where possible going beyond empowerment to support transformative outcomes. This means that programme design will take into account the different ways activities may impact men and women and disadvantaged groups more broadly. The development of gender and inclusivity strategies will be a key selection criterion for suppliers.

Activities to support the mainstreaming of gender and inclusivity into each of the programmes may include:

MEASURES TO STRENGTHEN THE GENDER AND INCLUSIVITY CONTRIBUTION
Measure	Description
Gender analysis and impact / Assessment	Bidders (at tender stage) required to submit a preliminary gender equality assessment (including consultation with women’s groups) outlining how they propose to address gender issues in the programme design. All contracted delivery partners contractually required to address gender equality. Assessment of potential interventions from a gender/inclusive perspective before finalising individual programme plans.
Capacity building and gender / mainstreaming skills	Ensuring that suppliers have appropriate gender/inclusivity skills-sets and that this capacity can be built and shared with wider partners. / A gender expert will be involved at appropriate stages to ensure the programme continues to maximise the opportunities to deliver gender equality / Internal gender and equality training will be carried out; a gender and equality champion (internal) will be identified
Monitor and evaluate against / gender impacts	Where feasible, suppliers and programme teams will be required to collect gender-disaggregated data and include specific indicators on gender in their log frames
Gender involvement and / consultations	Where appropriate, women and other excluded groups will be included in programming discussions and with partners as activities are undertaken and monitored, to consider the impact of the interventions on them

OUR APPROACH TO VALUE FOR MONEY

The China Prosperity Fund programmes covered in this business case have been designed with a strong focus on value for money (VFM), with particular thought given to an efficient means of delivering both long-term, structural change through on-going activities, complemented by more responsive activities that remain tightly linked to the systemic change aimed for.

The economic appraisal shows a high return for the programme both on a primary and secondary benefits basis. It estimates primary benefit (£843m) and secondary benefit (£240m) over ten years. As such, the programme, at a cost of £85m (£78m discounted) delivers a significant return on investment and excellent VFM. This conclusion is based on conservative assumptions and evidence of the impacts of other similar programmes.

VFM will be a central factor in the active approach to programme management that will be taken. Complemented by a robust monitoring and reporting system (see Management Case), it will be a requirement that our partners and suppliers ensure that resource is directed to those activities which are shown to generate the most impact and deliver good value for HMG. This may involve scaling certain activities up or down, depending on performance. VFM indicators will be a key reporting requirement provided to the China Prosperity Fund Advisory Board (chaired by the China Portfolio Senior Responsible Officer (SRO)).

VFM will be measured on an on-going basis at the programme level, drawing on the log-frames developed for each of the programmes. These will be further revised and developed during the design/inception period for each programme, and in collaboration with the teams appointed to undertake monitoring and evaluation.

Input costs will be measured in order to ensure that they do not exceed market rates. They are not generally expected to decline during the life of the programmes, but rather are likely to increase in line with wage growth. Each programme will continually appraise which activities are working most effectively and adapt accordingly, while also taking into account the expectation that benefit trajectories will differ depending on the type of intervention. Drawing on best practice from DFID’s VFM paper on the fourth ‘E’ – Equity, indicators will also be disaggregated by sex to allow some assessment of equity.

In addition to comparing VFM indicators between and within programmes, external benchmarks will also be monitored as data allows. This will include similar programmes delivered by other donors. As such, the China Prosperity Fund Advisory Board will be better positioned to drive performance and present a strong VFM case to the Prosperity Fund Portfolio Board, demonstrating the internal value of the China PF portfolio and its performance relative to others across the Fund.

Base lining will be undertaken during the transitional period and refined during the design/ inception phase of each programme as part of the approach to monitoring and evaluation. The benchmarks denoting poor value for money for each programme will also be developed and refined further during the design/inception phases of each programme. In the event of these occurring, the FCO will consider significant modification to the programme course, strategies and partnerships, including the option of stopping funding for the relevant initiative.

Metrics for the monitoring of VFM will be developed through consultation with lead suppliers and will be tailored to each programme. Indicative general measures (based around DFID’s “4Es” understanding of VFM[76] (Economy, Efficiency, Effectiveness and Equity) are outlined in the table below.
[76] See for example, DFID programmes LASER, SPRING, Business Innovation Facility.

VFM INDICATORS
Economy / (securing inputs at the best value)	Efficiency / (inputs to outputs)	Effectiveness / (outputs to outcomes)	Equity
Unit costs (daily rates) of contractors and/or average fee rates across the components / Ratio of locally-sourced expertise vs international / Supplier management fees. / Unit costs of key products and services, such as research reports, workshops, knowledge management systems/products etc. / Overheads as a % of total spend / Total unit costs of technical assistance delivery (including overheads, delivery costs, expenses, etc.) / Number of subcontracts competitively advertised	The volume of relevant stakeholder funds and resources leveraged, both public and private, for every pound of funding; / Percentage of projects/products rated ‘very good’ or ‘excellent by end user / Average time/engagement intensity needed to convert activities into outputs / The cost of new products developed (e.g. evidence products, delivery plans, bespoke toolkits, business/financial models); / Productivity gains realised in supported firms for every pound of funding.	Policy recommendations adopted; / Jobs created/incomes raised linked to the intervention; / UK commercial wins linked to the intervention; / Cost per law changed/stakeholder influenced/business reached	Proportion of male to female contractors/consultancy days / Salaries/rates funded by programme (e.g. highest to lowest, junior to senior) / Proportion of men vs women, old vs young who participate in programme activities / Cost of any adjustments needed to make training accessible for each gender, people with disabilities, people from poorer region, other marginalised groups

COMMERCIAL CASE

INTRODUCTION

The Commercial Case sets out the procurement strategy and delivery mechanisms by which the programme’s objectives will be achieved. It follows on from decisions taken in the Appraisal Case about the best approach to doing that. In so far as it is possible, the case is organised sequentially - starting with the programme delivery, ensuring value for money and due diligence, market analysis, securing suppliers, performance measures, key contract terms and risk management. It will also set out the process to ensure delivery partners comply with the requirements of the International Development Act 2002 (IDA), and the Gender Equality Act 2014 (GEA), and how the interventions will promote gender equality.

PROGRAMME DELIVERY

Phase One of the China Prosperity Fund portfolio consists of four programmes: China Business Environment; Financial Services; Energy and Low Carbon Economy and Infrastructure. In all programmes, the main mechanism for delivery, constituting the biggest part of the total budget, was to appoint a single supplier (who may or may not be working with sub-contractors or consortia partners) to design and deliver the majority of each programme’s outcomes and activities.

The other mechanisms by which these programmes are delivered are an ad hoc contracting facility (up to 10% has been committed to support agile and reactive programming at the individual programme level – smaller contracts, self-implemented activities, grants or Memorandum of Understanding (MoUs). These mechanisms are following FCO general procurement policies, and are not covered in this commercial case.

China Business Environment

The China Business Environment programme will support progress towards a stronger rule of law, focusing on five policy areas: standards, investment environment, anti-money laundering, intellectual property protection and commercial dispute resolution.

The Programme consists of three contractual components including a) Main Component, b) Standards Component and c) Investment Environment Component. As set out previously, the unique political-economic environment of China means that the ability to respond flexibly will be vital. While the Main Component was procured via the Prosperity Fund (PF) Framework, the programme also deployed open tender and agreed MoU as alternative routes to select suppliers with specialist expertise and strong China experience to deliver the programme objectives. The table below outlines the three contractual components and respective procurement route. The suppliers are required to work with each other and develop synergies to deliver the overall programme impact and ensure an integrated programme.

Component	1 – Main Component	2 – Standards Component	3 – Investment Environment Component
Procurement Route	PF Framework	Open Tender	MoU
Supplier	PricewaterhouseCoopers LLP	British Standard Institute	World Bank
Policy Areas	Anti-Money Laundering / Commercial Dispute Resolution / Intellectual Property / Investment Environment	Standards	Investment Environment

The Investment, Infrastructure and Operations Committee (IIOC) endorsed the recommendations of preferred suppliers for the Standards Component and Investment Environment Component on 22 May 2019. Thus this commercial case sets out only the procurement strategy and delivery mechanism by which the objectives of the Main Component will be achieved.

The programme procured PricewaterhouseCoopers LLP (PwC) as the preferred supplier to design, deliver and manage a technical assistance programme to improve the business environment in China, under its main component. The programme will run to March 2022, with the possibility of extension.

The overall impact of the Main Component is to promote 1) sustainable and inclusive growth through more robust commercial dispute resolution mechanism, stronger controls on money laundering, improved investment environment and intellectual property rights protection; and 2) increased trade and investment cooperation between China and international (including UK) cooperation. Through these two objectives, the Main Component will meet the primary purpose and secondary benefits of the Prosperity Fund.

The intended outcomes are listed below:
  1. Improvement in the predictability, accessibility, efficiency and enforceability of commercial dispute resolution outcomes and more consistent commercial dispute resolution legal framework.
  2. Improvement in the effectiveness and enforceability of China’s anti-money laundering policies and court judgements.
  3. Improvement in the fairness, transparency, predictability and  competitiveness of the investment environment.
  4. Improvement in the predictability, accessibility, efficiency and enforceability of IP court judgements and legal framework.

Financial Services

The Financial Services programme will work in areas where the UK has expertise to promote financial sector reform through sharing policy and private sector expertise, and capacity building in the Chinese regulatory sector, to enable a transition to a more efficient, productive, inclusive financial services sector.

The programme focuses on five policy areas, including: (I) financial stability & regulatory reform, (II) financial technology (fintech), (III) insurance, (IV) pensions and (V) financial inclusion. These have been developed through rigorous analysis, scoping and consultation with Chinese and UK government, regulatory, business and academic research stakeholders.

The programme procured Deloitte as the preferred supplier for the main part of the programme to design and implement a 3-year technical assistance programme on financial services in China, in consortium with Palladium and Tsinghua Centre for Finance and Development. The programme will run to March 2022, with the possibility of extension.

Component	1 – Main Component	2 – Financial Inclusion Component
Procurement Route	PF Framework	MoU
Supplier	Deloitte LLP	International Finance Corporation
Policy Areas	Financial stability & regulatory reform / Fintech / Insurance / Pensions / Financial Inclusion	Financial Inclusion

The Financial Inclusion component listed above will be delivered under a MoU, therefore it has not been included in this commercial case. Thus, this case sets out only the procurement strategy and delivery mechanism by which the objectives of the Main Component will be achieved.

The overall impact of the Financial Services programme is intended to be (1) a more effective regulatory environment for financial services to promote sustainable and inclusive growth in China, and (2) increased trade and investment cooperation between Chinese and international (including UK) businesses. Through these two objectives the programme will meet the primary and secondary benefits of the Prosperity Fund.

1. The intended outcomes are listed below:
  1. Regulatory effectiveness and predictable environment: More market-driven, transparent approach to regulation with more effective and efficient regulation design and decision making processes, reducing systemic financial risk.
  2. Regulatory innovation and increased competition: More innovative regulators use pilot initiatives to support the introduction of better products and services. Increased competition and level playing field for domestic and foreign entrants, including UK firms.
  3. Sustainable growth and resilience: Revised regulatory approach encourages market growth of responsible saving and investment, and better financial resilience through incentivising pensions and insurance markets development.
  4. Inclusion and access to finance: Improved access to financial services for underserved populations in Chinese society, plus more supply of better financial products by leveraging fintech as a technological enabler.
Energy and Low Carbon Economy

The Energy and Low Carbon Economy programme will match China’s specific reform needs with UK energy and low carbon strengths, reducing global emissions by accelerating China’s energy transition. It will focus engagement across four policy areas: clean technologies; supporting the effort to bridge from coal to a low carbon energy system; system reform and risk; and international governance and engagement.

The programme will be delivered through two channels: (1) A Prosperity Fund Framework call off tender of a supplier for the Energy Component and (2) a Direct Award to Chatham House for the Climate Risk Component.

Component	1 – Energy Component	2 – Climate Change Risk Assessment Component
Procurement Route	PF Framework	Direct Award (Single Source) / Commercial Contract
Supplier	ICF Consulting Services Ltd	Royal Institute of International Affairs (Chatham House)
Policy Areas	Clean technology / Bridging transition / System reform and risk / International governance and engagement	System reform and risk

Part 1: Energy Component

The Energy Component procured ICF International as the preferred supplier to deliver the services that collectively provide the advisory, administrative and management services necessary to achieve the portfolio of technical assistance activities. The component will run to March 2022, with possibility of extension.

The Energy Component will be delivered through a Fund Management model which is specifically designed to operate within the unique characteristics of Chinese political economy, ensure HMG can work with the appropriate UK and Chinese expertise and ensure the UK is flexible and responsive to China’s rapidly evolving energy policy environment.

The overall impact of the Energy Component is intended to be (1) accelerate China’s low carbon transition and reduce greenhouse gas emissions; (2) increase the sustainable and inclusive deployment of clean energy technologies at lower costs; and, (3) expand China’s green goods and services and create opportunities for international partners, including the UK. Through these three objectives the Component will meet the primary and secondary benefits of the Prosperity Fund.

The intended outcomes are listed below:
  1. Adoption of market, finance and technology policies and regulations that support the transition to a low carbon growth model, level the playing field, and manage related systemic risks.
  2. Introduction of more cost-effective development and deployment of clean energy technologies and infrastructure to reduce GHG emissions.
  3. Implementation of ambitious actions for more transparent engagement with international climate change and energy governance structures.
Part 2: Climate Change Risk Assessment Component

1. Whilst funded by the Prosperity Fund, the highly specialist, expert and political nature of the Climate Risk Component means that the deliverables required were beyond the capabilities of the organisations on the PF framework, as indicated by the market engagement. The Project required a lead organisation to (a) lead and (b) programme manage a coalition of UK and Chinese experts from across the areas of policymaking, research and business. The lead organisation was required to have:
  1. A proven track record of working with UK and Chinese government officials and experts on climate risk and attendant issues up to Vice Minister level;
  2. Proven convening, representational and programme management capabilities; and
  3. Proven ability to work on sensitive and political issues free from conflicts-of-interest or commercial interests.

As a result of the requirements, the Climate Risk Component was awarded to Chatham House in November 2019 to design and implement a 3-year technical assistance programme on climate risk with China. The component will run to March 2022, with possibility of extension.

The overall impact of the Climate Risk Component is that emissions reduction and resilience strategies and policies in both China and elsewhere in the world are fully informed by a perspective on climate change risks that is incorporated into all levels of decision making; and that international organizations working on issues of global concern use appropriate climate risk indicators in the planning, conduct and monitoring of their work.

1. The intended outcomes are:
  1. Enhanced awareness and understanding of the dimensions of climate risk among decision-makers globally, and within a select group of key international organizations and strategic planners in the Chinese government.
  2. Better institutional and national planning to address emissions, direct and systemic Climate Risks through the incorporation of indicators of Climate Risk into planning, monitoring and programme management in the Chinese government and in international organizations.
  3. The development of knowledge communities working on Climate Risk in China and the UK that are supportive, engaged, and able to provide policy relevant recommendations on Climate Risk.
  4. UK corporate partners to be involved throughout the process to help shape and progress business contribution in areas where the UK has a strong commercial expertise.

Infrastructure

The Infrastructure programme will promote the involvement of international best practice in design, engineering, financial, professional and legal services, and environmental and social standards in Chinese-led infrastructure projects, facilitating and raising standards in growth-enhancing infrastructure projects in developing countries.

The programme procured KPMG as the preferred supplier to design and implement a 3-year technical assistance programme with China on Chinese-led infrastructure projects in Africa and developing Asia. The programme will run to March 2022, with possibility of extension.

Component	1 – Main Component
Procurement Route	PF Framework
Supplier	KPMG

The overall impact of the Infrastructure programme is intended to be (1) inclusive growth and poverty alleviation in ODA-eligible partner countries through cooperation with China on Chinese-led infrastructure and (2) increased infrastructure trade and investment cooperation between Chinese and international (including UK) businesses. Through these two objectives the programme will meet the primary purpose requirements of the Prosperity Fund, and deliver secondary benefits.

The intended outcomes are listed below:
  1. Long-term, structural improvements in the delivery environment to facilitate more sustainable, inclusive, commercially viable and higher quality infrastructure projects that contribute to poverty reduction.
  2. Pilot projects developed which successfully integrate international and Chinese expertise and best practices to increase project sustainability, inclusivity, commercial viability, quality, and poverty reduction potential.
  3. Increased international private capital investment into infrastructure projects.
  4. Increased cooperation between international (including UK) and Chinese firms on infrastructure projects.

ENSURING VALUE FOR MONEY AND DUE DILIGENCE

Value for Money

1. Value for Money (VFM) has been one of the criteria used throughout the process in order to ensure alignment with HMG and Prosperity Fund standards. It has also been taken into consideration for the procurement route and the evaluation criteria:
  1. Economy, efficiency, effectiveness and equity (the ‘4Es’ model)
- Rates were benchmarked against other programme frameworks, including CSSF and DFID frameworks. As these are maximum day rates, we expected that through further competition, better VFM was achieved. As these are maximum day rates, the expectation is that through further competition, better VFM will be achieved. Suppliers were required to set out the breakdown of supplier overhead costs, including profit in the bids.
- The Most Economically Advantageous Tender ("MEAT") was used in the process twice. Prices were tested within the Framework competition, providing balance of quality versus price and a second time, during the Call Off procedure, where the MEAT was used as a baseline to score bids;
- The selected supplier demonstrated the proposal appropriately resources their team in terms of seniority, experience, quantity of days of contribution and effort to deliver the desired outputs;
- Proposals were found advantageous where it was proved that essential components could improve impact of the activities, local technical capacity or introduced Good Industry Practice into the sector.

Due Diligence

Under the Framework Award process, initial due diligence of potential suppliers has been completed. The call off process provided for a call for further competition in a single stage evaluation process. Bidders needed to provide significant detail on their sub-contractor and consortium members within their bid as relevant and to provide assurance that they are fit in terms of financial standing and ethical and legal requirements to provide and deliver services to HMG .

Where the Framework has not been used - open procurements, grants and MoUs - standard procedures on carrying out due diligence have been followed. This included consultation with FCO Commercial and the FCO’s Policy Programme Transformation Unit, as well as DFID’s Commercial Relationships team (as appropriate).

MARKET ANALYSIS

Market Engagement
This section outlines the engagement the all programmes undertook to assess whether the market had the capability, capacity and motivation to deliver the services required, as well as the bids received.

1. All programmes engaged with over 20-30 potential implementing partners and beneficiaries from September 2016 through to November 2018, with key market engagement events including:
  1. Programme-specific workshops for potential suppliers in the UK and China;
  2. Prosperity Fund Market Engagement Day in London for Framework suppliers and other interested bidders;
  3. One to one supplier engagement in Beijing to test and refine the requirements set out in the Statement of Requirements (SoRs).

The market engagement events indicated that there was sufficient private sector interest in delivering the services required to achieve the outcomes and outputs set out in the Strategic Case for each of the programme’s main components. This interest was both at a global (Framework Agreement) level and at local supply chain level. Engagement also identified that these bodies were used to working together in China as consortia or as prime contractors/sub-contractors.

However, the results from the market engagement demonstrated that the Climate Risk Component of the Energy and Low Carbon Economy programme required consideration for a direct award as an alternative procurement path that would better meet the objectives.

It should be noted that during the procurement process, the FCO renamed the programme Rule of Law for Business to China Business Environment to better reflect the nature of the requirement. The initial procurement that was run for Rule of Law for Business Programme resulted in the Authority exercising its right not to award as the Authority determined that the requirements set out in the SoR had changed sufficiently that the most appropriate course of action would be to retender the requirement.

Recommendations that arose from the market engagement events were incorporated into the SoR, where applicable.

Bidders

As indicated by the market engagement events undertaken, all programmes received considerable interest from Framework suppliers in bidding for these opportunities. The bids received are detailed below per programme.

Business Environment: The Main Component received two bids. Both bids were compliant based on compliance checks, which was satisfactory. It should be noted that there was four bids for the original Rule of Law for Business procurement. The Authority was content with just two bids for the retender given that they were from the two highest scoring bidders based on the evaluation of the initial bids for the first Rule of Law for Business ITT.

Financial Services: The programme received two bids, both of which were compliant based on the initial compliance checks, which was satisfactory considering only seven of the fifteen possible suppliers have offices in Mainland China. Framework suppliers who did not bid indicated this was due to other commitments and PF priorities, as well as one interested supplier who specified issues with elevated costs associated with operating in China that did not suit the global day rates they had submitted to the Framework.

Energy and Low Carbon Economy: The programme received three bids, which were all compliant based on the initial compliance checks, which was very satisfactory. Framework suppliers who did not bid indicated this was due to other commitments and PF priorities.

Infrastructure: The programme received five bids, which were all compliant based on the initial compliance checks, which was very satisfactory. Framework suppliers who did not bid indicated this was due to other commitments and PF priorities.

SECURING IMPLEMENTORS

This section details how the main advisory, management and delivery contracts for each programme’s main suppliers were procured through the PF Framework. It sets out how and why the Framework was used and how Statements of Requirements (SoRs) were drawn up.

Delivery Model

1. The Appraisal Case considered four options for delivering the programme’s objectives, including:
  1. Do nothing
  2. Fully contracted out model
  3. HMG partnership model
  4. Multilateral delivery model.

It was concluded that option three, HMG partnership model, was the preferred delivery model as it would provide good VFM, adaptability, capability/capacity and control over risk. Please see the Appraisal Case for further rationale.

Procurement Route

Two procurement options were considered by the programme teams in order to procure the suppliers for the main Advisory, Management and Delivery contracts for each programme:
  - Prosperity Fund Framework
  - Full open competition, following the OJEU process.

Undertaking four call-offs (one each for China Business Environment, Financial Services, and Energy and Low Carbon Economy, and Infrastructure) from the Prosperity Fund Framework was assessed as the most appropriate option for the procurement of the main suppliers.

1. Use of the Framework as the main sourcing route offered a number of advantages:
  1. Due diligence was carried out on each supplier centrally and procurement timescales were significantly reduced as a result;
  2. There was improved VFM on rates and costs;
  3. Suppliers were not required to identify their consortium or sub-contractors to bid for a place on the Framework. This meant that flexibility was retained for the suppliers to identify their supply chains to meet specific local requirements as and when they arise.

The Framework set out key contractual terms which the suppliers were required to adhere to. The Framework is managed robustly by the FCO PF Commercial Team in London.

The Tender Notice stated that bids would be welcomed both from single agencies (with or without sub-contractors) and from multiple agencies joining up to form partnerships or consortia. In the case of a consortium partnership, a single contract would be issued to the lead consortium partner who will be responsible for managing other partners. It would be at the discretion of bidders on how to structure any consortium or supply chain, where performance of particular functions or provision of specialist expertise is required and subject to the programme design.

1. The PF Commercial team undertook the procurement on behalf of the programme teams to procure one managed service contract using the following lots:
  1. Business Environment: Lot A1 Business Environment
  2. Financial Services: Lot A2 Finance Trade
  3. Energy and Low Carbon Economy: Lot B3 Energy
  4. Infrastructure: Lot B1 Infrastructure

Creating the Statements of Requirements (SoR)

The scope of activity to be undertaken for each programme was defined in a detailed Statement of Requirements (SoR). The SoRs were written so as to ensure delivery of the programme outputs as described in this business case and allow for effective supplier management. We specified our required outcomes, impacts, and any minimum outputs. The SoR allowed scope for the implementer to input their own ideas as to how best to deliver the required outputs and outcomes, thus benefitting from their expertise and innovative outlook. The SoR included an explicit section on IDA and GEA compliance requirements.

The SoRs set out the requirements for two phases of each of the programmes. First, a Design Phase, which will involve detailed scoping and design of programme methodology, the delivery and finalisation of log-frames, MREL and detailed action plans and budget. Upon successful completion of the Design Phase, the supplier(s) will enter into the main Implementation Phase. Details are set out below.

Phase 1 – Design Phase:

This will scope out, prepare the ground for and delineate the final package of activities and deliverables. This will include refining existing intervention suggestions as well as offering innovative, practicable and timely ideas for interventions. The design phase will require advisory services to the FCO in order to finalise each programmes’ design and activities. Key outputs will include, but not limited to the following:
- A finalised Programme Delivery Strategy for the life of the programme, including situational analysis and the social and gender impact assessment;
- A detailed, costed annual outputs-based work plan for the first 12 months after the Design Phase, including an agreed list of early activities/outputs to be delivered, the output based work plan will be refined through an agreed process that will be set out in the contract with the FCO to ensure it is realistic and offers good value for money;
- Outline output based work plans for subsequent years. These will be agreed annually through an agreed process that will be set out in the contract to ensure they are realistic and offer good value for money;
- Revised/validated logical framework;
- Monitoring and Evaluation Plan (to demonstrate with quantitative and qualitative evidence progress against delivery of activities and outputs and their contribution to achieving the programme’s outcomes and impact);
- Supplier team structure to deliver the programme. Team members should be the same as those submitted in the contract tender. Any changes to team membership should be agreed with FCO and staff replaced should be the same or better calibre (in terms of knowledge, experience and skills).

Phase 2 - Operational Phase

This will implement the work plan agreed at the end of Phase 1 (Design Phase) to deliver each of the programmes’ objectives. The operational phase will require delivery services whereby the delivery partners will deliver the required interventions.

Will require management services in that the lead supplier for each programme will manage activities – and any additional suppliers or subcontractors that may be required for the successful delivery of the programmes on behalf of the FCO.

MANAGING SUPPLIERS DURING DELIVERY

This section outlines the main responsibilities of suppliers, both during the design phase and then in the main implementation phase. It sets out our approach to contract and payment terms at each stage, and contract management roles and responsibilities.

Suppliers’ Key Responsibilities

The main supplier of each programme will take responsibility for ensuring the aims and objectives of the programme are achieved as set out in the detailed SoRs (Phase 1 - design and Phase 2 - operational).

The main supplier will manage the delivery of activities, identification and disbursement of funds to any subcontractors and ensure compliance with FCO’s and the PFMO’s financial and management requirements, including MREL requirements. Key responsibilities will include:

- Assure the proposed programme activities for suitability against the Theory of Change and assess their likelihood to achieve programme outcomes.
- Implement the detailed, costed work plans, defined during the Design Phase, in such a manner as to ensure public funds are spent efficiently, effectively and honestly in order to implement programme activities that deliver of core outputs, realise desired outcomes and achieve the anticipated impact;
- Manage FCO funds, including where agree procuring third party delivery partners at project level or to deliver specific pieces of work;
- Monitoring and reporting on the programme performance against a milestone-based implementation scheduled agree with the FCO, and aligned with the detailed, costed work plans, defined during the design phase;
- Continuously demonstrate how the programme identifies and mainstreams diversity, equality and inclusion throughout design and delivery, including but not limited to actively promoting greater gender equality;
- Ensure lessons learnt from programme implementation are captured and disseminated externally (to relevant partners in the public and private sector) to ensure the sustainability of outcomes, and internally (to the FCO and other relevant departments) to ensure continual revision and improvement of programme delivery.

Contract and Payment Terms

The approach to the commercial model are milestone payments and fixed price elements where the detailed requirements provide for a level of risk sharing and incentivisation for suppliers.

The initial design phase has been set as a fixed price with a detailed set of requirements and quality measures provided within the Invitation-to-Tender (ITT), ensuring VFM for HMG and incentivising the supplier to deliver to time and quality.

Payments will be in line with HMG standards; payments terms and invoicing procedures as detailed in the contract documents.

Contract Duration for Framework Suppliers

The proposed timings for contracts are outlined below per each programme’s main supplier:

Stage	Timing
	Business Environment – PwC	Financial Services - Deloitte	Energy and Low Carbon Economy – ICF International	Infrastructure - KPMG
Contract sign, commence programme delivery	June – July 2019	June – July 2019	April 2019	March 2019
Inception phase	July – October 2019	July – October 2019	April 2019 – July 2019	March 2019 – June 2019
Implementation phase	November 2019 – March 2022	November 2019 – March 2022	August 2019 – March 2022	July 2019 – March 2022
Closure phase	October 2021 – March 2022	October 2021 – March 2022	October 2021 – March 2022	October 2021 – March 2022

The Call Off Contract will be let for the full Term with a review point at the end of the Inception Phase and a Break Clause in March 2021 to align with the UK Government’s Spending Review.

In the event that the contract does proceed to the Implementation Phase, the Authority will issue a contract amendment to include the details of the services to be provided in the form of updated Statement of Requirements, detailed costs and an output based payment plan as set out in Condition 18 – Changes of the Call off Terms and Conditions.

In the event that a decision is taken to terminate the programme, the Programme Director and the Authority’s Commercial Team will liaise with the Delivery Partner to determine the timescale for, and the most appropriate means of, termination in accordance with the Call Off Contract.

If agreed by both parties, this programme may be extended beyond the Term by up to an additional 24 months. Take up of any extension period is subject to the Authority’s written approval, the continuing needs of the Programme and additional funds being released over and above the current budget.

Contract Management

All staffing requirements for these programmes are included in the Management Case, as instructed by PFMO. The staffing and admin budget is benchmarked at 5% of the total programme budget allocation (originally 3.5%).

The programme teams will be responsible for managing the contract, and will be supported by the central team at Post and CPG. The Programme team has ensured that contract management resource is in place prior to contract award.

Programme managers will be responsible for:
  1. Rigorous day to day operational management including on-going due diligence, ensuring management information is received;
  2. Relationship management including working with stakeholders to support the supplier’s progress;
  3. Monitoring progress against Key Performance Indicators and Payment by Results mechanisms such as milestone payments, and reporting on these;
  4. Technical quality assurance for quality delivery;
  5. Managing contract variations;
  6. Maintaining contract documentation;
  7. Risk and benefit management;
  8. Contract reviews including cost review;
  9. Financial oversight;
  10. Escalation, issue resolution and conflict management;
  11. Mobilisation and exit management;
  12. Ensuring GEA compliance and technical QA for gender, poverty and inclusion.

Programme managers will be supported by expertise in the following as and when required:
  1. Intervention performance assurance
  2. Financial Management: their role will include monitoring supplier costs, modelling the impact of proposed significant variations, contributing to contract reviews and assessing financial reports
  3. Legal Assurance: their role will include drafting of variations and legal interpretation
  4. Commercial management and assurance e.g. VFM on contract variations

It should be noted that staff will be delivering these programmes and not simply managing them. The teams will provide diplomatic and commercial wrap-around support to the suppliers. To put it simply, the socio-political environment in China, and the policy facing nature of this programme, necessitates Embassy staff involvement. Whilst we will be contracting with sector specialists, the programme staff are the ‘China’ and ‘China government’ specialists that cannot be procured elsewhere. They are essentially delivering parts of the programme that cannot be done by any external supplier. This represents one of the key delivery risks to the programmes – that private sector suppliers will be unable to access Chinese government, and the programme teams (who can provide that access) are not sufficiently staffed to do so because they are limited by the benchmark outlined above.

PERFORMANCE AND REPORTING

Detailed reporting and monitoring requirements have been agreed between the suppliers and the Programme teams. Regular supplier meetings to discuss KPIs, VFM being achieved and performance will take place throughout the contract duration, and particularly at key stages of implementation, in consultation with programme team. Outputs from these discussions will also be issued to inform the Annual Review Reports. The programme manager will submit quarterly progress reports on the performance of the programme.

Type of meeting	Frequency	Attendees / recipients	Output
Programme management meeting	Annually	Programme Steering Committee	Annual Report submitted
	Quarterly	Programme Steering Committee	Quarterly Progress report submitted
	Monthly	Meeting between FCO Programme SRO and Supplier Programme Director	Monthly Financial Forecast submitted. Minutes and note on follow-up actions circulated
	Weekly / Biweekly	Meeting between FCO Head of Programme and Supplier Team Leader	Minutes and note on follow-up actions circulated

RISK MANAGEMENT

Management of Key Procurement and Commercial Risks
Each Programme SRO will be responsible for implementing a consistent and robust approach to risk management with suppliers.

Each programme will have a clear risk management matrix which addresses the seven risk categories; external, safeguard, operational, delivery, fiduciary, reputational and strategic.

The Central Team will maintain a portfolio level risk matrix and register – including those risks associated with suppliers.

Suppliers will be required to present and maintain a clear risk matrix and risk management process which will be revisited on a monthly basis between Programme Teams and suppliers.

Any evidence of fraud or corruption will be raised within 24 hours of being reported and will be taken to the Financial Compliance Unit.

Please see the Risk Register in the Management Case which includes wider commercial risks and a summary of how these will be mitigated.

FINANCIAL CASE

INTRODUCTION

This section covers the estimated financial implications of the programme, flowing from the indicative interventions set out in the Strategic and Appraisal Cases, the proposed delivery model explained in the commercial case, and the staffing requirements in the Management Case.

We are seeking up to £85 million of Prosperity Fund ODA funding up to 2021, divided between four programmes. Transitional Funding in 2017/18 has been allocated. A further tranche of Transitional Funding has been requested to pay for continued analytical work, technical assistance for business case/Statement of Requirement development, and strategic initiatives that give new programmes a head start, as set out in guidance.
PROGRAMME BUDGET

The initial projected budget allocation is set out below (up to 2021 only; programme now extended to 2022):

BUDGET ALLOCATION (INDICATIVE) 2017-2021. (ALL FIGURES IN £MILLIONS)

Programme	17/18	18/19	19/20	20/21	Total
China Business Environment	1	2.45	13.9	10.15	27.5
Financial Services	1	2.25	10	9.25	22.5
Energy and Low Carbon Economy	1	2.5	10.25	6.75	20.5
Infrastructure	1	1.9	6.25	5.35	14.5
TOTAL SPEND	4	9.1	40.4	31.5	£85m

The budget allocations and spend forecasts set out in this Financial Case remain indicative at this stage.

This timeline and likelihood that large scale Implementation will not start until at least the start of FY 2019, coupled with the proposed end date for the programme of 31 March 2022 (meaning no funding can be programmed beyond that date), means that there may be only around two years available for large scale outsourced delivery of the programmes.

As such, the need for flexibility - as set out in detail in the Commercial Case - is vital in allowing us to begin delivery earlier, thereby maximising the programming period available.

A full spend of the 2017/18 Transitional Funding will be achieved. The allocation that was approved was relatively modest – only £2.55 million (not including staffing/admin) of Transitional Funding for further business case development and pilots to be completed during FY17/18. The time frame was later extended by PFMO, meaning £350K of the original allocation will be carried forward into FY2018/19 and spent by 30 September. These elements are therefore not contingent on approval of this business case.

The Phase One staffing and admin allocation for 2017/18 received from PFMO was £984,000. This was received in May 2017. At the time of writing (March 2018) we are awaiting confirmation from PFMO about whether this allocation will be reduced to reflect Q1 costs being charged into the previous f/y (i.e. a full year salary costing being allocated but only required for 9 months).

The administration budget is forecast to total £6.7 million over the lifespan of the programme (based on staffing at Full Economic Cost). This equates to 7.7 per cent of the total budget. This includes the central programme functions (such as the Finance, Comms, Reporting, Strategy). As set out in the Management Case, Phase Two of the China programme (£55 million – currently at Strategic Outline Business Case stage) will require significantly lower staff costs (less than 3 per cent), as we will not need to replicate the central programme functions. Therefore taken together, the staffing budget is expected to be much lower as an overall percentage – currently forecast to be approximately 5 per cent of the total Phase One and Two budget.

The financial case does not include a provision for MREL.

The Financial Case does not include a provision for compensation for staff whose jobs are cut either during or at the end of the programme. However, the need for this contingent liability is included in the financial risk register. It is subject to further clarification from PFMO and PFDU on handling this Prosperity Fund-wide issue.

The Financial Case does not include a separate contingency budget. The Financial Case does not include a specific separate contingency budget. However, this is the purpose of the Flexible Funding (see Commercial Case).

Staffing and administration costs have been separated out and have been equally allocated across the four programmes.

Exact allocations together with budget timelines (including timing of key payments) will be finalised once procurement has been completed. Detailed activity-based budgets with full financial forecasts will be developed as detailed contracts and programmes are agreed.

A key focus of all programmes in the China portfolio is policy reform in China, with the Chinese authorities being key stakeholders for each one. It is not possible to accurately predict the pace and scope over policy reform over the medium-term, and as such there will remain some uncertainty over timing and exact levels of disbursements. Work plans and associated budgets will need a degree of flexibility to reflect this. We will closely monitor forecasts and spending against budgets as the programme develops.

Reallocations within the budget envelop agreed for each programme will be carried out in line with the relevant approval processes and spending authority limits.

How will this be funded?

1. Funding for this programme will come from £1.2bn Prosperity Fund announced by the Government in November 2015. Advice will be sought from PFMO on whether VAT will be chargeable given delivery is taking place entirely outside of the European Union. There will be no financial aid to governments.
2. The implementation of this programme will mostly be done through external implementers (primarily commercial contracts, though with the possibility of MoUs and grants too). Because of the nature of this work (services), a clear majority of external implementers’ costs will be personnel time costs (fees). Project implementation will also involve relevant reimbursable costs such as project-related travel and accommodation, events organising and other delivery-related costs. This will be in line with the requirements as set out in the Framework T&Cs, or in accordance with FCO guidance where applicable. Funding will also be required for HMG staff salaries, and we will also set aside a small amount for training and development of HMG staff managing the programme and overheads.

Any capital assets procured under this programme will be treated in accordance with FCO procedures and declared on an annual basis. Should assets remain at the end of the programme; an exit strategy will be agreed with FCO.

In the design/inception report to be delivered under each contract, suppliers will be required to set out a plan for exploring opportunities for co-funding from other sources, to maximise value for money for Prosperity Fund resources. Co-funding sources may include seeking to cooperate with other ODA funds, commercial partners’ financial contribution (where appropriate given ODA requirements) or in-kind support from co-implementers.

How will funds be paid out?
As set out in the Appraisal and Commercial Cases, a range of delivery options are likely to be used. These will include the Prosperity Fund Framework, open market tenders, MoUs and potentially grants.

For all contracts and financial agreements, SMART performance matrices will be used to link payments to specific activities. Payment will be made in arrears and FCO will reimburse the service provider on the delivery of results and satisfactory performance of milestones achieved.

Funding tranches will be agreed with suppliers based on the SoR and on the approach and activities agreed at design/ inception phase. It is expected that funds will be reimbursed on the agreed payment schedule. No in advance for need is envisaged – any legitimate request for an advance of need either by a direct service provider or a third party contracted by a direct services provider will be raised with HMT for approval.

FINANCIAL MANAGEMENT
Budget Responsibility and Financial Reporting

The reporting requirements for implementers will be set out in the contracts agreed with the winning bidders, and will specify the need for compliance with PFMO/PFDU requirements, as appropriate, DFID Smart Rules and guidance.

Forward-looking budgets, delivery plans, and milestones will be agreed following submission of the inception report under each contract, and annually thereafter. Obligations for meeting spend forecasts will be built into the contracts to ensure effective costs and spend management. Spend will be reviewed at quarterly meetings between the programme lead and contractors and any concerns on ability to meet forecasts will be raised immediately.

Budgets and delivery plans will be produced alongside retrospective analysis of performance in the preceding year. These annual reports will be supplemented by regular reports of progress against the work plan and logframe outputs, a risk register, and any expected deviations from the agreed forward-looking budgets and delivery plans. Invoices will be delivered along with these quarterly reports, with payment made in arrears against satisfactory completion of activity set out in the agreed work plan.

1. Implementers will submit a regular report along with an invoice for fees and expenditure. Monitoring of invoices and activities will be undertaken throughout the duration of the programme. Funding will not be disbursed if we have concerns about an organisation’s track record.
2. Given the nature of the work of these the programmes covered by this business case, it will need to be flexible in order to reallocate resources toward areas with greatest traction and impact. Hence, the targets under the log frame will be reviewed after each annual review.

SCALING UP AND DOWN
An outline assessment of how each of the four programmes covered in this business case could be scaled up or down should more, or fewer, resources be available, is set out in table below. We expect that rigorous evaluation of bids, close collaboration and monitoring of suppliers and careful contract management should reduce the chance of cost over-runs. Nonetheless, the scaling down options would also be potential responses should they occur.

	Scaling up by 10% would imply…	Scaling down by 10% would imply…
China Business Environment	- Possible inclusion of further thematic strands closely related to existing strands, e.g. broadening the corporate governance strand; / - Additional specific provinces and more “end to end” initiatives included within programme scope – with implications particularly for work along the Belt and Road.	- Reduced ambition and breadth of topics to be covered in institutional exchanges; / - Fewer work streams under each of the strands; / - Potential removal of one thematic strand (likely to be AML).
	Benefit would be: Business environment cuts across multiple sectors and geographies, therefore scaling up will increase exposure to UK/International best practice and higher chance of success and positive spill over.	Impact would be: progress towards key reforms would be slower, impacting on primary purpose calculation. One key area of intervention, with high chance of success, possibly lost (AML). Chance of success decreased overall; less likely that Chinese authorities would follow UK model, impacting secondary benefit.
Financial services	- Greater number of policy centre work streams; / - Undertake more complex and far reaching financial inclusion projects; / - Higher volume of officials trained in the academy.	- Reduced ambition and scale for Financial Service policy centre and academy; / - Reduced ambition in financial inclusion stream; / - Fewer work streams, number of bespoke training programmes.
	Benefit would be: This programme is where largest primary and secondary benefit is likely to derive from. It also underpins other programmes. Scaling up therefore likely to derive commensurately bigger results.	Impact would be: progress towards key reforms would be slower, impacting on primary purpose calculation. Less UK exposure also means less exposure to UK policy and commercial expertise, so fewer export wins likely to fall to UK companies.
Energy and Low Carbon Economy	- Increased breadth and depth of UK engagement on energy and low carbon issues that are central to international emissions reduction efforts (e.g. Chinese power sector reforms) / - Expansion of activities into Chinese Tier-2 and Tier-3 Chinese cities / - Enhanced focus on gap between policy and implementation	- Reduce breadth and depth of UK engagement on energy and low carbon issues that are central to international emissions reduction efforts (e.g. Chinese power sector reforms) / - Narrow focus on more easily accessible and serviceable locations (Tier-1 cities only) / - Narrow focus on fundamental policy and market reforms; implementation concerns become secondary order issues
	Benefit would be: / - Enhanced breadth and depth of activities that help position UK near the centre of internationally significant decision-making / - Expanded geographic coverage would support efforts to broaden UK footprint in China and foster long term working-level relationships that are likely to increase in value over the programme evaluation period / - Efforts to close “implementation gap” will support efforts to bring forward require energy reforms and emissions reductions.	Impact would be: / - Narrower and shallower activities that help seek to defend rather than progress UK position UK on energy and climate change issues in China. / - Narrower geographic coverage would focus efforts on existing footprint directly covered by the Embassy and Consulate Generals / - Implementation is left to Chinese government and other agencies and donors, potentially delaying energy reforms and emissions reductions.
Infrastructure in Africa and developing Asia	- More regions and/or projects targeted for partner country collaboration and/or additional resource per region / - Additional programme strands e.g. a seed fund to establish a financing mechanism or to roll out UK infrastructure methodologies (five case model; project initiation pathway etc).	- Reduced scale and ambition of reform programme / - Fewer regions and/or projects targeted for partner country collaboration / - Reduced scale and ambition of China infrastructure policy reform programme and/or fewer cities and/or projects targeted for cooperation.
	Benefit would be: programme is scaleable; each additional region/city included will increase primary and secondary benefits; / -Roll out of financing mechanism and/or UK methodologies has potential to help in both China and 3rd countries	Impact would be: decreasing number of regions included will lead to decline in primary benefit and to secondary benefit; / Reducing PPP training will slow the take up of UK/International advice and expertise; it also risks allowing competitors to take over our position

RISK MANAGEMENT

The financial risk of this programme is assessed to be low-medium on the basis that technical assistance programmes are not highly susceptible to fraud and corruption and that the suppliers will have been through the full FCO due-diligence process during the PF Framework procurement exercise.

The main financial risks to the programme spending as planned are set out in the Management Case. They include:
  1. Procurement delays and delivery delays resulting in drawdown being postponed
  2. Insufficient programming time available (resulting in a pressure to spend quickly)
  3. Procurement bottlenecks when tendering multiple contracts simultaneously
  4. Changes to UK and/or Chinese government policy, undermining the programme

Should unforeseen problems arise in the programme, our maximum financial exposure will be dependent upon the timing of these problems. Experience from other similar programmes indicates that the highest risk point is at the end of implementation phase where funds will have been spent without any primary or secondary benefits having been achieved. The amount of funds committed at design inception phase will vary between each programme. Thereafter, spend will be linked to the achievement of impact so exposure will be low.

Financial / fraud risks, together with an assessment of their probability of occurrence, impact if they occur, and key mitigations is included in the management case below and a detailed risk register will be developed during design/inception phase of each programme. This will kept under tight review with a particular focus on financial risk and exposure.

Break-clauses will be built into the contract at relevant points e.g. design/inception phase to manage any need to significantly down-scale or close programme(s) which are significantly under-performing or for another reason e.g. shift in relevance or ability to deliver results.
MANAGEMENT CASE

INTRODUCTION

This section describes how the overall programme will be implemented and governed.

GOVERNANCE AND MANAGEMENT STRUCTURES
The budget for the China Prosperity Fund Portfolio will be held by the FCO. The FCO will delegate responsibility for the allocated funds to the programme SRO, both in terms of management of public money and ensuring compliance with the International Development Act. Specific details of the delegation are pending a final version of the SRO letter.

Minister-Counsellor Prosperity will be the SRO of the portfolio, providing overall strategic oversight and accountability for delivery of the programme in China. The SRO will be supported by the China Prosperity Fund Advisory Board, consisting of senior representatives from across HMG, including FCO (Embassy, Consulates and London-based China Department, Asia Pacific Directorate and Prosperity Fund Department), DIT, DFID, British Council and Cabinet Office (PFMO). The Advisory Board will meet every three months to review progress and help shape strategic priorities.

The pillar-specific programme management teams (‘Programme Teams’) and the central programme management team (‘Central Team’) will be responsible for ensuring that information, reporting and recommendations and move between the management and governance structures for each programme.

The overall management and governance structures will be as shown below:

MANAGEMENT STRUCTURE OF THE CHINA PORTFOLIO

To note above: China SRO is now the Minister Counsellor; Project Sponsors are now Programme SROs; Rule of Law for Business now called China Business Environment; Skills Programme has been withdrawn; Future Cities now called Urban Climate Change.

STRATEGIC AND OPERATIONAL MANAGEMENT – BUSINESS/PROGRAMME/SUPPLIER

To note above: HMA role is no longer included and the Minister-Counsellor is now SRO.

Strategic Programme Management

The SMS1 Minister-Counsellor Prosperity will act as SRO of the China Portfolio. Reporting to him/her will be the Prosperity Fund Counsellor who will provide oversight of each of the programmes, and ensure coherence with other programmes (such as Global Britain Fund, DIT and DFID initiatives as well as other Prosperity Fund programmes run from the centre or other FCO Posts). S/he will be line manager of the pillar programme directors. Accountability and responsibility for the delivery of the programme will flow centrally through this chain up to the SRO.

To ensure alignment with the ‘business’, a Programme SRO (UK based SMS or D band) will be appointed for each programme. Their key functions will be to provide strategic direction, policy input and maximising benefit realisation to each of the programmes. They will be responsible for coordinating between the relevant policy and DIT teams at Post, and with London and Chinese policy stakeholders, in order to steer the programme in the right direction, ensuring alignment with the Country Business Plan. They will chair the steering committee of the relevant programme. They will act as counter-signing officers to the programme directors.

Operational Management and Staffing Profiles

Operational management will be in the hands of the Central Team and each of the Programme teams. The size and make-up of the programme teams will flex according to need. The staffing model has been calibrated to allow for active management and engagement with suppliers and stakeholders. Each programme will be managed by teams made up of a programme director (C5 or D6 (LE)) leading on strategy and programme design, and 2 programme managers (C Band - LE). The exact split of responsibilities will be flexed according to need. At its peak, the Central Team will consist of a maximum of 2 D band (UK based), 4 C band (LE) staff, 3 B3s (LE) and 2 A2s (LE). At the time of writing (March 2018) we have never taken up the full allocation available, and will only do so when the resource is clearly needed.

Roles and Responsibilities:
FUNCTION	PERSONNEL	RESPONSIBILITIES
SRO	Minister Counsellor Prosperity	Overall accountability for China Prosperity Fund Portfolio
PF China Advisory Board	Chaired by the SRO with senior level representatives including from Whitehall departments and China network	Review Fund progress, provide challenge and advise on strategic priorities across the portfolio.
Programme SROs	Senior (SMS/D band) policy/DIT members of staff - one per programme	Strategic direction, policy input and maximising benefit realisation for each programme.
Management	Prosperity Fund Counsellor (D7), supported by Prosperity Fund Programme Director (D6)	Manage China Prosperity Fund Programme at Portfolio Level, Central Programme Team and Programme Teams.
Delivery	Central Team, Programme Teams, led by D6 Programme Directors and supported by Programme Managers (as well as Suppliers/Delivery Partners)	Programme management including finance, procurement, monitoring and evaluation.

A guiding principle of operational management will be evidence-based adaptation. Using information from the project’s monitoring and reporting systems, programme teams and the Central Team will be responsible for testing and refining interventions and proposals on an on-going basis. The suite of activities within a particular programme is likely to change over the lifetime of the PF, to ensure they are delivering the highest possible impact and value for money in response to both learning and changes in the internal and external environment. Adaptive management may also have budget implications, with the Central Team able to recommend reallocations between programmes if impact analysis suggests this would deliver better results and/or value for money.

The previous policy and programme teams working on prosperity programming in China were experienced and had an excellent track record. However, historically most of such programming had been through numerous small projects initiated through a call-for-bids process. As we make the transition towards fewer, larger programmes procured through competitive tender, our staffing set-up has undergone a major transformation. A small number of previous staff were re-recruited for their project management skills and will be retrained in wider programme, procurement and contract management.

In considering this Management Case, it should be noted that the other programmes that will make up the China portfolio (Health, Global Partners, Urban Climate Change) also started to come online during 2017/18 (having been agreed by Ministers at Concept Note stage in July 2017). Some of the staffing decisions outlined in this case have been taken with these other, later programmes in mind, to help maintain continuity and a smooth transition.

As part of every programme’s annual review we will review staffing and decide for each position whether it is still required and the grading/requirements are correct.

Given the focus of the programme will be on policy reform, and the particular context of China, where long term, high level relationships are often key to success, it is vital that we deploy sufficient staffing resource, including in the Consulates-General located in different provinces of China, to provide enough support to the programme.

Capacity and Capability

Whilst the China Prosperity Fund network has a long and successful experience of running portfolios of projects, this will be the first time it will have managed a programme of this size. In addition to the more generic, high level training that PFMO is providing, we will also develop a bespoke training package which will include, at a minimum, four modules: procurement and contract management; MREL; finance and accounting; and staffing/capability. The training program will include in-house training but also short term secondments or shadowing opportunities to local private sector companies from whom we can learn best practice, and/or OGDs such as DFID China or the FCO Procurement hub in Manila. In this way, we will build up strong in-house capacity and capability. The aspiration is to make China a Programme Management Centre of Excellence.

Despite this strong focus on training and developing existing staff, where necessary, we will also hire in relevant expertise on short term fixed term contracts where we judge that the existing staff don't already have the necessary skill set and there is a short notice need for that work to be done. This has been factored into the staffing and admin costs set out in the Financial Case.

Working with Implementers and Suppliers

As set out in the Commercial Case, delivery of the majority of this programme will be outsourced to external suppliers. We will deal primarily with the lead supplier or lead consortium partner only (with whom we will contract), though interacting with sub-contractors as needed. Close coordination, clear lines of reporting and levels of authority, and clear governance arrangements will be key.

Within the lead supplier teams, we will expect a Programme Director and a Programme Coordinator to be appointed. The exact shape and requirements of their roles will be agreed with suppliers once they have been appointed, but in general the supplier’s Programme Director will be responsible for strategic management of the programme, including selection of sub-contractors and consortium partners and strategic communications as appropriate. This individual will sit opposite the relevant Embassy Team Programme Directors. Meetings every four to six weeks will be expected.

Reporting to that supplier’s Programme Director will be a Programme Coordinator, responsible for the operational delivery and day to day management of the programme, including sub-contractor/consortium partner and stakeholder management and communication. The individual will be responsible for ensuring that all parties on the supplier side comply with agreed operational systems and processes, overseeing the accurate production of management information, forecasting and billing on an agreed schedule. The individual will be the key day to day point of contact for the Programme Teams.

Whilst the Programme Teams will deal primarily with the lead supplier or lead consortium partner, they will also have regular, structured contact with suppliers/sub-contractors/consortium partners on a quarterly basis. This will be organised through the lead supplier, who will also be invited to attend to avoid any risk of miscommunication.

Details of organisational structures, operating systems, processes and reporting lines between lead suppliers and any consortia partners or sub-contractors will be a requirement in all appropriate Statement of Requirements and will be included in the technical evaluation of bids.

REPORTING

Generic Progress Reports

The contracted lead supplier(s) for each programme will provide monthly reports to the Programme Steering Group (chaired by the relevant Project Sponsor). The Embassy Team Programme Director, supported by their C-band programme managers, will then report monthly into the Central Team. The Central Team will collate these into a China portfolio level report covering the status of the each programme and the portfolio as a whole. This will be submitted to the SRO on a monthly basis, although this frequency can be reviewed and to PFDU on whatever reporting cycle is required. Reporting to the PF Advisory Board will be on a quarterly basis to suit the meeting cycle. Generic reporting routes will be as below:

Contracted delivery partner

Prosperity Fund Delivery Unit
(and PFMO where required)

Central Team
(via D7 and SRO as needed)

Programme Working group

Programme Steering group

Financial Reporting – including spend and forecasts accuracy:

All financial reports will be structured in a way which meets FCO, HMT and Cabinet Office requirements.

Budgets and delivery plans will be produced alongside retrospective analysis of performance in the preceding year. These annual reports will be supplemented by regular reports of progress against the work plan and log frame outputs, a risk register, and any expected deviations from the agreed forward-looking budgets and delivery plans.

Monthly financial data will be collected and will be used as a blunt tool for early identification of any discrepancies in spend and potential under performance. Programme Directors/ Programme Managers, with support from the Central Team, will be responsible for ensuring Prism is kept up to date. The Central Team will utilise the OBIEE Dashboard to undertake in-month and Outturn Analysis.

Annual Review

Annual reviews will be used as a continuous process of review and improvement throughout the delivery of each programme. The approach to Annual Reviews set out below is based on DFID’s SMART rules. If at a future date a PF approach is implemented that differs from this we will amend our approach accordingly.

An Annual Review of each programme will be undertaken separately but under the guidance of the Central Team to ensure coherence and consistency in both approach and timing.

A decision will be taken each year whether to use an internal or external party to undertake the Annual Review, recognising there are benefits to both (e.g. internal allows a much stronger understanding of the context of the PF programmes, external can be useful in providing fresh eyes and delivering difficult messages to stakeholders).

The Annual Review will undertake a formal review of items such as:
- Progress achieved since inception or the last annual review, including an assessment of the quality of progress;
- Assess and score progress during the last year against the Outputs in the log frame, including a consideration of Assumptions and Risks, and determine whether and what changes are required;
- Assess progress towards achieving the log frame Outputs and Outcome by the end of the programme;
- Make recommendations and identify action points regarding any major issues and problems affecting progress;
- Review the performance of partners, suppliers or contractors and processes (such as procurement, tranche payments, payroll and asset management);
- Assess whether the programme is on track to deliver Value for Money;
- Identifying priorities and work plans for the coming period;
- Assess whether the staffing structure, capacity and capability is appropriate.

The Annual Review will revisit the log-frame and test the assumptions that link the indicators and the outputs, outputs and the outcomes and outcomes to the impact remain valid.

The Annual Review will be delivered through a combination of desk based work utilising existing M&E data as well as external interviews with delivery partners, suppliers, beneficiaries and other relevant stakeholders.

The Annual Review will in the first instance be quality assured by the Prosperity Fund Counsellor before being presented to the Deputy SRO and SRO.

The information from the Annual Review will be used to:
  - Update delivery plans in accordance with key recommendations;
  - Update and revise existing activities, timelines and resources;
  - Amend the results framework below outcome level (above which would trigger the formal change process);
  - Update risk management plans.

An Annual Review recommendations tracker will be developed for each programme to ensure recommendations are being effectively responded to throughout programme delivery. This response will be reported on in the subsequent years Annual Review.

The Annual Review process will act as the formal mechanisms for ensuring effective management and delivery by suppliers from point of contract through to programme close. This will be supplemented by regular contract management meetings throughout the year, which will enable any problems or risks to effective delivery to be caught and addressed early on.

MONITORING AND EVALUATION (M&E)

The below sets out the expected monitoring and evaluation strategy as advised by the PFMO. The M&E of the China PF will be kept under review as the M&E approach is refined in London to ensure consistency.

The monitoring, reporting, evaluation and learning (MREL) for this programme will be consistent with the overall Prosperity Fund approach to MREL. The team in China will work with the central Fund MREL contractors to develop critical indicators for Fund and programme level reporting, identifying indicators that can be aggregated for regular reporting and management indicators to allow programme managers to assess progress and impacts. The programme MREL will be consistent with the programme theory of change and the log frame analysis that flows from this. Expenditure will be reported monthly, in line with Fund reporting requirements. Where possible, reporting will be disaggregated by sex, disability, age, etc.

Reporting Frequency and Costs

Programme implementing partners will be instructed to develop a regular results reporting system and will work with the central Fund Monitoring and Reporting contractor to ensure consistency with Fund processes and systems – particularly around data quality and consistency. Programme data capture and base lining will be the responsibility of the programme and its implementers but, as instructed, the costs of this will be charged to the central MREL budget.

Evaluation and Learning

If this programme is selected as one of the samples for fund level evaluation, we will work with the Fund evaluation and learning contractor to develop the strategic questions that will be required for both the fund evaluation and to provide feedback to programme managers on routes to impact. The overarching evaluation methodology will be decided by the fund level evaluators and we will work to deliver the required coordination between the various contractors at programme level. If the programme is not selected for Fund level evaluation we will work with the programme level evaluation and learning contractor to develop a set of strategic questions that we will want to answer through the process. These questions may include fund level questions if appropriate.

We further note that not all programmes are evaluable and as part of the coordination with the evaluation contractors we will assess this and decide on a way forward with the PFMO.

Monitoring and Reporting

Responsibility for data capture, base lining and reporting sits with each of the programme teams and their implementers. Indicators will be agreed with the fund level monitoring and reporting contractor, the evaluators and the programme implementers. The monitoring and reporting contractor will identify the data requirements in terms of format and quality. We will work with our stakeholders to ensure that reporting is done in a timely and useful manner.

Log-Frames

These will be further developed during design/inception phases and reviewed and updated on an ongoing basis.

ADAPTIVE AND FLEXIBLE PROGRAMMING

Adaptive programming is an approach being taken forwards by DFID (new guidance developed with ODI has recently been released).

These programmes will adopt adaptive programming to ensure flexibility by building this into the structure of the main implementer contracts. Funds will not be deployed all at once but rather act as a facility over the period of the programmes, allowing room for the programmes (and portfolio) to adapt to changes in risk, context and priority. Contracts and supplier agreements will also be structured such that work can be scaled if necessary and is dependent on performance. The budgets for each programme are indicative and can be adjusted if necessary within the overall £85m envelope in response to learnings and changing circumstances. A change management process will be agreed with the PFMO, determining the limits of adjustments that can be decided unilaterally at Post and the process to be followed if the proposed adjustments exceed those limits.

COMMUNICATIONS AND BRANDING

External communications will be a significant part of ensuring the China Prosperity Fund portfolio is successful. A key focus of each of the programmes is policy reform, which will of course need strong Chinese government buy in. A close association between the programmes and HMG will therefore be vital, and careful, consistent external communications with Chinese government (both national and provincial) will be required.

At the same time, the programmes will only succeed if we ensure that the potential positive spill-over commercial impacts and reputational benefits for the UK are realised. External communications will be needed to ensure that the private sector/business community can inform the focus of programming, is aware of the programme and well positioned to take advantage of commercial opportunities that the programme helps bring to market.

Proactive and joined up external communications will be required, which clearly demonstrate benefit generated from the investment: that sharing world class British expertise will help to create commercial opportunities for UK companies in China, and foster investment in the UK.

In order to maximise awareness and understanding of the programme, and to help ensure that beneficiaries and partners understand that this is a British government initiative, even though delivery may be outsourced, we will explore branding/identity options – guided by principles of strong HMG visibility and ownership, but with an emphasis on private sector engagement. It may make sense to create a semi-independent ‘brand wrapper’ around the portfolio or have slightly different products for different audiences. The Infrastructure programme has already been successfully branded as the ‘UK-China Infrastructure Alliance’. We will discuss ideas with the China Prosperity Fund Advisory Board and suppliers. We will also consider and incorporate the PFMO Communications Guidance as appropriate.

The key objectives for our communications and branding will be:
- Ensure UK companies are aware and able to take advantage of opportunities and access resulting from each programme’s activities;
- Influence national and local decision-makers to ensure effective implementation and delivery of the Portfolio, including maximising potential spill-overs;
- Use the portfolio to raise the profile and reputation of the UK in China and those partner countries for e.g. infrastructure, while facilitating access to stakeholders in national and local government and in the private sector;
- Seek to ensure support for China Prosperity Fund portfolio among UK public, press and Parliament;
- Raise the Portfolio’s profile through reporting of success/impact;
- Ensure that Embassy teams and Cross Whitehall partners are aware of the Portfolio’s objectives, processes and are actively seeking to align with them as appropriate.

Our audiences will be:
- UK business and investors (including trade organisations such as the CBBC and CBI), and academic institutions;
- UK press, public and Parliament;
- Chinese businesses and investors interested in partnerships with UK companies;
- Chinese national and provincial government, in particular decision makers in key sectors targeted by the programme;
- Chinese press and public;
- Embassy teams, other FCO posts and Cross Whitehall departments;
- 3rd country government, businesses and press where appropriate.

Strategic communications activities will therefore include:
- Ongoing engagement with relevant national-level ministries and provincial-level departments to raise the profile of programme activities and demonstrate the value of inclusive growth reforms; highlight the potential of UK companies in key sectors; and ensure we are aware of developing opportunities (e.g. major contracts, policy reforms etc.) and corresponding risks;
- Timely media moments (blogs, tweets, editorials) in China to highlight programme activities and successes to a wide audience capitalising on reputational benefits for the UK; and
- Communications activities including meetings, presentations and trade missions with UK companies (in China, UK and partner countries) that could benefit from the opening up of opportunities through the programme. This will link to work undertaken by DIT (and the CBBC) to directly facilitate business wins.
RISK REGISTER

The main risks are set out in the table below. This will be regularly reviewed. As set out in the Commercial Case, suppliers will be required to present and maintain a clear risk matrix and risk management process which will be revisited on a monthly basis. This will feed into programme level risk management matrices, which in turn will feed into a portfolio level risk matrix and register, held by the Central Team.
Delivery risks
Risk	Prob.	Impact	Mitigation
Approval of business case takes longer than expected	M	H	Maintaining flexible funding (whether through Transitional Funding or any other source) / Close and on-going engagement with London, including via SRO if needed, to ensure approval process is clear and goal posts no longer move
Programme delays (once approved)	M	H	Embassy programme teams and suppliers will have clear timelines for delivery, set out clearly in contracts / Sufficient resource allocated to contract management
Suppliers unable to engage sufficiently with Chinese government. Efforts to adhere to staffing cap leads to inappropriate delivery models chosen, and not enough HMG staff to support delivery of programme, reducing influence, tarnishing the UK brand, and undermining delivery	M	M	Ensure that the programme management teams are properly staffed, and strongly engaged with suppliers. / Regularly approach key stakeholders for feedback. / Ensure delivery model contains enough flexibility and access to HMG staffing resource to ensure successful delivery of programme / Continue to push PFDU/PFMO to relax staffing cap – it is not appropriate in market like China and risks poor VFM and perverse decision making (not hiring specialists due to high cost…).
Weak sustainability / legacy, as key relationships are developed by implementers, whose involvement is based on time-limited contracts	M	M	Strong engagement by programme teams in delivery. / Effective “wrap-around” diplomatic support for engagement with Chinese government
Slow delivery by external suppliers, risk of under spend	M	M	Mitigated by strong programme management by experienced delivery team in the China network and the sound systems in place for continuous monitoring. / Regular financial reporting will allow emerging areas of concerns to be spotted early and corrective action taken. Flexibility and contingency planning built into programmes to ensure that if necessary resources can be re-balanced away from underperforming areas of focus and towards successful ones.
Economic reforms are seen to be threatening social stability, and domestic political will for reform.	L	H	Targeting a range of sectors (diversification benefit) across the portfolio, all with strong, high-level political buy-in from the Chinese side.
Fading momentum for UK-China engagement should the bilateral UK-China relationship weaken?	L	H	Continued strong engagement by China network staff with key counterparts in the Chinese Government. Adaptive, flexible programming can respond to changing circumstances.
Weak procurement process / poor market response means procurement has to be repeated.	L	H	The China Network has broad market knowledge of providers in China for programming across the four programmes of this portfolio. As set out in the Commercial Case, we will undertake comprehensive early market engagement, and programme teams are now identifying and engaging with external implementers that meet our capacity, competence and due diligence requirements. / Adherence to FCO’s procurement policy will ensure all procurements are robust.
Weak internal governance, project management suffers as the China network struggles to scale up to a much larger prosperity programme	L	M	Change management process. Deploying a strong programme team with an excellent track record. / Up skilling existing staff, seeking to recruit in specialist expertise as required
Weak private sector response, including from UK business	L	M	Mitigated through working closely with DIT, CBBC and engaging with a wide range of businesses, both UK and Chinese. Programming designed in areas where it has been judged there is strong capacity and will from UK business to respond to growing opportunities, so delivering secondary benefit for the UK.
Chinese stakeholders reluctant to engage because of the high importance placed on UK economic benefits	L	L	Wrap-around diplomatic and commercial engagement from China network staff with programme delivery, ensuring that the programme’s focus on primary purpose and mutually beneficial activities is well-communicated. / Regularly approach key stakeholders for feedback.

Financial / fraud risks
Risk	Prob.	Impact	Mitigation
Compensation payments will need to be made to staff leaving the programme (particularly when programme closes), in line with local labour law.	H	L	Contingent liability for staff compensation should be incorporated into the budget, subject to further consultation with PFDU given this issue will affect all PF programmes
Programmes/projects do not yield adequate returns	M	M	Robust and thorough KPIs included in SoRs and contracts. / Applying stakeholder expertise and detailed analysis to forecast risk-adjusted project yields. Where needed this will include scenario modelling with sensitivity around key variables that affect the success of the project (e.g. interest rates, consumer/client behaviours etc). / Active adaptive programming is maintained so funding can be flexed if needed
Funds transferred to external implementers not being used for their intended purposes (including as a result of corruption)	L	H	Payments will be made in arrear (and where possible on an output basis) – active engagement and strong programme management by programme teams will further minimise risk. As part of the due diligence undertaken during the Framework/OJEU process, the financial management and accountability systems, and risk assessment processes, of suppliers will be assessed, and suppliers will be required to set out how they intend to manage corruption and other risks. FCO standard fraud prevention policy and practices will be robustly applied.
Spending does not represent good value for money	L	H	Robust design (including detailed budgets) during Stage One of the programmes / Transparent procurement and relevant award criteria to choose best offers in terms of VFM. / Active management of all programmes and projects, with regular monitoring feeding back into implementation. / Co-financing from stakeholders will be sought when possible.
Expenditure is not properly accounted for	L	M	Internally, mitigated by experienced programme teams, working with oversight from finance officers in the central team, robustly implementing financial management processes. The financial management and accountability systems of external partners will be assessed as part of the procurement due diligence process.

REFERENCES FOR CHINA PHASE 1 BUSINESS CASE