 Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Global Infrastructure Programme
Programme Value: £25m (originally), predicted expenditure is £14m (allowing for underspends and ODA budget reductions)		Review Date: 13 June 2019 – 14 October 2020
Programme Code: / GB-GOV-50-PF-14-INFRA (including GB-GOV-3-PF-INF-912; GB-GOV-3-PF-INF-922; GB-GOV-3-PF-INF-921; GB-GOV-3-PF-INF-913; GB-GOV-3-PF-INF-923; GB-GOV-3-PF-INF-911)	Start Date: SOBC approval – 4 October 2017	End Date: 31 March 2021

Summary of Programme Performance
Year	2019	2020
Programme Score	A	A+
Risk Rating	Moderate	Minor

Since the previous review in 2019, the Global Infrastructure Programme (GIP) has made significant progress, undertaking a wide range of activities in the Tier 1 and 2 partner countries, and delivering a number of key outputs that are on track to contribute to the realisation of the primary and secondary benefits. It has built on relationships with key organisations in partner countries with the team to establish a strong reputation, which has enabled it to both build capacity, and drive the adoption and embedding of UK methodologies: the 5 Case Model (5CM); the Project Development Routemap (PDR); and Building Information Modelling (BIM), albeit with different degrees of uptake across partner countries.

The programme has achieved a number of notable successes during the period covered by this Review. These include a significant GIP contribution towards the work that resulted in the signature of a Government to Government (G2G) agreement between the UK and Peru, with a direct contract value of £100m to UK firms, and potentially creating over £1.6 billion of additional contract opportunities in future, as well as establishing Trust Funds with the World Bank and Inter-American Development Bank to support infrastructure developments that utilise UK methodologies. These successes have significantly increased the potential for the GIP to deliver or exceed the level of primary and secondary benefits included in the business case. This progress has also reduced the risk of the GIP failing to deliver its expected objectives.

The GIP also faced a considerable challenge in needing to adapt the programme and delivery model to respond to Covid-19, as well as to manage significant in-year budget reductions of 42%. The Programme Team worked effectively with the delivery and commercial partners to move to an online delivery model, and to reallocate financial resources, enabling this to be achieved at no additional cost. Implementing the budget reductions required difficult choices to be made with regard to resourcing activities in partner countries. These have inevitably had consequences in terms of the level of support provided, and meant activity had to be significantly reduced or stopped in some countries, as well as implications for wider stakeholder engagement activity, e.g. with academia, business and civil society. However, the overall assessment of the Annual Review is that this process has been managed to ensure the programme can be sustained and the impact on the delivery of outputs and outcomes minimised.

In terms of benefits realisation, the main concern relates to the timeframe for the delivery of the primary benefits. The GIP business case estimated the Programme would deliver primary benefit NPV of £1,18 billion over the ten-year appraisal period 2017/18-2026/27, through an uplift in GDP for the three Tier 1 countries as a result of infrastructure investment. Whilst these benefits are highly likely to be achieved, there is a risk they are not realised within the appraisal period, due to the duration of infrastructure projects, and because only benefits accruing in three countries would be counted. Therefore, the Review Team concluded the approach to calculating the primary benefits should be reviewed, to ensure an accurate and realistic assessment of what the Programme has delivered should be undertaken, and to learn lessons for the design of future infrastructure programmes.

The Annual Review in 2019 made recommendations to better integrate Gender & Inclusion (G&I) considerations, ensure value for money, improve the commercial management of the Programme and strengthen monitoring and evaluation. Action has been taken to implement these recommendations, including:

1)      highlighting G&I considerations through training materials, guidance and case studies, increasing female participation in training programmes, and more regular oversight of progress against these objectives;

2)      stronger and more regular reviews of budgets and better financial monitoring;

3)      reviewing delivery resources, including within delivery partners, and recruiting a commercial officer to strengthen contractual oversight at FCDO; and

4)      consolidating the Theory of Change and log frame, to achieve greater consistency and enable better monitopring and evaluation.

The overall assessment of the Annual Review is that the Programme has made significant progress towards delivering its planned outputs and outcomes during the period under review, and that it remains on track to achieve or exceed the benefits identified in the business case. As a result, the conclusion of the Annual Review is that overall, the GIP merits a Programme Score of A+, and that the Programme Risk Rating is Minor.

List of recommendations for the final phase of the Programme
For Action by Programme Conclusion

Log frame: To enable the programme to assess partner performance and demonstrate progress at project closure, we recommend that the Programme Team revisit the programme-level log frame with delivery partners to clarify which project-level indicators and milestones feed into which programme-level indicators, and instate a clear, simplified process – owned by a member of the GIP Programme Team – for making updates to the programme log frame in step with delivery updates provided by the IPA and CDBB. A clear process will help to avoid confusion on how and what to score the programme against at project closure, and ensure there can be a fair and objective appraisal of delivery.

Programme Evaluation: For the next (and likely final) evaluation cycle, we recommend the programme team begin early planning with the evaluators to ensure activities can be completed while stakeholders are still available, and that a final, evaluative analysis of the programme’s results and contribution to outcomes can be available in time to feed into any project closure or transition reporting requirements.

Exit Planning: The Exit Plans produced by the delivery partners should be extended beyond key activities that need to be delivered and plans for programme closure, to include planning for sustaining activities and embedding them in other programmes. This should take account of the point at which funding for key elements of the GIP will end, particularly funding for the CDBB/BIM (December 2020), and seek to mititgate the risk of losing capability. The Programme Team should undertake an analysis of how bilateral programmes in Tier I and II countries, as well as other global programmes can utilise or integrate the UK methodologies, training materials or initiatives that have been developed through the GIP. This should also include enabling access to 5CM and PDR materials, and BIM Knowledge Products, particularly for target audiences in GIP partner countries. If an extension is funded by the CSR, the focus will switch to re-planning for a further period of delivery.

Review of Primary Benefits: The Programme Team should undertake a re-evaluation of the scale and timing of the primary benefits, and how these are calculated, with a view to identifying a more realistic timeframe for the realisation of these, taking account of the duration of the construction phase before these become operational, and also the benefits of the Programme in all countries where activities have been undertaken. This can then inform the development of future business cases for infrastructure programmes and investments.

Secondary Benefits: Devote adequate resources to fully operationalise the SB tracker, in close consultation with delivery partners in UK and at post, so UK business can receive timely notification of changes to the legal and regulatory framework in Tier 1 and Tier 2 countries, and when potential new business opportunities arise.

GIP Communications Strategy: Develop a communications plan to disseminate success and lessons learned from the GIP programme not only to targeted audience in the UK but also in partner countries and others that may have an interest in adopting the methodologies. FDCO to allocate resources to for the implementation of the plan as well as to nominate an owner of the plan. By 31 December 2020.

Gender & Inclusion: The Programme Team should maintain the momentum generated last year in embedding G&I considerations within the GIP. It should be a priority to take forward the G&I Action Plan, and to ensure that the actions within this are completed prior to the closure of the project.

Options for the Future and Embedding Lessons Learned

Explore and target potential synergies between the programme’s partners and other PF (or bilateral) programmes involved in infrastructure, such as Global Future Cities, Asian Infrastructure Investment Bank Special Fund, ASEAN Low Carbon Energy, Indonesia Renewable Energy and other bilateral programmes.

Secondary Benefits: As part of preparation for closure of the GIP, the Programme Team, in conjunction with DIT, should undertake a review of actual and prospective commercial opportunities in the partner countries and through the Multilateral Institutions, and ensure there is adequate awareness and resources in DIT to support UK firms to access these.

Commercial: The Review Team would strongly recommend that any forward structure for the programme (or for programmes with similar objectives) put in place sufficient central commercial support and contract management capacity before MoUs and contracts with delivery partners are signed. This will help to ensure agreements are of a high quality and supported by effective oversight and communication structures from the outset, and help to avoid any confusion over lines of accountability and/or suppliers going off track. A devolved contract management structure could also potentially be considered to reduce the number of relationships that need to be managed centrally.

Conclusion
There is a strong case for continuation of support for embedding the UK methodologies following the closure of the Programme. The GIP has demonstrated that there is both significant demand for the UK methodologies to support infrastructure investment in both countries and multilateral institutions, and that these are capable of delivering benefits in terms of increased infrastructure investment and inclusive economic growth, as well as creating opportunities for UK firms. The GIP has also demonstrated good value for money, and developed a number of guidance, training materials and other resources, which combined with the established and proven delivery methods and partners, would mean that support could be provided more efficiently in future. This could be achieved through either continuation of the GIP, or through embedding the UK methodologies in the delivery of other relevant programmes (bilateral or global).
SRO Commentary
I am pleased to see that the programme has continued to make good progress and I fully endorse the overall rating of A+.   It is indicative of a well-run programme that progress has been maintained since the last review in June 2019 despite the Covid-19 crisis and the subsequent cuts to the programme’s budget.  I note the excellent work from Infrastructure and Projects Authority and the Centre for Digital Built Britain, supported by effective commercial suppliers, that has been central to enabling the continued successful delivery of the programme in these difficult circumstances.
It is good to see that last year’s recommendations have been actioned and particularly pleasing to note the significant progress on Gender and Inclusion in a male dominated sector and green infrastructure development in line with ambitions to tackle the effects of climate change. This year, there are a robust set of recommendations that reflect the approaching end of the programme; there is a real opportunity for the programme to cement a powerful legacy of trained officials, embedded processes and knowledge products in partner countries that will lead to appreciable primary and secondary benefits.
JFU Commentary
We agree with the assessment. There have been exciting developments under the GIP over the last year, including on green infrastructure development plans in Peru and Colombia, working closely with both partner countries and other important stakeholders including the World Bank. Considerable progress has also been made on ensuring alignment of programme activities with wider government climate change objectives, as well PF guidance on gender and inclusion, as per the recommendations of the previous Annual Review. It will be important over the next 6 months to consider all options for the smooth transitioning of PF funded activity to other potential programmes, and value for money implications if spend needs to be prioritised further following the forthcoming Comprehensive Spending Review.

List of Acronyms
5CM – 5 Case Model (Methodology)
BC – Business Case
BE Bogota – British Embassy, Bogota, Colombia
BE Jakarta – British Embassy, Jakarta, Indonesia
BE Hanoi – British Embassy, Hanoi, Vietnam
BEIS – Department for Business, Energy & Industrial Strategy
BIM – Building Information Modelling (Methodology)
CAF – Latin America Development Bank
CDBB – Centre for Digital Built Britain (BEIS delivery partner)
DFID – Department for International Development
DIT – Department for International Trade
FCO - Foreign and Commonwealth Office
G&I – Gender and Inclusion
IIOC – Investment, Infrastructure and Operations Committee
IPA – Infrastructure and Projects Authority
IUK – Innovate UK (part of UK Research & Innovation)
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
L&D- Learning and Development
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
ODA – Official Development Assistance
PF – Prosperity Fund

## A. INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/global-infrastructure-programme
DevTracker Link to Log frame:	Not yet published

Prosperity Fund

The cross-Government Prosperity Fund was created in 2015 to promote economic growth in developing countries, and thereby increasing prosperity and reducing poverty, whilst also creating opportunities for international businesses, including UK companies. The Fund has a budget of £1.2 billion over the 5 years (2016-21) to provide technical assistance to partner countries to improve the business climate, reduce barriers to trade, investment and economic growth and support necessary reforms.

Global Infrastructure Programme

The Global Infrastructure Programme is a £25 million Prosperity Fund programme that aims to develop the capacity of partner middle income countries to bridge the current infrastructure gap, through training and embedding of proven UK methodologies in project planning, preparation and delivery. The Programme Theory of Change posits that these activities will unlock economic opportunities, increasing prosperity and reducing poverty, whilst also enhancing opportunities for international and UK business.

Following submission of a successful concept note, the Prosperity Fund Whitehall Ministerial Board approved the development of the business case on 25 October 2016. The Programme received interim funding of £640,000 on 7 July 2017 to enable it to commence activities whilst developing a detailed programme of work. The Strategic Outline Business Case was approved by the then FCO’s IIOC on 4 October 2017 and Outline Business Case approval by IIOC followed on 1 November 2017, with Ministerial approval received on 29 January 2018. The Letter of Delegation from the Cabinet Office authorising full funding of the programme was received on 12 April 2018. The Full Business Case was approved by IIOC on 12 December 2018, and an updated FBC was approved by the SRO on 11 March 2019.

A light-touch annual review for transition funding activities was published on 27 July 2018, when the programme received an overall score of A with a programme delivery risk of Moderate. A full Annual Review was conducted in June-July 2019, which also concluded the GIP should receive an overall score of A, and that the level of programme delivery risk remained Moderate.

Governance and Delivery Mechanisms

The GIP is a collaboration between the FCDO, the Infrastructure and Projects Authority (IPA) and the Department for Business, Energy & Industrial Strategy (BEIS) which delivers through its partner, the Centre for Digital Built Britain (CDBB). FCDO is responsible for programme management and Post support, IPA is responsible for infrastructure and operational matters and CDBB is responsible for BIM. The SRO is accountable to the PUS FCDO as Accounting Officer for the financial management of the programme budget, and for the delivery of the programme to the Prosperity Fund SRO, the Joint Funds Unit and Ministerial Board for the Prosperity Fund.
The key elements of the governance and delivery structure are:

- A Programme Board, chaired by the SRO, with representatives of the IPA, BEIS and BEIS (for CDBB), and DIT. This is responsible for strategic oversight of the programme, and ensuring that it is achieving milestones, as well as risk management. The Programme Board meets on a quarterly basis.
- A Project Controls Meeting, which includes FCDO, IPA, CDBB and commercial supplier staff involved in the delivery of the programme. This is responsible for financial and operational management, including risks, and for co-ordinating activities across the programme. The Operations Committee meets on a fortnightly basis.
- The IPA is responsible for delivery of the internationalisation of the: i) the 5 Case Model (5CM) that provides a standardised approach for developing business cases that increases transparency and improves the quality and viability of proposals; and ii) the Project Development Routemap (PDR) that supports effective delivery by offering early insights into the challenges the project needs to address before moving to the delivery phase and is focused on upfront capability strengthening, supported by PwC.
- The CDBB is responsible for delivering work in relation to Building Information Modelling (BIM) technologies and capacity building in partner countries, supported by Mott MacDonald.

Outside the formal governance mechanisms, there is regular contact between the team in FCDO, the delivery partners and staff in posts; the latter are also able to participate in Programme Board and Operations Committee meetings remotely. The IPA and CDBB teams have been involved in the delivery of activities in-country, and there is a strong network across the programme that facilitates effective joint working.

Rationale for intervention and Expected Impact

Infrastructure is vital for any country’s economic growth and development. Infrastructure is the basic physical and organisational structures and facilities needed for the operation of a society: economic infrastructure networks such as transport, energy, water and telecoms provide the basis for businesses to grow and be productive, whilst social infrastructure investment in schools, hospitals and housing supports quality of life. Yet, despite the critical importance of infrastructure, a significant global investment shortfall or ‘infrastructure gap’ has been widely acknowledged in recent years. McKinsey assess this at US$350 billion per year worldwide or US$5.2 trillion over the next 14 years.[1] Today, as well as the need for finance, there is also a critical lack of properly developed projects that governments and financiers can invest in with confidence.[2]
[1] McKinsey Bridging Global Infrastructure Gaps – 2016
[2] Financing Change: How to mobilize private-sector financing for sustainable infrastructure, McKinsey, 2016)

The GIP can help address that problem through the adaptation of UK best practice methodologies in infrastructure project planning, preparation and delivery. The methodologies put forward, tried and tested in the UK, will be adapted for international use and promulgated internationally with the help of the private sector. In turn, this will increase the number of good infrastructure projects coming to market as investable propositions, helping to bridge the gap. This will assist developing countries to install the economic and social infrastructure they need to sustain inclusive economic growth, with particular benefits for the poorest in society, and attract investors and lenders to deliver critical projects and programmes (see Strategic Case for more detail).

Cross-Government Programme with Multilateral and Private Sector Stakeholder Support

The multi-year funding offered by the Prosperity Fund offers a unique opportunity to address this problem strategically, through leveraging the collective expertise and resources of Government Departments through a co-ordinated multi-annual programme. The programme is a cross-Government initiative delivered by FCDO, the Infrastructure and Projects Authority (IPA) and BEIS (via their BIM delivery partner the Centre for Digital Built Britain) in collaboration with DIT and DFID, drawing on the:

- global reach and local connections of the FCDO overseas network;
- project management and fund management skills of the central FCO;
- infrastructure expertise and policy understanding of the IPA;
- digital construction and Building Information Modelling skills of BEIS (via CDBB);
- experience and expertise of DFID, in particular consulting on effective approaches to TA and engaging with their learning programme; and
- commercial knowledge and reach of DIT to exploit secondary benefit opportunities.

The Programme will deliver a range of capacity-building activities in participating countries, including the deployment of BIM and the 5 Case Model in relation to exemplar projects three key pathfinder (Prosperity Fund priority) countries in the Latin America and ASEAN regions, also encompassing regions covered by China’s Belt and Road Initiative, whilst supporting a wider set of countries in these areas over time. Partner countries were selected on the basis of their ability to: 1) deliver inclusive growth and economic opportunities (including for the UK); 2) their fit with the Prosperity Fund Theory of Change and Prosperity Fund priorities; and 3) their ability to act as ‘beacons’ to demonstrate the benefits of the new methodologies.

The Tier 1 pathfinder countries (covered in phases 2/3) were:

- IPA: Indonesia, Colombia and South Africa (added in 2018); and
- CDBB: Indonesia, Colombia and Vietnam

In addition, the GIP identified a number of Tier 2 countries (covered in phase 2) where there was also the potential for the Programme to achieve impacts consistent with its overall aim. These were:

- IPA: Vietnam, Peru, Mexico and Brazil; and
- CDBB: Peru, Mexico and Brazil

The original aim was to provide similar training and support packages as delivered in the Tier 1 countries. However, following the Covid-19 replanning exercise in 2020, which resulted in 42% ODA cuts to the programme in August 2020, CDBB transitioned work in Indonesia and Colombia to Tier 2 delivery, and reduced delivery in Mexico to supporting ISO implementation. The IPA did not go ahead with planned work in South Africa.

Additionality

The Programme will be complimentary to development assistance from Multilateral Institutions, and has broad support from the private sector. The World Bank view the proposed methodologies as filling a gap in the current support for infrastructure development, and are supporting the use of the UK methodologies, with a view to placing them on their knowledge portal for use around the world. The Inter-American Development Bank (IADB) and UN Office for Project Services (UNOPS) are also supportive. There is further support in the private sector in the UK and partner countries, which recognise the potential of the Programme to facilitate infrastructure investment and the improved delivery of infrastructure projects.

Methodology, Roll out, Sustainability

At the heart of this Programme is the adaptation and dissemination of world-leading UK methodologies for international use and their adoption as a matter of policy by the partner countries for their infrastructure projects in order to produce sustainable and lasting change. The programme will deliver via the following activities:

- Support to partner countries for infrastructure planning, business case development including rolling out internationally-adapted models for pathfinder countries, based on the UK’s 5 Case Model and Project Initiation Routemap, and funding direct technical support for these pathfinder countries (in conjunction with private sector consultants); and
- Promoting the UK’s Building Information Modelling (BIM) methods and standards that optimise the design, build and operation of key infrastructure, by funding development of local models and training.

Benefits

The programme’s appraisal case estimated that it would deliver an estimated £1.18bn in primary benefits (aggregate uplift in programme country GDP) over the first 10 years. In addition, it estimated the programme would deliver £452m in UK exports (both through UK consultancy wins and increased exports in goods) over 10 years. The above figures are based on the impact in just the three pathfinder countries over a relatively short period - the actual overall impact could potentially be higher, since this programme is designed to produce permanent change and to have far-reaching, potentially global impact.

Summary of developments since the previous Annual Review

During 2019-20, the GIP entered full delivery phase, with the delivery partners (IPA and CDBB) undertaking a range of capacity-building activities in market supported by their commercial partners, PwC and Mott Macdonald. These activities have been broadly successful, with a high level of participation by public and private sector organisations in the partner countries. In parallel, the GIP has also built strong relationships with a number of Multilateral Institutions, including the World Bank, the Inter-American Development Bank and with national partner orgnisations in Tier 1 countries.

As a result of Covid-19, the programme has had to make a number of significant changes during 2020. These have included a pivot to online delivery in March-April, and providing all training and capacity building online, which involved renegotiating contracts with the commercial partners, which was successfully achieved by the Programme Team, incurring no additional costs. This shift did not have any impact on the number or level of participation in the planned activities, and the Programme remains on track to deliver or exceed its planned outputs. It also had the beneficial side-effects of increasing the accessibility of training to officials in regional authorities based outside capital cities, making it easier for senior officials to attend, allowing a larger number of participants and increasing female participation in training programmes.

The Programme Team also had to manage a 42% in-year budget reduction for the Programme during July 2020, as a consequence of the reduction in GNI forecasts for 2020 reducing all budgets for ODA programmes, including those within the Prosperity Fund. The Programme Team worked collaboratively with delivery partners to plan these reductions, and minimise the impacts on the delivery of activities in partner countries. As a result of these reductions, IPA’s Phase 3 work was curtailed and activity in South Africa cancelled. The CDBB halted work in Indonesia and Mexico, and reduced work in other partner countries. However, the overall assessment of the Programme Team is that these will not have a significant impact on the delivery of the planned outcomes of the GIP, and this view is endorsed by the Review Team.

### Scope of the Annual Review

The GIP is now approaching the end of its project cycle prior to closure in March 2021. The majority of activity in this AR period focused on programme delivery following the mobilisation period. The Covid-19 pandemic led to a delay in this AR, as a result of which the review focuses on an extended delivery phase of the programme from June 2019-September 2020. It reviews progress against key output milestones, and considers whether work undertaken has positioned the GIP to maximise impact beyond closure, including options for extension.

Specifically, the AR will look to cover four key questions;

1. Is the GIP is meeting the indicator milestones as laid out in the log frame and are the activities, intermediate outcomes and outcomes (where applicable) either achieved or on track towards being achieved?
2. Have the fiduciary risks been properly managed, including value for money, proper use of funds and good financial management
3. Is the programme set up for the expected primary and secondary impacts to be delivered beyond closure: will people in poverty benefit from inclusive growth?
4. Given the proposed closure in 2021, what are the options for the future of the programme? In particular, if the option to baseline to FCDO in the SR is chosen, what would this mean for GIP in year 1 of the next SR period and beyond – what do you recommend?

Additionally, the AR will record overall progress to date, document lessons and make recommendations where appropriate.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
Inclusive Growth and Poverty Reduction
The business case for the GIP estimated it could deliver primary benefits, in terms of an increase in GDP in Vietnam, Colombia and Indonesia of £1,18 billion by 2026-27. These benefits accrue through increased investment in infrastructure. It was anticipated that the majority of primary benefits would be delivered after the conclusion of the Programme in March 2021, due to the duration of the design and construction phases for infrastructure projects, and that the main benefits are generated once these assets are in operation. Therefore, it is difficult to make a full assessment of the impact of the Programme in delivering inclusive growth.
However, the success of the Programme in delivering extensive capacity building work undertaken across the partner countries, and the success in embedding the UK methodologies in institutions and the legal and regulatory framework the three Tier 1 partner countries, Peru and the Multilateral Institutions, suggests that it has the potential to deliver, or exceed the anticipated benefits in the longer term. The UK methodologies and GIP-supported capacity building activities will be used to deliver a range of projects that will promote inclusive growth, including:
- £1.6 billion of infrastructure investment in northern Peru, to improve connectivity and mitigate the impact of climate change;
- £2.5m invested in developing the business case for £100m of investment in the delivery of four infrastructure projects in Colombia using the 5CM; and
- the Urban Mass Transport Programme in Greater Bandung across 6 cities, costing an estimated £6.22 billion, which is supported by the World Bank, the Swiss Government and the Indonesian Government, and a hydroelectric power project in Vietnam, for which the World Bank are providing £500m of loan finance towards a project with an estimated value of c£750m.

It is also likely these methodologies will be used in the delivery of further projects in Vietnam, Brazil and Mexico.

Whilst these programmes and projects provide a high level of confidence in the delivery of the projected benefits, it is less certain that these will be delivered over the timeframe in the business case. Achieving this would require a number of these projects to be completed and in operation by 2026-27, and it is not yet clear as to whether this is a realistic possibility.

Climate Change

The GIP has not fully integrated climate change considerations from the outset of the Programme, although there have been some successes in relation to deploying the UK methodologies in relation. Climate change was not a central focus of the original Propserity Fund, or a priority objective of the initial Programme. Despite this, both the 5CM and BIM have the potential to be used as powerful tools to improve the planning and design of infrastructure to minimise carbon emissions and wider environmental impact. In retrospect, this represents a missed opportunity to maximise the impact of the GIP.
However, the delivery partners and posts involved in the delivery of the GIP have worked to ensure these methodologies support wider UK Government policy on climate change, to integrate climate and sustainability considerations into the methodologies and training materials, and also to ensure the methodologies are used to support projects that will reduce carbon emissions and improve sustainability. The IPA also plans to undertake a green update of the international versions of the 5CM/PDR methodologies during 2020. The 5CM will support the implementation of an infrastructure investment programme in Northern Peru that aims to mitigate climate change. The Spanish translation of the 5CM materials is also likely to be updated to include more information on how to integrate climate considerations to infrastructure planning and design. The Programme in Brazil is also exploring opportunities to use the 5CM to support projects funded by green finance providers. The Programme Team have also been able to decline to support high carbon emitting projects (e.g. supporting the use of BIM to deliver a proposed LNG project in Energy City, Vietnam), in favour of ones that are more sustainable, in this case a hydropower project.
Gender & Inclusion
There has been significant progress made by the Programme Team to address G&I shortcomings identified in the 2019 Annual Review. Firstly, technical delivery partners have brought in G&I expertise (in-house and via commercial suppliers) while also leveraging guidance from FDCO teams in the UK and at post (when available). In addition, IPA draw on valuable support from the Work Opportunities for Women helpdesk and the Disability helpdesk, and have participated in the PF G&I Champions network.
Secondly, technical delivery partners (supported by commercial suppliers) identified valuable G&I entry points across the different GIP planned strands that culminated in the development of G&I actions plans for the 5CM/PDR and BIM.[3] These were later integrated into an overarching GIP G&I action plan that was recently approved by the Social Development Adviser (SDA) in the FCDO.
[3] CDBB/Mott Macdonald also undertook an impact assessment for GIP countries.
There is evidence that technical delivery partners have made progress in implementing their respective G&I action plans. For instance, a gender-balanced audience of training participants has been promoted; trainings are being conducted in an inclusive manner, using inclusive language and examples; G&I commitments have been incorporated into MoUs; G&I has been integrated into GIP training related materials and into the 5CM/PDR adapted international and local guides. Of relevance was the international 5CM guide with significant resources spent to ensure that G&I was fully mainstreamed across all cases while including an Annex where further G&I actions through the infrastructure project cycle with the potential to be transformative were identified. It was noted that the Social Development Advisor (SDA) in the FCDO accountable for the programme still has to review main deliverables to ensure earlier concerns have been satisfactorily addressed.
Phase 3 pathfinder projects that are expected to be delivered via Trust Funds in Colombia and Indonesia will also provide opportunities to integrate G&I. At present, G&I has already been included in the selection criteria for all pathfinder projects. The partnership with the World Bank in Indonesia provides adequate G&I rigour as projects will have to adhere to the World Bank’s environmental and social requirements. Similarly, in Colombia, applicants to the Pre-Investment Fund (PIF) will have to align with the International Finance Corporation Performance Standards on G&I issues. It is important to mention that the support for the 5CM from the G20 and MDBs creates an external incentive for countries to adopt the methodology, including G&I dimensions, as a means of accessing international finance for infrastructure projects.[4]
[4] Source: PF E&L, Cycle 1 GIP Evaluation report, September 2020.
However, the fact that G&I was not mainstreamed at programme inception may lead to some missed opportunities to maximize G&I-related outcomes across GIP. For instance, G&I consultative groups could have been pulled together to inform G&I action plans. GIP methodologies have the potential to achieve systemic effects with respect to G&I in infrastructure as it influences how infrastructure projects are selected, designed and implemented. The focus on ensuring gender balance in delivering training may also help to increase opportunities for women to participate in the planning and delivery of infrastructure projects, and progress in their careers in a traditionally male-dominated industry, due to their training in industry-leading methodologies.
Annual outcome assessment (Secondary Purpose)
The GIP continues to have clear linkages to Secondary Benefits (SBs), in line with the business case. In the short term, SBs achieved will be more likely to emerge in the upstream stages of the infrastructure cycle in the form of advisory services. In that regard, UK firms are well placed (and have a competitive advantage) given their experience and skills with GIP methodologies. During this year, some initial evidence has emerged in this vein that will be reinforced when the two Trust Funds (Colombia and Indonesia) pilot demonstration projects before completion of the Programme. Of relevance is the government-to-government reconstruction contract signed in June 2020 with the Government of Peru to provide technical assistance to the Reconstruction Authority where GIP did contribute to strengthen the UK commercial officer. The programme team estimates that UK companies will derive direct benefits from contracts worth approximately £100m worth from this agreement alone.
In the longer term, GIP is expected to lead to downstream SB benefits, as the systematic application of GIP methodologies in target countries should increase the pipeline of bankable infrastructure projects, creating commercial opportunities for UK firms and other international investors while increasing the investors’ confidence level. This is expected to be amplified with the endorsement of the GIP methodologies by the Multilateral Development Banks.
Soft power is another SB that has been emerging. GIP technical delivery partners (in particular IPA) have a strong reputation after years of building relations with key government stakeholders and are highly regarded by key senior national decision makers. This has indeed facilitated the buy-in of GIP methodologies, which will contribute to achieving primary purpose in the long term.
Finally, during this year capacity within DIT to support opportunities created by the Programme has improved. DIT has appointed a SB advisor to GIP who is in the process of enhancing coordination and communication among delivery partners, including country stakeholders so business opportunities can be identified in a timely manner and transmitted to UK businesses. The SBs plan was updated in consultation with DIT, which is intended to be revisited during Autumn 2020 in light of Covid-19 and ODA cuts.

Overall output score and description

The conclusion of the Review Team is that the GIP is on track for successful delivery, and merits an overall output score of A+. This reflects the significant progress made to date, and also the potential for further progress to be made before the closure of the Programme, as well as the longer term impact of the capability-building activities undertaken and the embedding of UK methodologies in the approaches of partner countries and the Multilateral Institutions.

Key Lessons

Programme Development and Adaptation: When there is a need to make significant adjustments to the budget or delivery model of programmes, there should be proactive and timely consultation of key partners and other stakeholders. This particularly applies to FCDO posts supporting implementation, which are responsible for maintaining relationships with local stakeholders. Looking to the future development of programmes, posts should also be involved in the design of these and planning for their implementation, to advise on local politics and institutions, and how the programme can engage these. This will help ensure a reasonable balance between programme-level objectives and oversight and effective local delivery of these.

Review of Primary Benefits: The Programme Team should undertake a re-evaluation of the scale and timing of the primary benefits, and how these are calculated, with a view to identifying a more realistic timeframe for the realisation of these, taking account of the duration of the construction phase before these become operational, and also the benefits of the Programme in all countries where activities have been undertaken. This can then inform the development of future business cases for infrastructure programmes and investments.

Commercial: The Review Team would strongly recommend that any forward structure for the programme (or for programmes with similar objectives) put in place sufficient central commercial support and contract management capacity before MoUs and contracts with delivery partners are signed. This will help to ensure agreements are of a high quality and supported by effective oversight and communication structures from the outset, and help to avoid any confusion over lines of accountability and/or suppliers going off track. A devolved contract management structure could also potentially be considered to reduce the number of relationships that need to be managed centrally.

Key Actions
The recommendations of the Review Team are set out in the Summary Section.
Summary of changes to the log frame since the last Annual Review
Upates have been made to the IPA and CDBB project logframes to reflect the following changes:
- Covid-19 mitigation replan affecting outputs, intermediate outcomes and outcomes (May/June 2020); and
- ODA cuts replan affecting outputs, intermediate outcomes and outcomes (Aug/Sept 2020).
In addition, a programme-level logframe was created with two aims:
- For ease of Prosporo reporting to PF Portfolio Board; and
- For use on Annual Review.
Work on this programme-level logframe was disrupted by ODA-cuts and CSR preparation during August/September meaning the output assessment had to be made against the indicators in the separate project-level logframes for IPA and CDBB.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Adapted GIP (IPA) methodologies and materials rolled out internationally (in target countries), incorporating concepts of inclusion and sustainability
Output number per LF		IPA - 1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 1a: International adaptation of Infrastructure Business Case and PIR materials approved by IPA	30/06/20 – Scale of indicators, 1-5 / Final adapted (initial) International materials completed and approved by IPA. / 5CM International materials approved by BBC Standards Board and materials published on .Gov. / PIR International materials approved by IPA and published on .Gov. / International materials reviewed and (further) adapted and approved by IPA. / MDBs and IFIs and international bodies adopt and promote 5CM international guidance and principles.	5CM = 3, PDR = 3 / Milestone 5 will be achieved throught the pathfinder demonstrator projects, with agreements now signed for Colombia, and close to finalised with Indonesia. / 5CM = 3, PDR = 3 / Milestone 5 will be achieved throught the pathfinder demonstrator projects, with agreements now signed for Colombia, and close to finalised with Indonesia.
Output Indicator 1b: Number of further local adaptations of Infrastructure Business Case and PIR materials approved by IPA	30/06/20 – 2 / Target is 2 - achieved	2
Output Indicator 1c: Number of landscape reviews completed for Tier 1 countries	30/06/20 – 2 / Target is 2 - achieved	na
Output Indicator 1d: International adaptation of Infrastructure Business Case and PIR training approach/plan, course, exam and certification	30/06/20 – 2	5CM = 2, PDR = 2
Output Indicator 1e: Number of local adaptations of Infrastructure Business Case and PIR training approaches/plans, courses, exams and certifications	30/06/20 - 2	5CM = 2, PDR = 1
Output Indicator 1f: Concepts of inclusion and sustainable social and environmental development mainstreamed into all GIP products including: International Infrastructure Business Case Guidance, locally-adapted Infrastructure Business Case Guidance, PIR, International Infrastructure Business Case Training Course, training plan (including training delivery and materials), socialisation (including in tier 2 countries and communities of practice).	30/06/20 – Scale, 1-4 / First draft Sustainable Development approach submitted by PwC and reviewed by IPA. / Sustainable Development approach agreed. / Concepts of inclusion and sustainable social and environmental development mainstreamed into all GIP training products. / Final adapted BC & PIR document pack submitted to FCO for G&I review	4

Output Title	Technical assistance to partners² to provide the tools, training and qualifications to apply GIP methodologies¹, supported by established organisational and professional networks
Output number per LF		IPA - 2	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 2a: Number of partner² Government officials (central and regional), and other candidates, that have completed Infrastructure Business Case and/or PIR training in Tier 1 & Tier 2 countries (disaggregated by location (central/regional) gender, etc)	31/03/21 – 378 / T1 5CM = 180 / T2 5CM = 90 / T1 PDR = 60 / T2 PDR = 48	349 / Brazil = 30 (Nov'19) / Indonesia = 110 (Jul'19-Feb'20) / Brazil = 101 (24% female) / Colombia = 21 (67% female) / Indonesia = 33 (48% female)
Output Indicator 2b: Percentage of partner² Government officials (central and regional), and other candidates, that have completed Infrastructure Business Case and/or PIR training in Tier 1 & Tier 2 countries and evaluated the course (content, materials and trainer) at an average score of at least 3 out of 5	30/06/20 – 80%	100%
Output Indicator 2c: Number of Infrastructure Business Case- and/or PIR trainers newly accredited under GIP	31/03/21 - 50	9
Output Indicator 2d: Proportion of candidates who have passed Infrastructure Business Case exams	31/03/21 – 50%	99% / (Target to be revised in line with ODA cuts –yet to be agreed with FCDO and PWC)
Output Indicator 2e: Adapted International Infrastructure Business Case/PIR resources available on a web-based platform	31/03/21 - 4	0

Output Title	Pathfinder projects for application of GIP methodologies for tier 1 (x2) countries successfully identified, selected and rolled out internationally (in target countries), incorporating concepts of inclusion and sustainability
Output number per LF		IPA - 3	Output Score	A
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 3a: Shortlist of pathfinder projects developed with partner countries in accordance with agreed selection criteria	31/03/21 - 2	NB: Board approval obtained to shift this deliverable from individual projects to Trust funds.
Output Indicator 3b: Number of projects across national public clients selected as pathfinders for the application of the GIP methodologies	31/03/21 - 2	NB: Board approval obtained to shift this deliverable from individual projects to Trust funds.

Output Title	Technical assistance to support regulatory and policy change, embedding GIP methodologies and capacity building at scale across national public infrastructure clients, industry suppliers, donor organisations and academia
Output number per LF		IPA - 4	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 4a: 5CBM: Number of countries demonstrating (evidence of) willingness to embed GIP methodologies over the long-term³ (IPA)	31/03/21 – Scale 1-4 / x2 MOUs signed with GIP partner countries / Senior sponsors identified for x6 Tier 1 countries / Established relations with officials in x3 Tier 2 countries (e.g. lead agency and other stakeholders confirmed, MOU signed, training strategy / schedule agreed) / Senior sponsor identified for South Africa and 2x Tier 2 countries	3 – on scale
Output Indicator 4b: 5CBM: Number of events (workshops / roundtable meetings / public events / country visits) hosted by the country sponsor with relevant stakeholders (public sector / private sector / investors / civil society / academics) (PwC & IPA)	31/03/21 – 8 / (March 2020) 16: Indonesia = 3, Colombia = 4, Brazil = 6, Mexico = 2, Peru = 1	24
Output Indicator 4c: GIP change management strategies and plans developed and maintained for target countries	31/03/21 - 2	2 – Indonesia, Colombia

Output Title	Built and maintained relationships, mutual trust and commitment for long-term collaboration between the UK and the partner country
Output number per LF		BIM - 1	Output Score	A++
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 1a: 'Number of countries demonstrating evidence of willingness to partner with the UK on infrastructure development over the long-term (e.g. signing of an MOU, or other form of senior sponsorship e.g. EFD - Economic & Financial Dialogue or Infrastructure Task Force Agreement)	30/06/20 – 5	6 / MOUs signed: / Vietnam - July 2018 / Colombia - June 2018 / Indonesia - July 2018 / Brazil – 2017 / Mexico - Letter of Intent signed with Hacienda / Peru - MoU signed by Ministry of Economy
Output Indicator 1b: 'Number of partner organisations with senior sponsor on GIP work assigned	30/06/20 - 6	6 / (Indonesia, Colombia, Vietnam, Mexico, Brazil, Peru)
Output Indicator 1c: 'Number of workshops, public events held and country visits hosted by the country sponsor with relevant stakeholders (public sector) - e.g. workshops, and roundtable meetings	30/06/20 - 31	38 / 38 / Vietnam (5) Indonesia (2) Colombia (5), Brazil (2) Mexico (3) Peru (2) Vietnam (2) Peru (2) Vietnam (1) Indonesia (1) Colombia (1) Mexico (1) Peru (1) Peru (1) Indonesia (1) Mexico (1) – inbound Peru (1) – planning Brazil (1) – planning Colombia (2) - strategy & framework Indonesia (1) - planning

Output Title	Technical assistance to support regulatory and policy change, embedding GIP methodologies and capacity building at scale across national public infrastructure clients, industry suppliers, donor organisations and academia
Output number per LF		BIM - 2	Output Score	A
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 2a: Number of public statements to implement a national BIM policy in the partner country, e.g. referencing "target BIM by year xxxx"	30/06/20 - 5	5
Output Indicator 2b: 'Number of plans developed to outline the high-level policy and programme level objectives (why BIM)	30/06/20 - 5	4 - Vietnam (1) Colombia (1) Mexico (1) Brazil (1)

NB: There is no BIM – 3 (legacy numbering system)

Output Title	Plans developed for national BIM programme and framework development (aligned with UK/International)
Output number per LF		BIM - 4	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 4a: 'BIM national strategy and Implementation plans developed, aligned with principles of UK/International practice	30/06/20 - 5	6 / Vietnam (1) Indonesia (1) Colombia (1) Mexico (1) Brazil (1) Peru (1)
Output Indicator 4b: 'Number of countries with sufficient resource assigned to develop a BIM legal and technical framework and proposed to adapt from UK/International practice	30/06/20 - 4	3 / Colombia, Vietnam, Peru
Output Indicator 4c: 'Number of countries with a BIM programme rollout plan (capacity building, pilot projects) produced by the partner government team	30/06/20 – 3	4 / Columbia, Vietnam, Peru, Brazil

Output Title	Capacity built of partner government central policy officials for implementing the UK programme methodologies
Output number per LF		BIM - 5	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 5a: Number of partner Government officials who have completed UK BIM policy training/workshops	30/06/20 - 220	259 – CDBB training visits to Vietnam (Sep18= 10, Mar19=7 Apr19=10), Colombia (Oct18=10 Mar19=10), Indonesia (Mar19=35), Brazil (Mar19=25), Mexico (Apr19 =20 ), Peru (Feb19 = 4) Vietnam (Jul19=4, Sept=15), Peru (Aug19 = 20) Colombia (Oct19=21), Peru (Nov19 =28) Peru (Feb20=32; male=20, female=12) Peru (Jun20=3: male=1, female=2) Peru (Sep20=5: male=3, female=2)

Output Title	Technical assistance to support regulatory and policy change, embedding GIP methodologies and capacity building at scale across national public infrastructure clients, industry suppliers, donor organisations and academia
Output number per LF		BIM - 6	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 6a: 'Number of pilot projects (social /economic infrastructure) identified across national public clients to implement elements of the UK BIM methodology	30/06/20 - 6	4 - Vietnam currently have 3 pilot projects underway, Ministry of Health, Ministry of Agriculture and Ministry of Transport, using BIM guidelines which refer to PAS 1192. Peru ARCC (1).
Output Indicator 6b: 'Number of Industry/academic events (e.g. conferences/training) held (with direct GIP involvement)	30/06/20 - 11	13 - 2 held in Colombia (see indicator 1C) 1 in Brazil in March 2019, Vietnam (NUCE BIM day, Cigos), Colombia (3 CCI, Camacol, transparency event) Peru (Infrastructure Task force), (BIM Show Live Feb) Brazil (3 - BIM Forum launch, SEBRAE, DIT water & sanitation).
Output Indicator 6c: 'Number of national / sub-national Public officials trained on BIM in procurement and projects (e.g. the lead champions for implementing BIM in projects, local trainers who will train other public officials)	30/06/20 - 550	1495 - Vietnam Nov 19 - MARD (30) MOT (47) MOC (31) MOIT/EVN (135) MAUR(58), Colombia (116 (62 Male, 54 Female) / Peru (361 (246 Male, 115 Female) / Mexico (51, (37 Male, 14 Female) / Vietnam (51 (41 Male, 10 Female) / Colombia: PMs (74, 50 male, 24 female) / Brazil: Fundamentals (236, 130 male, 106 female), / Peru: Uses (265 - 178 male, 87 female) / Indonesia: ISO (40 - 24 male, 16 female)

Output Title	Identification and selection of suitable Pathfinder projects, for application of GIP methodologies
Output number per LF		BIM - 7	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 7a: 'Number of countries where pathfinder project selection is underway	30/06/20 - 1	1 - Vietnam
Output Indicator 7b: 'Number of BIM Pathfinder projects that have commenced	30/06/20 - 1	1 - Vietnam
Output Indicator 7c: 'Number of artefacts (eg tender requirements, BEP, EIRs) showing the use of UK BIM Methodology on Pathfinder Projects	30/06/20 - 1	2 – Vietnam (procurement documents and BEP)

Output Title	National BIM legal & technical standards (with essential elements aligned with UK/international practice) are defined
Output number per LF		BIM - 8	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Output Indicator 8a: Number of countries with BIM legal & technical framework scope defined	30/06/20 - 3	2 – Vietnam, COlumbia
Output Indicator 8b: 'Number of countries that have adopted the principles of ISO 19650 in definition of framework	30/06/20 - 1	2 – Vietnam, Colombia

Key Points
UK Methodologies
- MoUs were signed with the Tier 1 countries (Vietnam, Colombia and Indonesia) in 2018, and the commitments have subsequently been implemented. An MoU was also signed with South Africa though will not be fully implemented due to the ODA cuts required in mid-2020.
- In relation to Tier 2 countries, MoUs have been signed with Peru and Brazil, and a Letter of Intent agreed with Mexico.
- The UK 5CM guidance has been successfully adapted to the international context (and translated into Spanish and the local language in Indonesia), with involvement of key stakeholders.
- The UK PDR guidance was adapted to the international context for middle income countries, and includes the concepts of sustainability and transparency.
- There is good evidence that G&I and climate/sustainability considerations have been integrated into the international adaptations of the 3 methodologies, training materials, and identification of pathfinder projects over the past year. IPA and CDBB G&I action plans have been effective in driving progress on the former. Stakeholders are able to point to clear examples where these considerations were made a focus in training (e.g. case studies on how to design infrastructure that is fully accessible from the outset), and/or were brought in to identifying which pathfinder projects for support (e.g. supporting a commuter rail project over airport construction in Indonesia). A final step that needs to be completed to ensure full G&I alignment is to allow the FCDO’s SDA to review the finalised materials – the log frame suggests this review was planned, but by the account of the SDA it has not yet happened.
- The team delivered a significant achievement in Colombia: the team made a significant achievement by supporting the incorporation of the BIM concept in the National Council for Economic and Social Policy (CONPES) for digital transformation in November 2019.
- BIM has made rapid and sustained progress in Vietnam. In Vietnam, an MoU has been signed with the Ministry of Construction, a steering committee and academic forum established, a technical framework defined and a pathfinder project selected with Vietnam.
- Progress on BIM has been more limited in Indonesia, with the CDBB not finding an easy entry point within a complex institutional environment, changing its target partner Ministry during delivery and effectively running out of runway
- ISO 19650 drafts are also in development in Brazil, Colombia, Peru and Vietnam, which provides a technical framework aligned with UK principles.
- The G20 has adopted the UK’s 5 case model approach and issued it as a global good practice standard in its “Good practice for the development of the Project Business Case” (2018).
- The Multilaterals’ platform for governments to record their infrasrture projects on and for Multilaterals and lenders to view investement opportunities (called SOURCE) is being reconfigured to the 5 case model – so that the 5 case methodology will effectively be promoted by the MDBs around the world.
- The office of the President in Colombia has required the infrastructure ministries to adopt the 5 case model for their infrastructure projects going forward. MOUs have been signed.
- The Indonesian government has already used 5 case tools to screen its government list of national priority projects and has committed to adopting the 5 case principles in the Government Work Plan (RKP 2020) which is being formalised by Presidential Regulation.
- Trust funds have been set up with the World Bank in Indonesia and Inter American Development Bank and Colombian state bank in Colombia, to showcase the methodologies on demonstrator programmes (with all funds programmed to be spent by 31 March 2021).
- The EBRD is applying the routemap methodology on its Samarkand road project.
- Overall, take up of the UK methodologies globally has been far more extensive than planned, and there is the potential for these to achieve a wider impact than originally assumed in the business case.

Capacity Building
- Since training began, 600 officials have been trained worldwide on the 5CM foundation and practitioner courses. 295 have been trained in Brazil, Colombia and Indonesia (and results are due to be reported from Mexico and Peru shortly), with trainees achieving a 99% pass rate and positive feedback. The programme continues to receive requests for 5CM training from a range of stakeholders, including some the programme has not previously engaged with.
- 1,495 officials have received training in BIM in the partner countries as of 30 September 2020.
- Progress has also been made in including more women in capacity building activities delivered, with gender parity achieved or exceeded in 5CM and PDR trainings in Colombia and Indonesia, though female participation lags male participation in other country settings. This is important as construction is generally a male-dominated industry in target countries, so upskilling women in industry-leading methodologies increases both their employment prospects and likelihood of inclusion in planning future infrastructure projects.
- Although there are only 9 trainers accredited under the GIP, partner institutions in Indonesia and Brazil have expressed their intent to become Accredited Training Organisations for the delivery of the 5CM. The IADB, World Bank and Brazil National State Bank (BNDS) have also expressed interest.
- The programme has successfully moved from face to face traiing to remote training. Demand for training already far outstrips the capacity of the programme to supply. Original class sizes were 20 each. For the latest training class (in Colombia) there were 150 applicants – and the class size was expanded from 20 to 60. Using the remote facility, IPA are now training officials based in regions as well as the main cities in partner countries.
- In summary, demand for training has been higher than originally assumed, and the GIP is adapting to providing a greater volume of training across a larger number of regions.

Sustainable Impact
- During this year, the programme decided to structure Trust Funds as the delivery model for IPA-Phase 3 in Colombia and Indonesia, which was considered by the programme team to be the best delivery option for maximising efficiency and programme impact. The programme has also had success in leveraging co-investment in these Trust Funds from government and multilaterals (see below).
- Colombia: A Pre-Investment Facility (PIF) housed by the local GIP partner, the national investment bank (FDN) with the participation of IDB and GIP was structured, initially investing GBP 1 million each. However, after the ODA cuts, GIP decreased its participation to GBP 550,000 but maintaining its equal voting rights. They have already selected 4 projects that will benefit from the UK methodologies. Procurement has already started.
- Indonesia: IPA will leverage on an existing World Bank Trust Funf for the Urban Mass Transport Programme in Greater Bandung to test the pathfinder project.
- These trust funds will continue after the scheduled end date of the Programme, and provide a platform for further investment, ensuring the sustainability of the initiatives supported by the Programme. The endorsement of the G20 will also help to deliver this, and encourage the wider adoption of the UK methodologies.
- The training progamme has been set up with an international accreditation and exam process and we are building a network of accredited training organisations (including the multilaterals) so that training can continue on a commercial basis even after aid funding has finished.
- CDBB has adopted the approach of seeking to develop strong local ownership on BIM strategies, combined with with adequate resourcing, of systemic transformation programmes. Alignment with UK principles is assured through the local implementation of ISO standards, and the delivery of a UK knowledge product toolkit developed by the GIP team.

Summary of responses to issues raised in previous Annual Reviews
The Annual Review in 2019 made a number of recommendations in relation to the delivery of the Programme, ensuring value for money, improving the commercial management of the Programme and strengthening monitoring and evaluation. The Review Team was presented with clear evidence that the Programme Team had taken action on the basis of these recommendations, and made changes to the Programme to improve its operation. The key recommendations and actions undertaken in relation to these are summarised below:

1)      integrating G&I considerations within the objectives of the programme, the methodologies, and the delivery of capacity-building activities in partner countries, as well as ensuring there is greater focus on these issues within the Programme governance mechanisms. This has resulted, for instance, in a significant increase in the level of female participation in training programmes, and also the inclusion of standalone modules and case studies relating to G&I being included in training materials;

2)      ensuring robust and effective budgeting, financial planning and monitoring, to mitigate financial risk. The Programme Team and delivery partners have introduced stronger and more regular reviews of budgets and monitoring mechanisms to achieve improved oversight. A supplier self-audit process has also been introduced, to provide an additional level of scrutiny, and to ensure FCDO has the ability to audit supplier financial performance;

3)      reviewing delivery resources, including within delivery partners, to ensure the Programme has access to the right skills and knowledge, and increasing contract management capability. This has resulted in additional commercial capability being brought into the programme, and greater resources linked to the integration of G&I across FCDO, the delivery and commercial partners; and

4)      reviewing the log frame, including output indicators and milestones, to consolidate these, ensure consistency, and enable more accurate and effective MREL. This has been undertaken, and the revised log frame, outputs and indicators are partially assessed in this Annual Review. However, some further work is needed to establish clear links between the programme and project-level log frames, and ensure a consistent approach is used for logging updates across the PT and delivery partners (as discussed in the MREL section).

Recommendations

The recommendations of the Review Team are included in the Summary section.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key cost drivers and performance
The Programme has continued to manage its expenditure in line with the agreed budgets. Spending in FY2018/19 was £2,551,870, against a budget of £2,366,000. Whilst this represents 108% spend against budget, this was previously planned and agreed with the JFU, and followed an underspend in FY2017/18 (when £571,729 was spent against a budget of £704,782). It was also in response to a request from Prosperity Fund to accelerate delivery and associated spend in order to balance the portfolio; and in practice, this increased expenditure has enabled activities to be undertaken more quickly, and resulted in less disruption from budget reductions in FY2020-21.
For FY2019/20 programme spend was £5.5m against a budget of £6.3m (the shortfall was due to the postponement of planned training and support visits during Jan-Mar 2020). The Programme began the year with a budget of £9.0m, which was reduced to £5.25m at mid-year due to a reduction in ODA budgets as a factor of the fall in GNI due to Covid-19. The main areas of spend over the year were in relation to the delivery of capacity-building activities, production of international and national UK methodologies related guidance to support Programme outputs and outcomes. This reflects the build-up of programme activity by Govt partners IPA and CDBB, and full delivery mode by Mott MacDonald and PwC, their respective commercial delivery partners.
As a result of underspends in previous years and ODA budget reductions, it is estimated that overall expenditure over the life of the Programme will be £14m, rather than the budgeted £25m. The GIP underspent by £5m over the first 3 years, due to delays in taking forward Phase 3 work supporting implementation of the UK methodologies in partner countries. This resulted in more expenditure being planned for this year, which was then affected by ODA budget reductions, resulting in this funding being removed from the Programme budget. However, this has not had an impact on the delivery of planned activities and outpurs, due to the pivot to online delivery.
Financial spend in Financial Year FY 2019/20
Item	Allocation	Actual spend	£ Variance	% Variance
FCDO staff	£276,554	£198,472	£78,082	-28%
FCDO admin	£120,500	£82,644	£37,855	-31%
IPA delivery costs	£1,130,374	£788,248	£342,125	-30%
CDBB delivery costs	£646,969	£665,161	-£18,192	+18%
Supplier costs (Mott M)	£1,601,946	£1,590,662	£11,284	-1%
Supplier costs (PWC)	£1,973,278	£1,833,855	£139,422	-7%
Post-led Colombia project	N/A	N/A	N/A	N/A
Post-led Peru project	£394,379	£374,902	£19,476	-5%
Inward training/conference visits	£56,000	£15,284	£40,715	-73%
TOTAL	£6,200,000	£5,549,232	£650,768	-10%

VfM Economy
The Programme Team have maintained good control of budgets and costs, and have worked within the budget limits agreed with the Prosperity Fund. The GIP has in place effective tools to track the cost of inputs and activities: monthly budgeting and forecasting for the Programme is undertaken by both government partners and delivery partners; and a monthly Project Cost Report and Activity Based Budget is submitted by the government and delivery partners to the FCDO programme team. These include forecasts and actual spend as well as breakdowns of costs by country/central activity/projects and milestones. This informs FCDO programme team expenditure monitoring, which covers programme personnel, travel and expenses and the costs of delivering programme activities e.g. developing international versions of tools, developing training materials and delivering training courses.
The Programme Team have also worked to ensure that changes required to the GIP due to Covid-19 did not lead to increased costs, and that they were able to work within reduced budgets for the year. The procurement and contract management processes for the commercial partners were sufficiently robust in relation to delivery costs that they have ensured the Programme Team were able to negotiate a fair price for the delivery of activities, and to protect the Prosperity Fund from cost increases. The reduction in the overall GIP budget has not had a significant impact on the activities delivered or the outputs, meaning that the economy and efficiency of spending has increased. The GIP has also consistently underspent over its lifecycle. As a result, it is anticipated that the entire programme is likely to cost £14m, representing 56% of the original budget of £25m. Therefore, the planned activities which have been undertaken, and the outputs which have in most cases been achieved or exceeded, have been delivered alongside a £9m saving in the budget for the Programme, providing further evidence of VfM.
This year, since the deployment of the contract manager in December 2019, procurement shortcomings have been successfully addressed and all is working to good standards. During FY2018-19 FCDO’s approach to contracting and procurement had shortcomings. Because of the need to follow the procurement rules, the procurement process took time to be completed. In addition, the original contracts between the parties were ambiguous and sometimes incomplete. In addition, there was a lack of experience and capacity within FCDO Commercial, and with the programme’s Contract Manager position not being filled until December 2019, despite FCDO efforts. The new contract manager has negotiated contract variations with each of the commercial suppliers in the last 9 months to address gaps in delivery plans. She also has introduced clearer budget management tools which link forecast and actual spend to log frame outputs and outcomes. These changes collectively enable a clearer view on whether partners are delivering on time and to budget, as well as against each of the core areas of activity needed to drive results.
Finally, the Programme Team has not taken forward last year’s AR recommendation about introducing unit cost benchmarking to support assessment of the programme’s VfM in purchasing inputs. They considered that a benchmarking review was not the best approach, as it is harder to undertake meaningful cost benchmarking for services than for products, due to the difficulty in finding comparable services, as there are relatively few suppliers with similar levels of expertise who have delivered similar contracts.  Instead, the Programme Team has in place is the Supplier Self Audit Certificate process, which requires the supplier to review and certify that charges submitted under the terms of the contract have been correctly calculated, and also enables the FCDO to undertake an audit of these charges for a period of 18 months, to verify the accuracy of these, the underlying data (on the basis of open book principles), and investigate suspected fraud or error. This is an effective tool, and will deliver much more meaningful and direct results than a benchmarking review for this type of contract. The Annual Review Team is satisfied with the approach taken by the Programme Team.
VfM Efficiency
The delivery and commercial partners are required to report against a range of output indicators for the Programme aim to enable the assessment of progress towards delivering the key outcomes. These include:
1)	outputs and supporting indicator and metrics in relation to in-market capacity-building activities (e.g. number of training events held, number of attendees, the gender balance of attendees and the pass rate and attendee assessment of the quality of the events);
2)	the number of countries that have taken steps to embed UK methodologies through policy or regulatory change (e.g. through signing MoUs with the UK, the adoption of BIM policies aligned with ISO 19650, or embedding the 5CM in infrastructure programmes); and
3)	the deployment of the UK methodologies in relation to pathfinder projects in countries.
The outputs are also weighted on the basis of their contribution to achieving the outcomes of the Programme and delivering both primary and secondary benefits. For example, delivering capacity building of officials to implement UK methodologies and the deployment of these on pathfinder projects in country is more highly weighted than the delivery of technical assistance in support of regulatory and policy change.

The outputs, indicators and metrics enable the collection and analysis of a range of quantitative and qualitative information about the delivery of GIP activities and the progress made towards objectives in each partner country. This enables an assessment of the efficiency and performance of the delivery and commercial partners, and comparisons of progress to be made, whilst also allowing for the specific circumstances of each country, including its policy and institutional structure, to be taken into account. These indicators and metrics have also been gathered throughout the Programme, and so enable a comparison of the delivery of the Programme before and after Covid-19. Whilst the delivery of some activities has slowed as a result of Covid-19, it is likely that all activities will be completed at the point the Programme concludes, without incurring costs beyond planned budgets.

Overall, the output indicators and metrics demonstrate a high level of efficiency in the delivery of the Programme, which pivoted to online delivery due to Covid-19, whilst continuing to deliver agreed training within the budget and surpassing a number of targets for activity. Over 600 hundred officials and other stakeholders have participated in training programmes in relation to the 5CM and PDR methodologies, with a very high pass rate, and high levels of trainee satisfaction. 1,495 officials have received training in BIM. This shift also enabled both the number of those being trained to be increased and the training of officials from a wider range of organisations (e.g. regional or local government agencies). The number of those trained is significantly in excess of the targets, and will help to embed the UK methodologies within institutions and policies in partner countries. The GIP has also succeeded in embedding the UK approach in the policy and practice of the partner countries. Therefore, the conclusion of the Review Team is that the Programme is operating at a high level of efficiency.

VfM Effectiveness

At this stage, it is anticipated that the GIP will achieve its planned log frame outputs by the time the Programme is closed, and that intermediate outcomes will be emerging. The key evidence supporting this assessment of the effectiveness of the Programme is the impact that it has had in relation to build capacity across officials that will be involved in the application of the methodologies, changes to legislation, regulations or policy in partner countries, and the use of the UK methodologies to deliver specific projects supported by national governments in partner countries and multilateral institutions. These will ensure the sustainability of the activities supported by the Programme. It is also anticipated that there will be additional outputs and intermediate outcomes delivered through initiatives that are not currently captured by the log frame, for example the establishment of the Trust Funds supported by multilateral institutions, that has facilitated the leverage of additional funds to support the application of the 5CM/PDR methodologies in Colombia and Indonesia.

Influencing: Whilst the GIP has been successful, and communications activities focused on stakeholders operating in partner countries have generated support for the Programme, including through active participation and funding, overall, the profile of the Programme remains low with the UK Government and amongst businesses. The GIP should build on the progress achieved during 2019-20 by doing more to communicate key messages about the impact it has had, and also the development of the UK methodologies and supporting training materials that provide the capability to build on the achievements of the Programme in existing partner countries, other countries where there is identifiable interest and through other UK Government aid programmes.

Sustainability: programme has laid strong foundations for the embedding of UK methodologies in partner countries. Yet the process of adoption is subject to a range of factors such as: i) external: whether partner countries make their use compulsory for infrastructure projects, whether methodologies are endorsed by multilateral agencies; and internal: whether sufficient resources are devoted to designing exit strategies to suit different country contexts (for example, identifying the right coalition of actors to partner with), whether these resources are also applied at the multilateral level.

VfM Equity

This year there has been considerable progress to address a lack of upfront G&I mainstreaming in programme activities while implementing G&I 2019 scorecard recommendations. G&I expertise has been brought into the delivery and commercial partners with G&I action plans developed that are at present in implementation stage (for more details please to Section B. Finally, G&I is now an agenda item on the monthly Operations Committee Liaison meeting as recommended by the previous Annual Review.

Assessment of whether the programme continues to represent value for money
Primary Benefits
The GIP business case estimated the Programme would deliver primary benefit NPV of £1,18 billion over the ten-year appraisal period 2017/18-2026/27. Primary benefits were calculated as the uplift in GDP for the three Tier 1 countries (Colombia, Indonesia and Vietnam), delivered through attracting investment in infrastructure. As identified in the previous Annual Review, there is a significant level of risk that the realisation of these benefits is delayed, due to the long time it takes a infrastructure projects to be designed, built and become fully operational, which is the point at which it begins to deliver significant economic and social benefits. The delays in identifying pathfinder projects for deployment of the UK methodologies, and the reduced number of projects on which these will be deployed through the GIP by project completion, have increased the risk of failing to achieve the expected primary benefits by 2027. Limiting the calculation of benefits to the three Tier 1 countries would also exclude benefits delivered in other countries (e.g. Peru), increasing the challenges of achieving the estimated benefits within the timeframe included in the business case. For these reasons, the Review Team concluded that following the conclusion of the GIP, it would be useful to conduct a review of the timing and scale of benefits realisation, with the aim of learning lessons for future programmes.
However, in the longer term, the engagement of partner countries and multilateral institutions through the Programme is expected to significantly mitigate this risk for the adoption of the 5CM (and to a lesser extent PDR), and could potentially generate additional benefits beyond those projected in the original business case. This does not apply to BIM, where one 1 pilot in Vietnam is expected to be completed by project completion.
In addition, demand for the UK methodologies has been much higher than expected (especially in Tier II countries, where primary benefits were not included in the business case) and the outreach could have been expanded if there had been funding to expand the number of countries, or to adopt a regional-based approach. The Programme Team have taken up on opportunities to maximise impacts by engaging with international institutions so methodologies can be embedded in the future beyond the target partner countries. At the same time, the programme successfully mitigated Covid-19 impacts at no extra cost.
During this year we have also observed that there have been fewer synergies than anticipated in the combination of the delivery of the Infrastructure and Projects Authority and Centre for Digital Built Britain methodologies. However, this has not impeded progress, and overall the Review Team concluded that the Programme will deliver VfM in relation to the primary benefits, even if this is not within the timeframe included in the business case.
Secondary Benefits
The Programme business case estimated the programme would deliver £452m in UK exports (both through UK consultancy wins and increased exports in goods) over 10 years (2017-18-2026-27) in the 3 Tier 1 countries. Significant progress has already been made towards this objective through the G2G agreement with the Government of Peru, which will deliver direct contractual benefits to UK firms of c£100m (4-5 times the value of the GIP), with a potential further £1.6bn of other business opportunities linked to the delivery of infrastructure.
Further opportunities are likely to be created through projects funded by multilateral institutions (e.g. the World Bank and Inter-American Development Bank), by leveraging on bilateral programmes (e.g. Colombia) to further embed UK methodologies, and by key government stakeholders involved in infrastructure development in Mexico, Peru, South Africa and Brazil that plan to adopt methodologies post completion using their own funds or through obtaining funding from multilateral institutions.
Commercial opportunities for UK firms are also likely to arise in relation to consultancy activities related to infrastructure project preparation, and also smaller scale opportunities in relation to the delivery of training on the 5CM and BIM. Therefore, the Review Team concluded that the GIP remains on track to deliver and potentially exceed its projected secondary benefits by 2027.
Overall, the performance of the Programme in relation to budget, the delivery of key activities and progress made towards outputs and outcomes is assessed by the Annual Review as representing value for money. Due to budget reductions, the Programme is likely to deliver its planned activities and achieve the majority of its outputs at a lower cost than budgeted for. There is is also emerging evidence that the Programme could in the long term exceed the estimated primary and secondary benefits. During this year, the initial investment in developing relationships with key individuals and institutions in Tier 1 and Tier 2 countries, and in multilateral institutions, has crystallised in commitments to use the 5CM/PDR and BIM methodologies on projects worth over £2 billion, which will deliver primary benefits in the partner countries. The Programme has also delivered secondary benefits (e.g. the G2G agreement with Peru) of 4-5 times its initial cost, and is on track to deliver or exceed the estimated secondary benefits.
Quality of financial management
The team has addressed the recommendations of the 2019 Annual Review[5] and during FY2019-20 the Programme’s financial management has been adequate.
[5] These were related to: i) have adequate budget allocations for FY 2019/20 for each of the programme line items are forecast as accurately so that the source of any under or overspend at the aggregate level is easy to identify over the course of the year; ii) FCO Team to conduct regular checks of a sample of delivery partner invoices each year against individual receipts to assure fiduciary risk. IPA and CDBB should action the same for their respective suppliers (PWC and Mott Macdonald).
The IPA and CDBB report their current and forecast spend on a monthly basis via their project dashboards. These are discussed at the monthly Operations Committee meetings, including variances to forecasts, monthly under/overspends, exceptional costs.
Purchase Orders were created for IPA and CDBB and invoices were submitted for delivery of support to the programme during FY 2018/19. These were scrutinised by the Programme Manager before being passed for payment. Mott MacDonald and PWC submit monthly invoices, with accompanying deliverables schedule, for payment against FCDO Purchase Orders. Each invoice is scrutinised by government delivery partners CDBB and IPA for accuracy and authority is passed to FCDO to arrange payment of the invoice.
The supplier self-audit process also provides for an additional level of assurance of robust financial management, as it requires the supplier to review and confirm that charges made under the terms of the contract have been correctly calculated, through a self-audit certificate. The contract also provides for a period of 18 months when the contracting authority (FCDO) can audit invoices submitted, to verify open book data, and to investigate any suspected fraud or error.

Date of last narrative financial report	12 June 2019
Date of last audited annual statement	12 June 2019

## E: RISK (1 page)

Overall risk rating
During this year, there has been a reduction of the programme risk to a Minor rating, given that the programme is in late stage of implementation with substantial progress made since the last Annual Review. Furthermore, GIP is on track to achieve most of planned outputs by completion.
Overview of programme risks
GIP delivery partners manage risks in an adequate and effective way. IPA and CDBB do proactively identify risks and defines risk mitigation actions with owners and timelines allocated where appropriate. Until March 2020, IPA and CDBB documented and reported[6] their risks to FCDO on a monthly basis at the Operations Committees meetings. Risks were reviewed and when required escalated to the programme risk register.
[6] IPA: risks were documented and reported through the IPA monthly dashboard report and related meetings, and PwC monthly reports and related meetings. For CDBB: a risk register was maintained, which was supported by a project controls meeting held twice-weekly/monthly, depending on need (Source: PF E&L, Cycle 1 GIP Evaluation report, September 2020).
From March 2020, a new collaborative tool (RAID log) was introduced to track and manage risks for GIP as part of the new FCDO governance process. The tool has around 60 risks classified across categories of varying severity and is updated by the government partners, commercial delivery partners and the FCDO fortnightly. Monthly forward look meetings are used to proactively anticipate risks and Strategic country review meetings have been established to continually monitor country status and risks of the programme ‘not landing’.[7]
[7] Source: PF E&L, Cycle 1 GIP Evaluation report, September 2020.
Main programme risks identified are as follows:
      - Resourcing: FCDO, IPA and CDBB each have personnel resourcing challenges that are being managed but preogramme delivery remains at risk from the difficulty and delays in recruiting staff.

      - Covid-19 effects on BIM have resulted in a virtual method of support to deliver the pathfinder project in Vietnam, which may be less effective as this arguably would benefit from a more face-to-face and hands on training/coaching approach with officials. To cope to some extent with this risk, CDBB is putting together a legacy of 30 knowledge products (KPs) while expanding the number of officials trained on BIM.

      - Embedding: Recent ODA cuts have reduced GIP commitment towards the implementation of pathfinder projects (Phase 3), key to showcasing the benefits of the GIP methodologies while accelerating their embedding in Colombia and Indonesia. While this risk has been partly mitigated with the establishment of Trust Funds as a vehicle to deliver the projects (with participation of MDBs, local stakeholders and PF bilateral programmes), and because IPA sit on the Trust Fund boards that make strategic decisions and Embassy teams may be able to take over the role on programme expiry.

      - Sustainability (of achievements and momentum created, post completion to maximize programme impact): BIM Task forces in place in selected GIP countries that are leading on the national digital transformation with the guidance from CDBB/Mott Macdonald will lose traction when the programme is completed unless a transition/continuation plan is put in place;
        - Sustainability: despite high demand and buy-in for GIP methodologies for Tier II countries, progress made is not sufficient for countries to consolidate progress made in adopting and embedding the IPA related methodologies. Despite this, in Tier II countries there is willingness to continue embedding the methodologies by using their own funds or leveraging on the MDBs (for example Brazil, Peru and South Africa).

Outstanding actions and recommendations from risk assessment
Embedding: The Programme Team should undertake an analysis on how operational or planned bilateral programmes in Tier I and II countries can continue with the process of promoting and embedding GIP methodologies.

Sustainability: IPA and CDBB should ensure that there are feasible exit/transition plans in place for each partner country.

## F: COMMERCIAL CONSIDERATIONS (1 page)

Delivery against planned timeframe
Programme delivery is broadly in line with planned timeframes. Notwithstanding the delays caused by the onset of the Covid-19 pandemic from early 2020 in Asia (and then across the world), and the subsequent cuts to delivery plans necessitated by the ODA prioritisation exercise in July-August 2020, the programme and its delivery partners have done well to adapt to change and progress work on multiple fronts.
In particular, the programme’s quick decision to pivot to an online delivery model for all training has enabled it to exceed targets for the number of stakeholders trained. Specifically, the move to a fully online format seems to have increased accessibility for trainees based outside capital cities, and improved the ability of more senior government officials to participate (due to the change to a series of half-day sessions accessed online, which is less disruptive than requiring trainees to take full days out of the office).
The programme is naturally dependent on interest and buy in from public authorities responsible for developing infrastructure in partner countries, so it has been challenging for delivery partners to accurately forecast the level of demand and connected timescales for activities which can only proceed at the pace country partners want to progress. Consequently, some countries have achieved targets faster than expected, such as in Vietnam where demand for BIM support was high from the outset. Demand for 5CM in Tier II Latin American countries has far exceeded expectations. In other settings, work has progressed more slowly and/or through a more phased approach, such as in Indonesia where the complexity of the political environment required greater time for the CDBB team to understand and navigate, and the level of BIM uptake against plans is hence more modest to date. Nevertheless, the programme has made commendable progress in all countries it set out to collaborate with over the past year.
Performance of partnership(s)
The key commercial partnerships are with PwC, who provide support to the IPA in adapting the 5CM and Routemap methodologies and delivering training, and Mott MacDonald, who provide effectively the same nature of support to the CDDB on BIM. While the IPA and CDBB possess the subject matter expertise and bring strong reputations to government partnerships in target countries, their internal capacity to undertake substantial international engagement is limited, so the plan always was to support these projects with the procurement of commercial suppliers.
Both the IPA and CDBB are satisfied with the quality of work delivered and their relationships with the commercial partners. However, the governance model is complex, with PwC and Mott MacDonald being contracted by the FCO programme team, who hold the purse strings, and having to collaborate on day-to-day work with the IPA and CDBB. Several parties mentioned that this had been a source of challenge over the past year with respect to the FCO-IPA-PwC relationship in particular. The lack of a contract management resource within the FCO team at the time the contracts were being signed in spring 2019 meant that several important contractual terms, such as the number of trainings to be delivered, were left undefined for months. As a consequence, several months of work were delivered effectively under IPA’s instruction that in some cases was not formally documented in PwC’s contract.
As recommended in last year’s Annual Review, the programme brought in a new Contract Manager in December 2019, who made good progress in addressing these gaps and putting in place stronger processes to oversee supplier delivery to time and budget during the first half of 2020. Whilst all parties welcomed the increased resource in the FCDO for contract management and many felt that the appointed individual had done an excellent job, the delayed introduction of effective contract oversight unsettled some working relationships that had bedded down between the various partners in its absence. PwC’s technical expertise is also seen to be high, though the PwC project team lacks effective contract management support (from the perspective of the Programme Team).
Changes in the Delivery Chain
There have been no major changes in the delivery chain over the past year, with the same partners and suppliers active throughout. However, owing to the budget reductions necessitated by the ODA prioritisation exercise, Mott MacDonald plans to wind down support to the BIM project and CDBB by December 2020, after which CDBB will carry on as the sole, legacy partner.
Asset monitoring and control
The original UK versions of the 5CM and PDR methodologies are freely useable under open government licence, as are the international ones, and countries are able to adapt these. Similarly, the ISO 19650 standard for BIM is an international standard.
Recommendations
Commercial: Reflecting on this experience, the review team would strongly recommend that any forward structure for the programme put in place sufficient central commercial support and contract management capacity before MoUs and contracts with delivery partners are signed. This will help to ensure agreements are of a high quality and supported by effective oversight and communication structures from the outset, and help to avoid any confusion over lines of accountability and/or suppliers going off track. A devolved contract management structure could also potentially be considered to reduce the number of relationships that need to be managed centrally and, for example, to enable the IPA and/or the CDBB to sub-contract their own project delivery support. However, it is understood the latter was not considered within the current programme due to JFU preference that FCDO maintain oversight of the flow of ODA funds.

## G: BUSINESS ENVIRONMENT (½ page)

How has the business community and business environment responded to the programme?
The business community has responded positively to the programme. Multiple stakeholders commented that – because the 5CM in particular is recognised as a leading methodology originating from the UK, British firms have a reputational and expertise advantage, relative to firms from third countries, in helping partner countries to adopt and apply these methodologies. The potential for secondary benefits in the programme is strong and, in some cases, already being realised. For example, an unexpected consequence of the programme having to scale back delivery plans due to the ODA budget cuts in mid-2020 is that in some settings, such as South Africa, local partners have expressed a willingness to fund the training they were hoping to receive from the programme out of their own budgets. UK companies are in a good position to win methodology adaptation and/or training contracts, and will also have a competitive advantage for any consultancy work applying these methodologies to specific infrastructure projects.
The programme’s strategy arguably has been smart in building exposure and subsequent demand for UK expertise in target markets (e.g. Peru and Colombia), while also advocating for the adoption of these methodologies as an investment prerequisite with multilateral agencies and development banks, the latter of which should create demand for their introduction in further markets. It is notable that the programme has had particular success in raising the profile of UK infrastructure expertise in Latin America, a regional market which traditionally has been difficult for UK engineering and construction firms to break into.
The previous Annual Review recommended that the programme develop stakeholder engagement strategies to reach actors outside the public sector in partner countries, specifically in the private sector, academia and the media. This appears to be happening to an extent on a country-by-country basis, with the programme’s launch in Brazil, for example, taking the form of a multi-agency workshop which regional and national government stakeholders as well as representatives from academia. It is difficult to assess the effectiveness of these individual strategies on a country-by-country basis within the scope of this review, though as the programme enters its final months, it will be important to maximise opportunities for building awareness of – and forward demand for – these methodologies across actors in multiple sectors in each partner country, so that UK firms can effectively pick up where the programme leaves off.
Similarly, with respect to the previous AR recommendation that the delivery partners work with DIT to identify UK firms with the capability to support the delivery of infrastructure projects in partner countries, this appears to be happening on a country-by-country basis, with specific coordination with DIT in Vietnam, Colombia and Peru. For example, UK engineering consultancy Arup had been present alongside Mott MacDonald in training workshops on BIM in Vietnam, putting such firms in a good position to win any forward work.
What role has non-ODA spending played in promoting programme objectives?
There has been no non-ODA funding allocated to the Programme to date.

## H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme’s first MREL evaluation was completed in September 2020 and shared with the review team in the days before the Annual Review commenced. The report provides an overall positive assessment of the programme, noting the strong interest in its methodologies in partner countries and strong reputation of the government delivery partners. It also states that the evidence underpinning the programme’s Theory of Change is sound and suggests the programme will have a positive impact.
Evaluation recommendations advocate for the expansion of the programme beyond 2021 to respond to higher than anticipated demand for GIP support in partner countries, the acceleration of the trust fund models in Colombia and Indonesia to secure the future of pathfinder projects, greater inclusion of the private sector in training activities in partner countries, and greater upfront scoping when planning for any expansion of the programme to new geographies, among other areas. The lessons drawn out and the recommendations made by the evaluators largely are consistent with the observations of the review team, and this report and the evaluation speak well to each other.
While the GIP programme team had not held a cross-stakeholder meeting to discuss the findings of the evaluation prior to the AR, it is anticipated this activity will happen in the weeks following the Annual Review. The plan was to have a number of weeks between the evaluation and Annual Review delivery dates, in particular so that the review team could incorporate the Programme Team’s Management Response in the review findings and take a comprehensive view on how the evaluation is being used by the programme team. However, the multiple challenges of Covid-19 and ODA cuts meant that the Evaluation was unavoidably delayed.
Monitoring progress throughout the review period
Last year’s Annual Review recommended that the Programme Team consolidate project-level log frames into a streamlined programme log frame, ensure all output indicators had milestones and reporting plans in place, and incorporate G&I specific indicators into reporting. Progress has been made on all these areas, with the programme team working with the MR supplier (PA Consulting) to develop a programme-level log frame combining information from the two project-level log frames (owned by IPA and CDDB). A number of updates to indicators and targets have also been made in project-level log frames to reflect changes stemming from delivery experience and the impact of ODA cuts on FY 20/21 delivery plans.
However, on examining the programme-level log frame for this review, it became apparent that there were gaps in information on milestone targets and delivery. The document also lacked clear read across to the project-level log frames. In addition, the programme-level log frame was not revisited to ensure that it was aligned with the programme-level ToC developed by the E&L team in June 2020. The multiple challenges of 2020 meant that the plans to ensure that the programme-level logframe was fit for purpose and that all stakeholders were content were not carried through to the end. As a result of these various issues, the review team were asked to score the programme against the combined 12 outputs from the two project-level log frames (rather than the 4 outputs in the programme-level log frame). This is a shame, as efforts clearly have been made to put in place a more coherent and streamlined programme-level system. However, the missing final 20% of effort required to ensure a systematic approach to updating the programme log frame in collaboration with delivery partners has rendered the previous work somewhat wasted.

Recommendations

Log frame: To enable the Programme to assess partner performance and demonstrate progress at project closure, we recommend that the programme team revisit the programme-level log frame with delivery partners to clarify which project-level indicators and milestones feed into which programme-level indicators, and instate a clear, simplified process – owned by a member of the GIP programme team – for making updates to the programme log frame in step with delivery updates provided by the IPA and CDBB. This review should also ensure the project-level log frames capture all relevant outputs and changes to outputs resulting from the adaptations to delivery models over the past 12 months (e.g. change in focus from initiating pathfinder projects to establishing Trust Funds). A clear process will help to avoid confusion on how and what to score the programme against at project closure, and ensure there can be a fair and objective appraisal of delivery.

Programme Evaluation: For the next (and likely final) evaluation cycle, we recommend the programme team begin early planning with the evaluators to ensure activities can be completed while stakeholders are still available, and that a final, evaluative analysis of the programme’s results and contribution to outcomes can be available in time to feed into any project closure or transition reporting requirements.