MEXICO PROSPERITY FUND

ANNUAL REVIEW 2020

## Summary Sheet

Title: Mexico Bilateral Prosperity Fund / Period of review: July 2019 – June 2020
Programme Value: £60 million		Review Date: 27-31 July 2020
Programme Code: GB-GOV-50-PF-15-MEX (including GB-GOV-3-PF-MEX-911;GB-GOV-3-PF-MEX-912;GB-GOV-3-PF-MEX-921;GB-GOV-3-PF-MEX-922; GB-GOV-3-PF-MEX-923;GB-GOV-3-PF-MEX-924)	Start Date: April 2017	End Date: March 2023

Summary of Programme Performance
Year	2019	2020	2021	2022	2023
Programme Score	A	A
Risk Rating	Moderate	Moderate

#### Progress/lessons since last review

Last year’s Annual Review made 54 recommendations. 13 relate to the Fund as a whole, and were for London to action. Of these, we understand that 8 have been actioned, 4 are in progress, and only one (‘the FCO should develop a feedback mechanism for the cash flow forecast data, even if this is just to recognise that is received and the information is adequate’) is not completed.

The remaining 41 recommendations relate to the Mexico bilateral PF programme. 11 have been actioned, and 21 are in progress. We judge that 7 are no longer relevant, leaving just two relating to secondary benefits to be started (38: ‘The Secondary Benefits Action Plan is updated in line with new guidance…’; and 41: ‘the Secondary Benefits Advisor’s role be better integrated into PT structures’). A gap in filling the PF Commercial Officer position is the reason behind the inability to achieve these two actions. We are assured that they will be addressed when the new PF Commercial Officer starts her role in August 2020.

#### Top 10 recommendations this year

	Recommendation	Detail	Lead
1	Refresh cost-benefit analysis in autumn 2020	B7, D13	Prog Team
2	Set target of Paris compliance by mid 2021	B5, G4	SRO
3	Shift £6m from Energy to other programmes	B8, C(E)7	SRO
4	Develop strategic approach to secondary benefits	B3, G7	Prog Team
5	Encourage roll-out of successes to Southern States	B9	SRO
6	Strengthen non-gender aspects of G&I in programme	B4, D15	Prog Team
7	Strengthen strategic comms back to the UK	G2	Prog Team
8	Improve financial management/performance	D19, F8-9	Energy and Financial Services Delivery Partner
9	Retain Deputy Head but consider using natural attrition	B6, F12	SRO
10	Hold back (or seek extra) evaluation support for the autumn	E8	Prog Team

#### SRO Commentary

I am grateful to the Review team for all their work on the Annual Review, and for their constructive recommendations. It is encouraging to see that the Programme overall has received a strong bill of health, despite all the challenges this year around COVID-19 (impacting on the deliverability and strategic context of the Programme, as well as the overall HMG ODA budget envelope).

We will take forward the Review recommendations, including setting the target of Paris compliance by mid 2021, and seeking to shift some funding away from the Energy programme as well as promoting our energy transition ambitions. I also welcome the recommendation to do more in the South of Mexico – something I have been keen on from the start, given the relative poverty of the southern states compared to the north.

I also very much endorse the recommendations around gender and inclusion (G&I), and strengthening our strategic comms and secondary benefits strategy. These latter two areas are more important than ever in a constrained resource environment, where we need to be able to demonstrate the impact of our Programme and the benefits to the UK.

#### JFU Commentary

We note the Mexico programme’s progress in the year under review. The testing and implementation of programme-supported financial inclusion innovations, for example, is one of several promising developments.

That the programme is broadly on track, despite COVID-19, is an achievement. Programme staff and partners have shown impressive adaptability. Moving training and meetings online has enabled progress. So has good financial management.

The review makes important recommendations which JFU supports. For example, completing planned Paris-alignment activities is important, as is the proposed review of allocations across strands.
#### List of Acronyms

ACROL	Anti-Corruption and Rule of Law
AMAFORE	Mexican Association of Retirement Fund Administrators
AMLO	Andres Manuel Lopez Obrador (President of Mexico)
APF	Agile Programming Fund
API	Application Programming Interface
ASEA	Agencia de Seguridad, Energia y Ambiente (Health & Safety Executive equivalent)
BFA	Bankable Frontier Associates, a private company
C&R	Climate and Resilience
CFE	Comision Federal de Electricidad (Federal Electricity Commission)
CNBV	Comision Nacional Bancaria y de Valores (National Banking and Securities Commission)
COPARMEX	Mexican Employers’ Association (CBI equivalent)
DFID	Department for International Development
EL	Evaluation and Learning
EPI	Energy, Participation, Inclusion (Energy Centres)
FAN	Fintech Adoption Network
FCDO	Foreign, Commonwealth & Development Office
FCO	Foreign & Commonwealth Office
FDI	Foreign Direct Investment
FOSU	Finance & Operations Service Unit
FinTech	Financial Technology
FS	Financial Services
FY	Financial Year
G&I	Gender and Inclussion
GDP	Growth Domestic Product
G2P	Government-to-Public
HMG	Her Majesty’s Government
IBS	Industrial Baseline Study
IDB	Inter-American Development Bank
IFC	International Finance Corporation
ITT	Invitation to Tender
JFU	Joint Funds Unit
KPI	Key Performance Indicator
MoU	Memorandum of Understanding
MR	Monitoring and Repoting
MREL	Monitoring, Reporting, Evaluation & Learning
MSMEs	Micro, Small and Medium Enterprises
NGO	Non-Government Organisation
O&G	Oil and Gas
ODA	Official Development Assistance
ODI	Outward Direct Investment
PF	Prosperity Fund
PM	Prime Minister
PT	Programme Team
SEGOB	Secretaria de Gobernacion (Home Office equivalent)
SLA	Service Level Agreement
SRO	Senior Responsible Officer
SRP	Supplier Registration Portal
ToC	Theory of Change
VfM	Value for Money
WB	World Bank

## A. Introduction and Context

DevTracker Link to Business Case:	www.gov.uk/government/publications/prosperity-fund-mexico-programme
DevTracker Link to Log frame:	Not uploaded yet

The Mexico Prosperity Fund bilateral programme is a £60 million five-year initiative that started in 2017. It aims to reduce poverty by promoting greater inclusive growth in Mexico, working in four areas: Energy, Future Cities, Financial Services and Anti-Corruption and the Rule of Law (ACROL).

Since the last Annual Review, a number of important contextual changes have taken place:

COVID-19. This has most immediately had an impact on programme outputs: principally delays in activities due to travel and other restrictions, and constraints on beneficiary bandwidth. But it has also affected a number of assumptions within the theory of change, and is changing the nature of poverty in Mexico: Q2 GDP fell over 17%, the IMF forecasts a 6% recession by the end of 2020, and Mexican statistics suggest that 90% of businesses have been affected, particularly in the automotive, tourism and retail sectors. There is also a disproportionate negative impact on women, exacerbated by high rates of domestic violence.

1. New approach to UK ODA. Changes in UK GDP have required a £3bn saving to be found from UK ODA, resulting in a £2m saving sought from the Mexico PF programme this calendar year. The Foreign Secretary has clarified immediate ODA priorities: ‘bottom billion’ poverty reduction, girls’ education, climate, COVID-19 and ‘force for good’ (together with maintaining operational capacity).
2. Government policy. In Mexico, the President’s economic policy has doubled down on signature infrastructure projects and an oil/gas-driven energy policy. Meanwhile progress on social programmes and anti-corruption has run into challenges, and the President’s fiscal stimuli to respond to COVID-19 is smaller when compared to other countries. The UK has invested in significant short-term fiscal stimuli and has an increasing focus on climate (with the UK shortly hosting COP26).

All these changes are still taking place at the time of writing this Annual Review, making the prognosis for the future is highly uncertain. Additional political changes are expected from elections in Mexico next July (13 Governor elections, municipal elections in 29 of 32 States, and a new Chamber of Deputies). We have made recommendations based on our best estimate for the future context. Where necessary, we have considered different scenarios. But it means the recommendations below should be treated with appropriate caution.

As with last year’s Annual Review, we have been heavily informed by (and are indebted to) the Evaluation Report – which was produced in May 2020. That report goes into much more detail about programme implementation, and we have attempted to avoid duplication – focusing instead on the larger strategic questions. Constraints on the length of the Annual Review have also limited our ability to get into the detail. As such, this document should be read in conjunction with the Evaluation Report in order to give the full picture of the Prosperity Fund in Mexico.

We are grateful to the programme team and delivery partners, who have been generous with their time in pulling together the documents we have used as evidence to support our judgements below. We are also grateful to the HMG and delivery partner stakeholders with whom we held interviews from 27-31 July 2020 to supplement that evidence. And finally, we thank those in HMG who have provided appropriate quality control. As ever, any errors that remain are our sole responsibility.

## B: Executive Summary

The programme has made significant progress since the last Annual Review. It was launched formally by the Foreign Secretary in Mexico’s Palacio Nacional in August 2019, and formed a central element of the UK-Mexico Partnership for Sustainable & Inclusive Growth signed during that visit. All four strands have moved from inception into implementation. Individual launches for each strand have taken place, with strong evidence of Mexican government buy-in. The theories of change and logframes were refined in the autumn of 2019, with the following adjustments (subject to a further revision planned in the autumn of 2020):

1. Programme: more detail throughout, including clearly-defined primary and secondary impacts (with more gender/inclusion detail on the former); assumptions inserted throughout.
2. Energy: gender-disaggregation at all levels; more gender-sensitive outputs.
3. Future Cities: greater focus on ‘safer, inclusive, resilient and sustainable’ urban transport; reshaping intermediate outcome 2 from digital mechanisms to a pilot-based approach.
4. Financial Services: greater gender-focus throughout, especially for intervention 1; addition of RegTech and interconnectivity outputs for intermediate outcome 2.
5. ACROL: streamlined impact; more detailed outputs; addition of judges workshops and consultancy work on anti-discrimination within beneficiary institutions.

We concur with the Evaluation findings that ‘the design of the programme is sound and aligns well with both Mexico’s National Development Plan and the Prosperity Fund’s objectives’, and that ‘emerging results are promising’. Examples of emerging primary benefit results include changes to national FinTech legislation; incorporating gender/inclusion considerations into anti-corruption procedures in Jalisco; designing safer and more inclusive bus stops in Guadalajara; helping Mexico City identify new, fairer public transport fare structures; launching a FinTech regulatory sandbox and accelerator programme; and helping shape the Government’s economic recovery package in the energy sector. In general we judge the programme is on track to achieve significant primary benefits. One important factor has been the high degree of agility and adaptive programming demonstrated throughout – something we commend. Overall assessment: A.

We also agree with the Evaluation that the programme has ‘supported some early secondary benefits for UK firms’. These are particularly evident in the Future Cities and Financial Services strands: the PF has contributed to export contracts worth £25m in water, £4.5m in airport infrastructure, £4m in fraud detection and £2.7m in financial payments, amongst others. The programme has also generated a longer-term commercial pipeline for contracts in the energy supply chain, cyber, and disruptive/innovative FinTech. And all strands have generated strong ‘soft power’ and network benefits, thanks to a plethora of high-profile launches and MoUs with federal and state-level governments. To maximise the opportunities over the next year we recommend a more strategic approach to defining, securing and communicating secondary benefits (see ‘Business Environment’ below). Overall assessment: A.

One particular strength of this programme has been the mainstreaming of gender and inclusion. The Evaluation notes that ‘the programme has strengthened its potential to improve the lives of women and girls and to promote social inclusion’; we concur. The programme has steadily improved its G&I scorecard over the last two years: all areas are now ranked at least as ‘minimal alignment’ with the Gender Equality Act, and on three of five indicators (design, capability/institutional incentives, and partnerships) the programme was ranked in April 2020 as having ‘potential for economic empowerment for women and girls’. While no areas are currently ranked at the highest level (‘potential for transformation’), and we recommend strengthening non-gender inclusion aspects, this shows a strong trajectory for the programme.

Since the last Annual Review, UK ambitions and guidance on climate mainstreaming have expanded – with a PM commitment that all ODA will be Paris-compliant. We judge that the programme is making progress towards this ambition, but recognise that it requires retrospective changes. We further recognise that the programme is primarily a poverty-reduction one, not a climate one. Nonetheless we recommend that the SRO sets all delivery partners a goal to have ensured appropriate Paris-compliance within their strands by the middle of 2021.

On programme management we concur with the Evaluation that ‘a capable programme team and strong cross-embassy coordination are supporting the programme. There are good systems for management, governance and achieving value for money’. We would add that the delivery partners are capable, experienced and committed to the goals and spirit of the Prosperity Fund, and there is a strong and productive relationship between delivery partners and the Embassy team, and between the Embassy team and a more coherent London support/oversight function. Important lessons have been learnt over the last year, such as stronger contract management skills, the embedding of the ‘Virtual Team’ model for cross-programme coordination, and a fusion-approach to prosperity, one of the most advanced we know in the HMG network. This is in part thanks to the creation of a new Deputy Head role, which we recommend maintaining.

We judge that the programme has responded well to COVID-19. Leadership has provided strong guidance around mitigation and adaptation, and a helpful framework (built around four Mexican government priorities of health, MSMEs, gender and green) to guide delivery partners. Particular credit is due to the Future Cities programme for designing/approving within two weeks a £750k support package for five large cities. Quick take-up of online tools has mitigated the immediate impact of the pandemic (although care is needed in future to prevent this from reducing programme take-up from older and poorer populations), and each strand has demonstrated good thinking about longer-term adjustments needed. Assumptions within the theory of change and logframes are on track to being updated to take into account the ‘new normal’.

In the absence of an updated appraisal case, we found it hard to make a recommendation on allocations between strands. Nonetheless we recognise the urgency for the SRO to take decisions on this, to allow delivery partners to plan accordingly. And programme leadership was clear that they wished us to make ‘brave’ and ‘bold’ recommendations. The energy programme is both significantly larger than other strands (more than double the size), and exogenous factors have made progress on energy slower – principally the difference on energy policy between the UK and Mexico since the Business Case was approved. This is likely to affect both primary and secondary benefits. We recommend that if the SRO cannot await an updated appraisal case, and in the absence of a viable alternative vehicle to EPI, she exercises her delegated powers to shift 10% of the total PF budget (£6m) from Energy to other programmes (especially replenishing agile funds and Future Cities), encouraging the energy programme to focus on energy poverty and energy transition (especially renewables and efficiency), and taking care to preserve the sustainability of EPI – both for the period of the AMLO Presidency, and to provide optionality in future administrations. The impact on the energy programme should be mitigated by seeking earlier co-funding from donors or the private sector. This will inevitably change the dynamics of the energy programme’s outcomes (particularly the spirit of EPI). But we judge this to be a necessary loss to ensure programmatic balance and Paris compliance.

The programme has a good balance between federal and subnational activity, which increases impact and mitigates risks. This approach has flexed to fit the new political context (e.g. more work in Tabasco) in a demand-driven manner. But there remains a gap in coverage of the south of Mexico, only partially offset by other UK ODA programmes operating in Mexico. We recommend that the SRO directs delivery partners to roll out successful interventions to southern states, bearing in mind constraints around budgets and states’ own absorptive capacity.

The headlines for other elements of the Annual Review are:

1. Energy. Progress but a significantly-changing external environment. Assessment: B
2. Future Cities. Risk-appetite to define balance between Int 1 and 2. Assessment: A
3. Financial Services. Suggest shifting balance from Int 1 to 2. Assessment: A(-)
4. ACROL. Agility and communications key over the next year. Assessment: A
5. VfM. Good financial management; new appraisal case needed to judge VfM properly.
6. Risk. Strong risk management procedures in place.
7. Commercial considerations. Excellent delivery partner relationships and team size right.
8. Business Environment. Excellent cohesion, and comms much-improved.
9. Monitoring & Evaluation. Good; scope to use MREL intel better in programme decisions.

Other recommendations are given throughout the rest of the Annual Review. We have summarised the top ten recommendations at the beginning of this document. Given the constructive approach of the Mexico PF programme towards recommendations in the last Annual Review and previous Evaluation Reports, and given the strengths of the programme we have identified above, we are confident that the Mexico PF programme is in a strong position to achieve greater results over the year ahead.

## C. Detailed Output Scoring

### Energy
#### Indicator table

Indicator	Milestone	Progress	Score
Number of women and men taking a training course	360	The indicator is on track for delivery, but due to COVID-19, the start date for the pilots’ implementation has been postponed. / However, the Energy delivery partner has elaborated the ToRs and completed competitive processes to develop and implement all ten pilots. Four of which are open to all audiences, including the low-income sector. / These projects will help target populations by finding new ways to improve their lives; including obtaining jobs in previously unexplored areas.	B
Number of training programmes provided on-site and online	3	The indicator is on track for delivery, but due to COVID-19 the training programmes had to be adapted. The Energy delivery partner is planning to develop online versions of training courses that were supposed to be delivered in the centres. / Online versions will be available for two of these pilots, which will be remotely accessible, increasing the number of people that can attend these courses.	A
Number of SMEs trained	20	The indicator is on track for delivery, but due to COVID-19, the start date for the pilots’ implementation has been postponed. / The Energy delivery partner is on track to develop five pilots to provide training to SMEs to obtain new contracts, in the regions of influence.	B
Number of SMEs registered in Centre Systems (SRP)	20	The Energy delivery partner is finalising the update and customization of the SRP tool, which will be ready for the first SME pilot training. The following actions are being undertaken: / • The system is being programmed and its functionality tested / • The legal disclaimer is under review. / The Energy delivery partner is currently collaborating with Carbon Trust to develop a decision tree that will categorize different SMEs. Upon completion, workshop materials will be developed. The workshop will train SMEs on system functionalities, and it will explain the benefits of using them.	B
Number of partnerships with regulatory agencies and chambers (local and national)	6	The Energy delivery partner has worked with different stakeholders to establish partnerships and meet this indicator’s goal. For example: / • Agencia de Seguridad, Energia y Ambiente (ASEA): Once approved, the Energy delivery partner will share a letter of intent with them to reach an agreement. / • Ethos: the Energy delivery partner received their proposal for training CFE officials. Their contract is yet to be signed. / • Jalisco: the Energy delivery partner has been working with the state government to complete SME surveys. / • Tabasco: the Energy delivery partner has approached Tabasco officials to create a joint working group.	A

#### Key points

The main progress for this Annual Review for the Energy strand is moving from inception (which ended in November 2019) to implementation and secured approval to establish the Jalisco project hub. It is worth noting that more than half of the implementation time now has been affected by COVID-19.

In its first year of implementation, the Energy strand conducted market research to maximise the impact of the interventions (i.e. SMEs surveys, interviews with energy experts). The results of that research informed the Industrial Baseline Study (IBS), which helped determine gaps in national content investment and limitations to job creation. Also, the Energy delivery partner identified the existing training institutions, courses and certifications currently offering similar curriculum to the one to be offered by EPI (launched during these months of implementation). Furthermore, during these first months of implementation, the team undertook further stakeholder engagement with different actors from Jalisco, Tabasco and Mexico City. This included actors in federal and local governments, industrial chambers, local organisations and educational institutions.

Due to the COVID-19 pandemic, the start date for the training pilots’ implementation has been postponed and some of them had to be reshaped into digital formats. As part of the COVID-19 response, the delivery partner confirmed that it seeks to also provide: (i) training on SMEs’ crisis management; (ii) cost reduction through energy efficiency; (iii) technology adaptation for new forms of commercialization; and (iv) activities that strengthen links between SMEs and innovative funding sources.

The strand is experiencing changes with the energy priorities of the current government, which are different from UK’s energy policy (e.g. Paris agreement). However, the strand has a Climate and Resilience (C&R) Strategy and Action Plan incorporated into EPI’s vision and all its activities. Furthermore, the strand is currently focusing on building transferable skills for energy sector workers and activities that support low carbon transition or reduce emissions in the O&G sector.

These are areas still under discussion, because the guidance from London states the strand should steer clear of activities that drive oil production. Meanwhile the strand is making sure that G&I is a cross-cutting area/focus for all the activities in the energy sector, which is very gender unequal.

#### Recommendations

The Embassy to have discussion to determine the focus of the activities for the energy sector and their mitigation of climate risks or if further actions need to be taken.

The Embassy to assess the impact on the sustainability of EPI if the strand scales down (e.g. by £6m), if the SRO needs to take urgent decisions and the strand lacks an alternative implementation vehicle.

The Embassy and the delivery partner to rethink how to scale up as much as possible the gender transformative aspirations of this strand.

Establishing effective financial reporting systems with delivery partners (e.g. detailed information, forecast accuracy).

### Future Cities

#### Indicator table

Indicator	Milestone	Progress	Score
Intervention 1
Output 1.1.A Number of recommended integrated transport strategies prepared for consideration by the relevant Authority	2	Met. Integrated transport strategies are being delivered in Mexico City and Queretaro.	A
Output 1.1.B Number of stakeholder groups consulted / regarding the recommended integrated transport strategies	61	Exceeded through meetings and interviews with wide range of stakeholders.	A+
Output 1.2.A Number of agreements for operation / integration, new collection and/or data sharing prepared with input from the relevant authority for their approval	1	Met. Data sharing protocol for Monterrey will be delivered in year 2.	A
Output 1.2.B Number of stakeholder groups consulted / regarding the agreements for operation integration, new / collection and/or data sharing	33	Significant engagement with transport and other organisations.	A+
Intervention 2
Output 2.1.A Number of city proposals reviewed	12	Met.	A
Output 2.1.B Number of cities selected for the pilot	3	Met, with Guadalajara, Hermosillo and Mexico City selected.	A
Output 2.2.A Number of potential pilots identified that have a particular impact on women and girls	5	All pilots were selected to prioritise gender and inclusion issues.	A
Output 2.2.B Number of stakeholder groups engaged / during integrated transport solution pilot identification	17	Exceeded.	A
Output 2.3.A Number of feasibility studies delivered	1	In progress. Outline business cases for Guadalajara and Hermosillo have been prepared, and one is in preparation for Mexico City.	B
Output 2.3.B Number of identified solutions deemed appropriate for full-scale pilot implementation / following completion of a feasibility study	3	Met, with pilots identified for all three cities.	A
Output 2.3.C Number of interventions designed with / demonstrable participatory consultation from local / communities affected, women and vulnerable groups	3	Met, through consultation with a range of stakeholder groups.	A

#### Key points

The strand consists of two interventions, which began their implementation phase in September 2019. The strand has put in place good arrangements for delivery, and has an effective implementation partner in the alliance of organisations led by the Future Citie’s delivery partner. The recent evaluation report noted strong positive relationships with the delivery partner alliance, including effective identification and management of risks.

Intervention 1 consists of four projects in Mexico City, Queretaro, and Monterrey focused on integrated transport planning, with the potential to significantly improve public transport in general and for excluded groups in particular. Intervention 2 consists of three pilot projects in Mexico City, Hermosillo and Guadalajara, which were chosen from a total of twelve candidate projects in February 2020 after a rigorous selection process. The projects have a strong focus on gender and inclusion and have the potential to make immediate improvements to women and girls’ experience in using public transport.

The Future Cities strategy for secondary benefits envisages that these are likely to be soft power and network effects in the short term, which in turn may enable longer term benefits in the form of FDI, ODI and exports. A recent success for Intervention 1 was the discussion of alternative financing mechanisms (the Workplace Parking Levy) with Nottingham City Council, creating the possibility e.g. for commercial contracts for UK firms implementing similar schemes in Mexico.

Intervention 1 has progressed well, achieving all of its output targets, with the delivery partner able to deliver the work effectively using virtual methods. The only element of work to face delays is the design of a data management centre for urban mobility in Monterrey, which has been pushed back from August to November 2020. Overall, Intervention 1 has strong acceptance and feedback from stakeholders, integrates gender and inclusion considerations throughout its design and is on course to achieve its intermediate outcome results.

While intervention 2 has met most of its output targets so far, the projects have been significantly disrupted by the impacts of the pandemic, have made slower progress and are currently paused pending a gateway decision on their future. The Agile Programme Fund has been effectively mobilised to compensate for this pause, helping partner cities identify how to refocus their transport systems as they exit the lock-down. While this creative use of funds has allowed the strand to continue engaging with stakeholders and delivering benefits, it is a short-term initiative and leaves unresolved the question of how the intervention can address two significant barriers:

Deep face to face engagement at community level was originally planned for each pilot to ensure a strong focus on poverty and inclusion issues. However, this has been significantly hindered by COVID-19 restrictions. While the delivery partner has made innovative use of technology (e.g. using drones for fieldwork in Mexico City) and could potentially use alternative methods to engage with potential beneficiaries, there is a significant chance that this will only be partially successful and that the projects will be weaker as a result.

A more fundamental issue reflects the ability of city governments to deliver capital spending to implement the pilots if successful. While this reflects the economic recession in Mexico rather than a lack of interest, it challenges a key assumption in the strand’s theory of change, that city authorities would commit to full-scale adoption of solutions tested in the pilots. While re-focusing the pilots on projects with low capital spending (e.g. micro-mobility improvements such as ramps or street lighting) remains an option, there is also a risk that the potential impacts envisaged in the business case will be significantly reduced.

Given these barriers it is clear that going ahead with the city pilots even with modifications is a high risk strategy.

#### Recommendations

Given the performance so far of the two interventions and the barriers to successful delivery, we recommend shifting resources from Intervention 2 to Intervention 1. There are various ways this might be achieved. These include:

1. Compensating for this by identifying alternative sources of support for the current city pilots (e.g. other donors).
2. Identifying if there are any elements of the city pilots that can be delivered at lower risk and scaling down the projects to focus on these elements.
3. Ending the pilots.

While options b) and c) would create a challenge for delivery with our stakeholders, this might be mitigated by implementing integrated transport planning projects in Guadalajara and Hermosillo (and consider Mexico City – as it already has two Intervention 1 projects). Switching resources between interventions in this way (or by switching them from other strands) could also enable Intervention 1 projects to be rolled out in southern Mexico.

### Financial Services

#### Indicator table

Indicator	Milestone	Progress	Score
Number of international experts engaged in supporting HCD methodologies for strengthening financial inclusion and safeguarding users' transactions	2	So far, the strand has engaged with 6 experts. The HCD approach of Intervention1 has been discussed with experts. They identify the FS strand as a benchmark that will implement this methodology in Mexico. They are interested in keeping in touch and learning about this process (e.g. Ideas 42, BFA, IDB Invest, IFC-WB and CGAP).	A+
Number of male and female in the lower 40% of the income range receiving behavioural design financial interactions	0	The strand has had direct contact with potential beneficiaries and has designed education materials based on their financial lives to achieve broad implementation reach.	B
Number of social programmes that will establish relationships with the British Embassy as a result of the intervention	2	The strand has established 1 relationship with social programmes and authorities of the CNBV. From these programmes, National Institute of Solidarity Entrepreneurs has established a relationship with the Embassy now. There will be soon conversations with the Secretary of Labour for an alliance with Young Adults Building the Future programme.	B
Number of associations and institutions that will establish relationships with the British Embassy as a result of the intervention	2	The strand has deepened one relationship with one association, The Mexican Association of Retirement Fund Administrators (AMAFORE). Other financial institutions will participate in the project soon.	B
% of standards in the secondary regulation issued influenced by international best practice	100%	During 2019, Open Data secondary regulation and ATM API standards were published. All standards issued are based on international best practices, manly from the UK.	A
Number of international experts engaged in the provision of professional services for Open Finance	3	Three international partners are collaborating with intervention 2 for the development of Open Finance standards. These companies are: TESOBE (Germany), Accenture International (Ireland) and Open Vector (UK).	A
Number of projects submitted to the National Securities and Banking Commission seeking to test their products and services through the sandbox	6	The target will be met in October 2020. 60 project proposals have been received to participate in the SandBox Challenge. From this number, six will be selected in July 2020 that will receive technical assistance for two months. In this way, in October the six projects will be sent to the CNBV so that they can test their products in the SandBox.	B
Number of international start-ups engaged in the authorisation process through the Mexican Regulatory SandBox	0	Even though the first milestone is for 2021 (2) the team expects that the target will be met in October 2020. 10 international start-ups are participating in the Fintech Challenge.	A
Number of active FAN's	2	The launch of the Fintech Caravan in April 2020 started as the first FAN programme in the state of Queretaro. The MoU's signature is planned in July 2020. There are approaches with Campeche and Sonora, schedules to begin the second FAN from the beginning of 2021.	A
Number of new Fintech participants in the adoption programme per year	3	To be met in August. The open call for the participation of Fintechs in the FAN of Querétaro will start in August , up to 12 finalists will be chosen and 3 will be selected.	A
Number of activities linked to adoption	24	Some delays, including due to COVID-19. The first activity was delayed and due to launch he Fintech Caravan in April 30th. Between July and August three more activities will be implemented (i.e. Fintech Day and two Fintech‘s workshops for MSMEs).	B
Number of MSMEs and final users participating in any FAN activity	400	The milestone will be entirely reach at the end of the year. / 55 representatives of MSMEs participated actively in the launch of the Fintech Caravan in April 30th. It is planned a high participation in the upcoming activities due to the interest and commitment of the allies in Queretaro, government programs and meetings with other associations.	B
Number of associations and institutions at national and state level that will establish relationships with the BE as a result of the intervention	3	The team has established relationships with Chambers of Commerce (COPARMEX) and two government institutions (Ministries of Youth and and Queretaro’s Sustainable Development Ministry).	A

#### Key points

The main progress for this Annual Review for the Financial Services strand is moving from inception (which ended in August 2019) to implementation. The strand was officially launched by the Lord Mayor of London and the Mexican Finance Minister. It is worth noting that more than half of the implementation time now has been affected by COVID-19.

Intervention 1 (I-1) has been restructured due to the changing political context. It was initially meant to work with the G2P Prospera programme, which was cancelled following a change in federal government. The team were able to identify other government programmes that could allow the implementation of financial inclusion and education, choosing Sembrando Vida and Jóvenes Construyendo el Futuro. Given the current context, the delivery partner has informed us that work on Sembrando Vida is no longer feasible. There is an ongoing analysis to address this and to determine an appropriate implementation plan to deliver the intervention’s intended outcomes. With Jóvenes Construtendo el Futuro, the delivery partner is contributing to the design and content of a digital platform to enrol more young people to long-term retirement savings. While intervention 1 remains the intervention with the clearest link to vulnerable populations, it currently has much less of a gender focus than it was first envisaged (due to the change in beneficiaries of the social programmes), but wider inclusion aspects have been incorporated as a result of this shift. This intervention has a signficiant risk of not achieving the scope established in the Business Case due to shifts in government priorities and changes in resource allocation.

The outputs for interventions 2 and 3 are still on track for delivering its milestones and targets. Intervention 2 focused on implementing the Open Finance Phase I (API standards for open data) which was approved by CNBV and published in the Official Diary of the Federation on June 2020. At the same time, Intervention 2 finalised the development of the Open Finance Phase II (API standards for debit transactions) with the assistance of Accenture as sub-contractor. The SandBox Challenge started on February and by June, 166 applications were received from national and international FinTechs, 59 of which were authorised by the Organising Committee. It is estimated that at least 20 innovate models will go through to the next phases. The SupTech platform analysis was concluded and the process to start the development of phase I is expected to start in July/August 2020. Intervention 2 is working with CNBV, which has been very receptive to the strand’s activities and is seeking more support on three areas: i) continue developing standards for Open Banking, ii) develop the SupTech platform that enables the automatization of supervision of banks and; iii) scale up the regulatory Sandbox in order to allow FinTechs to develop products in a safe regulatory environment. There is opportunity for the Intervention to work on additional projects and with a wider set of regulators to enhance the strand’s primary and secondary impact, should additional funding becone available.

Intervention 3 Caravana Fintech was launched on April in Queretaro to accelerate the potential impact of the first cohort to be selected from the Open Call for Fintechs to be launched in August 2020. This event was later strengthened by a virtual meeting between HMA and the Governor of Queretaro in June to promote collaboration and work with the MSMEs sector in Queretaro. The second FAN will be launched in Campeche during year 2 implementation.

The delivery partner also submitted two COVID-19 response notes. The first one addresses financial education for vulnerable MSMEs and the second aims to understand MSMEs financial needs and alternative finance used during and after the COVID-19 crisis. These two projects are expected to be developed in the next few months.

#### Recommendations

The delivery partner to involve more actively the Embassy team in strategic conversations with key stakeholders in order to provide further support with key stakeholders.

The Embassy and the delivery partner to rethink how to scale up as much as possible the gender and inclusion transformative aspirations of this strand as envisaged in the business case.

The Embassy to redesign the scope of Intervention 1 to scale it down (i.e. targets and money) and shift that money to scale up Intervention 2 and beef-up the G&I strategy of Intervention 2, provided it is confident that it can mitigate loss of direct impact on end-users.

The Embassy to evaluate the impact of scaling down and up Interventions 1 and 2, respectively.

Establishing effective financial reporting systems (e.g. detailed information, forecast accuracy).

The delivery partner to keep continuity in the headquarters team leadership that can contribute with a more strategic approach to the strand leadership.

At this stage, we have no evidence that Intervention 3 should be scaled down or up because delivery intervention will begin in August 2020. Suggest reconsidering in the next Annual Review cycle.

### Anti-corruption & Rule of Law (ACROL)

#### Indicator table

Indicator	Milestone 2020	Progress	Score
Number of formal collaboration agreements in place with relevant institutions / (Ind. Number 1.1)	6	On track. Main gap is at federal level given challenges with stakeholders.	B
Number of sets of recommendations provided which incorporate UK or international best practice. / (Ind. Number 1.3)	4	On track. Clear evidence in CDMX and Jalisco, slightly further behind in Tabasco (not least due to COVID-19 related delays).	A
Number of recommendations provided to improve inter-agency coordination / (Ind. Number 3.1)	2	On track. Some small COVID-19 related delays.	A
Number of Communities of Practice meetings held / (Ind. Number 3.3)	4	In the process of being created. The number of meetings will be cumulative.	A
Number of knowledge-sharing missions held between UK and Mexico / (Ind. Number 3.5)	0	Delayed due to COVID-19; considering virtual event as alternative.	B
Percentage of staff surveyed who demonstrate awareness of policies relevant to gender and inclusion / (Ind. Number 3.6)	20%	On track. Milestone completion date – 2022.	A
Percentage of institutions with a named point of contact for gender and inclusion issues / (Ind. Number 3.8)	65%	On track. Milestone completion date – 2022.	A

#### Key points

The ACROL strand has made good progress since the last Annual Review. At federal level it has navigated challening relationships and secured good buy-in thanks in part to a now-embedded Strand Governance Board (although a federal-level MoU has been delayed, partly due to COVID-19). A good visit of British judges helped launch the strand, and a regional strategy has been agreed. Some deft management of the strand helped it continue when COVID-19 hit, for example digital reviews of files or Zoom-based training; this also reflects a high degree of trust that has been built up with stakeholders in a naturally-sensitive area of government policy. Early results have included the incorporation of good gender guidelines into Jalisco’s criminal procedures (with opportunities to broaden out to non-gender related inclusion issues such as indigenous communities), and some good secondary benefits (and opportunities) from cyber- related work: the strand has clearly helped open doors here. Thus we judge it is on track to meet most outcome-level objectives (with a slight challenge around cyber, due to federal policy) and key performance indicators. On value for money, the strand seems to be relatively efficient/effective; and equity is built into the concept. There is little concern on the Paris-compliance side.

Internally, processes are improved. Financial planning is excellent. Relationships between the Embassy and delivery partner teams (on which the Evaluation had some suggestions) are much improved, with a capable team in place and good relationships which allow effective escalation (especially around external engagement). Risks are managed well via monthly meetings, although the strand should continue to discuss these openly and honestly between Embassy and delivery partner teams. The theory of change and logframe were revised last autumn, and are in the process of being revised once again (e.g. to update assumptions on cyber, strengthen the link between homicides and poverty, and align with the overall PF theory of change). Thus the main challenges for the strand are external: minimising COVID-19 delays; ensuring buy-in even if/when Mexican stakeholders change over the next year; deploying wider HMG levers for stakeholder engagement at federal level or in Tabasco. We would add that this strand has an inherent risk of failing to demonstrate the benefit to end-users, given the nature of the interventions – the team should give thought on how to bring that element out in its communications.

#### Recommendations

Increase agility, including to navigate changes in stakeholders. This means considering whether a small Agile Programming Fund might help – or, alternatively, using other PF strands or HMG levers (such as load-bearing diplomatic relationships) to get alongside new stakeholders. Getting dedicated MREL resource into the delivery partner will help here.

Replicate more. Early results should be cascaded to other stakeholders/states where possible, to demonstrate replicability and increase take-up of recommendations. We recommend greater use of government ‘champions’ such as the Fiscalia Especializada en el Combate a la Corrupción in Jalisco. The imminent launch of Communities of Practice will help here.

Improve communications. The ACROL Comms Strategy is the only one yet to be scrutinised/approved. This is important given the need to (a) increase Mexican political will to implement ACROL policies, to match the technical work provided by the rest of the strand; and (b) increase UK understanding of why the strand exists, and early impacts on both primary and secondary benefits.

## D: Value for Money & Financial Performance

#### Cost drivers and performance

For FY 2019/2020, the budget was £11,037,853. Actual spend for the year was £10,973,361; this reflects a managed underspend of £64,492, representing an 99.4% spend against budget. The managed underspend was due to an over-allocation on programme development activities (annual review, external financial audit, launch events, PF regional conference, regional engagement, and stakeholder engagement and coordination events).

The key cost drivers of the programme are the programme delivery and the staff costs, accounting for 93.5% and 3.7% of the actual spend respectively. Admin staff costs are in line with JFU guidelines and the programme expects to stay within this range over the lifespan of the programme. Staff costs show variance due to vacancies in Q4.

The Energy strand had an overspend due to the initial forecast being based on the commercial proposals submitted at ITT stage, which did not necessarily reflect the accurate and financial numbers for each milestone. The other three strands had an underspend, as projected since the beginning in the forecast outturn. During the last quarter, COVID-19 forced delivery partners to adapt and make changes on some activities, which altered budgets and exacerbated the underspend.

Expenditure for FY 2019/2020
Concept	Allocation	Actual spend	£ Variance	%Variance
STAFF COSTS (UK & local)	£466,175	£406,055	£60,120	12.9%
PROGRAMME DEVELOPMENT	£342,696	£51,422	£291,274	85.0%
PROG ACROL	£1,829,201	£1,439,876	£389,325	21.3%
PROG ENERGY	£3,389,802	£4,330,219	-£940,417	-27.7%
PROG FINANCIAL SERVICES	£2,355,503	£2,208,849	£146,654	6.2%
PROG FUTURE CITIES	£2,374,476	£2,284,940	£89,536	3.8%
PLATFORM CHARGES	£280,000	£252,000	£28,000	10.0%
TOTAL	£11,037,853	£10,973,361	£64,492	0.6%

The Business Case was approved in December 2018. Since then a number of contextual changes have occurred. The COVID-19 crisis (sanitary and economic), new approach to UK ODA and changes in government policies (e.g. G2P programmes and energy policy). Therefore, the value for money case within it requires review and potential updates.

#### Economy

The business case considered that the programme will be delivered through four contracts to enable a strategic approach across the interventions for each strand. This approach has brought flexibility to capitalise windows of opportunity to influence government policy in Mexico. The experience and expertise of the delivery partners has also helped promote economy and efficiency in the programme work, as has improved commercial skills in the programme team (a recommendation from last year’s Annual Review).

All of the programmes’ budgets show an over or underestimation. However, the programme has established procedures to monitor spending and the review team includes the Head and Deputy Head of the PF, Programme Managers, Programme Officers, Finance Officers and the Contract Management lead. Based on anecdotal evidence from interviews across the programme team and its delivery partners, the financial information (of some delivery partners) does not provide the level of detail in order to correctly forecast activities and identify savings. Each programme went through a competitive procurement process and, as such, the winning bidder(s) were selected as the Most Economically Advantageous Tender In order to have detailed information that contributes to a better decision-making process and ensures greater control over costs. We recommend that the programme team encourage delivery partners to provide detailed forecasts where they have not been provided properly, identify and report cost-savings, and support effective benchmarking.

#### Efficiency

We judge that the programme will achieve its output indicators and has been well managed even in the current context. One of the main impacts on the four bilateral programmes’ interventions is the COVID-19 sanitary and economic crisis. Nevertheless, they have adapted to this new context quite rapidly, showing that the programme is resilient and flexible. For example, in adapting activities, the Energy strand delivered a virtual conference with the Ministry of Economy.

Although some milestones might experience some delay, most 2020 milestones at output-level will be delivered on time. For example, Financial Services launched virtually the Caravana FinTech in April 2020. This event marked the start of the first Fintech Adoption Network (FAN) in Queretaro. The Future Cities strand adapted to minimise disruption and has developed innovative solutions such as drone infrastructure mapping to advance projects despite lockdowns.

One of the main lessons learnt has been around communication between and among Embassy and delivery teams, and stakeholder engagement. The current comms strategies have helped to maintain coherent and participatory processes, and avoid affecting relations and misunderstandings on wider topics (coordination, finance and procurement).

The team is confident that the changing context will not have significant impacts to delivery. However, we recommend the programme team and its delivery partners assess the economic, political and social impacts in each of the strands, especially the implications for the ToC and logframes (milestones and targets) before the cycle 3 Evaluation starts.

#### Effectiveness

The programme and strand ToC were refined in the autumn of 2019. The strand logframes were reviewed and updated before the cycle 2 evaluation started (February 2020) and the programme logframe was fed from the strand logframes’ indicators and uploaded to Prospero in July 2020. All of these documents have undergone considerable updates over the last year.

The programme just moved to its first year of implementation and the first results will be provided during 2020. However, there are some milestones that have already been met or exceeded. There are early results for the Financial Services and Future Cities strands at the output level indicators and all of the strands are on track to deliver to deliver their milestones later this year. Nonetheless, there will be some delays and adaptations of some milestones due to COVID-19. Thus, we recommend reviewing the strand and programme ToC and logframes (milestones and targets) for subsequent years.

The Business Case estimated a central scenario of £886m primary benefits and £462m secondary benefits (see table below). Secondary benefits also include non-monetisable aspects such as considerable network, soft power benefits and political influence. The four strands have several good relationships with Federal and State level authorities, education institutions, civil society, NGOs and national and international MSMEs. Even though the programme is on track to deliver some results, the effects of COVID-19 and changes in Mexican and UK government priorities will have an impact on the programme (and particularly in our view Energy). Thus, we recommend assessing those impacts and evaluating the scope of primary and secondary benefits that the programme will be able to deliver by updating the appraisal case. This will include an assessment of sustainability of the programme.

Business Case calculation of primary/secondary benefits per strand
Strand	Primary Benefit (£m)			Secondary Benefit (£m)
	High	Central	Low	High	Central	Low
Anti-Corruption and Rule of Law	809	219	24	234	153	72
Financial Services	421	221	80	52	28	4
Energy	320	215	129	376	254	139
Future Cities	684	231	53	35	27	20
Total	2,234	886	286	697	462	235

#### Equity

The programme underwent a light G&I review in its cycle 2 evaluation. The April 2020 scores were 4/5 for three of the categories (programme design, internal capability and partnerships) and 3/5 for two of the categories (financial resources and accountability mechanisms).

We judge the programme team is strengthening its G&I capability. All strands have methods and tools for mainstreaming G&I activities across their interventions. All delivery partners have G&I resources within their teams (and an appointed G&I lead). But equally we believe all strands can do more to promote wider inclusion. ‘Vulnerable populations’ is a broad concept requiring clear definition, to have targeted activities and pathways to achieve the primary purpose of the Prosperity Fund. We recommend that the G&I strategy is not limited to a focus on gender, but also clearly defines vulnerable/marginalised populations (e.g. youth, indigenous communities).

New G&I leads have been appointed within the programme team, who hold regular meetings with delivery partner G&I leads. Strand and programme-level logframe information is disaggregated for some indicators for income, vulnerable groups and gender categories. From interviews with the Embassy team, some strands feel that less work has been done on gender recently due to the focus on COVID19 and political-economy factors. While this might hold true, COVID19 heightens the need to strengthen and broaden existing G&I strategies. This is because different socio-economic analyses have shown that low-income populations, women and young people will be the hardest hit by the crisis. Thus, we recommend reviewing the G&I strategies for each Strand in light of the current context and adjusting it where necessary.

#### Value for Money

The programme is on track to deliver good value for money despite the current political, economic and social changes. Programme performance on budget, milestones and progress against outputs to date suggests the programme as a whole still represents value for money, though it is still in the early stage and the reporting of results is limited to the output level, rather than intermediate outcome, outcome or impacts. However, there are risks associated with the current country-global context that might shift the overall impact of the programme compared with the original business case. The programme team and its delivery partners have submitted their COVID-19 responses, which contain updates/changes to main aspects of programme delivery

#### Quality of financial management

The programme has financial management processes in place to set budgets, track expenditure, invoices and forecasts, including financial risk management. However, the financial information provided by the delivery partners for Energy and Financial Services has not been clear or adequate to date. The programmes have access to high-level data regarding actual spend but cannot investigate individual spend items. The teams report a lack of accuracy on forecasting, details of the actual costs and little or no information around savings. The delivery partners have provided updated templates to provide more accurate and detailed information, however the main concerns from the programme team have not been addressed. We recommend the Financial Services and Energy delivery partners strengthen communication with the programme team on financial management, and take on board the team’s requirements and recommendations, as well as to agree the timing for reporting savings (e.g. quarterly). We also recommend that the team uses the forthcoming external audit (pushed back due to COVID-19) to ensure anti-fraud and corruption measures are sufficient.

ACROL and Future Cities delivery partners have provided the level of detail required by the programme teams. Whenever there are changes in expenses and forecasts, there are clear and detailed explanations of the updates.

Given the current context, it has been hard to provide accurate forecasts that stick within the +/-1% variance requirements we have been told is set by London for financial year forecasts. We recommend JFU and FCO London re-confirm if such tight variance targets still apply in the current context.

Date of last narrative financial report	30th June 2020
Date of last audited annual statement	November 2019

## E: Risk

#### Overview

The main programme risks are to achievement of outcomes (rather than being fiduciary, safeguarding or reputational). These stem primarily from the impacts of COVID-19 and from changing political imperatives in both Mexico and the UK. While the former is obviously new, political changes have been constant (and managed well) throughout the programme.

Strands face a variety of different risks, and as a result achievements may be greater in some areas than others, and/or delayed compared to initial expectations. There is a case for re-allocating funds between/within strands to focus on where returns are likely to be greatest. Despite these risks the programme still has potential to substantially deliver its objectives. We assess the overall risk to be moderate, given the level of agility shown to date.

#### Management

The programme has strong systems and practices in place to manage risk. It has made good use of these in recent months, responding effectively to the challenges posed by COVID-19 and ensuring negative impacts are significantly lower than they could have been. Existing strategy and governance structures for addressing COVID-19 impacts are robust and functioning well. Existing tools such as strand risk registers are more useable. The programme team has also focused consistently on managing political changes at strand and programme level and has sought additional support for this (e.g. directing E&L to focus on this issue in this year’s evaluation).

This year’s evaluation identified a clear line of sight to identify, mitigate and manage risk throughout the PF structure in Mexico. Risk management is one of eight criteria in the value for money scorecard, and the programme was scored 3.75 out of 5 by the evaluators (the highest of the eight scores), indicating good performance. The PT has also implemented or is in the process of implementing all recommendations on risk from last year’s Annual Review.

There is evidence from minutes, risk registers and the programme dashboard of a strong focus on addressing COVID-19 risks from an early stage in the pandemic. There is also evidence of active and early discussions with delivery partners to address issues, and of delivery partners themselves identifying problems and seeking solutions. Examples of effective mitigation include re-designing energy sector training courses to deliver these online, using the Agile Programme Funds to help partner cities develop post-lockdown planning when the city pilots were paused, and identifying alternatives to the Sembrando Vida programme for financial education.

Effective risk management has contributed to strong delivery, with partners largely achieving logframe targets in challenging circumstances. The strength of the response to COVID-19 is further illustrated by the fact that the more significant challenges to programme delivery are not primarily related to COVID-19

#### Recommendations

There is limited availability of information for decision-making, for example current discussions on re-allocating resources. While logframe data provides information on progress, results need further analysis and interpretation to be useful for decision-making. Although this is the purpose of the annual evaluation, events this year have shown how quickly priorities can change. We therefore recommend the planning process for the annual evaluation retains a proportion of allocated days, to be used for additional evaluation purposes that may arise later in the year. Given that the number of E&L days will now be be reduced in the context of wider budget cuts, this implies that next year’s evaluation will need to be carefully focused on priority issues

## F: Commercial Considerations

#### Delivery

While the consequences of COVID-19 have had a significant impact on the programme, many activities have been able to go ahead as planned or with small delays, and delivery partners have met most of their logframe targets this year. The most significant changes to the delivery plan have been:

1. Pausing the city pilots intervention in Future Cities (due to difficulties in conducting essential fieldwork, and the scaling back of city budgets needed to finance successful pilots)
2. Delays in implementing the interventions in Financial Services (due to challenges with the Mexican government’s Sembrando Vida programme) and Energy.

The difficulties with these strands are counterbalanced by the strong progress elsewhere. There is also potential to scale up some elements, notably Future Cities intervention 1 (integrated transport planning), and Financial Services interventions 2 and 3 (data standards, regulation and fintech).

#### Performance of partnerships

Delivery partners have performed well in progressing with implementation, despite significant challenges raised by the pandemic and stakeholders’ changing priorities. By adapting existing implementation plans better results have been achieved than would otherwise have been the case. So far, existing mechanisms have therefore provided enough flexibility for an agile programming approach. The SRO’s view that arrangements have not prevented change where needed underlines this point. Implementation has been helped by a cooperative approach, with delivery partners flagging emerging issues early on. While this year’s evaluation report identified several challenges in the PT – delivery partner relationship for the ACROL and Energy strands, progress has subsequently been made in addressing these.

The Agile Programming Fund (APF) stands out in supporting an agile approach. In particular, APF funding is helping cities review transport systems as they exit lock-down, and a project with Women’s World Banking has supported the search for alternative collateral for women. These have sustained the Future Cities and Financial Services strands’ potential to achieve primary purpose benefits for women and excluded groups. Given the high level of uncertainty from political changes and the future impact of the pandemic we recommend the programme retain the APF, even if budget cuts mean its size needs to be reduced.

#### Commercial management systems and service level agreements

The key levers for delivery partner management are the logframe KPIs, service level agreements (SLAs) and Payment by Results (for two of the contracts). The programme team has used the SLAs actively, and all delivery partners agree the SLAs have effectively focused their attention on the key issues. Delivery partners and embassy teams also agree that the information required under the SLAs is appropriate and is actively used for programme management, but the Embassy team thinks there is room for refining the SLAs particularly for continuous improvement and forecasting with a view to hold the delivery partners accountable. Further adjustments may be needed (for example, to ensure the embassy is fully involved in stakeholder engagement at strategic moments such as when the Sembrando Vida programme indicated it could not work on financial education).

The key challenges for our delivery partners has been in complying with SLAs for financial reporting and forecasting. This is particularly evident with our delivery partner for the Energy and Financial Services strands. Delivery partners are obliged to provide detailed monthly forecasts, and for actual annual spending to match the forecast last agreed by both parties with a margin of +/- 1 per cent. It has just been agreed with the four strands that December forecast will be the last agreed forecast for this SLA to be measured against.

We recommend the programme team continue its efforts to ensure the relevant forecasting is provided by the Energy delivery partner by having conversations to ensure the alignment on monthly forecasting needs. We further recommend that the London commercial team reviews and suggests improvements on the forecasting SLA to incentivize the delivery partners to better forecast.

The Energy delivery partner also delivers projects in Mexico for the Global Skills and Global Health programmes. While the predominance of a single delivery partner has been identified as previously as a potential risk, there is no evidence that this has yet occurred in practice. The Energy delivery partner’s establishment of a Financial and Operations Service Unit (FOSU) to manage back office operations across its PF work in Mexico also holds the potential for efficiencies, though it will be important to assess whether this materialises in practice. The programme team should consider that establishing the FOSU in itself will not address the forecasting issue itself given that not all the Energy delivery partner’s-managed projects (e.g. the DfID-run Global Health project) require the same level of detail in financial reporting. We therefore recommend that the detailed financial reporting requirements for the Energy and Financial Services strands are re-confirmed in specifications for the FOSU.

#### Asset monitoring & control

The programme is now beginning to deliver some outputs that may count as assets, e.g. the local content platform for the Energy strand, financial models for Future Cities partners, and some physical assets for the EPI Centro in Jalisco (e.g. solar panels, IT equipment). While the team has not identified any specific risks in relation to monitoring the management of assets, it previously requested guidance from central London teams on who is responsible for monitoring high value items and what constitutes a sufficient level of oversight (e.g. spot-checks or visual confirmation). While clarification of this issues was advised in last year’s annual review, it has has not yet been achieved. We recommend that the programme team clarify this with London counterparts.

#### Staffing

The Mexico programme has an effective and committed team in place which has developed its capabilities significantly over the review period and proved highly capable in achieving results in challenging circumstances. It has benefitted from a high degree of continuity in staffing allowing for a consistent approach and ongoing development of capabilities. Delivery partners also have effective teams in place and have replaced team members where necessary.

The team has added one position in the review period: a Deputy Head. This has undoubtedly been necessary given the scale and complexity of management tasks, need for beefed-up central functions, and to address limited team experience in managing large delivery partner contracts. We recommend retaining this role, and – for the moment – the Contract Management Lead role. But given that the programme size may reduce in the longer-term, we suggest the SRO consider slimming down the team in the longer-term if a reduction occurs by taking advantage of natural attrition if/when it arises.

Overall workload remains high, and there is potential to reduce this and create more time for reflection and strategic thinking. We recommend the other strands review the example of the Financial Services strand in reducing workload by triaging delivery partner deliverables. This divides these into three groups depending on the level of review and feedback rather than scrutinising all outputs in the same detail.

## G: Business Environment

#### Communications

We note a significant improvement on communications in-country. Mexican stakeholders are more aware and supportive of the programme (due in part to beefed-up comms resource in delivery partner teams). Initiatives like the Foreign Secretary’s PSIG and the Ambassador’s COVID-19 related communications have generated a sense of coherence across what could otherwise be quite a disparate set of interventions.

The programme should refresh the Comms Strategy to (a) push responsibility down to delivery partner comms leads where possible and (b) secure more high-level credit and a more strategic approach to communications. But our principal recommendation is that the programme focus more on the communications challenge back in the UK. The PF programme should play a ‘first amongst equals’ role in generating coherent communications across all HMG programmes in Mexico, docking in to the wider Embassy comms team to ensure maximum impact.

#### Climate

Climate concerns have become more pressing in recent months, given the PM’s commitment that all UK ODA will be Paris-compliant (which we understand to mean ‘consistent with a path towards global achievement of the commitments set out in the Paris Agreement’) and the UK’s imminent hosting of COP26. The team has worked hard to understand the climate risks and opportunities of the programme. Consultants identified actions to ensure that the Enery and Future Cities strands comply with HMG’s commitment to align ODA with the goals of the Paris Agreement.

We recommend the SRO set a clear ambition for the whole programme to be Paris-compliant within the next few months, and certainly before COP26. This will require delivery partners to make alterations to all strands, but particularly Energy.
#### Cohesion

There is excellent cohesion within the programme, with innovations such as regular Programme Director / Team Leader meetings and Supplier Days helping to join up the individual delivery partners. There is also good cohesion with global PF programmes, thanks to strong PF leadership and senior structures within the Embassy team. And there is excellent cohesion with wider HMG work, driven by the Embassy’s Prosperity Strategy and innovative (and successful) ‘Virtual Team’ model, which has generated a culture of collaborative working across sections. Governance structures such as the Programme Management Committee and Programme Strategy Advisory Board also help drive coherence across programmes. The merger of the FCO and DFID should hopefully support this over the next year. We are confident that the Mexico bilateral PF is well-placed to navigate those developments and grab new opportunities / mitigate new risks.

#### Secondary benefits

The programme has achieved some good initial impacts on secondary benefit: particular examples include PF contributions to export contracts worth £25m in water, £4.5m and £1.9m in airport infrastructure, £2.8m in railway infrastructure, £4m in fraud detection, £2.7m in financial payments, and £30k in open banking. These have benefited British firms in Northern Ireland, Scunthorpe, Derby, Sheffield, Glasgow, Cambridge and Liskeard – amongst other parts of the UK. Additionally UK soft power and network effects have been generated across all strands. Non-ODA funds have been used effectively in a targeted way, administered well by the Embassy team. This is particularly impressive given that secondary benefit definitions were only clarified centrally in September 2019.

There are now significant emerging areas of opportunity, notably in the transport, energy, FinTech, green finance and cyber sectors. We are not able to judge whether the programme is ready to exploit those opportunities, given the long gap in filling the Secondary Benefits Officer position. But now that position has been recruited, we recommend that the Embassy urgently defines a Secondary Benefits Action Plan with clear metrics; ensures that delivery partner plans are aligned; and learns from regional best-practice in Brazil and Colombia.

## H: Monitoring & Evaluation

#### Evidence and evaluation

The Cycle 2 (2019/20) Evaluation was carried out from January to May 2020 and focused on engagement, capacity, management and governance. They key findings are the following:

1. Engagement: While changes in policy and in key government personnel have created challenges, the programme has navigated these with only minor delays (1–2 months).
2. Capacity: The programme team and delivery partners have the capacity to deliver the programme, though this is often stretched
3. Management: Overall, the management practices are good.
4. Governance: The programme has appropriate governance arrangements, but these could be further strengthened.

#### Monitoring

The programme and strand ToC used in the evaluation and Annual Review were drafts created with the support of the Monitoring and Evaluation (MR) Hub in August 2019. The team is seeking to refine all ToCs (at the strand and programme level) in the autumn of 2020, taking into account government policy changes and the impacts of COVID-19. The aim of this exercise is to strengthen the impact causal pathway. Furthermore, the strand and programme logframes will be updated to assess the impacts of COVID-19 on the interventions. The current version of the programme logframe only has proposed indicators for outputs and intermediate outcomes, and follows the programme ToC – we recommend adding targets in the next 6 months, to allow future Annual Reviews to assess if the programme is on track to achieve the outcomes and impact expected when the business case was approved. All of the logframes (at the strand and programme level) propose to disaggregate metrics (e.g. by income, gender, age) and set milestones and targets and assumptions made.

For the first months of implementation there are some results, and on balance all strands are on their way to achieve 2020 milestones later this year. However, there are no clear responsibilities for updating this information in Prospero. The programme team is not fully using this tool that could help them track the progress of their programmes and their interventions.

#### Recommendations

ToC/logframes: review and update of the ToC and logframes with the MR Hub and Evaluation team in Autumn 2020.

Output Indicators: Ensure all output indicators have associated milestones and implement reporting against these.

Strengthen MR: the Programme team to work with the MR Hub to set a clear framework to update results and have a better understanding of the potential of Prospero.

Support from E&L: the Programme team to use as support the E&L days to undertake further work as needed later in the year.