Annual Review
Brazil Prosperity Fund
Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Brazil Bilateral Prosperity Fund
Programme Value: £56M		Review Date: 05/08/2019
Programme Code: GB-GOV-50-PF-01-BRZ (including GB-GOV-3-PF-BRB-912; GB-GOV-3-PF-BRB-924; GB-GOV-3-PF-BRB-922; GB-GOV-3-PF-BRB-923;GB-GOV-3-PF-BRB-913; GB-GOV-3-PF-BRB-911; GB-GOV-3-PF-BRB-921)	Start Date: 01/04/2018	End Date: 31/03/2023

Summary of Programme Performance
Year	2018/2019
Programme Score	B
Risk Rating	Moderate

Summary of progress and lessons learnt since last review
This is the first review for the Brazil Bilateral Prosperity Fund programme, and covers the period from 2017-2019, 2017-2018 being a transitional period and 2018-2019 the first full year of the programme.
The Prosperity Fund at its present scale and approach is a relatively new entity. As the programme moves from procurement into inception and implementation of multi-year programmes, we want to recognise that this has not been an easy process, often for reasons beyond the control of the programme team. The programme has also experienced considerable change in the political context, as a result of changes in government in Brazil specifically. The team have largely been able to respond effectively to this change as a result of good preparation and strong links with relevant government departments and regulatory bodies.
Against this background, individual strand managers have coped surprisingly well, and have focused on continuing delivery within their individual strands. We have seen some really good individual elements of management and received excellent feedback on the efforts of the present Head of Prosperity Fund to create a more consistent and coherent approach and build a more permanent base for her successor to work from. Accordingly, the view of the review team is that if the team as a whole can create a consistent programme-level approach using the best of the best and follow through on the work that has already been done, this could be a very strong programme by the time of the next review.
Overall, the programme has made good progress in the last two years establishing the programme governance and programme management structures to support the design and delivery of four programme strands on energy, future cities, trade and green finance programmes, aligned with the Prosperity Fund primary purpose and secondary benefits. We especially recognise the efforts of the programme board, outgoing Head of Prosperity Fund, and programme team. Some individual programme strands have made strong progress moving from procurement into inception. However, both the documentation of the programme and the interviews we have conducted so far suggest that there is a significant disconnection between the strategic (that is, SRO and board level) and operational (that is, strand management level) layers of the programme, which is creating difficulties in assurance and risk management (especially around appropriate escalation); in interactions with the centre (especially around challenge to the centre as a whole and construction of proposals for guidance and support); and in delivery. For example, some members of the team were not aware of the appropriate escalation routes for risks below SRO level, or of how their reporting interacted with SRO engagement with London; individual strands had constructed reporting and management templates, but reporting at the SRO level was constructed separately rather than being brought together at an intermediate level.
List of recommendations for the next year
High-level/strategic recommendations - We recommend that the programme team should:
  1. Make a clearer case to the centre (PFD, JFU and CPG) on admin resourcing, including reclassification of some resources to implementation, as has been done in Mexico and Colombia. This would place the programme on a more secure footing to restructure its virtual teams somewhat and draw in specialist resource to support the teams. It would also ensure that the programme is clearly in compliance with existing rules on admin spend;
  2. Recruit a small pool of expertise; our interviews suggest a number of possible requirements for expert support, especially around contract management, monitoring and evaluation, communications, diversity and inclusion. The team is unlikely to be able to recruit all of the specialist resource it requires, so we recommend that it should prioritise on the basis of need and of availability of support from the centre;
  3. Rethink the present line management structure to give a clearer set of incentives to strands, so that they engage more effectively with the programme at a strategic level and with one another. Options for doing so include:
    1. Aligning line management structures with financial accountability, so that the bilateral programme strand leads are managed by the Head of Prosperity Fund and the global programme strand leads by policy leads, and structuring virtual teams around strands. This is the approach taken in other programmes, such as Mexico, Colombia and South East Asia, and has been seen to be effective there. It offers very clear control for the Head of Prosperity Fund and around financial management, but reduces links between this programme and others, especially where there is a shared policy interest;
    2. Retaining the existing formal line management arrangements, but creating a stronger and more formalised set of links between the Head of Prosperity Fund and the policy leads who have direct line management responsibility for strand leads. This has worked well in the case of global strand leads in Mexico, and elsewhere in Whitehall on (for example) EU Exit deployment. It offers more direct influence to the programme manager, while retaining links across political themes, but has a significant time cost for both managers;
    3. Creating softer levers for the Head of Prosperity Fund by giving them control of the small pool of expert resource referred to above, and a clearer position as the link for escalation between operational and strategic management. This has relatively low resource costs and offers some influence to the Head of Prosperity Fund, especially if the demand for expert resource is high, but may not be sufficient to address the present concerns;
  4. Free up time for the Head of Prosperity Fund to work more proactively to improve timing and quality of support from, and communication with, the centre. The experience of other programmes is that driving out appropriate support and engagement from the centre has been a key part of the Head of Prosperity Fund’s role, and that this has been especially effective where groups of programmes (such as those in the LatAm countries) have been able to work together to set out their needs.
  5. Build on existing good work to create a clear and consistent understanding within the different strands and for the broader programme team where relevant of the importance of appropriate escalation and programme management processes, so that issues are properly escalated to the strategic level and pursued thereafter. At present, there is good evidence of appropriate escalation from the SRO level to the centre, but limited response; and different strands have very different levels of risk tolerance and different risk management tools. Harmonising these processes and defining a clear route of escalation through the Head of Prosperity Fund would allow the programme to set a consistent, defined risk appetite, and to ensure that teams escalate where needed.
  6. Make clearer use and documentation of consistent approval processes for changes to strands’ theories of change and actual activities. At present, the programme has clear documentation for approval of significant change at SRO level, such as the changes to strands following political change in Brazil.
  7. Engage with other programmes (perhaps including those in the region) to create more helpful and appropriate guidance for clearance and use by the centre on a range of issues including MREL, contract management and risk management – this has been an approach that has worked for other programmes. Alternatively, programmes could exert pressure on the centre to create appropriate and timely guidance.
2. We recommend that central teams including JFU and PFDU should take a more customer-centred approach to developing guidance, support, and training for programmes (especially around timing and quality), and in particular:
  1. Signpost more clearly how teams can access support on contracts other than standard framework contracts;
  2. Adapt the timing of guidance and training to the actual timing of Prosperity Fund programmes, so that programme and strand leads are able to access support in time to deliver strong commercial outcomes and good value for money;
  3. Develop guidance and training in partnership with programmes so that they meet the needs of programme and strand leads on first publication.
3. We recommend that Department for International Trade (DIT) leads should engage more effectively with the Prosperity Fund as a whole to deliver secondary benefits, for example by working with teams to establish where the UK has niche expertise and could draw on it effectively, or by a more systematic approach to leads and contacts within relevant markets.
Recommendations on performance management
1. The team should set clear expectations for suppliers around project management and contract management from the start of the contract / agreement incorporating these formally into contracts/agreements and setting expectations through kick-off meetings and subsequent regular performance management meetings. For example, strands that have yet to agree contracts and begin inception should learn from the experiences of the Future Cities and Trade strands, and define clear expectations (including templates) for financial management and project reporting, and for assessing log frames. The Future Cities and Trade strands should also continue to develop their reporting approaches, and the programme as a whole should harmonise approaches as much as possible to create a consistent reporting framework;
2. Future key training should be planned for well in advance, to minimise further risks to the programme;
3. Clear documentation and induction are vital to mitigate the risk of staff turnover; in particular, a clear documentation process for change control below the SRO level is needed;
4. The team should consider how it can share learning as effectively within Brazil as it does with colleagues across Latin America, and in particular consider whether it can make more frequent opportunities for the different strand leads to share learning in person (both within the bilateral programme and across programmes. Possibilities for doing so include allocating some funding to support contact between teams based in different cities; defining champions for specific areas of expertise, or making better use of existing learning spaces such as PF Learning.

Recommendations on VFM and financial performance
Consider the explicit, documented use of multi-criteria approaches (possibly drawing upon independent facilitation support from the analytical community) to develop and compare strategically coherent packages of work within strands and support decision-making around reprioritisation of work within a tighter financial envelope. These approaches will be especially useful where costs and benefits cannot be fully monetised, for example where thinking around the political goals of the UK and of Brazil is necessary This is especially important for the Energy and Trade strands, but will also be of use for Green Finance in navigating political issues and for Future Cities in managing over-programming and navigating the relationship with the supplier, especially in light of the early overspend in this space;

1. Develop a clear, updated understanding of the costs, benefits and risks of the individual elements of the programme, at a level appropriate to supporting development of strategically coherent, best-value work packages;
2. Arrange for an appropriate audit, working with JFU to develop understanding of the key lines of enquiry for the auditors and define the scope of the work

Recommendations on risk
1. Define and implement a consistent, programme level structure and set of tools for managing risk and delivery within and across strands e.g theory of change, lessons learned between strands. This will help the team to internalise a structured management process in their routine, to develop a risk mind-set and to develop a consistent approach across strands. At present, although a great deal has been done to improve risk management, strands have individualised approaches to recording and escalating risk, and the risk mindset is not yet consistently embedded throughout the team.
2. Integrate strands even more closely with other relevant teams, such as Political/Policy teams or comms teams, perhaps through regular discussions or joint plans. Integration with Comms teams in particular could improve the quality of internal communication with London (to help communicate the programme’s VFM case and manage risks around over-programming) and external communication (which would support the relationship with key stakeholders). Even closer integration with political teams (which is already strong for some strands)
3. Establish an institutional memory. An organised approach using the FCO’s preferred document management software and/or training spaces is needed – particularly as the team has experienced some staff turnover.

Recommendations on commercial considerations
1. Take a partnership rather than a client-implementer approach to the relationship, building on and strengthening examples of where this is happening already in Strands e.g. OECD relationship and learning lessons where this has not worked in transition/inception such as the World Bank relationship. A partnership approach where implementers are encouraged to involve the programme team in programme development and delivery can help to ensure that risks are raised early, that the programme team is able to capitalise on the relationships with stakeholders and can drive up the overall quality of the deliverables. It is also likely to incentivise a positive relationship in which issues are escalated early and problems are shared to find joint solutions, which is a key mitigation for managing risk. As part of this process, the team should ensure that they and the supplier have a strong shared understanding of the theories of change for the programme as a whole and for the specific strand under consideration.
2. Set expectations clearly at the start of inception for the type of involvement the PF team plans to have during the lifetime of the programme, including: engagement with stakeholders, branding and communication of the programme, involvement in decision-making.
3. Provide clear and consistent guidance and templates to suppliers early on (in the contract/agreement and in the mobilisation phase), in order to ensure that suppliers deliver what the team requires, including guidance on: the role of the supplier in secondary benefit delivery (including logframe indicators); performance and financial reporting tools and templates e.g. format and content required for financial reporting; and risk management tools.

Recommendations on business environment and secondary benefits
1. The programme strand managers, supported by the Secondary Benefits Advisor, should continue to develop their secondary benefits strategies and action plans. Outlining the steps of programme delivery in a way that creates and explicitly identifies the opportunities for international businesses, including from the UK, to come in and deliver their expertise, coupled with a vigorous prioritisation of the opportunities identified to select priority sectors to focus very limited non-ODA resources on for maximum impact.
2. The programme should develop a stakeholder engagement strategy at the portfolio level, to support the ongoing effective and coordinated stakeholder engagement and stakeholder management by the strands, particularly with intergovernmental agencies and development banks, but also with academia, the private sector, civil society and beneficiary groups.

Recommendations on MREL
1. The programme strand managers, where requested, should receive training on Theories of Change and logframes, to help teams to support the use of these tools and approaches to learn, drive adaptation and results-based management, assess and explain impact., and to manage the programmes in a results-based way;
2. Support from the centre (JFU and PFDU) to develop a programme management tool to support effective and monitoring of key activities throughout inception and into implementation, and including clear guidance on data quality. ,
3. Further guidance from the centre (JFU and PFDU) is required for the programme team and implementers on developing partial programme specific baselines against intended outcomes, by different strands during inception, for results to be measured against in implementation. This will be complemented by a contextual baseline produced for the multi-cycle evaluation led by the Fund, as outlined in the approach paper. ,
4. The planned evaluation to provide technical sector specific findings and insights during the inception period, to support necessary adaptations on the Theory of Change and logframe, ahead of implementation. Also for a substantive evaluation to take place ahead of the next annual review, to reduce burden and overlap.

List of Acronyms
AR – Annual Review
BC – Business Case
BBC – Brazil Prosperity Programme
DIT – Department for International Trade
E&L – Evaluation & Learning
FCO – Foreign and Commonwealth Office
G&I – Gender & Inclusion
IFC – International Finance Corporation
JFU – Joint Funds Unit
MCDA – Multi Criteria Decision Analysis
M&R – Monitoring & Reporting
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation & Learning
ODA – Official Development Assistance
PF – Prosperity Fund
PFDU – Prosperity Fund Delivery Unit
PT – Programme Team
SDGs – Sustainable Development Goals
SBs – Secondary Benefits
SRO – Senior Responsible Owner
ToC – Theory of Change
VfM – Value for Money

      1. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Prosperity Fund
The cross-Government Prosperity Fund (PF) was created in 2015. The primary purpose of the Prosperity Fund is to support the inclusive economic growth needed to reduce poverty in partner countries. Through this primary purpose, the Fund’s activities will contribute to the UN Sustainable Development Goals (SDGs). The fund also looks to create new economic opportunities for international business, including UK companies, and mutually beneficial economic relationships as secondary benefits, as a result of this economic growth. The Fund has a budget of £1.2 billion over the 7 years (2015/16-22/23) to provide technical assistance to partner countries to promote economic reforms and remove barriers to trade, to strengthen policy capacity and build strong institutions and tackle corruption.

The Brazil Prosperity Programme
The Brazil Bilateral Prosperity Fund programme has been running since 2017, and is due to run unto 2023. The Business Case (BC) for the Brazil Prosperity Programme (BPP) was approved in early 2018. The Brazil Prosperity Programme (BPP) is a £56 million Foreign and Commonwealth Office (FCO) led bilateral programme funded via the Prosperity Fund (PF). As outlined in the business case (BC) the BPP aims to support Brazil’s economic modernisation, where increased productivity in Brazil for renewed economic growth and poverty reduction, by reducing transaction costs and stimulating competition and innovation. The secondary objective of the programme is increase business opportunities in Brazil, including for the UK, by stimulating competition and removing specific market barriers. The programme is divided into four different strands: Trade (£16 million), Green Finance (£5 million), Energy (£25 million) and Future Cities (£10 million). Since this is the first annual review, the period of the review will cover from the receipt of transition funding from 2017-2018, but with a focus on the period between August 2018 to August 2019 after final business case approval and the full funding moved over to departmental baseline.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
This Annual Review was carried out before commencement of the inception phase for all but one of the programme Strands. Consequently, an assessment of whether the outcomes of the programme will be achieved by the end of the programme will be made as part of the evaluation which is scheduled to be carried out towards the end of the inception phase. This Annual Review therefore focussed on assessing whether the right processes and tools were in place to support the delivery of the programme’s primary purpose, including appropriate theories of change, logframes, gender and inclusion strategies, and plans for scaling and mainstreaming of the projects included in the programme.
The Review concluded that some of these tools are in place in each strand of the programme, and that the programme team has done a remarkable job in continuing to keep delivery moving given a gap in senior leadership within the team and difficulties in obtaining appropriate support and expertise at some key points. Nevertheless, the programme needs to improve consistency between Strands and to continue to embed processes which will ensure the programme is able to deliver primary impact. The inception phase provides a key opportunity to do this, which should be grasped in order to mitigate the present risks to programme delivery.
The team also delivered £3.3m of transition programming in 2017/18. The majority of this programming was focussed on informing programme design and there is some good evidence that the team have begun to incorporate the results of the transition projects into programme design, through the SoRs, or have planned to do this as part of the inception phase for the programme.
Annual outcome assessment (Secondary Purpose)
The programme has been broadly designed to align with areas of strength for the UK’s business sectors. The programme strand managers have considered secondary benefit in their design, considering thematic areas where secondary benefit may be achieved.
In both 2017-18 and 2018-19, the programme was allocated £225k of non-ODA funding. In 2017-2018 it underspent slightly, delivering £207k of non-ODA projects, and in 2018-19 it overspent very slightly, delivering £235k of non-ODA projects. There is some early evidence that projects will feed into the Secondary Benefits strategy for the programme and that funding has been used to identify tangible areas of opportunity, including specific target companies.
As the programme moves into inception phase and primary interventions become further defined and confirmed, the programme team will need to work closely with DIT colleagues to refine the secondary benefits plan to ensure that an action plan is in place, built upon tangible and specific opportunities which will result from the primary interventions. There is good evidence that the Secondary Benefits lead for the programme has a good understanding of the work required to do this. However, this understanding does not yet extend to the wider team, and there is not, as yet, a clear and consistent working relationship, and clear split of responsibilities between the programme team and the relevant DIT sector team. An example of this is that the non-ODA projects for 2017/18 were delivered by the DIT team, and the programme team as a whole were not significantly involved in, or aware of the non-ODA portfolio (although this varied between strands with some Strand leads (although a minority) having good oversight). As with other areas, the level of engagement between DIT and programme colleagues varies between programme strands, with some well interlinked with DIT colleagues and others with no engagement. The need for coordination and a clear split of responsibilities in relation to Secondary Benefits will be intensified as the programme moves into inception, with the added role of implementer to be incorporated into this split.

Overall output score and description
The overall output score for the programme is B (outputs moderately did not meet expectation). This reflects the fact that there have been some delays in starting delivery of the programme, most notably in contracting with delivery partners, as well as there being a wide variation in outputs between Strands. The programme has also faced resourcing issues, most notably a gap of 8 months without a Head of Prosperity Fund, as well as a number of changes in key personnel. Despite this the programme team has done a remarkable job at continuing to deliver, including delivering the majority of transition projects on time and to expected standard. However, overall the variation across strands means that the programme is not consistently meeting expectations across a number of outputs.

Key lessons
Key lessons emerging from the delivery of transition projects, and development of the multi-year programme over the last year are:
- The need to set clear expectations for suppliers around project management and contract management from the start of the contract / agreement: across a number of transition projects, and the inception phase for the Future Cities programme the team experienced issues with the quality of project management and contract reporting from their suppliers. Their concerns included delayed reporting of risks and issues. This has often led to misunderstandings between the team and supplier which could be averted in future by setting out reporting requirements clearly in any contracts or agreements for delivery of work, including providing the supplier with specific reporting formats.
- Training for the team on procurement and contract management was needed at a much earlier stage. The impact of training being provided late in the procurement process (May 2019) has had a direct impact upon programme timelines. Future key training should be planned for well in advance, to minimise further risks to the programme. The review team notes that the Brazil programme requested this training from JFU/PFDU in December 2017, but that training was not provided until May 2019.Clear documentation and induction are vital to mitigate the risk of staff turnover. The Brazil programme team has experienced several changes in key personnel over the past year e.g. the Future Cities programme has had three programme leads. Clear programme documentation and induction could help minimise this risk.
- There is no clear documentation on change control at the programme level. There is a clear change control process for changes that exceed the SRO’s delegated authority, but the process for changes below SRO level are not clearly documented and have caused some confusion and a lack of documentation of changes made at the Strand level which means that the links between agreed funding and subsequent spend/delivery are not as clear as they should be.

The programme team has some good opportunities for sharing learning in their team, across the Prosperity Fund and externally, particularly, through the Latin America PF network, the Latin America regional conference and through PF Learning. The Head of the PF in Brazil has also introduced a regular lessons learned slot into team meetings since January 2019.
Overall, the observation of the review team is that whilst these opportunities exist, and there is some good evidence of lesson learned sharing within the Latin America network by the Brazil team, the team could be doing more to share both learning and experience within the team itself. This is a challenge with the team based across 4 different locations in Brazil and the variation between Strands across a number of areas e.g. structure and content of Statement of Requirements (SoR), approach to G&I, approach to MREL, suggests that this is not currently working as effectively as it could. There are some areas of good practice across the team where the wider team could benefit hugely from the experience of their colleagues e.g. development of logframe indicators by the Green Finance Strand team using international best practice.

Key actions
Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Output	Action	Timeline	Team member responsible
1	Consider the explicit, documented use of multi-criteria approaches (possibly drawing upon independent facilitation support from the analytical community) to develop and compare strategically coherent packages of work within strands and support decision-making around reprioritisation of work within a tighter financial envelope		Programme strand managers and Head of Prosperity Fund
	Develop a clear, updated understanding of the costs, benefits and risks of the individual elements of the programme, at a level appropriate to supporting development of strategically coherent, best-value work packages		Programme strand managers and Head of Prosperity Fund
1	Extend stakeholder interactions to include a wider range of beneficiaries; in particular direct beneficiaries of the work and their representative groups.		Programme strand managers
1	Improve both content of and engagement with theories of change, and draw clear links between theory of change at strategic level and that at operational level.		Programme strand managers and Head of Prosperity Fund
1	Develop thinking on scalability and broader delivery in the inception phase, and as a matter of urgency		Programme strand managers
1	Embed understanding and use of logframes to support results-based management, by delivering appropriate training among other actions		Head of Prosperity Fund
2	Consider more permanent embedded G&I resource as part of review of specialist support.		Head of Prosperity Fund
2	Share learning between strands and continue to embed G&I as necessary.		Head of Prosperity Fund
4	Embed links with new DIT contact in post, and through him develop networks to DIT colleagues in London		Programme strand managers and secondary benefits manager
5	Project and financial management requirements and expectations from the Programme team to be clearly set out in Contracts and Administrative Agreements, kick-off meetings with implementers and monitored through regular progress meetings.	August – October 2019	Programme strand managers and Head of Prosperity Fund
5	Evidence from the transition projects to be reviewed and incorporated during the inception phase, particularly around G&I, where this was not possible in the Statement of Requirements.	By end of inception phase	Programme strand managers
7	The SRO and programme team should consider mitigation of the budgetary and delivery impact of a delayed inception phase. This could include negotiating a new payment profile with JFU/PFDU, bringing forward spending e.g. starting some implementation activities in parallel to the inception phase, or looking to spend more through implementers where contracts/agreements are already in place e.g. World Bank, OECD.	By March 2020	SRO / Head of Prosperity Fund
7	The SRO and programme team should continue to manage the expectations of stakeholders around the start of inception given the contracting delay.	August – October 2019	SRO / Programme team
7	The programme team should begin discussions with implementers immediately after contract signature around ensuring that the mobilisation period for the contract is not impacted by the contracting delay, particularly in relation to staffing e.g. it may take the implementers several weeks to bring together the programme team and/or they may need to re-recruit positions where individuals put forward in the bid are now no longer available.	August – October 2019	Programme strand managers and Head of Prosperity Fund
7	The FCO Commercial team should review its processes in relation to contracting to ensure that this is as efficient as possible to minimise delays in contract signature, including entering into contract development ahead of final procurement approvals being secured. Thinking about where teams get the resources	September 2019	FCO Commercial team
7	The programme team should plan now for a revision of contracts at the end of inception to ensure that the inception refined programme design, KPIs and SLAs and comprehensive project management requirements are set out in the contract.	November 2019	Programme strand managers and Head of Prosperity Fund

Summary of changes to the logframe since the last annual review
N/A
## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Output 1: The programme has the necessary systems and structures in place to ensure the programme is sustainable and able to adapt to changing circumstances in an appropriately evidence-based way.
Output number per LF		1.1, 1.2, 1.3	Output Score	A/B
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
1.1.1 Change management procedures are sufficiently robust.	March 2019	4 The team does not at present have clear and consistent change management processes, and there are some significant gaps in the documentation
1.1.2 Contracts reflect sufficient flexibility to allow the programme to change	July – September 2019	4 Most contracts not yet signed, though teams have designed them with appropriate breakpoints at inception stage. The teams may not always have sufficient information on individual programme elements to make best use of this flexibility.
1.1.3 Structures in place and used to maximise the political intelligence the programme strand managers have to inform their work.	March 2019	2 There are good links to the relevant policy units and governance boards, which most strands have used to advantage in responding to recent political changes - recognising changes, considering impacts and adapting the programme. . There is some inconsistency between strands, and more formal risk management and monitoring structures and processes have been implemented more recently.. We recommend the continuation of this ongoing process in order to increase awareness and a risk mindset.
1.2.1 Key government departments, regulators and public sector agencies/banks consulted on programme design and their suggestions taken into account.	March 2019	3 Strand leads generally have good links to the relevant public sector agencies, departments and regulators, and have clearly drawn on them in developing the programme. At the next stage, it will be important to develop beyond this to ensure the views of beneficiaries are fully taken into account.
1.2.2 The programme has high-quality theory of change, with the programme context and beneficiaries taken into account and the assumptions and causal pathways (including G&I and secondary benefits) well-articulated and underpinned by currently available robust evidence.	December 2018	4 The latest version of the Theory of Change (May 2019) is of good quality. A high-quality Theory of Change would require: (1) detail on how the intended project outputs are expected to be brought about by project activities and the accompanying rationale for these activities, based on the programme context outlined in an supporting narrative; (2) documented conditions, particularly assumptions, that need to be met in order for such activities to result in the intended outputs and outcomes; (3) inputs – monetary and nonmonetary – needed to support project activities; (4) further specificity on the intended beneficiaries beyond re ‘the women and the poor,’ and results of the intended benefits for beneficiaries; (5) secondary benefit activities and intermediate outcomes, and clear demarcations of secondary and primary benefit pathways; (6) identified linkages between and across programme strands. The fact that these things are missing makes it difficult for the programme to demonstrate VFM.
1.2.3 The programme is on track to have 4 high-quality strand logframes and one overarching logframe with impact, outcome, intermediate and output indicators and milestones by the end of the inception phases.	July 2019	3 The programme is on track to have adequate strand logframes and an adequate overarching log frame by the deadline. To achieve high-quality logframes, there is a need for (1) further guidance and training on using logframes to support result-based management; (2) metrics closer to the direct influence of the programme at the intermediate and outcome levels to trace contribution from outputs; (3) indicators and methodologies for measuring intended G&I benefits; (4) sector specific technical support to review and challenge logframe impact, outcome, intermediate and output indicators; (5) guidance on the process for developing baseline data to measure progress against (intermediate) outcomes and impacts targets; and (6) a process for critically reviewing and assessing baselines provided by implementers.
1.2.5 The Programme Board reviews the theory of change biannually and whether the programme is on track in terms of implementation bimonthly.	July 2019	3 Reviews take place as described
1.3.1 Buy in from key stakeholders to the vision of delivering results at scale assuming success of interventions including commitment to work on codeliverables in building a pathway to scale.	July 2019	2 Some stakeholders on some strands are engaged around broader delivery, but in general plans around scalability and replication are not sufficiently advanced to gain full buy-in
1.3.2 Steps needed to scale up the programme interventions considered and reflected in the Programme Theory of Change and on track to be included in the logframes by the end of inception phases.	July 2019	4 The programme team have had substantial discussions on how to scale interventions and a conceptual framework was developed with input from the programme team economist, and disseminated through an E-Learning discussion on PFLearning. However, practical guidance has not yet been developed and socialised, nor included in specific plans. There is still time for this to be completed and to be utilised by programme strand managers.

Key Points

Summary of responses to issues raised in previous annual reviews (where relevant)
n/a, as this is first review

Recommendations
Develop clear understanding of costs, benefits and risks at the level of individual programme elements at the level where trades within strands can reasonably be made, to support reprioritisation where necessary
Extend stakeholder interactions to include a wider range of beneficiaries.
Improve both content of and engagement with theories of change, and draw clear links between theory of change at strategic level and that at operational level.
Develop thinking on scalability and broader delivery in the inception phase, and as a matter of urgency
Embed understanding and use of logframes to support results-based management, by delivering appropriate training among other actions

Output Title	Output 2.1 Programme designed to make a positive impact on women and the poor.
Output number per LF			Output Score	B
Risk:		Moderate	Impact weighting (%):
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
2.1.1 Programme has a high quality Gender and Inclusion Strategy which is being implemented.	July 2019	4 Not yet delivered, though some progress towards it and some innovative thinking
2.1.2 The programme is taking action against the recommendations from the G&I Scorecard stocktake review which assessed whether G&I was adequately reflected in the business case.	August 2019	2 Clear action and progress
2.1.3 Appropriate resources allocated to provide sufficient expertise on gender and social inclusion to programme team.	March 2019	4 Resources being recruited, but not yet in place

Key Points
Some strands have developed innovative approaches to diversity and inclusion, and are hoping to embed them securely into delivery at inception stage; no strand has (as yet) a fully embedded approach to G&I.
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
Consider more permanent embedded G&I resource as part of review of specialist support.
Share learning between strands and continue to embed G&I as necessary.
Output Title	Output 3: The Programme has Good Governance, Management and assurance structures and processes in place
Output number per LF		3.1, 3.2, 3.3, 3.4	Output Score	B
Risk:		Moderate	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
3.1.1 Regular opportunities for programme team to share lessons learned	March 2019	3. Ongoing improvemt. Team Meeting twice a month, Regional Conference, Away Day, Trainnings, Thematics meetings (inception phase). We recommend continuation.
3.1.2 Information governance ensures information risks are mitigated and information compliance and accountability are the norm.	March 2019	Not yet in place, though there is some progress towards appropriate use of Sharepoint
3.2.1 All key decisions are recorded and stored in a well-organised accessible format on Sharepoint.	March 2019	4. Key decisions are not recorded properly.
3.2.2 The programme does an effective and relevant compliance audit annually.	March 2019	4 No compliance audit thus far
3.3.1 Statements of requirements/EFO/AA are reviewed critically by the Programme Board.	December 2018	3 This takes place
3.3.2 Contract Quality Assurance Group is in place.	May 2019	3 Yes
3.3.3 Training in contract management is provided.	January 2019	4 Training was provided, but was too late to offer full support to strands
3.4.1 Governance structures both actual and planned have clear delineation of roles and decision-making or advisory powers.	March 2019	3. Governance structure exists but the roles of the Boards and Senior Leadership are not clear for the team. Also, decision-making and advisory involving London is not effective. We recommend a stronger narrative/communication plan and evidence based approach towards London in order to get their buying and interest to support the Brazil programme.
3.7.2 An effective Prosperity Fund Governing Board meets regularly (e.g. monthly or every 6 weeks) to give strategic direction, taking into account programme evidence, in order to take key decisions on adaptation.	July 2019	3. The Board meets regularly; a clearer and better understood escalation process might help it to focus more effectively on risk mitigation.
3.7.3 An overall ODA governance structure exists to maximise UK ODA coherence/ complementarity in Brazil and deal with reputational risk.	July 2019	4. An overall ODA structure exists but does not maximize UK ODA coherence and complementarity. Areas for improvement: i) better communication and knowlodge alignment between teams; mapping intersections ( area, stakeholders), implementing activities that maximize ODA resources. Individual teams cooperate well with adjacent programmes, however.
3.7.4 Agreements and continuous consultation exists between the PF and the different parts of the Brazilian Government that sufficiently support continuity and coordination for each of the 4 strands of the programme.	July 2019	2. Strands have appropriate agreements and consistent engagement with the Brazilian government. In order to mitigate risks to delivery, we recommend that future strand governance includes civil society organisation and private sector organisations, to support meaningful delivery for key beneficiaries and to mitigate against unexpected political change.

Output Title	Output 4 Secondary Benefits pursued effectively
Output number per LF			Output Score	B
Risk:		Moderate	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
4.1.1 Effective structures integrate PF team and DIT teams to deliver secondary benefits.	March 2019	4 The existing secondary benefits lead has begun to develop links, but they are not yet sufficiently embedded for reliable delivery
4.1.2 A high quality secondary benefits strategy exists and is being implemented.	August 2019	4 One is under construction, but is not yet delivered or being implemented
4.1.3 Secondary benefits sufficiently integrated in the programme level logframe, 4 strand level logframes, and theory of change	August 2019	4 Secondary benefits are not yet sufficiently integrated in the programme level logframe and strand level logframes at all levels, and tend to be incorporated at the impact and outcome levels only. Work is ongoing to identify secondary benefit interventions and activities which should support the incorporation of lower level secondary benefit metrics and targets in logframes. Further guidance is required from London, on secondary benefit definitions and setting secondary benefit milestones and targets

Key Points
Good initial work now needs to be implemented in full. There is an opportunity to engage with the new DIT Secondary Benefits lead.
Summary of responses to issues raised in previous annual reviews (where relevant) - n/a

Recommendations
Embed links with new DIT contact
Output Title	Output 5 The Programme makes effective use of transition evidence, particularly in the Statements of Requirements and Commercial Agreements.
Output number per LF			Output Score	A/B
Risk:		Minor	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1a.1 Relevant transport in Sao Paulo EFO Study and pilot completed to a high standard and on time.	April 2019	Sao Paulo EFO Study currently being delivered. Delivery to date has been of good technical quality, though project management outputs have been less satisfactory. The Study has been delayed due to additional outputs being suggested by the supplier, with delivery expected in October 2019. The pilot originally conceived to be delivered in the inception phase has been postponed to the implementation phase (Post-October 2019)
5.1a.2 Evidence from studies/pilots on transport in Sao Paulo incorporated into the Administrative Agreement with the supplier.	August 2019	Evidence is being used to inform the development of the Administrative Agreement, although the signing of this has been delayed until October 2019. A concept note proposal based on the EFO study evidence has been provided by the supplier, and a stakeholder workshop to develop the logframe for the period to be covered by the Administrative Agreement has been held.
5.1b.1 Relevant water loss and behavioural change studies completed to a high standard and on time.	June 2019	Water loss and behavioural changes studies are currently being delivered. Delivery to date has been of good technical quality, though project management outputs have been less satisfactory. The Study has been delayed with delivery now expected in October 2019 due to an additional activity being added to the delivery by the supplier. The cost of the inception phase has therefore increased significantly.
5.1b.2 Evidence from EFO studies on water in Recife incorporated into the Administrative Agreement.	June 2019	Evidence is being used to inform the development of the Administrative Agreement, although the signing of this has been delayed until October 2019. A concept note proposal based on study evidence has been provided by the supplier, and a stakeholder workshop to develop the logframe for the period to be covered by the Administrative Agreement has been held.
5.2.1 Green Finance Transition Studies/Activities completed to a high standard and on time.	March 2019	All transition activities were completed on time and to a high standard. Overall the team were satisfied with the deliverables but felt they did not exceed expectations.
5.2.2 Evidence from Green Finance transition studies/activities incorporated into the Statements of Requirements and Contract.	December 2018	Incorporated into statement of requirements, but not yet into contracts.
5.3.1 Energy Programme Transition Studies/Activities completed to a high standard and on time.	April 2019	All transition activities were completed on time and to a high standard. Overall the team were satisfied with the deliverables but felt they did not exceed expectations.
5.3.2 Evidence from Energy Programme transition studies/activities incorporated into the Statements of Requirements and Contract.	December 2018	Evidence from relevant transition studies / activities was promised to bidders when the SoRs went to the market. The team has since provided copies of all relevant studies to the bidders via the procurement platform.
5.4.1 Trade Transition Studies/Activities completed to a high standard and on time.	March 2019	The majority of transition studies and activities were completed on time (one baseline study will complete in September 2019). Overall delivery was to a high technical standard, although project management by the implementer could have been strengthened. The expectations of the team in relation to an OECD study were exceeded, with a significant shift in the Government’s openness to working on OECD ascendance created as a result.
5.4.2 Evidence from Trade transition Studies/Activities incorporated into the Trade Statements of Requirements and Contract.	December 2018	Outputs from the transition activities applicable to the Statement of Requirements and Contract were not available in advance of the SoRs being issued to the market. [effectively this is unscored]

Key Points
- Some delays which have prevented fully being able to take into account transition evidence in the SoRs and Contracts. However, still a really good opportunity to do this during the inception phase. Recommend the team continue to do this, particularly the inputs around G&I
- Supplier project management came through as a consistent theme where the team were not satisfied. Should look to build clear mechanisms for project management into the contracts (either before inception or during revisions at the end of inception), and set clear expectations for suppliers around project management in kick-off meetings and regular progress meetings.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
- Project and financial management requirements and expectations from the Programme team to be clearly set out in Contracts and Administrative Agreements, kick-off meetings with implementers and monitored through regular progress meetings.
- Evidence from the transition projects to be reviewed and incorporated during the inception phase, particularly around G&I, where this was not possible in the Statement of Requirements.

Output Title	Output 6.4 The Programme is designed to have a positive impact on gender and inclusion issues
Output number per LF			Output Score	B
Risk:		Moderate	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
6.1a.1 The mobility in Sao Paulo programme includes components that bring direct benefit to women and social inclusion and these are credibly reflected in the Theory of Change and logframe.	August 2019	3 The Theory of Change makes reference to ‘Technology pilots shown to be cost-effective means for more efficient water management in Recife and improved mobility in Sao Paulo (including proven benefits for women and the poor).’ This is reflected in the logframe, which includes the following intermediate outcome statement, ‘Sao Paulo and Recife begin to implement more widely piloted technologies benefitting women and the poor.’ The accompanying indicator is ‘Number of females and males who have benefited from the pilot(s),’ disaggregated by sex, age and income quintile. However the indicator is not sufficient for measuring precisely how more efficient water management is to be measured, both within the pilots and more widely.
6.1a.2 Any potential negative impacts on gender and social inclusion from mobility programme in Sao Paulo appropriately identified and mitigated.	August 2019	Some work on identifying negative impacts and unintended consequences, not yet complete
6.1b.1 The water in Recife programme includes components that directly benefit women and the poor and these are credibly reflected in the Theory of Change and logframe.	June 2019	The Theory of Change makes reference to ‘Technology pilots shown to be cost-effective means for more efficient water management in Recife and improved mobility in Sao Paulo (including proven benefits for women and the poor).’ This is reflected in the logframe, which includes the following intermediate outcome statement, ‘Sao Paulo and Recife begin to implement more widely piloted technologies benefitting women and the poor.’ The accompanying indicator is ‘Number of females and males who have benefited from the pilot(s),’ disaggregated by sex, age and income quintile. However the indicator is not sufficient for measuring precisely how more efficient water management is to be measured, both within the pilots and more widely.
6.1a.2 Any potential negative impacts on gender and social inclusion issues from the water programme in Recife appropriately identified and mitigated.	June 2019	Some good BI work and early thought about negative consequences
6.2.1 The Green Finance Programme includes components that bring direct benefit to women and the poor and these are credibly reflected in the Theory of Change.	March 2019	The Theory of Change makes reference to ‘Pipeline of ESG certified sustainable infrastructure projects available to investors bringing benefits to women and the poor,’ at the outcome level. This is reflected in the logframe at the impact level, with the inclusion of an indicator measuring the 'Number of females and males estimated to benefit from sustainable investment projects leveraging private investment,’ disaggregated by sex, age and income quintile. / The Theory of Change also make reference to ‘Two pilot projects selected – both to benefit women and the poor – ESG (including gender and poverty impact under S -Social) methodology applied, at the output level with an accompany indicator in the logframe measuring, ‘Number of females and males estimated to benefit from pilot,’ disaggregated by sex, age and income quintile. / Again both indicators could be strengthened by specifying the kind of benefits that will be measured/are intended and how these should be measured. It may also be useful to incorporate an indicator on gender and inclusion at the outcome level to measure the contribution of the programme in influencing sustainable and inclusive investment projects leveraging private investment.
6.2.2 Any potential negative impacts on gender and social inclusion from the Green Finance Programme appropriately identified and mitigated.	March 2019	Still under development
6.3.1 The Energy Programme includes components that bring direct benefit to women and the poor; these are credibly reflected in the Theory of Change.	August 2019	The Theory of Change makes reference to ‘Lower electricity and gas prices due to the programme, (than otherwise would be the case), bring benefits to women and the poor,’ at the outcome level. The logframe outcome statement makes reference to a ‘More competitive and efficient energy market’ however, there are currently no indicators measuring direct benefit to women and the poor.
6.3.3 Any potential negative impacts on gender and social inclusion from the Energy Programme appropriately identified and mitigated.	August 2019	Potential negative impacts still being identified
6.4.1 The Trade Programme includes components that bring direct benefit to women and the poor; these are credibly reflected in the Theory of Change.	August 2019	The Theory of Change makes reference to ‘SMEs (including Women Owned Enterprises) increase trade and investment in global value chains’ at the outcome level, and to ‘Access for SMEs to a pipeline of international trade opportunities with better logistical and training support. Special focus on SMEs owned or run by women and employing poor people,’ at the intermediate outcome level. / The logframe included indicators measuring the, ‘Total additional export and import values in Brazil for trade and services, disaggregated by MSMEs participation,’ the ‘Cost reduced in importing and exporting procedures in the selected Ports, including for MSMEs that use the Ports,’ and the ‘Additional number of Brazilian MSMEs trading in foreign market and/or participating in global value chains, disaggregated by gender, region and type of company.’
6.4.2 Any potential negative impacts on gender and social inclusion from the Trade Programme appropriately identified and mitigated.	August 2019	Potential negative impacts still being identified

Key Points
Some strands have developed innovative approaches to diversity and inclusion, and are hoping to embed them securely into delivery at inception stage; no strand has (as yet) a fully embedded approach to G&I.
More work is needed at inception phase to understand the impacts on social inclusion fully and to embed them in delivery.

Summary of responses to issues raised in previous annual reviews (where relevant) n/a

Recommendations
Continue to embed gender and inclusion in development of work at inception stage; develop good early thinking into concrete action

Output Title	Output 7 The programme has effective commercial management systems in place.
Output number per LF			Output Score	A/B
Risk:		Major	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
7.1.1 Specific, clear, and comprehensive Future Cities EFO signed.	December 2018	EFO was signed
7.1.2 Specific, clear and comprehensive AA signed for Future Cities Programme spend.	June 2019	The completion of the inception phase for the Future Cities programme has been delayed to October 2019, following which the Administrative Agreement will take effect. This Agreement is in the process of being developed but has not yet been negotiated with the implementer or signed.
7.2.1 Specific, clear, and comprehensive Green Finance statements of requirements launched.	December 2018	A statement of requirements for the programme was launched in November 2018.
7.2.2 Implementers for Green Finance selected through a fair process run according to Government procurement rules.	April 2019	An implementer was selected through a fair process in line with Government procurement rules in January 2019.
7.2.3 Specific, clear, comprehensive and good value for money contract signed for all Green Finance Programme spend.	June 2019	A contract has not yet been signed for the Green Finance programme. It is expected that signature will take place in July 2019 given that a final version was sent to the implementer in [June/July].
7.3.1 Specific, clear, and comprehensive Energy statements of requirement launched.	December 2018	A statement of requirements for the programme was launched in January 2019.
7.3.2 Implementers for Energy selected through a fair process run according to Government procurement rules.	April 2019	An implementer was selected through a fair process in line with Government procurement rules in April 2019.
7.3.3 Specific, clear, comprehensive and good value for money contract signed for all Energy Programme spend.	August 2019	A contract has not yet been signed for the Energy programme and the team have experienced a delay in starting contracting due to a delay inreceiving Ministerial sign-off. There is a very high risk of delay in contract signature based on the timelines required between approval and contract signature for the other Strands of the Brazil programme.
7.4.1 Specific, clear, and comprehensive Trade statements of requirement launched.	December 2018	A statement of requirements for the programme was launched in September 2018.
7.4.2 Implementers for Trade selected through a fair process run according to Government procurement rules.	April 2019	An implementer was selected through a fair process in line with Government procurement rules in January 2019.
7.4.3 Specific, clear, comprehensive and good value for money contract signed for all Trade Programme spend.	July 2019	A contract has not yet been signed for the Trade programme. The contract development work has been completed but has not yet been sent to the supplier to review and so there is a moderate risk that the contract will not be signed by the end of July 2019.

Key Points
- Publication of SoRs and selection of suppliers largely delivered on time, in some cases, well in advance of the milestone.
- Contracting has taken much longer than anticipated – in some cases there will be an 8 month gap between when suppliers were selected to a contract being signed. This carries significant risks for ensuring that the team receives what they evaluated in bids – there is a high likelihood that personnel included in the bids may have now secured other opportunities and so the team may face challenges around needing to ensure implementer teams are quickly resourced during implementation, and to the same standard. The delay in the start of inception will also need to be managed in relation to reaching spending targets for the 2018/19 financial year, managing stakeholder expectations and ensuring that inception design work is timely. This is particularly an issue for the Energy strand, which has experienced further delays in contracting.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
- The SRO and programme team should consider mitigation of the budgetary and delivery impact of a delayed inception phase. This could include negotiating a new payment profile with JFU/PFDU, bringing forward spending e.g. starting some implementation activities in parallel to the inception phase, or looking to spend more through implementers where contracts/agreements are already in place. The SRO and programme team should continue to manage the expectations of stakeholders around the start of inception given the contracting delay.
- The programme team should begin discussions with implementers immediately after contract signature around ensuring that the mobilisation period for the contract is not impacted by the contract delay, particularly in relation to staffing. For example, it may take the implementers several weeks to bring together the programme team and/or they may need to re-recruit to some positions where individuals put forward in the bid are now no longer available.

- The FCO Commercial team should review its processes in relation to contracting to ensure that these processes are as efficient as possible to minimise delays in contract signature, including entering into contract development ahead of final procurement approvals being secured. It should set out clearly where teams are expected to obtain expertise in support of non-standard contracting and especially of contracting not carried out via FCO frameworks.
- The programme team should plan now for a revision of contracts at the end of inception to ensure that a more refined programme design, KPIs and SLAs and comprehensive project management requirements are set out in the contract.

Output Title	Output 8 The Programme has effective stakeholder management systems in place.
Output number per LF			Output Score
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
8.1.1 The Future Cities Programme has Advisory Bodies for both water and mobility strands that includes key stakeholders.	December 2018	3 The Future Cities Programme organised Theory of Change workshops with the supplier, local government officials, academics and civil society to inform the programme design.
8.1.2 The Future Cities Programme is on track to develop a revised theory of change and logframe for both water and mobility strands with key stakeholders in time to annex to Administrative Agreement.	June 2019	4 A revised logframe is underway
8.2.1 The Green Finance Programme is on track to have an Advisory Body that includes key stakeholders.	July 2019	3 Green Finance programme has used transitional funding to provide technical M&E support on best practice green finance and infrastructure indicators.
8.2.2 The Green Finance Programme develops theory of change and logframe with key stakeholders.	August 2019	The logframe will be refined in the inception phase.
8.3.1 The Energy Programme is on track to have an Advisory Body that includes key stakeholders.	August 2019	3 The Energy programme Theory of Change has been reviewed internally and shared with key stakeholders.
8.3.2 The Energy Programme develops theory of change and logframe with key stakeholders.	August 2019	4 Likely to be delayed - the logframe will be refined in the inception phase
8.4.1 The Trade Programme is on track to have an Advisory Body that includes key stakeholders.	August 2019	There is a programme advisory group, which includes government and regulatory stakeholders. A wider range of stakeholders would help in later phases.
8.4.2 The Trade Programme develops theory of change and logframe with key stakeholders.	August 2019	The Trade Programme has presented the programme Theory of Change to the Deputy Minister of Trade, government office and the programme advisory group. The logframe will be refined in the inception phase.

Key Points

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
Widen range of stakeholders to ensure delivery

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key cost drivers and performance
Spend to date has been on transitional projects, which have provided good support for the development of the full programme, and have largely been delivered on time and to the team’s planned budget for the programme as a whole though there is some significant underspend relative to allocated and business case budgets for 2018/19.

Detailed breakdown of costs for Financial Year 2018/19:
STRAND	ALLOCATION	ACTUAL SPEND	VARIANCE	%VARIANCE
GREEN FINANCE	£ 188,140	£ 194,956	-£ 6,816	-4%
TRADE*	£ 1,120,302	£ 768,622	£ 351,680	31%
FUTURE CITIES	£ 615,470	£ 504,504	£ 110,966	18%
ENERGY	£ 452,273	£ 473,903	-£ 21,630	-5%
PROGRAMME DESIGN AND CAPACITY BUILDING ENGAGEMENT**	£ 77,685	£ 76,381	£ 1,304	2%
OTHER ADMIN***	£ 50,000	£ 51,340	-£ 1,340	-3%
OVERHEADS****	£ 850,000	£ 1,318,600	-£ 468,600	-55%
TOTAL	£ 3,353,870	£ 3,388,306	-£ 34,436	-15%

*£300K underspend due to postponement of "Diagnostic of requirements for Brazilian ports" to inception phase in FY 18/19
**including Gender assessment, economic support and capacity building missions
*** including staff travel, regional support from London and in the region; learning and development / ****including staff costs and platform charges

Programme teams have suffered from gaps in middle leadership, and in particular from a disconnect between operational and strategic understanding of value for money and theory of change. The programme is presently over-programmed by around 20% and spend is planned later than is set out in the SRO letter.
	19/20	20/21	21/22	22/23
Actual estimated requirement	£10.1	£14.9	£23.3	£14.4
Business case budget	£14.4	£17.2	£15.2	£4.9
JFU allocation	£18.2	£24.8	£0.0	£0.0

There have been significant delays to contracts, which exacerbate issues around spending profiles to the point of posing a risk to VFM (business case budgets, allocated spend and present forecasts are set out in the table below, in £M, and it can be seen that if the programme spends according to current plans, it will experience a very significant shortfall in later years). It should be noted, however, that transitional projects have largely been delivered on time and to budget, and provide useful support to the programme as a whole.
Programme management overheads including staffing are around 8%, largely as a result of the relatively high cost of staff in Brazil (staff numbers and grades within individual strands are lower than those for other similar programmes); the team has informal documentation setting out agreement to this position. The cost of staff has also meant that the team has found it difficult to recruit specific expert support for the programme as a whole. This is likely to be an ongoing issue in balancing adequate oversight against affordability, although at the time of writing the programme is nearly fully staffed.

The ‘overheads’ budget was significantly overspent. This was due to unforeseen and un budgeted ‘platform costs’ for services provided by the FCO to the Prosperity Fund (including office and residential accommodation). Although these costs will fluctuate and are difficult to predict, the team has now budgeted these for future financial years.

VfM performance compared to the original VfM proposition in the business case
The programme has changed somewhat since the original business case, and because formal change controls have been limited it is not possible to link the present theory of change and VFM assessment clearly and fully back to the original business case. Nevertheless, the programme has a theory of change for each strand, and is developing approaches to ensuring VFM.
Economy: The contracting process is partially complete for only one of the four strands (Trade); the others are have yet to sign contracts (Green Finance, some elements of Trade, and Energy) or are renegotiating agreements (Future Cities). For this reason, the review team’s sight of the procurement processes and outcomes is limited at this stage. For one of the four strands (Green Finance), delivery partner costs and fees are determined largely by FCO frameworks. Of the remainder, one (Future Cities) has been subject to significant unflagged overspend on the inception phase of the Water project (amounting to 53% of the relevant project, or 11% of the total) by the delivery partner and difficulties in obtaining appropriate financial reporting. The team is developing tighter controls for the remainder of the programme, with appropriate senior support, and plans to absorb the overspend within the costs of future phases of the programme; the impact on overall VFM has not yet been assessed. The third (Trade) includes an element of non-standard contracting with a multilateral organisation, and seems to be delivering appropriate economy, though it remains over-programmed. The final strand (Energy) is still working on contracting, and is likely to deliver through FCO frameworks. The team has expressed some concern (especially in the Green Finance and Trade strands) that framework contracts have not limited the scale of inception phase work appropriately, and that accordingly the balance between design work and on-the-ground delivery is not as economical as they would like (or had expected, following discussions with FCO procurement)
Efficiency and effectiveness: the programme has not yet begun to deliver on the ground or to convert inputs into outputs and for all four strands the inception phase will be key in terms of designing appropriate logframes and developing approaches to programme design within a (possibly) more constrained envelope. At present, the programme team does not have a sufficiently detailed understanding of the costs, benefits and risks of individual elements of the programme to support such an approach; we recommend that the team work with contractors to develop such an understanding with all due speed, and consider the use of MCDA approaches where a qualitative understanding is the best that is available. Logframes and governance processes are partly in place, but need to be developed at pace during the inception phase to allow the team to deliver VFM. The Energy strand hopes to draw on substantial matched funding to allow delivery of a very broad programme within a smaller than planned funding envelope, but has not yet confirmed this funding. The Green Finance strand is subject to some delivery risk as a result of political and contextual change.
Equity: none of the strands as yet has a complete approach to delivery of outcomes around gender and inclusion, though all have made very encouraging recent steps in this direction and the team as a whole has clearly treated this as a priority.
Assessment of whether the programme continues to represent value for money
Overall, the review team notes that the programme is likely to deliver VFM; it has selected interventions that are similar to those of other Prosperity Fund programmes that do present clearly-evidenced VFM and has clearly aligned its approach to local political and economic conditions. The team is also committed, and is developing appropriate financial and programme management processes at pace. However, issues around change management, delays in contracting, and delays in full development of theories of change and primary outcomes mean that it is not presently possible to demonstrate that the programme will definitely deliver VFM.
The most significant risks to VFM are:
1. The absence of clear, consistent change control processes, high-quality and cohesive theories of change, and high-quality log-frames, which would allow the present designs of individual strands to be aligned clearly with the theory of change for the programme as a whole. The approach to individual strands has changed since the BC as a result of political and contextual change, and although the change is in general appropriate and meets the needs of the Brazilian and UK governments, it cannot be clearly mapped back to a best VFM approach;
2. A lack of detailed understanding of the costs and benefits of the individual elements of the programme, at a level appropriate to supporting reprioritisation of each strand. This is needed to allow the programme to continue to deliver VFM within a revised spend envelope at a strand and at a programme level, and to front-load spending where appropriate, for example;
3. A clear alignment of the strategic and operational layers of the programme, such that financial and delivery risks can be assessed at strand level and escalated;
4. Availability of central support and training such that strand leads are able to manage contracts and deliverables with confidence and deliver clear economy and efficiency.
Quality of financial management
Two strand delivery partners are in place at present (one, for Trade, covers only part of the work of the strand), and both have slightly unusual contractual arrangements, as both are international organisations with solid track records in the relevant areas. As a result, the team have had some difficulty in ensuring that appropriate financial reporting and management is delivered within the delivery partners’ standard contracting approaches, and in one case there has been a significant unflagged overspend. The team are aware of this and are putting in place appropriate financial controls (see also recommendations in Commercial section). The team has appropriate systems for internal reporting, but has no external audit in place at this stage; we recommend that such an audit should be arranged.

Recommendations (see also recommendations around contractual approaches and financial management in Commercial section, high-level recommendations around change management, training and specialist support, and recommendations around development of logframes in MREL section)
1. As discussed in more detail in the strategic and MREL sections of this report, make clearer use and documentation of consistent approval processes for changes to strands’ theories of change and actual activities, and build on existing work to develop logframes and programme management tools.
2. Consider the explicit, documented use of multi-criteria approaches (possibly drawing upon independent facilitation support from the analytical community) to develop and compare strategically coherent packages of work within strands and support decision-making around reprioritisation of work within a tighter financial envelope. These approaches will be especially useful where costs and benefits cannot be fully monetised, for example where thinking around the political goals of the UK and of Brazil is necessary. This is especially important for the Energy and Trade strands, but will also be of use for Green Finance in navigating political issues and for Future Cities in managing over-programming and navigating the relationship with the supplier, especially in light of the early overspend in this space. Work will need to be completed well before the end of the inception phase of the relevant strand(s), to allow for appropriate definition of work beyond the inception phase;
3. Develop a clear, updated understanding of the costs, benefits and risks of the individual elements of the programme, at a level appropriate to supporting development of strategically coherent, best-value work packages. Work will need to be completed well before the end of the inception phase of the relevant strand(s), to allow for appropriate definition of work beyond the inception phase;
4. As discussed in more detail in the strategic section of this report, rethink the present line management structure to give a clearer set of incentives to strands, so that they engage more effectively with the programme at a strategic level and with one another.
5. As discussed in more detail in the strategic section of this report, engage with other programmes (perhaps including those in the region) to create more helpful and appropriate guidance for clearance and use by the centre on a range of issues including MREL, contract management and risk management, or to exert pressure on the centre to create appropriate and timely guidance. We also recommend that central teams including JFU and PFDU should take a more customer-centred approach to developing guidance, support, and training for programmes (especially around timing and quality).
6. Develop guidance and training in partnership with programmes so that they meet the needs of programme and strand leads on first publication
7. Arrange for an appropriate audit, working with JFU to develop understanding of the key lines of enquiry for the auditors and define the scope of the work. This should be completed as soon as possible, to allow the audit to influence future work.

Date of last narrative financial report
Date of last audited annual statement	None

E: RISK (1 page)
Overall risk rating: Moderate
Overview of programme risk
The annual review evidences shows that the Prosperity Fund team in Brazil has always considered risks in its work. Although the implementation of a risk management structure and tool was done recently, it is possible to highlight cases in which the team had implemented a strong risk mitigation plan and delivered positive results. Success on this sense includes the ad hoc work done during election period in Brazil, when the team developed a coordinated strategy with political and policy staff for risk assessment and mitigation plan. Since March/2019, the team has been working on the Risk Register, tool that covers risks for the portfolio level and for each strand. The assessment process of completing the register brought awareness for the programme strand managers regarding the importance of managing risks in a more structured way. Although it was a helpful exercise and the orientation is to revise the register monthly, the tool and a risk mind-set is not entirely integrated to the team’s daily work. It is clearly an ongoing process.
As part of the risk management structure, the Prosperity Fund Board analyses and updates the Risk Register quarterly. In addition, the programme strand managers can escalate risks to the Prosperity Fund Board, which occurs every six weeks, when they need advisory or decision making from Senior Managers. The information revised by the Board is submitted quarterly to London and there is a structure to communicate with PFDU and JFU through monthly call where post leadership scales-up issues and risks. Although there is a structure for treating risks from a preventive perspective, the annual review team noted that most of the time the established governance operates in a more solving problem perspective than thinking about mitigation in advance. Also, regarding risks owned by London and despite the formal structure for escalating risks, previous experiences show difficulties getting support, clarified guidance and answers from the centre, especially concerning staffing and capability in which decisions and restrictions on additional resource often sit elsewhere.
Both the documentation of the programme and the interviews we have conducted showcase that individual strand managers have coped surprisingly well, and have focused on continuing delivery and on creating solutions within their individual strands. Nevertheless, evidences suggest that there is a significant disconnection between the strategic and operational layers of the programme, which affects the portfolio strength, cross cutting actions and learnings and the integration of management tools.
Outstanding actions and recommendations from risk assessment
The Annual Review team recommend that the programme should consider:
1. Defining and implementing a regular structure for the team to engage with risk tools as well as integrate them to other key programme tools – e.g theory of change, lessons learned between strands. This will contribute to the team to internalise a structured management process in their routine, to develop a risk mind-set and to level out strand’s risk management.
2. Integrating Prosperity Fund more completely with other areas of relevance, such as Political/Policy team, for assessment and mitigation of political and reputational risks. Integration with Comms teams has also been indicated to be necessary, as it could improve the quality of internal communication with London (to help the central buy in PF Brazil) and better external communication (which would support the relationship with key stakeholders).
3. Establishing roles, responsibilities and a joint strategy for managing risks with the implementer. Also, integrating the Prosperity Fund and implementer’s risks tools will contribute to clarify riskownership and monitoring.
4. Making a clearer case to centre on administrative resourcing, including reclassification of some resources to implementation, as has been done in Mexico. This would place the programme on a more secure footing to restructure its virtual teams somewhat and draw in specialist resource to support the teams;
5. Rethinking the present line management structure to give a clearer set of incentives to strands, so that they engage more effectively with the programme at a strategic level and with one another.
6. Establishing an institutional memory. An organised Sharepoint/cloud will allow teams to access information on previous projects and on-going ones, which is helpful particularly when there is new staff joining. The team recommends clear guidelines on information management for both strand and portfolio level.

F: COMMERCIAL CONSIDERATIONS (1 page)
Delivery against planned timeframe
Overall delivery of the programme is behind the timescales set out in the Business Case. It was expected that the programme would be in its inception phase for all four Strands during this first Annual Review.
Programme Strand	Expected timescales (Business case)	Expected timescales (logframe)	Actual timescales	Explanation
Energy / ToRs launched Supplier selected Contract signed	Sept 2018 Dec 2019 Mar 2019	Dec 2018 Apr 2019 Aug 2019	Feb 2019 Apr-TBC TBC	Delays in receiving Ministerial approval for the Final Business Case for the programme means that contract development and signature has been delayed.
Future Cities / EFO signature Administrative Agreement signature		Dec 2018 June 2019	[Mar 2019] TBC –	The end of inception phase has been delayed until October 2019 at which point a new Administrative Agreement will need to be signed. The team are currently negotiating an extension to the EFO to cover the extended inception phase.
Green Finance / ToRs launched Supplier selected Contract signed	Sept 2018 Dec 2019 Mar 2019	Dec 2018 Apr 2019 Jun 2019	Nov 2018 Jan-Mar 2019 TBC	Delays in contracting experienced. It is expected that given the progress made on the contract to date that this will be signed in July 2019.
Trade (procurement) / ToRs launched Supplier selected Contract signed	Sept 2018 Dec 2019 Mar 2019	Dec 2018 Apr 2019 Jul 2019	Sept 2018 Jan-Mar 2019 TBC	The Trade strand has experienced significant delay in the contracting stage. Development of the contract has commenced but a version has not yet been shared with the selected supplier – it is therefore expected that the signature is likely to happen later than for Green Finance, likely in August 2019.
Trade (OECD agreement)	n/a	n/a	n/a

Slippage has occurred due to a number of factors:
- Optimism bias in the original business case timescales.
- Contracting taking significantly longer than expected. This is due to two reasons a) the programme team not receiving contract management training at an early enough stage, resulting in the team needing significant time to understand the contracts, and amend these before sending suppliers contracts which then require additional time for negotiation; b) the Commercial team in London not being sufficiently resourced to support contract development and signature e.g. access to legal resources has been limited.
- Reduced resource at Post, including carrying a key gap at the Head of Prosperity Fund level which has impacted the development of the SoRs for the programme, and as a result the amount of work required to complete contracting as some of this was not considered before the ITT was published.
- Approvals have been delayed in specific cases – most notably for the Energy programme where Ministerial approval for the programme following procurement has not yet been secured.

This has not impacted costs (or at least there is no evidence to suggest this). However, it will impact upon the spending profile for the programme, with significantly more spending being pushed to later years due to the delay in the start of inception and implementation.
Some mitigating actions were taken by the team to try to mitigate the risk of delays in the procurement process:
- Seeking contract management training to inform contract finalisation. The team had been requesting this from the PF central teams for over a year ahead of the procurement being finalised. However training was only provided in May 2019.
- Seeking to learn lessons from other programmes. The team incorporated lessons from the Mexico, China and South East Asia programmes into their SoRs documents.
Suggested remedial action / action to further mitigate risk of continued delays:
That the team consider building additional contract management expertise into their staffing structure: this could be a permanent member of the team, support through a contracted organisation, agreed allocated support from one of the PF central team in London, or shared regional contract management support e.g. through the Latin America Procurement Hub. The team are going to require continued support on contract management through the inception phase and critically at the end of inception where contracts will need to be varied for implementation delivery. The team does not currently have access to sufficient resource to do this and it is clear that the FCO Commercial team will not be able to provide this resource.

Performance of partnership(s)
The programme currently has two partners in place for the programme .
The programme also implemented transition projects in 2017/18 where they partnered through a mixture of MoUs, commercial contracts and grants. Some of these partnerships have generated lessons that the programme team have identified as areas that they can learn from when building their relationships with their selected suppliers.
The team are preparing to kick-off inception phases for the Energy, Trade and Green Finance strands. This will mean the programme will be working with these partners for the first time. There is significant opportunity for the programme team to implement lessons learned in their approach to onboarding their suppliers for the inception phase, both from their transition project experience and from other PF programmes in the network who have undergone this process.
The Prosperity Fund programme in Brazil could be a more effective partner by:
- Taking a partnership rather than a client-implementer approach to the relationship. A partnership approach where implementers are encouraged to involve the programme team in programme development and delivery can help to ensure that risks are raised early, that the programme team is able to capitalise on the relationships with stakeholders and can drive up the overall quality of the deliverables. It is also likely to incentivise a positive relationship in which issues are escalated early and problems are shared to find joint solutions which is a key mitigation for managing risk.
- Setting expectations clearly at the start of inception for the type of involvement the PF team plans to have during the lifetime of the programme, including: engagement with stakeholders, branding and communication of the programme, involvement in decision-making.
- Providing clear and consistent guidance and templates to suppliers early on, including: the role of the supplier in secondary benefit delivery (including logframe indicators); performance and financial reporting tools; risk management tools.

Changes in the Delivery Plan
There have been no material changes to the delivery chain between the approval of the OBC and this Annual Review. As part of the procurement process suppliers for the Trade, Energy and Green Finance strands were required to submit a Delivery Chain Map [which is annexed to this Review].
Asset monitoring and control
The knowledge within the team of the process for approving asset and equipment purchase, and the process for monitoring assets once purchased, varied considerably across the programme team. Several of the selected suppliers included asset purchase within their delivery plans – the Future Cities programme being the most significant of these, where implementation will rely heavily on the use of equipment. It is therefore key that the programme team receive training on the process for asset approval at the earliest moment, that they communicate this process to suppliers early in inception, and that they put in place the necessary tools to monitor this throughout the lifetime of the programme.

G: Business Environment (½ page)

How has the business community and business environment responded to the programme?
All four programme strands have engaged effectively with key external stakeholders, particularly government officials, intergovernmental agencies and development banks, through consultations, dialogues, workshops and discussions to gather evidence, ensure alignment and the continued relevance of the proposed interventions. During the period under review, programme strands received positive external feedback. In June 2018, OECD Secretary General Ángel Gurría described the work the Prosperity Fund trade programme is doing to support Brazil align with OECD standards as a ‘game changing.’ The engagement driven by the trade strand is perceived to have strengthened the UK’s relationship with the OECD.  It is recommended that the programme develop a stakeholder engagement strategy at the portfolio level, to support the ongoing effective stakeholder engagement and stakeholder management by the strands, particularly with intergovernmental agencies and development banks, but also with academia, civil society and beneficiary groups.
Whilst the Brazil PF programme is designed to open markets and generate opportunities, programme strands have engaged considerably less with the business community to date, particularly to inform the design of interventions. Programme staff have relied on Department of Trade (DIT) colleagues to raise awareness of the programme and potential opportunities for the private sector through launch events and market consultations. During the review period, DIT, Canning House and the FCO (funded by non-ODA) held a regional lunch event, showcasing how companies can engage in Brazil, Colombia and Mexico by showcasing business opportunities that arise from the Green Finance, Future Cities and Energy programmes. The forum aimed to strengthen an aligned regional approach for the Prosperity Fund and its commercial opportunities in Latin America. Over 60 businesses attended the event. Feedback received from companies was very positive. The event focussed on prospective implementers and rather than engagement with the broader business community. It is recommend that the programme further explore the role of the private sector (internationally, including the UK, and within Brazil), particularly the private sector’s role in supporting mutual prosperity, by working with DIT to understand the barriers and business imperatives faced by the private sector in participating in development locally, and building this thinking into the development of secondary benefits work.

 (Where relevant) What role has non-ODA spending played in promoting programme objectives?
Non-ODA spending has been used to raise awareness of the PF Programme among private sector in the UK and to highlight UK specialist expertise with Brazilian stakeholders, with the intention to maximise the commercial opportunities for UK companies through partnerships.

More specifically non-ODA (£205,000) has supported:
- A mission to São Paulo from 3 UK SMEs interested in Brazil’s urban mobility market to match them with Brazilian companies, under the bilateral Future Cities Programme;
- A mission to London for COMPESA (the Water Utility of Pernambuco) to attend the International British Water Conference to better understand expertise in water loss monitoring and management;
- A commissioned report on UK capabilities on water loss management;
- A seminar with the Brazilian government, development banks and UK companies as part of the Infrastructure and Capital Markets Task Force on best practices for the use of guarantees scheme, capital markets and green finance in Infrastructure project and UK expertise in implementing its guarantee scheme.
- A report on UK investors in Infrastructure and Sustainable infrastructure projects in international markets;
- Delivery of a Urban Mobility workshop for six Brazilian municipalities on best practice, international standards and models for transport concessions in cities such as Santiago, Bogotá, London and in Singapore that contributed to the entry of international players and further competition;
- Open Data Institute (ODI) mission to Recife to lead a workshop with City representatives from Recife and Belo Horizonte, the two cities in Brazil that will be benefited through the Global Future Cities Prosperity Fund to present the benefits and value of open data to deliver better services;
- A hackathon organised with Porto Digital (Recife Tech Hub) focusing on developing mobility and open data.

There are some challenges facing the programme in regard to maximising secondary benefits. Staff demonstrated a wide diversity of opinion on the potential for secondary benefits, the extent to which they are a priority for the programme and prospective implementers. Secondary benefits definitions and guidance, particularly with regards to measurement, from London has not kept pace with the team’s needs and has led to differing interpretations of what is expected. Furthermore, the role of non-ODA to support specific programme secondary benefit objectives has not been strategically outlined nor identified, and in its absence there is no strategy, defined pathways or metrics to assess the effectiveness of non-ODA in supporting ODA programme objectives. Moreover, the bidding process coordinated by London for further non-ODA took place before any systematic assessment of the effectiveness of the first non-ODA projects.
The Secondary Benefits Advisor, has started developing a Secondary Benefits action plan and strategy, through conducting workshops with individual strands and DIT to support the identification of secondary benefits within primary purpose interventions. The relationship between the programme and DIT was described as positive and productive.
The team acknowledged that secondary benefits can occur before, during and after the delivery of primary benefits due to their enabling characteristics, and that secondary benefits can form a key part of the delivery of primary benefits. It is recommended that the programme strands, supported by the Secondary Benefits Advisor, continue to develop the steps of programme delivery in a way that creates and explicitly identifies the opportunities for international business to come in and deliver their expertise, coupled with a vigorous prioritisation of the opportunities identified to select priority sectors to focus very limited non-ODA resources on for maximum impact.

H: MONITORING & EVALUATION (½ page)

The Brazil Prosperity Fund Bilateral programme has not been evaluated to date. While an evaluation approach paper has been prepared, the timing of an evaluation by the PF’s Evaluation and Learning (E&L) partner is currently under discussion with the Joint Funds Unit and programme team. The primary purpose of the evaluation would be to assess the programme’s design, coherence and likelihood of success, generate learning for the Brazil programme team (PT) about results (what has been or is likely to be achieved), factors that have supported or hindered success and what works well or less well to support ongoing and future programming and cross-Fund learning.

The initial interactions between the E&L team and previous head of Prosperity Fund, took place in 2018, with a focus on defining the best Monitoring, Reporting, Evaluation & Learning (MREL) approach for Brazil, keeping track of programme activities and identifying the best time to launch the evaluation process. The conclusion was that more intensive interactions would be useful at a later stage, after the general elections in November 2018, supporting the revision of ToCs. In February 2019, the new head of Prosperity Fund, programme economist and E&L team discussed the E&L areas of interest. These were further refined at an E&L Workshop with the wider programme team in April 2019 to inform the approach paper, which was submitted to JFU in May 2019. Staff interview for the annual review demonstrated general awareness of the evaluation but not a detailed understanding of its objectives and purpose, and there were some questions on its distinction from the annual review, which suggests further guidance and communication is required.

In the first half of April 2019, the MR team prepared a preliminary revision of the programme’s overarching Theory of Change remotely, combining the Theories of Change of the individual four strands. The involvement of the programme team in developing the programme’s overarching ToC is understood to have been minimal. The programme ToC is an aggregation of the strand-level ToCs, with very limited consideration of interactions between strands. However, individual strands demonstrate strong ownership and high levels of engagement with strand level Theories of Change, some of which have been validated with key programme stakeholders, via consultations and workshops lead by strand leads. There are differences in how the illustrated ToCs are used to reflect changes in the approach. Changes to the approach are sometimes documented by updating the results framework, or the SOR. Therefore these documents are performing the role of a ToC – instead of routine refinements to the ToC strands are refining these documents.

An Evaluation Stocktake took place at the E&L Workshop during the Brazil Programme team Away Day, which involved a presentation of the Theory of Change of each strand, followed by discussion of causal pathways, key assumptions and risks, presentation of the Monitoring & Reporting (M&R) version of the Brazil Programme ToC, followed by focused discussions on coherence and recommendations for adjustments. Staff commented on the usefulness of this session in enhancing their engagement and understanding of programme causal pathways. However, it was expressed by a number of staff that a more general Theory of Change training would be useful, for those unfamiliar with the ToC approach, to better understand how to use the approach to learn, adapt, assess and explain impact. The E&L workshop also included a participatory session for the programme team to review and prioritise the evaluation questions for the evaluation.

Regarding the timing of an evaluation, it would be useful for an evaluation to provide technical sector specific findings and insights during the inception period, for necessary adaptations ahead of implementation. Also for a substantive evaluation to take place ahead of the next annual review, to reduce burden and overlap.

Processes and structures are being developed to support informal learning between programme strands on processes and best practice, whilst capacity to engage with learning is often limited due to programme management burdens. It was noted that the bi-annual regional conference provides an excellent opportunity for regional learning. Staff also demonstrated the value of the recent commercial training, and expressed desire for further learning and training on programme management, supported by robust programme management tools. There was also an expressed need for further thematic learning with bilateral programmes operating in the same sectors across the PF portfolio. The team are not using PFLearning, the formal online learning tool, extensively. However, at least one strand manager described participating in the recent PFLearning e-discussion on scale-up and found it very helpful; the team should consider whether further discussions of this form would be helpful in this context.

Monitoring progress throughout the review period

The Monitoring and Reporting (M&R) team conducted a field visit to Brazil in November 2018. The objectives of the visit were to provide training on Prospero, to work with the programme team to refine their ToCs and logframes, and to work on the portfolio’s overall monitoring strategy. Staff expressed that the visit was useful, although the training on Prospero was untimely given design work was ongoing and that training would be more effective closer to the on-boarding process, while there is an acute need for a programme management tool to support effective and monitoring by strand of key activities leading into inception.

Programme strands differ as to the extent to which they have thought-through how they will conduct monitoring activities – for example, how they might collect baselines and define the key metrics and targets for the programmes. Though some very interesting work is progressing within individual strands on specific areas. The Green Finance programme has used transitional funding to engage the International Finance Corporation (IFC) to provide technical M&E support on best practice green finance and infrastructure indicators. While the Trade Programme is working with OECD to produce a contextual baseline on SMEs. The effectiveness of these approaches should be further explored as a model for providing more technical sector specific support with the development of indicators and contextual baselines.

Quality of data is imperative if results are to be measured and reported accurately and effectively, with links to wider learning and adaptive management. There is a need for training and/or support on collecting high quality data through monitoring exercises. The E&L service can provide data quality support to programme teams.

There is need for more general guidance on using logframes to support result-based management and programme effectiveness. Otherwise there is a risk that logframes may become inadequate to support some programme needs and may result in programme accountability for metrics outside of the direct or indirect control of the programme, and difficult to measure indicators without data required for milestones and targets. There is also a need for guidance on generating and reviewing baseline data to measure progress against intermediate outcomes and impacts.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C