Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Prosperity Fund Global Trade Programme (GTP)
Programme Value: £150 million (£141 million revised budget) [1]		Review Date: 25 September 2020
Programme Code: PF TRA	Start Date: 1 April 2019	End Date: 31 March 2023
[1] Total approved budget revised down from £150m to £141m following UK government ODA review in June 2020. However actual aggregate budget of current commitments is £119.8m.

Summary of Programme Performance
Year	2019	2020
Programme Score	A	C
Risk Rating	Moderate	Severe / Major

Summary of progress and lessons learnt since last review
This is the second annual review of the Prosperity Fund Global Trade Programme (GTP), covering the period July 2019 to August 2020. The review questions & methodology are set out in the TOR. The review team held a number of bilateral interviews with key FCDO and Whitehall/HMG officials including the SRO and GTP programme leadership and team. Externally consultations took place with all the delivery partners, some posts and in-country beneficiaries[2]. These consultations were supplemented with desk assessments of progress reports, evaluations and analysis of data/information[3] provided by the GTP programme management team and delivery partners. From these assessments it is clear that the programme and its thematic areas (trade related inclusive economic development, trade and customs facilitation, tackling non-tariff barriers, and supporting trade negotiations with developing countries) are relevant for the achievement of UK Aid objectives and our trade policy priorities now we have exited the European Union and approach the end of the transition period. The programme has the potential to deliver on its primary purpose (inclusive growth for poverty reduction), if tackling Non-Tariff Barriers (NTBs) leads to e.g. reduced prices and increased employment for women and other excluded groups[4]. However this will only be possible if the programme seizes the opportunity offered by FCDO transition to restructure; address points made on VFM; and mainstream Gender and Inclusion (G&I) concerns more effectively across its activities, so that resources and activities across the piece target excluded groups, supporting delivery of the primary purpose of this ODA-funded programme.
[2] Annex 1: See attached list of interviews both internal/HMG and externals.
[3] Annex 2: See attached list of documents and reference materials reviewed.
[4] Global Trade Programme Theory of Change. Prosperity Fund Full Business Case. Enabling Future Trade. Global Trade Programme. Final (January 2019)

In the last 12 months various aspects of the GTP programme components have transitioned from business case/inception stages to pre-implementation and implementation. Like all UK Official Development Assistance (ODA) initiatives, the GTP programme faced two major challenges during this period namely the Covid19 pandemic which has impacted operations, and consequent budget cuts due to the ODA review. These resulted in a number of programme workstreams opportunities, challenges and risks transpiring that need to be addressed in order to maximise the potential for this programme to achieve its ultimate outcome and impact statements as per the Theory of Change summarised below,

It is important to note that this review covers the GTP as a whole programme (including the Service Manager (SM), World Bank/World Customs Organisation, and UK Trade Partnerships Programme components). Individual components and projects within this global programme are performing at a range of different levels, some very well (e.g UK Trade Partnerships Programme). The question that this review addresses is performance of the whole Global Trade programme against the original full business case objectives, plans and assumptions, particularly focussing on the last 12 months (July 2019 to August 2020).

Achievements
In the last 12 months the GTP has seen intermediate results being achieved, for example,

The Service Manager Research and Analysis sub-component has launched a number of research projects to support the evidence base to address non-tariff barriers and regulatory reform issues to help liberalise trade and investment. Some good examples below,
- Nigeria Trade Facilitation: This research has a) been the main document to provide an evidence base to inform and structure activities on the African Continental Free Trade Area (AfCFTA) at Post, both as part of the GTP and other programmes, b) has been used by all programmes at Post working on Ports modernisation for stakeholder engagement, and c) been sighted in the Economic Development Forum (EDF) ministerial meeting, which is the key meeting for the bi-lateral agreement between the UK and Nigeria.
- Turkey new presidential system: This analysis has a) been used by programmes at Post to understand who key stakeholder are, and b) provided a baseline on the standards and quality infrastructure system in Turkey to inform the Turkey Standards intervention.
- ASEAN digital trade connectivity research: This research is exploring the feasibility and impacts of creating an ASEAN regional digital trade facilitation system, through the establishment of a private sector-led National Digital Trade Platform. This research will develop a roadmap for digital connectivity, which the private sector will then deliver (ASEAN Business Advisory Council). This project was included in the joint statement on UK-ASEAN economic dialogue and is playing a key role in supporting the UK application to become an ASEAN dialogue partner, which is a key HMG objective.
- Vietnam National Trade Repository (NTR) research: The Vietnam NTR research project is a significant part of the Vietnam NTR intervention, identifying the legal instruments and content for the National Trade Repository. This research has been key to keep the main stakeholder for the Vietnam NTR intervention, MOIT, engaged.

The World Bank/World Customs Organisation Trade Facilitation (WB/WCO) programme has delivered analytical studies to help middle income countries address Trade Facilitation implementation gaps; supported National Trade Facilitation Committees to progress implementation of the WTO Trade Facilitation Agreement. For example,
- A conference on Authorised Economic Operators (AEO) in Sao Paulo, Brazil resulted in joint statement by 10 Heads of Customs to continue AEO collaboration.
- A time release study deliverd by the WB and WCO was finalised for Brazil to enhance the evidence base for border/customs reforms, which is supporting reforms in 10 other countries in the region.
- A Gender Approach Paper to enhance this sub-programme’s contributions to G&I outcomes is also being used to influence programme stakeholders’ policies and practice to support G&I in trade facilitation, border and customs reforms.

The UK Trade Partnerships Programme (UKTP) component of GTP (led by FCDO’s Trade for Development Dept. with a separate log frame and governance arrangement) has started implementation. An MoU was signed with the UN agency’s International Trade Centre (ITC) based in Geneva. The UKTP sub-programme’s work on SMEs has been making some progress despite Covid19: (a) launching the National Policy on Quality Process in Comoros; (b) engaging farmers in Fiji to enhance trade in ginger value chains; (c) developing communication strategy for 24 EPA countries to raise awareness among SMEs about EPA use preferences and benefits; (d) in the Caribbean region over 400 entrepreneurs and business support institutions joined in four thematic webinars conducted in partnership with Caribbean Export, Caribbean Network of Services Coalitions and Organisation of Eastern Caribbean States (OECS).

Some projects under the Service Manager coordinated workstream have started implementation, for example the Brazil Intellectual Property Office modernisation which has been receiving some traction from policy makers and business. Indonesia is supporting the Indonesian government with marine strategic development planning (including fisheries, tourism and how to attract private sector support and investment). Trade Forward Southern Africa plans to contribute to more and better trade within Southern African Customs Union + Mozambique (SACU+M) and between SACU+M and international markets, including the UK to support the realisation of inclusive growth and mutual prosperity for poverty reduction in the region. This programme has a strong focus on women and other excluded groups and will select interventions in sectors and sub-sectors that disproportionately benefit women.

Additionally, GTP support to the Southern African Customs Union (SACU) Secretariat's Customs Modernisation Programme (CMP) has contributed to 135 African firms being accredited as preferred traders – a status provided to firms with substantial import/export transactions, and which have a level of confidence about their operations (including tax administration) by Customs Dept. The SACU Secretariat have said that this accreditation scheme should reduce the experience of delays and costs at the border and by extension increase revenue for SACU member countries (Botswana, Eswatini, Lesotho, Namibia and South Africa).

Challenges
The programme and GTP team in FCDO faced a number of complex challenges in the last 12 months that has impacted delivery and the performance. These challenges include:

Covid19 pandemic - which has in the last 6 months substantially impacted the ability of delivery partners to implement activities while travel restrictions continue, strict Standard Operating Procedures are in place (e.g. to ensure adherence to physical distancing); and PF procurement activities were on hold. These consequently affected engagement levels with government, private sector and other programme stakeholders.

The ODA review in June 2020 has had a substantial impact on GTP. Overall the GTP global budget was reduced from £150.0m down to £141.0m (a reduction of £9.0m); although current aggregate commitments add up to £119.8m. Much of this reduction came out of the World Bank/World Customs Organisation Trade Facilitation component (seeing a reduction of £6.0m from an original budget of £25.0m), and a proportion from the UK Trade Partnerships Programme. This could pose a risk in the future for the GTP as majority of the benefits (as per the business case assessment) is likely to emanate from implementation of trade facilitation, border and customs reform measures. Unfortunately the ODA review short deadlines did not provide the GTP team adequate time to consider all budget cuts/deferment options (including cost/benefit analysis). The GTP team are in the process of reviewing programme workplans and logical frameworks to ensure key activities and outputs can be delivered in line with the original Theory of Change and objective of the GTP, but with a reduced budget (and limited delivery time). It will be important for the team to consider in detail the potential impact of these budget cuts/deferments on the ability of the programme to delivery against the primary purpose (poverty reduction through inclusive growth) and secondary benefits (in the broadest senseas per JFU guidance – both commercial and non-commercial benefits).

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
Risks
The programme is facing three major/severe risks that need to be addressed urgently (within the next 3 months). These are as follows:

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Value for Money (VfM) – As things stand, now that the inception phases for each programme strand are now complete, our observation is that the programme does not satisfy core value for money tenets. From a cost perspective, the ratio of non-intervention costs to intervention costs has worsened during the period under review – primarily as a consequence of ODA reprioritisation – and does not meet the ratio intended in the original full business case. Costs for services remain high. There are indicators that parts of the programme have been efficient, however performance varies widely from country-to-country and intervention-to-intervention. Delays and reductions in the programme’s breadth of ambition also leads us to question whether it will meet its effectiveness obligations over the implementation period without radical restructuring and reprioritisation. Moreover, the programme’s decision-making governance processes has paid insufficient attention to tracking quantitative benefits, focusing entirely on cost and scheduling efficiencies only, meaning that it is unclear whether benefits can be adequately delivered in the time available. Finally, there are concerns from an equity perspective, elaborated below.

Whether the programme is sufficiently focused on inclusion is also a severe risk we want to flag at this stage, which should have been addressed through inception. Urgent attention is required in order to identify the beneficiaries. Although there are islands of good practice within TFMICs, UKTP and SM elements, overall there is a high risk that the benefits of the programme are not equitably distributed.
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Another important area where there is a medium risk of non-delivery by the programme end date is on Secondary benefits. While a Secondary Benefits Approach has been produced by SM, it is not clear that this has been endorsed by the GTP Board and operationalised by the GTP FCDO programme team. The team does not have a dedicated Secondary Benefits Adviser (ideally who would work to liaise between FCDO and DIT, business and business associations) to help contribute to secondary benefits realisation. Finally while there is more clarity on the types of secondary benefits that could be realised from the SM component, there is no such clarity with regards to the other two main components of the GTP (the World Bank/World Customs Organisation Trade Facilitation, and the UK Trade Partnerships Programme workstreams). For example a detailed secondary benefits realisation plan and tracker linked to the overall MREL framework could contribute to demonstrating the programme’s contribution to the PF’s secondary benefits objectives.

Opportunities
As we transition away from the European Union and tackle the economic fallout from the Covid19 pandemic the GTP can play an important role to support the UK’s trade negotiations with developing countries; contribute to enhancing two-way trade and investment, and help tackle barriers to trade through supply and value chains with these emerging economies (e.g. address the tilt towards protectionism in some sectors – health goods such as PPEs due to the pandemic). There are opportunities now to make strategic decisions that could positively contribute to the programme’s ability to achieve its intended outcomes and impact in the long term as per the full business case/Theory of Change. This includes strengthening value for money through identifying efficiencies and cost savings in delivery, and ensuring G&I is integrated well in the logical framework. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX The recommendations below elaborate further on how these opportunities can be taken forward within the next 3 to 4 months.
Prioritised list of recommendations
		Scores			Results
Recommendation		Relative urgency[5]?	Relative criticality[6]?	Risk introduced[7]?	Total score (out of 9)	Weighted score[8] (out of 18)
1	Produce a robust and detailed global level logical framework for the GTP, covering all GTP sub-programmes (Service Manager led projects, World Bank/ World Customs Organisation Trade Facilitation programme, UK Trade Partnerships Programme programme). This global logical framework should follow the Prosperity Fund/JFU template and guidance, and include clear impact, outcome, outputs statements, with indicators, baselines, annual milestones, end of programme cycle targets, output weightings and assumptions. To be completed urgently, reviewed by MREL specialists and JFU, and approved by the GTP Programme Board (and potentially the PF Portfolio Board) latest by December 2020. In addition, the global programme level risk assessment and mitigation plan should be updated and monitored quarterly and should include G&I related risks and mitigation.	3	3	3	9	18
2	On Gender and Inclusion (G&I), to ensure compliance with the International Development Act (IDA) and align with PF G&I policy, develop a G&I action plan (to include clear objectives, level of ambition, deliverables and appropriate resourcing to achieve them for the whole GTP programme, as per AR 2019 recommendation). As part of the recommended management and capability review (below) attention needs to be given to appropriate level of G&I resource to deliver this G&I action plan, within HMG, as well as within all primary and secondary delivery partners. GTP G&I policy lead support is particularly required for projects that have scored low on the G&I scorecard, Brazil and Vietnam.	3	3	3	9	18
3	Deliver demonstrably improved Value for Money for the programme as a whole.The programme must introduce better governance and achieve better performance so that every pound of public money spent in the future achieves trackable and optimal results. Thematically, the programme must ensure that specific improvements are introduced before any upcoming decisions that will commit departmental spend in 2021/22. This general timeline is recommended because of the ongoing uncertainty surrounding both the quality of historic spending decisions (currrently being advised as part of an independent audit), and the relative value of aggregate outcomes as promised in the department’s original investment approval – the full business case. / Full details and requirements have been laid out in Section D.	2	3	3	8	15
4	Implement pending actions from last year’s annual review (2018/19), see further details in Sections A and D below. The programme team should develop an AR recommendations tracker, with a designated lead responsible for tracking and driving progress on Annual Review G&I recommendations.	2	3	3	8	15
5	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	3	2	1	6	14
6	As this is a £141 million programme facing complex internal and external challenges it is recommended that an independent midterm evaluation takes place in 2021 to coincide with the next annual review, including if possible travel to project sites (Covid19 travel restrictions allowing). This review should demonstrate progress on delivery against the recommendations of previous annual reviews (including the current review), particularly focusing on financial management, VfM, and G&I, against a complete and overarching global logical framework.	2	3	2	7	14
7	Undertake a review/audit of FCDO governance and management structures to ensure that they are fit for purpose, especially in the light of the FCO/DFID merger. Enhance capacity for procurement/contract management, and performance management of delivery agents function of the GTP team in order to be able to deal with the growing complexity and increased workload of managing this multi-million pound ODA programme. Ensure that PF guidance on procurement, including on G&I (SoRs, bid evaluation etc) is followed in all future GTP procurements.	2	2	2	6	12
8	Return the development policy function back to FCDO from the Service Manager contract, and restructure staff resources within GTP. Explore (with the ongoing FCO/DFID merger) the creation of a broader trade and development advisory support team to offer technical advice and oversight on the programme. This team should include G&I/social development, trade for development, economist, regulation & standards, M&E and programme management expertise. This will also support the GTP’s objectives with more collaboration and complementarity between the PF GTP and ex-DFID aid for trade programmes.	2	2	1	5	11
[5] Scoring out of 3: <2 months = 3, >6 months and <1 year = 2, >1 year = 1
[6] Scoring out of 3: High = 3, Medium = 2, Low =1
[7] Scoring out of 3: Low = 3, Medium = 2, High =1
[8] The scoring criteria has weighted: urgency (3), criticality (2) and risk introduced (1).

SRO Commentary (January 2021)
I am grateful for this annual review that recognises the areas where the programme has had impact as it has moved from inception to delivery. I accept the recommendations and will structure the team to deliver the changes required. The report also highlights the challenges faced by the programme and the impact of the ODA reprioritisation exercise on overall economic case of the programme and in operations and governance through the focus and redistribution of staff to the Government’s response to Covid-19. The subsequent ODA reprioritisation and bar on commercial activities above £3m has meant numerous activities originally outlined within the Strategic Implementation Plan (SIP) have been removed as either not affordable, or not achievable in the time frame available. Whilst the impact of the three main elements of the programme interventions are evidenced, I accept the recommendation that these need to brought together into a consolidated Theory of Change across the programme (Recommendation 1).
The report calls for a G&I action plan (recommendation 2) and appropriate resourcing which will be followed up. The projects underway require more detail on milestones but I would note there is no evidence they are not compliant with the IDA. The research is identified as of a good quality and is required to be embedded in a timely way at all stages of the programme cycle.
We are increasing the resourcing in the team to enable this work to take place urgently alongside the other recommendations and have secured support from the FCDO Economics Unit, Joint Funds Unit (JFU) and from across the wider Prosperity Fund team and have filled key posts gap in a key finance and governance roles. In light of the ODA reprioritisation and the impact on the original economic case (and other points raised in the Annual Review) we are reviewing the structure of the Service Manager contract and specification to reduce cost and improve the overall vfm of the interventions (Recommendations 3, 5 and 8)
These changes including those outstanding from 2019 (Recommendation 7) will be in place by the midterm review (Recommendation 6), which is due to commence in March 2021. I have asked the Prosperity Fund head in the Joint Funds Unit to review the management and governance of the Programme (Recommendation 7) and will act on there recommendations.
Addendum – SRO April 2021 – Service Manager provided additional evidence post completion of the review demonstrating progress during review period towards 2019 Annual Review Recommendation 7 (documented sharing of lessons on support to country programmes subject to drafting of the report.) and 2019 Annual Review Recommendation 8 (demonstrating how research informed and influenced design of country projects.)
JFU Commentary
JFU agrees, overall, with the findings of the review, and that this programme (despite elements that are performing well) can only continue with serious reform and restructure. JFU agrees that the programme operates in a high priority and strategically important space, and that this along with islands of good practice identified, justifies the continuation of some programme activities, rather than full closure. It is important to recognise that elements of the programme are well implemented and delivering good results; the review is focused on the programme as a whole.
However, the results, accountability, design, governance and VFM issues the Review has identified raise serious concerns. The priority from the JFU’s perspective is a) quick and concerted action to address the most serious issues and b) learning lessons to ensure that we understand, collectively, what has gone wrong & ensure that we put in place measures to ensure that this does not happen again.
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
We agree with the proposed independent MTR (timing & process to be worked out with MREL input in order to deconflict); along with a review by April 2021 formally review the extent to which the Action Plan has been implemented.
List of Acronyms

DFID – Department for International Development

DIT – Department for International Trade

DSA - Food Standards Agency
EPA - Economic Partnerships Agreement
FCDO – Foreign, Commonwealth & Development Office

FCO - Foreign and Commonwealth Office

G&I – Gender and Inclusion

GSI – Gender and Social Inclusion

GTP - Global Trade Programme
IIOC – Investment, Infrastructure and Operations Committee

IPR - Intellectual Property Rights
JFU – Joint Funds Unit

KPIs – Key Performance Indicators

L&D- Learning and Development

MICs - Middle Income Countries
MoU – Memorandum of Understanding

MREL – Monitoring, Reporting, Evaluation, Learning

ODA - Official Development Assistance
PF – Prosperity Fund

TFSA – Trade Forward Southern Africa
SM - Service Manager
TFA – Trade Facilitation Agreement

TFMIC - Trade Facilitation Support to Middle Income Countries Programme

WB – World Bank

WCO – World Customs Organisation

WEE - Women’s Economic Empowerment

## A. INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	Link to Business Case
DevTracker Link to Log frame:	Link to Log Frame

The Global Trade Programme (GTP) is the single largest Prosperity Fund programme and will provide technical assistance and other support to facilitate free trade and open markets for Official Development Assistance (ODA) eligible Middle Income Countries, enabling greater investment and interaction with global value chains to create jobs and prosperity.  This will be delivered through a focus on two core objectives intended to boost equitable economic growth and reduce poverty: 1) to enable partner countries to identify and remove non-tariff barriers; and 2) to create the conditions for increased international trade in support of the UK Government’s objectives. With poverty reduction as the primary objective, the GTP will also deliver secondary benefits through increasing market access for international businesses, including from the UK, as well as building bilateral partnerships on trade related issues with key emerging markets in support of the UK trade strategy.
The GTP has three separate component or sub-programmes with their own logical frameworks (and in the case of the UK Trade Partnerships Programme component, a separate governance structure and lines of accountability as required by DFID assurance processes – SMART Rules). These components are in the process of being consolidated under a new and updated global logical framework (as recommended by this review team). All three components are now in the early stages of implementation.
The DFID UK Trade Partnerships Programme has completed inception and started implementation, despite Covid19 delays. In the last DFID annual review (March 2020) for this sub-programme it received an A rating.

The World Bank (WB) and World Customs Organisation (WCO) programme on Trade Facilitation is progressing with some early intermediate results in the Philippines and Brazil. The pandemic has highlighted the urgent need for trade facilitation reforms, such paperless and automated systems and inter-agency cooperation, to keep critical goods flowing through borders (e.g. PPEs). Through TFMICs, the WB and the WCO continue to provide guidance and technical assistance to countries to implement best practices to facilitate the flow of goods. In light of the unique profile and reputation of the developing partners, the programme managed to adapt quickly in moving project activities forward during the pandemic related constraints. The WB leverages its country offices utilizing virtual modalities and relying more on local staff and consultants. The WCO is leveraging its Customs to Customs approach and reputation pivoting to offer remote/virtual capacity building where possible as part of a blended approach.

Following the approval of a Full Business Case in February 2019, and the subsequent procurement process to obtain a service delivery partner , a Service Manager was appointed in April 2019. On contract signature, the GTP team began a 6 month inception phase to ensure the SM provided value for money against priority deliverables.. The GTP – SM component has two live interventions the Brazil IPO and Trade Forward Southern Africa, with five more interventions in the immediate pipeline, either in or nearing procurement, despite having been delayed due to the effects of COVID-19. The Service Manager also has responsibility to deliver a programme of research.

The programme has had a turbulent time due to the COVID-19 pandemic, with numerous projects put on hold, as well as a bar on commercial activities above £3m. The subsequent ODA reprioritisation and adjusted timelines has meant numerous activities originally outlined within the Strategic Implementation Plan (SIP) have been removed. They are either not affordable, or not achievable in the time frame anymore.

Progress on recommendations from 2019 AR
Preparing for delivery phase:
Recommendation	Progress
To ensure the GTP transition into full delivery is smooth, the GTP team should ensure the main supplier and supply chain have as much clarity on the core requirements to prioritise accordingly. This should include potential delivery partners (e.g. key institutions in country).	Evidence this has been completed for World Bank/World Customs Organisation Trade Facilitation, and UK Trade Partnerships Programme workstreams. The SM component continues to be problematic with clarification pending on roles and responsibilities when it comes to financial management for the whole GTP programme.
To manage potential bottlenecks, this also means developing a tool to manage multiple processes to support effective financial management, especially between flexible and committed programme funds.	Not clear this has happened.
While also developing a workforce plan to ensure the GTP team has sufficient capability and capacity and approved by the Strategy board by Oct (or ASAP after).	Pending, due to recent ODA review and Covid19 related delays, and will be impacted by Spending Review outcome.

Establishing the programme management framework:

Recommendation	Progress
The GTP team should fast track the GTP Theory of Change (ToC) and results framework development to help inform project-level ToCs and results frameworks and ensure these align to the overall GTP and Prosperity Fund ToC and GTP results framework. The overall GTP ToC and results framework should provide enough specificity to help guide project selection, design, implementation and reporting but at the same time not restrict the flexibility of the fund given its demand-driven nature. The team should review and refine the ToC and results framework regularly (at least annually) as and when the context changes or new evidence emerges.	2020 update: This recommendation has not been completed. The theory of change has not been updated since the version published in the full business case. Therefore it has not been updated to reflect all the developments in the programme. Intervention business cases have referenced the original theory of change, however there should be a feed-back process to the central theory of change, and to ensure clear G&I sensitive pathways to primary purpose. Similarly, a programme level logframe has not been completed. Lower level logframes have been produced – however there is little evidence that management or governance process uses the lower level logframes to actively manage or track the programme’s progress. Creation of a global programme level logframe is an urgent issue, because the SRO needs to have sufficient insight into all workstreams and use it as a central aspect in all future decisions.

Assessment framework version 2.0:

Recommendation	Progress
Greater specificity and prioritisation of criteria is needed (e.g. evidence that the interventions are likely to deliver expected results), which should reflect developments in the overall GTP ToC and results framework.	2020 update: This recommendation has not been completed. There is little evidence that the programme uses any scientific processes to study specificity or prioritisation. Recent key decisions have focused only on cost and scheduling requirements – where a wider assessment framework would have perhaps led to alternative prioritisations.

Integration of inclusive growth, gender equality, women’s economic empowerment and poverty reduction issues across the GTP programme and associated projects is essential.
Recommendation	Progress
The overarching ToC requires strengthening to explicitly cover these issues in the causal pathways including potential distributional effects. The support of the social development adviser and the supplier’s new gender and inclusion adviser (starting formally in September) will help integrate gender, inclusion and poverty reduction priorities. But, they should not substitute building capability within and across teams (and wider-HMG) on understanding potential differentiated effects of interventions (e.g. gender, income groups). The Centre of Excellence (CoE) and research and analysis strand has the potential to help develop understanding, capability and identify good practice interventions. The team should also build from existing research, analysis (e.g. GTP’s Work and Opportunities for Women (WOW) Helpdesk thematic brief) and expertise within the team (e.g. gender and inclusion champions), contractors, partners (e.g. WB, DFID, ITC) and wider HMG, as well as peer-to-peer learning across the PF (e.g. gender and inclusion champions etc.) and learning from the first round of projects before commissioning new research and analysis. The team should identify ‘best practice’ project-level business cases (GTP and wider) and share these across the team and promote greater peer-to-peer learning. We recommend using the GTP WOW guidance (as a starting point) to inform any new research and analysis, as well as consultations with beneficiaries and stakeholders. Developing the proposed programme-level Gender and Inclusion Action Plan (drawing on the G&I scorecard approach) will be an important step to further strengthen integration.	Partially delivered. Research & analysis on G&I has been undertaken; this is valuable & adds significantly to the knowledge & evidence base (e.g. Turkey, Vietnam, Indonesia; Zimbabwe value chain (UKTP). Positive progress on resourcing, including provision of a full-time G&I expert policy lead by sub-contractor to SM, and a part-time G&I research specialist to lead on Research and Analysis Fund support (from Sept 2019 to Jan 2020, not yet replaced), as well as gender experts in ITC & WCO, with some collaboration. In addition, development of G&I checklists & training materials by SM, with FCDO, building on the WoW Helpdesk G&I & trade thematic briefing & country plan reviews, shared with PF G&I champions network. A programme-level G&I action plan (or even an interim one, while G&I country-level analysis and impact assessments are undertaken) has not yet been developed.

Closer engagement with DIT
Recommendation	Progress
To ensure better alignment and increase efficiency and effectiveness of GTP projects and interventions. Discuss and agree roles and responsibilities (e.g. on design and reporting) at the next Strategy Board.	2020 Update: Feedback from DIT indicates they have been adequately engaged through participation at boards and information updates. They feel that they have been given opportunity to help shape upcoming and new interventions – especially around secondary benefits. This interaction should continue to be encouraged and deepened.

Addressing delays

Recommendations	Progress
Ongoing/End of inception: Given the need to design and deliver large amounts of the GTP across several trade-related issues and countries, the GTP should set out how it and the wider network are working to minimise delays.	Partially delivered. The Programme team reviewed the governance structure to ensure that the correct functions and resource were in place, and that decisions were made efficiently. This was confirmed by the independent evaluation: ‘The operational model is allowing the programme to quickly respond to emerging priorities. Recent examples include the FCO and service manager working together and responding to needs emerging from the recent COVID-19 crisis, pivoting support to new concepts’. However it is not clear whether the current structure could be made more efficient.

Cross GTP Lessons Learning
Recommendation	Progress
Given how comprehensive the assessment framework is, the GTP team should consider how it might learn from its application to three programmes. For instance, what were the challenges in its application? How well and consistently was it applied? How could it be improved? How were trade-offs between criteria managed? Are certain criteria prioritised, e.g. gender/social impact evaluations?	Not delivered, as far as we are aware, in the shape of documented learning.

How design is informing strategy and delivery
Recommendation	Progress
GTP should consider collating examples of how the strategy is practically informing design and delivery for future annual reviews.	Partially delivered, unless the team can point to specific examples. The GTP Analytical Group comprises a network of stakeholders and experts. All research is reviewed & approved by this group to ensure it can be used more widely and to avoid duplication. Research products are disseminated across Whitehall. Tracking influence of research products is planned by the Analysis group, but not yet operational.

Expertise vs workload
Recommendation	Progress
GTP team should have an independent stocktake in six months on the skills, expertise and balance of work as it moves towards delivery.	Not delivered.

Transferring funding from back-off functions to delivery
Recommendation	Progress
The GTP team to evaluate, possibly in the next annual review, once the portfolio is more established, what (if any) transfers from “back office” funding to delivery were achieved?	Not delivered. This has not been achieved, please refer to the GTP VFM assessment.

Comprehensive Results Framework

Recommendation	Progress
Recommendation: the GTP team consider, as they develop a comprehensive results framework (RF), building a VfM framework to accompany the RF. This should enable the team to develop indicators to help make the VfM case for GTP. This should also help focus the analysis on informing the VfM case and, when changes (e.g. new countries/projects) are proposed, offer a clear framework for assessing VfM. The team should draw on the VFM scorecard developed by the Prosperity Fund’s EL contractor, which includes possible indicators.	2020 Update: This recommendation has not been completed. The 2020 annual review thoroughly encourages that this is undertaken as a priority.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
The Global Trade Programme has two overall outcomes:
- More inclusive economic growth, due to factors such as higher employment and lower prices that reaches to poor (sic)
- Higher UK GDP growth, due to improved export revenues, returns to capital and lower cost imports[9]
  [9] FCDO (2019) Global Trade Programme Full Business Case

 Overall, the programme has made progress, but to date, there is no clear evidence of contribution to inclusive economic growth through any pathway. A number of interventions are in implementation, although projects are for the most part still at an early stage. However, because there is still no overall programme logframe, MREL plan or programme-wide G&I action plan to monitor contribution of all elements of the programme (service manager, DFID UKTP Programme, World Bank & WCO) to primary purpose outcomes, it is difficult to comment on overall progress. The SM ‘programme’ logframe proposes outcome measures that are too high level (e.g. labour force participation rates, GINI index).
The programme Evaluation (July 2020) found that ‘[t]he programme has progressed significantly in the last 12 months, building on the previous two years spent setting up the programme and procuring the service manager. However, it has taken the programme a long time to set up and few projects are in the implementation stage. Given many of the expected results will take time to materialise and there are evidence gaps in the ToCs that need testing, the delays significantly compromise the likelihood of delivering expected results envisaged in the GTP business case. Moreover, despite delays, the original timelines in the GTP business case to deliver expected results were unrealistic.’[10] The likelihood of achieving results will have further decreased as a result of Covid-19’s impact on operations.
[10] Prosperity Fund (2020) Global Trade Programme Evaluation Report Cycle 1
On Primary Purpose and G&I, the evaluation (July 2020) found that ‘GTP is now making progress in elevating and addressing the integration of G&I objectives across the programme and project, with senior management strongly committed to G&I. There is a lack of unequivocal evidence on the relationship between reducing trade barriers and inclusive growth which the programme plans to address through undertaking country-level analysis and impact assessments. However, the research is slow to start, given delays in agreeing how best to manage and commission the research. The programme is moving quickly in designing initial concepts and business cases without these research inputs, which is a missed opportunity that compromises the potential quality of design and likelihood of projects achieving G&I-related results and creates a risk to VfM.’

The review team agrees with this assessment, although we would clarify that while there was evidence of strong commitment to G&I from the previous SRO, it will be good to see this commitment confirmed by new senior management on both HMG and service manager side. Finally, we agree that G&I research is of good quality, but the challenge is to ensure that it is embedded in all stages of the programme cycle – as the Vietnam NTR project demonstrates.

Annual outcome assessment (Secondary Purpose)
Similarly, and for similar reasons, there is no clear evidence that the programme is contributing to higher UK GDP growth, due to improved export revenues, returns to capital and lower cost imports[11]. The programme evaluation (2020) found that ‘there is not a consistent understanding across the GTP team on the PF's approach to secondary benefits. In some cases, there is an assumption that secondary benefits can only occur after primary purpose, however secondary benefits can occur earlier and without compromising the potential achievement of primary purpose. Also, some documents refer to UK rather than international benefits.’ The review team agrees with this assessment. While the service manager has produced an approach document to secondary benefits (slides), the review team is concerned that there does not seem to be a clear plan to deliver and track secondary benefits.
[11] FCDO (2019) Global Trade Programme Full Business Case

Overall output score and description
C
Key lessons
The following lessons are drawn from the Programme Evaluation:
- It is important to be realistic about the length of time it takes to design a programme and associated projects. Results can take years to materialise, particularly those related to changes in behaviour, attitudes and norms. Programmes should reduce the level of ambition of expected results, or extend the timeframes for implementation.
- The rigidity of FCDO processes can make it difficult to be responsive to the changing situations and needs in country and by government stakeholders. An example of this is that some business cases have not yet received approval, while conversations with in-country stakeholders started last autumn.
- To achieve greater rigour in design, programmes such as the GTP need to bring in sufficient technical expertise and conduct consultations on achievable results and assumptions early on to ensure sufficient evidence to back up project concepts and a shared understanding between those involved. This includes more in-depth review of existing evidence and conducting additional research and analysis where necessary to develop robust and plausible pathways to realistic expected results. The evidence should consider both enabling and constraining factors as well as any unintended effects. A monitoring and reporting system should address any evidence gaps. Staff also need to better understand the value of using relevant tools and frameworks to strengthen the design process.
- The demand-driven nature of the programme makes it difficult to design a coherent programme with common objectives and results. The development of an effective monitoring and reporting system should follow a participatory approach and bring in relevant technical and practical expertise to ensure a shared understanding and realistic expected results. The system should also collect data to address evidence gaps, particularly on how the programme enables the sharing of the benefits of mutual prosperity. Moreover, it is important to align all elements of monitoring and evaluation systems and frameworks, ensuring compatibility and avoiding potential duplication.
- Contracts that are based on outputs rather than time and materials have the potential to both contain cost and improve quality. Understanding the ask and costs up front is key to ensuring VFM from a time and materials contract.

Key Actions
See detailed recommendations for the next 12 months listed in the Summary Section.

Summary of changes to the logframe since the last annual review
A log frame has now been developed for the GTP- SM component only. There are separate logframes for WCO/WB and UKTP components.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)[12]
[12] Global Trade Programme Evaluation Cycle 1 report; other progress reports and interview evidence on activities and outputs from three separate components and their separate logical frameworks; GTP team self assessment following verification.

SM Component Outputs:

Output Title	Improved adoption of International Standards
Output number per LF		1	Output Score	C
Risk:		Major/Severe	Impact weighting (%):	No weighting indicated in Logframe.
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of individuals reporting better knowledge and understanding of international standards as a result of GTP activities	Target is 416 by March 2023	Interventions contributing to the indicator: / There are currently four interventions in the SIP that will contribute to changes in this indicator. They are the Indonesia Bundle (comprising Marine Spatial Planning and Fisheries), Trade Forward Southern Africa (TFSA), Turkey Standards and Turkey AEO. / How the intervention(s) will contribute to the indicator: / The OPPDs for these interventions all include plans for Standards specific training and capacity building with direct technical assistance to standards authorities and entities in some cases (e.g. TFSA). / What has the intervention(s) done over the last 12 months? (activities/results): / Trade Forward Southern Africa (TFSA) has completed the inception phase and started implementation. The Delivery Partner has been procured to deliver training with a specific component of the training focussed on Standards. Information and trade needs assessments have been conducted in all six SACU+M countries to understand the potential knowledge/info gaps. The pilot in Aquaculture conducted in Namibia, South Africa and Mozambique has mapped the existing gaps for producers of abalone, oysters and mussels in achieving international standards and specifically the EU Audit for such imports. The other three interventions (Indonesia Bundle, Turkey Standards and Turkey AEO) are currently at OPPD (Business Case) stage following extensive research and analysis, Country Plan development and NPC development.

Key Points
No annual milestones, gender disaggregation or intersectional characteristics, data disaggregation indicating location, ethnicity and religion, income quantiles, difficult to ascertain how activities under this output are contributing to indicator and to the end stage targets, and to higher outcome and impact statements of the global ToC.
Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable, previous annual review addressed operational, governance and inception planning issues.
Recommendation
Produce a more detailed global logframe that includes baselines, annual milestones, impact weightings, end of year targets. In addition consider how standards reform interventions contribute to poverty reduction/G & I, and some activities can demonstrate impact for these objectives. In addition consider what that public good impact will be following reform of standards policy, and how this could benefit international business (including for UK firms).

Output Title	Better protection for Intellectual Property Rights
Output number per LF		2	Output Score	C
Risk:		Major	Impact weighting (%):	No weighting indicated in Logframe
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of patents approved per examiner p.a	Target is 58 by March 2023	Interventions contributing to the indicators: / There is currently one intervention in the SIP that will contribute to the three IP Output indicators: Brazil IP. / How the intervention(s) will contribute to the indicator: / The Brazil IP intervention aims to improve the efficiency of INPI and includes capacity building/training of INPI staff. The Brazil IP Business Case explicitly references two trainings, one during process design and one during implementation. / What has the intervention(s) done over the last 12 months? (activities/results): / Brazil IP was one of the GTP's initial pilot projects and although still in the inception phase of delivery, one of the early successes of this intervention has been the signing of an MoU between the UK and Brazilian governments in relation to the work to support the Brazil government to modernise their Intellectual Property Office. This led to high profile media coverage with both governments verbalising their expectation of increased investment in Brazil and an increased opportunity for UK business as a result of the project.
Number of trainings provided to IP agencies	Target is 2 by March 2023
Number of IP agencies with improved capacity	Target is 1 by March 2023

Key Points
No annual milestones, difficult to ascertain how activities under this output are contributing to indicator and to the end stage targets, and to higher outcome and impact statements of the global ToC. However the Brazil IP project seems promising, with a high level of government and private sector uptake for the project. Interview with Brazil’s IP authority demonstrated strong buy-in for the project, and a clear view how it will contribute to modernising the IP office’s administration to deal with a backlog in IP applications. Progress against two indicators is likely to be achieved (number of trainings provided to IP agencies, and number of IP agencies with improved capacity). However progress against the key indicator (number of patents approved per examiner p.a) is difficult to ascertain as project is still in the early stages of delivery, and the whole programme has experienced operational delays due to Covid19.
Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable, previous annual review addressed operational, governance and inception planning issues.
Recommendation
Produce a more detailed global logframe that includes baselines, annual milestones, impact weightings, end of year targets. In addition consider how IP reform interventions contribute to poverty reduction/G&I, and some activities can demonstrate impact for these objectives. In addition consider what the public good impact will be following reform and enhanced capacity of IP administrative process, for international business (including for UK firms).

Output Title	Streamlined Customs Procedures
Output number per LF			3		Output Score	B
Risk:			Major		Impact weighting (%):	None in current logical framework
Risk revised since last AR?			N		Impact weighting % revised since last AR?	N
Indicator(s)		Milestones		Progress
Number of individuals reporting better knowledge and understanding of Customs procedures as a result of GTP activities		Target is 140 by March 2023		Interventions contributing to the indicators: / There is currently one intervention in the SIP - TFSA, and a a separate intervention the SACU Customs Modernisation Programme (CMP) that will contribute towards this indicator / How the intervention(s) will contribute to the indicator: / TFSA has completed inception phase and is now in implementation. This project has been designed to include a customs training component. / CMP provides improved knowledge and understanding of modernised customs procedures and regional integration for SACU Member States in the field of customs. / What has the intervention(s) done over the last 12 months? (activities/results): / TFSA has completed inception phase and is now in implementation. It is therefore too early to measure outcomes of the intervention, however it has already begun to deliver positive external exposure for the GTP. HMG has signed an MOU with the Southern Africa Customs Union (SACU) Secretariat who will provide delivery support. The signing ceremony received positive reviews from all suppliers. / The Customs Modernisation programme was promoted by the Foreign Secretary on Twitter raising awareness for the good work.
Number of capacity building efforts to improve compliance with Trade Facilitation Agreement		Target is 1 by March 2023		Interventions contributing to the indicators / There is currently one intervention in the SIP that will contribute towards this indicator - Trade Forward Southern Africa (TFSA). / How the intervention(s) will contribute to the indicator / This intervention completed inception and is now in delivery - was designed to include a customs training component which will contribute to improved Trade Facilitation outcomes. / What has the intervention(s) done over the last 12 months? (activities/results) / This intervention has proved particularly responsive to the growing C19 pandemic identifying several new initiatives that will support inclusive growth across Southern African countries in scope of this contract. In Namibia for example, a report has been produced requested by Namibia’s Ministry of Industrialization and Trade (MIT) which focuses on: / 1. An assessment of Namibia’s current cross-border digital trade in services, including recommendations for practical measures to remove impediments to the use of electronic trade documents at the national level (with reference to regional initiatives through SACU), as well as rules and regulatory frameworks governing the digital trade of specific services to strengthen Namibia’s digital market capacity. / 2. A roadmap of different policy options for Namibia to return to growth through trade, including a COVID-19 situational analysis on trade impact and the way forward across different sectors/value chains. / C-19 specific support is also in different stages of delivery in Lesotho and Botswana and Mozambique through the TFSA programme.
Number of improvements to customs procedures as a result of GTP interventions		Target is 2 by March 2023		Interventions contributing to the indicators:There is currently one intervention in the SIP that will contribute towards this indicator, this is Vietnam National Trade Repository (NTR). / How the intervention(s) will contribute to the indicator: / Vietnam NTR is currently in the procurement phase and the GTP is procuring the implementation of an NTR which will simplify the process by which international traders access information relating to trade rules and regulations. This is expected to result in two improvements to customs procedures. A portal which successfully links to the NTR will be the first improvement and access for international traders to obtain consolidated trade information will be the second improvement. / What has the intervention(s) done over the last 12 months? (activities/results): / Despite the fact that this intervention is not yet in delivery, there is already potential to strengthen the UK/Vietnam relationship. The relationship with the Vietnam Ministry of Industry and Trade has been built up through extensive engagement over the past year. They support a proposed side-line event with UK Government to launch the National Trade Repository alongside a November 2020 ASEAN meeting. / What has the intervention(s) done over the last 12 months? (activities/results) / The Vietnam NTR intervention was conceptualised and then progressed through initial research, Country Plan development and NPC development. There is also a Vietnam NTR research project currently in delivery.

Key Points
No annual milestones, difficult to ascertain how activities under this output are contributing to indicator and to the end stage targets, and to higher outcome and impact statements of the global ToC. However the SACU and Vietnam projects are making progress. Interview with SACU Secretarit have highlighted preliminary results from the CMP that this project is contributing (indirectly) to certifying nearly 135 African traders with a customs accreditation status (preferred trader).
It will be important to ensure trade facilitation and customs reform activities under the Service Manager workstream does not duplicate but complements the GTP components led by the World Bank and World Customs Organisation.
Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable, previous annual review addressed operational, governance and inception planning issues.
Recommendation
Produce a more detailed global logframe that includes baselines, annual milestones, impact weightings, end of year targets. Consider using the body of literature and evidence on aid for trade, particularly trade facilitation and customs reforms interventions and their potential impact (if designed correctly) on poverty reduction, G&I and broad inclusive economic growth (sources: World Bank, OECD, WTO, UNCTAD, ITC).

Output Title	Improved Regulatory Practice
Output number per LF		4	Output Score	B
Risk:		Major	Impact weighting (%):	None in current logical framework
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of Regulations simplified and consolidated	Target is 30 by March 2023	Interventions contributing to the indicators: / There is currently one intervention in the SIP that will contribute to this indicator - Brazil Regs. / How the intervention(s) will contribute to the indicator: / The Brazil Regs Business Case articulates that 100 regulations will be simplified, or consolidated where necessary and obsolete regulations may be removed. / What has the intervention(s) done over the last 12 months? (activities/results): / Brazil Regs was one of the initial pilot projects for the GTP and has been on hold since early February 2020 pending Ministerial approval to issue ITT.

Indicator(s)	Milestones	Progress
Number of individuals reporting better knowledge and understanding of Regulations as a result of GTP activities	Target is 671 by March 2023	Interventions contributing to the indicators: / There are currently six interventions in the SIP that will contribute to this indicator. These are Brazil Regs, Vietnam NTR, Indonesia Digital Health, Mexico Regs, Indonesia Bundle, and Trade Forward Southern Africa (TFSA). / How the intervention(s) will contribute to the indicator: / Brazil Regs was one of the initial pilot projects for the GTP and has been on hold since early February 2020 pending Ministerial approval to issue ITT. Vietnam NTR is currently in the procurement phase. Indonesia Digital Health and Indonesia Bundle are currently at OPPD (Business Case) stage. TFSA has completed inception and is now in delivery. TFSA has developed an Info Hub that will serve a central gateway for business in Southern Africa to access details about process and regulations relating to trade with foreign countries, particularly those pertaining to the UK-SACU+M Economic Partnership Agreement (EPA). / Targeted EPA related training to the private sector is currently being designed so that traders are familiar with the new policies and regulatory requirements effective as a result of the UK leaving the EU. / Mexico Regs is at OPPD stage but is now being taken forward by the World Bank. All of the interventions have Regulations specific training sessions outlined in their respective Business Cases. / What has the intervention(s) done over the last 12 months? (activities/results): / In Brazil, Vietnam, Indonesia and Mexico, extensive and sustained research and analysis and stakeholder engagement has been undertaken to progress the interventions through the various stages of the programme lifecycle (Country Plan, NPC, Business Case). This has involved 127 meetings with Government and 61 meetings with private sector organisations including local businesses and UK businesses operating in-country. Another success has been engagement with trade organisations representing over 1,500 UK businesses in Vietnam, Mexico, Indonesia, Turkey and Nigeria.

Indicator(s)	Milestones	Progress
Number of improvements in trade related laws, regulations and policies	Target is 5 by March 2023	Interventions contributing to the indicators / There are currently three interventions in the SIP that will contribute to this indictor. These are Brazil IP, Indonesia Bundle and Indonesia Digital Health. / How the intervention(s) will contribute to the indicator / Brazil IP is currently in the inception phase and contains four elements that will improve policy (Process Design, Pricing Policy, IT and HR). Indonesia Bundle is currently at OPPD stage, and the intervention has been designed to include two improvements to environmental management mechanisms. These are (1) An interregional Marine Spatial Plan in Indonesian territorial waters and (2) Improvements to the MSP and M&E Framework. Indonesia Digital health is also at OPPD stage and involves two improvements to the regulatory framework for regulating digital health services. Specifically, these are e-pharmacy and telemedicine. / What has the intervention(s) done over the last 12 months? (activities/results) / Brazil IP was one of the GTP's initial pilot projects and although still in the inception phase, one of the early successes of this intervention has been the signing of an MoU between the UK and Brazilian governments in relation to the work to support the Brazil Government to modernise their Intellectual Property Office. This led to high profile media coverage with both governments verbalising their expectation of increased investment in Brazil and an increased opportunity for UK business as a result of the intervention. Indonesia bundle and Indonesia Digital Health were developed through extensive research and analysis and in country stakeholder engagement. A Country Plan for Indonesia was produced during the six-month inception phase to set up the GTP. This included detailed economic and political analysis of the situation in Indonesia and existing barriers to trade with a prioritised long-list of potential interventions. An additional prioritisation exercise that involved sustained significant in-country stakeholder engagement was then undertaken to reach a prioritised short-list, after which these interventions were progressed through to NPC stage and ultimately Business Cases were developed for these interventions. There are Research projects for Indonesia MSP and Indonesia Digital Health currently in Delivery as per the Additional Commentary on Research section (below).

Key Points
No annual milestones, difficult to ascertain how activities under this output are contributing to indicator and to the end stage targets, and to higher outcome and impact statements of the global ToC. Regulatory reform is a complex process, with ingrained political economy challenges in many target middle income countries, hampering progress and inclusive growth. Close and regular monitoring should take place to understand the potential impact of the proposed reforms planned by these projects, how policy makers perceive them and to identify opportunities to use the outcome from the projects to influence policy, legislation and regulations.
Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable, previous annual review addressed operational, governance and inception planning issues.
Recommendation
Produce a more detailed global logframe that includes baselines, annual milestones, impact weightings, end of year targets.

World Bank / World Customs Organisation Component:
Output Title	Technical assistance and training to reform trade facilitation laws, procedures, processes, systems, and consultative mechanisms within the context of the WTO TFA is provided to selected MIC countries
Output number per LF		Referenced 1.1.1 in the World Bank/WCO separate logical framework	Output Score	C
Risk:		Moderate/Major	Impact weighting (%):	No output weighting in World Bank Results Framework
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1.1.1 Number of WTO TFA measures supported in TFMIC countries (#) / 1.1.1.2 Number of new / laws/regulations/amendments/codes /government policies drafted, or contributed to the drafting (#) / 1.1.1.3 Number of procedures/firm-level policies/practices/standards recommended for improvement or elimination (#) / 1.1.1.4 Number of countries supported in the area of organizational development (Leadership Management Development, Human Resource Management, Stakeholder collaboration, Integrity, gender equality and diversity etc.) (#) / 1.1.1.5 The ratio of increase in the number of enrolled users, and number of users who have completed, the WCO e-learning training on Gender Equality in Customs from beneficiary countries before the program, and after the program has ended (%) / 1.1.1.6 Number of baseline TRS completed (#) / 1.1.1.7 Number of end-project TRS completed (#) / 1.1.1.8 Number of WTO TFA gaps analysis reports completed (#) / 1.1.1.9 Number of in-country gender surveys completed, and reports drafted with recommendations to improve gender parity in trade (#) / 1.1.1.10 Number of country-level events delivered and/or facilitated by TFMIC (#) / 1.1.1.11 Number of completed in-country validation scoring sheets, in accordance with the WTO TFA tracking tool methodology (#) / 1.1.1.12 Number of WBG Working Papers focusing on assessing and improving the impact of trade facilitation interventions (#)	TBD after data is collected during diagnostic phase / 1.1.4-1.1.7 Initial target is 5 (Brazil, India, Nigeria, Philippines, South Africa) during diagnostic phase; pending any additional MIC countries to be considered	The programme is too early in the planning/pre-implementation stage. However the following activities have taken place in the last 12 months, which despite Covid19 should provide a basis for resurgence of activities to deliver against the WB/WCO TF programme objectives: / Brazil / World Bank delivered: WCO delivered: / - AEO conference in Sao Paulo resulted in joint statement by 10 Heads of Customs to continue AEO collaboration. / - Mission to Brasilia in February 2020 successfully achieved high-level government buy-in for the project. / - Preparatory work and desk research on existing laws, policies, and procedures for the TFA Gap Assessment. / - TRS work moving forward as planned. / - Virtual meetings and preparatory work related to the trade and gender study undertaken. - Mission to Brasilia in February 2020 successfully achieved high-level government buy-in for the project and identified needs going forward. / - Virtual meetings and preparatory work related to the gender equality and diversity organizational assessment undertaken. / India / World Bank delivered: WCO delivered: / - Analysed potential synergies and benefits from similar programmes by the WCO and FCO. / - Planned a mission for March 2020 to begin project activities, which was postponed due to COVID-19. / - Discussed potential support around risk management and post-clearance audit to Central Board of Indirect Taxes and Customs (CBIC), advance rulings, pre-arrival processing, separation of release from clearance and potential support to other border agencies. - Exchanged with the CBIC on different areas on Customs’ internal organizational development where the administration may need support. / - Analysed potential synergies and benefits from similar programmes by the WBG and FCO. / - Planned a mission for March 2020 to begin project activities, which was postponed due to COVID19. / Nigeria / World Bank delivered: WCO delivered: / - Establishment of strong relationships with the partner country, other donors, and relevant stakeholders. / - Coordination with other donors working on trade facilitation in the country to avoid duplication of work. / - Prioritization of areas for support. / - Support in reviewing the Trade Facilitation Roadmap. - Received strong commitment from the NCS. / - Coordination with other donors working on trade facilitation in the country to avoid duplication of work. / The Philippines / World Bank delivered: WCO delivered: / - Discussions with the BOC in February and March 2020 to finalize the scope of work. / - Planned kick-off mission for April 2020, / which was put on hold due to the spread / of COVID-19. - Exchange with the BOC following the August 2019 Mercator Scoping mission on the scope of work. / - Planned Forward planning mission for April 2020, which was postponed due to COVID-19. / South Africa / World Bank delivered: WCO delivered: / - Maintained dialogue with Customs Administration to advance the analysis and design of the trade facilitation support programme. / - Identified potential areas for support, including conducting a TRS, assessing the NTFC, conducting a Gap Assessment, potential support for the development of a Single Window framework, potential support to develop a comprehensive border management cooperation strategy, support to expand the AEO programme. / - Planned scoping missions in January and March 2020 to further analyse needs, engage with the private sector, and secure high-level government buy-in. - Confirmed commitment from SARS following the June 2019 Mercator Scoping mission on the scope of work. / - Exchange with SARS and IMF to plan a review of South Africa’s Customs Legislation.

Output Title	Global knowledge, learning and measurement products and indicators are generated for MIC countries
Output number per LF		Referenced 2.1.1 in the World Bank/WCO separate logical framework	Output Score	C
Risk:		Moderate/Major	Impact weighting (%):	No output weighting in WB Results Framework
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1.1.1 Number of global and regional events delivered (e.g. peer-to-peer, learning events) (#) / 2.1.1.2 Percentage of female participants in events (%) / 2.1.1.3 Number of TFA alignment methodologies developed/ improved (#) / 2.1.1.4 Number of communications materials developed (e.g., videos, blogs, brochures, newsletters, etc.) (#) / 2.1.1.5 Enhancement of the time release study methodology (including considering of gender component) / 2.1.1.6 Flagship report/handbook on best practice of trade facilitation interventions		See comments in the output box above.

UK Trade Partnerships Programme Component:
(This component of the GTP programme led by FCDO’s Trade for Development Dept. has its own governance structure and reporting timelines. The last annual review took place in March 2020 and it was marked an A, see the full AR for this component pasted below).
Update September 2020: There are no major updates to add to the last AR of the EPA component. Similar to other ODA programmes, activities and delivery of outputs have been impacted by Covid19 restrictions. Some parts of the programme have innovatively transitioned to online delivery. The programme team is monitoring risks and adapting to the “new normal” of delivering ODA during Covid19.
Recommendation: As this component is funded by the Prosperity Fund Global Trade programme, its separate logical framework should feed into the global GTP logframe (to be developed), and clearly show alignment with the GTP’s global ToC.

Output Title	Validated consolidated report for component 1 – transitional support to EPA partner country governments
Output number:		1	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
UK-ACP EPA agreements implemented by partner countries	Country scoping missions and reports completed via TAF2+	Ongoing
	MOU signed with CARICOM Secretariat with accompanying workplan	Ongoing

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]
Transitioning from trading with the UK under the EU EPA agreement to trading under a new UK EPA agreement and managing the implementation of a new trade agreement places demands on the UK’s partner country governments. Component 1 of the UKTP programme is designed to support our partner country governments to meet those demands through the provision of technical assistance and other support to implement the agreements.
This component of the UKTP programme is closely linked with the entry into force of UK EPAs because it relates to support for the implementation of those agreements. If the agreements are not in force, there is nothing to implement. Our timelines for this work was therefore dependent on the UK’s departure from the EU which were influenced by the political context, including the UK general election and the UK’s negotiations with the EU.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
As mentioned above, negotiating and implementing a new trade agreement places significant additional burden on our partner country governments and regional secretariats even though the EPAs between the UK and ACP countries replicate the equivalent EU-ACP EPAs. Multi-country surveys have found that developing countries often lack trained and experienced trade policy analysts and negotiators, have weak institutions that fail to build collective memory; and are frequently unable to access and assimilate relevant external expertise, limiting their ability to address transition issues at short notice. Support for implementation of agreements will commence when agreements come into effect (or shortly beforehand), however, during this period desk-based assessments and scoping work will continue. A due diligence assessment will also be carried out for CARICOM Secretariat in preparation.
Describe any changes to this output, and any planned changes as a result of this review. [1 paragraph]
In light of a number of extensions to the timeline for concluding a withdrawal agreement with the EU, and then the conclusion of a withdrawal agreement which is in effect until December 2020, the activities under this component were postponed for most of the review period. Preparatory work still took place, including receiving an initial proposal from the CARICOM Secretariat of a workplan and budget and a TORs from TAF2+ for carrying out scoping for support in the non-CARICOM EPA partner countries have been agreed.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
It was agreed during this review period that the scoping work under TAF2+ would also cover the SACU+M region, at the request of the Global Trade Programme SACU+M programme manager. This was agreed by the TAF2+ team within the current envelope of TAF2+ funding. The scoping work has changed from in-country missions to remote interviews and desk based research to adapt to covid-19 restrictions on travel.

Output Title	Memorandum of Understanding (MoU) between the Government of the United Kingdom and Northern Ireland acting through the Department for International Development (“DFID”) and the International Trade Centre (“The Partner”)
Output number per LF		2	Output Score	A
Impact weighting (%):		25	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Business case agreed	Submission and approval of Business case	Completed and Published
Terms of Reference agreed	Approval of Terms of Reference	Completed
Partner has cooperated with the rules around disbursement of funds, ongoing audit and assistance, due diligence, communication and branding	Completion of due diligence / Release of payments of two prepayment amounts as per the MoU.	Completed

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]
A Memorandum of Understanding (“MoU”) was agreed between the Government of the United Kingdom and Northern Ireland acting through DFID and the International Trade Centre. The MoU sets out the terms of DFID’s grant to ITC and governs our arrangements for delivery of the UKTP programme. A sum of £17m of the total UKTP budget was allocated to ITC with disbursement tranches assigned to milestones. During the drawing up of the MoU between DFID and ITC, two prepayments were negotiated for the first year to enable ITC to carry out scoping missions and activities in countries and regions to help with design of the programme. The first tranche of funding of £1.55m was released upon signature of the MoU. The second tranche of £2.7m was released upon receipt of the draft of the inception report including the work plan.
Prior to the MoU agreement and in line with DFID governance rules and standard practice for DFID, an enhanced due diligence (EDD) assessment was carried out to confirm that ITC’s corporate policies and processes, audit, anti-fraud, safeguarding controls are in keeping with DFID’s normal rules and expectations. The EDD also focused on ITC’s governance structures, financial management, audit processes, risk management, procurement and the monitoring and managing of downstream partners. The EDD was completed in October 2019 concluding that (ITC), as an implementing partner, had the capacity and capability to deliver DFID trade-related programmes to promote increased trade and sustainability.
As part of the EDD process, a desk-based review and face to face meeting also took place when the DFID team visited ITC HQ in Geneva on 21st August 2019 to in particular, discuss how ITC manages risks, fraud, audit, safeguarding issues and programme governance and management. These discussions were open, honest and challenging with helpful contributions from subject specialists. The DFID Programme Manager posed specific questions to extract specific information and also to provide ITC with an opportunity to present further evidence.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
During the inception period, the EDD assessment reaffirmed that ITC have developed a set of metrics to track VFM along the 4 E dimensions (economy, efficiency, effectiveness, equity) of DFID’s framework in each country and over the duration of the programme. The ITC employs a range of approaches designed to achieve VFM. On Economy, ITC aims to reduce costs by sharing costs with/ seeking contributions in kind from partners. ITC aims to maximise efficiency and effectiveness through partnerships, technology and cost-sharing. ITC will continue its model of working with partners in this project. ITC’s established networks, presence in country and experience in delivering similar projects to UKTP programme also added to VFM in selecting ITC as an implementing partner.
Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]
The DFID Programme Manager recommended that ITC further strengthen its downstream partner mapping. DFID has asked ITC to consider gathering more assurance and due diligence on their downstream partners particularly around performance assessments and their tracking of payments to beneficiaries. Although no fiduciary risk is envisaged in these partnerships there could be reputational risks to DFID as a donor and ITC as an implementer. A CUBED assessment was carried out by ITC to assess partner organisations’ capability and capacity. The CUBED assessment approach was used to mitigate and avoid delays in selection of partners and procurements if needed. The methodology adopted was effective as it assessed organisations in a uniform and fair manner, the process was transparent and evidence based, the selection of an institution had to justified when presented for approval. The validation process provided the opportunity to approve or challenge any findings or present recommendations to further assess the results. ITC is presently considering extending mandatory training on safeguarding, including a zero-tolerance statement on bullying, harassment and sexual exploitation and abuse to non-staff including consultants, independent contractors and volunteers. Progress on this initiative will be reviewed during the implementation stage.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
ITC has strong overall governance and control arrangements, with good oversight as part of the UN system. ITC has the capacity to carry out the scope of UKTP work and ITC’s systems offer adequate protection to DFID’s resources and reputation. During the inception phase of the UK Trade Partnerships programme, we found ITC to be co-operative, flexible and open to changes in scope of activities and sectors to achieve greater value for money and impact.
- It has strong delivery systems, procedures and good staff capacity in these areas. Its processes and performance appear strong across the project cycle from project initiation to evaluation, as evidenced both by formal evaluations and audits and by feedback from another DFID departments funding ITC.
- No significant concerns over ITC’s financial viability, which are effectively underwritten by WTO and UNCTAD. Its ability to properly account for funds in an open and transparent manner is also strong and evidenced by both UN internal audits and external assessments including by the UK Audit Office.
- The MoU template requires the ITC approver of payments to view evidence of payments receipts, certificates etc. ITC’s approval levels are set to ensure payments are made with scrutiny. For higher payments the request is followed through the Grants Committee that require more detailed evidence and justification prior to approving disbursement of funds.
- ITC requires its consultants and individual contractors to abide by ITC’s policies addressing bullying, harassment, sexual exploitation, and abuse. This is also addressed in MOUs with grantees/implementing partners. ITC have agreed to take all appropriate measures to prevent sexual exploitation or abuse of vulnerable people.

Output Title	Validated consolidated inception report for components 2 and 3 as well as individual inception reports for pilot export promotion projects in 10 ACP EPA countries
Output number per LF		3	Output Score	A
Impact weighting (%):		30	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Field data collection and analysis missions completed	Scoping mission reports	Complete
Reports contain trade facilitation issues; sector/product choice; gender and environment mainstreaming; risk register; preliminary results framework and workplan.	Scoping mission reports and Final consolidated Inception report	Complete
Validation workshop with stakeholders	Final consolidated Inception report	Complete

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]
Since May 2019, research, field data collection and analysis missions were the focus of ITC’s activity. Their finalised consolidated inception report is in good shape covering theory of change, results, VFM and risks, as well as an overview of the trade intelligence component and a summary of each country project, including product/institution selection, strategy, governance and expected results. It is supported by eight detailed individual country reports as well as two reports with risks and recommendations on gender and environment mainstreaming in the Zimbabwe project.
Producing and reviewing many reports simultaneously has been a challenge for both ITC and DFID teams. ITC has accommodated DFID’s interest in its role extending beyond quality assurance to an advisory one. ITC teams have worked hard to revise the draft reports based on DFID’s comments.
There were weaknesses in the initial draft inception reports received from ITC. In particular there was a lack of clarity on the linkages between the evidence and analysis and ITC’s conclusions and recommendations. For example, there were some evidence gaps in relation to the sector selection in the ten pilot export promotion countries. Strengthening the justifications for decisions on sector selection has been a valuable process, allowing DFID/ITC to better understand challenges and needs in each target country. ITC presented evidence about the static and untapped demand for exports from a range of sectors per country. This led ITC to look at some more niche sectors in some countries, such as herbs and spices in Fiji and Penja pepper in Cameroon. There was also a lack in clarity on the link between the challenges identified and the interventions recommended to address those challenges. Through a process of detailed review and discussion of the draft inception reports ITC addressed the weaknesses in the reports, which, in turn, has strengthened our confidence in their proposals.
Since approving the final versions of the country reports, ITC have started to hold launch events and workshops in country, to raise awareness, determine target firms training needs and assist firms to increase capacity to export to the UK/EU markets. The most recent quarterly report (April-June 2020) demonstrates good progress towards annual milestones in nearly all outputs. The first launch workshop took place in Madagascar in January 2020 which was well attended and the most recent was held in Mauritius in September 2020. ITC has revised its budget for this FY after the significant cut in budget following the reprioritisation exercise, and workplans are being updated to reflect the slow down in activities in some countries..
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
VfM was not formally tracked by ITC or reported to DFID during the inception phase of the programme. There was no formal framework for the monitoring it, so it was not part of the regular reporting cycle between ITC and DFID. However, we note that the final consolidated inception report was delivered to the expected quality after a few iterations. The effort put into the process by both ITC and DFID teams was invaluable as the document will form a solid base for the implementation phase of the programme.
Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]
This output is now completed. However, through review and discussion of ITC’s inception reports we have identified some areas to monitor during the implementation phase of the programme. These are set out in the lessons learned and recommendations section below.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Areas to monitor in the year ahead include:
Sector selection
In Ghana, strong market growth is predicted for cocoa derivatives, however, it is clear that the project will need to complete an in-depth analysis of UK/EU market trends and requirements as a first activity of the implementation phase. This will be realized through consultation of multiple data sources available and meetings with the industry. This will include structured interviews with buyers in EU/UK as well as local processors of cocoa derivatives to address concerns of supply and volume of beans. ITC will undertake further analysis of UK/EU market trends to determine whether there is enough demand for the cocoa sector.
Interventions
Proposed interventions were refined over the course of the inception phase. In Zimbabwe, there were concerns around which business model would be best suited to supporting small-holder farmers given the challenge of contested land ownership. ITC undertook business engagement and narrowed this down to promising models, lead farms and lease models, plus an irrigation scheme model.
Political economy risks
- The ITC is also identifying which non-tariff barriers and enterprise-level challenges are outside the scope of UKTP but which still need to be monitored, such as corruption within the textiles supply chain in Madagascar. To mitigate against the non-tariff barriers and enterprise-level challenges ITC will ensure only those enterprises willing to innovate are selected to make the textiles and clothing sector more competitive
- Political economy risks were identified in Comoros and ITC will need to monitor the risk of exporting companies increasing their market dominance to the exclusion of cooperatives and other small players.
- In Ghana, ITC will also undertake further political economy analysis to identify whether there could be risks of resistance within the value chain for moving from the export of raw cocoa beans to the export of semi-processed products and identify potential benefits for these businesses.

VFM and results
- In Côte d'Ivoire, DFID has asked ITC to demonstrate the cost effectiveness of the proposed skills training activities and explore standardising training on complying with sanitary and phytosanitary certification.
- In the Caribbean region, further clarity is sought around a coherent export potential strategy to overcome the small-scale results predicted for the Eastern Caribbean islands.
- There remains a need in Fiji to look at the potential demand for regional exports within the Pacific region to justify the cost-effectiveness of the proposed interventions.
- In terms of expected results, in the Caribbean region, ITC modified job-creation targets to make them more ambitious over 10 years given that the services sector needs more time to mature.
- For Cameroon, DFID has also asked for ITC to re-assess the ambition of the job-creation results.

Output Title	An inception report on improving market information and systems in EPA countries
Output number per LF		4	Output Score	A
Impact weighting (%):		30	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Assessment of market information availability, mapping of web-portals and reporting systems in EPA countries	Spreadsheet mapping web-portals and their capability	Complete
Report containing project strategy including intervention logic	Final Consolidated Inception Report	Complete

Briefly describe the output and provide supporting narrative for the score. [max 1/2 page]

Component 2 of the UKTP programme seeks to build awareness and transparency of timely trade and market information and the EPAs to create an enabling environment for EPA country exporters. ITC produced a comprehensive inception report outlining their project strategy for this component. This followed an assessment of market information availability, mapping of web-portals and reporting systems in EPA countries. This component has four interrelated interventions: centralising trade data and information; communications and capacity building; trade alerts helpdesk services; and business environment surveys. ITC has set out the reasoning for this component noting the importance to small-medium sized enterprises (SMEs) of understanding the regulatory and business environment in the countries of origin and destination of exports and improving exporters' ability to report potential trade constraints.

ITC found that only 6 out of around 24 EPA countries (Bahamas, Jamaica, Fiji, Ghana, Mauritius and Zimbabwe) have a good coverage of trade-related data required to raise awareness on the use and benefit of the Economic Partnership Agreements (EPAs). They also found weakness in 9 out of 24 countries’ national capacities to collect or maintain the necessary data to build their capacity on data quality. Whilst in 10 other countries, activities to consolidate available information are needed. Given the granularity of this analysis and detailed intervention logic, ITC has scored an A.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
VfM was not formally tracked by ITC or reported to DFID during the inception phase of the programme. There was no formal framework for the monitoring it, so it was not part of the regular reporting cycle between ITC and DFID.
Describe any changes this output, and any planned changes as a result of this review. [1 paragraph]
This output is now completed as the inception report has been finalised and approved. Lessons learned and recommendations relating to this component of the programme are set in the section below.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
The UKTP inception period coincided with high activity on the development of other trade-related HMG digital initiatives in the run up to Brexit. We are grateful to ITC for its flexibility in adapting its initial proposals to accommodate changes made necessary to avoid duplication with other initiatives. Our key recommendation for the year ahead is to ensure there is regular collaboration between ITC and the relevant HMG digital teams.
DFID had some reservations about the effectiveness and sustainability of output 2 concerning setting up or strengthening country-specific mechanisms to monitor the business environment given the need for partner government buy-in and capacity for them to succeed. This online mechanism will allow companies to report non-tariff barriers (NTBs) in exporting goods to the UK/EU markets with designated national focal points in identified institutions tasked with processing queries. ITC provided additional evidence and case studies and we have agreed with ITC that the monitoring system will only be implemented if the partner country endorses it and integrates it in its trade facilitation strategy.
ITC also clarified that the aim of the monitoring system is to act as a ticketing system for businesses to raise their concerns and create public-private dialogue rather than to resolve NTBs directly. The constraints captured during the business surveys in 2021 will also feed into the monitoring system from 2022. Given that results measurement on output 2 (making the business environment more transparent) is difficult to capture, it will be valuable to see the feedback of exporters on whether their experiences with regulatory and procedural trade obstacles are successfully brought to the attention of policy makers.
The need for a regional approach in the Caribbean was clarified by ITC in the finalised inception report. Despite varying information gaps, the existence of regional initiatives and regulations will create synergies with national work plans and increase the overall sustainability of trade information. This will include regional organisations facilitating access to trade information in partnership with national organisations; capacity building of trainers on advanced market analysis and a lighter touch business surveys to make the best use of resources. To ensure skills sustainability at the national level, the basic market analysis training will still take place nationally.
A miscommunication about countries within scope for this component was realised and clarified with ITC quickly. DFID and ITC must take care to be clear on the agreed scope given the large number of target countries. It is potentially confusing to stakeholders that UKTP covers all EPA countries except the Southern African Customs Union and Mozambique,which is covered in a separate programme, and we will have to keep this under review [UPDATE: FCDO has now agreed that TAF2+ programme will scope the EPA implementation needs in SACU+M. This is now in process]. Regular face-to-face/teleconference meetings with ITC are valuable to flush out issues that might not come up in written correspondence. These lessons are important to remember as and when the scope of the programme changes in future with the potential accession of additional countries to the UK EPAs (e.g. Samoa, Solomon Islands, East African Community).
DFID and ITC had early discussions regarding the constraints on activities in non-ODA countries (e.g. Seychelles and some CARIFORUM countries) given that UKTP is ODA funded. Non-ODA eligible countries will still be able to take advantage of some aspects of the trade intelligence component. For example, ITC will be organising project activities at the regional level and enabling self-funded attendance by representatives of non-ODA eligible countries. However, some confusion about ODA rules amongst ITC’s country teams has demonstrated the importance of ensuring that guidance on the rules and restrictions on the use of ODA funds are filtering down from ITC’s central team to ITC’s country teams.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key cost drivers and performance
Financial spend in 2020/2021

Lifecycle Spend: actuals + forecast[13]
[13] Programme actuals have been included to August 2020 and current forecasts until the end of the programme. These figures include VAT where appropriate and exclude any unconfirmed changes from 2020 Spending Review negotiations.

The 2020/21 forecasted spend is projected to exceed the budgeted allocation by £0.5m for a total of £22.4m. A large portion of the budget during this review period was spent on project initiation and planning – in particular, the production of new project concepts and business cases.[14] These costs have driven much of 2020/21’s £0.5m overspend and created complaints from HMG that the service manager should not be charging for the production of new project concepts. Conversely, Covid 19 has reduced some aspects of 2020/21’s budgeted spend because the pandemic’s international travel restrictions and resultant delays have caused some costs to be delayed or avoided.
[14] These costs have not been quoted or broken out in the financial spend tables because they are in active dispute between HMG and the service manager.
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
Although there has been programme progress during the last year, the net position of the programme is behind schedule compared to the ambitions set out in the full business case and innascent planning at the previous annual review. The 2019 UK general election and the 2020 global Covid 19 pandemic are the main causes for the overall programme’s delays. Further business efficiency risks will continue to exist as future Covid 19 pandemic waves may hamper interventions on the ground. The 2020 UK ODA reprioritisation is the main cause of the scope of the programme’s scope being reduced or “paused” – 9 out of 21 GTP-led interventions have stopped development as a result of ODA spending adjustments.
The programme has requested budget increases in the 2020 Spending Review to recoup budget lost from the ODA reprioritisation – however the results have not been released before completion of this annual review. According to the programme’s current strategic implementation plan, 4 of the stopped projects must be restarted before January 2021 to be delivered by end-Q4 2022/2023, the current end date of the programme. As the approval to spend could only be approved in the next financial year with an increase in budget from the 2020 spending review, it is unlikely that they could be completed with the current approved lifecycle. Whilst another 3 of the projects could only be completed by end-Q2 2023/24 in any case. Therefore reinitiating these workstreams will have additional costs beyond the pre-ODA 2020 budget, because they will incur contractual extension costs.
Recommendations:
 (a)XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
(b)XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
(c) The programme must consider its complete financial performance against the ambitions promised in the full business case – and decide if it still makes financial sense to continue as currently planned. This assessment may affect future scheduling and scoping of programme activities. It must occur as soon as possible to ensure that public money is being used as efficiently as possible before any potential wastage occurs. This should be completed before 31/03/2021 so that the financial impacts are agreed before the start of the 2021/22 financial year.
(d)XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXVfM performance
The full business case outlined that the original £150m budget should target £100.0m of interventions – including £40.0m on non-tariff barriers to trade and a £60.0m flexible delivery budget. A total £50.0m would be spent on central management services, research and analysis, and access & enabling.
The 2020 ODA reprioritisation reduced the 2020/21 spend by £9.1m, with the majority coming from a £6.0m reduction in the 2020/21 trade facilitation intervention partnered with the World Bank and WCO. The alterations to the programme have had also reduced the planned total future spend. The expected lifecycle spend is currently £119.8m. This lifecycle budget is less than the figure in the full business case because it reflects 2020/21 ODA budgetary reductions and the subsequent lifecycle programmatic impact.
Economy (are we getting inputs at the right price?)
The programme has used new project documents and business cases to develop the case for planned interventions. These business cases sit under the programme’s overarching full business case that was signed off in 2019. The responsibility of producing individual business cases is delegated to the service manager and non-service manager workstreams. The assurance process for these business cases has been active – and the GTP economics team provide the main quality assurance feedback for service manager led documents. Where interventions exceed agreed guidelines, each intervention business case is assured and approved by departmental processes outside of the programme team. The service manager was selected after a competitive tendering process.
The ratio of central programme planning and spending costs to interventions costs has significantly deteriorated compared to the ratio approved in departmental investment decision. As things stand, without a fundamental restructuring of the programme, time extension, revisiting of the balance between the project components and renegotiation of the budget, there is a risk that every pound being spent on the central planning and non-multi-lateral intervention will buy 84% fewer outputs than originally intended in the full business case, at the point of programme closure. In the full business case, £100.0m of interventions were meant to be delivered with a central support cost[15] budget of £50.0m – a ratio of 1:0.5. This design was prior to the assignation of funds to multilateral organisations that have independent programme planning operations. As the Global Trade Programme has developed, £21.5m has been assigned to the World Bank/WCO to deliver the TFMICs programme and £18.8m has been assigned to DFID/ITC to deliver the UK Trade Partnerships programme. As a result, the central programme planning fund and the central costs budget was reduced to £38.1m[16]. The impact is that the £38.1m central costs are now only directly developing and delivering £41.4m of interventions.[17] Thus on a planning cost to intervention output ratio, the situation has worsened to 1:0.92. This highlights that the right quality outputs are no longer being relatively purchased at the ratio in the full business case. From a public money perspective, spending almost £1 to deliver £1 of intervention will not be economic.
[15] Global Trade Programme FBC v.14: “…Core services in scope - up to £10m for all management services” + “Research and Analysis Budget – up to £20m” + “The Access & Enabling Budget – up to £20m” => a total maximum budget of £50.0m for these activities. Importantly, the words “up to” included before each of these allocations suggests that there is no opportunity to transfer funds between these activity streams. I.e. unused reseach and analysis budget cannot be used to increase the access & enabling budget beyond £20.0m.
[16] According to the lifecycle financial plan above
[17] This analysis is likely to be a best case scenario – as it has assumed that all project spending in country is “intervention spending”. It is likely that the project spending in country includes planning costs. This would reduce the £41.4m estimate and increase the £38.1m estimate – worsening the programme’s value for money performance. However this cannot be confirmed until after completion of the financial audit.
The ratio of planning to intervention spending varies greatly within the portfolio. The evidence indicates that the central costs are relatively expensive compared to similar services charged by multi-laterals in the trade facilitation stream of the programme. The central funds total “cost to deliver” is 92% of its intervention fund. Comparatively, the World Bank/WCO’s projected £1.6m “cost to deliver” is only 7% of its total intervention fund.[18] Whilst it has been noted by some stakeholders that it is to be expected that a commercially sourced supplier would be more expensive than a multi-laterals – and the service manager’s remit includes tasks like financial management of the entire Global Trade Programme – a potential x13 relative cost indicates weak value for money for these services.[19]
[18] 7% calculation provided by GTP economics team as part of their internal value for money report.
[19] More accurate analysis is dependent on the internal audit results.
During the period under review, the percentage of small (<£1.0m) projects has increased from 42% to 54% in the service manager’s portfolio compared to the original plans during contracting. This reflects the Global Trade Programme’s shift in relative ambition to more small interventions – such as research projects instead of medium and large projects (>£1.0m). There are now only 14 medium and large programmes planned, compared to an initial envelope of 21. The cause of these changes are rooted in the effects of ODA reprioritisation and the programme’s development. Nonetheless, this indicates that some of the original impetus of the programme to pursue more medium and large projects has been lost. It is likely that fewer medium and large interventions might achieve smaller long run benefits because they might not achieve economies of scale.
Recommendations:
(e) The programme must consider the viability of the programme’s central costs considering their direct programme output has reduced. It must produce a report for the SRO outlining its recommendation and its argument either to continue or alter approach. The SRO must then provide direction on the programme. A timeline to address this recommendation needs to be agreed by 01/12/2020 and ensure that long term financial impacts are actioned before the start of the 2021/22 financial year.
Efficiency (how well are we converting inputs into outputs)
The efficiency performance of the programme is mixed – especially in the workstreams managed by the service manager. As the majority of the programme’s interventions are still in early development, this efficiency report focused on produced documents and outputs – e.g. processes used in the production of business cases and new project concepts. It is too early to assess theory of change outputs. The evidence suggests working relationships in Indonesia, Mexico, Nigeria and Brazil have been productive and indicate efficiency. However performance in Vietnam, Columbia and Turkey have been less efficient.
As part of the GTP Economics Team’s internal value for money report, evidence was collected to summarise the main causes of programme inefficiency. The first main area is the quality of relationships between supplier country offices and HMG. Notably, relationships are further complicated by co-ordination issues between suppliers’ international offices. A second area are the delay impacts of the Covid 19 pandemic on international trade priorities and programme schedules.
There is evidence that the programme has adapted to poor performance and taken corrective actions where required. As the programme moves into more programme implementation, the programme will have to adjust its performance analytics to assess its efficiency.
Recommendation:
(f) As processes mature and the work structure between HMG and the service manager becomes more consistent, the programme should document best practice in countries and create positive advice for new interventions. This can be sensitive to political economy limitations. A timetable and governance process to manage this should be agreed by 31/03/2021 so that best practice is actioned in the financial year 2021/22.
Effectiveness (how well are our outputs delivering the desired outcomes?)
Total benefits for the entire £150.0m budget in the full business case were not calculated. The full business case only calculated benefits against a portion: the non-tariff barrier spend. It allotted £40.0m intervention costs (£64.0m including planning and development costs) and estimated that this part of the programme alone would deliver £2,032.0m[20] primary benefits and £31.0m[21] secondary benefits[22] over the 10 year appraisal period[23].
[20] Real and discounted at 10% per year
[21] Real and discounted at 3.5% per year
[22] Only to UK GDP and did not calculate any secondary benefits to non-UK GDP
[23] 2018/19-2027/28
Evidence that the programme is performing in line with or better than business case benefits estimation
As the programme has developed, governance processes have been established to ensure that each of the programme’s interventions estimate high-level benefits outcomes. Separate logframes have been produced in each of the main programme streams (central, DFID/ITC) and indicators have been established to track performance. Where research projects have been undertaken, comments have indicated that they were of high quality and provided useful information that feedbacks into future intervention design and improves intervention targeting.
There are only two projects currently in delivery, so it is too early to see if results are achieving intended results – nor confirm if the interventions will have long-lasting impact.
Evidence/risks that benefits may not be as high as in business case estimation
There is little evidence that the programme considers net benefit impacts or long run net outcomes before making cross-programme decisions. The programme does not maintain a governance process to ensure that current programme-wide total benefits are reported against the values promised in the department’s original investment approval (the full business case). Therefore, it cannot guarantee that the total outcomes of the programme will be effective, because its ongoing net outcomes are not being actively considered in the aggregate.
Evidence indicates that key decisions have treated benefits as incidental to programming decisions. A key example is when the trade facilitation budget was reduced by £6.0m during the ODA reprioritisation process. No cost/benefit exercise was undertaken to ensure that the programme pursued optimal benefits. Due to the time pressures, the decision only referenced time scheduling and cost criteria. Whilst this is understandable in this case, it is symptomatic of other programme decisions that were not under similar extreme time pressures. Furthermore, this breaches the 2019 Annual Review’s recommendation to introduce a “prioritisation criteria”. Intervention selection and changes in scope do not use outcome impacts as a central criteria – which suggests that that the long run, the programme has not been assuring its position relative to the estimate £2,032.0m in the full business case. Moreover, in the specific example of reducing the trade facilitation budget, the programme’s existing evidence base in the business case highlights that it is the programme’s most evidenced and predicatable benefits generator, which suggests it should have been the last area to be cut. However in this decision, it was one of the first, and moreover, one of the largest proportionately.
The 2019 Annual Report’s recommendation to “review and refine the ToC” for opportunities to improve it as a programme tool has not been followed. It is still using the same version published in the 2018 full business case. And importantly, the 2019 recommendation to produce a central programme log frame has not been followed, so there is no tracking of all the streams in a single document. The review team has seen evidence that despite numerous and escalating requests by the core team to the Service Manager, this deliverable has never been produced. Instead, the programme maintains disparate logframes (e.g. the projects managed by the service manager, DFID) that do not mirror format or contents. Whilst the separate stream logframes are useful at a lower level, a central logframe would aid overarching programme monitoring and focus on both primary and secondary purposes. This would be especially useful if tracked with quantitative milestone and indicator achievements. Summary documents for the entire programme do not bring this information together into a singular repository to actively understand how all three streams in the Global Trade Programme are performing. It would provide an evidence base for future decisions.
Due to the Covid 19 pandemic, the programme has suffered delays during inception and delivery. Although teams have reacted flexibly to use new technology where available (e.g. video conferencing instead of international travel), there are still unavoidable long run impacts that threaten the ability of the programme to deliver goals within the programme’s intended lifecycle. For example, the DFID/ITC work stream is looking to extend its timeline by a year – with impacts to budgets and scheduled achievements.
The full business case estimated that £255.0m primary benefits and £3.0m secondary benefits attributable to the programme will have been delivered by the end of 2020/21. The programme does not report against these estimates so therefore it is not possible to verify progress. In part it might be because of approved scheduling delays meaning that fewer interventions are in delivery than originally planned. Nonetheless, the governance process and documentation to verify approval of any slippage in these benefits has not been produced. It is important for the programme to understand what benefits will be achieved by currently planned programmes and provide options for recovering or improving benefits performance. If the programme had completed the 2019 Annual Review’s recommendation to create a VfM framework, this issue is likely to have been reduced. However as the recommendation was not followed, it is likely to continue to be an issue.
Recommendation:
(g) The programme must run a benefits audit of all planned non-tariff barrier interventions. The results of the audit should be assessed relative to the target promised in the full business case. The programme must decide if its total forecasted benefits is satisfactory compared to its budget and the overarching ambitions that were agreed in the business case’s investment approval. A timetable to address this recommendation should be agreed by 01/12/2022 so that decisions can be made in time for the 2021/22 annual budget.
(h) The programme must include benefits impacts as an equal decision criteria to scheduling and cost. This must be ingrained in its governance processes to ensure that public funds are being spent effectively. It will also create another indicator for programme performance in 2021’s Annual Review. This governance process should be in place by 31/03/2021, so that decisions made during 2021/22 are made with the improved process.
(i) The programme should pursue 2019’s recommendation to “review and refine the ToC and results framework regularly (at least annually) as and when the context changes or new evidence emerges”. This should be completed before the next annual review.
(j) The programme should pursue 2019’s recommendation to build “…a VfM framework to accompany the RF…” and it should be applicable to all workstreams in the programme so that intra-programme interventions are being appraised fairly. This should be completed before the next annual review.
Equity (are benefits distributed in a way that supports inclusive growth)
Gender equality marker (programme level): 0.
Latest G&I scorecard (selected projects) completed as part of the Programme Evaluation, July 2020 - variable, overall rating 3. Although there are islands of good practice, overall, there is a high risk that the benefits of the programme are not equitably distributed.

While it includes some potential entry points, the design of the programme could be stronger on G&I. In particular, clear G&I objectives are not stated in the business case and the overall, programme level of ambition on G&I for GTP has not been stated, neither is there an overall, agreed programmatic approach on G&I, around which individual projects can cohere(some individual projects, e.g. UKTFP has developed an approach.
As the programme is now in full implementation, these design shortcomings need to be carefully managed. One key way to do this would be through a programme level logframe and Theory of Change, with G&I well integrated, and clearly identified causal pathways & assumptions articulated from a G&I perspective (according to PF G&I policy & guidance). The lack of programme logframe & TOC is therefore a significant risk from a G&I perspective. For example, the assumption is that trade will contribute to inclusive growth and poverty reduction by default, and that no specific targeting is required[24], could be challenged, and associated risks & mitigating actions identified and included in the programme risk matrix.
[24] Interviews with programme delivery partners, 18/9/20; interview with Programme Evaluation Lead 29/9/20
Despite this, there has been positive progress on G&I. For example, the Service Manager provided a full time G&I expert, as well as (from Sept 2019 to January 2020 only) a part-time G&I research specialist for support to the Research and Analysis Fund[25]; ITC and WCO draw on in-house gender experts[26]. Tailored GTP-specific G&I checklists and training materials have been developed by the SM G&I expert in co-ordination with the FCDO’s Social Development Adviser (SDA), which build on the WoW Helpdesk’s G&I and Trade thematic brief and Country plan G&I reviews. Although G&I research & analysis started late in the programme cycle, this is valuable & adds significantly to the knowledge & evidence base (e.g. Turkey, Vietnam, Indonesia G&I; Zimbabwe value chain (UKTP)[27]. GTP’s G&I approach has been shared by the G&I specialist with HMG PF G&I Champions, and good practice BCs shared for wider learning[28]. A regular G&I catch up for HMG and SM G&I experts is convenved, which is good practice[29], and should be extended to include other specialists across the programme. The strong outputs of the SM G&I expert were recognised in the 2020 GTP evaluation report[30].
[25] Interview with Service Manager, 16/9/20
[26] Interview ITC 18/9/20; Interview with WCO 22/9/20
[27] Gender sensitive value chains in horticulture: A case study from Zimbabwe (ITC, nd)
[28] Interview with G&I Policy Lead, 14/9/20
[29] Interview with FCDO economist & G&I Champion, 15/9/20
[30] Global Trade Programme Evaluation Report, Cycle 1 (July 2020)
In terms of individual projects, the Evaluation Report found variable performance on G&I across sampled projects (see scorecard above). We understand that the G&I scorecard assessment was based on programmes at an early stage and are therefore based on plans & intentions & would require verifying now that they are in delivery[31]. Supporting greater participation of women and other excluded groups is a key priority for the Trade Forward Southern Africa programme in particular, with key measures taken for better integration. It would be good to examine the extent to which needs analysis continues to inform this initiative, and to ensure that it is linked with, and draws on learning and best practie emerging from other women & trade initiatives. Both Brazil and Vietnam score low on progress to integrate G&I across the programme (as per G&I Scorecard above, 2 rating i.e. insufficient evidence of alignment with the PF G&I Policy and Guidance), and it is therefore recommended that the team and SM ensure focused GTP G&I policy lead inputs to ensure full GEA compliance and that minimum standards are met.
[31] Interview with Programme Evaluation Lead 29/9/20
Overall progress is therefore mixed, and the GTP programme-level G&I action plan (which usually follows completion of G&I country-level analysis and impact assessments) has not yet been developed. At the same time, there is a belief that G&I is only critical at design & procurement stage – in fact it should be a priority throughout the programme cycle[32]. One project (Vietnam) went to procurement before the G&I research could be completed, the tender documents were missing a G&I perspective and did not follow PF and GTP G&I procurement guidance[33]. ODA reprioritisation has led to significant cuts to G&I expertise and an ad hoc approach[34]. The evaluation report concluded that the senior management is strongly committed to gender and inclusion, and that progress is being made. Our understanding is that this refers to HMG senior management, on the basis of emphasis given to G&I in meetings & e.g. in Annual Review comments, which is encouraging[35]. However, based on actual activity, progress and resourcing levels, we conclude that this commitment does not translate into systematic and consistent focus on G&I[36]. The risk that current G&I analysis is too late, and the GTP constitutes a portfolio of weakly aligned projects on G&I, is now very likely to be realised.
[32] Interview with FCDO GTP Programme Staff, 8/9/20
[33] Interview with FCDO Global Programmes SDA, 14/9/20
[34] Interview with G&I Policy Lead, 14/9/20; follow up communication with FCDO Global Programmes SDA
[35] Interview with Programme Evaluation Lead 29/9/20
[36] Interview with FCDO GTP Programme Staff, 8/9/20; interviews with delivery partners (varous); Interview with G&I Policy Lead, 14/9/20; Interview with FCDO Global Programmes SDA, 14/9/20; analysis of key documents
Gender and Inclusion Champions: whilst the programme benefits greatly from the support of Gender and Inclusion Champions, the champion role does not substitute for G &I specialists, neither can champions be expected to apply a full time role to G&I needs. The Gender and Inclusion specialists have so far had a strong working expertise in international development and this must be the requisite blueprint for future inputs from Gender and Inclusion specialists.
Recommendations:
(k) to ensure compliance with the International Development Act (IDA) and align with PF G&I policy, develop a G&I action plan (to include clear objectives, level of ambition, deliverables and appropriate resourcing to achieve them for the whole GTP programme, as per AR 2019 recommendation). The G&I action plan should be agreed by the GTP Operational Board by 1/1/21.
As part of the recommended management and capability review, attention needs to be given to appropriate level of G&I resource to deliver this G&I action plan, within HMG, as well as within all primary and secondary delivery partners. GTP G&I policy lead support is particularly required for projects that have scored low on the G&I scorecard, Brazil and Vietnam.
A coherent cross-programme approach to building the evidence base on the contribution of trade to poverty reduction, gender equality and women’s economic empowerment should be agreed as part of the logframe rewview; this should include maximising synergies with other HMG efforts (e.g. RED’s Growth Research Team) and Multilaterals (e.g WB Umbrella Funds on Gender and Trade).

Assessment of whether the programme continues to represent value for money
As things stand, the programme does not satisfy core value for money tenets, and urgent management attention is require in order to get the GTP on track. From a cost perspective, the ratio of central planning costs to intervention costs has worsened during the period under review – and does not meet the ratio intended in the original full business case. The services exchanged for public money do not appear economic –There are indicators that parts of the programme have been efficient, however performance varies widely from country-to-country and intervention-to-intervention. Whilst on the benefits side, delays and reductions in the programme’s breadth of ambitions make it questionable if it will meet its effectiveness obligations. Moreover, the programme’s decision-making governance processes has treated core quantitative benefits objectives as incidental, focusing entirely on cost and scheduling efficiencies only. So it is uncertain that the programme should have chosen more effective decision retrospectively. And more importantly, it is unlikely that it could ensure select effective decisions in the future.
Quality of financial management
The financial management of the Global Trade Programme has been delegated by HMG to a service manager via contract. The responsibilities of the service manager are broad – authorising the service manager to act on behalf of HMG and demands that the service manager supports financial management of all Global Trade Programme expenditure[37]. The service manager has substantive experience performing these roles in both public and private international organisations.
[37] Contract clause 2.7 (a): “act as first point of contact on all Financial Management for the GTP on behalf of the Authority”. Contract clause 2.7 (b): “support the authority in planning, managing and executing best practice financial management in respect of all expenditure for the GTP.”
The service manager has been contracted to collate and report against all spend in the programme – including the c.£21.5m trade facilitation programme (World Bank & WCO) and the c.£18.8m UK Trade Partnerships Programme (DFID). Furthermore, the service manager has been given specific authority to manage spend for delegated sub-contractor partners and delivery partners as part of the flexible funds for interventions and central programme functions[38]. The service manager’s position creates a responsibility to HMG to advise and pursue value for money and cost-effectiveness, as recommended by guidelines on spending public money.
[38] Including Research and Analysis, Access and Enabling and, Management Costs
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
During 2019/20-2020/21, there have been three external events that have incurred financial impact. Firstly, 2020 UK General Election, secondly the immediate economic impacts of the global Covid-19 pandemic, and thirdly the 2020/21 ODA reprioritisation process. It has been noted that the service manager has been co-operative when responding to the resultant financial challenges. This includes finding significant savings from their operational budget as part of the ODA exercise.

Date of last narrative financial report
Date of last audited annual statement

## E: RISK (1 page)

Overall risk rating: Major/Severe
Overview of programme risk
The GTP risk register currently contains 55 open programme risks, with severities ranging from 0 to 23. The most frequent severity is 16. Approximately 87 risks have been closed since the start of the programme. The Service Manager regularly adds, shares, seeks updates and reviews risks as part of ‘business as usual’ activity and there is a review on a monthly basis by the FCO programme team at the Monthly Programme Delivery Meeting. It is then passed to the SRO before being submitted to JFU as required. The risk register is in line with JFU guidelines for the management of programme risk, including pre and post mitigation RAYG ratings, detailed mitigation details, proximity, impact, etc.
Project risks and issues are managed by the Service Manager country lead and the appropriate FCO Programme Manager for each project. Both Project and Programme risks are reported on the GTP Portal (Programme management information system). As required these project risks are escalated to programme risks via reports and dashboards to the monthly Programme Delivery meeting and Operations Committee. The risks are reviewed and discussed and mitigations agreed.
Although the risk register appears thorough, the records indicate that the majority of the risks have not been updated in the last three months. Only 9 risks have been updated since July 2020 – and of that, 4 of the updates were to close the risks. One possible reason for the lack of progress on the risks are that many are still assigned to people no longer part of the programme. This indicates that the risks are currently “unowned” officially. It is uncertain if the current owners are aware of their responsibility, this leads to their lack of progress.
Importantly, the risk register includes entries focused on the relationship between the service manager and the team (TRA24), and that benefits will not be achieved (TRA86). This suggests that the programme was aware of these issues before this annual report. However, there was a lack of successful action to minimise the impact. As an additional note, not all the risks are well written – a number describe issues and not risks (TRA64, TRA114, TRA115). These should be rewritten as actual risks, or moved to an issues log. The current key programme level risks are:
a) Reputational/Financial – The programme has recognised that interventions may not achieve adequate levels of benefits or returns (e.g. TRA86). This is correct – however there are no mitigations described and no indication that the programme actively looks to manage this risk.
b) Operational – The programme has recognised the complexities associated with delivery, including stakeholder risks and timetable risks.
The risks highlighted above of a) lack of whole programme logframe and b) inconsistent approach to G&I (and appropriate mitigation) should be included in the risk register.
## F: COMMERCIAL CONSIDERATIONS (1 page)

The twin issues of COVID-19 and the ODA review have had a significant impact on the timeframes of the GTP from an intervention perspective. With the onset of quarantine in March, an assessment was made on the risks to the planned interventions. Brazil IPO and TFSA were preparing to enter delivery; a decision was made to prioritise activity on five further interventions whose progression to market and delivery would be least affected. Despite this, delivery has been delayed by as much as a quarter in some cases. With the need to find cuts due to the reduction in the ODA allocation, all other interventions were put on indefinite hold, and all additional activity/spend for the TFA and EPA programmes was placed on hold until FY 21/22. The Brazil Regulations intervention remains ready to progress but requires ministerial approval. The question of completion of the paused activity before the hard programme deadline of March 2023 is being closely monitored: each intervention currently on hold would have a cut-off point after which it would be no longer viable to procure.
On the SM contract, three inception milestones were moved into the operations phase to allow intervention delivery to commence, and some inception payments have been held back to incentivise delivery/performance.
Performance of partnership(s)
The GTP runs a two tier system of partnership, initially with the Service Manager, and then with the delivery partners for the interventions. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
SM directly manages the partnerships with the delivery partners. Of the two current interventions, both are currently proceeding according to the approved timelines, and are delivering their contracted outputs.
SM also manages procurement and contract management for the research element of the GTP. To date, whilst a significant portion of FY 20/21 research, totalling £849,950, had to be cut as a consequence of the ODA review, all remaining research projects are proceeding according to schedule and to the satisfaction of the GTP Economics team. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
In addition, SM manages a contract with DAI, to provide policy leads (G&I, regulation, standards, other). XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Changes in the Delivery Plan
As outlined above, eight GTP interventions have been placed on indefinite hold due to the ODA reduction, leaving at least £12 million of potential activity pending. The remaining interventions are in delivery, or being accelerated through procurement. Beyond stakeholder maintenance, work on the WCO, WTO, and DFID interventions has been deferred to next year.
There have been changes to the Service Manager relations following the ODA and the contract review. SM has changed their GTP delivery leadership and reduced their floating team for the GTP, and will no longer readily call on Drawn Down resources outside the approved core team.
Asset monitoring and control
The GTP has recently approved the final inception payment for delivery of the GTP portal, which is a Management Information System used as a repository of programme data and project management information. Robust data protection measures and information management procedures, as well as information security procedures, are in place. Due to the potentially commercially sensitive information stored on the system, dual factor authentication is required for log-in, access can only be achieved through approved channels, and where suppliers need to access, and the organisation must be formally approved by FCO IT. The Portal is siloed, with the various management sites only available to those with approved access.

G: Business Environment (½ page)

How has the business community and business environment responded to the programme?
The GTP has undertaken comprehensive engagement with the business community and associated stakeholders as part of the development of the long and then short-list of potential interventions that then were prioritised into the Strategic Implementation Plan (SIP).
127 meetings with Government and 61 meetings with private sector organisations including local businesses and UK businesses operating in-country took place. This included engagement with trade organisations representing over 1,500 UK businesses in Vietnam, Mexico, Indonesia, Turkey and Nigeria in support of the secondary benefits impact of the programme.
The individuals and groups engaged have been positive towards the GTP and keen to work collaboratively to validate and shape project design where appropriate. The discussions to-date have helped to form a better understanding of the barriers to trade faced. In some instances, potential solutions to consider have also been offered to the programme from these key stakeholders.
The supplier market is also engaged to deliver GTP projects as designed. The contracted Service Manager is responsible for the procurement of a delivery partner to deliver projects in the host country. The usual route to do this is to run a competition via the Prosperity Fund Framework, which was let by, and is managed by FCO Commercial as Framework owner. The Service Manager has successfully engaged the market through events and the provision of regular market updates. There has been strong interest in the GTP programme with all suppliers on the trade lot attending a supplier day, and attendance at market engagement calls in relation to specific projects. In addition to the Framework suppliers, FCO commercial hold a list of over 500 suppliers who have expressed an interest in the programme and are updated as to the development of the GTP as they may wish to deliver part of a project as a subcontractor to a Framework supplier.
The other components of the GTP have also engaged with businesses, business association and regulators. The World Bank and WCO have held a number of consultations and engagements in Brazil, India, Nigeria, Philippines and South Africa. The UKTP component delivered by the ITC has extensively engaged and is in the process of actively partnering with SMEs and relevant associations to support their participation in international trade, and to take advantage of UK trade preferences that will be established following our transition from the EU.
(Where relevant) What role has non-oda spending played in promoting programme objectives?
N/A

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
Evaluation
An evaluation of the GTP was completed in July 2020[39]. The evaluation sampled a limited number of interventions: Brazil IP, Indonesia MSP, TFSA, Vietnam NTR and World Bank TFP. The evaluation offers a series of in-depth findings & lessons learned, focused on progress to date & design; governance and management; connections, complementarities and coherence; learning, a number of which are referenced in this review. The programme response to evaluation recommendations is not yet clear. The next evaluation round (cycle 2) is planned for 2021.
[39] Global Trade Programme Evaluation Report Cycle 1 (2020
One key finding is on M&E: ‘The service manager developed their own GTP M&E framework, not initially aligned to government standard log frame formats and Prospero, necessitating additional work to retrofit and align the GTP M&E framework. The global level programme log frame is not yet finalised. The process to develop the log frame has taken a long time, with insufficient consultation and uptake of comments and recommendations to improve the process and output, which significantly delayed the process until recently. The service manager also attempted to strictly align the indicators to the ToC which made the exercise more challenging. It is important for the programme’s MREL framework to collect data, such as indicators disaggregated by sex and age, to address the weaknesses stemming from the limited evidence on the relationship between reducing barriers to trade and distributional effects.’[40]
[40] Global Trade Programme Evaluation Report Cycle 1 (2020) (p52)
Programme logframe & Theory of Change
The development of a programme lograme was also a recommendation of the 2019 Annual Review. ‘The GTP team should fast track the GTP Theory of Change (ToC) and results framework development to help inform project-level ToCs and results frameworks and ensure these align to the overall GTP and Prosperity Fund ToC and GTP results framework.’[41] However, as mentioned in earlier sections, the programme does not have an overall Logframe incorporating SM, UKTP, and World Bank/WCO projects.
[41] Global Trade Programme Annual Review 2019
The narrower SM logframe has been updated (18 August 2020 [version v1.5]) but appears unfinished, e.g. lacking milestones, baselines, impact weightings. Improvements to the log frame could now include C19 effects and how programmes made pivot indicators to address these given that women and marginalised groups are likely to have been impacted most. The UK Trade Partnerships Programme will require updating following recent separate annual review (March 2020). The World Bank / WCO results framework is incomplete, requiring baselines, annual milestones, end of programme targets, and impact weightings.
 the GTP programme log frame should align with JFU MREL and G&I guidance. In particular, it should integrate more specific indicators reflecting data disaggregation for gender and marginalised groups including age, ethnicity, geographical area (urban, peri-urban, rural) income percentile. As mentioned in the Business Case, the programme logframe should align where possible with the WBG Trade and Competitiveness Gender Results Framework
An overall Programme Theory of Change exists in the Business Case, but has not been updated since 2018. Improvement is needed on casual pathways and distributional impact.
It should also be noted that MREL oversight is undertaken by an MREL committee comprising programme team, delivery partners and MREL contractors.
The Global Trade Programme via the Service Manager has commissioned and funded a number of research reports during the period under review, with the primary aim of supporting programme design and delivery:
•	Turkey new presidential analysis
•	Nigeria business linkages
•	Nigeria tracer study
•	Nigeria trade facilitation
•	Poverty, Gender & inclusion analysis and impact assessments for Vietnam, Turkey and Indonesia (drafts)
•	Indonesia MSP (draft)
The following research projects have moved into delivery in the period but are not yet complete:
•	ASEAN digital trade connectivity (27/11/20 completion)
•	Indonesia digital health (06/11/20 completion)
•	Turkey Authorised Economic Operator (AEO) (30/10/20 completion)
•	Vietnam National Trade Repository (NTR) (30/10/20 completion)[
The research & analysis part of the programme is well managed with good oversight processes: the GTP Analytical Group meets on a monthly basis in order to monitor progress of Research & Analysis. The group is in the process of setting up a system for tracking research influence. While they do contribute to the evidence base on the links between addressing NTBs and inclusive growth, there is scope for further focus on global public goods in relation to research and analysis focus on gender equality and women’s economic empowerment e.g. in relation to what works for response to Covid 19, for example through the World Bank multi donor Umbrella Fund on Gender Equality.
Monitoring progress throughout the review period
As mentioned in the evaluation, there were issues with the service manager developing their own M&E framework, not aligned to government standard log frame formats and Prospero.
The Annual review was desk-based including documents/correspondence assessments, video calls with key stakeholders including HMG team, service manager, secondary delivery partners (e.g. DAI, World Bank, WCO, International Trade Centre), previous independent evaluators (consortium made of TetraTech, LTS, Integrity), and partner country reps (Brazil & SA).