Brazil Prosperity Fund Programme

“UK-Brazil Prosperity Partnership – Poverty Reduction and Productivity Gains”
2018 – 2023

Annual Review Report 2020

# Summary Sheet[1]
[1] Please refer to Annex I for the List of Acronyms

Title: Brazil Bilateral Prosperity Fund Programme / “UK-Brazil Prosperity Partnership – Poverty Reduction and Productivity Gains” / Period of Review: September 2019 to October 2020
Programme Value: £56.45 million		Review Date: 3-16 November 2020
Programme Code: N/A	Start Date: Aug 2018	End Date: March 2023

## Overall assessment

Year	2019	2020	2021	2022	2023
Programme Score	B	A-
Risk Rating	Moderate	Moderate

## Strand-by-strand assessment

Strand	Primary benefit	Secondary benefit
Energy	A-	A-
Future Cities	B	A-
Green Finance	A	A
Trade	A	A+

## Progress/lessons since last review

Recommendations made by the AR 2019 and the RR 2020 are being tracked for implementation and a Continous Improvement Plan has been created. 86% of the recommendations accepted from AR 2019 have been completed, with remainder due to be done by December. 31% of the recommendations accepted from RR 2020 have been completed, 36% are in progress, and 33% have not started but are due to be completed by March 2021.

## Top 9 recommendations this year

	Recommendation	Paragraphs	Lead
1	Set target to meet G&I minimum standards by mid-2021	16, 66-67	SRO
2	Use any ODA reductions exercise to make strategic tweaks	18, 62	SRO
3	Reduce excess admin (Board frequency, number of indicators)	19, 95	PT
4	Improve Future Cities relationships between key actors	22, 33-35	PT, WB
5	Keep Paris-compliance of Energy strand under review	20, 27	PT
6	Fill expertise gaps on G&I, MREL, comms and climate	21, 66	PT
7	Develop clearer narrative to communicate the programme	19	PT
8	Prepare for post-PF period (evidence, x-ODA coherence)	22	SRO
9	Review VfM of altered activities at end of Year 1 of implementation	64	PT

## SRO Commentary

I would like to thank the Annual Review Team for this thorough and balanced review. The review reflects the significant progress the Brazil Prosperity Fund programme has made over the past year, moving decisively from inception to full implementation. This has taken place in the extraordinarily challenging circumstances of the COVID pandemic, which has impacted the working lives of everyone involved. It has also required agile adaptations, including to events and stakeholder engagement. Especially in consideration of this context, I welcome the Annual Review's programme score, which has progressed from B to A-, together with a Primary Benefit Assessment of A- and a Secondary Benefit Assessment of A. I am particularly pleased with progress on Secondary Benefits, on which the Brazil programme is recognised as something of a front runner, with tangible commercial results building on the soft power gains.

I support the recommendations of the Annual Review and will work with the Programme Board and Team to monitor implementation over the coming months. In times of scarce resources, I am keen to increase coherence of all HMG ODA programmes in Brazil behind a compelling central narrative. These recommendations will help us to ensure the Brazil Prosperity Fund is fit for purpose to meet the new challenges that lie ahead, helping Brazil to build back better, as we work in partnership for mutual prosperity.

## JFU Commentary

This Annual Review takes place as all programme strands make the transition from inception to implementation. The Review reflects a programme in much better organisational and management shape than it was a year ago. It is encouraging to see in particular, the clear progress that has been made on integrating a stronger gender and inclusion emphasis into the sector strands, backed up by the provision of specialist expertise.

There remain steps to be taken to improve the articulation of the change being aimed for across each sector to better reflect the impact the programme is having. It could be clearer where the major successes are being achieved and how performance across the sectors compares. As such, JFU agrees with the recommendation to assess and revise outputs and indicators across the programme, to aid comparability and to facilitate decision-making across the portfolio.

# A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/countries/BR/projects
DevTracker Link to Log frame:	To be uploaded

This £56 million programme is part of the UK’s Prosperity Fund. It aims to support Brazil’s economic openness and sustainable infrastructure, leading to increased productivity to facilitate increased income, sustainable jobs and poverty reduction. The secondary objective is to integrate use of innovative technologies by Brazilian firms and open new markets, leading to opportunities for UK and international businesses. It is divided into four different strands: Trade (£16m), Green Finance (£5m), Energy (£25m) and Future Cities (£10m).

Over the period of this review, the context has changed twice for the programme. First, the Brazilian government’s policies have changed or become clearer. There has been a greater push on liberal economic reforms (e.g. to align to OECD standards with the intention of acceding), and a drive to reform the energy sector. By contrast, the politics around issues of deforestation (and thus climate) have become more controversial, and less aligned to the UK approach (which now has an explicit aim of ensuring Paris-compliance of ODA, as part of the run-up to COP26 in 2021).

The second contextual change has been, of course, the COVID-19 pandemic. The IMF projects GDP could shrink 5.8% in 2020, and a respected Brazilian think-tank FGV predicts that 15 million people could slip back into poverty in January if the Brazilian Government does not introduce a new welfare programme to replace its current emergency cash transfer scheme due to end in December. Like other countries, Brazil has had to divert huge political and fiscal resources to containing the immediate economic & health impact. The pandemic has also forced the UK Government to refocus its international approach more on COVID-19, and (due to a fall in projected GDP) temporarily reduce its ODA funds worldwide in this calendar year.

Given the pandemic is ongoing, there is considerable uncertainty over planning assumptions. Additional uncertainty is caused by local elections in Brazil (at the time of writing), and by the implications of the US Presidential elections. We have written this Review on the basis of our best guess for the future – assuming, for example, that the pandemic will continue into at least mid-2021, and that ODA cuts in the UK will continue to bite. But we would underline that the SRO should consider the Review’s recommendations in the light of this uncertainty.

In writing this Review we are indebted to our predecessors who wrote the last Annual Review (in August 2019) and latest Readiness Review (in June 2020). We have taken on board their key recommendations to assess progress over this period, which were in summary:

  1. More consistency and lessons-learning between strands
  2. More specificity in Theories of Change, logframes, indicators, and contracts
  3. Better contract management capability in place
  4. Clearer mechanisms for delivery of VfM and secondary benefits, and more integration of gender & inclusion

We have also tried to focus on larger, strategic questions in this Review – noting that other internal processes are taking place in parallel to consider detailed issues of fiduciary compliance.

We are grateful to the programme team and delivery partners, who have been generous with their time in pulling together the documents we have used as evidence to support our judgements below. We are also grateful to the HMG and delivery partner stakeholders with whom we held interviews to supplement that evidence. And we thank those in HMG who have provided appropriate quality control.
# B. Executive Summary

We conclude that the programme has made significant progress since the last Annual Review. All four strands have been procured, with supplier teams in place. Three strands have moved through inception into full implementation, with agreed theories of change under an agreed overall programme-level theory of change. Most programmes have defined logframes and KPIs, and the rest are on track to finalise these by the end of the year. All theories of change and logframes reflect a greater understanding of the Brazilian context, alignment with Government poverty-reduction policies, and a better sense of the programme’s potential. They now include clearer assumptions, more gender-disaggregated indicators, and stronger detail.

All this bodes well for the programme as it moves into its delivery phase. In addition, some initial discrete primary benefits have been realised, such as the launch of a Women in Finance Charter, design of a distributed solar power pilot in a favela in Rio de Janeiro, and online matchmaking for MSMEs to encourage social entrepreneurship in Brazil. But it is still early days for the programme and the COVID-19 pandemic will make achievement of poverty reduction harder in Brazil, so there is a risk to achievement of the outcomes set out in the business case, particularly given the small time window of the programme. Primary benefit assessment: A-.

We judge a more positive picture on secondary benefits. The programme has already started contributing to specific business wins (e.g £22m on energy, or a recent £53k contract for a Cornwall-based water company), and has delivered several activities – e.g. a TfL Mission to London – which may generate future opportunities. It also has a strong Secondary Benefit strategy and toolkit in place. Although significant benefits are yet to materialise (partly due to COVID-19), this is compensated by significant soft power benefits – the SRO wrote recently to the Foreign Secretary, for example, that ‘the Prosperity Fund has been a game-changer for our relationship with the powerful Economy Ministry, and across the Brazilian government’. Secondary benefit assessment: A.

We find that the programme has made good progress on gender & inclusion. Suppliers now have G&I Action Plans and advisors in place. Early successes include launch of a Women in Finance Charter commitment from Sao Paulo’s transport ministry to create a central reporting channel for gender-based harassment, and embedding gender concerns into the Energy Ministry’s post-COVID plans. Work remains to ensure that all strands meet central PF minimum standards on G&I (as per refreshed guidance), with Trade now compliant and Future Cities furthest away (according to the latest assessments available). But we recommend the SRO sets a target for all strands to meet PF G&I policy’s minimum standards (as assessed by the PF G&I scorecard) by the middle of 2021.

One highlight of the year was the programme’s agile adaptation during the early months of the COVID-19 pandemic. Teams moved immediately to remote working, and in June the Board took a strategic look at the programme, informed by recommendations from suppliers. Based on clear principles, the SRO was able to stop or delay some activities, and amend/authorise others to support Brazil through the pandemic, such as a green mobility package for Sao Paulo, a COVID recovery plan for the Energy Ministry, a pilot to reduce cost of electricity in Rio favelas and the implementation of handwashing facilities in poor areas in Recife. This complemented other nimble uses of ODA (e.g. the FCDO’s International Programme) and policy (e.g. a vaccines dialogue) to help Brazil respond to the increased risk of poverty, and represents good programme management.

We have no clear answer to the SRO’s question about scaling up/down strands. We accept that there is not yet enough evidence to make big decisions: supplier performance is variable (but generally improving), and it is too early to assess performance against the appraisal case, particularly as COVID-19 will have affected some of that analysis. We should also guard against a prejudice towards strands which are seeing early successes. That said, we do not expect that such hard evidence will become apparent until it is too late to make strategic choices on portfolio balance. Also, it is probable that the SRO will be asked to make cuts in the programme next year, reflecting likely falls in overall UK ODA allocations. If that happens, we recommend taking a pragmatic and strategic approach to those cuts. One way is to seek a range of cuts from all suppliers, and then consider the portfolio as a whole, according to the principles outlined in Section D below.

A common theme which emerged was around over-complexity of the programme, in three senses: (a) excess bureaucracy, (b) too many sub-strands, and (c) lack of a compelling overarching narrative. This is tough to resolve without reshaping the programme, which we do not recommend given the difficulties of securing approvals above the SRO’s delegated authority. So, subject to imminent guidance from London, we recommend reducing the frequency of PF Boards to every 2 months, with a monthly SRO-led meeting to take strategic decisions. In the meantime we recommend developing a clearer narrative which (via a new Comms Strategy) helps the SRO communicate externally, and helps other teams in the Network (e.g. DIT) engage better with the programme. And the programme should try to reduce admin for suppliers by rationalising the number of indicators (and making them broadly consistent between strands).

We conclude that the programme is broadly Paris-compliant (which we understand to mean ‘consistent with an emissions trajectory for Brazil which meets the COP21 goal’), with a suggestion on Energy covered later in the Review. This is based on an assessment in April 2020 which notes beneficial climate impacts from Green Finance (greater investment in low-carbon infrastructure), Future Cities (reduced water leakage and pollution from traffic congestion), and Energy (driving up solar, offshore wind and sustainable biofuel usage). It is also supplemented by a more recent analysis (still in draft at the time of writing) which finds that the Energy programme’s work on natural gas can be expected to reduce GHG emissions by 2.8MTCO2e in 2029 – e.g. by facilitating a future biogas-based transport sector. It is also encouraging that the programme team and suppliers are committed to mainstreaming actions to tackle climate change further into the programmes – e.g. through efficiency and storage in Energy, or ports’ emissions intensity in Trade. We do not at this stage recommend eliminating the small strand of work on gas market liberalisation in the Energy programme, given its potential to facilitate intermittent renewables and the strategic importance of this work. But, we recommend keeping this under close review with the Ministry of Mines & Energy over the next year, and re-assessing this issue at the next Annual Review.

Team capability is much improved. The programme team’s structures are clearer and more cohesive internally and with other parts of the Embassy. Staff turnover has been managed effectively. A particular improvement has been creation of a central Operations Team which has a strong grip on issues like finance and governance. The main gap remains on depth of in-country cross-cutting expertise: especially gender/inclusion (to align with PF minimum standards), MREL (to ensure consistency across ToCs, logframes and KPIs), comms (to embed a recently-agreed PF Comms Strategy) and climate (given the increasing focus on Paris-compliance). We accept the programme team’s assertion that these cannot be ‘mainstreamed’ into existing roles – although would suggest the team might test this with new staff. So we recommend the team fills these gaps either via hiring staff, or drawing on more central technical support.

In the medium-term, we recommend that the SRO begins to prepare for the post-Prosperity Fund period. Much remains uncertain, including the size of UK ODA, nature of poverty in Brazil, and priorities of the FCDO following an imminent Integrated Review in the UK. But now is the time to start developing the evidence base and analytical capability to understand poverty and gender issues in Brazil, and to integrate better ODA-funded activities across HMG’s footprint, currently split between at least four different teams in the Network – for example, using Green Finance to create an ‘on-ramp’ to larger loan-based support via the ICF’s Sustainable Infrastructure Programme. A better understanding of multilateral development banks will help guide the SRO on whether/how to route future Prosperity Fund type funding via the MDBs.

# C. Detailed Output Scoring
## Energy

### Key Points

The biggest achievements of the Energy strand this year were the approval of procurement, selection of the delivery partner, completion of inception and beginning of implementation phase. This took longer due to scope amendments to eliminate previously-intended work on fossil fuels. Given that work on natural gas is paused, we focus here on renewable energy.

Inception Phase ran from December 2019 to June 2020, and Implementation Phase started in July 2020. The programme is progressing at pace, making up for the lost time; with evidence of 8 outputs starting delivery across 4 renewable energy subsectors: Waste to Energy, Biofuels, Solar, and Offshore Wind. Six outputs are planned to start later. The programme is also advanced on stakeholder engagement (critical for delivery), with a good range of interactions with the Brazilian Government (Federal and local), end beneficiaries and the private sector. The programme also covers a wide geographical scope in areas with potential for growth and poverty reduction.

The programme focuses on improving regulatory frameworks via research and whitepapers and delivering pilots to test new technologies. These approaches carry higher risk because impact is dependent on external partners such as the government and private sector. They will also take time to bear fruit. The team is confident it has mitigated these risks via a careful selection of sectors and types of regulation. We do not have evidence to suggest another approach, but we recommend keeping this under review over the next year to test likelihood of impact, and suggest the team carries out regular evaluation of activities to consider alternative, more creative approaches which draw on a broader range of interventions.

The team is mainstreaming gender and social inclusion in all activities. A GESI action plan has been developed, and strand has a senior specialist in place. The evidence provided by the time of the review suggests that such initatives still seem stand-alone and are not specific to the scope of the programme. However, during the quality assurance period a new logframe has been revised by the PF Social Development Advisor with more thorough G&I considerations, but work remains to be done to decide which G&I activities should be selected for specific strands and pilots. We recommend that further work is done to target these activities accordingly, informed by diverse stakeholder engagement and close work with workstream leads.

Recent analysis suggests the Energy strand is broadly Paris-compliant, and work on renewables is expected to show positive outcomes related to Nationally Determined Commitments (NDCs) by Year 2 of implementation. A concern was flagged around work on liberalisation of the natural gas market – a small component of the programme but a key request from the Brazilian Government. Early assessment had indicated possible misalignment with the Paris agreement, but we are assured that, given the significant political interest and risk of loss of traction on the programme, the team is working to ensure that natural gas activities are Paris compliant whilst also meeting Brazilian government expectations. From a technical perspective, the evidence shows that the programme is effectively focusing on the use of natural gas as a transitional fuel, and on repurposing infrastructure for renewables – which may bring effective emission reductions in Brazil.

This strand adapted quickly to COVID-19. A full assessment of the impacts in Brazil’s energy sector was carried out following request from the Brazilian government, which concluded that there will not be a long-term reduction in energy demand (notwithstanding a short-term drop). No energy sectors have been dropped as results of this analysis, but activities have been adapted to reflect sector challenges. We recommend keeping this under review to ensure if more severe adaptations are necessary in the end of the first year of implementation.

Overall we judge the strand is on target to achieve expected outcomes by the end of the programme. However, as the pilot technologies in scope of work are at early stages of development and they may take time, the programme might benefit from at least one year’s extension to provide better assurance. We recommend the SRO keeps this under review, particularly during year 2 of implementation, and seeks adjustments as necessary.

Governance arrangements and stakeholder engagement have been outlined in reports, but not yet implemented. Better communication and coordination are important and should be quickly implemented to ensure continued beneficiary engagement. We recommend the delivery partner to establish steering committees and define a frequency of meetings to report on the programme progress with beneficiaries soon.

### Recommendations

Keep Outputs under review from an effectiveness value for money perspective with regular testing through out the first year of implementation; create intermediate outputs evaluation periods; ensure potential need for adaptation of activities happen fast; consider other types of activities to provide better assurance of impact;

Review some indicators for better causal/attribution links in the different levels of the logframe (from output to outcome);

Review GESI opportunities at project/task order level and select specific activities with programme scope.

Carry out continued review of likelihood to achieve the pilot outcomes and the research to turn into policy within the programme timeframe, and flag early if adjustments are required.

Establish programme steering committee with beneficiary presence and clear definition of roles, responsibilities and frequency of meetings.

## Future Cities

### Key points

Following a meeting between the Ambassador and World Bank Country Director in July 2019, work on the Future Cities strand sped up and the inception phase (funded via an External Financing Output arrangement) was completed in November 2019, three months later than planned. The substantive Administrative Arrangement establishing the Trust Fund was agreed in March, and this strand is now in implementation. A number of contracts have been signed with subcontractors to assess mobility issues such as accessibility, 5G connectivity and traffic-light modernisation.

There has been some progress in this strand. The Theory of Change (with assumptions) is finalised, and logframes and indicators are due to be completed by the end of this month. Supplier teams are in place, including stronger oversight of both the water and mobility elements. The frequency and quality of comms between the programme team and World Bank is improved. Successful mobility outputs have included a first-of-its-kind gender & inclusion mobility assessment, urban logistics study, and transport mission to London for Sao Paulo – the latter beating expectations with 20 participants, which has opened up a new area of work around governance and integration of transport agencies. The programme has also completed a study of water loss in Recife (the first in 10 years), and an interesting behavioural change study on how to change public behaviour on bills payment. Fiduciary risks have been managed well, and there is evidence that the programme is leveraging wider change: crowding in World Bank resources to build an Operations & Control Centre in Sao Paulo or support Bus Rapid Transit in the east of the city; or helping Recife to build a new water-loss department in Compesa.

That said, there remain three significant challenges in implementation of this strand:

Delays. All beneficiaries criticised significant delays in programme implementation. One beneficiary has been waiting since June to sign a grant agreement to purchase equipment for its smart water pilot; and likewise another beneficiary is awaiting grant agreements around the proposed smart traffic lights pilot and Ops Centre. This has had a negative impact on both beneficiaries. While some of these delays may be attributable to wider challenges around COVID-19 adaptation, the beneficiaries have stated that some of the Delivery Partner’s management processes should be improved.

Information flow. Both beneficiaries and the programme team report that the delivery partner needs to improve detail, accuracy and frequency of information. Equally the supplier noted a risk of confusion or inconsistency between messages being given to the beneficiaries by themselves and by the programme team. We recommend therefore that a regular rhythm of meetings is established to improve information flow all around, with the supplier leading on technical meetings and the programme team participating in regular management meetings. This will also help accelerate the programme to overcome the delays described above; and generate institutional memory to overcome any changes of key personnel in the supplier and/or beneficiaries, as have happened on water and may happen soon in mobility.

Bureaucratic incompatibility. A clear message from the supplier was the level of information required by the programme team is excessive: in addition to the overall Theory of Change and logframes/indicators, the Prosperity Fund requires detailed quarterly (not annual) reports at activity-level, detailed financial data, specialised plans on gender/inclusion and secondary benefits, and so on. This diverts staff time away from external-facing work,and generates knock-on work for beneficiaries to provide this information. And is consistent with the recent OECD DAC peer review which reports that ‘partners find…[UK] systems onerous, feeling that they pose an additional administrative burden, focus dialogue on compliance rather than shared analysis and transfer too much risk’. We recommend that the programme team (with PFD) and supplier discuss where compromise might be possible on reporting requirements, recognising that this is an unusual arrangement for both sides. Options might include reducing the quality of quarterly reports, slimming down the number of indicators, and allocating more staff in the supplier to provide necessary management information.

Overall this has been a difficult start for the Future Cities programme, especially on the water side. The prognosis for the future is more positive, as the programme develops a rhythm and gets deeper into implementation of key activity. In addition to the suggestions above we recommend that the supplier secures dedicated internal MREL and gender & inclusion support from its wealth of experts, and complete a G&I plan and Secondary Benefits plan by the end of March (if necessary with the Embassy holding the pen on the latter) to be consistent with other strands of the Prosperity Fund.

More broadly an intensive effort is needed to build greater trust and more respect between all parties: to give beneficiaries reassurance that their views are heard, to free up World Bank time to focus on the essentials, and to provide the Embassy the minimum level of compliance necessary (recognising that the supplier has strong expertise in delivering ODA effectively using its own procedures).

### Recommendations

Establish a regular rhythm of meetings to improve information flow, with supplier leading on technical meetings and the programme team participating in regular management meetings.

Programme team, PFD and supplier discuss where compromise might be possible on reporting requirements.

Supplier secures dedicated internal MREL and gender & inclusion support from its wealth of experts.

Suppier completes a G&I plan and Secondary Benefits plan by the end of March (if necessary with the Embassy holding the pen on the latter).

## Green Finance

### Key points

The biggest achievement of the Green Finance strand this year was to move to select the delivery partner and move from Inception Phase to Implementation Phase in April 2020. During inception the Prosperity Fund Board approved two priority sectors: sanitation and waste management, and renewable energy. This allowed the programme to focus early on defining activities to attract sustainable investment, underpin by a target to finance at least two executable projects.

A further success was the selection of two Brazilian Development Banks to act as vehicles for the definition of rules on Environmental, Social and Governance (ESG) investments: BNDES (Brazil’s National Development Bank) and Caixa Federal (a big public bank with an important role in infrastructure development). Engagement with BNDES is mature: two programme workshops secured the participation of 10% of the Bank’s total staff, and BNDES is committed to create an ESG Department to evaluate green investments. Engagement with Caixa is still in early stages, risking small delays in delivery of some activities. Programme governance is improved, via the establishment of a Strategic Committee, a Technical Cooperation Agreement with BNDES on top of the already signed MoU (to support exchange of information) to be signed until the end of 2020, and an Independent Reseach and Innovation Committee with sustainable policy experts to advise on the programme outcomes.

We note that the programme is highly-dependent on the partner banks in the early stages, although this dependency should reduce over time. The team is reducing concentrated dependency by including a third partner institution (Associação de Fomento ao Desenvolvimento), and recommend the programme continues this approach so it can attract more private sector investment and deliver sustainability beyond the lifetime of the programme.

Relations between the team and supplier are much-improved, following alignment of expectations around objectives and scope – and remaining issues are being tackled. The quality of analysis remains good, and KPIs remain valid (albeit evolved from the ones in the business case).

Given the potential synergies of work on renewables with the Energy strand, strand teams and delivery partners have joined-up governance. However, both strands have types of priority projects and different target audiences. The pilots in the energy strand are at earlier stages of technology development, while the green finance ones are ready for investment, making integration between the two strands beyond exchange of information limited at the moment. The potential alignment would only be perceived beyond the lifetime of the programme when it is expected technologies supported by the energy strand will be ready for sustainable investment generated by the green finance strand. The two sided approach of these strands being riskier (energy) and more conservative (green finance) on technology investment creates a positive risk balance from a programme perspective. However, we recommend both strands continue keeping a shared governance to find potential early links, including with potential work on the energy strand – and, indeed, other programmes such as the ICF’s Sustainable Infrastructure Programme – to attract more sustainable investment in the future.

The strand adapted well to COVID-19 restrictions, despite seeing a slow down in implementation in the early months of the pandemic due to lack of availability from government partners (hence making important the continued reduction of dependency). However, the adaptation process was thorough with the revision of activities and inclusion of others. We have a high level of confidence in continued delivery.

The strand is considered Paris-compliant, with opportunities to make a positive contribution to our climate equities. The opportunity lies in the information generated by the programme that can be immediately used for the benefits of the NDCs. We recommend the strand to consider how to bridge this knowledge to find links to support the implementation of the Paris Agreement in Brazil.

The green finance has the most ambitious gender targets in the programme. It developed a Women in Finance Charter that was signed by different finance institutions collaborating with the programme and aims to promote women participation in the financial market. On the other hand, identification of gender activities more specific and relating directly to the programme activities is still underway. At the moment, the gender equality promotion aspect is not clearly connected with the specific programme outcomes and target a wide and disseminated financial market. We recommend the delivery partner find more specific opportunities within the intended initiatives to find better attribution to the programme efforts and further dissagregate indicators by sex in the logframe.

Finally, the programme is currently defining the criteria to select the investment projects which the programme will support. This presents a good opportunity to consider the direct positive impact on end beneficiaries as a criteria and enhance the direct impact of social inclusion and reduction of inquality, providing greater attribution to the programme. So we recommend criteria, once defined, include social inclusion and poverty reduction potential, and are approved by the Prosperity Fund Board.

### Recommendations

Reduce the strand’s logframe to a more manageable and proportionate size, particularly in outputs, considering the amount of funding to this strand.

Continue reducing the level of dependency of the programme’s success on partner banks.

Continue shared governance with the energy strand and find potential links in how the technologies supported by the energy strand can more easily access sustainable investment.

Find active ways to support the implementation of the Paris Agreement.

Refine gender activities and better link them to the specific programme outcomes, including further disaggregation of indicators.

Include potential of social inclusion and poverty reduction as criteria for selection of projects and have the set of criteria approved by the PF Brazil Board.

## Trade

### Key points

The main progress for the Trade programme has been the transition of the MSMEs and Ports interventions from their inception phase in September 2019 to their implementation in April 2020. The programme has been able to implement several milestones, including the programme adaptations which focus on the Covid-19 crisis, delivery of MSMEs pilot plans, and working with the port communities to convene effective Port Community Systems Steering Groups. Its implementer, Palladium has been very active on responding to the team’s requests and programme changes to keep on track, avoid major delays and meet expected outcomes.

Since the MOU between the FCDO and the OECD was signed on May 2019, considerable progress had been made in defining the external governance for the programme to take into account new structures within the Brazilian government. The negotiations and signed agreements to support Brazil’s accession to the OECD have also advanced during this year. Despite the cancellation of several seminars and missions due to Covid-19, eleven projects have been delivered in partnership with the OECD and the Brazilian government. One of the most successful is the Transfer Pricing project, which supported dialogue initiation and follow up discussion of the Transfer Pricing rules between the Brazilian government and the OECD. This part of the programme has successfully implemented 75% of its budget allocation.

The first quarter of implementation saw a change in the programme’s direction and its ability to move beyond current Covid-19 challenges. Teams adapted programme activities to minimise disruption and leverage opportunities to contribute to economic recovery in Brazil. For example, in June 2020 the MSMEs pilot (with the IDB) delivered an online matchmaking event in the food and beverage sector, which attracted 340 MSMEs and 130 international buyers from 53 different countries and facilitated 580 meetings between Brazilian companies and foreign buyers. The result was $28.7m of immediate sales, with an additional $150.8m expected over the next year.

Although the Trade programme does not have a unified G&I action plan, the inception report responds to many of the trade-related recommendations of the G&I assessment and the MSMEs and Ports have their specific G&I action plans. Recent interventions have had a strong focus on diversity and inclusion, connecting groups such as women entrepreneurs or the black entrepreneurs’ networks. As an example, the Ports component has included a series of awareness-raising workshops within relevant communities and distribute knowledge about the roadmap for Port Community Systems implementation. The programme has also explored possible synergies between the ports involved in the programme (Suape, Santos, Itajaí and Rio de Janeiro) and the Port of Itaqui, a reference in Brazil for its implementation of G&I actions that are delivering strong results for the port community.

The ToC for the MSMEs and Ports components shows good understanding of the context for supporting more inclusive foreign trade in Brazil by modernising and integrating processes in ports, making them focal points to catalyse growth around which clusters of MSMEs can grow and enter global value chains. The ToC also includes causal pathways for achieving SB.

### Recommendations

A complete ToC for all elements of the Trade programme is recommended to demonstrate how the different components (OECD, Ports, MSMEs) will integrate to help realise the primary purpose and secondary benefits. This might include a secondary benefits narrative.

To consider allocating extra funding to support Brazil’s OECD accession. This additional funding will enable the program to upscale current projects and implement new activity in areas such as green and resilient growth. Recent activity has increased soft power in Brazil, and the UK is now considered one of Brazil’s key partners on OECD accession as a direct result of the projects funded by the MoU.
# D. Value for Money & Financial Performance

## Cost Drivers and Performance

The allocation of the programme for FY 2019/20 was £5,386,548. Actual spend was £4,874,050, which represents 90% spend against the allocated budget. The programme ended the year 10% underspent due to a payment to the World Bank for delivery of the Future Cities strand which had to be delayed to the following financial year. Other variances are explained below, but they have been managed through monthly forecast adjustments. This delay happened due to the fact that the Bank is paid in advance and there was not sufficient evidence received that the previous payment was used in up to 80% to justify the previously forecasted payment. This documentation issue has been resolved in FY 20/21, as described below.

The key cost drivers for the programme in FY 19/20 were programme delivery (initial projects delivery, preparation for procurement and procurement and inception phase delivery costs), programme monitoring, and staff costs. They represented 74%, 3% and 23%, respectively. This is in line with the total programme cost expectations. Staff costs seem to be higher this FY due to proportion of spend, but overall spend is aligned with the business case. Programme admin costs are above the JFU threshold, but this was expected given high labour costs in Brazil, and approved as part of the business case.

Each strand line below shows a certain level of variance, as most strands did not have a delivery partner procured in the beginning of the FY, when the allocation was given. Trade, Green Finance and Energy strands signed contracts during the FY, and forecasts had to be significantly adjusted to reflect contract negotiations, particularly for delivery of inception phases, which were completed by the end of the financial year (except for the energy strand that completed inception later in June/2020). Staff costs also had significant variance mainly due to exchange rate fluctuation.

From April/2020, the programme team readjusted expected costs using lessons learned from the previous financial years, particularly on staff costs, where there is little control from Post or more accurate ways to forecast. Monthly forecast accuracy has been improving in FY 20/21 and cost drivers remain similar. Expenditure risks as a result of COVID-19 have been quickly mitigated and activites scrutinised during Q1 and Q2 to keep good level of implementation. The main changes were related to removal of travel and reallocation of resources.

Table 1 – Expenditure FY 2019/2020
STRAND/SPEND TYPE	TOTAL ALLOCATION	ACTUAL SPEND	£ VARIANCE	%VARIANCE
Trade	£1,838,340	£1,417,867	£420,473	22.87%
Green finance	£580,000	£575,995	£4,005	0.69%
Future cities	£478,398	£398,500	£79,898	16.70%
Energy	£865,534	£1,197,356	-£331,822	-38.34%
Staff costs UKB	£400,000	£296,065	£103,935	25.98%
Staff costs LE	£450,000	£296,169	£153,831	34.18%
Programme admin	£88,500	£57,804	£30,696	34.68%
Programme Monitoring (all strands)	£120,776	£89,098	£31,678	26.23%
Platform costs	£565,000	£549,550	£15,450	2.73%
Credit (FY 18/19)	£0.00	-£4,354	£4,354
TOTAL	£5,386,548.00	£4,874,050.00	£512,498.00	10%

Table 2 – Partial Expenditure FY 2020/2021

STRAND/SPEND TYPE	TOTAL ALLOCATION	ACTUAL SPEND TO OCTOBER-20
Trade	£4,378,325	£1,363,820
Green finance	£1,485,399	£516,890
Future cities	£3,684,754	£3,480,250
Energy	£3,411,709	£1,180,853
Staff costs UKB	£220,537	£161,882
Staff costs LE	£229,463	£145,635
Other admin	£60,000	£6,250
Programme Monitoring (all strands)	£33,785	£304
Platform costs	£496,028	£496,028
TOTAL	£14,000,000	£7,351,912

## Value for Money

The programme is on track to deliver good value for money. Considering the programme is in the first stages of implementation, performance so far is analysed on the output level and initial positive evidence related to stakeholder engagement, definition of workplans, and potential to achieve primary and secondary benefits. Those positive evidences related to Economy and Efficiency, which are described below. It is still early to assess Effectiveness, although there are some aspects captured in this AR related to the Energy strand that we advise to be kept under revision. Adaptation to COVID-19 has been positive so far as implementation has not stopped and activities have been quickly shifted to continue to achieve the expected outcomes.

## Economy

The programme is following the expected financial and commercial considerations in the business case for delivery of the programme. This included procuring three commercial delivery partners and signing two MoUs (one with the World Bank and one with the OECD). The procurement process was led by the former FCO Commercial Team and used the Prosperity Fund Framework, therefore ensuring consultancy fees and other costs are in line with spend caps. The commercial contracts came under the expected value saving £4.2m for the programme. However, this was not enough to cover the current total overprogramming which is at £7.2m (13%), which the team is managing to converge to available allocation. Total staff costs spend continue in line with the expected proportion approved in the business case (7%). Despite this, programme still needs to make financial adjustments in the next years to reduce total overprogramming. We recommend the programme to develop a plan to reduce the overprogramming in the coming years to a manageable extent (of around 5%).

All commercial contracts included measures to ensure economy in particular activities, such as the requirement for delivery partners to follow FCDO Brazil’s travel guidance. It does not allow business class travel, it requires the use of FCDO approved hotels and expenditure ceilings. OECD also follows this measure, which is a very positive outcome of negotiations to ensure economy. There are approval processes in place should delivery partners require exceptions.

COVID-19 presented opportunities for economy in the programme and this was evidenced by the considerable reduction of travel costs throughout the year and partial reinvestment in other programme activities, which were delivered for less money.

## Efficiency

Programme outputs seem fit for purpose, on track to be achieved, and initital evidence of success. There are potential risks identified under the Energy strand activities (described in paragraph 23), which we recommend to be kept under review during the first year of implementation. Future Cities strand has issues with data reporting from the World Bank, as described in Section C. Team progressed in finding a common ground over the past months, however World Bank still finds difficult to comply with all of PF’s reporting requirements. Most output advances are due to be tracked in March/2021, and we recommend earlier review points, as described in the MREL section. Clear evidence of progress in engagement with beneficiaries, creation of steering committees, successful completion of inception phases with further definition of expected outputs, outcomes and workplans, and technical contextual analysis.

The team adapted activities and workplans to COVID-19 restrictions fast, and all programmes continue delivery at pace with high confidence of delivery within the programme period. At the start of the pandemic, the programme carried out a thorough feasibility analysis and reshaped activities (e.g. virtual events and meetings), bringing forward activities from following years possible to be implemented remotely this year. For example, the Trade programme implemented a virtual match-making event with MSMEs. This ensured expected spend and implementation levels remained fairly as expected before the pandemic, and outputs remained fit for purpose. Despite the positive changes, delivery partners reported that some activities are taking longer to be implemented and they are monitoring closely potential future impacts.

The team is confident that the pandemic and changes in context will not have immediate impacts on the programme. But this may change if the restrictions continue to last and a deeper review may be necessary. The programme team also adapted fast to remote working practices and were able to engage with delivery partners. Some strands reported intitial lack of availability from beneficiaries to engage, but most has been overcome or is being overcome without major risks.

## Effectiveness

All strands refined ToCs during the past year with support from the MREL team. Logframes have been created and revised with delivery partners. They seem fit for purpose and require some minor adaptations, described in the MREL section. Most initial intermediate outcomes and/or outcomes are expected to be reported in March/2021, in the end of the first year of implementation. Therefore, there is not much evidence now for effectiveness assessment, although from the analysis of outputs, primary outcomes seem to be on track to be met and secondary benefits already show evidence of outcomes delivered.

That said, we expect the programme may be required to make cuts over the next year given the current economic situation in the UK. If so we would recommend that the programme team try to take a strategic rather than salami-slicing approach. They should consider the economy, efficiency, effectiveness and equity of the different options, and examine also (i) success to date, (ii) prospects for additional activity and (iii) stakeholder buy-in – and present a recommended (set of) options to the SRO for approval. Based on anecdotal evidence during this Review (which would need to be tested during this rapid exercise), initial indications suggest:

1. Shifting the portfolio balance from Energy (which faces a number of risks) towards Trade (given the relative success of the OECD work to date)
2. Considering options to replicate early successes at sub-national level
3. Holding back some ODA to create an ‘Agile Fund’ which could be used for small-scale new, tactical or exploratory work which supports the overall Theory of Change

The programme team progressed in relevant recommendations from the last Annual Review. There were three key recommendations: #1 was rejected by the Brazil PF Board due to lack of specificity; #2 has been addressed and now the programme has a clearer understanding of costs and benefits following completion of procurement processes, inception phases and refinement of theories of change, logframes and work packages; #3 is being implemented as an audit of the Brazil Network that includes the Prosperity Fund is being carried out in parallel to this review.

There is not enough evidence to evaluate effectiveness of COVID-adapted activities as well. No counter-factual information limits options to confirm if virtual events have been more effective than in-person events or not, for instance. Therefore, we recommend the programme team with support of the MREL team to carry out a revision in the end of Year 1 of implementation to confirm if activities implemented during the year delivered similar expected outcomes and evaluate if they should continue as it is provided they created savings mostly in travel.

The business case estimated a total impact between £1.2bn and £3.4bn in overall primary benefits and between £84m and £705m in secondary benefits over 10 years. The KPIs defined remain valid with minor changes resulting from the evolution of thinking during implementation. However, COVID-19 will bring additional growth and poverty challenges in Brazil. This may change the estimation of programme impact provided assumptions and context have changed. So we recommend recording those changes during the period of the pandemic, and create checkpoints for evaluation of changes to potential primary and secondary benefits.

## Equity

The Readiness Review carried out in the middle of 2020 showed the programme requires further work to meet G&I strandards. The programme team is progressing on improvements with delivery partners to ensure minimum requirements are met soon. The programme team still has G&I capability gap, and the team is evaluating options on how to fill it, whether find resources within the current team, hire extra support, or draw on more central technical support. We recognise that resources may limit the programme’s ability to achieve this.

Delivery partners count with G&I teams, and logframes have expected gender-related outputs and outcomes as well as indicators dissagretated by sex and other social measures. During interviews programmes reported a positive focus on and engagement with end-beneficiaries, i.e. social groups to benefited by the programme outcomes. We recommend to strengthen this engagement throughout implementation and not only during Y1. We also recommend to immediately improve links or better blend gender related outputs to programme sector activities as most seem stand alone to each strand focus. Finally, we recommend improving the programme’s performance against the G&I scorecard by the end of the FY.

## Quality of Financial Management

The programme team has improved standard programme and financial management processes during the past year and is now managed to a high strandard. The introduction of the Brazil PF Standard Operating Procedures (SOPs) created a strandardisation of practices for the team and for the delivery partners. These SOPs also introduced new templates and reporting mechanisms to be used by commercial partners, which provides a good level of details on progress and also finance. This includes a deep dive on each strand every three months to check for proof of expenditure. The team also has monthly financial management procedures led by the Operations Team, which includes revision of detailed workplans and financial meetings with each strand to confirm expenses, forecast and accuracy. New Operations Reports provided the Brazil PF Board with better oversight of finances.

There are still challenges related to financial management with multilaterals, World Bank and the OECD. These multilaterals are reluctant to adopt all of the team’s required procedures, which limits the team’s access to detailed financial information. Despite this, the team was able to negotiate a compromise with the institutions, which adopted some minimum financial reporting standards, which allows the team to have better control than in previous years.

Overall these processes do not bring excessive bureaucracy to the programme and were deemed fit for purpose. And they ensure that – despite lacking change controls guidance below SRO level – there is a good level of oversight from seniors. The SRO would like further clarity on how this is dealt daily, though. Therefore, we recommend a simple change control guidance to be introduced reflecting current practices to provide further assurance to the SRO.

Date of last narrative financial report:	19 October 2020 (updated detailed workplans received every 5th business day of the month; financial reports received on the 12th business day of the following month after a payment is requested)
Date of last audited annual statement:	N/A

# E. Risk

OVERALL RISK RATING: MODERATE

## Overview

Due to the Covid-19 pandemic, continuous monitoring and adaptations have been conducted in order to effectively reduce disruption to milestones delivery. In May 2020 the programme evaluated the impact of social distancing and consequently revised workplans to ensure that activities were capable of being delivered remotely. Implementers have also assessed needs, opportunities and continued viability for adaptation across the four strands. The conclusion of this assessment is that all programmes remain viable and some programmes now feature new projects to cover new economic issues.

The team has successfully monitored and managed risks related to Covid-19. This includes the impact of delays, reduced buy-in from government stakeholders, and the failure to adapt adequately to the new operating environment. During the programme adaptation process the team has ensured full alignment with the business and budget allocations, enabling it to continue focusing on poverty reduction and the creation of commercial opportunities for international businesses.

Covid-19 adaptations have had a very limited impact on programme forecast spend and allocations. However, the underspend risk is high, so the PF Operations team has been evaluating programme spend monthly and adjusting forecast and allocation accordingly to minimise the possibility of significance variance by the end of the financial year.

## Outstanding actions

Risk identification and management processes have been established at the portfolio level based on the Brazilian context (responding to an Annual Review recommendation last year). Risks related to Covid-19 have been included and monitored regularly. Risks are flagged at PF Board if there is a relevant change.

There is an inherent risk associated with changes of the requirements of the Brazilian government; if the programme does not address express or implicit changes quickly, interventions may lose traction with the main stakeholders. Long-term outcomes of the programme are dependent on the success of partnerships with local stakeholders. The Programme Team has been able to manage strategically its relations with government stakeholders to keep them engaged and aligned with the programme. For example, the Energy programme received a request from the Ministry of Energy and Mines to undertake additional work on Covid-19 adaptations; it was possible to accommodate the request in the Energy programme design and meet with Brazilian government needs.

Following a last year AR recommendation about establishing an institutional memory, a permanent Analyst joined the Operations team in July 2020. He is supporting the team on managing and centralising information, and ensuring effective governance.

# F. Commercial Considerations

## Delivery against planned timeframe

All four strands started their respective inception phase last year and have moved to their implementation phase. The programme is on track overall although there are small delays in some activities due to Covid-19.

Procurement and contracting processes have taken longer than envisaged and have led to delays in bringing delivery partners on board. The programme currently has two agreements with multilateral organisations for implementing the Future Cities strand and the OECD workstream of the Trade programme and three commercial contracts for the Energy, Green Finance and Trade programme (MSMEs and Ports).

Table 3 – Programme expected and actual timescales

PROGRAMME STRANDS		EXPECTED TIMESCALES (BUSINESS CASE)	ACTUAL TIMESCALES	COMMENTS
Energy	ToRs launched	Sep-18	Feb-19	Business Case approved in October 2019 and contract signed with Adam Smith International
	Supplier selected	Dec-19	Apr-19
	Contract signed	Mar-19	Dec-19
	Inception	Apr-19	Dec-19
	Implementation	N/A	Jul-20
Future Cities	EFO signature	N/A	Mar-19	Administrative Agreement to implement Future Cities programme has been signed with the World Bank Brazil for full programme delivery.
	Administrative Agreement signature	Mar-19	Mar-20
	Inception	Apr-19	May-19
	Implementation	N/A	Mar-20
Green Finance	ToRs launched	Sep-18	Nov-18	Contract signed with EY and amended to include IMC in the consortium.
	Supplier selected	Dec-19	Mar-19
	Contract signed	Mar-19	Jul-19
	Inception	Apr-19	Jul-19
	Implementation	N/A	Apr-20
Trade	ToRs launched	Sep-18	Sep-18	Contract signed with Palladium in partnership with EY, Procomex, the University of São Paulo, Hamburg Port Consulting, OCO, Next Trade, Endeavor Brazil and the IDB.
	Supplier selected	Dec-19	Mar-19
	Contract signed	Mar-19	Sep-19
	Inception	Apr-19	Sep-19
	Implementation	N/A	Apr-20
	OECD Agreement	N/A	May-19	MOU between FCDO and OECD signed in May 2019.

## Performance of partnerships

The introduction of standard reporting templates to the delivery partners (costed Workplan, Financial Report, Quarterly Programme Monitoring Report, Risk Register and LogFrame) have improved the reporting details and increased consistency on the information provided by different programmes. The SOPs also state minimum reporting frequency, monthly financial meetings with each programme team and a clear reporting structure. The programme team has also developed some common Performance Standards for suppliers to be included in the commercial contracts. This has ensured a common set of expectations for delivery and management of the programmes.

The team held its first Suppliers Conference in February, on the back of a recommendation in last year’s Annual Review. The Conference was useful in creating a partnership-based approach and setting the tone of the programme’s expectations. A second virtual Supplier Conference was held in June, focusing on addressing overall concerns and challenges relating to the effects of Covid-19 adaptation.

Progress with suppliers is going well. The strengthening of existing relationships and development of new connections has helped to co-create solutions between the programme, the Brazilian government and the suppliers which have had fresh and meaningful impact.

Some implementers such as Palladium have performed well, navigating a unique programme that requires very strong programme management leadership and a robust programme management system. On the Trade programme, lessons learned are being applied and the supplier is progressing ahead with its drive to establish partners, workplans, budgets and contracts in place for next year pilots.

Based on interviews, engagement with different implementers in the early stages has not always been straightforward. Programme management, definition of objectives, staff turnover, roles and responsibilities, among other aspects affected the delivery of the programmes. However, delivery partners have reflected on how to manage the programmes effectively, getting the right teams in place, and striking the right balance between stakeholders. Good examples of this are the Trade and Green Finances programmes, which have relationships that are running smoothly with close engagement with the Brazil Government and programme teams.

By contrast, contracting and working with multilateral banks like the World Bank has been challenging. This relationship has improved and the World Bank now has a better understanding of the PF’s needs following the closer involvement of the new Country Director. However, there is still some misalignment between the PF’s management needs and what the Bank can deliver. Additionally, experience has shown that problems still need to be escalated on time, support for secondary benefits is not included as part of its implementer role, and a G&I plan is lacking.

# G. Business Environment

## Cohesion

Synergies with the PF global programmes, UK Funds and other relevant UK government departments operating in Brazil have been very valuable to support the PF’s work in the country. The programme team has a good relationship with the political team and has started developing a closer relationship with the Development Counsellor and her team.

There has also been an effort to reinforce the importance of working together with DIT on secondary benefits and non-ODA funded activities. The integration of both teams clearly has benefits at a thematic level; for example, the PF Energy team is well integrated with its policy and DIT Energy colleagues. There is also a natural synergy between the Green Finance team and the DIT Financial Services colleagues, and a good cooperation between the Smart Cities programme and the DIT Infrastructure.

Virtual Teams has been pivotal in sharing expertise and priorities. They discuss and plan ideas and objectives together, and jointly structure business engagement. The Energy virtual team is connected with the Climate team; they have assessed MOUs as an effective mechanism to establish partnerships; and are currently working on three MOUs which include clean growth and climate change.

## Secondary benefits

The programme has made significant progress in aligning knowledge, communications and secondary benefits strategy across programmes, suppliers, and commercial teams. The creation of the Tools Pack (KPIs, Plan and Tracker) and plans for each strand provide a clear pathway to the realisation of secondary benefits. Currently, Energy and Green Finance programmes have secondary benefits plans, and Trade and Future Cities are expected to have them by the end of the financial year. One risk is around World Bank engagement on secondary benefits.

The Tool Pack has been an innovative tool to monitor the progress of the programme, follow up opportunities and create content to maximise the impact of communications – and is rightly held in high regard by other PF programmes such as Mexico and Colombia. The programme has also created a secondary benefits’ Impact Bank, which brings together the commercial and non-commercial impacts of the interventions. This shows for example that this year the programme has directly supported four export wins worth approximately £44m in the Energy, Life Sciences, and Infrastructure sectors. All strands have been unlocking opportunities to generate SB in such areas as soft power, network effects and market access.

It is likely, that the realisation of SB will be affected, at least in part, if the Covid-19 situation continues for a longer period. Accordingly, closely monitoring macroeconomics and trade and investment trends in Brazil and globally will be important – and the team should keep secondary benefits targets under review. We recommend that use of these tools should be included as part of the Quarterly Monitoring Progress Report.

# H. Monitoring & Evaluation

## Evidence and evaluation

The Brazil programme underwent a Readiness Review (RR) between June and July 2020 to assess how prepared the programme was to start delivery. The review concluded that programme has an adequate set of MREL documentation to track and report on progress. The conclusions were based on the good progress of processes established to date, particularly revision of Theories of Change.

Since the last AR the programme has developed and refined theories of change for all strands; developed logframes (reviewed by the MREL team); and are implementing MREL plans. All logframes have been uploaded to PROSPERO, although the Future Cities strand is going through another thorough revision of indicators.

All strands have standard monitoring and reporting procedures after the introduction of PF Brazil Standard Operating Procedures and templates to suppliers. This allows more coherent evaluation and tracking of progress across the programme. Once logframes are concluded, there will be no MREL requirements missing in the programme.

Logframes have been checked in detail as part of this AR for quality and consistency across the strands. On balance they all have appropriate quality of information to track progress against the intended programme objectives. Description of outputs, intermediate outcomes and outcomes and indicators are overall at the right level of the results chain, with some minor exceptions. Trade, Green Finance and Energy strands follow the same format of logframe template – and the different format for Future Cities does not affect the quality of the information. All logframes consider disaggregation of results by different appropriate measures to each strand (sex, age, income or other) and well as potential secondary benefits. Because all logframes were produced during 2020 they already take into account COVID-19 impacts on expected progress.

That said, all logframes (with the exception of Trade) are long and have too many indicators (particularly at output level), making tracking of progress difficult. Currently the programme has 163 indicators divided in 85 outputs; 62 indicators divided in 20 intermediate outcomes; and 42 indicators divided in 25 outcomes. We recommend a reduction to a more proportionate level to relevance of spend in each strand, particularly for output indicators.

All logframes count with the same milestone reporting timelines: March 2021, March 2022 and March 2023. We recommend strands to revise their periods of milestones reporting in order to make them relevant to track progress at the appropriate times and not only in the end of each financial year. Outputs particularly should count with more frequent checkpoints.

The Future Cities strand has different MREL procedures, reflecting World Bank policies. However, the programme team negotiated effectively with the Bank to ensure these meet our MREL requirements. Despite this positive progress, we recommend better coordination of reporting between the Water and Mobility projects as they currently seem two separate projects. We also recommend to merge the two logframes (Water and Mobility) to better show the relation between the two projects, common goals and even make easier to consider value for money decisions. The sources of indicators also need to be better described to ensure replicable analysis, if necessary.

## Monitoring progress

Progress in most outputs and intermediate outcomes is expected to be reported by March 2021. However, the programme showed positive evidence of progress on governance arrangements, definition of implementation plans, expectations, adaptation to COVID-19 and engagement with Brazilian government, beneficiaries and suppliers. Products and analysis are being generated at pace, according to logframes. Energy has already reported one milestone achieved, which is positive despite the short implementation period to date.

The programme continues to report against the objectives/KPIs described in the Business Case, ensuring the partnership and need for the programme remain valid. Energy and Green Finance KPIs have evolved to be more accurate and attributable, but are still within the same intended objectives.

## Recommendations

All logframes should include or make reference to standard PF KPIs at Outcome Level to make easier to relate to the Fund’s objectives.

Milestone reporting periods should be adjusted to reflect more frequent reporting and not at the end of each financial year.

Programme should reduce size of logframes proportionally in each strand (particularly in the Green Finance strand) to allow easier tracking of progress and value for money.

Future Cities strand should finalise indicators updates, merge logframes of Water and Mobility projects, spell out acronyms and clearly state sources of evidence of progress against each indicator.

# ANNEX I – LIST OF ACRONYMS

ABDE – Associação Brasileira de Desenvolvimento
AR – Annual Review
BETF – Bank-executed Trust Funds
BFGP – Brazil Green Finance Programme
BNDES – Brazil National Development Bank
BRT – Bus rapid transit
CET – Companhia de Engenharia de Trafego
CRM – Customer Relationship Manager
CVM – Comissão de Valores Imobiliários
DAC – Development Cooperation Directorate
DIT – Department for International Trade
ESG – Environmental, Social and Governance
FCDO – Foreign, Commonwealth and Development Office
FY – Financial Year
GCF – Green Climate Fund
GDP – Gross Domestic Product
GESI – Gender Equality and Social Inclusion
GFP – Green Finance Programme
GHG – Greenhouse Gases
HMG – Her Majesty’s Government
IDB – Inter-American Development Bank
IMC – IMC Worldwide
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
LE – Locally Engaged
MaaS – Mobility as a Service
MOU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluating and Learning
MSMES – Micro, Small and Medium-sized Enterprises
NRW – Non-Revenue Water
OCC – Operations and Control Center
OCO – OCO Global
ODA – Official Development Assistance
OECD – Organization for Economic Cooperation and Development
PCS – Port Community System
PF – Prosperity Fund
PIMS – Plant Information Management System
REOI – Request for Expression of Interest
RETF – Recipient-executed Trust Funds
RMR – Recife Metropolitan Region
RR – Readiness Review
SB – Secondary Benefits
SMES – Small and Medium-sized Enterprises
SPMR – São Paulo Metropolitan Region
SRO – Senior Responsible Owner
THSC – Trade Hub Steering Comitee
TO – Task Order
UKB – United Kingdom Based
UKPF – United Kingdom Prosperity Fund
VFM – Value for Money
WB – World Bank
WIF – Women in Finance

# ANNEX II – ENERGY INDICATORS

*Caveat: these indicators are being updated by the supplier at the time of review, to include inter alia more detail on gender & social inclusion

OUTPUT	OUTPUT DETAILS	PROGRESS DETAILS AND ACHIEVEMENTS	DELIVERY DATE
1.1	Waste-to-energy: Increased research-based knowledge about benefits and barriers for business to grow in waste to energy	Activities initiated in July 2020. / The first deliverable (D1) for TO 1.1.1 (Research studies on national and international technological advances) was finalised with the production of the study Mapping of technologies and potential for W2E. Delays on the beginning of implementation phase and rearrangements in TOs priorities requested changes in milestones’ dates for some deliverables. Activities on track to achieve deliverables on revised timeline.	D1 – 30th September 2020
1.2	Waste-to-energy: Research-based white papers and legal and regulatory instruments developed for strengthening the regulatory framework on waste to energy	Activities initiated in July 2020. / The first deliverable (D1) of TO 1.2.1. (Strengthening the implementation of the policy to foster the expansion of W2E in Brazil) was the production of a diagnostic analysis of the current regulatory framework for W2E, aiming to identify gaps in the legislation and regulations that hinder investment in this area. / Other activities on track to achieve deliverables on time. / First deliverable to TO 1.2.2. under dependence of final approval of the TO by the FCDO. If approved, it will be delivered by the end of December.	D1 – 7th October 2020
1.3	Waste-to-energy: Pilots of waste to energy technologies and business models that can get to scale within the Brazilian market	Activities initiated in August 2020. / The first deliverable (Identifying potential for technology deployment in biogas) refers to mapping out technologies for biogas deployment and the second deliverable (Project summary sheets for shortlisting pilots and assessments according to challenge statements and selection criteria) were submitted on 26th October. This proposed three biogas pilots which would support new technologies in Brazil to updgrade biogas to biomethane. Feedback awaited from FCDO. A final deliverable (D3) will be a report and overview presentation for proposed pilots.	D1 – 26th October 2020 / D2 – 26th October 2020
2.1	Biofuels: Pilots of new technologies in biodiesel production that can get to scale within the Brazilian market	Activities initiated in September 2020. / The first deliverable (D1) of TO 2.1.1 refers to mapping new technologies for biodiesel deployment, supply chain and logistics in selected states.	D1 – 30th October 2020
4.1	Solar, storage and smart grids: Pilots of new solar, storage and smart grid (interface) technologies to support commercial models that can work in disadvantaged rural and urban areas	First milestone of Solar Pilar Pilot achieved on 17 August 2020. This included the Pre-Qualification Questionnaire documentation & launch of the competition challenge. BEP’s website also went live on 17 August 2020 as part of the launch. / 14 applications received and 12 were selected for the next stage of the competition. The final application stage was launched on 22 October with a deadline of 23 November. / With regard to the scoping of further pilots in this sector, the first deliverable (D1) of TO 4.1.1.(Identifying potential for technology deployment in solar, storage and smart grids technologies) maps new technologies and how their deployment can improve the market for low-income consumers. The second deliverable (D2) , also completed provides Project Summary sheets for the shortlisted pilots and a recommendation for which pilots to implement.	First milestone of Solar Pilar Pilot achieved on 17th August 2020. / D1 – Report delivered on 26th October 2020 / D2 – Summary sheets updated and delivered on 26th October 2020
5.1	Offshore Wind: Legal, economic, and social benefits of offshore wind analysed and presented to government and investors	Activities initiated in August 2020. / The first deliverable (D1) of TO 5.1.1., which was to map the environmental and socioeconomic barriers and benefits of offshore wind projects is completed. The second deliverable (D2) was the Webinar for validation, that took place on 26 October 2020.	D1 – 20th October 2020 / D2 – 26th October 2020
5.2	Offshore Wind: Support for the design of a commercial and financing model for offshore wind energy	Activities initiated in August 2020. / The first deliverable (D1) of TO 5.2.1. was to compile in a Draft the international best practices about port infrastructure, transmission lines, contract modalities (incl. financial risk for contracts), and value chains.	D1 – 30th October 2020.
5.3	Offshore Wind: Collaborative approach developed for offshore wind regulations	Activities initiated in August 2020. / The first deliverable (D1) of TO 5.3.1. was a Draft of applicable legal framework being conducted. The first draft was submitted but it needs better structure and clearer conclusions. The 2nd Submission will be on 31 October 2020	D1 – 20th October 2020 / D2 – 31st October 2020

# ANNEX III – FUTURE CITIES INDICATORS

OUTPUT	DESCRIPTION OF PROGRESS	STATUS	SCORE	COMMENTS
A1. Recommendations for the São Paulo bus system’s OCC and OMMS and long-term strategy for the integrated OCC and OMMS for MaaS defined	Request For Proposals closed 24 August and winning firm selected. Contract negotiations anticipated to commence by mid-October. Winning firm to participate in upcoming workshop.	Delayed / Contracting process delayed due primarily to shortlisted firms requesting extension to deadline of Request For Proposals.	B	Delay in the WB procurement process.
A2.1. Methodology for cost-benefit analysis of smart traffic lights implementation developed	Activity started. Consultants supporting development of microsimulations on future Aricanduva BRT corridor. Activity will be presented during upcoming workshop.	On Track	A+
A2.2. Report on the evaluation, characterization and dimensioning of the most recommended technological alternatives for smart traffic lights and 5G and strategy to implement a smart traffic light project along key corridors and a potential city-wide project with new technologies completed	Pre-bid conference with shortlisted consultants 15 July. Request For Proposals closed 17 August. Contract negotiations anticipated to commence mid-October. Winning firm to participate in upcoming workshop.	Delayed / Contracting process delayed due primarily to shortlisted firms requesting extension to deadline of Request For Proposals.	B	Delay in the WB procurement process.
A2.3. Pilot of new smart traffic light technologies prioritising public transport along Av. 9 de Julho implemented	Possibility of changing implementing agencies discussed during mission. Forecast due date not expected to change and original executing agency expected to remain involved in project preparation.	Signature of Grant Agreement pending. / Conversations resumed in August. Mission to discuss document preparation for Grant Agreement took place in September.	B	Due to Covid19 impact, and reduced supporting from the traffic agency (CET), pilot was postponed for next financial year. / Current engagement is going well and we hope to be able to have the Grant Agreement signed with the City Hall in the beginning of the next year.
A3. Institutional governance assessment of the SPMR concluded	Request For Proposals closed 10 August and winning firm selected.	Delayed / Contracting process delayed due primarily to shortlisted firms requesting extension to deadline of Request For Proposals and need for due diligence to confirm firm’s availability.	B	Delay in the WB procurement process.
A4. Technical feasibility study for upgrading bus corridors into full BRTs and prioritization strategy for deployment of bus corridors program completed	TORs finalised. Possible change in implementing agencies for A2.3 created opportunity to include A4 in RETF (recipient executed). Would allow SPTrans to develop tasks not otherwise possible under BETF (bank executed). Proposed change under discussion.	On Track	A-	Activity brought forward. Waiting for procurement process. Depending on decision around bank executed x recipient executed.
A5. Strategy paper to include gender differences in mobility and perception of safety in planning and design and proposal report for unified 3-digit harassment complaints number completed	Request For Proposals closed 29 September.	Delayed / Release of Request For Proposals delayed.	B	Delay in the WB procurement process.
A6.1. Urban cargo logistics regulations analysed and pilot of last-mile deliveries solutions implemented	Firm contracted.	On Track	A+	Activity brought forward and well advanced. Contractor very engaged and reaching conclusion soon.
A6.2. Report on recommendations to promote pedestrian, bicycle and public transport over private car use completed	TORs in preparation.	On Track / Launch of REOI postponed to modify program schedule.	B	Procurement process delayed. Activity was expected to start in Sep 20 but now forecast to Nov 20.
A6.3. Report on micro-accessibility library for Latin America and recommendations for implementation of micro-accessibility for Sao Paulo paper completed	Consultant selected.	Delayed / Contracting process delayed due to need to align TORs with Secretary of Mobility and Transport	A-	Activity brought forward. Some delays in the procurement process but advancing well.
A6.4. Report on bicycle path planning and tactical urban planning for pop-up bicycle paths completed	Activity started.	On-track	A	Activity brought forward. Advancing well.
A7.1. Analysis of barriers to mobility by socially vulnerable groups, women, elderly people and people with disabilities completed	As a result of COVID-19 and the need for increased social distancing, A7 was split into two distinct activities allowing A7.1 to proceed without further delay. Request For Proposals closed 17 September and winning firm to be selected early October.	Delayed / Contracting process delayed due primarily to shortlisted firms requesting extension to deadline of Request For Proposals	A-	Slight delays in the WB procurement process but progressing well.
A7.2. Baseline survey of Aricanduva corridor completed		Delayed / Because of COVID-19 and the need for increased social distancing, activity postponed until 2021.	B	Activity delayed for next financial year due to Covid19.
A8.1. Communication needs to implement disruptive transport policies assessed	Activity started.	On-track	A
A8.2 Promotional campaigns developed and delivered.	WB to work with municipal government and UKPF to draft TORs for communications firm to support Programme’s dissemination and communication strategy once other activities have progressed further.	Delayed / Promotional activities with the municipal government must be postponed during the election period.	A-	Delayed due to municipal elections.
A1. Training modules on NRW and Performance-Based Contracts for technical staff and managers delivered	Firms shortlisted. Proposals due 15 October.	On track	B	Delayed. Activity expected to start in March 2020, it was delayed due to covid19. The baseline start date were Aug 20, now Nov 20.
A2/3. Long-term NRW Programme for RMR designed and organisational structure for NRW management defined	TORs in preparation.	Delayed / Contracting process delayed to accommodate the decision to amalgamate two activities. Any impacts resulting from this slight delay are expected to be offset by efficiency gains.	B	Expectation from the beneficiary to be core activity for component 1. / Delays in the WB procurement process. Initial baseline date Jun 20, then Oct 20. Now Jan 21.
A4. Plant Information Management System (PIMS) upgraded and expanded	Procurement process underway. TORs approved. Signature of Grant Agreement pending.	On track	C	Grant agreement process delayed significantly due to WB internal procedures. Initial forecast Jul 20, then Oct 20. Now Jan 21.
A5. At least three SMART Water Technology pilots implemented	Procurement process underway. TORs under review. Signature of Grant Agreement pending.	On track	C	Grant agreement process delayed significantly due to WB internal procedures. Initial forecast Jul 20, then Oct 20. Now Jan 21.
A6. Participate in at least one national or international event(s) on Smart Cities and NRW	Activity scheduled to start once Programme results become available, toward end 2021.		A	Activity forecasted for next financial year.
A1. Up to three behavioural interventions implemented	Design of first intervention currently underway	On track	A+	Progressing well
A2. Training on user-centred design thinking and behavioural insight delivered to technical staff and managers	16-hour virtual learning module on Design Thinking, Human-Centred Design, and Behavioural Insights scheduled to be delivered to two cohorts of up to 25 participants from 13-16 October	On track	A+	Progressing well, Compesa is very engaged to this activity
A3. Diagnostic Report on the application of behavioural science to sanitation service delivery completed	Contract negotiation underway. Anticipated contract start date 10 October. Kick-off meeting scheduled for 13 October. Fieldwork scheduled to start immediately after Municipal elections.	On track	A	Slightly impacted by elections timeframe
A4. Regional workshop on the application of behavioural sciences to the water and sanitation sector	Opportunity mapping underway (to identify opportunities for regional knowledge-sharing)	On track	A-	Some small delays to start, but advancing well
A1. COMPESA’s Customer Relationship Management (CRM) system upgraded, expanded and fully utilised		On track	C	Waiting Grant Agreement to be signed to publish ToR for tendering. / Initial forecasted date Jul 20, then Oct 20. Now Jan 21.
A2 Data enrichment techniques and debit negotiations via instant messaging multiplatform applications e.g. WhatsApp, implemented		Delayed / This activity was modified to address current client needs.	C	Waiting Grant Agreement to be signed to publish ToR for tendering. / Initial forecasted date Sep 20, then Oct 20. Now Jan 21.
A3 COMPESA’s functional and regional units assessed	TORs finalised and justification for single-source contract in preparation.	On track	C	Compesa has advanced on the ToR. As part of the ODA Reprioritisation process, it was proposed to the PF board to combine activities A3 and A4 into one and reduce the scope. Still need to validate with Compesa.
A4. Organisational structure for innovation defined	TORs finalised and justification for single-source contract in preparation.	On track	C	Compesa has advanced on the ToR. As part of the ODA Reprioritisation process, it was proposed to the PF board to combine activities A3 and A4 into one and reduce the scope. Still need to validate with Compesa.
A5 Long-term market strategy for the RMR designed in response to new regulatory environment	Preliminary TORs under review. Anticipated start date November 2020.	On track	B	Delayed. WB reviewing ToR elaborated by Compesa. Procurement process still to be launched.
A6 Gender mainstreaming activities implemented	Data analysed and results presented. Discussion and design of specific sub-activities currently under discussion.	On track	B	The World Bank has yet to share any information on the progress of this activity.

# ANNEX IV – GREEN FINANCE INDICATORS

OUTPUTS	INDICATORS	YEAR 1 MILESTONE (MARCH 2021)	YEAR 1 PARTIAL RESULTS
OUTPUT 1.1.	Primary Indicator 1.1.a.
Adoption of an ESG Methodology for sustainable infrastructure financing from the selected Brazilian Development Banks	Number of selected BDBs with a new policy approved	N/A	N/A
	Number of selected BDBs with a new policy formulated	1	BNDES is developing the ESG Department, anf for that is formulating the new policy.
	Number of selected BDBs with policy agenda approved	1	BNDES once having the policy formulated will approve it internally.
OUTPUT 1.2.	Primary Indicator 1.2.a.
Establishment of new processes and policies at the selected BDBs, including action plan and organizational structure & responsibilities for sustainable infrastructure financing	% of execution of BDBs action plans	N/A	N/A
	Primary Indicator 1.2.b.
	Number of BDBs' action plans publicly disclosed	N/A	N/A
OUTPUT 1.3.	Primary Indicator 1.3.a.
Implementation of tools for project financing, including key indicators at portfolio and project levels	Number of projects assessed through new methodology and tools	N/A	N/A
OUTPUT 2.1.	Primary Indicator 2.1.a.
Technical report which baselines public and private sector investment in sustainable infrastructure in Brazil, identifies key barriers and proposes solutions in relation to the primary and secondary benefits of this programme	Number of technical reports delivered	1	1 (100%)
	Primary Indicator 2.1.b.
	Formalised evidence that stakeholders (e.g. MoE, other ministries, Central Bank, BNDES, Caixa, ABDE and private sector representatives) acknowledge the report’s findings	N/A	N/A
OUTPUT 3.1.	Primary Indicator 3.1.a.
Model and a report assessing the degree of BNDES alignment with 2 degrees scenario	Number of model and reports delivered to BNDES to assess the alignment of 2 degrees scenario.	1 model and 1 report delivered in year 1	The model and report are being elaborated, and are on time do be delivered by March 2021 as expected.
OUTPUT 3.2.	Primary Indicator 3.2.a.
Events (online or face-to-face) to share key findings with other Brazilian Development Banks members of ABDE	Number of workshops (online or face-to-face) to promote 2 degree alignment to other ABDE members	N/A	N/A
	Primary Indicator 3.2.b.
	Number of participants attending the workshops (online or face-to-face) that report an improved understanding in the 2 degree alignment methodology process.	N/A	N/A
OUTPUT 4.1.	Primary Indicator 4.1.a.
Formalised green finance regulations (definition, taxonomy and criteria)	Number of planners and granters endorsing the definition	N/A	N/A
OUTPUT 4.2.	Primary Indicator 4.2.a.
Specific regulations for governmental and private sector investments on sustainable infrastructure projects.	Number of laws / regulations / amendments / policies recommended	1	Recommendations are to be discussed with Ministry of Economy and CVM.
OUTPUT 5.1.	Primary Indicator 5.1.a.
Capacity building of BDBs on ESG Methodology and capital market tools	% Attendance in workshops (online or face-to-face) according to the Capacity Building Plan, considering targeted number and attendees profiles	N/A	N/A
	Primary Indicator 5.1.b.
	Number of positive feedback from engaged participants (participants indicating "excellent" or "good" on a 5 point scale)	N/A	N/A
OUTPUT 5.2.	Primary Indicator 5.2.a.
ESG application on pilot projects with performance metrics evaluation, in addition to project reports during one-year implementation support	% of achievement of relevant ESG criteria by projects	N/A	N/A
OUTPUT 6.1.	Primary Indicator 6.1.a.
Capacity building of key public entities on ESG Methodology	% Attendance in workshops (online or face-to-face) according to the Capacity Building Plan, considering targeted number and attendees profiles	N/A	N/A
	Primary Indicator 6.1.b.
	Number of positive feedback from engaged participants (participants indicating "excellent" or "good" on a 5 point scale)	N/A	N/A
OUTPUT 7.1.	Primary Indicator 7.1.a.
Standardised monitoring tools and indicators for assessing sustainable infrastructure project impacts and creation of financing and de-risking mechanisms	Number of stakeholders (organisations) who receive information on the financing and de-risk mechanisms and monitoring tools	N/A	N/A
	Primary Indicator 7.1.b.
	% of positive feedback from engaged international stakeholders (participants indicating "excellent" or "good" on a 5 point scale)	N/A	N/A
	Secondary benefit indicator 7.1.a.
	Number of international stakeholders (organisations) who receive information on the financing and de-risk mechanisms and monitoring tools	N/A	N/A
	Secondary benefit indicator 7.1.b.
	% of positive feedback from engaged stakeholders (participants indicating "excellent" or "good" on a 5 point scale)	N/A	N/A
OUTPUT 7.2.	Primary Indicator 7.2.a.
Validated mechanisms	Number of mechanisms tested by the Delivery Team in the two Pilot Projects	N/A	N/A
OUTPUT 8.1.	Primary Indicator 8.1.a.
Case studies of the pilot projects, which demonstrate climate and social impact, are disclosed to investors and project developers	Number of case studies developed	N/A	N/A
	Primary Indicator 8.1.b.
	[Energy] Number of jobs generated for low income communities by pilot projects	N/A	N/A
	Primary Indicator 8.1.c.
	[Sanitation] Proportion of low income people served by the pilot project (lowest income quintile)	N/A	N/A
OUTPUT 9.1.	Primary Indicator 9.1.a.
Promotion and outreach of ESG Methodology and Green Finance to key stakeholders including investors and financiers, broader range of public entities, project developers and planners and granters	% Attendance in events/meetings (online or face-to-face) according to the Promotion & Outreach Plan	N/A	N/A
	Primary Indicator 9.1.b.
	Number of positive feedback from engaged participants in Promotion & Outreach activities (participants indicating "excellent" or "good" on a 5 point scale)	N/A	N/A
OUTPUT 9.2.	Primary Indicator 9.2.a.
Mobilisation of institutions, companies and public entities on the importance and advantages of green finance, as well as its international best practices	Number of institutions, companies and public entities participating in workshops, training events, seminars, conferences etc. (online or face-to-face)	20	The activity related to this indicator is under review so there might be a slight change on the milestone date, however, the main indicator will continue the same.
	Primary Indicator 9.2.b.
	% of positive feedback from engaged institutions (participants indicating "excellent" or "good" on a 5 point scale)	70%	The activity related to this indicator is under review so there might be a slight change on the milestone date, however, the main indicator will continue the same.
	Secondary benefit indicator 9.2.a.
	Number of international institutions, companies and public entities participating in workshops, training events, seminars, conferences etc. (online or face-to-face)	5	The activity related to this indicator is under review so there might be a slight change on the milestone date, however, the main indicator will continue the same.
OUTPUT 10.1.	Primary Indicator 10.1.a.
Provision of means and mechanisms by which the UK and international financial institutions and service providers can gain a better understanding of the investment environment for Brazilian Sustainable Infrastructure	Number of engagements (online or face-to-face) conducted between BDBs and international entities	3 engagements	This activity is progressing as expected and those engagements are foreseen to happen in the next couple of months. The March 2021 milestone still feasible.
	Primary Indicator 10.1.b.
	Number of institutions in key engagements (online or face-to-face) between BDBs and international entities	5	This activity is progressing as expected and those engagements are foreseen to happen in the next couple of months. The March 2021 milestone still feasible.
	Primary Indicator 10.1.c.
	International market assessment that assesses the Brazilian green finance sector compared with the international offer	1	The international market assessment is being elaborated and still on time to be delivered by March 2021 as expected.
	Primary Indicator 10.1.d.
	Evidence of report outputs used in engagement events	N/A	N/A
	Secondary Indicator 10.1.a.
	Number of engagements (online or face-to-face) conducted between BDBs and international entities.	3 engagements	This activity is progressing as expected and those engagements are foreseen to happen in the next couple of months. The March 2021 milestone still feasible.
	Secondary benefit indicator 10.1.b.
	Number of international institutions engaged in GFP webinars or events/workshops.	5	This activity is progressing as expected and those engagements are foreseen to happen in the next couple of months. The March 2021 milestone still feasible.
	Secondary benefit indicator 10.1.c.
	% of positive feedback from engaged institutions (participants indicating "excellent" or "good" on a 5 point scale)	70%	Once the events were realized the survey will be sent to all participants. The March 2021 milestone still feasible.
OUTPUT 10.2.	Primary Indicator 10.2.a.
ESG framework methodology for the Brazilian Development Banks is considered broadly aligned to UK and International investor interests	Number of organisations engaged that consider the ESG framework methodology is broadly aligned to their interests	N/A	N/A
	Secondary Indicator 10.2.a.
	Number of international organisations engaged that consider the ESG framework methodology is broadly aligned to their interests	N/A	N/A
OUTPUT 11.1.	Primary Indicator 11.1.a.
Online platform with operational project pipeline (with constant updates) and match-making functionalities	Number of sustainable projects included in the online platform.	N/A	N/A
OUTPUT 11.2.	Primary Indicator 11.2.a.
Information about Brazilian infrastructure market included in the platform, with offered dedicated support to interested entities	Number of Brazilian entities seeking support.	N/A	N/A
	Secondary benefit indicator 11.2.a.
	Number of international entities seeking support.	N/A	N/A
OUTPUT 11.3.	Primary Indicator 11.3.a.
Online platform is disseminated among relevant international investors and service providers	Number of Brazilian investors, financiers and project developers enrolled in the online platform.	N/A	N/A
	Primary Indicator 11.3.b.
	Number of accesses in the online platform.	N/A	N/A
	Secondary benefit indicator 11.3.a.
	Number of international investors, financiers and project developers registered in the online platform.	N/A	N/A
	Secondary benefit indicator 11.3.b.
	Number of accesses from international institutions.	N/A	N/A
OUTPUT 12.1	Primary Indicator 12.1.a.
Financial institutions engaged in actions and awareness events to discuss current gender equity context, how to accelerate opportunities for young women and disclose the WIF initiative	Number of institutions, companies and public entities participating in events (online or face-to-face) related to gender equity, young women empowerment discussions and WIF agenda	10	The contact with the key partner to develop the WIF is ongoing, so this event might happen by beginning of 2021, keeping the March 2021 milestone feasible.
OUTPUT 13.1	Primary Indicator 13.1.a.
Support WIF implementation and established initiatives for young women’s empowerment through engagement with potential partners, forging strategic alliances, designing of a specific governance structure and delivery of WIF commitment and launch framework	Number of institutions engaged in partnering with BGFP and delivering WIF initiative.	2	These institution willl be invited to partner with WIF initiative once the key partner has been defined. Anyhow, the expected milestone still feasible.
	Primary Indicator 13.1.b.
	Number of institutions engaged in partnering with BGFP to support young women empowerment through established initiatives	N/A	N/A
OUTPUT 14.1	Primary Indicator 14.1.a.
Assess Target Institutions (BDBs and selected FIs) G&I initiatives and gaps and report G&I considerations and findings to feed into the G&I development framework	Number of gender institutional assessments conducted.	2	1 (50%) - BNDES Waiting the MoU to be signed with Caixa to conduct the gender institutional assessment.
OUTPUT 15.1	Primary Indicator 15.1.a.
Collaborative G&I development framework to conduct capacity building aligned to Target Institutions (BDBs and selected FIs) needs and provide technical support. Capacity-building and technical support are considered: monitoring and orientation on G&I aspects and technical content, documents and policies revision and validation to implement agreed gender equity actions. It will not be in the scope: creation of any material or deliverables execution.	Number of capacity-building sessions provided.	N/A	N/A
	Primary Indicator 15.1.b.
	Number of technical support provided.	N/A	N/A
	Primary Indicator 15.1.c.
	Number of positive feedback from engaged institutions (institutions indicating "excellent" or "good" on a 5 point scale).	N/A	N/A
OUTPUT 16.1	Primary Indicator 16.1.a.
Develop climate change risk assessment scorecards for use in BNDES risk assessment processes	Incorporate key climate change transition risks into existing risk assessment scorecards utilised at BNDES, based on agreed prioritised exposures.	N/A	N/A
OUTPUT 17.1	Primary Indicator 17.1.a.
High quality input into BNDES GCF proposal	Carbon Trust deliver high quality drafting, to the satisfaction of BNDES, for all agreed sections of the GCF proposal.	All sections delivered	The GCF workstream is currently in a redefinition point, so the expectative to delivery all agreed section by March 2021 are uncertain, this milestone shall be reviewed depending on BNDES' response.

# ANNEX V – TRADE FACILITATION INDICATORS

OUTPUT	INDICATOR	YEAR 1 MILESTONE	STATUS (NOV 2020)
MSME Component / Enhanced capability, opportunity and motivation of MSME actors (including under-represented women/black-owned/led MSMEs) through pilots aimed at providing MSME support, market access interventions, and improving the broader MSME ecosystem through systemic interventions.	Governance - Trade Hub Steering Committee (THSC) is operational and effectively oversees piloting of interventions and capacity building	MSME Services - THSC oversees pilot interventions MSME Services - THSC agree on the design of pilots for Y2 Systems - THSC agree on Trade Hub Digital Platform design	On Track to Meet Expectation (A)
	MSME Services - Number of pilots resulting in new or improved MSME trade-related services	3 pilots launched	On Track to Meet Expectation (A)
	MSME Services - Number of Brazilian MSMEs benefitting through direct engagement with the programme (Cumulative)	565	On Track to Exceed Expectation (A+)
	Systems - Trade Hub Digital Platform (i.e. the 'wardrobe') successfully designed, tested and launched	Digital platform design drafted	On Track to Exceed Expectation (A+)
	Systems - Number of new or improved services developed by the programme incorporated (i.e. as 'hangers') into the Trade Hub Digital Platform (i.e. 'wardrobe')	-	On Track to Meet Expectation (A)
	Across all aspects of MSME component G&I Mainstreaming is carried out and PF G&I Framework is adopted	All pilots successfully achieve G&I mainstreaming and PF G&I minimum compliance 2 PF G&I Empowerment or Transformation activities* undertaken.	On Track to Exceed Expectation (A+)
2. Ports Component – Demonstrable engagement of key port community actors, formalisation of port community governance structures, diagnosis of port systems and potential efficiency savings, and solutions scoped and supporting PCS IT systems.	Port actors integrated into port community governance structures and benefitting through direct engagement with the programme	Actors of 4 ports participate in additional capacity building workshops	On Track to Meet Expectation (A)
	Port processes mapped through diagnostic activities and technical advice provided to the port community	"As-Is" and "To-be" Processes Mapped in 2 target ports for 3 services/functionalities and 2 services /functionalities for additional 2 ports	On Track to Meet Expectation (A)
	PCS IT system and constituent modules designed and piloted in the Port of Santos	Functional and non-functional specifications developed for Santos PCS IT system	On Track to Meet Expectation (A)
	Across all aspects of Ports component G&I mainstreaming is carried out and PF G&I Framework is adopted	All activities successfully achieve G&I mainstreaming and PF G&I minimum compliance 1 PF G&I Empowerment or Transformation activities* undertaken.	On Track to Exceed Expectation (A+)
3. Learning and adaptation - Demonstrable evidence that the programme is learning and adapting to deliver the greatest chance of delivering impact and strong VFM	Number of pilots adapted (scaled-up, scaled-down, closed-out) or pivoted based on insights generated by the programme’s MREL system	MSME - 3 pilots adapted or pivoted	On Track to Meet Expectation (A)
	Number of research/analytic/content pieces produced that (a) enhance the existing export/trade evidence-base, (b) highlight G&I aspects, and (c) feed into future interventions aimed at enhancing MSME participation in global value chains or efficiencies in the 4 target ports	2	On Track to Exceed Expectation (A+)