COLOMBIA PROSPERITY FUND PROGRAMME
EVALUATION REPORT 2021 (CYCLE 2)
February 2021
Version history
D03_04	Prosperity Fund Colombia programme Cycle 2 Evaluation Report
Revision	Written by	Checked by	Approved by
Revision 0	Jennifer Butz, Clarissa Samson, Ulrike Hotopp, Liisa Kytola, Bibiana Sáenz	Stephen Spratt
Revision 1	Jennifer Butz, Clarissa Samson	Colombia Programme team
Revision 2	Jennifer Butz, Clarissa Samson	Dulce Pedroso
Revision 3	Jennifer Butz

Table of acronyms
Abbreviation
AR	Annual Review
CAF	Banco de Desarrollo de América Latina (Development Bank of Latin America)
CONPES	Consejo Nacional de Política Económica y Social (National Council for Political Economy and Social)
COVID-19	2019-nCoV acute respiratory disease
CSO	Civil society organisation
DFID	Department for International Development (UK)
DIT	Department for International Trade (UK)
EL	Evaluation and Learning
EQ	Evaluation question
FCO	Foreign and Commonwealth Office (UK) until 1 September 2020
FCDO	Foreign, Commonwealth and Development Office (UK)
FDN	Financiera de Desarrollo Nacional (National Development Financing)
G&I	Gender and inclusion
HMA	Her Majesty’s Ambassador
IP	Implementing partner
IUK	Innovate UK
JFU	Joint Funds Unit
KII	Key informant interview
MoU	Memorandum of Understanding
MR	Monitoring and reporting
MREL	Monitoring, reporting, evaluation and learning
NCE	No-cost extension
OCDS	Open Contracting Data Standards
OCP	Open Contracting Partnership
ODA	Official development assistance
ODI	Outward direct investment
OECD	Organisation for Economic Co-operation and Development
PEL	Programme evaluation lead
PF	Prosperity Fund
PFDU	Prosperity Fund Delivery Unit
PT	Programme team (in Colombia)
SB	Secondary benefit
SDA	Social Development Advisor
SDG	Sustainable Development Goal
SECOP	Sistema Electrónico de Compras Públicas (Electronic System for Public Procurement)
SIGRA	Gestión de Riesgos Agropecuarios (Agricultural Risk Management)
SMART	Specific, Measureable, Achievable, Relevant, Timely
SRO	Senior Responsible Owner
ToC	Theory of Change
ToR	Terms of Reference
VfM	Value for Money

Contents

Tables
Table 1: Limitations to Cycle 2 evaluation and their mitigation	7
Table 2: Colombia programme ToC score	10
Table 3: G&I scorecard summary findings	11
Table 4: VfM score for Colombia programme	16
Table 5: RAG rating of evidence and strength of contribution	20
Table 6: Digital application LISTO – summary of contribution analysis	22
Table 7: Irrigation management – summary of contribution analysis	23
Table 8: Open procurement – summary of contribution analysis	25
Table 9: Addressing PT’s Cycle 2 learning objectives	30
Table 10: Cycle 2 priority recommendations	32
Table 11: List of key informants	2
Table 12: Cycle 2 Bibliography	5
Table 13: Cycle 2 illustrative interview guide	16
Table 14: Aligning the PF with Colombia's national priorities	18
Table 15: ToC assessment	21
Table 16: Colombia programme and project summary	26
Table 17: Strength of data score criteria	30
Table 18: Colombia programme summary findings against evaluation questions	30
Table 19: Prosperity Fund gender and inclusion scorecard	57
Table 20: Programme-level G&I scorecard assessment summary	58
Table 21: Agritech G&I scorecard assessment ratings	63
Table 22: Sampling of agritech projects	63
Table 23: Infrastructure strand G&I scorecard assessment ratings	69
Table 24: Sampling of urban development and rail rehabilitation infrastructure projects	69
Table 25: Institutional strengthening strand G&I scorecard assessment ratings	73
Table 26: Sampling of institutional strengthening projects	74
Table 27: G&I recommendations	78
Table 28: Value for Money scoring system	80
Table 29: VfM comparative scoring	81
Table 30: Programme-level VfM scorecard	87
Table 31: Innovations in the Colombia programme	99
Table 32: Summary of sampled results	105
Table 33: RAG rating of evidence and strength of contribution	106
Table 34: User indicators of LISTO app (table adapted from supplier final report, January 2021)	111
Table 35: Evidence items, analysis of strength and support for claim	112
Table 36: Evidence showing the contribution of other factors to results identified	113
Table 37: Barriers to programme achievement of outcome-level results	113
Table 38: Items of evidence demonstrating contribution of programme to identified result	118
Table 39: Evidence and testing that evidence	119
Table 40: Factors hindering change and achievement of outcome	119
Table 41: Evidence and testing of evidence	124
Table 42: Evidence and testing of evidence	125
Table 43: Cycle 1 recommendations and actions taken	128
Table 44: Cycle 2 full recommendations	129

Figures
Figure 1: Colombia Prosperity Fund programme regional coverage	5
Figure 2: Fund-level Theory of Change	9
Figure 3: Digital application – causal pathway of result claimed	21
Figure 4: Irrigation management – causal pathways to result claimed	23
Figure 5: Open procurement – causal pathway to result claimed	25
Figure 6: Colombia’s umbrella ToC	20
Figure 7: Secondary benefit by type	93
Figure 8: Secondary benefit by sector	97
Figure 9: Products available on LISTO trading platform	107
Figure 10: Causal pathways	108
Figure 11: Causal pathway of change to result	115
Figure 12: Causal pathways of change to result	121
Figure 13: Alignment of results achieved with programme outcomes and impact	127

BOXES
Box 1: Head of the Prosperity Fund Colombia Programme endorsement for the Cycle 2 evaluation report	2
Box 2: COVID-19 impact in Colombia	3
Box 3: Selected G&I results by strands	62
Box 4: Selected agritech project G&I results	68
Box 5: Selected G&I results from infrastructure strand	73
Box 6: Beneficiary takes G&I action	77
Box 7: Selected G&I results from institutional strengthening strand	78
Box 8: Infrastructure strand example of VfM measure	82
Box 9: Risk management	85
Box 10: Farming Data – soft power and ODI	96
Box 11: ToR from Private Sector Advisory Panel	96
# Executive summary
Brief overview / The design of the programme is sound and aligns well with both Colombia’s National Development Plan and the Prosperity Fund’s objectives. / The programme has strengthened its potential to improve the lives of women and girls and promote social inclusion, although monitoring and reporting of this needs to be improved. / The programme is delivering verified results with selected intermediate outcome such as improved yields, better prices and expanded markets for smallholder farmers and improvements in public procurement processes at the subnational level. / Innovations drive progress on both primary purpose results and secondary benefits. For example, an application to connect farmers with buyers has expanded access to markets – a primary purpose – and resulted in the British application developer establishing a presence in Colombia. / The programme has delivered secondary benefits for UK firms in five of the six types of secondary benefits envisioned by the Prosperity Fund.

What is the Colombia Prosperity Fund Programme?
The Colombia Bilateral Programme: Unlocking Economic Opportunities in Colombia’s Post-Conflict and Conflict-Affected Regions is a GBP 25.5 million five-year initiative that started in 2017. Through three strands – agriculture, infrastructure and institutional strengthening – the programme’s primary purpose is to support economic development, unlock economic opportunities and drive growth in post-conflict and conflict-affected regions. The programme seeks to benefit about three million people with a focus on women and girls in Colombia’s poorest regions. Its long-term goal is to generate more inclusive economic growth equal to GBP 1.99 billion over 10 years and to deliver secondary benefits of commercial value of an estimated GBP 265 million by 2026.[1]
[1] Colombia bilateral programme business case, 28 August 2018.
What did the evaluation look at?
The Cycle 2 (2019/20) evaluation was carried out from October 2020 to February 2021. The programme began implementing its projects in 2018 and is beginning to generate results at the intermediate outcome level. The scope of the evaluation reflects this and focuses on whether the programme’s structures and the ways in which it engages with stakeholders are likely to optimise future results.
In April 2020, the Programme team and the Evaluation and Learning team conducted a one-day virtual workshop to establish the six objectives of this evaluation. These are:
- Provide SMART recommendations to match ambition with time availability and support a strategic response to challenges and opportunities related to COVID-19.
- Provide insights to enable the Colombia Programme team to understand where it fits within the Prosperity Fund network and how to strengthen further its alignment with Fund objectives.
- Support the Programme team to gain a more strategic view of challenges, early wins and long-term needs.
- Identify gaps and opportunities to mainstream gender and inclusion through presenting findings which strengthen programme, strand and activity incorporation of gender and inclusion.
- Contribute to Colombia’s 2020 Annual Review by providing the Programme team with preliminary findings from the Cycle 2 evaluation following the data collection phase.[2]
  [2] The delay in approving the evaluation start date meant that the Evaluation and Learning team was only able to provide early observations to the programme team before the AR process concluded on 27 November 2020.
- Assess contribution claims of selected results by using contribution analysis.[3]
  [3] This Cycle 2 evaluation report for Colombia represents the first use of contribution analysis for a PF programme. Lessons learned in applying this methodology will be shared with EL teams throughout the network.
The main audiences of the evaluation are Her Majesty’s Ambassador to Colombia (the Senior Responsible Owner), the Colombia bilateral Programme team, other embassy section teams, the 2020 Annual Review team, the Joint Funds Unit and the Prosperity Fund Delivery Unit. The findings will also inform other teams and stakeholders across the Prosperity Fund and the overall Fund evaluation report.
Sources for the evaluation include programme documents, secondary information including Colombian government policy documents and 68 interviews conducted in November and December 2020. The Foreign, Commonwealth and Development Office’s Evaluation Quality Assurance and Learning Services quality assured this evaluation. The views expressed are those of the independent evaluation team.
What did the evaluation find?
Design: Early challenges with implementing partners’ function and performance are resolved and delivery is progressing. The Programme team has resolved the challenges to programme delivery that emerged from assumptions it had made about the capacity, focus and alignment of the various implementing partners.
Potential to achieve primary purpose: The programme is delivering results and, in some cases, intermediate outcomes. Evidence shows that the programme is ambitious and likely to contribute to the majority of its intermediate outcomes and selected outcomes, despite challenges faced in 2020, including COVID-19. Although the Colombia bilateral programme did not face reductions in financial year 2020/21 due to changes in official development assistance, there is an outstanding funding issue related to payment schedules with implementing partners which is delaying the launch of nine of Colombia’s 34 planned projects. The programme’s three strands are delivering results at different rates due to the complexity of infrastructure and the longer time periods required for policy and institutional change.
- Agriculture: Early project activities delivered output and, in some cases, intermediate outcome results despite travel and freight restrictions. The seven agritech projects are proof-of-concept projects designed to introduce and apply UK innovations to smallholder producers of nationally important crops, including coffee, chocolate, bananas and tilapia. These projects have been most impacted by COVID-19. Six of seven projects received no-cost extensions, but the extended duration of the pandemic may put at risk scaling and replication, on which higher levels of results depend.
- Infrastructure: There has been some progress in this strand even though the urban development and rail rehabilitation activities are complex and need additional time to demonstrate feasibility. Selected projects, such as the redesign of transport systems in Manizales and a Smart City redevelopment plan for the historic centre in Santa Marta, however, have shown progress in unlocking economic opportunities through improved urban systems, as well as gains in gender and inclusion considerations in these systems. The rail rehabilitation projects are likely to support more inclusive economic growth, but have not yet advanced sufficiently to demonstrate actual results.
- Institutional strengthening: The strand’s regional competitiveness activity faced early delays due to implementing partner practices and changes in subnational administrations. The Programme team and delivery partners have addressed these challenges and four of the six projects are underway. The work on open public procurement and corporate governance reform in the National Infrastructure Agency are yielding advances related to gender and social inclusion protocols, as well as building greater capacity and demand for public oversight of procurement at the national, department and municipal levels. These projects are beginning to generate intermediate outcome-level results such as increased openness in public procurement in selected departments.
Gender and inclusion: The Colombia programme meets the Prosperity Fund’s gender and inclusion minimum standards, with one strand, infrastructure, exceeding requirements. The programme leadership has championed gender and inclusion from the start. Promoting gender equality and social inclusion are core objectives of the Colombia programme and visible in the way the programme has planned, resourced and implemented its activities. The Programme team continues to build its internal gender and inclusion capacity and to adapt based on learning from projects. It is also building the capacity of delivery partners and stakeholders to understand what gender and inclusion means in practice. The team has set relevant requirements for all activities to engage with end beneficiaries, specifically women and members of other excluded groups, throughout each project’s cycle. However, the monitoring and reporting systems used could be improved and more directly tied to the results defined in the programme’s results frameworks.
Value for Money: The Colombia programme has a score of adequate in the Value for Money scorecard; the Evaluation and Learning team sees this score rising to good in the programme’s direction of travel. The Programme team uses its logframe indicators to monitor progress and steer delivery. However, implementing partners have their own processes and procedures which do not always align with those of the Fund. The Programme team makes use of cost containment measures, including memoranda of understanding with implementing partners, to monitor quality and costs. Inefficient tender and contract administration, and the need to change internal rules in one case, caused risks to programme delivery, now resolved. The strands’ causal pathways are valid and show the likelihood of delivering primary purpose and secondary benefits. The programme enables actors and systems to perform with new skills and capabilities which support the sustainability of Prosperity Fund programme outcomes. The Programme team demonstrates strong learning, adaptability and decisive action to address risks. There is clear evidence that it has had a positive impact on the understanding of and need for gender and inclusion as part of project design and delivery.
Secondary benefits: There is evidence of an interlinkage between delivery of primary purpose and secondary benefits. The Colombia PF programme delivered 13 commercial and six soft power secondary benefits by December 2020. These cover five of the six types envisioned by the Prosperity Fund, including outward direct investment and market access (including imports). The Secondary Benefits Advisor establishes and grows relationships with companies to deliver secondary benefits. However, the Programme team is clear that these are always secondary to primary purpose. The Evaluation and Learning team identified both internal and external barriers which, if resolved, could further strengthen the delivery of secondary benefits.
Results and contribution: The Evaluation and Learning team used contribution analysis to confirm the level of contribution the Prosperity Fund has made to selected results. These include:
- Result 1: Users of Farming Data’s ‘LISTO’ app have increased accessibility to markets through real-time agricultural information. The platform increases market transparency and helps farmers avoid exploitation by middlemen, which improves connections with buyers. This has been shown to achieve higher sale prices, positively affecting household incomes and the wider rural economy.
- Result 2: Irrigation management services enabled banana growers to improve management of limited water resources. Growers in the post-conflict region of Magdalena now have access to real-time soil moisture and climate data to support irrigation management during dry seasons. Farmers rely on digital services to make more efficient use of scarce water resources and reduce potential negative environmental impacts from field run-off into local river systems.
- Result 3: Improved public procurement processes at the regional government level through increased transparency and accessibility of procurement data. Data use and analysis presented in newly created public procurement information platforms has also led to better promotion of tender opportunities relevant to suppliers, stimulating greater competition to mitigate risks of corruption.
Learning: The lessons from this evaluation show that the programme could be strengthened through:
- Ensuring complete alignment across contracts and reporting mechanisms by standardising reporting formats and content.
- Reinforcing lines of communication from the Programme team through to direct beneficiaries to ensure that the layers of programme management deliver desired messages, principles and information.
- Sharing lessons and insights across implementing partners and suppliers by periodically convening thematic sessions to explore lessons and best practices.
Lessons were also identified for the broader Prosperity Fund network. The Colombia programme has leveraged its application of innovations to deliver primary goals and secondary benefits. The project partners engage end users early in the design process and continue that connection throughout. The Programme team and the delivery partners have demonstrated an appropriate capacity for adaptation which has supported project progress towards goals. And finally, the evaluation shows that when addressing urgent issues in the Colombia context, there is a greater concentration and focus of stakeholders which generates momentum for the project and its results.
Recommendations: In addition to the learning above, seven priority recommendations were co-created which, when addressed, will strengthen the delivery, monitoring and reporting on project progress and enable the Programme team to better strategise programme implementation in the coming year. In brief these are:
- Ensure complete alignment across Memoranda of Understanding, contracts and reporting mechanisms.
- Review communication lines from the Programme team to implementing partners to suppliers to direct beneficiaries to ensure that the layers of programme management harmonise and reinforce desired messages and principles.
- Consider sharing lessons and insights with implementing partners and suppliers by periodically convening thematic sessions to explore lessons and best practices.
- Assess project status 6–12 months before conclusion to create project sustainability plans.
- Review the Theory of Change and logframes (intermediate outcomes, gender and inclusion level of ambition, Value for Money indicators, nesting/structure, assumptions) to ensure these frameworks are strong tools.
- Evaluate the Value for Money scorecard to optimise all aspects of Colombia programming.
- Undertake actions which will enable the Prosperity Fund to translate the positioning for secondary benefits into actual wins.

The Prosperity Fund is a UK government initiative supporting inclusive economic growth in partner countries through a GBP 1.2 billion portfolio of programmes over seven years. The Fund’s activities will contribute to achieving the UN Sustainable Development Goals, while creating opportunities for international businesses as a secondary benefit. / Scrutiny of the Fund’s work is undertaken by the Prosperity Fund Evaluation and Learning service, led by Tetra Tech International Development, in partnership with NIRAS-LTS International and Integrity. Evaluations take place annually at programme and Fund levels and aim to identify learning for programmes, thematic issues and sectors. This is the second evaluation of the Colombia programme.

# Introduction
## Purpose and scope of the evaluation
This is the second annual evaluation (Cycle 2) of the Prosperity Fund (PF) Colombia Bilateral Programme: Unlocking Economic Opportunities in Colombia’s Post-Conflict and Conflict-Affected Regions (the Colombia programme hereafter). The Programme team (PT) identified the objectives for Cycle 2 in a one-day virtual planning workshop facilitated by the Evaluation and Learning (EL) team on 8 April 2020 just as COVID-19 restrictions were put in place in Colombia and around the world. The PT identified the following objectives:
1. Provide SMART recommendations to match ambition with time availability, and support a strategic response to challenges and opportunities related to COVID-19.
2. Provide insights to enable the Colombia PT to align itself with the overall PF network and objectives, assisting Colombia’s understanding of where and how it fits within the Fund.[4]
  [4] This comparative analysis will be briefly assessed in the evaluation report, and further supported through engagement with relevant sector leads throughout the evaluation process. The Colombia team has expressed interest in a regional (that is, Latin American) comparative assessment.
3. Support the PT to gain a more strategic, informed view of challenges, early wins and long-term needs.
4. Identify gaps and opportunities to mainstream G&I through presenting findings which strengthen programme, strand and activity incorporation of G&I.
5. Contribute to Colombia’s 2020 Annual Review (AR) by providing the PT with preliminary findings from the Cycle 2 evaluation following the data collection phase.[5]
  [5] The delay in approving the evaluation start date meant that the Evaluation and Learning (EL) team was only able to provide early observations to the programme team before the AR process concluded on 27 November 2020.
6. Assess contribution claims of selected results by using contribution analysis.[6]
  [6] This Cycle 2 evaluation report for Colombia represents the first use of contribution analysis for a PF programme. Lessons learned in applying this methodology will be shared with EL teams throughout the network.
In the planning workshop, the PT opted for a landscape evaluation. This broad assessment includes evaluating the 11 evaluation questions (EQs) of the PF together with the scorecards for gender and inclusion (G&I) and Value for Money (VfM), the secondary benefit (SB) assessment methods, and the Theory of Change (ToC) checklist.
Although 2020 brought unforeseen challenges, the evaluation objectives remained unchanged, with the exception of adding the sixth objective of contribution analysis. (See Section 5 for findings of the Cycle 2 learning objectives.) Further guidance related to evaluating a programme’s response to COVID-19 and the reprioritisation of the UK’s official development assistance (ODA) was received in October and reframed the EL team’s approach to the first evaluation objective.
## Audience and stakeholders
The primary audience for this evaluation is the Senior Responsible Owner (SRO) and the PT, as they seek to strengthen the existing good practices and identify methods to correct weaknesses. This is particularly important due to the internal leadership changes of the Colombia programme as well as the challenges associated with the national and international programming environment in 2020. Other stakeholders include:
- the Joint Funds Unit (JFU) and Prosperity Fund Delivery Unit (PFDU).
- the Department of International Trade (DIT) and other teams at post in Colombia.[7]
  [7] These include the PF global programmes (Global Infrastructure, Better Health and Global Trade), the International Climate Fund, the Newton Fund and other initiatives of the Foreign, Commonwealth and Development Office run by the Embassy.
- other PF programmes as they may benefit from this comparatively early Cycle 2 evaluation.
- other stakeholders who seek to understand the progress being made in Colombia and the VfM that this taxpayer investment represents.
The PT has been engaged throughout the process of this evaluation as detailed in the Colombia programme Cycle 2 Approach Paper.[8] It shaped the evaluation in the April 2020 planning workshop, provided documents and identified stakeholders for interview, while PT members made themselves available for interviews, commented on early drafts and co-created the recommendations during a findings and recommendations workshop in January 2021. In accordance with the PF’s publication policy, the PT is responsible for disseminating this evaluation report, for which the EL team will provide support.
[8] The Cycle 2 Approach Paper was an update of the more fulsome Cycle 1 Approach Paper as per the JFU’s instructions to EL. See Annex 1.
Box 1: Head of the Prosperity Fund Colombia Programme endorsement for the Cycle 2 evaluation report
“The Cycle 2 evaluation could not come at a more opportune time. As we enter the last year of implementation for the Colombia programme, the insights provided by the EL team give us a solid basis to progress with the programme, making some important modifications to ensure effective delivery of results. The EL products are comprehensive in their scope to reflect the totality of the programme, and the level of analysis is also deep, demonstrating the detailed understanding that the EL team has of the programme. The recommendations made are accurate and will be extremely helpful as we continue our implementation. We are proud to be the beneficiary of the first contribution analysis in the entire Prosperity Fund, and we have enjoyed the collaborative approach that the EL team has taken to ensure that the Colombia programme’s results are well captured in this evaluation.”
Head of PF Colombia Programme

## Report structure
The rest of this report is structured as follows:
- Section 2 provides context through an overview of the Colombia programme and highlights the external influences on the Colombia Prosperity Programme since the Cycle 1 evaluation.
- Section 3 summarises the approach and methodology for the evaluation, including limitations.
- Section 4 provides findings on a range of issues, including the uptake of Cycle 1 recommendations, learning since Cycle 1, ToC assessment, G&I, VfM, SBs, results and contribution towards primary purpose, governance and management and risks.
- Section 5 links the learning objectives identified by the PT with the analysis and findings made by the EL team. It also offers lessons for wider PF learning.
- Section 6 presents the priority recommendations co-created in January by the PT and EL team.

# Context
This section summarises key elements of the political and economic landscape in which the programme is being implemented. It aims to provide context for the following discussion of programme delivery issues rather than give a full analysis in its own right.
## Country context
This section highlights the external influences on the Colombia programme since the Cycle 1 evaluation. The greatest external influence has been the COVID-19 pandemic and its impact on official priorities and attention at the national, department and municipal levels which represent the greatest number of programme stakeholders and delivery partners. Yet, in some cases, the COVID-19 environment created greater relevance and uptake of the Colombia PF projects.
### COVID-19
Colombia closed its borders between March and September 2020 to all but essential travel and freight. Internal travel was also prohibited until September which led to a steep economic drop and rising rates of inequality which, in some cases, led to public protests. Early assessments from government, civil society and international agencies uniformly note that the impact of COVID-19 has been more severe on vulnerable populations and especially women and girls (see Box 2). The PT notes that its business case expectation that “the introduction of UK innovations would have a significant (10–15 per cent increase) on the lives of beneficiaries” is no longer likely to be true due to the unprecedented economic downturn. Nevertheless, evidence indicates that the PF interventions will contribute to improving the lives of beneficiaries as presented in Section 4.7 Selected results and contribution towards primary purposes.
Following a presidential recovery plan issued in July, the government of President Ivan Duque released a comprehensive plan through the National Council for Political Economy and Social (CONPES) in September for public comment.[9] The CONPES plan supports job creation, infrastructure and other PF priorities.
[9] The public comment period concluded in November. CONPES has yet to release the final official plan.
In the embassy, Her Majesty’s Ambassador (HMA)/SRO reassigned the PT members temporarily from their PF roles to support consular activities in assisting thousands of British nationals to repatriate from Colombia.[10] The SRO also tasked the Head of the PF to convene section heads to promote a cross-post dialogue on ideas and actions.[11]
[10] These reassignments ranged from 3 to 6 weeks for the PF team which meant that there was a temporary vacuum in the PF’s ability to react and adapt the PF programming.
[11] The PF coordinates most closely with the International Climate Fund, the Newton-Caldas Fund for research and innovation, and the Conflict, Stability and Security Fund. The 2020 Annual Review explored the current quality of coordination and made recommendations to improve this going forward.
Box 2: COVID-19 impact in Colombia
- Colombia had registered 192,345 COVID-19 cases and 50,187 deaths by 22 January 2021.[12]
  [12] www.coronatracker.com/country/colombia
- Between June 2019 and June 2020, employment fell by 27 per cent for women and 18 per cent for men. The two sectors most impacted by the crisis were: 1) public administration, defence, education and health care; and 2) artistic activities, entertainment, recreation and other service activities. In these sectors, the loss of employment for women was triple that for men. [13]
  [13] National Statistics Office of Colombia (2020) Report on the Statistics of Employment and Gender Gaps, page 2. www.dane.gov.co/files/investigaciones/boletines/ech/Informe-sobre-cifras-de-empleo-y-brechas-de-genero-10-2020.pdf
Evidence shows that all programme partners in Colombia felt that others could have done better with communications, clarity and focus – from suppliers to IPs to the PT to the JFU. For example, the PT acted on JFU guidance to develop COVID-19 responsive projects. Working with IPs and some suppliers, the PT developed and submitted six new project ideas, only to learn after that funds to support these would have to be found from existing resources.[14] This late-coming information left suppliers, IPs and the PT frustrated by having spent time and resources developing projects that could not be funded.
[14] One project between Imperial College London and the Colombian Ministry of Health on epidemiological modelling to support public health response to the COVID-19 pandemic in Colombia is being agreed; the second project related to a survey of COVID-19 impacts in rural Colombia was void during tender. The PT is now in discussions with the Ministry of Agriculture to identify appropriate uses of the funds to support shared and aligned goals.
For the projects already in delivery, the PT, IPs and suppliers demonstrated creativity and adaptability to maintain and even extend programme reach in spite of pandemic restrictions. These adaptations included new partnerships to sustain activities, changes in the modes used to engage stakeholders and beneficiaries, and adaptations in methodologies to connect with stakeholder sets in different, effective ways. For example, the open procurement project benefitted from public outrage against embezzlement by local officials in four administrations who diverted COVID-19 relief for their personal gain – propelling attention and support for open procurement as never before. In another example, the developers of an online market platform found greater relevance for their product when in-person agricultural markets closed and both sellers and buyers needed to find functional alternatives.
Economic contraction. UK’s ODA reprioritisation to align with its Addis Ababa Action Agenda pledge in June 2020 did not impact the bilateral Colombia programme. Its fiscal year (FY) 2020/21 baseline of GBP 4.8 million was agreed by both the First Secretary and the Prime Minister in July 2020. The UK government’s 2020 Spending Review in November has implications on when disbursements to IPs could be made, which is the ‘pre-payment issue’ referred to in this document. Project delivery depends on those pre-payments as IPs need the resources in advance to initiate contracting processes. Although the PT continues to make progress on project design, contracting has been postponed until the FY2021/22 budget is announced, which represents a ten-month delay. Evidence suggests that these extended delays reduce the likelihood of these projects being implemented, which would impact negatively the PT’s ability to meet its overall programme targets. This is particularly true for the complex rail rehabilitation and urban development projects on hold, which have the potential to impact the lives of millions of citizens through improved water and sanitation systems, better transport and integrated services.
According to many of those interviewed for this evaluation, Colombia’s national and subnational authorities have diverted their attention and their budgets to respond to COVID-related urgencies, including health and socio-economic challenges. There is evidence to show that as a result, there is less focus on or budgets for co-funding of PF projects. This may result in a reduced scope of programme replication or scaling. Also, there are fewer financial resources for contracts or commercial agreements which may impact SBs.
## Colombia Prosperity Fund programme
The PF Colombia programme is a GBP 25.5 million initiative that began implementing projects in 2018. The programme includes three strands which correspond to five sectors of the PF results framework.[15] The strands divide further into seven activities and 34 projects.
[15] These PF Fund-level sectors are infrastructure, human capital and innovation, trade, financial and economic reform, and transparency and anti-corruption.
- Agriculture: The seven Agritech Catalyst Challenge Fund projects are proof-of-concept projects designed to introduce and apply UK innovations to smallholder producers of nationally important crops, including coffee, chocolate, bananas, tilapia. These projects have been most impacted by the COVID-19 restrictions. However, early project activities delivered output and, in some cases, intermediate outcome results despite restrictions. Six of seven projects received no-cost extensions (NCEs), but the extended duration of the pandemic risks the scaling and replication on which higher levels of results depend.
- Infrastructure: The urban development and rail rehabilitation activities in this strand are complex and require additional time in feasibility as they result in designed and built infrastructure. Nevertheless, selected projects such as redesign of transport systems in Manizales or a Smart City redevelopment plan for the historic centre in Santa Marta have demonstrated progress in unlocking economic opportunities through improved urban systems and gains in G&I considerations in these systems. The rail rehabilitation projects are likely to support more inclusive economic growth, but have not yet advanced sufficiently to evaluate actual results.
- Institutional strengthening: The strand’s regional competitiveness activity faced early delays due to implementing partner (IP) practices and changes in local administrations. The PT and delivery partners addressed these challenges and now four of six projects are underway. The work on open procurement and reform in the National Infrastructure Agency is yielding advances related to gender and social inclusion protocols as well as building greater capacity and demand for public oversight of procurement at the national, department and municipal levels. These activities are beginning to yield intermediate outcome results such as increased openness in public procurement in selected departments.[16]
  [16] Departments are roughly equivalent to states and are the largest subnational administrations, followed by municipalities.
The programme management structure of the Colombia programme consists of:
- PT – SRO, Head and Deputy Head, advisors, support staff
- IPs – regional banks: Development Bank of Latin America (CAF), Findeter, Financiera de Desarrollo Nacional (FDN), Innovate UK (IUK), the International Center for Tropical Agriculture and the Open Contracting Partnership (OCP)
- Suppliers – delivery partners who competitively bid for projects
- Direct beneficiaries – government institutions at the municipal, subnational and national levels
- Final beneficiaries – Colombia’s citizens, farmers, entrepreneurs, civil society organisations (CSOs) and firms and individuals from the private sector
Evidence shows that the PF used a particular selection process to identify projects in each of the activities.[17] These selection criteria resulted in a suite of projects that tackle regional and socio-economic inequalities and promote inclusive economic growth that addresses Colombia’s multidimensional definitions of poverty. Figure 1 shows the programme’s geographical reach.
[17] The PT selected projects based on: “i) their ability to deliver growth and open new market opportunities including for the UK; ii) research indicating that these are important unmet needs that no other donor or agency is fully addressing; and iii) their fit with the PF Theory of Change (ToC)”. Colombia Business Case, August 2018, page 4.
Figure 1: Colombia Prosperity Fund programme regional coverage

# Approach
The EL team reviewed documents from all projects and activities, including memoranda of understanding (MoU), contracts and monthly and quarterly reports. The team supplemented its literature review by conducting key informant interviews (KIIs) with stakeholders from all seven activities and 83 per cent of the 23 active projects to generate findings and recommendations for the bilateral programme.[18]
[18] See Annex 2 List of key informants and Annex 8 Colombia programme’s project summary.
## Data collection and evaluation question sampling
Three broad types of evidence were assembled and reviewed for this evaluation:
- programme documents provided by the PT
- 68 KIIs,[19] including those with:
  [19] The PT provided a broad set of stakeholders to consider for interviewing. EL used that initial list to begin the KIIs and added to it as the evaluation required. EL took all measures to assure the anonymity and confidentiality of the interviewees and the views expressed during the KIIs. This included securing notes on a server not accessible by the PT and anonymous references in the report.
  - internal stakeholders at post including the SRO (the HMA); the current and former heads of the PF in Colombia; the current and former deputy heads of the PF in Colombia; the PT advisors;[20] the Head of DIT in Colombia; and the Head of the Economics, Science and Climate Department at the embassy in Bogotá
    [20] The PT changed both the Head and Deputy Head of the bilateral programme. Both former and current officers were included in KIIs.
  - delivery partners, including IPs, suppliers and direct beneficiaries
  - external stakeholders, including representatives from national and subnational authorities, international organisations, the private sector and final beneficiaries of the Colombia programme.
- secondary sources depending on the technical areas related to each strand.
EL coded the evidence against PF’s EQs using a qualitative data software called MAXQDA to ensure that insights and evidence were well managed and more easily traceable. This was especially useful as the EL team was unable to hold the in-person brainstorming and exchange that would ordinarily occur during an evaluation, particularly as the EL team members were located in four different countries.[21]
[21] EL team members were based in Colombia, Mexico, Canada and the UK.
### Evaluation questions
During the April 2020 planning workshop, the PT and EL reviewed the 12 EQs for the PF,[22] and opted for a landscape approach using nearly all of these. This approach provides the PT with a breadth of analysis and enables the PT to understand the programme from many different perspectives. Those EQs not prioritised have been addressed through the other methodologies used in this report.[23] The findings from all of these lines of inquiry are combined in this evaluation report.
[22] In the time between the April planning workshop and the final sign-off on the approach paper in October, the PF had adjusted the 12 EQs to 11. The evaluation matrix and EQ findings in Annex 9 reflect the revised EQ matrix.
[23] EL uses six methodologies to produce a full evaluation, including the EQs, G&I scorecard, VfM scorecard, SB methodologies, the ToC checklist and contribution analysis.
### Beneficiary engagement
The EL team made every effort to include people from socially excluded groups and to gather evidence of programme results from a diverse population through direct contact and by speaking with CSOs which represent these individuals. Furthermore, through document review and KIIs, the EL team assessed supplier and PT beneficiary engagement in the different components of programme design and implementation in the past year (such as whether adequate resources were available for necessary beneficiary engagement) and how beneficiary feedback has informed the PT’s ongoing activities. (See the G&I analyses in Section 4.4.)
### Limitations of the evaluation
The limitations are identified in the Cycle 2 Approach Paper. The actions taken by EL to mitigate these limitations during the Cycle 2 evaluation period are noted in Table 1.
Table 1: Limitations to Cycle 2 evaluation and their mitigation
Limitation	Explanation	Mitigation
Data collection and KIIs	The evaluation relies on the delivery partners and the PT for primary documents and data. Due to restrictions on travel and in-person interviews with stakeholders and engagement with PT, some key informants, particularly rural beneficiaries, may not be contactable.[24]	The EL team triangulated PT, IP and supplier information to identify and reach relevant KIIs and secure timely documentation. The EL team engaged beneficiaries across Colombia’s rural and urban areas to ensure optimal inclusion. Where people could not be reached, EL engaged local CSOs and federations who represent and/or regularly engage with beneficiaries.[25]
Delivery compression and timing changes	The FCDO may be redeployed to contribute to the UK’s response to COVID-19 in Colombia. This redeployment may impact the PT’s available timing and focus to prepare and undertake a full evaluation.	The PT was redeployed at the onset of COVID-19, but longer delays were in receiving feedback on the Approach Paper from JFU. Once EL received approval, it engaged with the PT and launched the evaluation within two weeks on 26 October. The delay meant that EL was able to provide early observations to the November AR team, but not full findings and recommendations.
Assessing attribution of results	As investment resources of the national and subnational governments are much greater than PF investments, during the evaluation it will be challenging to isolate the different sources of annual funding in the regions aimed at achieving similar objectives.	The EL team used contribution analysis to assess selected results claims. EL also tested the ToC’s causal pathways for the overall programme as well as for the selected claims assessed by the contribution analysis methodology.
Accuracy of results and quality of data reported in logframe	The PT updated strand and programme ToCs in March 2020. The IPs may not have adapted their data collection and reporting to align with these new results frameworks. This may create gaps in the accuracy and quality of data needed to inform the ToCs and logframes, including gaps in data when assessing the Fund-level intermediate outcomes.	The delay in the evaluation start meant that IPs had time to adapt their own data collection and reporting methods and mitigate this limitation.
Delays or barriers faced in programme implementation	Delays and contractual issues during programme implementation may mean few results emerge and/or projects lack maturity to assess programme-level (intermediate) outcomes. This also includes implications on the programme due to the COVID-19 pandemic.	Delays did occur. The PT and EL divided the analysis of the AR to focus on outputs and for EL to concentrate on intermediate outcomes and outcomes to build synergy across the two evaluations. EL also explored a wide range of documents to identify any gaps between planned delivery and results with what was evidenced by December 2020.
[24] In the Approach Paper, the PT noted: “It could be difficult to carry out participatory planning and consultations with women, girls and other vulnerable groups, as [the] COVID-19 crisis is increasing inequalities and these groups are facing extreme difficulties to restore their livelihoods. Their time, needs, interests and resources can be redirected towards guaranteeing access to basic needs, instead of participating in other activities”.
[25] For example, in one instance final beneficiaries were unidentifiable and therefore unreachable due to service agreements which protected confidentiality.

# Findings
This evaluation uses six distinct methodologies and approaches to deliver the full spectrum of findings and learning insights required of the PF. These include the standard PF EQs, a ToC checklist, the G&I scorecard, the VfM scorecard, the SB analysis and contribution analysis. The use of these various methodologies enables EL to draw and triangulate evidence from multiples sources to deliver findings and learning to the PT and all audiences of this evaluation.
## Uptake of Cycle 1 recommendations
EL made 11 recommendations in the 2019 Cycle 1 Colombia programme evaluation. The first of these was directed to the PF overall and the last was directed to EL itself.. Ten of the recommendations were acted on, but one related to VfM training for staff and IPs was not addressed due to other 2020 priorities. This recommendation was made again by the 2020 AR and the PT has prioritised VfM in the Cycle 2 recommendations.
## Learning since Cycle 1
Evidence drawn from KIIs and document review, including the 2020 AR, indicates that the Colombia PT has learned significant lessons since the Cycle 1 evaluation produced in October 2019. Some of these have immediate application; others are more relevant for future programmes.
### Immediate application
Lessons from COVID-19 response. The PT took away “important lessons” from the innovative ways suppliers, IPs and the PT itself found to deliver results remotely. The PT wants to ensure that the positive use of new tools and approaches is not lost when face-to-face engagement starts again. KIIs indicated that these include use of digital platforms to reach more deeply and more widely across stakeholder sets, the creation of new online tools and the more efficient exchange of documents and data.
Willingness of subnational authorities to co-fund. The PT cites the co-financing from cities and departments for PF-funded feasibility studies of rail and urban development projects. The PT sees this as a clear demonstration of local ownership which increases the likelihood of feasibility studies reaching the implementation stage quickly. Co-financing also increases the likelihood of project outcome sustainability.
Build clarity to achieve G&I goals. The PT spent much of 2020 reinforcing and revising G&I strategies, plans and targets in existing projects. The PT lesson, as noted in the 2020 AR, is “for the remaining new projects, ensure IPs and suppliers have a clear understanding of the PF’s G&I requirements”.
Align with the Paris Agreement on climate change. The June JFU stocktake found 11 areas of opportunity to improve Colombia’s alignment with the Paris Agreement, including red-flagging the regional competitiveness project of the Aerocafé. The PT is taking action on these recommendations and seeks to work with the PF’s climate consultants to improve alignment with the Paris Agreement and other environmental priorities.
### Future application
Have a conversation regarding the scope, role and functions of direct delivery partners. The PT learned that IPs and suppliers create both challenges and opportunities for the delivery of the PF in Colombia. For example, by pre-paying IPs for project delivery, the PT created predictability in a chaotic programme environment. Also, the PT learned that low value projects are not attractive to the Prosperity Fund Commercial Framework firms (hereafter, Commercial Framework), which resulted in voided tenders. In the future, the PT has indicated it will review the scope, roles and functions of IPs and the Commercial Framework and make changes. The goal of the PT is still to increase VfM by reducing the frequency of design and procurement processes, speed up the design and delivery of projects and allow for consistent direct engagement between the PT and its suppliers.
Train PF’s diplomats and civil servants on designing commercial opportunities. The PT has had to learn about SBs and developing commercial opportunities while actually planning and attempting to deliver them. The PT strongly suggests that future programmes include meaningful training about the complexities and processes needed to deliver SBs before programme launch.
Train DIT on FCDO priorities and programmes. In a similar vein, the PT suggests that it is vital that DIT understands the full range of possibilities of the PF to expand commercial opportunities for international firms, including firms from the UK. There is a strong sense that DIT Colombia has yet to fully appreciate or support the PF team to identify, cultivate and realise the full range of commercial opportunities. One way to do this is to have DIT and PF map the supply chains for PF sectors. HMA’s December 2020 initiative to better sync up embassy sections holds the opportunity to improve this situation.
## Theory of Change evaluation
### Contribution to the Fund Theory of Change
The Colombia programme has the potential to contribute to all five of the Fund’s intermediate outcomes (as shown in Figure 2):
- investment in infrastructure (agriculture, regional competitiveness, urban development and rail rehabilitation)
- human capital and innovation (agritech, urban development and open procurement)
- trade (agritech, rail rehabilitation)
- financial and economic reform (agri-insurance, open procurement)
- transparency and anti-corruption (corporate governance and open procurement).

Figure 2: Fund-level Theory of Change

SDSR: Strategic Defence and Security Review
### Colombia’s ToC strength
EL assesses the strength of a ToC through five frames: structure, plausibility, feasibility, sustainability and usability.[26] In March 2020, the PT, together with IPs and members of PFDU, Monitoring and Reporting (MR) Hub and EL, gathered in Bogotá to review and revise the causal pathways of the seven activities as represented in the ToCs for the three strands and the programme ToC. The assessment that follows is for the programme ToC. This assessment against the five frames follows below and is presented in summary in Table 2.
[26] In 2019, EL commissioned an expert to assess PF ToCs and develop a checklist to assess the strength of ToCs, which are considered living documents. This checklist differs from that used in the Cycle 1 evaluation for Colombia.
In addition to the qualitative assessment based on the various sub-questions within each element, the methodology provides a ‘weak’, ‘adequate’ or ‘strong’ rating for each of the elements. The scoring criteria for that part of the assessment are:
- Weak: Information is either not available or superficial.
- Adequate: Information is available and gives confidence that the PT has considered the issue. But there are gaps or lack of detail in some areas.
- Strong: There is detailed and convincing consideration of the issue.
Table 2: Colombia programme ToC score
ToC assessment frame	Programme ToC score
Structure	Adequate
Plausibility	Adequate
Feasibility	Strong
Sustainability	Strong
Usability	Adequate

### Structure
EL finds the structure score for the programme ToC is ADEQUATE. In early March 2020, a combined Monitoring, Reporting, Evaluation and Learning (MREL)/PFDU team joined the Colombia PT to review the causal pathways in the Colombia programme umbrella ToC. During those workshops, all agreed that nesting the activity/strand ToCs[27] into the umbrella programme ToC would enable the PT to monitor progress and tell the full story about the process of change and the PF’s role in those results. To achieve this umbrella ToC, the results from the strands were transferred to the programme, but to one level lower from where they sit in the strand ToCs.[28] The final result at the programme impact level is a statement of the combined effect of all strands. In the umbrella ToC, that impact statement is: “Sustainable, inclusive economic growth, reduced poverty and increased gender equity, contributing to progress towards the SDGs and mutual prosperity”.
[27] The governance strand has a unified ToC for its three activities (institutional strengthening, corporate governance and open procurement); the agriculture strand has a ToC for each of its two activities (agritech and agri-insurance); the infrastructure strand has a ToC for each of its two activities (urban development and rail).
[28] For example, the strands’ intermediate outcomes – the point at which pilots, standards or policies are adopted by relevant direct beneficiaries – become the programme’s outputs. Similarly, the strands’ outcomes –the point at which adopted pilots, standards or policies are implemented widely, scaled or replicated – become the programme’s intermediate outcomes. Finally, the strands’ impacts – intended changes after 5–10 years of the PF interventions – became the programme’s outcomes.
### Plausibility
EL finds the plausibility score for the programme ToC is ADEQUATE. The umbrella programme ToC shows logical coherence, particularly when combined with the strand/activity ToCs, which provide more detailed information on the outputs that feed into the umbrella ToC. This is linked to the structure assessment just above. The Colombia programme ToC and the associated strand/activity ToCs demonstrate ample ambition which show the connection between primary purpose and SBs at the intermediate outcome level (via the institutional strengthening strand) and across the board at the outcome level.
### Feasibility
EL finds the feasibility score for the programme ToC is STRONG. The programme and strand/activity ToCs are ambitious, but achievable at the time they were revised in March 2020. The revised ToCs accounted for changes in the programming environment which had impacted the first 18 months of programme delivery. The ToCs do not account for the COVID-19 pandemic, the ODA reprioritisation or the delay in funds linked to Colombia’s system of pre-payments to the IPs (based on operating procedures of IPs) – all of which unfolded after these ToCs were produced. Conceptually, the ToCs present changes along causal pathways that are still mostly within the realm of possibility to deliver. The exception to this may be selected agritech projects which were granted NCEs due to COVID-19-related restrictions and the inability to engage directly with the project beneficiaries.[29] The strand/activity ToCs were co-designed with the IPs and included rigorous discussions related to risk and risk management of the pathways being proposed.
[29] These include projects related to: cacao bean fermentation, satellite technology to inform coffee bean growers, bio-pest control of coffee cultivation and tilapia. One agritech project, a software application linking producers and buyers, realised greater results than planned (see Section 4.7 and Annex 14 Selected results and contribution towards primary purpose for more details and analysis).
### Sustainability
EL finds the sustainability score for the programme ToC is ADEQUATE/STRONG. The programme and strand/activity ToCs indicate clearly what must happen at each successive stage of result to ensure that the PF investments are sustainable. However, the economic impacts of COVID-19 and ODA reprioritisation (neither of which were cited as assumptions or risks in these ToCs) have cast some doubt on sustainability, particularly in some of the agritech projects.[30] Nevertheless, evidence shows that the PT anchored its original design on UK and Colombia’s national priorities, which have been well adapted to the evolving situation in both countries.[31] Another pathway which supports outcome sustainability is reflected in the programme and strand/activity ToCs’ integration and uptake of the private sector to achieve primary purpose as well as SBs. The assumption that informs the outcome and impact statements is that through PF contributions, market dynamics will result in more inclusive economic growth, greater competitiveness and openness for trade. This market-based pathway includes the introduction and dissemination of innovations, which can be identified in all the ToCs and is evidenced in programme documents for this evaluation and the 2020 AR.
[30] See Section 4.7 and Annex 14 for further details.
[31] The new UK foreign assistance priority sectors: climate change and biodiversity, including investing in research and science; COVID-19 and global health security; girls’ education; science, research and technology, including ‘leveraging global science partnerships’, open societies and conflict resolution, and trade and economic development. With the exception of girls’ education, there is strong evidence that the bilateral Colombia PF programme accounts directly for the other five priorities. See www.ft.com/content/726590b0-a05c-409f-85b1-5db2b3662176
### Usability
EL finds that for reasons noted above in the structure score, the usability score for the programme is ADEQUATE. While there is evidence that the PT use indicators from logframes to assess and adjust programme delivery, there is less evidence that the PT uses the ToC for programme adaptation. However, the ToC is structured in such a way that it does offer that utility if the PT chooses to use it.
### Recommendations
- In light of the events of 2020, EL advises the PT to review its strand/activity and programme ToCs to review assumptions and revise causal pathways as needed.
- EL also suggests that the PT reviews the ‘nesting’ of the strand/activity ToCs into the umbrella ToC and considers a more direct transfer of intermediate outcomes to intermediate outcomes so that results are at equal levels across the different frameworks. Plans for this exercise have been set for March 2021.
The priority recommendations are found in Section 6 of this report.
## Gender and inclusion
The Colombia programme meets PF G&I minimum standards. Promoting gender equality and social inclusion are core objectives of the programme and visible in the way it has planned, resourced and implemented its activities. The PT actively champions G&I issues and continues to build the capacity of IPs, government agencies and suppliers on what PF G&I requirements mean in practice for projects. As such, the programme has the potential to contribute to gender equality, women’s economic empowerment and social inclusion. This section provides a summary of the programme scorecard assessment (see Table 3).

Table 3: G&I scorecard summary findings[32]
[32] See Annex 10 Gender and inclusion scorecard and detailed analysis. RAG stands for red, amber, green.
Scorecard dimension	RAG rating	Findings
Overall score		The Colombia programme meets PF G&I minimum standards.
Design		Gender equality and social inclusion are core objectives of the Colombia programme and visible in the way the programme has planned, resourced and implemented its activities.[33] Although activities across the strands have the potential to generate benefits for women and other excluded groups, progress suggests that projects are not likely to do so equally. Agritech and urban development projects have and could generate economic empowerment for women. Institutional strengthening projects have not quite progressed sufficiently to assess whether their ambition is likely to be realised in practice.
Internal capability and incentives		The Colombia programme leadership has clearly championed G&I since its beginning. Early gaps in the PT’s G&I capacity may have contributed to lack of clarity on G&I requirements and guidance given to IPs and a lack of follow-up and monitoring of IP performance in relation to G&I. The PT demonstrates an active learning culture and bases adaptation on lessons from earlier projects. The PT has also continued to build its own internal G&I capacity. The programme has drawn consistently on external G&I and Social Development Advisor (SDA) expertise, and in early 2020, hired in a full-time, in-house SDA who also leads on MREL.
Accountability		At the programme level, the PT has set relevant requirements for all activities to assess the needs and concerns of end beneficiaries, namely women and members of other excluded groups. G&I has been well integrated into all activity logframes, with G&I-specific indicators and sex disaggregation. However, outcomes are often quite ambitious, and the programme may find it challenging to demonstrate contribution against higher-level indicators. IP and supplier reports could provide more granular progress information in relation to achievements than they do to report against logframe indicators.
Financial resources		G&I objectives are at the heart of the programme. The PT has put in place processes to ensure that projects assess the needs and barriers of women and other excluded groups and respond to these with concrete actions. The programme has allocated funds (GBP 150,000) at the central level for needed G&I support and has held G&I capacity building workshops for IPs and suppliers. IPs and some of the suppliers have allocated resources for G&I experts. Logframes are not used to their full potential in IP/supplier reporting, and G&I-related progress information is still not specific enough to enable an accurate assessment of progress.
Delivery partners		At the start of the programme, the PT assumed that IPs had more capacity and willingness to integrate G&I considerations meaningfully into projects than was demonstrated. G&I requirements and associated guidance have evolved and become clearer with time. Despite a slow start, IPs have ensured they have relevant G&I expertise and hired staff members in charge of overseeing and quality assuring G&I deliverables. Some IPs and suppliers have also hired G&I experts.[34] The IPs do not yet have the capability to fully monitor and manage the G&I-related work of their suppliers. To fill these gaps, the PT has continued to build its capacity on the PF’s G&I requirements, extending training to suppliers.
Results		All strands have progressed against their initial G&I action plans and begun to generate results that could be beneficial for women and other vulnerable groups. Agritech projects have built female producer capacity to use and adopt technologies and farming techniques and increased incomes. Through the institutional strengthening project, a G&I policy is being drafted for the National Infrastructure Agency (ANI) which could influence the procurement of future ANI projects. Infrastructure projects have undertaken initial G&I assessments and carried out consultations with citizens to explore barriers and needs.The G&I action plans indicate that urban projects could provide better access to transport, address issues of violence against women and girls and create job opportunities for women. There are indications of mindset changes in public authorities around publicly committing to the importance of G&I.
[33] Agritech projects have targeted female and smallholder farmers in post-conflict areas but have not consistently assessed the needs of women farmers or tailored activities to meet these needs. Instead, they have continued to gather evidence about women’s roles and decision-making in relation to technologies and farming practices during implementation but are yet to use the findings. Infrastructure G&I assessments are comprehensive, and urban projects such as Santa Marta have organised participatory consultations with citizens. The resulting G&I action plans set concrete G&I actions and requirements for contractors.
[34] The dimension has been given a green rating due to the actions taken to improve and the positive direction of travel, despite gaps in IP capacity.

### Design
Promoting gender equality and social inclusion are core objectives of the Colombia programme and visible in the way the programme has planned, resourced and implemented its activities. The PT has actively championed G&I and continues to build the capacity of IPs, government partners and suppliers on what G&I should mean in practice for projects. While all activities have the potential to generate some level of benefits for women and other excluded groups, progress suggests that not all projects are likely to do so equally. EL sampled activities that were more advanced in their implementation for this G&I analysis.
- Agriculture strand – agritech activity: Projects have, for the most part, targeted female and smallholder farmers in post-conflict areas, defined as vulnerable in Colombia’s multidimensional poverty definition.[35] Despite this focus, projects have not consistently assessed barriers and needs of women farmers or tailored activities to meet these needs. Initially, there was a lack of agreement between the PT and the IP on how far G&I considerations should be addressed, although grants to agritech suppliers included G&I terms. This led to delays in project sign-off. Suppliers have since carried out G&I assessments and developed G&I action plans in 2018 and 2019. These did not significantly influence project design, contributing to potential missed opportunities. There is also no evidence that projects consistently reported against these plans. Despite this, projects have surpassed their initial level of ambition (minimum compliance on the PF’s G&I framework) having already increased incomes for female farmers and improved capacity to use and adopt technologies and farming techniques.
  [35] Medida de pobreza multidimensional de fuente censal (dane.gov.co)
  Diversity and inclusion are important parts of this system.”
  IP KII
- Infrastructure strand – urban development and rail rehabilitation activities: All projects have conducted G&I assessments. The resulting G&I action plans set concrete actions and requirements for contractors at different stages of projects. For instance, responding to risks of gender-based violence along train lines and construction projects and actions to enable women and parents to take advantage of the economic opportunities, such as provision of childcare services. These projects aim to reach level 1 of the G&I framework to ensure that no harm is done and address women’s practical needs. However, the infrastructure G&I action plans demonstrate that projects could reach higher levels of ambition by providing better, more inclusive access to transport, creating opportunities for jobs for women and addressing issues of violence against women and girls.
- Institutional strengthening strand – regional competitiveness activity: The objectives of this activity are ambitious, aiming to influence subnational policies, systems and agendas to better address G&I considerations in local economic development projects. All regional competitiveness projects aim to achieve the minimum standard (level 1) of ambition on the PF G&I framework. Projects such as Aerocafé aim to achieve empowerment-level outcomes (level 2) because of the possibilities of generating women’s economic empowerment. While ambition levels are realistic in planned project outcomes, projects have not yet progressed sufficiently to assess whether these are likely to be realised in practice. Changes in regional governments and mayors in January 2020 delayed progress, requiring additional G&I awareness raising and capacity building.
### Internal capability
The leadership in the Colombia programme has championed G&I since the programme began. The programme has consistently drawn on external G&I and Social Development Advisor (SDA) expertise from the JFU and the Work Opportunities for Women Helpdesk to plug gaps in internal expertise and build IP and government partner G&I capability. This investment has contributed to awareness of G&I issues across IPs, suppliers and government partners, at least in terms of acknowledging the importance of this agenda.
In March 2020 the PT increased its internal G&I capacity by hiring a full-time, in-house SDA who oversees G&I work across projects.[36] The SDA provides capacity building and technical advice to the PT, IPs and suppliers, monitors project delivery and provides quality assurance. PT, IP and supplier staff value this expertise and support. In a few cases, IPs have requested further support from the PF to develop their own internal G&I policies. While this is positive, the PT should consider which requests are most strategic to support. The aim should be to build sufficient IP and supplier capacity to enable them to carry out the work themselves.
[36] This decision also represents better VfM than hiring external consultants.
Overall, the PT demonstrates an active learning culture in relation to G&I. It continues to learn from the experience of earlier projects and to adapt based on this learning. The PT has also shared project learning and experience with other PF programmes in the PF Learning Global G&I Champions Network.
### Accountability
Overall, most projects have engaged with end users of potential services to different degrees to shape the technical solutions offered by PF programmes. Urban development projects offer the most comprehensive examples, where consultations and G&I assessments have explored barriers and needs of women and members of other vulnerable groups in relation to planned developments.
G&I considerations have been integrated well across logframe results and their indicators. Indicators are mostly used to measure G&I-related progress. However, suppliers and IPs do not consistently use logframe indicators to report on progress. Although IPs report to the PT on G&I-related activities, reports lack information about the significance of activities or what they have achieved. This makes it challenging to assess progress against objectives. (See Section 5 Cycle 2 learning objectives and Section 6 Recommendations for more details.)
### Delivery partners
IPs, except for IUK,[37] have hired staff members in charge of overseeing and quality assuring G&I deliverables. PF’s requirements for G&I have evolved over time. The IP in charge of agriculture projects that started early on refers to the changing G&I requirements as changes in scope and, therefore, contractual in nature. However, IPs hired G&I experts after many of the projects had already started. Some of the suppliers have also hired G&I capacity to project teams.
[37] IUK had completed all contracting and were half-way through delivery when the SDA joined and developed remedial action plans.
Evidence drawn from KIIs and programme documents shows that at programme launch, the PT assumed that IPs had more capacity and willingness to integrate G&I considerations meaningfully into projects than they came to demonstrate. The PT has actively continued to build IP capacity on the PF’s G&I requirements and later extended training to suppliers. The PT’s ongoing role in capacity building and in managing G&I reviews of agritech projects suggests that not all IPs are yet able to carry out this function for their own suppliers. The programme management layers of PT, IPs and suppliers result in complexity which may make it more likely that G&I requirements are not adequately communicated to the project level and the quality of the work and deliverables is not sufficiently managed. Experience and remedial actions taken by the PT suggest this has been the case. (See Section 4.8 Governance and management)
### Results
The strands and their projects vary in the ways in which they have generated results for women and other vulnerable groups. Agritech projects have more control over their results while other activities, particularly regional competitiveness, are more ambitious and seek to influence policies and systems that are largely beyond the control of PF.
- Agritech projects were selected through a competitive process and were the first projects to launch. These have started to generate results such as increased incomes for female farmers and capacity to use and adopt technologies and farming techniques. In the cocoa fermentation project, female farmers increased their incomes. One of the farmers started an association of women cocoa producers, suggesting that the project will create results beyond the three initial female smallholders. The Farming Data app, LISTO, has successfully reached women: 24.2 per cent of LISTO users are women and 39 per cent of transactions have been completed by women. (See Section 4.7 Selected results and contribution towards primary purposes). In the next phase, the PT aims to replicate or scale successful projects. It will be important to consider women’s needs, roles and their decision-making power (for instance, using their findings from G&I assessments) in doing so. This could achieve benefits for a wider group of women.
- Infrastructure projects are at an early stage of development, with initial G&I assessments and action plans finalised. The assessments explored the barriers and needs that women and other vulnerable groups of people experience in planned infrastructure developments. There is evidence that the PF’s community consultation processes are a marked improvement from existing government processes, moving beyond merely informing communities of plans to genuinely consulting about needs. G&I action plans indicate that urban development projects could provide better access to transport and address violence against women and girls issues. This could contribute to achieving the results set out in the logframe. The activities and requirements set out in G&I action plans are translated into feasibility studies and contracts for companies that operate and manage the projects, which could generate positive benefits for women and members of other excluded groups. There are also indications of attitude changes in public authorities, at least judging by public commitments made to G&I. For instance, in Manizales, officials have committed to addressing G&I issues in its public transport system. There are also indications that the managing agent for the city’s transport system may include a G&I expert and quotas for women’s participation in other roles and in the contracts of operating companies. This may have positive impacts on project sustainability.
- The institutional strengthening strand’s regional competitiveness and corporate governance projects have not quite achieved intermediate outcomes and there have also been delays to delivering outputs.[38] Insufficient G&I capacity of IPs and suppliers has also contributed to delays. However, there are some indications of progress. For instance, plans for the Atlántico/Caldas Regional Commission’s agenda include gender equality considerations around access to job markets. These agendas are important roadmaps for the regional competitiveness commissions and will influence how they choose projects. Small shifts in the agenda of the National Infrastructure Agency (ANI) have also started to take place. Through the corporate governance reform project, a G&I policy is being drafted for ANI which could influence the regions and the contractors it works with. Other plans include gender quotas for the construction, operation and maintenance of fifth generation development contracts.[39] Each of these indications of progress are consistent with higher-level results that the activity envisions.
  [38] These delays are due to recent changes in regional governments and mayors, delays in bringing tenders to market, voided tenders, and COVID-19. Evidence suggests that if they succeed, it is likely they will have positive results beyond the PF programme.
  [39] Los proyectos de Quinta Generación (5G) tendrán como eje central la sostenibilidad y los temas sociales (ANI)
### Recommendations for G&I
The G&I recommendations identify areas in design, internal capability and accountability which, if addressed, will most advance the Colombia programme at this time. Two specific recommendations are:
- Assess the level of ambition of G&I goals with the recognition that policy influence and institutional change take a long time.
- PT, IPs and suppliers should ensure that G&I action plans are translated into feasibility studies and requirements for contractors to consolidate G&I in management and governance systems.
## Value for Money
### Summary Value for Money for Colombia programme
This section summarises the programme’s VfM rating using the PF VfM scorecard.[40] The main objective of the scoring is to highlight areas where there are opportunities for the PT to better deliver VfM and avert risks to VfM delivery. The Colombia PT provided self-assessment scorecards for the seven activities in the three strands in the overall programme. EL combined these self-assessments with the KIIs and document review to produce a VfM rating for the programme. On average, EL rated the activities one score lower than in the self-assessed scorecards. Table 4 presents EL’s summary VfM rating.
Table 4: VfM score for Colombia programme
Scorecard element	Attainment	Direction of travel
1. Relevance and robustness of VfM measures in place	Adequate	Adequate
2. Approach to procurement and cost containment	Adequate	Good
3. Efficient use of resources and inputs by PF interventions	Adequate	Good
4. Validation of PF ToC causal pathways for primary and secondary benefits	Good	Good
5. Sustainability of programme outcomes	Adequate	Adequate
6. Ability of leadership, management and oversight structures to support programme delivery	Adequate	Good
7. Strategies and measures adopted to enhance delivery and mitigate risk	Adequate	Adequate
8. Equity of programme design and approach	Adequate	Good
Overall VfM assessment	Adequate (rising to Good)

The direction of travel from the initial VfM reference point in 2019 to the autumn of 2020 demonstrates reflection and action on the part of the PT, the IPs and suppliers. Brief descriptions for the VfM elements are given below.
1. Relevance and robustness of VfM measures in place. While the Colombia programme does not have VfM indicators, the PT uses logframe indicators to monitor progress and steer delivery. Multilateral IPs have their own processes and procedures, including VfM frameworks, which do not always align with those of the PF.
2. Approach to procurement and cost containment. The activities in the PF programme make use of a range of cost containment measures, for example by ensuring required quality within cost parameters in MoUs with the IPs. Another example is the review period of deliverables before IPs make payments to suppliers.
3. Efficient use of resources and inputs by PF interventions. The PT designed the programme to use regional IPs and delegate programme management and delivery. The design aimed to ensure the PT would use its resources effectively and build on the regional and country-specific experience of the IPs. Evidence suggests this did not function as intended in some cases, although some IPs have met these expectations and are delivering well.[41]
[41] See Section 4.8 Governance and management
4. Validation of PF ToC causal pathways for primary and secondary benefits. All three strand-level ToCs and their causal pathways are valid and demonstrate the likelihood of the delivery of primary purpose and SBs.
5. Sustainability of programme outcomes. The programme enables actors to improve their work, which supports the sustainability of PF programme outcomes. Brief examples include evidence which indicates that ANI will be able to design and procure more inclusive and transparent tenders; complex infrastructure projects will use more sophisticated technical, inclusive and project management approaches; open procurement processes are strengthening in selected departments; and smallholders will understand and use more efficient and environmentally sustainable practices which improve yields and secure better prices in both real and virtual marketplaces. These examples show stakeholders delivering programme outputs and intermediate outcomes which are in their own interest and likely to continue over time.
6. Ability of leadership, management and oversight structures to support programme delivery. The flat governance structure matches the delivery mode in the PT and avoids the risks of a deep hierarchy. However, the roles and interconnection of the multiple boards and groups in strategic governance are not clear. There are also complexities in the management structure of PT, IPs and suppliers which have created challenges.
7. Strategies and measures adopted to enhance delivery and mitigate risk. The PT has demonstrated strong learning, adaptability and decisive action in addressing efficiency risks. Evidence shows the PT addressed risks by adjusting IP roles, altering programme budgets to improve attractiveness of previously void tenders, and opening tenders to national suppliers. However, there are some gaps in risk register including the exchange rate risk caused by the use of three currencies: US dollars, Colombian pesos and British pounds.
8. Equity of programme design and approach. There is clear evidence that the PF programme has impacted the understanding of and need for G&I as part of project design and delivery (see Section 4.4 Gender and inclusion). Evidence from interviews and documents demonstrate a strong PT commitment to work towards greater gender and social inclusiveness.
### Recommendations
Two priority VfM recommendations are:
- Make reporting on supplier VfM delivery (including quality of delivered outputs and outcomes) more transparent.
- Use VfM measures such as market testing to reduce the risk of void tenders.
## Secondary benefits
This section provides a summary assessment of the Colombia programme’s delivery of SBs.
Delivery of secondary benefits to date
There is considerable evidence in the Colombia programme of the close relationship between the delivery of SBs and primary purpose with each contributing to the other. By December 2020, programme documents support the PT’s claim of having delivered 13 commercial and six soft power SB wins which included five of the six types of SBs: market access, outward direct investment (ODI), exports, network effects and soft power.[42] SBs were partly achieved using non-ODA funds from the Opportunities Fund, but all were connected to the ODA-funded PF and are unlikely to have occurred without PF activity.
[42] The sixth SB which the programme has yet to deliver is foreign direct investment.
This range of SBs is different to many other PF programmes which focus more on high value SBs and large UK companies. Moreover, this range is broader than envisaged by the Colombia Programme’s Business Case and Secondary Benefit Action Plan, neither of which anticipated ODI wins.
- Market access. The Agritech Catalyst Challenge Fund has enabled the delivery of at least two examples of market access. These SB wins include improved quality of fruit for the production of ice cream entering the UK consumer market (resulting from a non-ODA agricultural trade mission); and improved quality of cocoa bean fermentation for enhanced flavour profiles of cocoa beans to benefit the UK consumer (cocoa bean fermentation project).
- ODI. A UK SME set up business in Colombia, following the signing of a contract for the integrated trading platform and data analytics for a Colombian smallholder project. Because the PF project allowed the company to build networks, it enabled a Colombian branch of the British SME to be set up to deliver other products to the Colombian market.
- Exports. Colombia has delivered three export SBs so far. One in the health sector, one in infrastructure and one in agritech. These include a contract between the Manizales local government and the PF supplier for commissioned technical work beyond the scope of the PF project. This is an export win for a British company and also provides benefits for the citizens of Manizales from a more comprehensive, integrated transport system.
- Network effects. Colombia’s agritech activity includes science-driven projects which involve UK universities where all participants benefit. One project uses Earth observation technology to support smallholders in the timing and quantity of irrigation in their banana plantations, reducing water use and erosion of nutrients in the soil (see Section 4.7 Selected results and contribution towards primary purpose). While this is the primary purpose of the project, the supplier gains information from the Colombian smallholders on actual conditions on the ground which enable it to fine tune its models. This is a network benefit for the university and the wider UK science community and society.
- Soft power. KIIs noted with regularity that the UK’s reputation and political capital in Colombia are strong and widely acknowledged. For example, the UK’s long-standing support for Colombia’s peace process created strong credibility at the national and subnational levels. This strong standing supports the PF delivering of soft power SBs. This is complemented by the PF’s use of UK innovations in project delivery. For example, participants in the regional competitiveness Aerocafé project explained that the department administration has given the project high priority particularly because of the UK’s PF engagement. After a decade of delays, the PF’s support to develop the masterplan created the necessary distance between the previous administration and the new authorities to allow the work to continue. Similarly, the PF’s role in rail rehabilitation – a high priority for Colombia – also demonstrates the trust and soft power which the UK has given the strategic role that rail plays in the country.
### Method of delivery and governance
The PT is clear about the objective of delivering SBs with a strong focus on the UK as a beneficiary country. It is also clear that SBs are always secondary to the primary purpose of greater, more inclusive economic growth. Evidence indicates that using UK innovations to delivery primary objectives also positions UK firms for subsequent SBs. This approach was made clear in Colombia's original business case. The PT’s governance boards include the review and advice on SBs in their Terms of Reference (ToR).[43]
[43] See Section 4.8 Governance and management for more details of the programme’s relevant structures.
There is some evidence that indicates a misunderstanding of SBs among IPs, including the use of private sector companies in delivering PF projects. Some stakeholders linked the objective to deliver SBs with the Commercial Framework and the requirement to use this in procurement processes.[44] This shows that these programme principals have not fully understood that SBs cannot be delivered via PF funds.
[44] KIIs with two different IPs indicated this continuing misinterpretation of SBs.
There is some evidence of a strong focus of delivering SBs for the UK. The delivery of SBs is driven by the PT’s Commercial Advisor who is funded from non-ODA budget and has a clear focus to deliver SBs for the UK. The PT is aware of how SBs can be steered towards the UK in the medium term. For example, the use of project management tools co-developed in the UK such as the Building Information Model (BIM) and the 5 Case Business Model in rail rehabilitation and regional competitiveness projects will make the market more recognisable and therefore more accessible for UK companies.[45],[46]
[45] BIM is a collaborative way of working, underpinned by the digital technologies which unlock more efficient methods of designing, creating and maintaining assets. BIM was developed in the UK. See https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/34710/12-1327-building-information-modelling.pdf. The 5 Case Business Model is a decision-making tool to identify the best option to achieve a set of objectives when investing capital. The 5 cases are: Strategic, Economic, Commercial, Financial and Management.
[46] See: Términos de referencia para contratar los estudios y diseños a nivel de factibilidad para la estructuración técnica, legal, financiera y de equidad de género e inclusión social de un tren de carga y pasajeros entre Bogotá y Zipaquirá.
The PT’s Commercial Advisor drives SB delivery, at times single-handedly. The Commercial Advisor has developed an approach which nurtures individual contacts and opportunities in SB delivery rather than approaching the whole market with a larger but less specific offer. This approach is based on learning from successes. While it demonstrates significant personal delivery capability, it also creates a potential bottleneck and risk due to relying on one person.
The blending of ODA and non-ODA funding has proved to be a useful delivery method. The PT has used non-ODA funds to support trade missions to and from the UK and Colombia. Examples are the mission of the Ministry of Transport to the UK to learn more about operational management and planning, British pavilion at Agrofuturo in Medellin, and agriculture missions in 2019. Since COVID-19 travel restrictions took effect, the PT has continued virtual trade missions. These activities allow UK companies to hear about the PF programme in Colombia and learn about the country which, in many cases, is a new business source for UK companies. Knowledge exchange at these events enables them to create networks and pursue opportunities resulting from the PF.
### Barriers
#### Internal barriers
Internal barriers are those within the embassy or the JFU to the delivery of SBs. One clear barrier is the low number of staff in the PF team and the wider post, including a DIT team which is too small to focus on PF SBs as well as meeting its own targets.
The DIT team does not focus on agriculture. DIT has no agriculture expert. The PF agritech activity has delivered several SBs, including the successful example of the Bionema. This firm supplies the agricultural sector with biopesticides and has successfully signed an MoU with a Colombian partner for future collaboration, training and coproduction. The chemical industry is an important sector in the supply chain and close to the pharmaceutical and life science industries in which DIT has expertise in Colombia.
Some KIs expressed a view that working through the IPs causes particular challenges because the link to the supplier and related markets is indirect. However, the one of the IPs rejects this, stating that it has a role to support SB wins, working hand-in-hand with companies. UK companies will be treated fairly if they bid for a follow-up contract.
The delay in the non-ODA budget has held up SB delivery. The delay in the sign-off of the non-ODA budget has held up further SB development (Quarterly Report Q1 2020/21). This demonstrates the role that the non-ODA funds play in enabling SB delivery.
#### External constraints
The DIT has identified more than 35 barriers to trade and investment with Colombia. These are mainly regulatory and legal barriers. An overly complex legal system has also been cited as a barrier by others. This legal system requires the use of local lawyers in the process of setting up a business, which adds further costs to starting trading or investing. It also adds a significant amount of time to the process which is not suitable for many businesses and puts Colombia at a disadvantage compared with other countries.
Perceptions in the UK business community of Colombia as a dangerous country, due to its long standing internal conflict and unsuccessful war on drugs also reduce the interest of engaging with the country and realising the potential of SBs. Several suppliers noted in their interviews that their perception of Colombia was coloured by popular media and they were initially hesitant to undertake activities in the country. Other firms have declined to engage.
### Conditions
The PT was not just an observer, but they identified a key role and took an active position.”
Government partner
The development of trust between UK firms and Colombian public sector organisations is an important condition in delivering SBs. Trust is an important condition in economic interactions and international trade generally[47] and no less so in delivering SBs. For example, the project for a strategic public transport system in Manizales allowed UK suppliers to build a relationship of trust with the city government. This then allowed the supplier to secure another contract with the city unrelated to the PF project.
[47] den Butter, F. A. G. and Mosch, R. H. J. (2003), Trade, trust and transaction costs.
At the governmental level trust can be gained by soft power. Five decades of work with the Colombian government and the current negotiation of the trade agreement and the 2020 Double Taxation Treaty create good conditions for SBs. The 13 commercial SB wins, often involving UK SMEs, demonstrate the role of trust in the resulting success.
### Recommendations
The SB analysis offers the following recommendations:
- Clarify the definition of SBs as referring to all international companies and communicate this to IPs and suppliers.
- Clarify again with IPs that PF funds do not pay directly for SBs.
## Selected results and contribution towards primary purposes
As detailed in the programme’s ToC, the Colombia programmes aims to support “sustainable, inclusive economic growth, reduced poverty and increased gender equity, contributing to progress towards the SDGs and mutual prosperity”. There are 23 active projects across three strands, which are producing outputs and early results. EL identified projects where evidence of intermediate outcome or outcome level results have been achieved and used a contribution analysis approach to further assess the degree to which the PF programme was a strong contributor to these results. EL also gathered wider evidence to assess whether projects were on track to achieve the outcomes described in the programme ToC.
Contribution analysis seeks to determine if the PF intervention was a necessary element among the range of factors which, combined, caused the observed result. Findings from this analysis allow for a better understanding of whether the outcomes would have emerged without the PF interventions. The methodology is presented in the Cycle 2 Approach Paper.[48]
A contribution claim[49] is based on the programme’s ToC and verified through evidence which also accounts for the role of other relevant causal factors. This section summarises the analysis and findings of each outcome result identified, tested against the ToC. Table 5 describes the rating system used to determine the strength of evidence and contribution of the PF programme to the outcome results.
[49] As opposed to attribution which relates to a singular cause and is rarely encountered in complex development landscapes where most often there is a package of causal factors.
In an October 2020 workshop, the PT identified seven results based on a wide range of evidence, which were then refined by the EL team. The EL team concluded that three of the seven higher-level results had sufficient evidence. To be clear, the results that have been selected for this analysis are not the only results to be achieved by the programme to date.
Table 5: RAG rating of evidence and strength of contribution
Strength of evidence	Strength of contribution
Green: Evidence supports (confirms) a causal claim across multiple data sources	Strong: Evidence of contribution is unequivocal. While the PF may not be the only contributor, the results would not have been achieved without PF support.
	Moderate: Evidence of contribution is present, as are other external factors and influences. PF activity was necessary but not fully responsible for outcome result.
	Marginal: Evidence of contribution is present, but this is marginal and highly influenced by other external factors, such that the change was likely even without the programme.
Amber: Evidence is unclear, whether confirmatory or disconformity, of a causal claim; or there is insufficient evidence to suggest the PF contributed to the change	Not assessed
Red: Evidence rejects (disproves) a causal claim	Not assessed

### Result 1: Development of a digital trading platform improves market and pricing
Figure 3 maps out the causal pathways which EL examined. The green hexagons indicate the areas where PF programme-related outputs, while the white and blue hexagons describe where external factors influenced the result.
Figure 3: Digital application – causal pathway of result claimed

The EL team assessed the contribution story of the PF in this project as the following: the development of the trading platform created a digital marketplace, giving smallholder farmers access to greater networks to buy and/or sell products. Users of the app have gained real-time access to location-specific market prices which increases market transparency and helps farmers avoid exploitation by middlemen. With more direct connections to buyers, farmers have achieved higher sale prices (20–23 per cent increase reported), which positively impacts household incomes. Table 6 below summarises the components examined as part of the contribution analysis.
Table 6: Digital application LISTO – summary of contribution analysis
Contribution analysis	Commentary and analysis
Result claimed	Adoption of agritech innovation has led to improved markets and pricing through creation of integrated trading platform.
Programme outputs contribution to outcome result / Lead supplier: Farming Data / Project inputs: / Demographic and technical analysis of context / Development of LISTO app, the integrated trading platform / Demo testing and product improvement / Continuous monitoring of G&I stats of users / User training workshops / Local project facilitators promote use of app and platform	Output 1: Adoption and use of app (LISTO) by smallholder sellers and buyers / Through promotion and training workshops, the farmers use the app and complete trade transactions, from pricing to marketing to sale and delivery. Farmers primarily use the smartphone app, but the platform is also accessible through a webpage and/or through SMS messaging. / Output 2: Continuous improvement to app for G&I/user-focused changes / The app has been improved following user feedback to ensure that it is usable and accessible to all farmers. The interface has been improved to make the platform more intuitive for farmers who were not used to using their mobile phones beyond making phone calls and/or texting. / Output 3: Trading platform creates a digital marketplace / Following the adoption of the trading platform by both buyers and sellers, the platform has created a digital marketplace. Feedback shows it to be a useful communication channel for accessing customers or producers.
Other influencing factors	COVID-19 pandemic creating a need for uptake of digital platforms / Endorsement from Ministry of Agriculture to use digital platforms and connections from Chambers of Commerce / Public promotion of rural mobile internet connectivity
Strength of contribution and evidence	Rating of evidence: Green[50] / Strength of contribution: Moderate to strong
Potential counterfactual scenarios: If the integrated trading platform was not created through the PF programme	Digital trading platform would have been piloted in another country, perhaps even a non-PF nation. / No feasible alternative to the traditional market during COVID-19 / Farmers would have continued to use middlemen for trading and/or traditional markets, which would not have led to improved pricing

### Result 2: Irrigation management service leads to improved quality and banana production
Figure 4 maps out the causal pathways which the EL examined. The green hexagons indicate the areas where the outputs and outcomes were a result of the PF programme, while the blue and white hexagons describe where external factors influenced the result. The evidence for each of the pathways is listed and labelled in a more detailed diagram in Annex 14.
Figure 4: Irrigation management – causal pathways to result claimed

Using contribution analysis, EL tested the outputs of the programme and its contribution to the outcome above: improved production (that is, yield) and quality of harvested crops. The PF-funded project resulted in banana growers using water resources more efficiently and improved crop quality through careful monitoring of soil moisture and weather in relation to the health of the crops. The irrigation instructions sent directly to banana growers via SMS have enabled farmers to improve their irrigation management. Table 7 below summarises the contribution analysis undertaken for this result.
Table 7: Irrigation management – summary of contribution analysis
Contribution analysis	Commentary and analysis
Result claimed	Adoption of agritech innovations leads to improved production (that is, yield) and quality
Programme outputs contribution to outcome result / Lead supplier: Climate Edge / Project inputs: / Modelling of irrigation dynamics using satellite and weather data to develop an irrigation scheduling service tailored to smallholder farmers / Set-up of software and hardware infrastructure / Continued collection of in situ soil moisture data in reference sites / Model is trialled and tested during multiple dry seasons to improve service	Output 1: Farmers receive irrigation recommendations via weekly SMS / The project supplier provides forecasted weather conditions and irrigation advice to smallholder farmers each week via SMS. The project supplier assessed how farmers were making decisions on irrigation which shaped the information included in the recommendations. This has supported smallholders to build their knowledge of irrigation requirements. / Output 2: Banana growers apply irrigation advice to their land / The project supplier reported that all the farmers were satisfied with the recommendations. The project supplier reports that farmers were using the recommendations to set their irrigation amounts and changing their previous practices.
Other influencing factors	National and regional government support to improve water resource management by regional government in Zona Bananera. Colombia’s Banana Zone, located in Magdalena, has faced water shortages, which has led to farmers abandoning land with no water for crops and consumption.[51] Colombia’s National Development Plan (NDP) 2018–2022[52] noted the need to develop plans for more sustainable use of water resources in the agriculture sector. The Magdalena Development Plan 2020–2023[53] also noted the need to provide greater support to poor and vulnerable populations and support restoration of ecosystems and water resources through better monitoring and government involvement with permit use through the Corporación Autónoma Regional Del Magdalena (Corpamag).[54]
Strength of contribution and evidence[55]	Rating of evidence: Green / Strength of contribution: Moderate to strong
Potential counterfactual scenarios: If banana irrigation services were not available to banana growers via the PF programme	Farmers noted that without this service their irrigation costs would have been higher, although their financial resources are limited. Farmers said they would have been worse off without the service. / Evidence suggests that water scarcity will worsen without appropriate conservation policies in place. / Banana production would not have improved: The norm is to irrigate until farmers see that the ground is sodden. Too much water in the fields leads to plant damage and nutrient depletion in the soils, as shown in the soil analyses.
[51] https://es.mongabay.com/2018/10/cultivo-de-banano-acapara-tierra-y-agua-colombia-cienaga-grande/
[52] www.oecd.org/dev/americas/Colombia-Country-Note-Leo-2019.pdf
[53] www.magdalena.gov.co/planes/plan-de-desarrollo-departamental-magdalena-renace-2020
[54] Corpamag functions within the regional government and is mandated to manage environmental concerns and promote sustainable development in Magdalena.

### Result 3: Improved open procurement increases competition and transparent use of public funds
Figure 5 maps out the causal pathways which the EL examined. The green hexagons indicate the areas where the outputs and outcomes were a result of the PF programme, while the white hexagons describe where external factors influenced the result. The evidence for each of the pathways is listed and labelled in a more detailed diagram in Annex 14.
Figure 5: Open procurement – causal pathway to result claimed

The EL team assessed the contribution story of the PF in this project as the following: Interviewees have reported that while the issues of corruption will continue beyond the life of the programme, the open contracting project has made a significant step forward in combatting this complex issue. There has been an increase in procurement process data uploaded on to databases which adheres to higher data standards. Evidence shows that among procuring entities that use the national system, SECOP II, there was a decrease of 6 per cent in direct contracts in favour of competitive awards last year and a 17 per cent increase in the average number of bidders. This improvement in competition has created fairer and more reliable processes for businesses. Nonetheless, work is needed to monitor the quality of data stored in electronic databases and to explore further external factors that pose a barrier to transparent disbursement of public funds. Table 8 below summarises the contribution analysis undertaken for this outcome result outlined in the yellow hexagon above.
Table 8: Open procurement – summary of contribution analysis
Contribution analysis	Commentary and analysis
Result claimed	Genuine open procurement promotes increased competition, VfM and good use of public funds
Programme outputs contribution to outcome result / Lead supplier: OCP / Project inputs: / Technical assistance to support open and accountable procurement in nine departments by presenting and using open data / Facilitating a series of training workshops across five departments on data reporting of transactions and procurement and open procurement data standards / Training and ongoing support to nine departments to effectively use and fully adopt the Electronic System for Public Procurement (SECOP) II / Civil society stakeholders taught to access and analyse data	Output 1: Increased engagement by regional governments / By the second year of the project (reported June 2020), the project reached and engaged five departments. These are now producing better data and have reported an increase in the number of procurement processes carried out in SECOP II, which are all in accordance with Open Contracting Data Standards (OCDS). / Output 2: Production and sharing of better quality data and information with public through SECOP and TVEC. / OCP (the IP) supported the increase in uptake and use of Colombia’s online portal that centralises government purchases and related data, called SECOP (I and II), hosted by the national procurement agency (Colombia Compra Eficiente).[56] The platform grants open access to electronic copies of government contracts for the general public to scrutinise. / Output 3: Transparency and availability of procurement data increased for multi-sector stakeholders / Departmental government stakeholders, journalists, academic researchers and other interested public parties were engaged to participate in a number of training workshops to learn how to access and process procurement data.
Other influencing factors	COVID-19 put more attention on open procurement processes / Pressure applied by the public and anti-corruption movements / International pressure applied / Colombia’s NDP incentivises government stakeholders to improve procurement processes
Strength of contribution and evidence[57]	Rating of evidence: Green / Strength of contribution: Moderate
Potential counterfactual scenarios: If open procurement activities administered through the PF programme did not provide training and capacity building support to local governments and procurement stakeholders	National government may have responded to international pressures to address issues and commit to measures proposed during anti-corruption referendum. / Regional governors and mayors may have responded autonomously to this issue. Under the direction of regional governments in different departments, evidence shows that stakeholders were working to address procurement issues, but may not have approached the issue in the same way (that is, data improvements for transparency). / CSOs and other public groups might have put pressure on public officials and used existing data platforms available to report on bidding statistics. The data would not have equalled the detail that they were able to use from OCP.
[56] www.colombiacompra.gov.co/colombia-compra/colombia-compra-eficiente

Conclusion
Overall, the contribution analysis findings show that PF is contributing to progress towards programme outcomes. Evidence suggests that, in the cases tested, the results would not have happened without the inputs of the PF programme. For the two agritech innovations, the evidence shows that developing the integrated trading platform and providing an irrigation scheduling service led to improvement of markets and production, respectively. The analysis also indicates that the improvement to regional open procurement processes enhanced the quality of electronic data systems and engaged a wide range of anti-corruption and procurement actors.
The EL team identified a set of external factors that acted as a supporting force alongside PF efforts. This suggests that the success of the projects may be partially attributable to external sources to varying degrees. Given the national and international pressures and commitments made, the EL team concluded that the open procurement project provided a ‘moderate’ contribution, as anti-corruption efforts coincided with project implementation. The agritech projects demonstrated a slightly stronger contribution (moderate to strong level) since external factors were less significant to the projects’ outputs (that is, the creation of the LISTO app and accompanying training and the SMS irrigation support service modelled).
While the three results show positive progress toward the objectives of the programme, the EL team identified barriers which challenge achieving results on a wider scale. For example, some barriers are related the cultural norms that exist in rural economies, where use of digital technologies and services require greater capacity building and more trust in information from certain sources. Agritech projects suffered delays due to COVID-19, which prohibited face-to-face interactions required for fieldwork and for more effective learning via training workshops. Other barriers have to do with the time associated with testing seasonal crops to validate results for wider adoption and scale benefits in the future more broadly.
## Governance and management
### Programme structure
This section describes the management structure of the PF Colombia programme, the intended functions of the various layers and their actual functions according to the evidence.[58]
[58] See also Section 4.5 Value for Money
#### Programme team
The Foreign and Commonwealth Office team that designed the PF programme in Colombia intentionally kept the PT lean by delegating most programme delivery functions to IPs and suppliers. Five Colombian nationals work as the PT’s strand and thematic advisors, and they each bring substantial expertise in their fields and professional networks of their own which contribute to PF programming and, as evidence shows, to other aspects of embassy engagement. Evidence demonstrates that their expertise contributes to both primary purpose and SBs. However, the advisors’ roles in project delivery and quality assurance are greater than was anticipated, particularly due to the need to reinforce G&I elements in projects[59] and to identify and cultivate SBs. The VfM analysis (see Section 4.5 Value for Money and Annex 11) indicates that the leanness of the PT may create risks to the overall programme.
Governance, done well, helps you focus on the right things at the right time.”
HMA
[59] See Section 4.4 Gender and Inclusion.
#### Implementing partners
The business case and other programme documents show that the Colombia programme sought to leverage its investments by working with multilateral regional banks as IPs, assuming these institutions would bring expertise, networks and institutional teams to bear and allow the PT itself to remain relatively small. This strategy was designed with VfM in mind and was conceptually sound. Other PF programmes, particularly global programmes, have used a similar delivery model.[60] EL finds substantial evidence, including in the Cycle 1 report, that the reality of these relationships has been more mixed than original assumed. For example, IPs have their own internal systems which were not necessarily aligned with PF systems or timing. These include internal due diligence systems which required significantly more time to advance project designs and associated contracting than had originally been indicated or planned for.
[60] Centre for Disaster Protection, Global Business Environment Programme, Global Anti-Corruption Programme and the ASEAN Economic Reform Programme.
#### Suppliers
The Colombia programme sources its suppliers primarily through two mechanisms.[61] The first, for the agritech activity, was driven through the IP IUK, which enabled the PT to reach directly into the UK’s innovation ecosystem through a call for proposals process which resulted in grants to firms and academic institutions. For all other projects, the PF and the IPs used the PF Commercial Framework in the first instance. Only when tenders failed multiple times did they enter the wider market.[62] The EL team found no inherent limitation in using firms to deliver primary purpose, and indeed, has found advantages related to sustainability and securing SBs in this arrangement. However, there have been advantages and challenges in how all these suppliers were resourced and the roles they play in programme delivery which bear review. For example, working through IPs created a chain of MoUs, grants and contracts in which the PF priorities related to G&I and VfM were muted. This created the need for subsequent G&I training noted previously. (See Section 4.4 and Annex 10 Gender and Inclusion scorecard and detailed analysis for more analysis.) A significant advantage in bringing firms and experts in as suppliers has been the dynamic use of a wide range of innovations in the infrastructure activities, particularly hi-tech innovations in agritech and agri-insurance as well as sophisticated design and planning systems.
[61] The exception to this is the open procurement activity IP, OCP, which has a grant from the PF institutional strengthening strand to deliver the work.
### Programme governance and management structures
The governance of the Colombia programme includes five groups. Evidence[63] suggests that the main functions of these groups are less about strategic discussions than about management-level issues. The exceptions to this seem to be the monthly meeting between the PT and the SRO and the Internal Programme Review Group, which combines management and governance functions.
[63] This evidence includes minutes from the different groups and remarks made during KIIs with relevant stakeholders.
- Internal Programme Review Group. This is a regular meeting between the PT and London-based PF colleagues including JFU and PFDU to track progress, receive and discuss guidance and generally ensure that the Colombia programme is aligned and compliant with the overall PF. These meetings also provide space for the PT to secure approval or clarify next steps for the programme.
- PF Investment Group. This is an internal embassy group which meets to discuss new projects or programmes and ensure that they align with UK principles and practices and are consistent with the UK’s purpose in Colombia. This group explores both primary purpose and SB implications of PF programming.
- SRO Monthly Meetings. These are regular meetings are between the PT and the SRO. Evidence indicates that they provide full line of sight and frank participation for all PF team members and are valued by all PT team members who were interviewed for this evaluation. All evidence shows that these meetings serve both governance/strategic and management functions.
- Private Sector Advisory Panel. This panel includes the PT and the firms in the PF Commercial Framework. It links the PT to the private sector, supports the framing of projects by testing market receptivity, and provides space for the Commercial Framework firms to explore forthcoming opportunities in greater detail.
- Stakeholder Group. This body initially met every six months, but moved to an annual schedule in 2019. The Stakeholder Group includes a broad set of stakeholders including IPs, suppliers, government partners and direct beneficiaries. The 2020 annual meeting coincided with evidence gathering for the AR, which meant it took the form of a broad check-in with programme principles. Minutes from previous meetings show that this is a consistent approach.
### Cross-embassy governance and management structures
Evidence suggests that the cross-post governance is limited to selected sections working on similar issues when the need arises (such as DIT and PF; or PF and the Environment, Science and Climate section). During COVID-19, KIIs provided evidence that there have been more frequent ad-hoc conversations across department teams. However, HMA launched a new cross-embassy group in December 2020 to “think about which fund or combination of funds, what expertise do we already have, how do we apply that and how do we mitigate risks associated. Not more bureaucracy but value added”. The next programme evaluation will consider the degree to which this cross-embassy effort has improved leveraging information, resources and action.
## Risks
The risks noted in this section are not necessarily reflected in risk registries, but programme reports and interviews with the PT indicate that the following contribute to or may present risks to the programme. (See Section 4.5 and Annex 11 on VfM for more on risk management.)
### Risks to the programme
The PF Colombia team, IPs and suppliers all contribute to regular risk matrices in their various reporting cycles. EL recommends that the risks noted below are accounted for in management discussions in the short term to ensure that they do not further compound the challenges faced in 2020 or during normal programme implementation.
- Thin staffing margins in the PT risk delays or gaps in programme implementation across entire strands if one of the advisors were to be absent for an extended time due to sickness or reassignment. For example, evidence shows that SBs are largely driven by the actions of one staff member and the same is true for G&I advances. By the same token, the technical advisors for the three strands have no support staff. Such delays were seen at the beginning of the COVID-19 period when HMA reassigned staff to consular services for three to six weeks. The PT may want to create plans to ensure that any unanticipated absences can be covered with existing resources.
- Interrupted lines of communications within delivery partners risks weakening clarity. This risk is not as great as it was a year ago due to the remedial actions taken by the PT to improve IP performance and clarify PF priorities. However, the PT should make no assumptions about these lines of communication. EL suggests that as long as the COVID-19 pandemic conditions exist, it is worth making explicit and routine check-ins with IPs and suppliers about priorities and challenges.
- Reporting templates add work for the PT and distort the perspective of delivery partners. Evidence shows that the reporting templates fail to provide information that the PT needs for decision-making. This is especially true for reporting that aligns with logframes and ToCs. The absence of this information in supplier and IP reports means that the PT must spend time calculating or extrapolating logframe and ToC information. This situation also creates a gap in how the suppliers and IPs understand their role in delivering PF results, and limits their vision to delivering discrete activities, rather than contributing to a larger set of results which the Colombia programme has committed to deliver.

# Cycle 2 learning objectives
This section provides suggestions that emerge from the EL’s findings that address the PT’s five original Cycle 2 learning objectives and also offer learning that have a wider PF network applicability.
## Learning for the Colombia PT
Table 9 presents the learning objectives of the team and the suggestions made by EL to address them.
Table 9: Addressing PT’s Cycle 2 learning objectives
Learning objective	EL suggestions
SMART recommendations to match ambition with time availability and support a strategic response to challenges and opportunities related to COVID-19.
Catalogue the COVID-19-related adaptations and innovations generated by beneficiaries, delivery partners, suppliers, IPs and within the PT itself to incorporate explicitly the responses that yielded positive results and address those which detracted or delayed project progress. These examples should be shared on PF Learning so that other PTs can learn and use some of these approaches. The PT could also use this catalogue as it joins the cross-embassy strategic planning sessions which HMA has planned for early 2021. / Link reporting to results frameworks. Subsequent reporting on a monthly and quarterly basis should reflect qualitatively and quantitatively how projects contribute to activity-level logframe indicators and ToC causal pathways. This can be done by adding a section to existing project dossiers to track clearly how each project aligns and contributes to output, intermediate outcome and outcome levels for each strand. Supplier and IP reporting should reflect this new section. / Assess projects 6–12 months before completion to ascertain where remaining PF resources (time, staff, funding) will optimise impact. The PT should discuss with other UK programmes in Colombia what can be brought to bear to achieve maximum results. With advanced planning, the PT can strengthen project outcome sustainability. This may include looking for opportunities to learn lessons from other projects or strands in the Colombia portfolio to see what has worked well and how it can be applied quickly to other projects. This would also provide an opportunity to create networks and linkages among PF stakeholders that may have not yet interacted with similarly engaged people and institutions.
Insights to enable the Colombia PT to align itself with the overall PF network and objectives, assisting Colombia’s understanding of where and how it fits within the Fund.
Request that meeting times are rotated to ensure direct participation of all programmes over time to strengthen the ability of PF Colombia to align itself with the overall PF network.[64] Evidence shows that even when the PF network offers discussions among theme-specific colleagues, the time difference between London and Bogotá means that PF Colombia is unable to join.[65] / Seek EL support to strengthen its connection to the PF network by organising informal sessions with sector experts, programme evaluation leads (PELs) from other PF programmes and other technical experts to exchange insights on selected topics. These sessions could be informal or structured, depending on the needs of the PT and the resources available to EL, but should be fairly low cost. They would augment, rather than duplicate, information available on PF Learning.
Gain a more strategic, informed view of challenges, early wins and long-term needs.
Invest one day each quarter to explore current challenges, celebrate progress, exchange lessons across programme principals and identify one or two optimal wins (aligned with results frameworks) for the next quarter.[66] / Extend similar strategy and implementation sessions to include other embassy sections, perhaps through the new cross-post group that HMA is launching in December 2020. These sessions could use the facilitation methods provided by EL and taken into cross-embassy discussions by the PT.
Identify gaps and opportunities to mainstream G&I through presenting findings which strengthen its incorporation into programme, strand and activity.
Assess costs and benefits of IP selection in the future and make a specific review of delivery partners’ G&I capacities before contracts or awards. / Plan to invest continuously in G&I capabilities among the PT, IPs, suppliers and direct beneficiaries, but decide at what point the IPs and suppliers are obliged to take lessons and practices forward on their own. / Assess the level of ambition of intermediate outcomes and indicators of all activities and strands, recognising that some will probably not be achievable within the lifetime of PF-funded activities. / Design and agree improved reporting formats and content with IPs and suppliers that capture results in a way that aligns with and informs the activities, strands and programme logframes and ToCs.
Contribute to Colombia’s 2020 AR by providing the PT with preliminary findings from the Cycle 2 evaluation following the data collection phase.
The delay in approving the Cycle 2 Approach Paper delayed the evaluation. The EL team was able to provide early observations to the PT before the AR process concluded in November, but was unable to provide a full evaluation. The PEL joined the AR team as an external reviewer, participating in selected interviews and focus groups.
[64] For example, EL holds its monthly PEL/relationship manager (RM) meetings twice – at 9.00 and 15.00 GMT – to ensure that PELs and RMs around the world have same-day information and can participate directly in peer exchanges.
[65] For example, the SB Advisors Network meets early morning GMT, which is the middle of the night for Colombia. The SB Advisor from India attends these meetings and later debriefs his colleagues in Brazil, Colombia and Mexico. High marks for innovation and collegial support, but three of ten PF bilateral programmes are routinely left out of direct participation.
[66] EL could support these sessions by structuring agendas and methodologies and/or through facilitating the days using flexible or engagement days available to support PTs.

## Learning for the wider PF network
The Colombia Cycle 2 evaluation identifies four primary lessons that may serve the broader PF network. These emerged in the various analyses, including G&I, VfM, SBs and contribution analysis. While the Colombia programme may offer technical lessons to various PF sector work, these lessons are crosscutting.
Lessons for wider PL learning
Evidenced lesson	Illustrative projects	Wider lesson
Innovations. The Colombia PT’s use of innovations has contributed to results for primary purpose and SBs. Evidence shows that linking UK expertise and applied technology has supported the delivery of outputs and intermediate outcomes so far.	Santa Marta Smart City / Open procurement / Bogotá-Zipaquirá / Gestión de Riesgos Agropecuarios (SIGRA)	Innovations bring applied technology to bear. / UK innovations position future SBs. / Organisation for Economic Co-operation and Development (OECD) innovations facilitate telling the PF story to a wider audience.
Seek out and listen to users/beneficiaries. The projects which began their implementation by reaching deeply and broadly to engage users, communities, stakeholders and women and other vulnerable groups demonstrate stronger relevance and adoption of ideas and practices. This supports sustainability.	Aerocafé / Manizales / La Dorada-Chiriguaná / ANI institutional strengthening	Projects with early discipline identify and engage users and stakeholders, including women and other vulnerable groups. / Projects that apply insights from these groups have higher levels of commitment and support. / Higher levels of support strength the project’s post-PF sustainability.
Constant adaptation. Projects which adapt methods, scope and content in a disciplined way show more consistent achievement of intermediate outcomes.	LISTO app / Regional competitiveness councils / Ibagué sanitation	Adaptation, within parameters, can take advantage of unforeseen opportunities. / Projects responsive to changing environments build in resilience and relevance for users.
Urgency. Projects which respond to urgent challenges gain greater attention, focus and participation than those which address more chronic challenges.	All agritech projects / Rail rehabilitation / Open procurement	A sense of urgency or criticality seems to boost attention and action by stakeholders. / Chronic challenges can be subdivided into segments to build the sense of urgency to generate momentum.

# Recommendations
This section presents the headlines for the top seven recommendations co-created by the PT and EL during the January 2021 Findings and Recommendations Workshop (Table 10). The two teams discussed the findings of the full evaluation draft and, from that discussion, identified these priority recommendations. Additional recommendations made throughout this report are compiled in Annex 15.
Following the submission of this Cycle 2 evaluation report to JFU, the PT began addressing these priority recommendations with EL support. This includes EL preparing and delivering materials and workshops to support the PT to address efficiently these priorities within the time and the resources available to the PT.
Table 10: Cycle 2 priority recommendations
Reference	Recommendation	Lead actor(s)	Time frame
Section 4.9.1 Risks to the programme	Ensure complete alignment across MoUs, contracts and reporting mechanisms.	PT Advisors and IPs	By 1 July 2021
Section 4.5.2 Opportunities to improve Value for Money; Section 4.8 Governance and management	Review communication lines from the PT to IPs to suppliers to direct beneficiaries to ensure that the layers of programme management harmonise and reinforce desired messages and principles.	Head of PF, PT Advisors	By 1 July 2021
Section 5 Cycle 2 learning objectives	Consider sharing lessons and insights with IPs and suppliers by periodically convening thematic sessions to explore lessons and best practices.	PT Advisors and IPs	By 31 December 2021
Section 4.5 Value for Money	Assess project status 6–12 months before conclusion to create outcome sustainability plans.	Head of PF, PT Advisors, IPs	As relevant
Section 4.3 Theory of Change evaluation; Section 4.4 Gender and inclusion	Review the ToC and logframes (intermediate outcomes, G&I level of ambition, VfM indicators, nesting/structure, assumptions) to ensure these frameworks are strong tools.	Head of PF and PT Advisors	Before next AR
Section 4.5.2 Opportunities to improve Value for Money	Evaluate the VfM scorecard to optimise all aspects of Colombia programming.	Head of PF and PT Advisors	By 1 July 2021
Section 4.6.3 Barriers (to SBs)	Undertake actions which will enable the PF to translate the positioning for SBs into actual wins.	Head of PF, PT Advisors, DIT, HMA/SRO	By 1 July 2021