MEXICO PROSPERITY FUND PROGRAMME
EVALUATION REPORT 2020 (CYCLE 2)
October 2020
Version history
D16_04	Prosperity Fund Mexico Programme Cycle 2 Evaluation Report
Revision	Written By	Checked By	Approved By
Revision 0	J. Butz; U. Hotopp, L. Bernal	A. Gardiner
Revision 1	J. Butz	S. Marment, C. Pando, C. Hernandez
Revision 2	J. Butz	A. Gardiner, K. Byrne, Mexico PT (all)
Revision 3	J. Butz, F. O’Sullivan	D. Pedroso
Revision 4[1]	F O’Sullivan	D. Pedroso
[1] While final revisions to this report were made after the merger of the Foreign & Commonwealth Office and the Department for International Delivery (DFID), references to DFID have been retained as the report was drafted when DFID was still in existence.

Table of acronyms
Abbreviation
ACROL	Anti-corruption and Rule of Law
BC	Business case
CDMX	Mexico City (the newest State in Mexico)
CNBV	Comisión Nacional Bancaria y Valores (National Bank and Securities Commission)
CONEVAL	Comisión Nacional de la Evaluación de la Política de Desarrollo Social (National Commission for the Evaluation of Social Development Policy)
CSO	Civil society organisation
DFID	Department for International Development (UK)
DIT	Department for International Trade (UK)
EL	Evaluation and Learning
EPI Centro	Energy strand’s branded Central Delivery Unit and state-level “hubs”
EQ	Evaluation question
FCO	Foreign and Commonwealth Office (UK)
FDI	Foreign direct investment
G&I	Gender and inclusion
HMA	Her Majesty’s Ambassador
HMG	Her Majesty’s Government
ICF	International Climate Fund
IO	Intermediate outcome
JFU	Joint Funds Unit
KII	Key informant interviews
MoU	Memorandum of understanding
MR	Monitoring and Reporting
MREL	Monitoring, Reporting, Evaluation and Learning
MSME	Micro-, small and medium-sized enterprise
ODA	Official Development Assistance
ODI	Overseas Direct Investment
PF	Prosperity Fund
PFDU	Prosperity Fund Delivery Unit
PMC	Programme Management Committee
PT	Programme team
SAB	Strategy Advisory Board
SB	Secondary benefit
SGB	Strand Governance Board
SMT	Senior management team (Future Cities Alliance)
SoR	Statement of Requirement
SLA	Service-level agreement
SRO	Senior Responsible Owner
ToC	Theory of Change
ToR	Terms of reference
UK	United Kingdom
VfM	Value for money
VT	Virtual team

Contents

TABLES
Table 1: Contexts and factors influencing programme management outcomes	7
Table 2: Contexts and factors influencing programme management outcomes	13
Table 3: Comparison of G&I scorecard scores for the Mexico programme 2019–2020	17
Table 4: Gender and inclusion indicators in the Mexico Programme strands	18
Table 5: Mexico Programme Cycle 2 value for money scorecard	19
Table 6: Secondary benefit types identified in Cycle 2 secondary benefit analysis	21
Table 7: Selected secondary benefits that the programme has contributed to	22
Table 8: Recommendations for the Prosperity Fund network	25
Table 9: Recommendations for the Cycle 2 Annual Review team	27
Table 10: List of key informants	29
Table 11: Bibliography	31
Table 12: Cycle 2 Integration of inquiry tools and learning priorities	34
Table 13: Cycle 2 illustrative interview guide	38
Table 14: Strength of data score criteria	40
Table 15: Mexico Programme summary findings against evaluation questions	40
Table 16: Value for money scoring system	69
Table 17: Self-assessment of value for money through exploratory questions	70
Table 18: Strand self-assessments	72
Table 19: Evaluation and Learning revised score	72
Table 20: Comparative assessment of Cycle 1 and Cycle 2 programme Theory of Change	79
Table 21: Programme and strand Theory of Change strength	84
Table 22: Actions taken against critical Cycle 1 programme recommendations	85

FIGURES
Figure 1: Integrated learning areas of Cycle 2	3
Figure 2: Mexico Prosperity Fund Programme regional coverage	4
Figure 3: Evaluation Questions and lines of inquiry in the Cycle 2 evaluation	34
Figure 4: Opportunities for secondary benefits	75
Figure 5: Fund-level Theory of Change	79
Figure 6: Mexico Programme Theory of Change	83
Figure 7: Cycle 2 schedule	88

BOXES
Box 1: Examples of advanced planning and weak planning	23
Box 2: Secondary benefits arise in unexpected ways	77

ANNEXES
# Executive summary
BRIEF OVERVIEW / The design of the programme is sound and aligns well with both Mexico’s National Development Plan and the Prosperity Fund’s objectives. / Limited information on results is available as programme implementation has only recently begun. However, early indications suggest the programme is on track to achieve primary purpose and secondary benefit goals. / A capable programme team and strong cross-Embassy coordination are supporting the programme. There are good systems for management, governance and achieving value for money, with some scope for improvement. / The programme has strengthened its potential to improve the lives of women and girls and to promote social inclusion. It has also supported some early secondary benefits for UK firms.

What is the Mexico Prosperity Fund?
The Mexico Prosperity Fund is a five-year initiative of up to GBP 60 million that started in 2017. It aims to reduce poverty by promoting greater inclusive growth in Mexico. The programme comprises four strands: Energy, Financial Services, Future Cities and Anti-Corruption and the Rule of Law. It is managed by a programme team based in the British Embassy in Mexico City, and delivered by three suppliers.
What did the evaluation look at?
The Cycle 2 (2019/20) evaluation was carried out from January to May 2020 and focused on engagement, capacity, management and governance, reflecting the learning priorities of the programme team. The programme’s four strands are at a very early stage of implementation, hence few results have been achieved.[2] The scope of the evaluation reflects this and focuses on whether the programme’s structures and the ways it engages with stakeholders are likely to maximise future results. The evaluation had five objectives:
[2] The Financial Services and Future Cities strands began their implementation phases in October 2019, and the Anti-Corruption and Rule of Law and Energy strands began implementation in January 2020. As the review of documents and interviews was carried out in February and March 2020, the time period since the start of implementation was too short for the evaluation to comment on whether programmes are on track or in line with the expectations set out in the theory of change and logframe.
1. Assess the capacity of the programme team and suppliers, identifying strengths and weaknesses.
2. Assess processes for engagement with stakeholders and make recommendations on how best to sustain their participation and support over time.
3. Evaluate governance structures and processes to strengthen results and improve value for money.
4. Evaluate management structures to improve value for money.
5. Identify findings for use in the programme’s 2020 Annual Review.
The evaluation also updated previous assessments on gender and inclusion, value for money and secondary benefits for international and UK businesses. The main audiences of the evaluation are the UK Ambassador to Mexico (the Senior Responsible Owner), the programme team, other embassy teams, the team carrying out the 2020 Annual Review, the Joint Funds Unit and the Prosperity Fund Delivery Unit. The findings will also inform the overall Prosperity Fund evaluation report.
Sources for the evaluation include programme documents, secondary information including Mexican government policy documents and 55 interviews conducted in March 2020. The results have been discussed with the programme team, and the evaluation report was quality assured by the DFID’s Evaluation Quality Assurance and Learning Services. The views expressed are those of the independent evaluation team.
What did the evaluation find?
Design: The concept for the programme is strong and clearly aligned with Mexico’s National Development Plan and with overall Prosperity Fund objectives. The programme looks likely to deliver on both its primary purpose and secondary benefit objectives. There are, however, three ways the programme could be strengthened:
- Update the pathways to change for each strand, to reflect changes since moving from the design phase into implementation.
- Identify the areas in which the programme could increase its potential for impact, focusing on how the strands could support each other’s impact. This assessment should consider soft power and development of commercial networks, as factors likely to facilitate greater future trade and investment successes.
- Support further leadership skills development of the programme team to enhance further strategic planning and operational delivery of each strand and the programme more broadly.
Potential to achieve primary purpose: While the relative success of the programme and its strands will only become clearer over time, there is reason to expect the programme is on course to achieve its primary purpose. The Cycle 1 (2018–19) evaluation found that the design of each strand was sound in terms of the logic and plausibility of the road maps. This Cycle 2 evaluation finds that, although the programme has only recently moved into implementation, its strands have got off to a good start. There are as yet few output- or outcome-level results to report. Nonetheless, successful delivery of the following first-step activities indicates that the preconditions for later achievement of the programme’s primary purpose and secondary benefit objectives are being met.
- Energy: Approval was secured from government authorities to establish the Jalisco project hub (one of three centres from which the strand will be delivered[3]) as well as to implement the training programme for energy regulators.
  [3] The others are in Mexico City (the overall HQ) and the southern state of Tabasco.
- Financial Services: The strand was launched by the Mexican finance minister and Lord Mayor of London. This high-profile event demonstrated the status of the strand to sector stakeholders, which should promote successful delivery. The regulatory sandbox competition was also launched, representing the start of a process to boost the fintech sector in Mexico.
- Future Cities: Strand activities were launched in five Mexican cities with the participation of state governors. A new digital centre to support urban planning in the city of Monterrey was also legally incorporated.
- Anti-Corruption and Rule of Law: Memoranda of understanding were signed with three state justice and anti-corruption institutions.
There are also indications that the Financial Services and Future Cities strands will begin to deliver substantial outputs by the time of the Annual Review in the early summer of 2020.
Engagement: While changes in policy and in key government personnel have created challenges, the programme has navigated these with only slight (one to two month) delays. One key reason for this minor impact is that all strands are engaged actively at the federal, state and municipal levels with a range of stakeholders from the private sector, academia and civil society. In specific Strands, engagement has been particularly successful in securing endorsement of strand objectives by federal stakeholders. The level of engagement by the programme team has varied at state level and requires more attention and coordination, in particular in the states of Tabasco and Jalisco.
The programme team and suppliers have the capacity to deliver the programme. Programme team capacities are sometimes stretched, however. There is scope to address this and increase efficiency by clarifying roles and responsibilities.
Management: Overall, the management practices established for the Mexico Programme are good. The programme team is conscientious, hard working and focused on its mission. There are indications that strand managers are more successful where a clear vision of objectives is shared by suppliers and where they adopt a more executive style of programme management. This includes developing relations of trust with suppliers, allowing confidence in their expertise and taking an inclusive approach to decision making. The programme team would nonetheless benefit from leadership skills training to reinforce their current programme management capabilities.
Governance: The programme has appropriate governance arrangements, but these could be further strengthened. The programme is supported by strong cross-Embassy coordination, and key elements of the governance system are working well. This is important given the complexity of the UK’s activities in Mexico. The Programme Management Committee has played an effective role in ensuring overall coherence and coordination within the Embassy, supported by the virtual teams. Minor revision to the composition of the Strand Governance Boards should be considered periodically, and governance of secondary benefits could also be strengthened.
Gender and inclusion: The programme team has continued to focus on gender and inclusion issues and has thereby increased the programme’s potential to achieve better outcomes for women and girls and to reduce social exclusion. However, the chance of achieving these in practice would be improved by renewing regular meetings between the programme team and the suppliers’ gender and inclusion advisors as well as by improving gender and inclusion logframe indicators.
Secondary benefits: The programme has made good progress in developing and implementing plans for secondary benefits and has contributed to export wins for UK firms worth approximately GBP 21 million. There is, however, further scope to maximise future results. This includes strengthening cooperation between programme and DIT staff to improve understanding among middle and senior managers and addressing the governance gap for secondary benefits described above. Advance planning to create opportunities for secondary benefits is also important, but this currently varies across the strands.
Value for money: The programme has put in place processes, structures and systems which provide strong potential to achieve value for money. While the extent to which this potential is realised in practice will depend on how far planned results are achieved, the current direction of travel is good. Performance could be strengthened by implementing the Joint Funds Unit guidance from 2018 on value for money indicators and by updating the terms of reference for the Programme Management Committee, Strategic Advisory Board and Strand Governance Boards to make specific reference to value for money. Commercial arrangements should also be kept under review (in particular the potential risks to efficiency and costs from a single firm holding several Prosperity Fund contracts in Mexico).
The Prosperity Fund is a UK government initiative supporting inclusive economic growth in partner countries through a GBP 1.2 billion portfolio of programmes over 7 years. The Fund’s activities will contribute to achieving the UN Sustainable Development Goals, while creating opportunities for international businesses as a secondary benefit. / Scrutiny of the Fund’s work is undertaken by the Prosperity Fund Evaluation and Learning service, led by Tetra Tech International Development, in partnership with LTS/Niras and Integrity. Evaluations take place annually at programme and Fund levels, and aim to identify learning for programmes, thematic issues and sectors. This is the second annual evaluation of the Mexico Programme.

# Introduction
## Purpose and scope of the evaluation
This is the second annual evaluation (“Cycle 2”) of the Prosperity Fund (PF) Mexico Programme. Objectives for Cycle 2 were identified through a two-day planning workshop with the programme team (PT) in Mexico City in December 2019. Specific evaluation questions were identified to understand performance at an early stage in the implementation of each strand, and the following objectives were agreed:
1. Assess the capacity of the PT and the suppliers to deliver projects, identifying strengths and areas of opportunity.
2. Assess processes for engagement with stakeholders and make recommendations on how best to sustain their participation and support over time.
3. Evaluate governance structures and processes to optimise value for money (VfM) and strengthen programme results.
4. Evaluate management structures and processes to improve VfM.
5. Identify findings for use in the programme’s 2020 Annual Review.
The evaluation fieldwork was conducted shortly after the strands began their implementation phases (four months after this starting point for two of the strands, and two months afterwards for the other two strands). Accordingly, there are few results to comment on, and the evaluation team was guided by the PT not to focus on this. The evaluation has, however, noted whether the programme is on track for achieving its primary purpose and secondary benefits objectives.
## Audience and stakeholders
The primary audience for this evaluation is the PT, as it seeks to strengthen the good practices emerging in the early months of implementation and identify methods to address areas of opportunity. Cycle 2 will inform the Senior Responsible Owner (SRO) and her team in considering reallocation of funding for the second half of the programme. Other stakeholders include:
- The Joint Funds Unit (JFU) and Prosperity Fund Delivery Unit (PFDU) who may gain insights as the Mexico programme is further along in delivery than most other PF programmes.[4]
  [4] Interviews with the JFU and PFDU indicated that findings from the seven evaluations conducted in 2019 each provided recommendations and insights which they consider, rather than focusing on those stemming from specific evaluations.
- The Department of International Trade (DIT) and other teams at Post in Mexico City.[5]
  [5] These include the PF global programmes (Skills, Health and Global Trade), the International Climate Fund, and recently started financial services from the Department for International Development as well as the Newton Fund and other initiatives of the Foreign and Commonwealth Office run by the Embassy.
- Other PF programmes as they may benefit from this evaluation as they move into implementation.
- The team conducting the Annual Review in the summer of 2020 as relevant recommendations are included.
The PT was involved in the planning of this evaluation as detailed in the Mexico Programme Cycle 2 Approach Paper.[6] The team has continued this engagement by providing documents, identifying and helping with outreach to stakeholders for interview, providing key informants, and commenting on an earlier draft.
[6] The Cycle 2 Approach Paper was an update of the more fulsome Cycle 1 Approach Paper as per the JFU’s instructions to EL.
## Report structure
The rest of this report is structured as follows:
- Section 2 summarises the approach and methodology for the evaluation.
- Section 3 describes the country context and provides an overview of the Mexico programme.
- Section 4 provides an assessment of whether the programme is on track to achieve its primary purpose.
- Sections 5, 6, 7 and 8 consider capacity, engagement, governance and management issues respectively.
- Section 9 summarises key points from an assessment of the programme theory of change (ToC), based on the fuller analysis in Annex 10.
- Sections 10, 11 and 12 provide cross-cutting assessments of gender and inclusion (G&I), value for money (VfM) and secondary benefits (SBs), with further analysis provided in Annexes 7, 8 and 9.
- Section 13 provides recommendations for the PT and for the forthcoming Annual Review.
Annexes providing more detail on specific issues include the Cycle 2 Approach Paper; a list of key informants; a bibliography; the methodology, including limitations and how risks were managed; an illustrative interview guide; the full evaluation matrix; fuller analyses on G&I, VfM and SBs; the programme ToC and a ToC checklist; a consolidated evaluation findings summary against all evaluation questions (EQs); the Cycle 2 Evaluation and Learning (EL) team biographies; and the Cycle 2 schedule.
# Approach
The Mexico Programme is more aptly described as a portfolio of programmes. The evaluation team therefore explored the individual strands to generate findings and recommendations for the overarching programme. This strand-up approach is well suited to learning, particularly to drawing lessons from within the programme itself.
This learning from within is relevant for two reasons. First, few bilateral PF programmes have advanced as far as the Mexico Programme. It has required guidance earlier and has had to resolve the challenges associated with moving from procurement to implementation sooner than most programmes.[7] Second, the Mexico Programme has advanced through the various stages from business case (BC) to implementation as an integrated programme. While the advance has been relatively uniform, strand programme managers have faced varied challenges and have responded in different ways, providing an opportunity for learning.
[7] The other notable bilateral programme with each of its strands in implementation is Colombia. Through the Latin America conferences, held regularly among Brazil, Colombia and Mexico, there is substantial regional information sharing and cross-programme lesson learning.
## Data collection and evaluation question sampling
Three broad types of evidence were assembled and reviewed for this evaluation:
- Programme documents provided by the PT (see Annex 3).
- Fifty-five key informant interviews (KIIs). These included:
- Internal stakeholders at Post including the SRO, Her Majesty’s Ambassador (HMA); the Policy and Prosperity Counsellor; the Head of the PF in Mexico; additional PT officers;[8] the Head of UK’s International Climate Fund (ICF) programmes in Mexico; and several officers from DIT. Interviews with JFU and PFDU representatives were conducted as part of the broader and concurrent Prosperity Fund evaluation.
  [8] The PT has expanded during 2019 to include a contracts manager, a governance and communications officer, and two finance officers. These individuals were all interviewed during the Cycle 2 KIIs.
- External stakeholders, including representatives from federal and state authorities, international organisations and the private sector.
Secondary sources depending on the technical areas related to each strand.
All documents reviewed for this evaluation are noted in the footnotes and the bibliography (see Annex 3).
### Evaluation questions
The December 2019 planning workshop revisited the twelve overall evaluation questions (EQs) for the Prosperity Fund, and selected six of these to focus on in Cycle 2, as presented in Table 12 (see also complete answers to each question in Annex 6).
The Cycle 2 evaluation addresses the six sampled EQs for each strand, as well as thematic evaluations through the G&I scorecard, the VfM scorecard and the SB methodologies. The findings from all of these lines of inquiry are combined in this programme evaluation.[9] Figure 1 shows how the EQs refract a variety of areas of exploration, including the themes and learning priorities for each cycle.
[9] Individualised strand analyses are beyond the scope of the PT sample and Cycle 2 resources.
## Cycle 2 learning priorities
Learning priorities identified in the Cycle 2 planning workshop were summarised into four categories: capacity, engagement, governance and management, highlighting the main challenges the team face in the early stages of implementation.
Figure 1: Integrated learning areas of Cycle 2
These learning areas were understood as the following:
Capacity
Engagement
Governance
Management
- Capacity. Capacity has two dimensions. The first is having the sufficient knowledge (technical and contextual) to effectively manage the strand and programme. The second is the human resource bandwidth (i.e. enough hours in a day, days in a month) to deliver what is expected in the manner it is expected (i.e. good quality, on time, aligned to targets).
- Engagement. Engagement explores the strands’ and programme’s outreach and seeks to assess the following questions: Who comes to the table? How do they come to programme activities? What is the level of their engagement? How will engagement be sustained over time? Communications and managing expectations are also elements of engagement.
- Governance. Governance includes which structures or bodies are in place to support the strategic oversight of the programme and strand implementation.
- Management. Management includes which operational and administrative processes are available to support the implementation of the strands and, through them, the programme.
These four learning areas do not stand alone nor are they linear. They are integrated, each one informing the others. For instance, without strong capacity—both technical and bandwidth—all other factors are compromised. Without effective engagement, the governance and management of strand and programme activities would weaken, and so on.
# Context
This section summarises key elements of the political and economic landscape in which the programme is being implemented. It is intended to provide context for the following discussion of programme delivery issues rather than a full analysis in its own right.
## Country context
In August 2019, Dominic Raab made his first trip as Foreign Secretary to Mexico and signed a new partnership agreement with Mexico’s Foreign Minister, Marcelo Ebrard, anchored in the existing PF programme. In his official press statement, Raab noted: “there are huge opportunities to boost two-way trade, create jobs, tackle poverty and inequality and address key Mexican priorities such as strengthening transparency and reducing corruption.”
The first full year of the presidency of Andrés Manuel López Obrador was 2019. Events in the country have changed strands within the Mexico Programme and seem likely to continue to do so as the programme advances. For example, while President López Obrador’s energy priorities vary from some of the PF’s selected objectives, the overall goal of greater inclusive economic growth and poverty reduction is strongly shared by the Mexican leadership.
## Mexico Prosperity Fund programme
The PF Mexico programme is an initiative of up to GBP 60 million. Its four constituent strands—Energy, Financial Services, Future Cities and Anti-Corruption & Rule of Law (ACROL)—have moved from design to procurement to inception as a holistic unit. Figure 2 below shows the programme’s current geographical reach.[10]
[10] In Figure 2, CDMX is Ciudad de Mexico, Mexico City. It is no longer a federal district, but a state in its own right.
Figure 2: Mexico Prosperity Fund Programme regional coverage

The national context offered opportunities and challenges as the strands finalised their designs and results frameworks during inception:
- For the Energy strand, a focus on upskilling and expanding the energy sector workforce and strengthening regulators’ knowledge of international standards is intended to support inclusive economic growth now and aid the transition to a lower carbon economy in the future.
- For Financial Services, the government submitted a 2020 budget that would nearly triple the funding for the government’s main poverty alleviation programmes. One implication of this is that millions of Mexicans stand to benefit from financial inclusion, allowing them to receive cash transfers through safe, reliable methods.
- Future Cities benefits from a high degree of momentum and enthusiasm from municipal and state authorities in the five cities in which it is being implemented. Federal budget cuts have affected municipal and state governments, and the strand’s support of already planned safer cities initiatives has been well received.
- For ACROL, the government priority to address corruption and reduce violence opened channels across a variety of federal secretariats, ministries and agencies at the national and state levels.
The PT utilised the inception phase as a way of learning in a safe environment in which the PT and suppliers could build stakeholder relationships, co-design delivery plans and learn from trial and error (and success).
During inception, the PT and the four sets of suppliers extended their outreach and engagement at federal, state and municipal levels. This enabled the strands to connect with stakeholders and beneficiaries and to set and manage expectations, which had been growing after the official announcement of a GBP 60 million investment from the UK.
The inception phase was also well timed as it coincided with the government coming into power. The six months (nine months for Energy) gave federal-level government stakeholders time to get their bearings in their new roles so that by the end of inception, both they and the PT were prepared to launch and integrate strand activities. Finally, the inception phase gave HMA time in her role as SRO to build confidence that the strands were well designed and actively promote cross-Post awareness and engagement.
# Is the programme on track to achieve primary purpose?
The bulk of the fieldwork for the evaluation was carried out in February 2020, very shortly after the programme moved into implementation. As a result, there are currently few meaningful results which show whether the programme is on track.[11] The strands have, however, achieved some initial successes, as indicated by the following examples. While these represent initial milestones at the very start of the pathway towards achieving primary purpose and SB goals, they are nonetheless essential first steps. In this sense, they provide confidence that the programme has made a good start:
[11] The Financial Services and Future Cities strands began their implementation phases in October 2019. While Energy and ACROL officially began implementation in November, in practice this occurred in January 2020 (the SRO was unable to approve the Energy workplan before then, and formal approval by Secretaría de Gobernación, Mexico’s interior ministry, was also only given in January).
- The Energy strand secured government approval to establish the Jalisco project hub,[12] as well as for capacity-building training for energy regulators, to be designed with Ofgem’s support.[13] The strand has also contributed to export wins worth GBP 21 million (See Annex 9 for the SB analysis).
  [12] One of three EPI Centro hubs for delivery of the project, the other two being based in Mexico City and in the state of Tabasco.
  [13] Ofgem—Office of Gas and Electricity Markets—the UK regulator for electricity and downstream natural gas markets.
- The Financial Services strand was officially launched by the Lord Mayor of London and Mexico’s Finance Minister. This high-level launch helped solidify government support for the strand as seen in the launch of the regulatory sandbox challenge, part of intervention 2.
- The Future Cities strand launched in cities with the participation of state governors. In Monterrey, Mexico’s third largest city, the strand’s data centre has been incorporated into the legal framework for the state of Nuevo Leon.
- The ACROL strand has signed memoranda of understanding (MoUs) with key state organisations and has made good progress on seeing early uptake of G&I considerations where there had been challenges during initial engagements.
# Capacity
The two elements in the definition of capacity—knowledge and bandwidth—interact with each other, creating different programme management outcomes across the strands and at programme level.
## Knowledge
All strand suppliers were selected on the basis of putting forward impressive teams with extensive and demonstrable technical knowledge of their subject areas. The programme’s strand managers have, however, shared concerns about their own levels of relevant technical knowledge since the Cycle 1 evaluation.
Despite these concerns, the evaluators strongly believe that the teams have sufficient knowledge to manage the strands successfully. There is also clear evidence that each strand manager has learned a considerable amount in the two and a half years they have been engaged in design, planning and procuring suppliers. The successful completion of inception phases and early implementation phase achievements described above further underline this.
There are, however, two areas relating to capacity where there is potential for learning and improved effectiveness. The first of these relates to different approaches to strand management, where the strand managers have responded to the differences of technical expertise between themselves and the suppliers and stakeholders in different ways, and there is scope to learn from what has been most successful so far. This is discussed further in Section 7 below.
The second relates to contextual understanding. As illustrated by this stakeholder quote, not all knowledge relates to technical expertise. There is evidence that local stakeholders consider awareness of local context and networks as equally important and look for this in all programme staff (not differentiating between the supplier or other delivery partners in the way that the PT in Mexico City might). This aspect of capacity is linked to engagement. Learning on what has been effective here is explored more fully in Section 6.
The most important capacity is to understand the conditions for success in every locality.”
KII, local stakeholder
## Bandwidth
It is clear to the evaluators that staff members across the PT are dedicated and passionate about meeting the mission of the PF in Mexico. Nonetheless, challenges around fatigue and being overwhelmed with the amount of time it takes to deliver the programme and its strands were raised by staff at all levels within the PT.
The senior PF management in Mexico are aware of this issue and have expanded the team since the Cycle 1 evaluation to include a dedicated Governance and Communications Officer,[14] and to hire in two new positions, a Deputy Head of PF to support the Head of PF Mexico and a dedicated Secondary Benefits Officer to support the PT.[15]
[14] A specific recommendation made in the Cycle 1 Annual Review.
[15] The Deputy Head post was appointed in March 2020 from within the team; the SB Officer position was still in recruitment at the time of this writing. In the Cycle 1 evaluation, there was an SB Officer in the DIT whose portfolio included renewable energy and SBs. This individual has since left post, giving the PF team an opportunity to redefine the role to focus on SBs and support the PT.
The PT members note that these additions are welcome but might do little to reduce their respective workloads. The EL team therefore suggests a review of the staff’s level of effort, comparing workloads against similar UK departments, including the DFID and ICF, to identify practical measures to address the situation.
## Recommendations for capacity
The EL team recommends a stock-take of skills and roles with both the PT and suppliers to explicitly map where there are strengths and how to more efficiently coordinate roles and responsibilities. The Annual Review team is advised to monitor the progress of the task force investigating PT bandwidth and make its own recommendations.
# Engagement
Engagement here refers to relationships with external stakeholders across various levels of government and in different sectors, including the private sector, academia, civil society and wider public.[16]
[16] There is also an internal dimension to engagement, covering relationships within Post, the PT and suppliers—these are addressed separately below in the sections on governance and management.
Overall, engagement at both strand level and for the programme as a whole is productive, collaborative and participatory. The breadth of stakeholders has expanded substantially between Cycle 1 and Cycle 2, reflecting the greater complexity and engagement required of a programme in implementation. There is evidence that effective external engagement has been essential in getting the programme through its design and inception phases and into implementation.
However, the kind of the engagement varies between strands. There is evidence that when engagement is predictable, constructive and advances a shared agenda it contributes strongly to progress. Correspondingly, delays in engaging external stakeholders, regardless of the reason, risk negative consequences. The evaluators noted a correlation between the quality of internal team engagement and the quality and strength of external support, suggesting that clear internal collective agreement on key messages is helpful in promoting communication and acceptance by external stakeholders.
EL devised a three-point rating system to assess what has worked well and less well in terms of the way individual strands have carried out external engagement. This rubric is then considered across a range of factors as summarised in Table 1 below.
- Model indicates the strand is demonstrating best practice in programme management and can be considered a model for other strand managers to emulate where possible and relevant.
- Functional indicates the strand is performing to expectations for the specific factor. While there is room for improvement, at this early stage in implementation performance is adequate.
- Potential indicates there is room for improvement which would enhance strand delivery and performance. Other strands may offer insights on how to strengthen programme management outcomes.
Table 1: Contexts and factors influencing programme management outcomes
CONTEXT	ENERGY	FINANCIAL SERVICES	FUTURE CITIES	ACROL
Aligned with the National Development Plan. To what extent is the strand goal aligned to the 2019–2024 National Development Plan and how does that triangulate with PF goals and ODA principals?	Functional	Model	Model	Functional
Supported by key federal partners. To what extent is there proof of support by key federal-level partners and stakeholders?	Functional	Model	Model	Functional
Supported by key state partners. To what extent is there proof of support by key state-level partners and stakeholders?	Functional	Functional	Model	Functional
Strength of other networks. To what extent is there clear evidence for engagement and support from the following sectors?
Private sector	Functional	Model	Model	Potential
Academia	Model	Model	Model	Potential
Civil society	Potential	Model	Model	Functional
Community	Potential	Functional	Functional	Potential
Market demand. To what extent is there evidence that the strand responds to market demand relevant to its sector?	Model	Functional	Model	Potential
Balance of technical and local knowledge. To what extent is there sufficient technical knowledge grounded in the realities and networks in and across Mexico?	Potential	Model	Model	Potential

## Alignment with the National Development Plan
All strand teams have done a good job in articulating how the strand supports Mexico’s 2019–2024 National Development Plan and government policies. The strands which reflect the described priorities seem to have made more advances than those that do not, but it is not an exact correlation. Vigilance may be required to ensure the programme continues to reflect these priorities while also delivering UK objectives. Strand Programme Managers should periodically undertake a risk review of this triangulation and submit to the Programme Management Committee (PMC) for review and discussion.
## Support from key federal partners
All strands have invested substantial time engaging key government stakeholders, including ensuring participation by relevant senior-level officials in their respective Strand Governance Boards (SGBs). The result of this engagement varies across the strands. It is clear that support from federal authorities facilitates programme delivery and direction. Where there is less support or where this is only partial there is a corresponding risk of delayed delivery and a weaker sense of direction among delivery partners. EL recommends that the strand teams identify which government stakeholders have make-or-break authority over their strand and clarify engagement guidelines to create greater predictability.
A number of examples illustrate what has helped promote engagement:
- Some strands are using MoUs to define support and collaboration and establish clear roles and relationships with partners at all levels of government. Formalising relationships in this way is likely to support the delivery and achievement of programme objectives.
- Engagement from highly respected stakeholders has also helped to promote trust and confidence at key moments. For example, the Financial Services strand was officially launched into implementation by the London Lord Mayor and Mexico’s Minister of Finance and Public Credit. There is evidence from KIIs to suggest that this high-profile bilateral inauguration created momentum in the earliest days of the strand’s implementation.
- Strong existing relationships with government counterparts also helps. For instance, the Financial Services supplier has team members who were recently part of one of the lead government partners, the Comisión Nacional Bancaria y de Valores (CNBV), the National Bank and Securities Commission. The ability of the team to understand and engage the CNBV constructively, anticipating this institution’s own challenges and opportunities, has significantly contributed to implementing the strand’s second intervention.[17]
  [17] Intervention 2 seeks to strengthen the fintech sector by pursuing a regulatory and supervisory environment that fosters the creation and consolidation of innovative fintech to encourage a more widespread financial market for all.
- The Future Cities strand has a matrix of suppliers (‘the Alliance’)[18] that facilitates engagement with technical experts, local stakeholders and UK-based resource partners, promoting achievement of both primary purpose and secondary benefits. The dynamic engagement of members of the Alliance has been structured around a formal senior management team to create a well-informed circle of programme implementers. This arrangement uses the skills and networks of all members, promotes consistent messaging and helps to communicate expectations throughout the alliance’s membership.
  [18] The Future Cities Alliance is a mix of UK firms and Mexico-based CSOs. PricewaterhouseCoopers holds the contract; partners include Steer, World Resources Institute Mexico and the Institute for Transportation Development and Policy (ITDP).
## Support from state-level partners
Implementing the strands to deliver the results anticipated in the ToCs and logframes requires a combination of engagement and capacity. For example, where there is strong local buy-in and collaboration, evaluators noted greater progress. Where there is delayed engagement and communications with local stakeholders, there may be challenges in delivering outcomes as planned.
The strands have consolidated their plans for engaging local-level stakeholders (at the state and municipal levels) as the strand designs and plans were finalised during the inception phase.[19] At the time of gathering evidence for Cycle 2, not all strands had yet engaged their state-level stakeholders.[20] For those that have, there is evidence of greater appreciation for the goals of the PF and a willingness to support it and join efforts. For those strands that have delayed engagement, there is evidence of confusion about the intentions and functions of the PF. EL recommends that the strands that have yet to meaningfully engage state- and local-level stakeholders find a way to do so immediately.[21]
[19] By design, engagement to date has been at the institutional level and not yet at the individual beneficiary level in municipalities.
[20] Two months after the data-gathering period, all strands have now engaged state-level stakeholders.
We want to manage expectations and navigate all the interests effectively. You need a strong case built before you put it outside and let people punch it.”
KII, local stakeholder

[21] Even if this means writing an email or holding a conference call.
Each of the strand suppliers has deployed state or municipal local leads as part of their teams.[22] These leads are vital for outreach and delivery of strand activities. However, there is also a risk if efforts are not joined up that local stakeholders receive different messages and/or have too many demands placed on their time. This is especially relevant in Jalisco and Tabasco where multiple strands are active. EL recommends gathering supplier state or municipal local leads from different strands periodically (either virtually or in-person) to promote coherence and consistent messaging at local level.
[22] Each strand refers to these local leads with different titles, but they are referred to generically within the PT as supplier state or municipal leads.
There is good evidence that the strands have a sequenced plan for engaging additional states in subsequent years as activities consolidate into results.
## Engagement with other networks
The PF strands rely on a wide range of stakeholders from multiple sectors to strengthen programme delivery and impact. Each of the strands note these multi-sector stakeholders in their ToCs and engagement strategies. The evidence for having engaged these groups at this point in implementation varies.
- Private sector. The strand suppliers have created SB plans, which by definition include engagement with the private sector or related associations. The programme’s high-level Strategic Advisory Board (SAB) also includes private-sector representation in the form of the British Chamber of Commerce in Mexico. However, the inclusion of the private sector in delivering primary purpose ranges from strong, where the sector is clearly engaged, to more hypothetical, where delivery is either delayed or not yet inclusive of the private sector. Because of the density of PF programming in Jalisco and Tabasco in particular, EL recommends developing a strategic approach to engaging with the private sector.[23]
  [23] The Energy and ACROL strands plan to have a joint MoU with the state of Tabasco, which is an excellent example of official coordination. Similar approaches should be taken engage with other sectors mentioned here.
- Academia. Some strands are using stakeholders from academia as a way of strengthening the legitimacy and sustainability of programme design and delivery. This is an approach used to manage specific government policies and positions, particularly those related to working with the private sector and civil society. It is recommended that strand teams with slighter networks with academia consider how they can be incorporated into delivery.
- Civil society. All strands are engaging civil society from the community level up to national- and international-level civil society organisations (CSOs). Some SGB members encourage the strands to be strategic at how groups, particularly in the local level, are brought into meaningful discussions to ensure broad and sustained support for the PF and for its interventions. Again, this is especially important in Jalisco and Tabasco given the density of PF programming there. EL recommends mapping the engagement of CSOs to identify any overlaps and develop a strategic approach to working with them.
- Community. Two of the four strands—Financial Services and Future Cities—currently have clear relevance in engaging communities on a broader basis, although this may change as the other strands extend their programme engagement locally. Strong engagement and communication will promote sustained demand for the services that these strands seek to improve and make more inclusive. These strand teams are advised to coordinate closely with the local CSOs and local officials to reach deeply into communities to achieve the broadest level of grassroots support and demand.
- Market demand. EL anticipates that strands (or interventions within them) that are based on a clear understanding of end user beneficiaries or consumers are likely to have better delivery outcomes than those that are not. Examples of such a clear understanding include the Energy strand’s industrial baseline surveys, which assessed demand directly from potential users of the proposed services, or the use of a competitive selection process for city-level pilot projects by the Future Cities strand. Where strands (or interventions) have not directly engaged those who define their markets to formulate strand activities, EL recommends they do so and revise their strand designs accordingly.
## Balance of technical and local knowledge
The PT staff, suppliers and stakeholders all note that technical and local knowledge must both be present for effective programme delivery. Local knowledge is important to successfully implement the strands, which has implications for both capacity and engagement. Some strand suppliers consciously organised teams that balance technical and local knowledge, while others seem to be taking an immediate approach. Early evidence from the Mexico programme indicates that a more conscientious approach improves both efficiency and effectiveness. Now that the strands are in implementation, a mapping exercise to assess technical and local knowledge (and gaps) may prove helpful for further engagement and management of the strands.
## Other recommendations
In addition to the issues already discussed, EL recommends the following measures which apply in general to engagement work:
- Develop concise narratives with graphics and images which reflect the programme’s ToCs to use across digital platforms and in hard copy, promoting a stronger understanding of the scope of PF in Mexico for a range of audiences and stakeholders.
- Ensure engagement plans are up to date, particularly given changes in the last year at municipal, state and federal levels, and aligned with the strand’s G&I strategies.
# Governance
## Programme and cross-post governance
The overall architecture for programme governance was assessed in detail in the Cycle 1 evaluation report and remains fit for purpose. At the highest level is the SAB, which is chaired by HMA and includes different federal Ministries. Within Post, the Programme Management Committee serves both strategic and operational purposes. It is also chaired by HMA and includes all heads of sections and programmes. At the strand level, there are SGBs.[24] The SGBs are designed to be advisory bodies rather than decision-making ones.
[24] With the exception of the Energy strand which has the Board of the EPI Centro to fulfil similar functions.
The most notable changes since the Cycle 1 report include the growing complexity of different initiatives (including non-PF ones) at Post. For example, in addition to the bilateral PF programme, other Post initiatives include projects from the PF’s six global programmes,[25] an ICF portfolio of projects, the Newton Fund and the Catalyst Fund (a PF-funded global finance programme run through the Department of International Development (DFID) from London).
[25] Transparency and Anti-corruption (other government departments), Global Skills and Global Health (both held by DAI UK), Global Anti-corruption, Global Infrastructure, Global Finance (DFID Catalyst Fund) and Global Trade (held by EY).
As each of these programmes (and their sponsoring departments, including BEIS, DIT and DFID) has grown its engagement and activities across the new political and economic landscape of Mexico, Post coordination has become increasingly important and intensive. Nonetheless, the Programme Management Committee and the virtual teams continue to play an important and effective role in the PT’s ability to coordinate and leverage other UK activities and investments.
In some strands, the virtual teams (VTs) are regarded as an important component of technical expertise within Post and in linking PF activities to DIT to support the achievement of SBs. In other strands, there is evidence that VTs have rotating participants, which requires conversations to be reiterated so that everyone is on the same page. This can reduce momentum and create frustration.
Informal linkages between staff at Post have also been important in promoting coherency (beyond the formal governance and management structures). These linkages are sustained, for instance, where individuals hold multiple roles or report to different line managers beyond the PF team and create webs for information-sharing across team boundaries. Harnessing existing organic linkages and actively promoting them is especially important given there are no formal resources to support cross-linkage between bilateral and in-country global programmes.
The SAB is the governance body for all UK programmes in Mexico. Its initial meetings were well attended by senior government stakeholders, during which the programme was given clear federal government positions on engagement and shared focus. However, the evaluators note that this body has not met since September 2019, with its December 2019 and March 2020[26] meetings both cancelled. It is important to ensure it remains a functioning body.
[26] The March 2020 PF SAB was cancelled due to the COVID-19 crisis.
## Strand-level governance
The ACROL and Future Cities strands have held two SGBs since moving into implementation, Financial Services has held three and Energy has yet to convene its governance body. There is clear evidence that the SGBs are promoting a breadth of idea sharing, creating new networks across an evolving federal landscape and enabling strands to make informed implementation decisions based on reasoned expertise from different stakeholders and sectors. In some cases, the SGBs also provide a forum for state-level authorities to interact with federal-level counterparts. The specific experience of convening the SGBs has varied:
- For Future Cities, the SGB noted that there was insufficient time to pursue the phasing in of pilot city activities as originally planned and advised the PT and supplier to begin simultaneous delivery of all five. In following the SGB’s guidance, the PT showed it values the SGB, which in turn increased the trust held by SGB members.
- For ACROL, its second SGB revealed an unexpected question by a key government stakeholder. The time needed to address this led to delays in implementation, and the situation required escalation to HMA and her senior team. Nevertheless, the situation is now resolved and there is good evidence that federal and state authorities are fully and productively engaged in strand delivery.
- For Energy, the EPI Centro SAB has been delayed as the PT consolidates key government relationships before the board is convened. It is understandable, given the ACROL experience, that the strand team want to ensure full government support and backing. However, there is evidence from KIIs that this delay is creating challenges to communication and engagement, particularly at the local level. Energy and ACROL have an agreement with the governor of Tabasco to sign a joint MoU, which is now delayed until conditions permit.
- There is good evidence that the Financial Services SGB plays a variety of important roles such as strategic adviser, ally, network-builder and risk assessor. For example, in the second SGB, members offered concrete suggestions on the scope of intervention 1, possible stakeholders and partners and provided possibilities of linking with similar initiatives in Mexico’s southern region, where poverty is most profound.
There is a delicate balance to be maintained in the SGBs. While terms of reference (ToRs) for these SGBs exist, expectations and roles must be continuously calibrated. Overall, there is strong evidence that the SGBs are contributing to the delivery of the strands as envisioned. On occasions, however, some high-level SGB members delegate their participation to more junior staff members. EL recommends that the Strand Programme Managers re-affirm the value of the high-level presence and reduce the frequency to delegate participation.
Where SGBs have already experienced obstructive behaviour on the part of one or two individuals, EL recommends a review of the SGB membership to create a broader range of representation, particularly adding local voices to balance out national-level ones.
# Management
## Programme level management
Overall, the management practices established across the Mexico PT are good. There is clear evidence that the PT is conscientious and mission-oriented. A set of issues and possible areas for improvement identified through the evaluation are discussed here but should not be taken as detracting from this overall judgement.
### Risk management
Risk management was a key focus of the Cycle 1 Annual Review and the EL team recommends that the Annual Review team return to the theme with equal vigour now that there are concrete examples of how the Post departments have mobilised and coordinated. There is some evidence that risk management is facilitated on a person-to-person basis from within the supplier or from the strand team. While this is consistent with Mexico’s cultural context and speaks volumes for the credibility and professionalism of the strand managers, it is important that the PT holds delicate conversations from an institutional perspective. This reduces the risk that solutions are tied to specific relationships and is important to ensure institutional memory of risk management given the likelihood of staff turnover.
### Financial due diligence
The PT is relatively new to the complex financial management required of large programmes.[27] Likewise, UK government-compliant reporting is new to many of the supplier firms. There is evidence that the financial reports submitted have improved with experience. The Strand Programme Managers have adopted an audit recommendation to review 10 per cent of invoices to assure compliance as part of the PT’s risk management processes. The team did well to identify some discrepancies, illustrating good financial due diligence and VfM practices. EL suggests that the Annual Review team pursue this inquiry further.
[27] The PT noted that they were familiar with project-level management, but the scale and scope of PF strands are substantially more complex.
### Service-level agreements
Service-level agreement (SLA) compliance and reporting tends to be managed by the suppliers’ UK-based headquarters and not from the strands Mexico-based central delivery units. The PT does have a process in place for engaging with these UK-based contract managers to review SLA compliance, which was just being tested during drafting of the evaluation.[28] Evidence suggests that while SLAs are not fully clear to all Strand Programme Managers, the regular tracking required in the SLAs has already revealed discrepancies that are being further investigated within the PF team in Mexico.[29] The EL team recommends that the Annual Review team explore the potential to strengthen the utility and management of SLAs during its analysis of Cycle 2.
[28] The quarterly SLA performance reviews began two months after the evidence for this cycle had been gathered.
[29] KII with PF Contract Manager.
### Communication of key concepts
As with any endeavour, the PF has generated a considerable amount of its own terms and definitions in both English and Spanish. There is some evidence that PF terms are not always understood by suppliers and other delivery partners. There might be some value in returning to the glossaries that accompanied the Mexico programme BC and updating these to reflect the tremendous amount of progress made in terms of scope and language. These glossaries could be translated into Spanish and shared at SGBs or included in service contracts as needed to foster greater clarity in PF communications.
### Central guidance
There is evidence that the further along the PF Mexico Programme is in implementation, the less need there seems to be to seek guidance from London (either from the JFU or the PFDU) for certain aspects. Central guidance has remained a sore point for the team, with most guidance delayed, received when it was no longer needed, arriving after a work-around was developed or insufficient for Mexico’s context. In Cycle 2, there is evidence that late guidance related to SLAs delayed the transition from inception to implementation. Other documents and templates that delayed action include MoUs with stakeholders,[30] non-disclosure agreements and guidance on SLAs, payment by results and gender-sensitive budgets.
[30] As opposed to MoUs with delivery partners, which function more like contracts.
### Learning across the programme team
There is clear evidence that the recommendations made to the PT in the Cycle 1 evaluation were acted upon. Annex 12 provides a summary of actions against the programme-level recommendations made in the Cycle 1 evaluation and Annual Review, which the PT identified as critical to address.
The PT also noted that they had important take-aways from the inception phase and the evaluation and have put their insights into action, indicating a key area in which value has been derived from both the evaluation and annual review process. Examples of learning points include:
- Linking Theories of Change to programme designs and ensuring that these link to the wider Prosperity Fund Theory of Change. The PT noted that the first evaluation enabled it to gain perspective on the mid-inception status of the connections between the programme designs presented in the bids, the emerging ToCs and the PF ToC overall.
- Incorporating criteria on all the themes—gender and inclusion, value for money and secondary benefits. The PT cited the evaluation as providing constructive insights on how to strengthen the thematic elements in their ToCs, their strand designs and in the milestones being produced by suppliers at the time. In particular, the insights related to increasing the role of social inclusion, beyond gender, were timely and largely reflected in subsequent ToCs and logframes of the four strands.
- Leveraging the benefit of cross-learning. The PT found value in assessing the way the team works across strands. After testing these methods and gaining insights from the evaluation, the PT began bringing suppliers into these approaches; for instance, having suppliers’ communications leads meet regularly to synchronise messaging. An inter-strand governance board to discuss how agile programme funds will be spent and to consider cross-cutting proposals has also been put in place.
- Managing virtual team effectiveness. During inception, the VTs were central to the technical design and strategic positioning of the strands. The PT gained insights from the evaluation and have enacted new mechanisms to ensure coordinated links into government and private sector.
According to KIIs, both JFU and PFDU also considered the recommendations provided in the seven evaluations submitted by EL in 2019.
## Strand-level management
The PT and strand suppliers defined their relationship, approaches, methodologies and goals over time. This definition started with the Statement of Requirements (SoRs) and initial bids, through the awarding selection into contract negotiation, and throughout the inception phase as a variety of milestone documents were prepared, discussed and approved. While each strand undertook these internal procedures, different management styles emerged.
The factors that promote a positive programme management outcome contribute to a greater predictability of processes, which seems to lead to greater levels of mutual trust.[31] This mutual trust seems to lead to a higher degree of confidence in actions and strategies, which in turn seems to lead to a more consistent pace of engagement and delivery of activities.
[31] Between the strand team and the suppliers.
There is evidence to suggest that Strand Programme Managers who have adopted a more executive style of programme management are seeing more positive outcomes. This style of management places a high degree of trust in supplier’s expertise and information and its ability to use the resources available appropriately and fully, with the PT and supplier sharing a strong vision for process and progress.
Other Strand Programme Managers have adopted a more directive, ‘line management’ approach with suppliers. In these examples, suppliers perceive that strand teams focus on what they know, which is a subset of the issues that require attention and decisions to be made.
Table 2 reviews the performance of different strands, based on the same three-point rating system (model, functional, potential) used above to assess external engagement.
Table 2: Contexts and factors influencing programme management outcomes
CONTEXT	ENERGY	FINANCIAL SERVICES	FUTURE CITIES	ACROL
Explicit role definition. To what extent do the PF and Embassy teams and the supplier understand each other’s roles and responsibilities?	Functional	Functional	Model	Functional
Consistent key personnel. To what extent has there been consistency in vision and design within the PF team and the supplier?	Potential	Functional	Model	Functional
Inclusive decision making. To what extent are crossroad decisions taken collaboratively by the PF team and the supplier?	Potential	Model	Model	Functional
Shared mission focus. To what extent do the PF team and supplier share a goal-based focus of the strand and programme as defined by the ToC?	Model	Model	Model	Functional
Mutual trust. To what extent is trust mutual and tangible between PT and supplier?	Functional	Model	Model	Functional
Confidence in strategies and actions. To what extent do the PF team and suppliers have confidence in their strategies and the actions needed to deliver on them?	Functional	Model	Model	Potential
Pace of engagement and delivery. To what extent is engagement supporting timely delivery against plans and targets?	Functional	Functional	Model	Functional
Effective messaging. To what extent is the messaging from the PF team and the suppliers consistent across all audiences?	Functional	Functional	Model	Functional
Predictability of processes. To what extent do the PF team and the suppliers characterise processes as predictable?	Potential	Model	Model	Potential
Coherence between governance and management systems. To what extent do governance bodies support the management systems within the strands?	Functional	Model	Model	Potential

### Explicit role definition
There are differences in how the strand teams and supplier roles are defined at a functional level. This creates variations ranging from an executive-style role taken up by the Strand Programme Manager to a style of management that strives to focus on every detail. It is suggested that leadership and communications training[32] could address this. A specific discussion between the PT and suppliers may also be useful in explicitly discussing the desired roles and ways of engaging each other.
[32] All strand teams were required to take PRINCE2 programme management training prior to the inception phase. Now in implementation, strand teams may benefit from leadership and functional communications skills development to complement their PRINCE2 training.
### Consistent key personnel
Evaluators noted two different findings regarding key personnel. There is evidence that consistency in the strand suppliers’ senior leadership contributes to greater consolidation of vision, messaging and delivery approaches. In this regard, changes in key personnel demonstrates adaptability as there is evidence that the replacements have reinvigorated their strands and strengthened alignment with government policies and stakeholders as well as with PF goals.
### Inclusive decision making
There is evidence of two broad types of engagement with suppliers. One maintains a client–provider relationship (top-down and linear), the other cultivates a partnership relationship (collaborative and iterative). This distinction can be seen in the quality of the PT–supplier relationship, the level of buy-in among programme principals and the progress made in the strands. While external factors do enter the equation, the level of inclusiveness in discussing and managing those factors creates a qualitative, material difference in strand performance. Strand Programme Managers should assess how to improve the potential for inclusive decision making.
### Shared mission focus
Each of the strands underwent changes in their designs and scope throughout their respective inception phases. Some of these changes were modest, while others required wholesale revision due to substantial changes in the programme environment. There is evidence that not all strands emerged from this process with a shared vision. EL recommends using the review of strand’s ToCs and logframes in autumn 2020 to consolidate progress to date and re-establish a clear and shared vision within and across the strands.[33]
[33] An MREL ToC and logframe review, similar to one undertaken in Colombia in March 2020, can help the PT and suppliers clarify and elevate their ToCs as these are now based on actual interventions rather than anticipated activity. This recommendation was made prior to the COVID-19 virus. The changes that this pandemic will bring about will surely require strategic decisions by the PT, informed by their suppliers and key stakeholders.
### Mutual trust
The quality of trust between the strand teams and their suppliers varies. Trust is built on a combination of factors, including the confidence in ability and knowledge, alignment and sharing of a vision, the positive engagement with stakeholders and partners, and the quality of management and administrative processes. Strand teams should take time to reflect on expectations for themselves and their suppliers and hold a conversation to discuss these expectations periodically to improve on each of these dimensions over time.
### Confidence in strategies and actions
The degree to which the PT and the suppliers have confidence in the strategies and action plans also varies. In some cases, there is a good deal of enthusiasm for how strategies can lead to long-term, sustainable goals through the activities currently underway. The strength of confidence is tied to the degree to which the PT and suppliers (and delivery partners) see the direct connection between what they are doing and what the PF hopes to achieve. A review and revision of the ToCs and logframes that tightly connect objectives, strategies and actions should improve the confidence of all those delivering PF programmes.
### Pace of engagement and delivery
The pace of engagement and programme delivery is tied to the elements noted above, including shared vision, strategy, confidence and trust. These combine to support or limit delivery against plans and targets. Where there is a higher correlation among these elements, there is evidence of a more positive rate of delivering against plans and targets. Where there is less correlation among these elements, there is evidence of delaying delivery which probability of falling short of targets over time. This has implications for the efficiency and effectiveness of the overall programme. This provides further support to the recommendation already made to provide training in leadership skills and communications for the PT.[34] Where necessary, strand teams might create a continuous improvement plan, building on their respective SLAs with suppliers.
[34] This should be broken down into digestible modules to ensure that PT members can accommodate this training into their already busy schedules (see Capacity).
### Effective messaging
The Mexico Programme focuses its messaging on the primary purpose of the PF: to strengthen inclusive growth to reduce poverty. There is evidence that this message focus has led to confusion among some suppliers as to why they should also pay attention to delivering SBs. Other suppliers are clear on how and even which types of SBs they intend to deliver, but struggle with how they message this aspect of the PF activities to stakeholders. Most stakeholders might not differentiate between the PF strands (which means that some strands are engaging the same stakeholder knowingly or not), while some do not differentiate between PF and other Embassy programmes (which means that different programmes and departments are engaging the same stakeholders knowingly or not).[35] Effective messaging supports the delivery of both primary purpose and SBs, and supports efficiency, effectiveness and equity. EL recommends that the PF strands[36] refresh the local stakeholder maps they created during inception and share them among themselves and with the PMC. EL further recommends that the VTs review these refreshed stakeholder maps to identify and account for any cross over or multiple programmes engaging single stakeholders to leverage engagement, coordinate activities and harmonise messaging.
[35] Recent changes in VT coordination are likely to mitigate this risk from within Post.
[36] The PF global programmes in Mexico should join this mapping exercise.
### Predictability of processes
The PT and suppliers across the four strands report varying levels of predictability in PF processes, which emerges from both governance and management systems. Strand teams (PT and suppliers) who describe a higher degree of predictability are more likely to demonstrate greater progress in their strand delivery, a higher degree of trust and satisfaction, and greater commitment to the PF mission. Where there is evidence of less predictability, the reverse is true. EL recommends that the PT and suppliers take stock in management processes now that implementation has begun and systems are becoming more regularised to identify gaps in flow and predictability.
### Coherence between governance and management systems
The SGBs were designed to address the information and networking needs for each strand. The coherence between governance and management has a direct impact on programme delivery. Now that the strands are in implementation and most of the governance bodies have met at least once, the PT should assess the potential to strengthen the contribution of the SGBs where possible and necessary.
## Other recommendations on management
The following additional recommendations would appear to be particularly pertinent to the Annual Review:
- Explore the potential to strengthen the utility and management of SLAs during its Cycle 2 analysis to ensure that administrative management is as strong as programme management.
- Return to the theme of risk management now that there are concrete examples of how the Post departments mobilised and coordinated to deliver positive outcomes.
- Explore the internal audit processes used since the Cycle 1 reports.
- For the PT, the EL team suggests returning to the glossaries that accompanied the Mexico BC and revise these to include the terms that have emerged since to ensure clarity in communications.
# Programme-level Theory of Change
This section summarises key points from an assessment of the programme level ToC. A full analysis is included in Annex 10.
The programme ToC is a composite of the four strand-level ToCs. It shows how the programme as a whole will lead to higher-level results, thereby achieving the long-term goal set out in the Mexico Programme impact statement. The Mexico PT decided to concentrate on developing strand-level ToCs and logframes first, and then to update the programme-level ToC subsequently, once the strand ones had been finalised. At the time of the Cycle 2 evaluation, the programme ToC had not yet been revised. However, a working ToC created with the support of the Monitoring and Reporting (MR) Hub in August 2019 was used for this assessment following the PT’s suggestion.
Overall, the Mexico Programme is conceptually sound, although the working version of its ToC does not adequately reflect the fullness of analysis and applied learning. The ToC can be improved primarily in three ways:
- Ensure the ACROL strand fully aligns with and supports the primary purpose of the Fund.
- Revise the programme ToC to reflect the strands’ pathways and logic more accurately since moving from the conceptual stage of design to the tangible stage of implementation.
- Develop a corresponding narrative to the programme ToC to capture better the nuance, linkage and leverage that the programme might offer across the strands and more broadly.
# Gender and inclusion
## Overview
The Mexico Programme invested in enhancing its G&I programme designs during the development of the BC in 2018 and with additional support from the JFU, PFDU and the other advisory services in 2019. The results of this early investment are seen across all five elements of the EL G&I scorecard.[37]
[37] The scorecard methodology allows an assessment of how well G&I elements are integrated into PF programmes and covers: programme design, internal capability/institutional incentives, financial resources, accountability mechanisms and partnerships.
G&I issues in Cycle 2 were subjected to a ‘light-touch’ review given that the Cycle 1 evaluation covered G&I in detail.[38] Table 3 shows the progression of the Mexico Programme’s G&I scores, covering:
[38] See Annex 5 for an illustrative interview guide for G&I questions asked during KIIs and Annex 6 for sub-questions under EQ4, EQ9 and EQ10 related to a G&I review. The EL team also assessed the four suppliers’ milestone documents—the Gender and Inclusion Mainstreaming Strategy and Action Plans, the Stakeholder and Community Engagement Strategy and Action Plans, the costed Workplans, and the logframes and strand indicators—to complete the document review for the Cycle 2 G&I review.
- The February 2019 review of the BC and SoRs for suppliers
- The May 2019 scores generated in the Cycle 1 evaluation
- The April 2020 scores produced in this evaluation cycle.
Table 3: Comparison of G&I scorecard scores for the Mexico programme 2019–2020
PROGRAMME	PROGRAMME DESIGN	INTERNAL CAPABILITY / INSTITUTIONAL INCENTIVES	FINANCIAL RESOURCES	ACCOUNTABILITY MECHANISMS	PARTNERSHIPS
February 2019	3	3	2	3	3
May 2019	3	3	3	3	3
April 2020	4	4	3	3	4

KEY	1: Not aligned with the Gender Equality Act	2. Insufficient alignment	3. Minimum level of alignment	4. Potential for economic empowerment for women and girls	5. Potential for transformation

## Programme design
Both gender and social inclusion elements have been incorporated into both the focus of the programme and its processes. Each of the suppliers submitted milestone documents that anticipated and addressed G&I opportunities during their inception phases, and several strands have conducted further analysis to strengthen their focus. The Mexico Programme includes activities in the north and central areas as well as the poorer southern region (see Figure 2 in Section 3.2), where poverty and exclusion is greatest. For example, the Energy and ACROL strands have hubs and centres in Tabasco and the Financial Services strand has extended its programming to Campeche on the Yucatan Peninsula. The PT is considering options that might increase its reach in the south, for instance using agile programming funds to share results from the five pilot cities[39] with municipal and state authorities in the south. Doing so could strengthen the programme’s focus on inclusion.
[39] Hermosillo, Guadalajara, Monterrey, Querétaro and CDMX.
## Internal capability/institutional incentives
Each of the strand suppliers’ key personnel include a highly qualified, well-regarded G&I Advisor in senior management. In addition, the strand suppliers’ resource pools include organisations with strong G&I reputations. There is evidence that suppliers provide consistent G&I training and materials as the strand stakeholder sets continue to expand. For example, ACROL and Future Cities have invested early engagement opportunities to introduce G&I themes to technical professionals—engineers and prosecutors—who might not have a strong background in this area. There is also evidence that while some government partners might not have G&I considerations in their mandate, the PT and suppliers work to ensure that G&I objectives are served. There is also evidence that G&I elements are requirements for participating in PF programming. For example, all proposals considered for Future Cities pilots and projects must include a substantial G&I component and ACROL have also included G&I diagnostics into their early engagement with federal and state stakeholders.
## Financial resources
The strand suppliers each delivered a costed work plan for the initial year of implementation and an outline work plan for subsequent years.[40] These documents clearly identify the financial resources being applied to G&I, such as G&I training sessions and expenses related to G&I-specific staff and consultants. However, these costed work plans likely undervalue the total financial commitment to supporting G&I objectives. There is no evidence to assess the financial resources dedicated to ensuring the participation of women or individuals from marginalised groups in strand or programme activities, which is often more time-consuming and resource intensive than when reaching into a majority or male population. The EL team do not recommend collecting this data (the process would be time consuming and could detract from programme delivery) but do encourage the PT and strand suppliers to consider this G&I dimension when assessing its financial allocation.
[40] Inception Phase Milestones 3.2 and 3.3.
## Accountability mechanisms
The programme uses a variety of accountability mechanisms in its constituent strands to ensure G&I considerations, goals and processes are respected. Regular reporting, including weekly calls, monthly reports, quarterly reports and annual reports each provide a formal venue for monitoring G&I implementation and progress. The evidence from programme reports indicates that suppliers submit reports with adequate information and actionable insights.
Table 4: Gender and inclusion indicators in the Mexico Programme strands
LOGFRAME LEVEL	ENERGY	FIN. SERVICES	FUTURE CITIES	ACROL
Impact	2	6	2	0
Outcome	5	5	6	0
Intermediate Outcome	5	7	1	3
Output	2	8	1	9

The programme aims to be transformative in its G&I impact. While strand ToC narratives and other design documents address G&I, the strand logframe indicators fall short of enabling the programme to document and report against its aspirations. In a review of the strand ToCs available on Prospero, G&I indicators are not represented with equal rigour across the four strands (see Table 4). Financial Services has the most robust use of G&I indicators in its logframe. ACROL has no G&I indicators at the outcome or impact levels. This is not consistent with the strand’s ToC and should be addressed.
Early in the inception phase, the PT convened what was to be a monthly gathering of the strand G&I Advisors together with the PT’s G&I cross-cutting lead. These meetings were discontinued shortly afterwards (even though they had been identified as best practice), and EL strongly encourages holding them at least quarterly if not monthly.[41]
[41] This coordination is consistent with other cross-strand groups that the PT uses to ensure leverage and coordination throughout the PF Mexico Programme.
## Partnerships
The milestone plans and strategies provide ample evidence that the partnerships created by the programme and its constituent strands to date reflect a commitment to support G&I objectives. For example, in KIIs with the state officials linked to the Energy strand, these officials spoke of equality as an important factor in their work and therefore an important point of alignment with PF objectives.
The strand resource pools include national organisations that provide entry into a whole range of CSOs, government authorities, private sector firms and academia with a focus and established track record in support of gender and social inclusion. The strand SGBs also support PF Mexico’s G&I objectives. Each of the SGBs, as well as the SAB, the high-level governance board for UK programming in Mexico, is constituted to build gender balance and create channels of communication with G&I institutions and actors.
## Gender and inclusion recommendations
- A specific effort to hone the G&I indicators should be undertaken during the review of strand and programme ToCs and logframes in autumn 2020. This should include providing G&I indicators at outcome and impact level for the ACROL strand.
- The PT should define all terms associated with G&I in both English and Spanish to ensure that indicators are properly defined, identified, measured and reported against.
- The EL team encourages the PT and strand suppliers to consider the financial reporting aspect of G&I as it assesses its G&I activities. This could include a qualitative assessment of how and to what extent resources are being dedicated to G&I objectives, rather than a detailed revision of existing reporting forms.
- The PT and the strand G&I Advisors are strongly encouraged to renew their regular meetings, if not monthly then at least quarterly, to capture progress in G&I results, identify areas for collaboration and ensure consistent messaging.
# Value for money
## Value for money scorecard assessment
The EL VfM scorecard was used to assess the four strands, with the strand scores then aggregated into an overall programme score—see Annex 8 for further details of the method and results.[42] Overall, evaluators rate the Mexico Programme’s VfM as good with a current attainment score of 3.53 out of 5 and a direction-of-travel score of 3.56 out of 5.
[42] Individual strand findings will be offered in additional Cycle 2 learning products.
Table 5: Mexico Programme Cycle 2 value for money scorecard
ELEMENT	ATTAINMENT	DIRECTION	COMMENTS
1. VfM measures	3.25	4	Need to combine the indicators used in the logframe to monitor progress of delivery with cost indicators to allow focused VfM management.
2. Cost containment	3.75	3.5	Effective steps have been taken to monitor spending (10% of invoices have been reviewed) and a review team that includes the Programme Manager, the Programme Officer, the Finance Officers and the Contract Management Strategy Lead has been appointed to identify and resolve any irregularities. An external audit of the suppliers is planned for 2020.[43]
3. Efficient use of resources	3.5	3.25	The finance team has capacity gaps associated with being new to their roles, but the PT is part of the review process for all financial reporting and has more experience to offer to this process.
4. Theory of Change	3.25	3.5	These scores are mainly driven by the assessment of the programme-level ToC in this evaluation report.
5. Sustainability	4	3.5
6. Ability of leadership	3.25	3.25	The leadership roles of the PMC and SAB in the delivery of the programme may need more focus. For example, the ToRs are high level and need some revisiting with respect to SBs.
7. Risk	3.75	3.75	There is a good risk management system in place and risks are discussed with the PMC and SGBs. The PT and HMA confirmed a clear line of sight from junior team members to the SRO allowing new risks to emerge and be discussed.
8. Equity	3.5	3.5	Gender and social inclusion play a key role in the design of the Mexico Programme and all its strands.
SCORE	3.53	3.56	Aggregated score (see Annex 8).
[43] The procurement for this audit has been delayed due to the COVID-19 situation, but the audit is still planned.

Value for money measures: All strands have developed indicators for their logframes. These have not yet been combined with cost indicators to allow for meaningful VfM indicators that would provide programme management with an immediate overview. A planned autumn 2020 MREL review of ToCs will provide an opportunity to consider and build in these VfM indicators to strand- and programme-level documents.[44]
[44] In 2018, the JFU provided guidelines for VfM indicators. These include: type 1 – monetary indicators compare the value of the programme (in monetary terms) against the cost; type 2 – quantitative indicators compare how much the programme has achieved (in numbers) against the cost; type 3 – qualitative indicators compare the kind of change the programme has achieved (in descriptive terms) against the cost; type 4 – indicators of systems/processes describe how VfM is being ensured (in management terms) compared to cost.
Cost containment: The cost containment and risk management steps taken by the PF have proven to be useful. Now that invoices are coming in, there have been instances with invoices not being in line with the expenses policies. That these are being found and challenged by the PT during spot checks and financial review is good evidence that there are robust procedures in place.
Efficient use of resources: Capacity has been and is likely to be a future risk to efficiency in Mexico’s programme and strands. Capacity gaps in terms of technical capacity as well as bandwidth could cause bottlenecks which lead to delays elsewhere. While some of the central capacity needs have been addressed (Deputy Head of PF hired and a SB Advisor role in recruitment), there are other capacity gaps. One of these identified in the evaluation is with the central finance team, which is comprised of two team members who are comparatively new to their roles.
There are capacity issues regarding HMA’s time. She plays a crucial role in representing the PF programme to ministers and senior officials in the Mexican government and HMG. In one KII, HMA was said to be one of the most articulate and informed SROs in the PF Network,[45] but her time is constrained. With recent challenges requiring her input now resolved, it would be useful for the PT to assess how much they anticipate needing HMA’s attention as the programme progresses, to provide more predictable and efficient calls on her time.
[45] KII with London-based stakeholder.
Theory of Change: Overall, the strand-level ToCs provide the causal pathways to deliver primary purpose and SBs. The programme-level ToC, once it is revised and finalised in autumn 2020, should clearly identify points at which the strands leverage—or even co-deliver—selected outputs and intermediate outcomes (IOs). Clarifying these VfM details will strengthen the programme and strand ToCs.
Sustainability: Sustainability of outcomes is mainly driven by measures taken at strand level. However, central governance, engaging external stakeholders and strategically positioning the Embassy close to federal- and state-level decision making influence sustainability by providing the necessary conditions within the Mexican government for them to want to preserve benefits derived from the PF investment.
Ability of leadership: The Programme’s governance structure includes a series of teams, committees and boards which cover a range of issues relevant to VfM. It would nonetheless be useful to review the respective ToRs of these bodies to ensure a specific reference to VfM is within their remit.
Risk: The PT conducts spot checks of invoices and has discovered discrepancies. While their discovery illustrates effective cost containment and governance, spot checks are time consuming and may not represent optimal VfM over time. EL recommends that the Annual Review team consider this balance of due diligence and time use in its Cycle 2 review.
Equity: There is good evidence that the programme and the strands have dedicated time and attention to ensuring G&I considerations have been worked into designs, ToCs and logframes. This is discussed in detail in Section 10 above.
## Value for money recommendations
There are a number of ways in which VfM performance could be strengthened. While each of these measures will contribute, they are (approximately) ordered in terms of priority.
- The PT should review the 2018 JFU guidance on VfM indicators and incorporate these into both the strand and programme ToCs to monitor delivery progress and allow focused VfM management.
- It would be useful to review the respective ToRs of the governance and management bodies (the SAB, the PMC and the SGBs) to ensure that VfM is specifically referenced in their remit.
- The leadership roles of the PMC and SAB in delivering VfM for the programme should be reviewed and revised as needed.
- As noted elsewhere, the PT should define key terms on the subject of inclusion in the context of Mexico and apply these equally across all strand ToCs and logframes.
- The PT should review the risks associated with cost containment and efficiency in a reduction of competition, particularly regarding a single firm holding multiple delivery contracts within PF Mexico.
- The Strand Programme Managers should assess how much they anticipate needing HMA’s attention as the programme progresses, including when her involvement would be needed so that she can best structure her time and focus.
- EL recommends that the Annual Review team consider this balance of due diligence and time use in its Cycle 2 review.
# Secondary benefits
The Mexico PF has made good progress in defining SBs, creating opportunities and cooperating to deliver them, and has achieved some early successes. It is clear that successful delivery of SBs will require ongoing coordination between the PT, suppliers and DIT. There is evidence that the necessary elements—strand team, VT, DIT and suppliers—are already in place, each with plans. The challenge going forward is to ensure that each party both understands its role and executes that role consistently and fully. A detailed assessment of SB performance for each strand is presented in Annex 8 and supports this assessment at programme level.

Table 6: Secondary benefit types identified in Cycle 2 secondary benefit analysis[46]
[46] SBs as noted in the respective milestone SB Plans from the four strands.
SB TYPE	ENERGY	FIN. SERVICES	FUT. CITIES	ACROL
Exports
Foreign direct investment (FDI)
Overseas direct investment (ODI)
Network effects
Market access (including imports)
Soft power

## Programme secondary benefit analysis
The Mexico Programme is well placed to deliver SBs and has already started to do so. The Energy strand has already contributed to export wins totalling GBP 21 million. Those SB types already delivered include exports and soft power—see Table 7:
Table 7: Selected secondary benefits that the programme has contributed to
SB TYPE	EXAMPLES FOR DELIVERED SBS AND OPPORTUNITIES
Exports	Security at major sporting events such as CONCACAF[47] 2022 World Cup qualifiers (ACROL).
Soft Power	Negotiating a cost-saving adjustment to air traffic regulations to enable UK airlines to continue flying as under EU open skies agreement.
Network effects	DIT ran a seminar with the University of Cambridge on oil and gas–related research questions. PEMEX sent 20 people, allowing the UK and other attendees to network and build relationships in this sector.[48]
[47] CONCACAF is the Confederation of North, Central American and Caribbean Association Football.
[48] Source: KII with DIT official.

There is also scope for the other SB types to emerge (market access, ODI and FDI).
Suppliers have SB plans intended to align with PF and Post objectives. There is, however, evidence of confusion that PF spending can be a SB—the PT should remind suppliers that this is not the case.
There are contextual barriers which need to be taken into consideration when evaluating progress made.
## Contextual barriers
The Mexican federal government has reservations regarding the concepts of SBs and ‘mutual prosperity’,[49] creating potential challenges to delivery of SBs.. Mexico government’s perception of corruption might raise another challenge to SB delivery as it could difficult for the programme to introduce international and UK companies to federal authorities, although this is less the case at state level.
We have a very positive relationship with the PF team – very well coordinated. Our activities function and operate according to plan. The PF is very good for the DIT team because it covers important, High Value Campaigns.”
KII, DIT

[49] Interviews with PT, DIT staff and suppliers.
Other challenges include newly introduced local content requirements which restrict the share of projects that can be delivered by other international businesses, including UK businesses. While this works in favour of achieving primary purpose by involving Mexican micro, small and medium enterprises (MSMEs) in PF projects, any follow-on opportunities that create SBs also have to comply with these regulations.
## Secondary benefit governance across the programme
The PT is aware of the need for a coherent SB approach across the programme. Businesses who communicate with the Embassy and the PF team tend not to differentiate between different strands, teams or other PF global programmes, highlighting the need for clear and consistent communication with them across all teams. However, there is strong evidence that the VTs have had a positive impact on the likelihood of delivering SBs.[50]
[50] Interview with the DIT Lead on Financial Services (and other DIT staff).
While SBs are included in the remit of the PF’s governance structures (i.e. PMC and SAB), the current ToRs for these bodies focus mostly on an increase in trade between Mexico and the UK. This creates a possibility that the full range of SBs and their delivery do not benefit from strategic oversight.
Recommendation: Given the programme context, it would be useful to review the ToRs of the PMC to clarify its role in the oversight of delivering the six types of SBs.
## Coordination and management
Being clear about roles and responsibilities in delivering SBs is important to avoid duplication of effort and overlooking gaps. However, despite the clear evidence for existing coordination between DIT and PF teams to deliver SBs, there is also evidence of misunderstandings. One of the reasons for mixed messages might be that DIT’s focus is on delivering against its targets of exports, FDI and ODI, while the PF aims for a wider array of six SBs, with soft power being an important enabling SB that leads to further benefits.
Recommendation: EL recommends bringing the PF and DIT teams closer together at all levels. The VTs have achieved close cooperation at the working level but there are still gaps in understanding at the more senior middle-management level. Revised PMC ToRs as suggested above could support this. The JFU and senior management at Post should also consider how to address the gap created by DIT’s targets for exports, FDI and ODI, focused on UK companies and the wider PF objectives, and bring the governance of SBs in each strand closer to the PF governance as a whole by requesting progress updates.
## Practical steps for delivering secondary benefits
There is evidence that some suppliers are carefully planning how to support achievement of SBs,[51] but there is still some uncertainty from some suppliers and for some types of SBs.[52]
[51] Future Cities, SB Strategy.
[52] KII with strand supplier.
Box 1: Examples of advanced planning and weak planning
Recommendation: The PT should ensure learning across the programmes on SB planning and delivery structure.
Other steps taken include the use of trade associations as multipliers,[53] or to work across the Latin American countries involved in the PF.[54] This reflects the multinational nature of many of the UK and international companies that may be interested in delivering SBs.
[53] Interviews with DIT staff.
[54] Interviews with DIT staff.
# Recommendations
## Recommendations for the Prosperity Fund network
The evaluation generated a range of areas for improvement, as set out in Table 8 below. These were reviewed at a findings and recommendations workshop held with the PT on 11 May 2020. From the list presented in the table, the following three should be priorities for strengthening the programme:
- Update the pathways to change for each strand, to reflect changes since moving from the design phase into implementation.
- Identify the areas in which the programme could increase its potential for impact, focusing on those where there is potential for strands to support each other’s impact. This assessment should explicitly consider soft power and development of commercial networks, as factors likely to facilitate greater future trade and investment successes.
- Support further leadership skills development of the PT to enhance strategic planning and operational delivery of each strand and the programme more broadly.
Table 8: Recommendations for the Prosperity Fund network
REFERENCE	RECOMMENDATION	LEAD ACTOR(S)	TIME FRAME
Programme
Capacity
Section 5	Utilise the recommendations throughout this evaluation to structure the action plan for the incoming PF Deputy Head.	PF Head and Deputy Head, together with PT MREL Advisor	April–December 2020
	Undertake a stock-take of skills and roles within the PT and suppliers to explicitly map their strengths and improve the coordination of roles and responsibilities.	PTs and senior leadership in Central Delivery Units	Before Cycle 2 AR begins
	Assess the PT’s level of effort and offer practical recommendations to mitigate fatigue.	PF Prosperity Counsellor and PT	By Cycle 2 AR submission
Engagement
Section 6	Bring supplier state and municipal leads together periodically to ensure communication and messaging consistency to improve engagement.	PT, governance and communications officers, suppliers and locally deployed team members	Quarterly
	Develop brief strand flyers to inform PF progress across SGBs—anchor language in ToCs and indicators; use graphics.	PF Head and Governance and Communications Officer	July 2020 (updated every six months)
	Proactively identify and leverage the links within Post.	PMC, Deputy Head of PF	Quarterly
	Explicitly discuss and identify the desired roles and ways of engaging each other during implementation.	PT and strand suppliers	Autumn 2020
	Undertake a mapping exercise to assess technical and local knowledge to advance engagement and coordination across and within strands.	PT and strand suppliers	Autumn 2020
	Review engagement expectations with government stakeholders which have make-or-break authority over strand implementation.	Strand Programme Managers, Head of PF, SRO	As soon as conditions permit
	Refresh the strand stakeholder maps from inception from the municipal, state and federal levels and share across strands and with the PMC.	Strand Programme Managers, strand suppliers, Governance and Communications Officer	Autumn 2020
	Review these stakeholder maps to identify and account for any cross-over or multiple programmes engaging single stakeholders to leverage engagement, coordinate activities and harmonise messaging.	VTs, PMC, PT	By 31 December 2020
	Map the engagement of sector stakeholders in Jalisco and Tabasco (due to density of PF activities) to identify any overlaps and opportunities for engagement from different areas of the programme.	Strand Programme Managers, strand suppliers, DIT	Before Cycle 2 AR begins
	Coordinate closely and over time with local CSOs and local officials to reach deeply into communities to achieve the broadest level of grassroots support and demand.	Strand Programme Managers, strand suppliers	As soon as conditions permit
	Directly engage those who define their markets to revise strand designs accordingly to support the PF objectives in both Mexico and in the relevant IOs at the Fund.	Strand Programme Managers, strand suppliers, Deputy PF Head, PT MREL Advisor, EL Sector Leads	As soon as conditions permit
Governance
Section 7	Reaffirm the value of high-level presence and reduce the frequency of delegated SGB participation.	Strand Programme Managers	Annually
	Review SGB membership to create a broader range of representation, particularly adding local voices to balance national-level ones.	Strand Programme Managers	Annually
Management
Section 8	Revise the glossary of PF terms in the BC to account for programme progress and nuance to date to improve clear and shared understanding of terms.	Governance and Communications Officer, PT MREL Advisor	September 2020
	Complete a diagnostic for leadership and communications training and incorporate into individual professional development plans for the coming year.	Strand team	By end of FY 20/21
	Take stock of management processes now that implementation has begun and systems are becoming more regularised to identify gaps in flow and predictability.	Strand Programme Managers, strand suppliers	By 31 December 2020
	Identify strengths and gaps in the connection between SGBs and strand ability to manage respective programmes.	Strand Programme Managers, strand suppliers	Autumn 2020
	Undertake a risk review of triangulation between national policies and UK PF priorities.	Strand Programme Managers, Head of PF, SRO	Annually
Theory of Change
Section 9	Revise ToCs to more accurately reflect the programme now that it moved from conceptual stage of design to tangible stage of implementation.	PT, MREL	Autumn 2020
	Produce a supporting programme ToC narrative to strengthen causal pathways and present the strategies for G&I, VfM and SBs.	Head and Deputy Head of PF, PT MREL Advisor, MREL	By 31 December 2020
	Review key documents and ensure these are posted on Prospero.	MR Hub, Programme Evaluation Lead and PT MREL Advisor	Quarterly
G&I
Section 10	Renew G&I Advisors Group to advance G&I programming elements and mitigate gaps.	Suppliers’ G&I Advisors and PT G&I Cross-cutting Lead	Quarterly
	Generate specific definitions for key inclusion terms (marginalised, disadvantaged, and vulnerable) and build into revised logframes.	PT MREL Advisor and PT	Before 2020 Annual Review
VfM
Section 11	Combine logframe indicators with cost indicators to allow for meaningful VfM indicators.	PT, MREL	Before Cycle 3
	Assess the PT’s need for HMA’s attention and map expectations of when that involvement would be needed.	HMA, Head of PF, PT	September 2020
	Identify where and to what extent strands may leverage or co-deliver on selected outputs and IOs.	PT, PT MREL Advisory	Autumn 2020
SBs
Section 12	Ensure the PT communicates that spending of PF money can never be counted as an SB.	PT, SB Advisor, strand suppliers	Immediately
	Review the PMC ToR to reflect fully on its role in the oversight of the delivery of the six types of SBs.	PMC, SB Advisor	Autumn 2020
	Ensure that DIT and the PF at the senior middle management level have a shared understanding and appreciation of SBs and their delivery.	PMC, DIT, SB Advisor, Deputy PF Head	By 31 December 2020
	Ensure that all types of SBs that the programme is helping promote are monitored and reported on.	PMC, DIT, SB Advisor, Deputy PF Head	By 31 December 2020
	Ensure learning across the strands with respect to planning and delivery structure for SBs.	SB Advisor, PT	Ongoing

## Recommendations for the Annual Review
Table 9: Recommendations for the Cycle 2 Annual Review team
LESSON	RECOMMENDATION	LEAD	TIMEFRAME
Section 5	Monitor the progress of the level of effort task force and make its own recommendations.	Cycle 2 Annual Review team	May–July 2020
Section 6	Interview UK-based contract managers to assess SLA compliance and feedback.	Cycle 2 Annual Review team	May–July 2020
	Assess the reporting structure associated with SLAs to confirm it best serves the PT.	Cycle 2 Annual Review team	May–July 2020
Section 8	Explore the potential to strengthen the utility and management of SLAs to ensure that administrative management is as strong as programme management.	Cycle 2 Annual Review team	May–July 2020
	Review risk management now there are concrete examples of how the Post departments mobilised and coordinated.	Cycle 2 Annual Review team	May–July 2020
	Explore the internal audit processes used since the Cycle 1 reports.	Cycle 2 Annual Review team	May–July 2020
	Review the financial reporting and review process to confirm its efficacy.	Cycle 2 Annual Review team	May–July 2020
	Assess the role of SGBs and the PT’s ability to manage their respective programmes.	Cycle 2 Annual Review team	May–July 2020

Annex 1: Cycle 2 Approach Paper

Annex 2: List of key informants
Note: individual names have not been included here in line with government guidance.
Table 10: List of key informants
#	ORGANISATION	POSITION[55]
1	UK Embassy	Her Majesty’s Ambassador
2	UK Embassy	Head of PF Mexico
3	UK Embassy	PF Mexico Counsellor
4	UK Embassy	Energy—Strand Programme Manager
5	UK Embassy	Energy—Strand Programme Officer
6	UK Embassy	FS—Strand Programme Manager
7	UK Embassy	FS—Strand Programme Officer
8	UK Embassy	FC—Strand Programme Manager
9	UK Embassy	ACROL—Strand Programme Manager
10	UK Embassy	ACROL—Strand Programme Officer
11	UK Embassy	PF Economist/MREL Coordinator
12	UK Embassy	PF Governance and Communications
13	UK Embassy	PF Global Trade Programme Manager
14	UK Embassy	ICF/MX Programme Director
15	UK Embassy	Senior Economist
16	UK Embassy	DIT—Regional
17	UK Embassy	DIT—FS and FC Virtual Team
18	UK Embassy	DIT—ACROL Virtual Team
19	UK Embassy	PF Contracts
20	UK Embassy	PF Finance
21	UK Embassy	PF Finance
22	PFDU London	Head of Prosperity Fund Delivery Unit
23	DAI—Energy Supplier	Programme Director & Team Leader
24	DAI—Energy Supplier	MREL Leader
25	SEDENER/Tabasco	Energy Transitions
26	Secretaría de Igualdad Sustantiva/Jalisco	Chief of Staff
27	DAI – Financial Services supplier	Programme Director
28	DAI – Financial Services supplier	Team Leader
29	DAI – Financial Services supplier	MREL Leader
30	DAI – Financial Services supplier	Inclusion, Education, Gender Leader
31	DAI – Financial Services supplier	Inclusion, Education, Gender Manager
32	CNBV – Comisión Nacional Bancaria y de Valores	General Director for Regulatory Development
33	CNBV	General Director Fintech Supervision & Innovative Models
34	CNBV	Deputy General Director Fintech Supervision & Innovative Models
35	CNBV	Deputy General Director Fintech Supervision & Innovative Models
36	SMT Future Cities Alliance	Programme Director
37	SMT Future Cities Alliance	Team Leader
38	SMT Future Cities Alliance	Deputy Team Leader
39	SMT Future Cities Alliance	G&I Lead
40	Future Cities Central Delivery Unit	MREL Lead
41	Future Cities Central Delivery Unit	C&R and SB Lead
42	Future Cities Central Delivery Unit	Mexico Programme Manager
43	UNO Mujeres	Sustainable Cities Programme Manager
44	Inter-American Development Bank	Transport and Mobility Expert
45	SEMOVIL	Head of Strategic Projects
46	PA Consulting-ACROL	Programme Director
47	PA Consulting-ACROL	Team Leader
48	PA Consulting-ACROL	Programme Liaison for CDMX
49	ACROL-EQUIS	Director
50	ACROL-EQUIS	Director of Programmes
51	Secretaria de Gobernación	Director, Unit to Support the Justice System
52	Secretaria de Gobernación	International Relations Director
53	Secretaria de Gobernación	Evaluation Deputy Director
54	Fortis Consultores	Director
55	Fortis Consultores	External Advisor
[55] CEGM refers to capacity, engagement, governance and management, the four priority learning areas identified by the PT during the Cycle 2 planning workshop in December 2019.

Annex 3: Bibliography
The following programme and secondary documents constituted the bulk of the literature reviewed for the Cycle 2 evaluation. Additional websites were consulted and are cited in footnotes throughout.
Table 11: Bibliography
#	DOCUMENT TITLE	DATE
PROGRAMME
1	Mexico Prosperity Programme Business Case	December 2018
2	Mexico Programme Cycle 1 Approach Paper	April 2019
3	Mexico Programme Cycle 1 Evaluation Report	August 2019
4	Mexico Prosperity Fund 2019 Annual Review	October 2019
5	Mexico Programme Theory of Change (ppt)	August 2019
6	Prosperity Fund Strategy Advisory Board Terms of Reference	March 2019
7	Strategic Advisory Board Minutes	6 June 2019
8	Mexico Deputy Head of Prosperity Fund Job Description	March 2019
9	DIT Prosperity Fund Commercial Lead Job Description	December 2019
10	Mexico Programme Quarterly Report Q3 2019/2020	January 2020
STRAND
ENERGY
11	Milestone 2.1—MREL Engagement Plan	May 2019
12	Service Level Agreements—Energy	June 2019
13	Milestone 2.4—Gender & Inclusion Mainstreaming and Action Plan	November 2019
14	Milestone 2.5—Climate & Resilience Strategy	December 2019
15	Milestone 3.2—Costed Annual Workplan (final)	December 2019
16	Milestone 3.3—Outlined WP Subsequent Years—Narrative	October 2019
17	Milestone 3.3—Outlined Workplan Subsequent Years—Excel	October 2019
18	Milestone 3.4—Delivery Chain Map	December 2019
19	Milestone 4.4: Industrial Baseline Study Phase 1	December 2019
20	Milestone 4.4 Evidence-Based Inputs to EPI Centro Pilot Definition	January 2020
21	Milestone 4.5 Workforce Gap Assessment	December 2019
22	Impact Pie VT Energy	September 2019
23	Secondary Benefits Log	January 2020
24	Theory of Change	January 2020
25	Updated Energy Logframe 3.1 (in Prospero & in Excel)	January 2020
26	VfM Self-Reporting Scores	January 2020
27	Energy and Low Carbon Family Approach Paper	April 2019
FINANCIAL SERVICES
28	Service Level Agreement—Financial Services	June 2019
29	Milestone 2.2 Climate and Resilience Strategy and Action Plan	August 2019
30	Milestone 2.3 Gender and Inclusion Mainstreaming Strategy	August 2019
31	Milestone 2.4 MREL Plan	August 2019
32	Milestone 3.2 Workplan for the first 12 months	August 2019
33	Milestone 3.3 Workplan subsequent years and closure	August 2019
34	Milestone 3.4 Delivery Chain Map	December 2019
35	Financial Services Theory of Change	September 2019
36	Financial Services Logframe (in Prospero & in Excel)	October 2019
37	Financial Services Virtual Team Impact Pie	January 2020
38	Secondary Benefits Plan - Draft version	January 2020
39	Strand Governance Board 1st Meeting Minutes	June 2019
40	Value for Money Scorecard Self-assessment	January 2020
41	Financial Services Family Approach Paper	April 2019
FUTURE CITIES
42	Service-Level Agreements – Future Cities	June 2019
43	Milestone 2.1 Plan for MREL Engagement	June 2019
44	Milestone 2.4 Draft Gender and Inclusion Strategy and Action Plan	June 2019
45	Milestone 2.5 C&R Strategy and Action Plan	July 2019
46	Milestone 3.2 Year 1 Detailed Costed Workplan – Narrative	August 2019
47	Milestone 3.2 Year 1 Detailed Workplan – Commercials Document	August 2019
48	Milestone 3.3 Subsequent Years Outline Workplan	August 2019
49	Milestone 3.4 Delivery Chain Map	August 2019
50	Draft Secondary Benefits Strategy and Action Plan	November 2019
51	Secondary Benefits Draft Project Plan – Project 1 – Mexico City Governance and Finance Reform	November 2019
52	Secondary Benefits Draft Project Plan – Project 3 – Monterrey Mobility Data Project	November 2019
53	Theory of Change	September 2019
54	Future Cities Logframe v3 (in Prospero & in Excel)	October 2019
55	Strand Governance Board 1st Meeting Minutes	July 2019
56	Value for Money Scorecard Self-assessment	January 2020
57	Future Cities impact pies	September 2018
58	Future Cities Family Approach Paper	March 2018
ACROL
59	Selection of Crimes Analysis	April 2019
60	Milestone 2.2 Climate and Resilience Strategy and Action Plan	May 2019
61	Milestone 2.3 The Gender and Inclusion Strategy	October 2019
62	Milestone 2.4 Plan for MREL Engagement and Compliance	September 2019
63	Milestone 3.1 Implementation Workplan Narrative	September 2019
64	Milestone 3.2 Costed Workplan	December 2019
65	Milestone 3.3 Workplan subsequent years and closure	November 2019
66	Milestone 3.4 Delivery Chain Map	November 2019
67	Approach to Service Levels Monitoring	November 2019
68	Theory of Change	August 2019
69	ACROL Logframe V2.0 (in Prospero & in Excel)	October 2019
70	Secondary Benefits Plan	January 2020
71	Value for Money Scorecard Self-assessment	January 2020
72	Transparency and Anti-Corruption Family Approach Paper	May 2019
SECONDARY DOCUMENTS
73	National Development Plan 2019–2024	April 2019
74	Anticorrupción en la seguridad pública, Segunda edición. Alejandro Carlos Espinosa Rafael Francisco Ortiz de la Torre, Guardia Nacional	December 2019
75	El Futuro del Sistema Nacional Anticorrupción de Mexico: La lucha anticorrupción bajo el mandato del Presidente López Obrador. Gina Hinojosa y Maureen Meyer	August 2019
76	Objetivo de Desarrollo Sostenible 11: Ciudades y Comunidades Sostenibles, Gobierno de México	September 2017
77	Programa de Impulso al Sector Financiero, Secretaría de Hacienda y Crédito Público	January 2019
78	Acuerdo Nacional de Inversión en Infraestructura del Sector Privado, Presidencia de la Republica y Consejo Coordinador Empresarial	November 2019
79	Issues Paper on Corruption and Economic Growth, OECD	September 2013

Annex 4: Methodology
The evaluation addressed six of the overall evaluation questions set for the Prosperity Fund as a whole. These were then tailored to the Mexico programme by defining a set of context-specific sub-questions (see Table 12 below). The research process then collected and reviewed information to answer these, based on an assessment of the learning priorities, as well as cross-programme thematic assessments on Gender & Inclusion, Value for Money and Secondary benefits as illustrated in Figure 3:
Figure 3: Evaluation Questions and lines of inquiry in the Cycle 2 evaluation

Table 12 illustrates how the analysis was undertaken in practice. Specifically, it shows how the EQs are cross-referenced with Cycle 2 sub-questions. It then shows how the different assessments undertaken by the evaluation team were considered to answer these questions, including:
- The five dimensions of the G&I scorecard[56]
  [56] The G&I dimensions are: (1) programme design; (2) internal capacity/institutional incentives; (3) financial resources; (4) accounting mechanisms; and (5) partnerships.
- The eight elements of the VfM scorecard[57]
  [57] The eight VfM elements are: (1) VfM measures; (2) cost containment; (3) efficient use of resources; (4) Theory of Change; (5) sustainability; (6) leadership; (7) risk; and (8) equity.
- The four elements of the SB analysis[58]
  [58] The SB analysis includes: (1) SB types; (2) measurement; (3) delivery; (4) coordination; and (5) governance.
- The PT’s four learning priorities for Cycle 2.[59].
  [59] The four learning priorities are capacity, engagement, governance and management (C, E, G, M in the table), which were identified by the PT during the Cycle 2 planning workshop in December 2019.
The full evaluation matrix is presented in the Cycle 2 Approach Paper (see Annex 1). A complete assessment of the programme and its four strands through the 12 Fund EQs can be found in Annex 6.
Table 12: Cycle 2 Integration of inquiry tools and learning priorities
EVALUATION QUESTION[60]	EVALUATION SUB-QUESTIONS	G&I DIMENSION	VFM ELEMENT	SB / ANALYSIS	LEARNING / PRIORITY
EQ1: What evidence is there that the programme is likely to contribute to intended outputs and intermediate outcomes, as well as any unintended/unexpected effects?	1a. What evidence is there that forecast primary purpose and secondary benefits for different strands are still likely to be achieved, given changes in the context since the approval of the BC? / 1b. Does the current trajectory of strand implementation have implications for the scale of benefits likely to be achieved? / 1c. How can the programme’s progress to date inform strategic decisions about programme design and allocations going forward?		4	1, 2, 3, 4	Capacity, Engagement, Governance, Management
EQ4: What evidence is there that interventions will be sustainable? Will they: / ensure environmental sustainability? / be sustained after programme closure? / lead to inclusive growth that reduces inequality?	4a. What arrangements does the programme have in place to ensure it is as receptive and flexible as possible to changing political conditions likely to impact on programme sustainability? / 4b. What lessons can the PT identify that will help them anticipate challenges in the future that may deter or limit sustainability?	1	4, 5, 6	2, 3, 4	Capacity, Engagement, Governance, Management
EQ5: What factors have contributed to the achievement of primary purpose and SBs?	5a. To what extent has technical capacity influenced the achievement of primary purpose or SBs to date? / 5b. Does the PT have/know what it needs to deliver all that has been promised? / 5c. To what extent have changing political environments influenced achievement of primary purpose or SBs to date? / 5d. To what extent does engaging various stakeholders influence the achievement of primary purpose or SBs to date?	2, 5	1, 2, 3, 4, 6, 7, 8	1, 2, 3, 4	Capacity, Engagement, Governance, Management
EQ7: Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements need to be made?	7a. What factors have most influenced the evolution of the programme ToC to date and why? / 7b. Are approaches and processes for (i) collecting, (ii) verifying data quality and (iii) analysing data sufficient to validate programme ToCs?	1, 2, 5	1, 4	1, 4	Capacity, Engagement, Management
EQ8: To what extent is the institutional governance set-up of the PF more or less effective in achieving (i) primary purpose (ii) SBs (iii) other results?	8a. How does the PT ensure that the governance systems in place are still optimal to achieve primary purpose? / 8b. Are plans to achieve SBs clear and measurable, and are arrangements to deliver them appropriate? / 8c. How does the PT balance PF coherence and coordination while maintaining alignment with other British Embassy projects?	2, 4	3, 6	1, 2, 3, 4	Engagement, Governance, Management
EQ9: What types of approaches, governance and management arrangements have been effective for achieving results and demonstrate good approaches to inclusive growth and VfM?	9a. How has utilisation of risk management tools enabled the PT to identify, escalate, and/or resolve issues within their respective strands to support primary purpose and VfM? / 9b. How have governance and management approaches served to strengthen institutional linkage and programme continuity? / 9c. To what extent do governance and management systems enhance clarity, coordination and project impact? / 9d. Are programme governance arrangements effective and are their required resources appropriate in terms of achieving VfM?	1, 2, 3, 4, 5	3, 6, 7	2, 3, 4	Capacity, Engagement, Governance, Management
[60] EQs and indicative judgement criteria as approved in the EL Inception Report March 2018.

### Limitations
The limitations identified on the Cycle 2 Approach Paper (see Annex 1) were mitigated during the initial three months of the cycle with the support of all required actors. There remain limitations to this evaluation, however. These include the following:
- Evaluators used a draft of the ToC created with the support of the Monitoring and Reporting (MR) Hub in August 2019 for this assessment (rather than the final version).[61]
  [61] The PT decided to concentrate on finalising strand ToCs during 2019 and the BC ToC is too out-of-date against which to evaluate the programme.
- KIIs were primarily conducted in Mexico City. Two interviews with state-level stakeholders were conducted by telephone. The EL team, supported by the PT, decided that there was little value in travelling to engage local stakeholders directly in this cycle.
A final limitation was having consistent documentation available for review in a timely manner. Having more robust and consistent data on Prospero will alleviate some of this challenge in future. Greater clarity on the documents the strands routinely create will also improve EL’s ability to request those documents.
### Learning for the Evaluation and Learning team
After submitting the Cycle 2 Approach Paper, the JFU requested greater clarity about the lessons the EL team learned in the Cycle 1 process and what steps were taken to apply those lessons to Cycle 2 engagement. Eight specific lessons were learned and acted upon, several lessons of which come from the early weeks of Cycle 2.
- Sequencing programme team interviews to allow for thoughts to emerge. Cycle 1 KIIs were one-off, three-hour interviews with the strand teams. This approach left no time for capturing ideas that bubble up after an intensive conversation. Cycle 2 KIIs were divided into a two-hour session at the beginning of the data-gathering fortnight and a one-hour conversation at the end of it. The two sets of KIIs gave both the PT and evaluators time for reflection, which allowed for more nuanced questions and information sharing.
- Anticipating the time needed to complete value for money self-assessments. During Cycle 1, the PT did not complete the VfM self-assessments as the time provided proved to be too short for the new methodology. In Cycle 2, evaluators provided a detailed but brief document on how to complete the VfM self-assessment and doubled the amount of time given for its completion. As a result, all four strands submitted a VfM self-assessment in Cycle 2.
- Building in more time and various ways for the programme team to review drafts. During Cycle 1, the PT and the EL team agreed to a schedule with a week of review time for draft documents. This was insufficient, particularly as the document neared its final form and required the SRO’s review. In Cycle 2, the PT and the evaluators agreed on a mix of ways to review the evaluation draft, including document sharing, a findings and recommendations workshop and online conference calls.
- Planning ahead for evaluation report dissemination. The Cycle 1 evaluation has yet to be circulated. The ownership of the report was not clear until several months after the report had been received by the PT, which was eager to make use of the findings and recommendations. These were cut and pasted into non-attributable documents so that the PT could engage their suppliers in time-critical discussions during the inception phase. A publication policy has recently been made available and the PT are planning the dissemination of the evaluation report to its stakeholders in both Mexico and the UK.
- Making more of an explicit linkage between the Evaluation Report and Annual Review. The timing of this evaluation has been explicitly linked to the Annual Review since Cycle 1. However, the EL team saw an opportunity to improve the planning and design of the Annual Review by directing specific recommendations to the Annual Review team. Drawing out specific recommendations for the Annual Review is intended to assist the Head of PF in Mexico to prepare the ToRs for the Annual Review team and to support the identification of required skills and expertise of that team.
- Aligning message and language. The Cycle 1 interviews were limited to internal stakeholders within the Embassy in Mexico and were, therefore, straightforward. With the external stakeholders for Cycle 2, the PT and the EL team worked together to craft a narrative that explained the EL role, and how information would be collected, stored and used. This narrative was prepared in English and Spanish and was validated by the PT’s Governance and Communications Officer. The lesson learned was that the time and care required to develop the narrative was well used, building greater trust between the PT and the EL team, creating a useful narrative about EL that the PT can use in other circumstances, and providing a clear introduction to important stakeholders that the PT and EL team will engage with throughout implementation.
- Setting deadlines for constituting the Evaluation and Learning team. This lesson was learned in the first weeks of Cycle 2. Due to delays in approval of one of the EL team members, the evaluator did not join the team until two days before the KIIs began. This left the evaluator with 48 hours to review and digest an enormous amount of information before flying to Mexico City. In future cycles, EL will seek to confirm and contract all team members no less than one full working week before any direct engagement with the PF principals or stakeholders.
- Securing documents throughout the year. In Cycle 1, the Mexico Programme documents were limited to the milestones and, therefore, easily identifiable. In Cycle 2, the documentation increased and it was not always clear to the EL team what existed. Prospero was not populated with programme documents at the time of evidence-gathering apart from strand logframes and indicators. The Programme Evaluation Lead will work with relevant PT staff to ensure that documents required for evaluations are routinely posted on Prospero or oth
Annex 6: Gender and inclusion Cycle 2 questions and analysis
Through its strands, the Mexico PT demonstrates consistent and good attention to G&I against the five dimensions of the scorecard (see Section 10). In short, there are no significant gaps in Mexico’s G&I inclusion approaches, but the PT believes that there is room to consolidate the existing good practices, strengthen its approaches and share lessons within the PF Mexico network and beyond.
In addition to the G&I scorecard dimensions reviewed in Section 10 of this report, the PT have recently raised additional questions related to its G&I positioning and performance to date.[62] Responses to these, based on the Cycle 2 evidence, follow below. The PT is discussing further areas of exploration with EL’s G&I Lead and the Programme Evaluation Lead, which would supplement this Cycle 2 analysis later in this fiscal year (2020/2021).
[62] These questions came after evidence-gathering, however, KIIs and document review enable EL to provide the response based on Cycle 2 evidence.
Do we have the right team leadership composition?
The PT included specific stipulations in the SORs when the strands went to market in June 2018 to ensure that G&I would be addressed in bids that were received. For example, SoRs required that key personnel include a senior-level, recognised and respected G&I specialist.[63] Proposals were also vetted against the centrality of G&I in strand designs and objectives.
[63] Early emphasis was on gender expertise given early guidance. The re-prioritisation of social inclusion came after the strands were in their respective inception phase. This was described in the Cycle 1 Mexico Evaluation Report.
Evidence shows that each of the four strands have recognised and respected G&I experts as part of their senior management teams, who integrate their expertise appropriately at that level. These advisors formed a community of practice group together with the PT’s Cross-cutting Lead for G&I early in inception to exchange ideas and solutions to strand development challenges. While this was recognised as a best practice in the Cycle 1 evaluation, the group’s engagement was not sustained. Several KIIs indicated that the time demands within each strand overtook the G&I Advisors’ time and focus. As noted in Section 13 of this evaluation, it is critical that this group re-engage to support cross-strand learning on both gender and social inclusion and to transmit insights and lessons deeply into their respective strand structures. It would be useful if the communications leads from the strand suppliers joined these sessions to support the disbursement of ideas and messages to their respective strand principals and partners.
How are strategies being operationalised and what tools does the PT have to verify progress?
Senior advisors with G&I expertise represent one element of capacity to deliver activities and programmes that achieve G&I results. The PT also wants to know how the strategies and plans developed as inception milestone documents are utilised to inform, monitor and report.[64] There were many strategies and action plans created by the strand suppliers during inception that addressed G&I themes. This emphasis is obvious given the primary purpose of the PF to promote greater inclusive economic growth to reduce poverty.
[64] At a minimum, these milestone documents were the Gender and Inclusion Mainstreaming Strategy and Action Plans, the Stakeholder and Community Engagement Strategy and Action Plans, the costed Workplans and the logframes and strand indicators. Some strands provided concentrated G&I analysis in their Climate and Resilience Plans, most notably the ACROL supplier.
Evaluators assess the extent to which G&I strategies are poised to be operationalised is by cross-referencing the strategies with the Year 1 costed workplans. This evaluation was too soon after implementation to assess the delivery against most of the G&I strategic elements. Overall, there is a traceable amount of strategic action backed up with financial resources during this coming year of implementation (see Section 10.4 of this evaluation for the financial resources dimension.) This evidence leads evaluators to anticipate delivery against the plans, which will be scrutinised in the Cycle 3 evaluation.
The strand teams have tools to support the monitoring, reporting and evaluation of G&I progress. These include the strands’ ToCs and logframes, regular reporting and governance mechanisms, such as the strands’ individual SGBs and cross-Post bodies such as the VTs and the PMC.
- Theories of Change: Different strands have differing levels of specificity related to ToCs, with some strands (Financial Services, Future Cities and Energy) including gender up to their impact statements. Some indicators are challenging to decipher specific targets, particularly when they are embedded in indices, as is the case for Future Cities and ACROL. As noted in the evaluation report, the ToC narratives are important to understanding the deeper analysis and context of these ToCs, including G&I elements and the pathways and supporting evidence for the achievement of these. The ToCs would be improved if some of this analysis was reflected in the ToCs themselves.
- Logframes: The strand logframes have been in near continuous evolution since inception. While opting for an adaptive approach to programme management is a basic premise of the PF, logframes cannot be used as management tools if the indicators and metrics are constantly changing. There is little evidence to suggest that logframes have been used apart from monitoring early outputs, which are already captured in regular reports. There are several recommendations in Section 13 that, if addressed, could improve the utility of the logframes as a management tool.
- Regular reporting: Each strand has a layer of established reporting from weekly calls between Strand Programme Managers and suppliers, monthly reports and quarterly reports, including stakeholder and community engagement quarterly reports. There is no evidence to suggest that the information flowing in these channels is shared beyond the respective strands. This means that insights and lesson learning related to G&I are not shared as widely as they should or could be. The PT could make more robust use of the Prospero platform, which is designed not only to house logframes, but has directories to upload quarterly reports, stories and lessons. PFLearning is another platform that the PT could use to share questions, ideas and insightful reports.
- Governance mechanisms: There are layers of governance mechanisms within strands and across the programme. For the strands, this includes the SGB, or in the case of Energy, the EPI Centro strategy advisory board. For the programme, there is the SAB, which provides high-level oversight to the PF programme in Mexico as well as for other UK programmes, such as the International Climate Fund, the Newton Fund, etc. There is good evidence that G&I functions of these bodies are both topical and representational. Topical in that G&I programme elements are discussed and advised on during the sessions; and representational in that the composition of SGB was specifically created to reflect gender balance in its members and in the competencies of institutions participating. In the Future Cities strand, there is evidence that one SGB member in particular is instrumental in connecting the strand implementation teams to local organisations and actors to facilitate community engagement. There is little evidence that these various governance bodies intersect or mutually reinforce the others, although it may be too early in the life of these bodies to add complexity to their respective ToRs.
- Management approaches: The strands each have a central delivery unit which is the centre for programme management on the supplier’s side. Some strands have a complex central delivery unit, as is the case with Future Cities. Some strands have created strand-specific advisory boards to further inform G&I analysis and decision-making, as is the case with Financial Services. The Energy team have relied on resource partners to create excellent analysis on the labour market dynamics within the energy sector through a G&I lens. The Future Cities team draws on the matrix of supply partners to train PTs and project partners on G&I themes. The results of this training can be seen in the consistent and high-quality proposals that come from municipalities and from the G&I-sensitive approaches that technical teams are adding to their analysis and planning. ACROL has a lean management profile, but it has already engaged a key state-level stakeholder to undertake an internal diagnostic of its G&I practices and policies very early on in the strand’s implementation. As the G&I Advisors did not meet regularly after the mid-point of inception, strands have missed the opportunity to exchange ideas and suggestions that are emerging from early progress and learning from different implementation approaches.

What does this look like in the strand suppliers costed workplans?
The PT has expressed some interest in gender-sensitive budgeting in the last year and sought JFU support in this regard in autumn 2019.[65] The costed workplans developed by the suppliers as they transitioned from inception to implementation have varying levels of clarity in showing financial resources supporting G&I activities or costs. As noted in Section 10.3 in this report, the Future Cities strand costed workplan has the most obvious and clearly identifiable expenditures related to G&I, with the G&I Advisor’s costs separately broken out as well as costs for internal and external G&I trainings.[66] The Energy strand has gender, inclusion and sustainability line items which can be used to discern expenditure. The ACROL strand has costed activities against coded outputs. One could cross-reference the documents to assess financial expenditure to achieve broad G&I goals. Financial Services has narrative reference to resources to deliver general strand activities in its workplan document, but evaluators did not have access to a Year 1 budget for the strand.
[65] The PT has not yet received support on gender sensitive budgeting.
[66] Even here, evaluators anticipate that this limited disaggregation of costs will lead to undercounting of the GBP value of investments made towards G&I progress.
Taking a step back, however, is the question: Will the additional effort to educate, adopt and utilise gender-sensitive budgets be a worthwhile investment at this point in the PF Mexico’s delivery? Evaluators are not convinced that this is the case. There is sufficient evidence that financial resources are being applied to secure gains in G&I objectives. The PT and the strands are likely to get more and better information by consistent use of existing management and monitoring tools already in active use to assess the quality and impact on G&I metrics.
How deeply do we connect into communities?
The strand suppliers have clearly given thought to their respective approaches to connecting with communities and the final beneficiaries of their efforts. This planning is found in the gender and inclusion strategies and the community and stakeholder engagement plans that were part of the inception milestone documents. The degree to which strands have already engaged into their identified communities varies in large part due to the duration of a strand’s implementation, all of which are now constrained by COVID-19 restrictions in effect throughout Mexico. For example, the Energy and ACROL strands had just began implementation in earnest only two months before the evaluation began, making it difficult to identify specific evidence of engaging the community beyond what was planned for as indicated in milestone documents. The Future Cities strand began its direct engagement with communities within pre-selected metropolitan areas much earlier in inception, anchored by city managers who helped the strand understand local contexts and who also served to educate city programme partners in PF priorities and opportunities.
The degree of community consultation is also driven by the causal pathways that the strands are using to increase inclusive economic growth. The Financial Services strand conducted thorough analysis on the market demand among women and marginalised groups during the strand’s redesign, but given the documents reviewed, it is difficult to ascertain the degree to which these market analyses included actually going into communities and engaging prospective end users of financial products and services.
The PT and the four strands are now confronted with a very different outreach environment. Again, a better question for the strands and the Mexico PT to explore and share is not “how deeply do we reach into communities?” but “how do we continue to reach into communities and effectively engage those we seek to most benefit?” There is evidence that each of the Strand Programme Managers and supplier teams are using technology to drive community and stakeholder engagement. The Future Cities supplier has demonstrated that using the telephone to reach isolated neighbourhoods in the periphery of metropolitan areas still yields useful information and contributions from people. This is another urgent topic for the G&I Advisors and communications leads to discuss in their next and forthcoming sessions. The PFLearning platform also offers insights from teams responding to COVID-19 around the world. The Mexico PT is advised to tap that resource as well as contribute to it.
Is that outreach relevant and utilised?
The most relevant outreach to communities would not only assess the barriers and constraints that relate to the strands but this engagement would also see supplier teams getting final beneficiaries’ views on what an improved system, service or process would look like. Often, end users have different levels of expectations or have practical ways of seeing improvements that differ from programme designers and implementers.
In several KIIs during Cycle 2, evaluators were told that this outreach into communities and with specific marginalised, vulnerable or disadvantaged groups would have to include a large measure of expectation management in terms of the scale, scope and timing of any changes or assistance that would be coming their way. There is good evidence that the four strands and the suppliers have accounted for this aspect of community engagement. Their cautiousness may have limited the depth of community connection at this point.
Another aspect of community and end user engagement highlighted in KIIs was that it had to be relevant and extend over time. Individuals and community leaders are not interested in a one-and-done outreach which risks leaving them feeling used and disposable. Outreach is best conducted so that the feedback from individuals and community groups is tangibly considered and, if possible, reflected back in subsequent engagements.
What best practices do we see within strands that we can learn from?
Each strand has generated good practice related to G&I that can provide learning and insights for others via PFLearning. Here, again, recurring meetings of the G&I Advisors will ensure that these best practices – or practices that haven’t worked – are shared on a timely basis. Formal reviews create inherent time lags, and the PT and suppliers would best be served by real time insights and learning.
- Energy – consider social barriers to G&I objectives, not just market ones. The energy sector, like the ACROL sector noted below, is a male-dominated environment in Mexico and around the world. In undertaking its in-depth industrial baseline study and the workforce gap analysis, the supplier explored not only trade and economic dynamics, but also took stock of social norms that create barriers to achieve strand-related G&I objectives. For example, in addition to assessing training centres and employers’ perspectives, the analysis considered the role of parents in influencing (and directing) their daughters’ career interest and training. In short, the supplier also looked into the socio-economic context of final beneficiaries. The evaluators took note of this whole-of-community approach to the industrial baseline study and look forward to assessing how these insights translate into community engagement to advance G&I goals.
- Financial Services – balance new government objectives with PF priorities and standards. The strand faced a steep learning curve at the beginning of inception and needed to redesign two out of three interventions. Although there seemed to be a high degree of alignment in the government’s new government-to-people programmes, the implications for the PF’s G&I goals were significant. The new programmes reduced the number of women as direct beneficiaries but they also increased the number of other marginalised and vulnerable groups (unemployed youth, elderly, disabled people). The strand team and the supplier used a rigorous, evidence-based approach to assess the emerging portfolio of government-to-people programmes against PF priorities (inclusive economic growth). This exercise not only led to the selection of the government-to-people programmes now included in the strand’s design, it created content and language to use to engage government stakeholders which demonstrated the shared goals in pursuing intervention 1 of the Financial Services strand.
- Future Cities – focused, simple messaging. The strand has a great many actors involved in programme design and delivery, starting with the Alliance, which makes up the core senior management team and each of the metropolitan areas, bringing another mix of stakeholders, including state and municipal authorities, private sector, academia and civil society. Keeping all of these actors moving in the right direction requires strong, consistent messaging about priorities. Gender and social inclusion is a core element to all messaging of the strand, internally and externally. By reinforcing this message, it is easier for each actor, from the streets up to the SGB, to remember and share that message.
- ACROL – motivate by drawing attention to existing national goals. The strand partners and participants for the ACROL strand are primarily in the criminal justice and anti-corruption system at the federal and state levels of Mexico. These institutions and the professionals within them were noted in the BC as historically G&I-insensitive. Nevertheless, through discussions and by showing an alignment to the stated G&I objectives of the current administration, the ACROL strand has secured a commitment by the Attorney General of one of the beneficiaries states to undertake an internal diagnostic of its G&I policies and practices with support from the strand. The strand used existing measures and objectives to gain interest, rather than introducing standards of gender and social inclusion that come outside existing official national sources.
What is the willingness of suppliers to take up changes and recommendations?
There is evidence that the PT and suppliers see the cross-cutting themes as somehow parallel to one another. A more apt metaphor would be to think of these as the themes as threads which weave together a holistic fabric to support achieving greater inclusive economic growth. Pull one thread, and the fabric/support weakens.
Evidence in both the Cycle 1 and Cycle 2 evaluations shows that the suppliers are mission focused and that themes can and should be regarded as tools to strengthen programme delivery and achievement. According to PT KIIs, there is the perception that there is greater interest in adopting evolving G&I practices than there is to motivate suppliers to address other cross-cutting themes such as climate resilience, VfM or SBs. Perhaps this is because G&I has been a development objective for a longer period of time. Or, because G&I was an important and more clearly defined component in the SoRs when the strands first went to market and the bidders, now suppliers, anticipated this theme more clearly in their original programme designs. Nevertheless, there is a high degree of confluence between and among the PF’s cross-cutting themes.
- Climate and resilience. Even in existing supplier documents, there is clear evidence of the awareness of this interconnection, which can and should be shared across PF Mexico suppliers and into the broader PF network. This is true even for the most recent of the cross-cutting themes, climate and resilience. For example, the ACROL supplier produced an excellent analysis of the disproportionate negative impact of climate change on women and vulnerable groups in Mexico.[67] The other strand suppliers also undertook climate resilience analysis to inform their strand designs and delivery.[68] As the Mexico PT anticipate guidance from London regarding climate change and resilience strategies, the early work it has already secured from suppliers should be shared to help shape the discussion and to provide possible examples to other programmes who will need to create and operationalise this thinking.
  [67] ACROL Climate and Resilience Strategy.
  [68] The Colombia PT requested and received copies of these, demonstrating that other programmes would benefit from knowing about and having access to these forward-thinking documents.
- Value for money. The PF’s understanding of VfM also shows a connection with G&I in the fourth “E,” Equity. Equity is assessed through the eighth element of the VfM scorecard and relies on the evaluation analysis provided by the G&I scorecard through the review of programme documents and KIIs. The PF understands that without G&I action and results, there can be no full VfM in the investment.
- Secondary benefits. As the name implies, SBs are secondary to the primary purpose expected of the PF, namely greater inclusive economic growth to reduce poverty. Yet here, too, SBs have the potential to support and influence G&I objectives through job creation and greater economic dynamism in the municipalities and states in which PF Mexico delivers its programming.

Annex 8: Value for money approach and analysis
The EL VfM scorecard interrogates eight elements across two vectors, attainment (what one sees today) and direction (what is likely in the future). The eight elements are designed to cover all of the ‘4 Es’ i.e. economy, efficiency, effectiveness and equity. The VfM scorecard elements and definitions are:
1. Value for money measures. Existence, relevance and robustness of VfM measures (VfM processes)
2. Cost containment. Approach to procurement and cost containment (Economy)
3. Efficient use of resources. Efficient use of resources by PF interventions (Efficiency)
4. Theory of Change. Validation of PF ToC causal pathways for generating primary purpose and SBs (Effectiveness)
5. Sustainability. Sustainability of Fund activities (Effectiveness)
6. Ability of leadership. Review of programme-level leadership, management and governance arrangements to deliver VfM (VfM processes)
7. Risk. Strategies and measures adopted to enhance delivery and mitigate risk (Effectiveness).
8. Equity. Equity of programme design and approach (Equity).
The VfM rating follows a numerical and colour-scoring system shown in Table 16 below:
Table 16: Value for money scoring system
NUMBER	COLOUR	DESCRIPTION
1	Red	No evidence against the scorecard element
2	Amber-red	Little evidence against the scorecard element
3	Amber	Adequate evidence against the scorecard element
4	Amber-green	Good evidence against the scorecard element
5	Green	Strong evidence against the scorecard element criterion

EL used the following assessment process to derive the programme and strand VfM scores:
1. Strand Programme Managers undertook a self-assessment of their strands. They were given two weeks to complete their self-assessments, using the tool in Table 17, below. The Strand Programme Managers generated their own scores, as seen in Table 18 below.
2. The evaluation team reassessed the strands VfM elements based on the available evidence from programme documents and KIIs and rescored the VfM scorecards. See Table 19 below.
3. The strand scores were aggregated into a single score to create an overall programme score.
4. This aggregated score was then complemented by a document review to bring together deeper evidence.
This approach provides some independence of assessment and identifies recommendations and steps that can be taken to improve VfM delivery at all levels of the programme and its four strands. For analysis of the programme VfM score for Cycle 2, see Section 11.1 of this evaluation.
Table 17: Self-assessment of value for money through exploratory questions
VFM ELEMENT	ATTAINMENT	DIRECTION	EXAMPLE QUESTIONS FOR C2 SELF-ASSESSMENT
1. Relevance and robustness of VfM measures in place			How have the indicators developed over the course of the first year? / What are the reasons for the observed development? Are there any unexpected changes in the indicators? / Are there any other important developments in the programme delivery including IOs not explained or included in the indicators? / Have any leading indicators been useful in providing an early warning function for the programme team? (If so, see Element 6)
2. Approach to procurement and cost containment			Has all the procurement activity been completed? Has the team adjusted its approach, if so how and why? / How does the procurement outcome compare to other similar programmes?
3. Efficient use of resources and inputs by PF interventions			Which resources have been used in the PF interventions? How does this compare to other programmes? Who were the main actors and decision makers in the PT and delivery partners? How did they cooperate? / Are there any insights into how the procurement could have been conducted more efficiently?
4. Validation of Prosperity Fund ToC causal pathways (for primary & secondary benefits)			Which outputs or IOs have been achieved to date? How were they affected by the PT’s actions (and other inputs and activities in the ToC)? Were any additional activities needed to achieve the outputs. Would other inputs or activities have been more appropriate? / Have there been any unintended outputs or IOs? If so, were these positive or negative? / Can SBs be identified that have been caused by the inputs and activities?

VFM ELEMENT	ATTAINMENT	DIRECTION	EXAMPLE QUESTIONS FOR C2 SELF-ASSESSMENT
5. Sustainability of programme outcomes			Will the first outputs and IOs lead to sustainable long-term outcomes and impacts? What are the drivers behind this (such as incentives, institutions, motivations)? If there are uncertainties, who is the PT addressing them? / Are there any environmental impacts? What are these and what is their long-term effect?
6. Ability of leadership, management and oversight structures to support Programme delivery			Has the leadership, management and governance structure been changed since the programme was set up? If so, how and why? / What discussions did the SGB or its sub-boards have of the VfM delivery? Were views and insights from junior team members included in the discussions and if so how? / Which insights from the programme were fed through to the JFU and other London-based decision makers? How useful have the insights from programme board meetings been for the JFU / How have any “early warning signs” been translated into actions? What were the main steps in the PT’s decision-making?
7. Strategies and measures adopted to enhance delivery and mitigate risk			What strategies has the PT put in place to deal with change? Which elements, objectives, tasks etc. has it changed since the start of the implementation phase? What effect have the changes had on the delivery? / Which risks have been mitigated and how? What does that demonstrate about the PT’s flexibility and adaptability? / Are there any constraints, impediments or barriers? If, so what are they and is there anything that has not been achieved or delivered because of a lack of flexibility or adaptability?
8. Equity of programme design and approach			Which groups are likely to or have been able to benefit from the programme so far? Are any groups excluded? If so, how can this be addressed to ensure that the primary purpose is achieved?
OVERALL VFM ASSESSMENT

Annex 9: Secondary benefit approach and analysis
The analysis for SBs is not structured around a scorecard or other rubric. Therefore, EL offers an evaluation of each individual strand to present the SB findings that support the analysis presented in Section 12 of this evaluation.
Energy
The SB strategy or action plan for this programme was in draft at the time of this evaluation. In January, the supplier noted in its SB log of export wins of GBP 21 million pounds between September 2019 and January 2020.[69]
[69] EPI Centro/Energy supplier SB log, 29 January 2020.
Secondary benefit types identified
- Soft power: Working as closely with the government has strengthened the pathway for the delivery of the programme’s primary purpose as well as SBs.
- Market access (including imports): The logframe includes the outcome-level indicator: Total value of the contracts awarded to the SMEs by UK companies (Mexican Pesos). This is an indicator for imports to the UK or local purchases by UK firms feeding into the production process. This fits the description of market access in the SB framework.
- ODI: The logframe contains the impact-level indicator: “Total Investment made by UK companies into the Mexican energy sector”.
- Exports: There is evidence from the KIIs that the PT and supplier have delivered exports as one of the SBs in this programme.[70]
  [70] Interview with DAI.
- Network effects: There is evidence from the KIIs that network effects can be achieved by this programme.[71]
  [71] Interview with DAI
Measurement
The strand team has several mechanisms by which SBs are monitored and measured. On a quarterly basis, the supplier reports SBs in the SB log, which is received by the strand team and distributed to the VT. The logframe also contains a number of indicators referring to SBs, which focus on the IO and outcome levels. The strand team is advised to use the SB logs to benchmark progress against the IO and outcome indicators to ensure an ongoing review and status check of SB progress.
Delivery
The SB strategy was still in draft form at the time of this analysis, however there is an established process by which the supplier, the strand team and the DIT coordinate to deliver SBs. There is evidence that while conversations between the strand team, the DIT staff and the supplier are underway, these parties have not yet established a clear flow to consistently deliver on SB opportunities. There is evidence that improvements can be made throughout related to consistency of participation, sharing and staying on message and timely response to opportunities and introductions.[72]
[72] Interview with the DIT team.
Coordination
The use of ‘impact pies’, sector-specific plans and objectives was noted in the Cycle 1 evaluation as a strong method of intra-Post coordination, including for SBs. Now that SB plans are drafted, it would be good to ensure a confluence across the SB plans, impact pies, and strand logframe indicators. In addition, the strand team is advised to account for the potential to leverage other strand activities in the SB plans and incorporate areas of coordination in the revised plans and logframes.
Governance
In the absence of an initial gathering of the EPI Centro’s Strategic Advisory Board, there seems to be no body specifically tasked with the governance of SBs in the Energy strand.
Recommendations
- Use the SB logs to benchmark progress against the IO and outcome indicators to ensure an ongoing review and status check of SB progress.
- Ensure a confluence across the SB plans, impact pies and strand logframe indicators.
- Account for the potential to leverage other strand activities in the SB plans and incorporate areas of coordination in the revised plans and logframes.
- Ensure that the strand’s EPI Centro Strategic Advisory Board meets soon and is able to address the needs of all stakeholders.
Financial Services
Secondary benefit categories identified
- ODI: The reformed and more active financial market will be a more attractive market to invest in (Draft SB Plan, Page 8).
- Exports: The reformed and more active market will require expert input which can come from UK and other international business (Draft SB Plan, Page 8).
- Market access (including imports): The Draft SB Plan refers to trade in general and also highlights the potential for imports into the UK. This matches the definition of market access used in the PF.
- Network effects: The Draft SB Plan highlights the potential for networks growing between UK (and other international companies) and Mexican firms especially in the fintech sector without active encouragement by the PT or the supplier.
- Soft power: This SB type is mentioned in the plan but not further discussed and not included in the indicators.
Despite the clear conceptualisation of SB delivery, there remains a misconception that primary purpose can be included as an SB even if delivered by the UK company.
The use of a ToC for SBs demonstrates a strong approach to the delivery of SBs and the required engagement in the topic. The document further demonstrates the use of indicators along the pathways in the ToC. This will enable the strand team to monitor that SB delivery is on track as the indicators match the assumptions.[73] The inclusion of the softer SBs in the ToC, such as soft power, would strengthen the overall analysis.
[73] Draft Secondary Benefit Plan for Financial Services Programme, Pages 9 and 10
Delivery
The Draft SB Plan is clear about the primary focus of the programme on the delivery of primary purpose. The supplier submitted the Draft SB Plan on 31 January 2020.
Similarly, the draft ToC for SBs in the SB Plan focuses on delivering for UK business (Draft SB Plan, Page 8).
The SB Plan conceptualises the delivery of SBs in an accessible manner by describing the steps in programme delivery linked to necessary conditions to achieve SBs (See Figure 4 below). For example, the presentation highlights the role of trust, alliances and relationships during the stage of building market capacity to deliver, the role of cooperation and participation in implementation and the importance of awareness and interest in the interaction and engagement with stakeholder as part of final delivery.
Figure 4: Opportunities for secondary benefits

Coordination
The use of ‘impact pies’, sector-specific plans and objectives was noted in the Cycle 1 evaluation as a strong method of intra-Post coordination, including for SBs. The suppliers have now created SB plans. While the Financial Services supplier has noted the need for coordination with other strands in its SB Plan, there is no clear reference to operationalising this. The EL team suggest that a good place to begin is by ensuring a confluence between the SB plans and the impact pies.
 The result of these partnerships and alliances will improve the capacity building and market environment, which will, in turn, increase trade, investment, knowledge transfer and influence between the UK and Mexico.”
Financial Services SB Plan
Governance
The Secondary Benefits Strategy calls for a defined governance structure for SB delivery headed by the SB Governance Committee. This includes the PT, the supplier and the DIT. This committee discusses the progress made on SB delivery. While there is a clear reference to the DIT’s specific interest in exports, ODI and FDI, there is no explicit reference as to how this group reports into strand or programme governance. This body is still under discussion between the strand team and the supplier.
Recommendations
- EL advises the Financial Services strand team and all others to ensure that contracts paid for by PF money are not included as an SB.
- The strand team are also advised to ensure a clear definition of SBs in all documents referring to international and UK business.
- The EL team suggest a review of the SB Plan and impact pies to ensuring confluence.

Future Cities
Secondary benefit types identified
- Exports: The logframe contains indicators that are likely to reflect exports of goods and services from the UK (and other countries) as a result of PF activity.
- ODI: Included in the ToC (SB Strategy, Page 5) but not reflected in the logframe.
- FDI: Included in the ToC (SB strategy, Page 5) but not included in the logframe.
The Future Cities SB strategy sees high potential for FDI and ODI and interviews with the Strand Programme Manager and supplier reveal a potential for soft power and network effects SB wins. There is some expectation that soft power and network effects are realised in the short term and might enable the long-term benefits of FDI, ODI and to some extend exports. FDI and ODI projects will require long-term planning and negotiations, which are not necessarily visible to the strand team at this point in time.
Measurement
The Future Cities supplier’s SB strategy has an indicator at the output, IO and outcome levels which reflects SB results. At the impact level, the strand identifies the urban competitiveness index, which is not a direct SB indicator. The strand logframe should be revised to include an impact-level SB indicator or make more distinctive the SB connection to the urban competitiveness index.
Delivery
There is strong evidence that the Future Cities supplier recognises the need to plan and integrate the delivery of SBs into the overall strand delivery. This approach would ensure that Future Cities SBs are overseen by the same governance structure as those for the delivery of primary purpose (see governance section below).
The supplier notices that UK businesses are interested in focused discussions and opportunities of SBs rather than high-level discussions of concepts.[74] There is evidence that the supplier has realised the need to engage with businesses which might take up SB opportunities, however there is also evidence that this is difficult and some UK business or entities do not engage easily.[75]
[74] Future Cities SB Strategy, Page 7.
[75] KII – Future Cities.
Coordination
The need for coordination with other PF activities is evidenced in the Future Cities SB Strategy (Page 13). There is also evidence that the VTs help with this and that coordination is working well.[76]
[76] KII with Gisela.
Governance
The SB Plan includes a governance section, which proposes quarterly meetings between the delivery partner, the DIT and the PF team to discuss progress. According to the plan, progress on the delivery of SBs is to be evaluated annually. While these SB governance conversations are clear, the link to and coordination with the SGB could be strengthened.
Recommendations
- The strand logframe should capture the SB indicators presented in the SB Plan, including indicators at all levels of the results.
- The links and coordination between the SB quarterly meetings and the SGB should be clarified.

Anti-corruption and Rule of Law
Secondary benefit categories identified:
- Exports: UK companies to increase exports including both goods and services in the relevant sectors. Some opportunities have already been identified.
- Market access (including imports): The SB Plan includes a paragraph on international missions and knowledge exchange, which could open up business opportunities, but fails to recognise that these go both ways, i.e., exports from UK and other international companies into Mexico as well as exports from Mexico. There is potential that learning from the Mexican partner can be imported into the UK by using Mexican expertise in the UK context or by UK and other international companies using Mexican expertise in their operations in Mexico. If this is not explicitly part of the existing SB Plan for the programme, EL recommends that it be included.
- ODI: For UK and other international firms to invest in the Mexican market and set up subsidiaries to provide services to Mexican events or critical infrastructure.
- Soft power: There are very clear opportunities for soft power and some of these have already been realised.
- Network effects: There is clear potential for opportunities to create network effects as UK and other international companies are brought together with Mexican partners as part of PF and DIT activities.
Measurement
The ToC offers a mix of indicators adding output-level indicators to the high-level impact indicators. However, there is no clarity in some of the indicators presented. For example, the indicator for the IO reads more like an indicator related to the spending of PF funds and, therefore, the delivery of the primary purpose: “Number of international and UK enterprises that were hired by institutions to provide capacity building products and services to detect and investigate selected crimes.” This indicator is also used at the output level where it is clearly linked to primary purpose.
In addition, the impact indicator focuses on ODI (“FDI by UK companies into Mexico”) only. This does not fully reflect the scope of SBs indicated in the supplier’s SB Plan.
Delivery
The ACROL SB Plan produced by the supplier is quite clear. It contains a table with potential goods and services which may be provided at a later stage by UK and other international companies to the Mexican authorities.[77]
[77] ARCOL SB Plan, January 2020, Pages 7 and 8
Evaluators found evidence for a discrepancy with respect to the confidence the team displayed regarding the delivery of SBs. While the PT, based on its collaboration with the DIT and the VT, is confident in its ability to achieve such benefits, the supplier is most cautious.
Box 2: Secondary benefits arise in unexpected ways
SB opportunities in providing security services to public events. Currently there are opportunities being discussed for UK and other international companies arising from the need to provide crowd control and safety during the 2022 World Cup qualifiers in Mexico and the United States.[78]
[78] Scheduled for Monday, 31 August 2020 – Tuesday, 12 October 2021, the CONCACAF qualifiers may be delayed due to ongoing COVID-19 restrictions.

Coordination
There is evidence that the ARCOL supplier considers the links to the other PF Mexico strands. The SB Plan mentions security-related opportunities arising for example in the Energy strand where critical national infrastructure needs to be effectively protected. There is further evidence from the interview that similar opportunities are already been taken up by the DIT team.
Governance
There is evidence for a well-structured governance in the ACROL team to deliver SBs, including regular meetings at different levels from weekly to quarterly to ensure communication is clear.[79] Quarterly meetings include the DIT team. Further SBs are then also discussed at the higher-level governance meetings of the PF. Maintaining this meeting-focused approach may prove challenging both in terms of time as well as in ensuring that these layers of engagement remain well-coordinated and effective.
[79] ARCOL SB Plan, Page 11.
Recommendations
EL recommend that the strand team develop adequate logframe indicators for SBs at all levels of the logframe representing all SBs identified in the SB Plan and other possible SBs.

Annex 10: Mexico Programme Theory of Change
This annex provides a detailed review of the latest working version of the programme-level theory of change.
The PF Mexico Programme ToC (see Figure 6 below) supports the Fund-level impact statement: “The Prosperity Fund aims to remove barriers to economic growth and promote the economic reform and development needed to reduce poverty in partner countries.”[80]
[80] https://www.gov.uk/government/publications/cross-government-prosperity-fund-programme.
The Mexico Programme impact statement in the August 2019 ToC draft is: “Higher rates of economic development and more inclusive productive sectors delivering services that contribute to a more resilient, sustainable and safer Mexico via improved urban development, a more competitive and accessible financial sector increased efficiency in detection and investigation of crime and an upskilled inclusive energy industry.” The Mexico bilateral programme and its strands are designed to support three of the five Fund-level IOs (see Figure 5 below): investment in infrastructure (Future Cities and Energy), financial and economic reform (Financial Services) and ease of doing business (ACROL).
Figure 5: Fund-level Theory of Change

In the Cycle 1 Evaluation Report, evaluators used a ToC checklist[81] to assess the quality of the strand and programme ToCs available at the mid-point of inception. Table 20 below compares the programme ToC in the Cycle 1 evaluation with the ToC available for this evaluation. Annex 11 assesses all four programme strands comparatively between Cycle 1 and Cycle 2.
[81] Scored against: Weak – insufficient, superficial or uncritical; Potential – some coverage, but gaps in important areas or in critical thinking; Reasonable – fairly complete and critical thought in most areas, but some yet unclear; Robust – clear, comprehensive, well-formulated, strong critical thinking.
Table 20: Comparative assessment of Cycle 1 and Cycle 2 programme Theory of Change
TOC CHECKLIST CRITERIA	PROGRAMME		DIRECTION OF TRAVEL
	Cycle 1	Cycle 2
Primary purpose	Reasonable	Reasonable	Unchanged
Context	Robust	Reasonable	Down
Beneficiaries	Reasonable	Reasonable	Unchanged
Actors	Robust	Reasonable	Down
Assumptions	Reasonable	Potential	Down
Pathways	Reasonable	Reasonable	Unchanged
Coherence	Reasonable	Reasonable	Unchanged
Deliverability	Reasonable	Reasonable	Unchanged
G&I	Reasonable	Reasonable	Unchanged
VfM	Reasonable	Reasonable	Unchanged
SBs	Reasonable	Reasonable	Unchanged
Sustainability	Reasonable	Reasonable	Unchanged
Additionality	Reasonable	Reasonable	Unchanged
Fund ToC	Reasonable	Reasonable	Unchanged
Fund linkage	Potential	Reasonable	Up

### Review of the programme Theory of Change
The quality of the programme ToC is dependent on the quality of the contributing strand ToCs. As a result, strengths and weaknesses in the four strand ToCs influence the findings for the programme rating. Of the fifteen criteria, the ratings for the Mexico ToC rose against one criterion (Fund linkage), stayed the same in eleven criteria and fell in three criteria. It should be noted that the existing ToC does not reflect the ongoing adaptation to the evolving political economy in Mexico, which the PT conducts regularly to remain relevant and well-positioned in delivering its programmes.
Primary purpose. EL’s initial assessment was that the programme theory of change is sound and that it is likely to contribute to greater inclusive growth and reduced levels of poverty in Mexico. This reflects an assessment at strand level that the current design and positioning of the four strands makes it likely that the programme’s objectives and intended impacts will be met. The only exception (see below) relates to the choice of one of the three types of crime as having a weak link with the overall aim of promoting inclusive growth.
Context. The environment in which the Mexico Programme strands operate varies. There is a high degree of synergy with Mexico’s National Development Plan in the broad goals of three of the four strands (Financial Services, Future Cities and ACROL). The context in which the Energy strand operates requires more nuance to ensure buy-in from both the Mexican authorities and UK audiences. The programme ToC does not reflect these nuances in its presentation, but there is ample evidence that it is managing the programme context effectively, as discussed above in relation to engagement of external stakeholders.[82]
[82] Evidence comes from strong stakeholder management in ACROL and Energy in particular (See Section 5.5.2).
Beneficiaries. The primary beneficiaries noted in the programme ToC include men, women, and micro-, small- and medium-sized enterprises (MSMEs) as well as official beneficiaries such as enforcement and regulatory agencies and municipal-level development authorities. UK and international businesses are also beneficiaries via SBs. While the strand-level ToCs offer greater specificity to these beneficiaries, the current programme ToC is rather general. However, given that the strand ToCs provide detail, this absence is not a significant issue for the programme ToC.
Actors. The set of programme actors expands on the beneficiary set noted above and includes the federal-level stakeholders who participate in governance boards and strand programme events. As with the beneficiaries, the programme ToC does not elaborate on the actors required to deliver against the full scope of the PF objectives.
Assumptions. There are no assumptions offered in the current programme ToC that would guide the reader and programme delivery partners towards context, definitions and nuance. Each strand-level ToC provides a narrative that offers further details, including assumptions. Evaluators strongly encourage the PT to create a supporting narrative at the time the programme ToC is revised.
Causality/Pathways. The causal pathways in the programme ToC are informed by selected outputs, IOs, and outcomes at the strand level. However, the strength of the causal pathways within the strands vary in driving progress towards the PF’s primary purpose. For example, evaluators recommend building a stronger causal pathway in the ACROL strand to link detection and investigation of homicide with strengthening inclusive economic growth within the current context.[83] The causal pathways of the Financial Services, Future Cities and Energy strands have greater strength, but there is room for improvement in the strand and programme ToCs, particularly regarding VfM (see Section 11).
[83] The ToC for the PF Transparency and Anti-Corruption identifies three pathways: improving transparency and accountability and facilitating more open markets with lower access barriers for legitimate business; changing attitudes and perceptions towards corruption, leading to a lower tolerance of corruption; increasing the penalties and risks for those who engage in corruption through implementation of measures that visibly improve justice and increase penalties for corruption, ending impunity for the corrupt, including the recovery of illegally gained assets. The most likely pathway in the ACROL strand is in visibly improving justice and increasing penalties for corruption. Its purchase is weak in relation to homicides.
Coherence. The programme ToC does not reveal the leveraging across strands that was articulated in the BC. Here, again, a supporting ToC narrative would enable greater detail and nuance in this regard and would provide an opportunity to present the efforts being made to foster coherence through engagement strategies and governance systems. There is evidence in other programme and strand documents that provide this analysis.
Deliverability/sphere of Influence. Overall, the outcomes in the programme ToC are within its sphere of influence. The likely contributions of the Energy, Financial Services and Future Cities strands into the programme ToC are logical and within delivery potential. Evaluators find potential in two of the ACROL strand’s three selected crimes in its current strand design,[84] but would recommend strengthening the third crime..
[84] ACROL identifies three selected crimes: homicides, cyber-crime and misuse of public funds. Evaluators note the potential to contribute to primary purpose in the pathways associated with cyber-crime and misuse of public funds.
Gender and inclusion. The G&I elements in the programme and strand designs and strategies are reasonable and evidenced in a range of programme documents.[85] Yet, the programme ToC impact does not include a reference to either gender or inclusion. In three of the four pillars of the programme ToC, greater benefits to women and girls (and to men and boys) are specifically noted in the output and IO levels. The Financial Services pillar includes references to gender in its outcome-level results. Future Cities has six G&I indicators at the outcome level with one at both the output and IO level. The ACROL strand has neither a reference to gender nor inclusion in its pillar in the current programme ToC. Without a narrative to supplement the programme ToC, the strand planning and potential to improve is not captured (see Section 9).
[85] Among the milestone documents with G&I elements submitted by each of the strand suppliers were the Gender and Inclusion Mainstreaming Strategy and Action Plans, the Stakeholder and Community Engagement Strategy and Action Plans, the costed workplans and the logframes and strand indicators.
Value for money. There is reference in the pillars to greater efficiency (Future Cities), more effective partnerships (Energy) and a wider range of products (Financial Services) which would infer greater VfM in the programme environment. However, the theme is not directly addressed in the ToC. In the absence of a supporting narrative, the VfM theme in the programme ToC is not particularly evident and does not reflect the considerable planning otherwise apparent in the programme documents. These gaps in the programme ToC create risks for VfM (see Section 11).
Secondary benefits. The programme ToC gives a clear indication of the SBs intended within each of the strands and offers its own programme-level SB goal of “a more competitive market with increased trade and investment opportunities for the UK and international markets”. Each of the strand suppliers has created an SB plan and reports monthly against progress made on SBs. The programme produced an SB plan associated with its BC in 2018. Guidance was provided in the Cycle 1 Evaluation Report and Annual Review to support the revision of the programme SB plan. Since these Cycle 1 reports, there is evidence that some SBs have emerged, particularly network effects and soft power. A ToC revision would enable the PT to capture these early wins as well as reconcile ToCs with strand SB strategies (see Section 12).
Sustainability. The sustainability of outcomes is reflected in the programme ToC outcome descriptions. This is further supported in the strand ToCs and their associated narratives. A revision of the programme ToC and an accompanying narrative would strengthen the claim and evidence for outcome sustainability.
Additionality. There is evidence that some of the strands have a greater additionality than others. For example, government partners of the Future Cities projects appreciate that the PF is willing to explore difficult challenges related to policy and governance whereas other actors might be more interested in tangible activities such as street or park construction. There is evidence that the EPI Centres, once up and running, could also provide evidence of additionality as these centres (“hubs” at state level) fill an unmet need identified in recent industrial baseline studies. The respective Strand Governance Boards (SGBs) offer an important dialogue platform to ensure coordination and leveraging among government and donor stakeholders, which should promote PF additionality in Mexico.
Fund Theory of Change. The programme ToC is designed to link to three of the five Fund-level IOs as discussed above. Overall, evaluators find good evidence of the programme’s ability to support those IOs. The potential to contribute to Infrastructure (Energy and Future Cities) and Financial Services (Financial Services) is clearly indicated.
Wider fund activities. The Mexico Programme has a strong potential to contribute to wider Fund activities by virtue of its state of implementation and the lessons it has learned as a front runner in the PF delivery process. These include lessons on substantive areas of programme delivery within the four strands as well as in programme management and contract management lessons. The Mexico PT are active participants in the PFLearning platform and have regularly shared their insights with colleagues there and at global and regional gatherings.

Figure 6: Mexico Programme Theory of Change

Annex 11: Strength of programme/strand Theories of Change—Cycle 1 to Cycle 2

Table 21: Programme and strand Theory of Change strength
TOC CHECKLIST CRITERIA*	PROGRAMME		ENERGY		FINANCIAL SERVICES		FUTURE CITIES		ACROL
	Cycle 1	Cycle 2	Cycle 1	Cycle 2	Cycle 1	Cycle 2	Cycle 1	Cycle 2	Cycle 1	Cycle 2
Context	Robust	Reasonable	Robust	Reasonable	Robust	Robust	Robust	Robust	Robust	Potential
Beneficiaries	Reasonable	Reasonable	Reasonable	Robust	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
Actors	Robust	Reasonable	Robust	Reasonable	Robust	Robust	Reasonable	Reasonable	Robust	Reasonable
Assumptions	Reasonable	Potential	Robust	Reasonable	Reasonable	Reasonable	Reasonable	Robust	Potential	Potential
Pathways	Reasonable	Reasonable	Robust	Robust	Reasonable	Reasonable	Reasonable	Robust	Reasonable	Potential
Coherence	Reasonable	Reasonable	Reasonable	Robust	Reasonable	Reasonable	Reasonable	Robust	Reasonable	Reasonable
Deliverability	Reasonable	Reasonable	Reasonable	Robust	Reasonable	Robust	Reasonable	Robust	Reasonable	Reasonable
G&I	Reasonable	Robust	Reasonable	Robust	Reasonable	Robust	Reasonable	Robust	Reasonable	Reasonable
Value for Money (VfM)	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
Secondary Benefits (SBs)	Reasonable	Reasonable	Robust	Reasonable	Reasonable	Reasonable	Potential	Reasonable	Reasonable	Potential
Sustainability	Reasonable	Reasonable	Robust	Robust	Reasonable	Reasonable	Potential	Robust	Potential	Potential
Additionality	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Robust	Reasonable	Reasonable
Fund ToC	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable	Robust	Potential	Potential
Fund linkage	Potential	Reasonable	Potential	Potential	Potential	Potential	Potential	Robust	Potential	Potential

*Weak – insufficient, superficial or uncritical; Potential – some coverage, but gaps in important areas or in critical thinking; Reasonable – fairly complete and critical thought in most areas, but some yet unclear; Robust – clear, comprehensive, well-formulated, strong critical thinking.
Annex 12: Actions taken to address recommendations in evaluation cycle 1
There is clear evidence that the recommendations made to the PT in the Cycle 1 evaluation were acted upon. Table 22 below provides a summary of actions against the programme-level recommendations made in the Cycle 1 evaluation and Annual Review, which the PT prioritised as critical during the September 2019 evaluation validation and sense-making workshop.[86]
[86] This workshop immediately followed the September 2019 LatAm conference which enabled staff from the PFDU and the JFU to join the sense-making workshop.
Table 22: Actions taken against critical Cycle 1 programme recommendations
RECOMMENDATION	LEAD ACTOR(S)	TIMEFRAME	ACTION TAKEN
‘Poverty’ should be defined to ensure common baselining and improve strategic communications with government stakeholders.	Head of PF/Mexico	Immediately	CONEVAL definition of multi-dimensional poverty adopted by PT
Strategic communications capacity should be increased in the PF team as a whole to mainstream strategic communications into the supplier networks and rest of the PT.	PT	Early implementation phase	Governance and Communications Officer hired into PT
The PT should ensure the current contracts in place are as robust and fit for purpose as possible and anticipate areas of change to avoid renegotiation of contracts during implementation.	PT	By end of transition month	Contracts Manager hired into PT. Contract management training provided by PFDU in September 2019.
The SRO is given full access to risk registers, in addition to the high-level risk register already received, every month with high priority risks highlighted.	PT and PMC	ASAP and ongoing	PMC, chaired by SRO, receives monthly risk registries from suppliers and PT. PF Head and SRO consult monthly on risk and programme progress
All strand teams should create a written common narrative related to the intersections of PF Mexico’s programmes to ensure that all are on message.	PT	Early implementation phase	Individual strand narratives are completed, but not one that speaks to the intersections of PF programming.
Strategic communications should be central to effort, backed up by verifiable actions, including message discipline within and across strands to build consistency and mitigate risks associated with inaccurate statements.	Head of PF/Mexico and Strand Programme Managers; Prosperity Counsellor	31 December 2019	Governance and Communications Officer hired into PT
G&I Advisors, through the G&I Group, should exchange inclusion indicators and interventions that promote both gender and social inclusion in their discussions before the close of the inception phase and identify shared indicators to enable the programme to better assess its G&I impact.	PT and supplier G&I Advisors	Mid-Oct ACROL, Financial Services, Future Cities; Nov Energy[87]	G&I Advisors group inactive. Cycle 2 recommendation is that this group be revived.
The PT should consider the process for allocating agile funding to new, small or rapidly developing projects can be streamlined.	PT	31 December 2019	The agile programme funds were first used to fund FC projects in February 2020.
In the context of having shared risk registers with suppliers, the PT should consider a standard process to manage sensitive information that should not be shared widely within the risks register, whist making sure information can be shared as widely as needed.	PT; Contracts and Risk Manager	31 October 2019	The main programme-level risk register is refreshed monthly by PTs; this register is not shared with suppliers. The PTs are able to add sensitive risks here that would not be added to the strand register. The top risks from the main register are presented at the monthly PMC. / PF Head or Contract Management Lead will flag highly sensitive or confidential risks with London Commercial promptly. These risks are registered on a version of the main register that is shared with a closed distribution list, including the SRO, Head of Prosperity, Head of PF and London Commercial. / The Contract Management Lead sends the top commercial risks to London Commercial quarterly as an add-on to the quarterly report because the PT is not able to upload these risks on Prospero due to the CoI of PA being responsible for the MR contract.
A more detailed Secondary Benefits strategy should be developed for all strands, using improved guidance from London.	PT; SB Advisor	Mid-November	SB plans submitted as part of inception phase milestones, but no further guidance from London was received.
The Secondary Benefits Action Plan should be updated in line with new guidance and turned into a more useful strategic document which (i) sets out all different types of SBs on offer including soft power, (ii) has a more realistic assessment of SB potential and (iii) clearly defines the respective roles & responsibilities of the DIT, the PT, PF suppliers and London.	PT Strand Programme Managers; SB Advisor	Mid-November	SB plans for strands completed or in final draft (Energy) which accounted for soft power, market access (including imports) and network effects and which adjusted the GBP value of benefits anticipated.
The PT should have clear responsibilities for risk management and should remain proactive in identifying and monitoring risks.	PT; VT risk reviews	31 Oct 2019	Evidence of strong line of sight throughout PF Mexico. Risk registries received monthly and discussed at the PMC, with additional pathways to respond to rapidly emerging risks.
[87] The different timeframe for this Cycle 1 action relate to the different inception phase lengths of the strands.

Annex 13: Programme Evaluation and Learning team
Jennifer L. Butz, Programme Evaluation Lead, Mexico. Ms Butz, a Mexican permanent resident for 14 years, has a 30-year career as a development specialist focusing on the full spectrum of project cycle management. She led the PF Mexico Cycle 1 evaluation. Ms Butz has conducted evaluations for USAID, the UN and numerous international NGOs. She has launched and sustained programmes in the Global Green Growth Institute and the World Bank and has led several country programmes in Asia and Southeast Europe. Her professional experience has taken her to more than 35 countries on 6 continents, with a special emphasis on Latin America, Asia and South/Central Europe. She has degrees from Michigan State University (BA) and the Monterey Institute of International Studies (MA – Honours).
Dr Ulrike Hotopp, Thematic Lead for VfM and SBs, has over 20 years’ experience as an economist in and outside of government. She worked in the Government Economic Service for 16 years, responsible for evaluations, appraisal and value for money analysis, most recently as Chief Economist of the UK’s Department for Environment, Food and Rural Affairs, including oversight of their contribution to the International Climate Fund. Dr Hotopp led the strategic analysis team in the Department of Energy and Climate Change, which included the analysis for the renewable energy strategy. She also led the team in the Department of Business, Energy and Industrial Strategy which developed its appraisal and evaluation methods including for regional policies. She has worked as part of the Prosperity Fund EL team since 2018 developing the methodologies used for VfM and SB evaluation. Dr Hotopp took part in evaluations of the Colombia Programme and the ASEAN Economic Reform Programme. Ulrike holds a PhD in Economics (International Trade) and an MA in International Economics from the University of Sussex. She holds a position as part-time reader for economic policy analysis at the University of Kent.
Luis Bernal, Evaluation Expert. Mr Bernal has more than 25 years of experience in evaluations across Latin America. He has led and joined evaluations for a wide range of multi-lateral and bilateral agencies, including the Inter-American Development Bank, UN Women, the European Union, USAID and the International Labour Organisation. He has also provided evaluation services to foundations and government (national and local) bodies. His technical area of focus is highly relevant to Mexico PF’s strands, including security & anti-corruption, small business development & microenterprise (rural and urban), gender equality, economic & social Inclusion (women, youth, minorities, people with disabilities, migrants, crime victims), workforce development, social protection and poverty reduction. Mr Bernal holds an MA in Public Policy – Educational Policy from the University of Massachusetts in Dartmouth.

Annex 14: Cycle 2 schedule
The schedule below was created during the December 2019 evaluation planning workshop. The evaluation process continues to meet the planned schedule. However, there is some possibility that the process now in its later stages may be delayed due to the FCO response to the COVID-19 crisis in Mexico and the UK.
Figure 7: Cycle 2 schedule