## GMPP
GMPP ID Number	Project Name	Department	Annual Report Category	Description / Aims	IPA Delivery Confidence Assessment / (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the IPA Annual Report on Major Projects)	Departmental commentary on actions planned or taken on the IPA RAG rating.	Project - Start Date / (Latest Approved Start Date)	Project - End Date / (Latest Approved End Date)	Departmental narrative on schedule, including any deviation from planned schedule (if necessary)	Financial Year Baseline (£m) (including Non-Government Costs)	Financial Year Forecast (£m) (including Non-Government Costs)	Financial Year Variance (%)	Departmental narrative on budget/forecast variance for 2020/21 / (if variance is more than 5%)	TOTAL Baseline Whole Life Costs (£m) (including Non-Government Costs)	Departmental Narrative on Budgeted Whole Life Costs
HMT_0004_2021-Q2	NS&I Rainbow	HMT	Government Transformation and Service Delivery	The Programme has three key aims to; / . Measurably reduce the costs of running the business; / . Become a self-service digital business with support for the vulnerable and excluded; and / . Deliver more nimbly, reduce risk and enhance scalability.	Amber	The Infrastructure Project Authority's Delivery Confidence Assessment rating is Amber.This is primarily due to the following factors: The SRO Delivery Confidence Assessment (DCA) rating at Q4 2021 (31st March 2021) was Amber, due primarily to the following factors; / -The Programme has recently received approval to proceed into the Delivery Phase and is currently mobilising against a re-baselined Programme schedule. / -The acquisition of key resources required to commence Programme and Project activities is underway and expect to increase.	2019-06-03	2024-07-31	The project end-date is 31 July 2024. This is primarily due to the following factors: The schedule baseline Programme end date at Q4 (31st March 2021) is 31 July 2024, has not changed since the Programme reported, due primarily to the following reasons; / -The Programme has recently received approval to proceed into the Delivery Phase and has carried out a Programme schedule re-baselining exercise which concluded that there was no impact on the end Programme delivery date following changes to the approval date. Sub-Programme milestones were able to accommodate the delays as per the teams ability to maintain key deliverable activity outputs. / -While the exercise was underway continued to work to deliver key Programme deliverables in line with the baseline plan with the available Programme resources.	£0.00	£0.00	Cannot calculate variance percentage as baseline is zero	The GMPP project did not provide data	£1,158.35	The projects Baseline Whole Life Cost is £1158.35m. This is primarily due to the following factors: The baseline Whole Life Cost at Q4 2021 (31st March) is £1158.35m. The baseline Whole Life Costs covers the period up to 2031.