Programme Completion Review - Summary Sheet

PROGRAMME TITLE: East Africa Migration Programme
Country and Region:	Kenya, Sudan, Ethiopia, Somalia, Africa
IATI Unique ID:	CSSF-03-000020
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), National Crime Agency (NCA), Crown Prosecution Service (CPS)
Total Budget:	ODA: 5.0m (3 years)			Non-ODA: £0
Total Spend:	ODA: 1.53m (2 years)			Non-ODA: £0
Original Programme Start Date: 1 April 2018		End Date: 31 March 2020
Outputs					Score
The adoption of UK supported human rights compliant actions and procedures necessary for successful disruption of Organised Immigration Crime (OIC) activity.					B
Strengthened policy engagement framework for influencing and leveraging key national, regional and international actors to adopt consistent and evidence led measures for tackling OIC.					B
Overall output score					B
Outcome Assessment: Increased effectiveness of both direct and indirect measures to tackle Organised Crime Groups (OCGs) in ways that are human rights compliant and do not pose unacceptable conflict sensitivity risks. / High quality advisory support and targeted interventions contributed to building some foundations for more effective, human rights compliant and conflict sensitive direct measures to tackle OCGs in the region. Sustaining and expanding these gains will depend on a conducive internal HMG and external political environment for migration programming.
Final Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2017/18		2018/19		2019/20
Programme Score (output/outcome scores			B	B	B	B
Risk Rating - low/medium/high			High		High

What support did the UK provide?
The East Africa Regional Migration Programme was initially designed as a three-year programme (2018-2021). It sought to create a more coherent and strategic approach to CSSF regional migration programming, following the introduction of migration project-level delivery, in response to the crisis in the Mediterranean in 2016. UK support included:
- A scoping study to better understand the enabling environment for Organised Immigration Crime (OIC) in East Africa and identify entry points for indirect countermeasures.
- Support to the Migration and Human Trafficking Crime Team in Ethiopia, implemented by the NCA and the CPS (to December 2019).
- Funding a UK Migration Adviser in Khartoum, providing assistance to support the Regional Operations Centre Khartoum direct engagement with the Government of Sudan, to strengthen human rights compliant criminal justice responses to OIC (to April 2019).
- Funding a UK Regional Migration Adviser based between Eritrea and Khartoum.
- Funding a European Migration Liaison Officer based at the European Delegation Addis Ababa (to April 2019).
- Support to the African Centre of Justice and Peace Studies, to monitor the implementation of anti-human trafficking laws and the death penalty in Sudan (to April 2020).
- Support research by Royal United Service Institute, to build an understanding of the exploitation of formal and informal financial sectors by human traffickers in Sudan and the regulatory environment.

What results did the programme deliver? Will they be sustained?
Despite the challenges, sound implementation and risk management resulted in the delivery of some programme outputs:
- Contributed to tactical advances in counter-OIC in Sudan (in FY18/19) including significant arrests during human trafficking operations in coordination with INTERPOL, supported by the Migration Adviser.
- Built capacities for investigating and prosecuting OIC in Ethiopia.
- Increased understanding and management by HMG of the human rights and conflict sensitivity risks, related to countering-OIC policy and programming in Sudan. Influenced international partners to take a more informed and cautious approach.
- Enhanced HMG’s situational awareness of regional migration issues and the criminal justice space in Sudan. Opened opportunities for HMG access to Sudanese authorities after the political transition.
- Identified potential entry points to weaken the enabling environment for OCGs.

These results created ‘foundations’ for more effective and human rights compliant direct measures to tackle OIC.

What lessons have been learned?

Successful management and governance of a regional, multi-country and thematic CSSF programme spanning several posts and departments can be challenging. It requires:

Senior level support, accompanied by strong mid-level regional programme management and policy support with the time, expertise and authority to filter CSSF processes and communicate policy to senior decision makers. In addition, to take decisions up, down and across the management chain. Regional governance needs to be coupled with clear processes for oversight and risk management of programme components, as well as activities at post.

Strategic patience coupled with sustained political interest and funding. The delivery of programmes with a complex multi-layer theory of change, require perseverance and a sustained funding commitment. It can take time for results to emerge.

Decisions to end funding should be accompanied by exit strategies with clear communication to those affected.