Annual Review - Summary Sheet

PROGRAMME TITLE: East Africa Security Programme
Country and Region:	East Africa
IATI Unique ID:	CSSF-03-000021
HMG Partners (LEAD in bold)	Ministry of Defence (MOD)
Total Budget:	ODA: £1.64m			Non-ODA: £9.63m
Budget this FY	ODA: £0.466			Non-ODA: £2m
Spend this FY	ODA: £0.587m			Non-ODA: £1.978m
Original Programme Start Date: April 2015		Planned End Date: November 2020
Outputs					Score
Output 1. Strengthened Kenyan led internal governance and management of the Counter-Improvised Explosive Device (C-IED) capability					A
Output 2. C-IED training delivered by a more capable and functional UK mentored Kenyan and EA staffed training cadre.					A
Output 3. UK political and policy engagement in support of Kenyan, regional and international engagement in regional C-IED capability development					A
Output 4. Increasingly regional and relevant force elements acquire the knowledge and skills to operate in a high threat IED environments through receiving training by the wing.					B
Overall output score					A
Outcome Assessment: The programme is making steady progress towards its objective: a capable C-IED Wing able to train both Kenyan and regional forces, with its own staff and instructors taking on responsibilities from UK contractors and British Peace Support Team (Africa) (BPST(A)). Covid-19 has delayed progress towards the planned transition of ownership and management. There continue to be some areas of concern relating to sustainability, regionalisation and the delivery of doctrine.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score		A/B	A/B	B	A	A	A	A
Risk Rating - low/medium/high		Low	Low		Low	Low	Low	Medium
*output/outcome scores
How has the programme changed during this period? / Significant improvements in programme oversight and management, through pro-active engagement by senior officials, better scrutiny to ensure Value for Money and contracting processes. / The Kenyan Defence Forces (KDF) have filled 98% of the posts in the C-IED Wing; UK contractors and BPTS(A) are adjusting to a mentoring role. / The Training Assessment System for Evaluation and Reporting (TASER) methodology is being implemented. / BPST(A) and the UK contractors have exported C-IED training to defence force units in Rwanda, Malawi and Zambia deploying on UN/African Union (AU) Peacekeeping Operations. / However, ambitions to develop the regional aspect of the C-IED Wing have yet to be met.

What support did the UK provide in FY 19/20?
- Began the implementation of the partnering agreement between the Defence Explosive Ordnance Disposal, Munitions Training Regiment (DEMS) and the Humanitarian Peace Support School; providing DEMS’ endorsed quality assurance and mentoring.
- Supported the Humanitarian Peace Support School hosting the third Africa C-IED Working Group and a high-profile ambassadors’ visit, promoting the C-IED Wing as a regional training centre.
- Facilitated working groups on C-IED doctrine and training curriculum development and harmonisation and the establishment of the C-IED Wing as a regional centre of excellence.
- Enhanced the programme monitoring and evaluation processes and programme management and reporting.
- Since 2016, UK has supported the C-IED training of 4,813 personnel. In this reporting period the Wing trained 723 personnel (including 24 females) on different types of C-IED courses. The Humanitarian Peace Support School has separately trained 925 Kenyan security personnel in IED awareness, based upon the training delivered through this programme.

Key results for FY 19/20:
- Implementation of the bilateral C-IED capability Institutional Development Programme to develop Kenya’s C-IED capabilities and specifically the C-IED Wing and its sustainment.
- The initiation of the Partnership Agreement between the Defence Explosive Ordnance Disposal, Munitions Training Regiment (DEMS) and the Humanitarian Peace Support School C-IED Wing, with specific training serials, setting up the C-IED Wing Training Development Cell (TDC) and certification of Kenyan instructors.
- C-IED training exported to military forces in Malawi, Rwanda and Zambia, through UK contractors, as part of pre deployment training for UN/AU Peacekeeping Operations, albeit without Kenyan support in every location.
- Humanitarian Peace Support School delivering C-IED training to the Border Police Unit (BPU).
- The development and implementation of communications plans supporting the Programme Office, and through BPST(A), to promote the C-IED Wing to internal and external audiences.
- Hosted an international ambassadors’ event to promote the C-IED Wing among potential donors and, with AFRICOM, the 3rd Africa C-IED Working Group, building relations with key international partners and stakeholders.
- Supported work on developing a UN/AU based C-IED curriculum for Africa and, the development of African Union (AU) C-IED doctrine.
- Successfully implemented the TASER ‘Outcome Monitoring Tool’.

Key Lessons
- The value of the C-IED capability Institutional Development Programme as the tool for establishing Kenyan ownership and leadership in driving the development of capability and delivery of the training centre, developing a Humanitarian Peace Support School sustainment strategy (on-going) and the importance of the role of the Threat Mitigation Officer, charged with its delivery.
- The need for a sequenced approach to the hand over process including mentoring the Kenyan trainers and ensuring Kenyan support to C-IED Wing maintenance and sustainment.
- The need to focus on technical delivery of regional C-IED training, answering the operational demand while functioning at a level below the regional political and security sensitivities.
- The need for other funding streams to support the C-IED Wing once this programme is ended.
- Appreciation by the wider community that the C-IED Wing delivers generic training, informed by operational lessons, while UN Mine Action Service provides theatre specific operational training to AMISOM (African Union Mission in Somalia) forces, which is time and circumstance critical, as the immediate IED threat evolves.

Summary of Recommendations for FY 20/21
- Ensure the full delivery of the C-IED capability Institutional Development Programme.
- Develop a programme transition plan and post programme strategy.
- Consider conducting an Access and Influence analysis of benefits and leverage accrued by UK and how these may assist HMG strategies in the region.
- Assess scope for the C-IED Wing as regional hub within a network of national C-IED training centres.
- With the International Peace Support Training Centre, assess the option of an ‘exchange officer’ programme at the C-IED Wing for regional participants.
- Develop a formal alumni network and information/experience exchange process.
- Explore options with the Kenyan Defence Forces and others for the local manufacture of C-IED equipment and materials, including Remotely Operated Vehicles.
- Adopt a ‘Friends of the C-IED Wing’ strategy to encourage sustainable partnerships and funding from other donors.
- Support adoption and implementation of African Union doctrine, including C-IED, based on UN standards. If necessary, work with the African Union to develop its doctrine.
- Consider how HMG diplomatic, security and military networks in the region could more effectively encourage Ethiopia, Uganda and crucially the African Union, to invest more in the C-IED Wing.