Annual Review - Summary Sheet

PROGRAMME TITLE: North East Nigeria Security and Conflict and Stabilisation Programme
Country and Region:	Nigeria, Africa
IATI Unique ID:	CSSF-03-000008
HMG Partners / (LEAD in bold)	Ministry of Defence (MOD), Foreign Commonwealth and Office (FCO)
Total Budget:	ODA: £12.9m			Non-ODA: £16.9m
Budget this FY:	ODA: £5.84m			Non-ODA: £8.5m
Spend this FY:	ODA: £3.911m			Non-ODA: 8.8m
Original Programme Start Date: April 2019		Planned End Date: March 2021
Outputs					Score
1. Increased capacity of targeted regional and security partners to take and hold ground from violent extremist organisations, with positive perceptions of them by conflict affected communities.					B
2. Senior Leadership of regional and security partners have increased capacity to develop a joint campaign plan that is realistic, based on wider stabilisation approach and in line with International Humanitarian Law (IHL).					B
3. Nigerian Intelligence Fusion Cell has improved intelligence gathering, assessment and sharing capacity.					B
4. Police and other security actors have increased capacity to deploy into target areas and respond to the needs of all citizens including women and girls.					A
5. Increased capacity of government and security actors to engage with conflict-affected communities to provide short-term basic services and livelihood options to citizens including women and girls.					B
6. Increased capacity of target communities to accept the reintegration of conflict-affected groups including women and children.					B
7. Improvement in the ability of security and government actors to process low level non-state armed group (NSAG) members and survivors, including women and children, into appropriate criminal justice, defection or reintegration pathways in a prompter and IHL-compliant manner.					C
8. Increased coordination across HMG and use of research to inform programme choices.					A
Overall output score					B
Outcome Assessment: This was a challenging year for the programme and the delivery fell short of expectations due to a combination of factors both inside and outside of control of the team, including the security situation and Covid-19. Despite this, there have been positive steps to improve management which should set the groundwork for improvements in 20/21. Areas such as the Regional Stabilisation Facility (RSF) and the International Office for Migration (IOM) programme, supporting disengagement, disarmament, demobilisation, de-radicalisation and re-integration (4DR), offer potential for strategic and catalytic effect. The sub-regional approach seems to be a sensible pivot. The strategy developed towards the end of the reporting period appeared to be delivering results and should be sustained into 20/21 to be truly tested.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score		A	A	B	A	B	B	B
Risk Rating - low/medium/high		High	High		High		High
*output/outcome scores
How has the programme changed during this period? The programme has changed in six key ways: (i) a shift towards a centralised management structure for the delivery of military training to the Nigerian Army; (ii) a decision to train formed units as opposed to individuals; (iii) the movement of the Mercy Corp Conflict Management and Stabilisation programme to delivery through the DFID baseline; (iv) the redesigning of the IOM disarmament, demobilization, rehabilitation, and reintegration (DDRR) project; (v) a new partnership with United Nations Development Programme (UNDP) on the RSF; and (vi) the design and implementation of the Public Safety and Security component involving partnerships with USAID, Office of Transition Initiatives (OTI) and International Alert (IA).

What support did the UK provide in FY 19/20?

The UK provided support across two programme components, focussed on addressing threats to the UK’s national security interests and regional stability, including the threat posed by Boko Haram (BH).

Programme Component 1:
- Training and capacity building for the Nigerian Army, including on compliance with International Humanitarian Law (IHL) and law of armed conflict.
- The Senior Military Adviser (SMA) Cameroon contributed to building relationships, delivering training and capacity building and establishing the UK footprint in the wider Lake Chad Basin region (LCB).
- The programme has funded Operation TURUS, the British military operation assisting in the development of the capacity and capability of the Armed Forces of Nigeria to counter violent extremist organisation activity. Through this, the UK has provided advice and assistance to the Nigerian Intelligence Fusion Cell in Abuja, the Theatre Command HQ (TCHQ) and its subordinate elements in Maiduguri, and the Multinational Joint Task Force (MNJTF) in N’Djamena. This was delivered through the UK Intelligence Fusion Cell (IFC), Liaison Support Team (LST) and Cellule de Liaison et Cooperation (CCL) respectively.

Programme Component 2:
- Support to UNDP’s Nigeria national window of the Regional Stabilisation Facility (RSF) which aims to address the immediate stabilisation needs of targeted communities through a rapid response package of support that is time-bound, localised and integrated, helping to create pockets of stability. The three main outputs of the facility are: (i) Community Security and the Rule of Law Strengthened (ii) Essential Infrastructure and Basic Services functioning; and (iii) Livelihood-related.
- Support to the International Organisation for Migration’s (IOM) implementation of the project: Strengthening the Rehabilitation and Reintegration of Male and Female Low-Risk Former Non-State Armed Groups (NSAG) Associates.
- Implementation of two projects under the organisation Hadin Kan Mu Karfin Mu (Our Unity, Our Strength) which targets women and child survivors of BH violence, and community and religious leaders and communities displaced by conflict.
- Funding for improvements to police stations and police barracks, police communications capability, and provision of police pre-deployment training.

Key results for FY 19/20:
- Training of approximately 11,500 Armed Forces of Nigeria (AFN) and Cameroonian personnel, of which 7,000 are believed to have deployed to North East Nigeria.
- Establishment of a Counter-Improvised Explosive Device (C-IED) cell which has reduced instances of death and injury.
- Improvements in intelligence sharing and campaign planning capability have led to strong progress in increasing operational and tactical cooperation between Cameroonian and Nigerian security forces.
- Needs assessment completed for the police in Borno State, which has been used to inform the selection of six sites for rehabilitation activities, and initiate work on two of these.
- UNDP’s RSF multi-stakeholder Board is now operational and four Joint Action Plans (JAPs) have been agreed and are in place.
- Provision of Psycho-Social Support (PSS) to individuals in detention camp Operation Safe Corridor (OPSC) in Gombe.

Actions taken on recommendations from previous Annual Review

Progress on previous Annual Review recommendations has been mixed. Many of the recommendations relate to the need for continuous alignment between the Theory of Change and Results Framework, which has not been fully achieved and has impacted on some successes over financial year 19/20. Progress has been good on previous recommendations linked to ensuring oversight by a person that has overall responsibility for policy on North East Nigeria, greater coordination amongst the international community, and strengthening the connections across British Military Advisory & Training Team (BMATT) and Operation TURUS. Further actions are required to ensure other recommendations are met, including updating the Theory of Change and Results Framework, considering of a more focussed approach; greater consideration of the potential to increase political access, and better capturing of gender-related issues.

Key Lessons

- Importance of MEL: Had a robust MEL system been in place, the objectives of the programme would have been adapted to reflect a turbulent operating environment.
- Importance of focussing first on personnel: the programme requires improved staff continuity, capacity and capability, and more technical expertise.
- Aligning policy and programmatic ambition: programmatic ambition and risk appetite must be adjusted to match revisions in policy ambition.

Summary of Recommendations for FY 20/21

- Ensure the right blend of staffing and expertise within the team.
- Consider a joint programme management function across components to provide policy and programmatic coherence and ensure effective and compliant programme delivery.
- A comprehensive MEL Plan should be developed with a viable Theory of Change (ToC) and Results Framework (RF) for the expansion into LCB.
- UNDP’s RSF is the only viable stabilisation effort in the LCB and so should continue as a central thrust of the programme in future. More focus should be placed on supporting key regional institutions such as the MNJTF and Lake Chad Basin Commission (LCBC).
- CSSF’s 4DR programming should be redesigned to be more fully integrated.
- Design work should consider how best to adapt to COVID-19.