Annual Review - Summary Sheet

PROGRAMME TITLE: Somalia Counter Extremism Programme
Country and Region:	Somalia, East Africa
IATI Unique ID:	CSSF-03-000026
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £18m			Non-ODA: £0
Budget this FY	ODA: £4.8m			Non-ODA: £0
Spend this FY	ODA: £3.626m			Non-ODA: £0
Original Programme Start Date: March 2015		Planned End Date: June 2021
Outputs					Score
Rehabilitation: Beneficiaries develop and enhance knowledge, skills and attitudes in an environment conducive to positive change.					A
Support to reintegration: Beneficiaries enhance their prospects for sustained socio-economic reintegration.					B
Support to Federal Government of Somalia (FGS): FGS enhances its capacity to deliver the National Programme.					A
Overall output score					A
Outcome Assessment: The programme is well aligned with cross-HMG strategic objectives. However, the programme’s contribution to cross-HMG strategic objectives is limited. This is largely the result of the difficult environment in which the programme operates and the limited scale of the intervention relative to the problem it is seeking to address. Looking ahead, effort will best be spent on designing a new evidence-based programme, founded on realistic ambitions and with an enhanced focus on sustainability.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	N/A	A	A	A	A	B	A	B
Risk Rating - low/medium/high	N/A	High	High	High	Med.	High	Med.	High
*output/outcome scores
How has the programme changed during this period?			The COVID-19 pandemic emerged late in the 19/20FY. The primary impact has been that staff, including those of the implementing partners were required to work remotely. In addition, some key activities were delayed.

What support did the UK provide in FY 19/20?

The CSSF-funded Counter al-Shabaab Programme (CaSP) aims to weaken al-Shabaab (aS) and undermine its appeal by encouraging people to permanently (and where appropriate, publicly) leave the organisation. The Programme intends to achieve its objectives by:

1. Funding a low-level defector rehabilitation centre in Mogadishu (Serendi Rehabilitation Centre) to provide a means by which rank and file fighters looking to leave aS can defect and reintegrate into their home communities; and,
2. Continuing to support the Federal Government of Somalia (FGS) to implement its National Programme for Treatment and Handling of Disengaged Combatants (“the National Programme”).

The Serendi Rehabilitation Centre (“Serendi”) is co-managed by the Defectors Rehabilitation Programme (DRP) under FGS Ministry of Internal Security (MoIS), and by the Rehabilitation Support Team (RST) from Adam Smith International (ASI). Since October 2015, the centre has rehabilitated 295 aS defectors (including 38 in 19/20). The RST also support activity under objective (ii) above.

Key results for FY 19/20:

- 38 defectors processed through to exit (101 defectors remained in the centre as of 30 March).
- Amnesty Policy approved by FGS Council of Ministers and decreed into law by Prime Minister, with support of RST.
- Capacity building delivered to DRP staff, Serendi Centre staff, and the FGS across all Pillars of the National Programme.
- Production of research report on female recruitment and participation with aS (‘Invisible Women of al Shabaab’), improving understanding and informing potential future programming.
- Joint third-party monitoring (TPM) commenced – from January – to incorporate German-funded/ International Organisation for Migration-delivered rehabilitation centres in Kismayo and Baidoa, enabling greater information sharing and data gathering against wider National Programme priorities.

Key Lessons

- Defections do not follow a single pathway; formal defections to the FGS are not the primary means of defection from aS.
- There is a substantial and important opportunity to engage with female combatants and former combatants.
- Inadequate data collection and sharing across the National Programme and related Disarmament, Demobilisation and Reintegration (DDR) initiatives is hindering effective planning, monitoring and evaluation.
- There is a varied understanding of the overall CaSP objective amongst stakeholders.
- The National Programme, including the Serendi element, incorporates an important messaging component and lays part of the ground for a future peace deal. This was achieved by signalling that the FGS are willing to refrain from labelling defectors as ‘criminals’ or treating them as such.
- Future success and sustainability of the National Programme will depend on:
  - Development and implementation of a joint approach from donors (funding and strategy).
  - Harmonisation between existing (adult) rehabilitation centres in Kismayo and Baidoa.
  - Improved data collection/sharing between all (adult and child) rehabilitation centres.
  - Increasing the level of FGS buy-in and support.

Summary of Recommendations for FY 20/21

- Revise the Theory of Change and Results Framework, considering lessons learned and available data and analysis.
- Develop a Value for Money (VfM) framework, including a clear VfM proposition, benchmarks and indicators.
- Finalise development of the proposed Joint Donor Fund and Strategy, ensuring FGS and wider International Community consultation and buy-in.
- Develop clear plans regarding sustainability and exit.
- Enhance long term (12 months +) post-rehabilitation monitoring of defectors.
- Continue developing the ‘outreach’ strand, to drive further defections.
- Develop an HMG strategic communication and influencing plan for the National Programme that includes key FGS stakeholders, existing and potential donors and key stakeholder organisations such as UNICEF and the EU.
- Continue advocating for greater data sharing with UNICEF, especially regarding overall beneficiary numbers.