Programme Completion Review - Summary Sheet

PROGRAMME TITLE: East Africa Crime and Justice
Country and Region:	Kenya, Tanzania
IATI Unique ID:	CSSF-03-000019
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Crown Prosecution Service (CPS), National Crime Agency (NCA)
Total Budget:	ODA: £7.805m			Non-ODA: £0.5m
Total Spend:	ODA: £6.770m			Non-ODA: £0m
Original Programme Start Date: April 2015		End Date: March 2020
Outputs					Score
Casework and Operations					A
Tactical Capacity Building					A
Strategic Access and Influence					A
Learning and Evidence Based Decision Making					B
Overall output score: A
Outcome Assessment: The programme made some progress towards achieving its outcomes in Kenya and Tanzania. However, it is less clear whether the outcomes produced strategic and sustainable effects, due to a lack of an ‘end to end’ approach. The programme also generated some secondary benefits in Kenya on HMG’s counter-terrorism response and around the contested Kenyan elections in 2017.
Final Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	n/a	B	A	A	B	B	A	B
Risk Rating - low/medium/high	n/a	Medium	Medium	Medium	Medium	Medium	Medium	Medium
*output/outcome scores

What support did the UK provide?
The programme supported a criminal justice focused response to Serious and Organised Crime (SOC) in Kenya and Tanzania, funding UK National Crime Agency (NCA) officers and Crown Prosecution Service (CPS) Criminal Justice Advisers (CJA) in Tanzania and Kenya. Core activities included the following:
- Criminal case work and casework mentoring.
- Senior leadership training for the Kenyan Police.
- Establishing, training and equipping vetted law enforcement partner units, e.g. the Kenyan Transnational Organised Crime Unit (TOCU), the Tanzanian Law Enforcement Detachment, and support to the Tanzanian Drug Control & Enforcement Authority.
- Training and equipping prosecuting agencies, e.g. Kenyan Office of the Director of Public Prosecutions.
- Working to establish improved case management procedures and the introduction of new investigative techniques (e.g. digital recording of interviews in Tanzania), strengthened legal frameworks (e.g. amended drugs legislation in Tanzania) and sentencing guidelines.
- Improving mutual legal assistance protocols and associated casework of interest to the UK.
- Support to community engagement with the criminal justice system through a Kenyan non-governmental organization, HAKI Africa.

What results did the programme deliver? Will they be sustained?
The programme delivered tactical outputs which contributed to outcomes.
- Increased effectiveness of serious crime related operations and investigations (counter-narcotics, human trafficking, child sexual exploitation, anti-corruption).
- Strengthened coordination between targeted criminal justice and law enforcement actors/institutions.
- Enhanced international and regional cooperation on serious crime cases and operations, including with the UK, and strengthened mutual legal assistance processes.
- Strengthened prosecution capability, notably in relation to anti-corruption in Kenya.
- A changed attitude to case progression within the judiciary in Kenya.

However, it was less obvious that the programme produced strategic and sustainable impacts.

The programme also generated some wider effects in Kenya through its contribution to HMG’s counter-terrorism response and a more informed UK response following the contested Kenyan elections in 2017. Case mentoring activity was of a high quality and generated valuable political access and influence for HMG and reinforced wider HMG efforts on SOC. The programme’s approach to conflict sensitivity, gender sensitivity and monitoring and reporting improved over the course of the programme.

Lessons Learnt
- Overall, programme effectiveness was reduced by a lack of coherent programme design, inadequate assessment of the law enforcement and justice system, a lack of sustained thematic focus on SOC areas, and insufficient monitoring to assess what is working and what is not.
- A casework-based theory of change to strengthening criminal justice outcomes (the basis of current CPS and NCA delivery models) was found to be valid but a focus on strengthening cross-HMG governance, oversight and strategic direction is needed in order to maximise programme impact.
- These weaknesses can be traced back to how the programme was initially set up and how relationships were established between the programme and core implementing partners (NCA and CPS) and its regional nature.
- The value of the TOCU model is likely to be limited unless the unit can be so successful in its investigative approaches, that these are adopted by others and that a sustainable funding model can be found. Conditions to achieve sustainability should be considered during the design phase of a programme.
- Programme Design Objectives and implementation should be informed not only by operational insights but a solid analysis of the system, the surrounding political economy and HMG’s SOC strategy. Outcomes and outputs should be realistic, specific and measurable and based on clear evidence and able to provide clear guiderails for programme delivery. Governance and management needs should be identified and the ability to fulfil these should be assessed, as part of programme design. Exit strategies need to be built into programme design from the outset.
- Delivering a casework and operations model requires strong governance and cross-HMG engagement in the SOC / criminal justice space to help ensure activity aligns with programme objectives and supported by broader HMG efforts.
- A strong policy lead at a sufficiently senior level is required to provide oversight, leadership and tasking responsibility at country level supported by a country level programme board with cross-HMG representation.
- CJAs and NCA staff require administrative and programmatic support. Financial management and reporting systems need to be streamlined between government departments.