Annual Review - Summary Sheet

PROGRAMME TITLE: Nigeria Security and Justice Reform Programme (SJRP)
Country and Region:	Nigeria, Africa
IATI Unique ID:	CSSF-03-000007
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £17.96m			Non-ODA: £0m
Budget this FY:	ODA: £5.2m			Non-ODA: £0m
Spend this FY:	ODA: £5.279m			Non-ODA: £0m
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Improved legislative oversight and accountability of Nigeria's security sector, including through increased citizen participation in legislative processes.					A
Informed, inclusive and constructive public dialogue on security and justice reform issues.					A
The Nigerian Police Force are perceived to be more capable, accountable and responsive by key stakeholders in target areas and oversight mechanisms.					A
SJRP is a coherent and impactful programme, which is well managed, adapts to the context and capitalises on HMG political engagement, including via Office of the Vice President (OVP) advisers.					A
Overall output score					A
Outcome Assessment: The SJRP fulfilled its overarching justification for the FY19/20 extension period, which was to finalise work on passing the Police Reform Bill, strengthen and secure other changes to police regulations and reforms (notably trust fund arrangements and the National Community Policing Framework), and consolidate improvements to police-community coordination structures. By the end of the programme, anticipated policy changes were mostly in place or imminent (the Police Reform Bill itself was passed in June 2020), and in the process, the programme had scored multiple unanticipated achievements in promoting reforms. The SJRP’s primary function, central to its theory of change, was its investment in relationships and network building at all levels of the Nigerian political system, from federal, state, and local. This was directly cited by Nigerian beneficiaries as critical to its value and success.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*	2019/20*
Programme Score	N/A	A	A	A	A
Risk Rating - low/medium/high	N/A	Medium	Medium	Medium	Medium
*output/outcome scores
How has the programme changed during this period? N/A

What support did the UK provide in FY 19/20?

The SJRP was a three-year programme led by the FCO, extended to four years in FY 19/20 to bridge the February 2019 elections. The extension consolidated the programme’s gains immediately following the elections, focused particularly on police reform and improved police-community relations. The programme also developed a transition plan for the follow components:
- Legislative and executive oversight and accountability: Improved legislative and executive oversight and accountability of Nigeria's security sector.
- Public Accountability: More informed, inclusive and constructive public dialogue on security and justice.
- Policing: The Nigerian Police Force (NPF) in target areas and oversight mechanisms are perceived to be more capable, accountable and responsive by key stakeholders.

Key Successes in FY 19/20:

Tangible improvement in democratic oversight of the Nigeria Police Force (NPF) through increased engagement by the legislative and the executive arms of government including:
- Presidential assent and implementation of Police Trust Fund Act; presidential white paper committee to recommend implementation of report on the Special Anti-Robbery Squad (SARS) to foster transparency in the operation and mandate of the SAR;
- Passage of the Police Reform Bill and greater public awareness and constructive engagement on security and justice issues through the media by widening the scope of security dialogue through public town hall meetings; and
- Support for local radio stations, raising awareness at community level.
Approval and implementation of community policing framework and support by the Nigeria Policing Programme (NPP), contributing to the consolidation of UK investment in community policing implementation in Nigeria.
NPP replicated its successful Community Safety Partnerships (CSP), local policing plan among other community policing initiatives in several locations across Borno State, Kano, Enugu and the federal capital territory.
Evidence of UK leadership and influence within security and justice landscape in Nigeria:
- The Inspector General of Police endorsed and adopted the Borno Police Needs Assessment conducted by NPP as a basis for all donor engagement; and
- Coordination with UN Development Programme and USAID to level UK access to the NPF on the joint donor offer in the North East, resulting in NPF engagement in the Regional Stabilisation Facility (RSF) funded by the donor community in Nigeria.
Targeted gendered related support improved implementation of the Women Peace and Security (WPS) agenda. This included a public hearing on gender, the development of Standard Operating Procedure (SOP) for the NPF Anti Human Trafficking Unit (AHTU), and SJRP’s collaboration with the French Embassy and Ministry of Women Affairs to commemorate “16 Days of Activism against Gender Based Violence” in Nigeria.

Summary of Recommendations for FY 20/21

- Institutional security sector reform should remain part of the UK’s programming portfolio in Nigeria. This work contributes to greater regional stability and strengthens and deepens UK-Nigeria working relationship, trust and mutual understanding at both federal and local levels.
- Some elements of the SJRP should be taken forward in future programming/funding:
- Continued technical advisory support to Public and Legal Advocacy Centre (PLAC) during the process of drafting the Armed Forces Act.
- Integrating elements of the newly passed Police Reform Act (and Community Policing Framework) into police training curricula, using lessons-learned and findings from previous training.
- Support to police annual planning processes, given that changes in the legislative environment (the Police Reform Act and newly created trust funds) provide a stronger policy hook for this work.
- Conduct a best practice review of the contracting methods used for projects of this type.
- Improve contingency planning for programme activities that hinge on bills and other legal reforms, where political or bureaucratic delays may be expected.
- During programme design, plan for and mitigate against the high turnover in Nigerian institutions by early engagement with political and institutional authorities.
- Where a programme is in its final year or where an extension is not pre-decided, full consideration of sustainability and handover should be included in planning.
- Nationwide or system-wide programmes, where certain activities depend on the outcomes of others, should consider phased or staggered implementation work streams.
- For future programming, consider developing the coordination of multiple implementing partners. This will ensure streamlining and consolidating of reporting and coherence of programme work.