Annual Review - Summary Sheet

Programme Title: Africa Peace and Security (APS) Programme
Country and Region:	Africa
IATI Unique ID:	CSSF–03-000017
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD)
Total Budget:	ODA: £6.9m			Non-ODA: £13.5m
Budget this FY:	ODA: £4m			Non-ODA: £4.5m
Spend this FY:	ODA: £3.93m (98.24%)			Non-ODA: £4.52m (100.40%)
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
1. Improved capability of Troop Contributing Countries and Police Contributing Countries on African Union (AU)/UN missions					A
2. Effective peace support centres providing relevant training and with clear path to being self-sustaining					A
3. Strengthened AU Peace Security Department (PSD)					A
4. Improved capability of Regional Security Mechanisms and AU/UN missions					A
5. Improved capability of targeted member state actors.					A
6. Strengthened AU capability to respond to conflict through well-developed preventative diplomacy strategies and early warning information.					A
Overall output score					A
Outcome Assessment: / The APS programme is a maturing and expanding programme combining strategic, operational and tactical support to peace support operations across Africa. It has continued to build productive relationships with personnel, governments and the African Union. Following its remit being made continental, there have been new challenges on governance and reach. These have been addressed successfully despite resulting in new demands being placed upon the programme management team and the British Peace Support Team Africa (BPST(A)). New or enhanced areas of work have been bedded in and harmonised with the other lines of activity.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*		2019/20*
Programme Score	African Union: C / BPST:B / MSC Cranfield: N/A	African Union: B / BPST: B / MSC Cranfield: N/A	African Union: A / BPST: B / MSC Cranfield: N/A	A	A	A	A
Risk Rating low/medium/high	Medium	Medium	Medium	Medium		Medium
*output/outcome scores
How has the programme changed during this period? / APS has become a continental programme, which increased the range of stakeholders and activities. The Results Framework has been updated to reflect the HMG Africa Strategy. BPST(A) has completed its transition of structure and range of responsibilities.

What support did the UK provide in FY 19/20?

- Pre-deployment training for African forces deploying on African Union (AU) and United Nations (UN) operations.
- Technical assistance to enhance AU delivery of Peace and Security Operations (PSOs).
- Technical assistance from BPST(A) to regional peacekeeping training centres in Ethiopia and Kenya.
- Support for the development and implementation regional maritime security frameworks in Eastern Africa.
- Activities to enable stronger mechanisms for weapons and ammunition accountability and management of small arms and light weapons.
- Support to the AU’s Department for Political Affairs to prevent and mitigate conflict.

Key results for FY 19/20:

- Monitoring & Evaluation (M&E): BPST(A) adapted Training Assessment System for Evaluation and Reporting (TASER) methodology.
- APS capability and capacity development:
  - Engagement in West Africa with French and US partner organisations and Pre-Deployment Training (PDT) for forces deploying on UN missions.
  - Supported Malawian forces deploying to MONUSCO (UN Stabilisation Mission in the DR Congo) on gender mainstreaming on operations.
  - Provided Technical Assistance to support the design of new AU PSO doctrine.
  - Initiated training in weapons and ammunition management for the AU Mission in Somalia (AMISOM) and Nigerian Forces involved in counter terrorism/counter insurgency operations.
- Supported the International Institute for Democracy and Electoral Assistance (International IDEA)’s work to develop the Gambian constitution and the South Sudan Peace Agreement.

Key Lessons

- Programme Management: Following the expansion of the programme to a continental remit, a significant change from the original programme, it was important to amend the Theory of Change (ToC), widen the membership of the Local Strategic Board (LSB), adjust the Results Framework and introduce a tracking process for implementation.
- Gender Mainstreaming: To meet planning and implementation requirements, it was important that support was sought from HMG gender advisers, which ensured the programme’s gender development work was more firmly set within the framework of Women Peace and Security.
- Monitoring & Evaluation: To support the collection of data and analysis, it was important to establish an M&E toolbox that included core methodology, TASER and ensure the M&E for training elements of this process were in place.

Summary of Recommendations for FY 20/21

- Governance. The expanded remit has increased programme governance responsibilities. Actors at Local Strategic Board level need to understand the roles and responsibilities of stakeholders to ensure coherence in guidance and direction.
- Continental Remit. Continue the re-structure of BPST(A) in line with its continental remit.
- Small Arms & Light Weapons (SALW). There is a growing demand from African states for support. There may be opportunities to use work in this area on partners’ defence systems and process, to tackle other management shortfalls.
- Access and Influence. The AU Team and BPST(A) are achieving significant levels of access, influence, understanding and engagement for the UK. Consider developing a Military Access and Influence measure to identify the specific benefits.
- International Institute for Democracy and Electoral Assistance (IDEA). Continue to support International IDEA but better define the links between inputs, outputs, outcomes and effects of their work, potentially through a Theory of Change process.
- CSSF and Defence Engagement. Clearer distinction should be made between outputs more suited to CSSF-funded activity and MoD Defence Engagement.
- Strategic Communications. Continental expansion creates a requirement to spend more time in communication and outreach to a wider range of stakeholders. BPST(A) should work closely with the APS Programme Office to develop a suitable approach.