Annual Review - Summary Sheet

PROGRAMME TITLE: Towards a Political Transition in Ethiopia
Country and Region:	Ethiopia, Africa
IATI Unique ID:	CSSF-03-000033
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for Internal Development (DFID), Ministry of Defence (MOD), National Crime Agency (NCA)
Total Budget:	ODA: £2.3m			Non-ODA: -
Budget this FY:	ODA: £0.32m			Non-ODA: -
Spend this FY:	ODA: £0.29m			Non-ODA: -
Original Programme Start Date: NOV 2019		Planned End Date: OCT 2021
Outputs					Score
Targeted HMG political engagement and policy initiatives to bring about a more inclusive political settlement.					B
Approaches to enhance the performance, compliance and accountability of selected security and justice institutions and actors designed and piloted.					B
Greater engagement, understanding and capacity of the main conflict/political parties and communities, to enable the inclusive political transition process to progress in Somali Regional State.					A
Increased awareness and understanding of the needs of victims and survivors (including Sexual Gender Based Violence (SGBV) progresses their rehabilitation and reintegration.					A
Peace and reconciliation arrangements are initiated and integrated into the wider political transition and reconciliation process.					B
Regional actors have improved understanding of the interconnections of political and conflict dynamics in the Somali regional state and wider Ethiopia and are enabled to effectively address cross-regional conflicts.					B
Increasingly robust cross-HMG evidence and learning processes, together with strengthened contribution to gender equality outcomes and stronger conflict sensitivity approaches.					B
Overall output score					B
Outcome Assessment: / Notable progress was made in the reconciliation process for Somali Regional State, with the programme making a significant contribution. Engagement on supporting political reform and scoping Security and Justice progressed at slower pace. This partially reflected disruptions caused by Covid-19 and external constraints, but also HMG internal factors, raising questions about the prospect of successful implementation.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	-	-	-		-		B	B
Risk Rating - low/medium/high	-	-	-		-		Medium	Medium
*output/outcome scores
How has the programme changed during this period?			Programme launched in Nov 2019.

What support did the UK provide in FY 19/20?
- Scoping and initiating activities in support of the political transition, finding in-roads into strengthening the capacity of Security and Justice Sectors, and mitigating ethnic tensions in Ethiopia.
- Support to transform the Ogaden National Liberation Front (ONLF) into a political party and wider reconciliation efforts in Somali Regional State.
- Development of a social media monitoring mechanism on disinformation and hate speech in the context of the upcoming general elections.

Key results for FY 19/20:
- Good progress in rolling out reconciliation work in Somali Regional State, contributing to the region developing into a rare ‘bright spot’ in an overall deteriorating country context.
- The successful initiation of a social media monitoring activity supporting the preparations for national elections promises to be a valuable contribution to HMG objectives, generating situational awareness on crucial discussions around the elections and providing an instrument for addressing new conflict dimensions.

Key Lessons
- Clearer agreement on the CSSF’s piloting function and associated risk threshold could help add value. This includes issues of ownership and programme governance mechanisms - HMG consensus-building on contentious issues such as engaging with the security sector is clearly a challenge. A more process driven, less discursive internal approach may produce better results.
- The programme identifies suitable areas for CSSF work but has so far struggled to secure buy-in from senior stakeholders – opportunities identified by horizon scanning require an acceptance of the risk of failure to be fully exploited.

Summary of Recommendations for FY 20/21
- Clarify the strategic fit with the larger HMG country portfolio, specifying the programmatic and political gains sought.
- Rapidly activate the Policy Fund as post-Covid circumstances permit and validate the continued value of this component.
- Continue to explore access points for support to the security (and justice) sector. New momentum could be injected by further clarifying the intent and approach to scoping and revisiting the component’s Theory of Change. Explore additional, external expertise to complement internal perspectives.
- Conduct evaluation and research around the Somali Regional State reconciliation support to explore scaling up options and identifying lessons to inform the wider national process.
- Strengthen Value for Money systems and processes with more focus on efficiencies.