Annual Review - Summary Sheet

PROGRAMME TITLE: Sahel Stabilisation
Country and Region:	Mali, Niger, Chad, Burkina Faso - Africa
IATI Unique ID:	CSSF-03-000024
HMG Partners (LEAD in bold)		Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £11.25m				Non-ODA: £1.1m
Budget this FY:	ODA: £3.74m				Non-ODA: £0.5m
Spend this FY:	ODA: £3.482m				Non-ODA: £0.5m
Original Programme Start Date: April 2018			Planned End Date: March 2021
Outputs					Score
1.1 New data and findings about conflict dynamics, interventions and approaches produced and disseminated.					A
1.2 UK participation at strategic level in national and international efforts in Mali, Niger and Chad.					A
2.1 UK support to peacebuilding initiatives in Mali, Niger and Chad increased.					A
2.2 Improved capacity of community and security forces to cooperate and work towards stabilisation.					B
Overall output score: A
Outcome Assessment: The reporting period saw a worsening operational environment (security, political, human rights) in all countries covered by the Programme. Bringing about catalytic positive change in stabilisation was therefore challenging and limited in scale and scope. Despite this, research and UK expertise were used to good effect and have begun to influence national and international stakeholders. There was improved delivery by Implementing Partners (IPs) in Mali and Niger. The Programme is also now ready to expand to activities in Burkina Faso and has laid the groundwork for further activities in Chad. Overall, outcomes are on course to meet expectations with an improved Theory of Change and evidence base.
Outcome Score: A				Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*		2019/20*
Programme Score	N/A	N/A	N/A	A	B	A	A
Risk Rating - low/medium/high	N/A	N/A	N/A	Medium		Medium
*output/outcome scores
How has the programme changed during this period? Number of Outputs reduced from five to four. Scope of delivery changed: Foundation Hirondelle project in Niger and strategic support to the EU in Mali ended. Search for Common Ground (SFCG) activities were reduced. New interventions included support to stabilisation in Central Mali through Adam Smith International (ASI) and in support of the Nigerien Government Stabilisation Agency (HACP) in Niger.

What support did the UK provide in FY 2019/20?
- Developed research and evidence base for stabilisation in Mali, Burkina Faso, and Niger through the Institute for Security Studies (ISS). Findings disseminated internally and externally to influence UK and partner policy and programming.
- Supported stabilisation efforts in Mali in line with the mandate of the UN Mission in Mali (MINUSMA) and the Government of Mali’s stabilisation plan for Central Mali.
- Developed land governance resolution and strategic communications projects, ready to begin implementation in FY 2020-21.
- Supported community-based conflict prevention/resolution/stabilisation projects in Mali and Niger, including work with the Government of Niger’s Stabilisation Agency (HACP)

Key results for FY 2019/20
- Influenced policymakers to use UK-funded research and data, and UK approaches to stabilisation, to improve the evidence base for policy and programming in Mali and Niger.
- Implementation of stabilisation projects through the MINUSMA Trust Fund that support the implementation of the Malian Government “Plan de Securite Integree pour la region du Centre” (PSIRC). This includes projects covering Civilian/Military relationship building and provision of technical assistance.
- Supported communities in southern Mali to identify conflict and resilience factors and develop potential conflict resolution mechanisms.
Built trust between the local population and security forces in community project bordering Mali and Niger.
Supported community development plans to enable stabilisation in Niger.

Key Lessons

- Data collection through IPs is proving challenging but will remain key in understanding impact at local and national and regional levels.
- The programme must take difficult decisions on geographical spread, due to risks of contagion of violence and instability. Within Mali, decentralisation could be a more explicit part of the portfolio.
- There are opportunities for more focused support to MINUSMA to reinforce UK troop deployment to UN Peacekeeping Mission at end-2020.
- The portfolio has important linkages to much larger UK ODA investments in the region which need to be made more concrete.
- Covid-19 will affect the programme in FY 2020-21. Though delivery is mostly through local partners, the programme should prepare for delayed activity if international staff can only work remotely.

Summary of Recommendations for FY 2020/21

- Influencing national and international partners through UK niche expertise. Given the multiple challenges in the region, its size, and the number of other international actors with significantly larger development portfolios and longer histories of engagement, the UK is right to look for niche areas where it can have most impact. Stabilisation expertise and evidence-based programming are two such areas. This should be used, and communicated, more effectively.
- UK funding for stabilisation activity through the MINUSMA Trust Fund (TF) should continue. Direct support to the TF could include the secondment of an adviser to help with M&E support, conflict sensitivity, human rights benchmarking, and project design and development.
- The Programme should have a more systematic approach to mainstreaming gender. This can be done by improvements to the Results Framework and its indicators, in collaboration with IPs.
- Programme delivery through local and international Civil Society Organisations (CSOs) should continue. There is scope to help CSOs improve their programme management and reporting.
- CSSF Sahel Programmes should prepare for post-March 2021 – the programme is currently planned to end in March 2021. In future it could be merged into a single Sahel programme, along with the Defence and Security Programme.
- The geographical scope should continue to evolve - the programme has begun to develop away from a Mali focus, with activity now underway in the tri-border region of Mali, Niger and Burkina Faso. This makes sense given the transnational nature of the threats and the need to contain the “contagion” of violent extremism and instability in the region.
- External MEL support for the Programme is now well established and producing positive results, including improvements to the Theory of Change and Results Framework, and support to IPs. This should continue, with the CSSF Team gaining progressively more ownership of MEL.