Annual Review - Summary Sheet

PROGRAMME TITLE: East Africa Preventing Violent Extremism
Country and Region:	East Africa – Kenya, Uganda, Tanzania, Ethiopia, and Mozambique
IATI Unique ID:	CSSF-03-000018
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Home Office (HO)
Total Budget:	ODA: £12m			Non-ODA: -
Budget this FY:	ODA: £4m			Non-ODA: -
Spend this FY:	ODA: £3.114m			Non-ODA: -
Original Programme Start Date: August 2019		Planned End Date: March 2020
Outputs					Score
1.1 Intervention packages for at-risk individuals in violent extremism (VE) hotspots and hotbeds are tested.					B
1.2 Greater understanding of the risks of radicalisation and recruitment and VE dynamics, through research and analysis, to inform future policy and programming.					B
2.1 Key non-state actors are provided with skills to support at-risk individuals that identify, refer, advise/mentor and safeguard them from radicalisation and recruitment into VE groups.					B
2.2 Key non-state actors are provided with skills to investigate VE dynamics and better identify those at-risk of radicalisation and recruitment.					B
2.3 Key non-state actors are provided with skills and opportunities to engage government on P/CVE action.					B
3.1 Context-appropriate methodologies to improve government knowledge of radicalisation and recruitment, and of good P/CVE practice are developed.					B
3.2 Support to the development and implementation of P/CVE policy frameworks.					C
3.3 Interventions to improve relationships and interactions between national and sub-national governments, and state and non-state actors on P/CVE, are provided.					B
4.1 Knowledge and learning utilised internally to inform adaptative management and shared externally with targeted P/CVE actors.					B
5.1 Programming is gender aware and conflict sensitive.					B
Overall output score					B
Outcome Assessment: The Collective Resilience Against Extremism (CREATE) project, assessed on its own merit, has performed sufficiently well in its inception period. The overall P/CVE programme, however, is missing key components including a Theory of Change (ToC) accounting for the programme as a whole and a complete programme-level Results Framework with milestones for FY 2019/20. An explicit HMG-led strategic approach to influencing key regional P/CVE stakeholders using the evidence generated by CREATE is needed to support successful programme delivery.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	B	B	B	A	A	A	B	B
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium		High
*output/outcome scores
How has the programme changed during this period?	Following the end of Building Resilience in Civil Society programme (BRICS) in FY 18/19, a new project titled Collective Resilience Against Extremism (CREATE) was launched in August 2019 with a new implementing partner consortium and its regional focus expanded to include Ethiopia and Mozambique, as well as Kenya, Uganda and Tanzania.

What support did the UK provide in FY 19/20?
- Interventions to assist individuals at risk of radicalisation or recruitment into VE groups and build the capacity of state and non-state actors to engage with VE.
- Support to the United Nations Office on Drugs and Crime (UNODC) improve the capacity of Kenya Prison Services to respond to threats of radicalisation in a prison environment in three prisons in Nairobi and Mombasa through training and technical assistance.
- Support to the United Nations Development Programme (UNDP) to assist Tanzania's National Counterterrorism Centre in developing a National P/CVE Strategy.
- Funding for Chalkstone Mosaic development of an Artificial Intelligence tool to analyse and predict trends in conflict in Kenya.

Key results for FY 19/20:
- Finalising the CREATE implementation model to work against three outcomes with at-risk beneficiaries, non-state and state actors.
- CREATE established relationships with local implementing partners in Kenya and Ethiopia and with government counterparts in Kenya, Tanzania, Uganda and Ethiopia.
- The research partner delivered two scoping assignments on VE in prisons in Kenya and the Kigoma region in Tanzania.
- The Community-Led Research and Action, which launched in two locations in Mombasa and combines research with counselling, showed a tentative increase in resilience in the first batch of participants.

Key Lessons
- Internal governance structures should provide strategic direction and coordination to build consensus on how the programme can make a valuable contribution to the UK’s strategic objectives.
- The political access and influence (PAI) strategy and outcome 4 should be HMG lead. Implementing partners do have an active role to play in securing PAI but this should be applied through timely strategic direction by HMG to benefit programming.
- Regional priorities should be clearly defined with implementing partners. The countries in which CREATE is poised to achieve the strongest results are not necessarily aligned with stated HMG stakeholder priorities.

Summary of Recommendations for FY 20/21
For the CSSF programme and policy teams:
- Review the P/CVE programme Theory of Change at the earliest opportunity. A comprehensive theory of change should reflect the expected programme impact, outcomes, the causal pathways linking the two, as well as contributions to regional strategies and the adopted gender strategy.
- Ensure that the direction and ownership of the programme-level PAI approach is clear and fully articulated.
- Seek out opportunities to integrate cross-regional programming using regional strategies and ambitions.

For the CSSF programme team:
- Develop a programme-level results framework that covers all the outcomes and funded interventions, measures the quality of women’s participation and tracks gender issues and risks with relevant mitigating actions.
- Ensure the analytical, strategic and resource commitments made on gender are prioritised and operationalised, including commissioning a robust gender analysis.
- Strengthen the accountability of the two UN-implemented projects, UNODC and UNDP. Each project should have its own results framework that sets out clear targets and timeline.

For the CREATE implementing partner:
- Ensure that CREATE now works towards delivery of more tangible outputs in Ethiopia and Mozambique.
- Develop an approach to better use evidence produced through CREATE, complemented by an evidence tracker to capture the potential application of major programme findings beyond the programme itself.