Annual Review - Summary Sheet

PROGRAMME TITLE: Niger Delta and Maritime Security and Stability
Country and Region:	Nigeria, West Africa
IATI Unique ID:	CSSF-03-000022
HMG Partners (LEAD in bold):	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD)
Total Budget:	ODA: £1.8m			Non-ODA: £1.36m
Budget this FY:	ODA: £0.9m			Non-ODA: £0.6m
Spend this FY:	Total spend: £1.478m
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Improved coordination, operational capability and capacity in the Nigerian Navy (NN) to address maritime threats.					A
Improved coordination, operational capability and capacity in maritime law enforcement agencies and criminal justice actors, to address maritime threats.					A
Strengthened evidence base, best practices strategies and mechanisms for dialogue, advocacy and engagement on insecurity and instability by key stakeholders.					A
Gender and conflict-sensitive pilots provide lessons for alternative policy approaches on security and stability in the region.					A
Overall output score					A
Outcome Assessment:	Outcome Score: A		Risk: Medium

Summary of Programme Performance
Year	2016/17	2017/18*			2018/19*		2019/20*
Programme Score	Output B (BMATT) / A (Niger Delta Stabilisation - NDS)	Output / B (BMATT) / A (NDS)		Outcome / B (BMATT) / A (NDS)	Output / B	Outcome / B	Output / A	Outcome / A
Risk Rating low/medium/high	Medium (BMATT) / Medium (NDS)	Medium (BMATT) / High (NDS)			Medium/High		Medium
*output/outcome scores
How has the programme changed during this period?			Two separate programmes were merged into one bigger programme from FY18/19 onwards.

What support did the UK provide in FY 19/20?

Security and governance
Capacity building provided by the British Military Assistance Training Team (BMATT) to the Nigerian Navy to improve maritime security in the Gulf of Guinea. This includes:
- Capacity building in maritime law enforcement, prosecutions and judiciary by the United Nations Office on Drugs and Crime (UNODC).
- Support to the Nigerian Government’s policy process to implement a coordinated development plan for the Niger Delta region – working with the Stakeholder Democracy Network (SDN).

Economic Development
Support to pilot economic diversification projects to provide alternative livelihoods in marginalised communities otherwise at risk of becoming involved in crime. Lessons were shared for replication and/or scale up with the Nigerian Government (federal and state), international missions and the private sector.

Political Analysis
Research and political economy analysis on conflict and stability issues in the Niger Delta to inform wider responses by HMG and the international community.

Key results for FY 19/20
- An increase of 30% in Nigerian Navy (NN) interventions in suspected maritime crime, and subsequent arrests, in the Gulf of Guinea.
- The signing by President Buhari of the Suppression of Piracy and Other Maritime Offences Act 2019.
- The agreement between Nigerian Government departments and maritime law enforcement agencies of a protocol for evidence collection under the Harmonised Standard Operating Procedures (HSOP) on Arrest, Detention and Prosecution of Vessels and Persons in Nigeria’s Maritime Environment.
- The launch by the Ministry of Niger Delta Affairs of a website for citizens to monitor the delivery of the Stakeholder Implementation Work Plan (SIWP) - a framework for the coordination of investments in development and stabilisation interventions in the Niger Delta Region.

Key Lessons
- Multi-project programmes with different components require a lot of resource to actively manage and bring implementing partners (IPs) together. This requires significant Senior Responsible Owner (SRO) time and needs to be included as a key part of their job description.
- Programmes such as this require sustained diplomatic engagement – with political analysis and the work of IPs used to inform high-level British High Commission political engagement.
- Effective and consistent communication of the objectives, value and results of programmes to internal stakeholders is essential to generate buy-in.
- Pilot projects and capacity building needs to focus on sustainability, which should be embedded at the programme design stage.
- More success can be achieved in promoting interagency cooperation through practical exercises and trainings where law enforcement agencies train each other and identify their own opportunities for coordination.

Summary of Recommendations for FY 20/21

Strategic
HMG should remain actively engaged in the Niger Delta - the recent Joint Assessment on Conflict and Security (JACS) identifies the importance of the region for the stability of Nigeria and UK interests.
- Consider commissioning an ongoing Nigeria-wide stability and political economy analysis project.
- Ensure continued diplomatic engagement on the anti-piracy bill and SIWP - the anti-piracy bill has yet to be implemented, and the SIWP has not yet been fully implemented.

Maritime security
- Key question to consider for the BMATT component – resolving the tension between focusing capacity building at the Western command base and the objective of delivering results in the Gulf of Guinea.
- Engage with the CSSF Monitoring, Evaluation and Learning (MEL) team on how better to track the medium-term effect of naval capacity-building. One challenge is the lack of access to NN data.
- Make collaboration between BMATT and UNODC a requirement for future support – the opportunities for increased synergy between these components was identified in the FY18/19 Annual Review but no noticeable improvement in collaboration was seen in FY19/20.

Cross-cutting
- Work with the CSSF MEL team in 2020/21 to confirm the appropriate level of VfM assessment.
- The risk register for FY 2020/21 should include a risk on the potential for an increase in piracy due to the emerging impact of the Covid-19 related drop in global oil prices, and mitigation measures to ensure that capacity-building support to an in-shore NN vessel does not exacerbate reputational risks or conflict risks.
- As soon as possible in 2020/21, refine the theory or change and results framework drawing on this review’s recommendations.