Annual Review - Summary Sheet

PROGRAMME TITLE: Nigeria Countering Organised Crime and Corruption
Country and Region:	Nigeria, Benin, Togo
IATI Unique ID:	CSSF-03-000006
HMG Partners (LEAD in bold)	National Crime Agency (NCA), Crown Prosecution Service (CPS), Immigration Enforcement International (IEI), Border Force (BF), Home Office (HO)
Total Budget:	ODA: £21.781m			Non-ODA:
Budget this FY:	ODA: £3.231m			Non-ODA:
Spend this FY:	ODA: £3.231m (estimated)			Non-ODA:
Original Programme Start Date: 2015/16		Planned End Date: April 2021
Outputs					Score
Joint Border Task Force (JBTF) and Project OKRA create vetted multi-agency units capable of conducting effective serious organised crime (SOC) investigations.					A
National Crime Agency (NCA) Project INSTINCT increases probability of safely recovering the hostage/s taken in criminal kidnap events.					A
Overall output score					A
Outcome Assessment: Project implementation continued throughout the year, despite the impact of COVID-19 towards the end of the financial year. Vetted units are now in place and functioning well. Joint Border Task Force (JBTF) and Project OKRA Units have played critical roles in the investigation and prosecution of corruption and trafficking cases. / INSTINCT has continued to demonstrate its effectiveness. Information exchange between partners including international counterparts (from South, East and West Africa, the EU, Australia and the Far East) is improving as a result of improved levels of trust. / Important steps were taken during the year to improve project documentation and management. Despite the progress made, it is possible that more could be done to leverage these positive results in support of HMG’s diplomatic and political engagement at strategic levels with Nigerian counterparts.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	B	A	A+	A+	A	A	A	A
Risk Rating - low/medium/high	Medium	Medium	Medium		High		Medium
*output/outcome scores
How has the programme changed during this period? In 2018/19 it was envisioned that the programme would conclude at the end of 2019/20. Midway through 19/20 a decision was taken to support an additional year (2020/21) to reach the required levels of project maturity to enable transition to host nation ownership.

What support did the UK provide in FY 19/20?

The programme for 2019/20 consisted of:
1. Joint Border Task Force (JBTF): capacity-building support by UK law enforcement mentors led by the NCA to the Nigerian multi-agency task force established in 2015/2016.
2. Project BODKIN (BENIN) and GALLEON (TOGO): support to develop units in Benin and Togo that use human intelligence, digital forensics and surveillance to gather evidence to be used in the prosecution of organised crime groups.
3. Project OKRA: An intelligence and evidence collection project focused on enablers of serious and organised crime. NCA developed a sustainable and long-term partnership with JBTF to deliver successful criminal justice outcomes, from target selection and development to prosecution.
4. Project INSTINCT: Anti-Kidnap Capacity Building project. NCA delivered capacity building on the management of Nigerian and international kidnap cases.

Key results for FY 19/20:

- A high-profile businessman was arrested and extradited from Togo for fraud and money laundering offences in July 2018and subsequently convicted and sentenced to five years imprisonment.
- Project BODKIN resulted in the largest seizure of cocaine (750 kg) ever in Benin, leading to six convictions, including senior gang members. A further seizure of cocaine (136.5 kg) in Benin the same month led to two convictions.
- In part as an adaption to COVID-19 and to help reduce delays in the prosecution process, the successful initiation of virtual trials using video link technology.
- The implementation of new custody Standard Operating Procedures which include specific guidelines on duty of care and the welfare of detained persons at JBTF HQ in Lagos has resulted in improvements in safety of those detained.
- The opening of the JBTF-funded custody facility and victim interviewing suite at the National Agency for the Prohibition of Trafficking in Persons (NAPTIP) Zonal Command in Benin City in January 2020 raised standards of witness care and detention.
- Digital forensic evidence is now obtained routinely in all cases.
- The implementation of a programme of intense operational activity, including targeting the highest level of criminality, led to the arrest of a major international drug trafficker.

Key Lessons

- Importance of clear financial planning to enable and manage programme delivery.
- Strong relationships are critical to ensure that the UK is seen as the ‘go to’ actor for international counterparts.
- Targeting and tackling more powerful aspects of SOC groups, encouraging cooperation between state and national level police commands, and promoting cooperation between different agencies requires sustained effort over a long-term period.

Summary of Recommendations for FY 20/21

- Financial management: It is critical to establish the minimum funding levels required to sustain each project component and internally consider a separate assessment of what it would take to re-establish cooperation in the future in the event the programme is significantly reduced or stopped at the end of FY20/21.
- A clear ‘lessons learned’ process would support the team to understand the key components behind the projects’ success and enable this learning to be shared more broadly.
- Communicating success: The team should consider what more they can do to capture the impact of the project against the Embassy’s overall priorities and ensure this is shared with colleagues in both Abuja and London to ensure it is understood.