Annual Review - Summary Sheet

PROGRAMME TITLE: Sahel Defence and Security
Country and Region:	Mali, Niger, Senegal (the Sahel region), Africa
IATI Unique ID:	CSSF-03-000023
HMG Partners (LEAD in bold)		Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £9.4m				Non-ODA: £10.9m
Budget this FY:	ODA: £2.8m				Non-ODA: £1.9m
Spend this FY:	ODA: £2.8m				Non-ODA: £1.4m
Original Programme Start Date: April 2018			Planned End Date: March 2021
Outputs					Score
Increased support to the G5 Sahel-Joint Force member countries of high-quality material and Human Rights support.					C
High-quality strategic advice, infantry, medical and International Humanitarian Law training provided to EU Training Mission in Mali					A+
Selected Officers from regional armed forces supported by the UK in professional development.					A
Personnel in Regional Security Forces are trained and mentored to more effectively generate and act on intelligence.					A
Increasingly gender aware programme delivery					C
Overall output score: A
Outcome Assessment: / The programme has made steady progress in building capacity of a range of Sahelian (primarily Malian) security actors. Improvements in capacity have manifested in improved intelligence generation and sharing, which has had real-world impact, such as helping tackle illegal migration routes. UK access and influence has increased over the duration of the programme, and in some areas, progress has been made towards formalising relationships. The performance issues identified in the last report in relation to the support to the Gendarmerie appear to have been resolved. The programme has helped prepare the ground for the UK deployment to the UN peacekeeping mission, MINUSMA, and UK forces have benefited from lessons learned during the programme.
Outcome Score: A				Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*	2019/20*
Programme Score	N/A	N/A	N/A	B/B	A/A
Risk Rating - low/medium/high	N/A	N/A	N/A	High	Medium
*output/outcome scores
How has the programme changed during this period? / Changes have been minimal during the reporting period, however, programme funding for National Crime Agency (NCA) work in Senegal ended in March 2020.

What support did the UK provide in FY 2019/20?

- Provided six military and two civilian secondees to the EU Training Mission (EUTM), supporting training to the Malian military on infantry, medical, counter-Improvised Explosive Devices (IED), and international humanitarian law.
- Provided two military officers and a senior civilian advisor to the UN mission in Mali (MINUSMA) to support planning (ahead of the UK’s deployment to MINUSMA) and coordination.
- Provided non-lethal equipment to the Nigerien battalion of the G5 Sahel Joint Force
- Supported the professional development of Sahelian military officers by sending selected officers on UK and regional command, strategic, leadership and operational courses, and by providing support to the Ecole Maintien de la Paix (Peacekeeping School) in Bamako.
- Provided training and mentoring to the Malian Gendarmerie to support intelligence-led operations.
- Provided training and mentoring to the Malian security service (DGSE) to tackle serious and organised crime and related threats.
- Supported the Senegalese Anti-Corruption Unit to tackle serious and organised crime.

Key results for FY 2019/20

- Strengthened relationships between the UK, Sahelian security and defence agencies, and international actors, as evidenced by an increase in the number of incidents of cooperation.
- Provided training on International Humanitarian Law and gender issues to over 1000 Sahelian troops undertaking relevant roles.
- Provided professional development training for nearly 100 Sahelian military officers and supported the work of the of the Ecole Maintien de la Paix (Peacekeeping School) in Bamako.
- Trained 65 members of the Malian Gendarmerie, supported the deployment of intelligence capacity in three locations, and helped generate nearly 600 intelligence reports that were shared with relevant authorities in the UK and the Sahel. This was particularly relevant as the UK prepared for its deployment of troops to MINUSMA.

Key Lessons

- Implementing partners – including British military seconded to MINUSMA– were not always as joined up or aware of the programme’s overarching objectives as they could have been.
- Remote mentoring (e.g. with the Gendarmerie) proved to be an effective way of building capacity, and in some instances may offer better value for money than face-to-face mentoring. However, this is only likely to be in the case when relationships have already been established.
- Providing unilateral support to the G5 Sahel Joint Force proved costly and difficult; where politically feasible, working through others (including the EU) can often be a more effective way of providing support.
- The equipment provided to the G5 Sahel Joint Force did not have the impact it could have had – either in terms of political leverage or operational effect – because it was not provided as part of an overarching package of support.
- The political access and influence gleaned from support for regional training courses for military officers would be significantly enhanced if a more systematic approach to maintaining alumni networks was taken.
- Where the drivers of poor performance of troops – e.g. in relation to International Humanitarian Law – are related to motivation or opportunity, rather than capability, training alone will be of limited benefit.

Summary of Recommendations for FY 2020/21

- When the programme concludes in March 2021, it should be merged with the CSSF Sahel Stabilisation programme to create a single programme and increase coordination. This programme should ensure it forms part of a broader HMG engagement in the Sahel which aims to both respond to the current conflict, address its root causes, and prevent future conflicts.
- Following the UK’s exit from the EU and consequent withdrawal from the EU Training Mission in Mali, the programme should consider reallocating support to the Ecole Maintien de la Paix (Peacekeeping School) in Bamako.
- The programme team should implement a regular forum to bring together implementing partners to share information on their respective projects.
- The programme team should work to develop more sustainable means of supporting the G5 Sahel Joint Force, in a way which complements French and EU support.
- The programme should look to increase its engagement with the Malian armed forces (FAMA) ahead of and in support to the UK MINUSMA deployment.
- The programme should look to increase its focus on gender, for example by increasing efforts to address the gender imbalance amongst those receiving training.
- The programme team should review the results framework, to ensure it reflects the breadth of programme activities, and the chosen indicators provide a robust means against which to measure programme success.