Annual Review - Summary Sheet

PROGRAMME TITLE: Somalia Security Sector Reform Programme
Country and Region:	Somalia, Africa
IATI Unique ID:	CSSF-03-000027
HMG Partners (LEAD in bold)	Foreign & Commonwealth Office (FCO), Ministry of Defence (MOD), Department for International Development (DFID)
Total Budget:	ODA: £20.00m			Non-ODA: £54.80m
Budget this FY	ODA: £5.27m			Non-ODA: £14.49m
Spend this FY	ODA: £5.21m			Non-ODA: £15.25m
Original Programme Start Date: April 2015		Planned End Date: March 2021
Outputs					Score
Federal Government of Somalia institutions can: negotiate, sustain, and oversee implementation of agreements and policies that provide strategic direction for Somali security sector development, and exercise political oversight of implementation and delivery including performance and behaviour of security forces.					A
Selected Federal Member States can effectively plan for and coordinate security forces, and thereby proactively collaborate with the Federal Government of Somalia.					B
Somali Security Forces begin successfully taking on security responsibility from African Union Mission in Somalia (AMISOM) in selected Federal Member States, allowing transition to move ahead as laid out in the transition plan.					A
AMISOM remain to provide framework security and provide effective support to enable progress on transition.					A
Overall output score					A
Outcome Assessment: / Limited progress was made at outcome level. Although the programme is playing an important role in supporting the UK’s security sector stabilisation efforts in Somalia, a combination of factors including overly ambitious outcome targets and an increasingly fragile political settlement mean the programme will not realise the intended security sector reform outcomes by the end of the 20/21 programme period. Looking ahead, effort will best be spent on designing a new programme that incorporates achievable outcomes which more accurately reflect the complex programming environment.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	B	B	B	C	A	B	A	B
Risk Rating - low/medium/high	High	High	High		High		High
*output/outcome scores
How has the programme changed during this period?			Decision to end funding for the Joint Police Programme (JPP) (beyond 19/20). / The Joint Operations Command Centre (JOCC) project was closed. A contribution was made to the new Joint Security Sector Governance Programme (JSSGP). / Decision to discontinue the payment of Somali National Army (SNA) stipends from FY20/21.

What support did the UK provide in FY 19/20?
- Technical assistance to a range of Somali political and security institutions through a contract with Adam Smith International (ASI). ASI advisors were embedded within key institutions to help advance international and domestic agreements around security sector reform.
- A contribution to the multi-donor UN Development Programme / UN Assistance Mission in Somalia-delivered Joint Security Sector Governance Programme (JSSGP) to enhance planning, coordination and oversight of security sector governance institutions at the federal and state levels.
- Provision of training, equipment, infrastructure (barracks and training centre) and vehicles to support the Somali National Army (SNA), plus support for stipends and related third-party monitoring.
- Costs of UK military personnel working with the SNA and UK advisers in the UN, Comprehensive Approach to Security Strand 2 (CAS2A: Federal Government of Somalia Ministry of Defence and the Somali National Armed Forces) and EU missions and seven UK military advisers working in/with the Africa Union Mission to Somalia (AMISOM) Force Headquarters and related activity including training courses.
- Contributions to the UNOPS-delivered Joint Police Programme (JPP) and the DFID-led Security and Justice programme.

Key results for FY 19/20:
Incremental progress in improving the approach to policy and strategy development at the Ministry of Internal Security (MoIS), Office of National Security (ONS) and Ministry of Defence (MoD).

Regional Security Office (RSO)/ONS engagement improved via the JSSGP, and RSOs now established in each state. Progress was made in the development and implementation of Federal Member State (FMS) Ministry of Security (MoS) ID&CB Plans and RSO ID&CB Plans (all FMS).

Op TANGHAM (UK military capability building mission) made progress in providing training and equipment for SNA Sector 60 (Baidoa).

The Military Support Team (MST) had an effective range of engagement with AMISOM Force Headquarters, including advising senior AMISOM officers.

Key Lessons
Somali political will is the primary determinant of whether SSR in Somalia will be successful in the short term, and sustainable in the long term. Donors can support this agenda but cannot control it.

SSR is a long-term enterprise requiring sustained engagement from a broad collective of domestic and international stakeholders. Programme-level outcome targets must therefore be realistic and achievable within a programme’s timeframe.

Summary of recommendations for FY 20/21
- Related to the existing programme:
  - Complete/update missing elements of the existing Results Framework.
  - Review the risk probability and risk owner of the SSR Programme’s fiduciary risks.
  - Expand information sharing efforts with Implementing Partners, particularly in relation to HMG strategic intent.
  - Operationalise the Value for Money framework.

- Related to design and delivery of a future programme:
  - Document how and why UK support to SSR in Somalia has evolved into a single programme.
  - Review all SSR Programme workstreams and ensure they are a good strategic fit and likely to deliver against stated programme outcomes.
  - Re-consider the business case for CSSF funding the JSSGP in future years.
  - Consider ways to further build sustainability into UK support so that the SNA can be sustainable beyond the end of the programme.
  - Understand (through evaluation and research) the political economy of the Somali Security Forces (SSF), Federal Government of Somali (FGS), UK and other donors – to inform new programme design and enable future programme adaptation.
  - Ensure any future programme reflects the above recommendations and incorporates outcome-level targets that are realistic and achievable within the programme timeframe.
  - Develop a cross-HMG influencing or engagement strategy which seeks to purposefully identify UK access to Somali decision makers and to translate it into actual influence employed.