## Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Somaliland (Somalia) Programme
Country and Region:	Somalia, Africa
IATI Unique ID:	CSSF-03-000012
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £17.165m			Non-ODA: £1.237m
Total Spend:	ODA: £17.467m			Non-ODA: £0.917m
Original Programme Start Date: April 2016		End Date: March 2020
Outputs					Score
Improved police training capacity and capability					B
Justice Sector provides higher quality justice with more transparent processes and more predictable outcomes.					A+
Coastguard is better able to manage their own operations unsupported and better regionally coordinated.					A
Defence sector has improved accountability, is better managed and coordinated through the Ministry of Defence and leadership training capability increased and professionalised.					A
Voter registration system is ready to be deployed during the forthcoming election period. National Election Committee able to demonstrate they are prepared to deliver the upcoming elections.					A
Marginalised and minority groups can effectively participate in the elections and the political process around it. Women, People with Disabilities, minority led Civil Society Organisations and female journalists are more effective in public policy influencing, awareness raising and community mobilisation.					B
UK support enables Intergovernmental Authority on Development (IGAD) in delivering mediation between Somaliland and Puntland, generating access to key stakeholders for the UK.					B
Overall output score					A
Outcome Assessment: / The programme has contributed successfully to several key HMG strategic objects for Somaliland. These include supporting improvements in peace and security, support to more inclusive politics and increased democracy and working towards more accountable and effective institutions and service delivery.
Final Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	B	A	A	B	B	A	A	A
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium		Medium
*output/outcome scores

What support did the UK provide?

Security and Justice Sector Reform: technical, mentoring and capacity building assistance to the Police, Judiciary, Defence and Coastguard through a contract with Axiom International.
- Democratisation and Inclusive Politics: technical and capacity building support to the National Election Commission (NEC) and political mediation through Interpeace and Sahan Foundation. The UK invested in activity to support the engagement of women and minority groups in the upcoming Parliamentary and Local Elections through Action Aid.
- Regional Peace Building: support to the IGAD led Somaliland/Puntland Dialogue Mediation through increasing capacity for shuttle diplomacy, promoting confidence building and engaging with the parties to reduce tension and mitigate the risk of resurgent border tensions.
- Somaliland Government and Media Communications: support to improve government communications, professionalising the media and supporting a new media law through a contract with Coffey International.

What results did the programme deliver?

Security and Justice Sector Reform: A Police Training Board was established, and a Police Training Academy completed. The Judicial Court Management System is operational and judicial complaints process embedded increasing transparency and accountability of the judicial process. Coastguard command and control capability has improved significantly. Drafting of the Armed Forces Act and pensions regulations supported enhanced civilian oversight. Future leader training professionalised.

Democratisation and Inclusive Politics: Support to National Election Commission (NEC) has been key to the development of capacity and capability to independently manage elections, building political trust in the electoral process and better equipping women and minorities to participate.

Regional Peace Building: Dialogue was established between clans, political, and religious groups in Somaliland and Puntland. The Peace Committee and a ceasefire-monitoring group have been established.

Somaliland Government and Media Communications: The programme established professional courses and media training facilities at the University of Hargeisa, reform of the media law and development of a charter for journalists and media houses. It helped the Ministry of Information establish a centralised Government Information Service.

What lessons have been learned?

Sustainability is dependent on institutional buy-in and budget provision. There was support for reforms from key individuals in the justice sector, coastguard and defence. However, police reforms had minimal support and there is limited capacity within the institutions to fund ongoing costs. Though the NEC is established and functioning, there is a question of sustainability, particularly if there are further delays to the elections. IGAD will continue the peace dialogue process with support from other donors and partners. The media programme finished in 2019. Courses were subsequently funded through sponsorship from government and the private sector.

Programme Delivery: In the Somaliland context, relationships and continuity matter. There are, however, risks with the programme being dependent on individuals as opposed to institutional relationships for success. As above, sustainability should be a priority for future programmes.

Consolidated Programme Management: During the last year, the team improved programme management and the results are clear to see. Programme team efficiency would benefit from rationalisation on one site – not spread over three posts.

Financial Management and VfM: Future programmes should have clearly defined structures for oversight and how to measure value for money.

Partnerships: Future programmes should ensure there is sufficient capacity within the programme team. This will ensure effective management of implementing partners with differing levels of capacity, experience and capability.