Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Sudan: Conflict Reduction and Stabilisation
Country and Region:	Sudan
IATI Unique ID:	CSSF-03-000030
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget:	ODA: ODA: £0.5622m			Non-ODA: £0.861m
Total Spend:	ODA: ODA: £5.854m			Non-ODA: £0.76m
Original Programme Start Date: 01 April 2017		End Date: 31 March 2020
Outputs					Score
HMG informs, influences and leverages Government of Sudan and international actors to deliver effective responses at national, regional and sub-national level with linkages established between programmes and political access and influencing.					A
Strengthened, gender-sensitive conflict management systems and peacebuilding processes in place in Darfur (including addressing SGBV).					A
An inclusive transitional period and peace process where civil society, youth and women contribute meaningfully to decision making.					B
Overall output score A
Outcome Assessment: The programme has contributed to conflict mitigation and stabilisation in Sudan by strengthening Sudan’s conflict management architecture at the national and sub-national level. However, it did not meet all its outcome level indicators. The overall influence of the international community on the peace processes, which have lacked inclusivity and transparency, in Sudan has been limited.
Final Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2017/18*		2018/19*		2019/20*
Programme Score	A (output)	B / (outcome)	A (output)	B (outcome)	A (output)	B (outcome)
Risk Rating - low/medium/high	Medium		Medium		Medium

What support did the UK provide?
During 2017 and 2018, with the Bashir regime in power, the programme had two components:
1. Support to the national level peace processes in Sudan led by the African Union High-Level Panel for Implementation (AUHIP)
2. Support to community level resilience and conflict mitigation in two key conflict areas: Darfur and the Two Areas through two UN Development Programme (UNDP) administered programmes: the Darfur Community Peace and Reconciliation Fund (DCPSF) and the Community Security and Stabilisation programme (C2SP) in the Two Areas.

At the end of FY 18/19, support to the C2SP was halted due to underperformance and to make funding available for smaller scale catalytic work. Support to AUHIP was halted in May 2019 to make way for new forms of support to national level peace processes. Following the unseating and arrest of the former President in early 2019, the programme entered a period of hiatus where it was unable to commence new projects due to unrest and insecurity. In August 2019, the programme adapted its support to a new transitional context with three strands of work:
1. Support to the Juba-based peace negotiations via a UK-funded representative (through TetraTech contract); and logistical support to the Darfur track of the peace talks through the African Union - United Nations Hybrid Operation in Darfur (UNAMID).
2. Support to the Darfur Community Peace and Stability Fund (DCPSF).
3. Additional projects strengthen civil society actors in the transition through:
  1. Support to the establishment of the UN Office of the High Commissioner for Human Rights (OHCHR) in Sudan
  2. Support to the Sudan Women’s Task Force (STF) through International Non-Governmental Organisation (INGO) Search for Common Ground (SFCG) Sudan to engage with female civil society networks across the different states to enhance their capacity to raise issues with government institutions.
  3. Support to Westminster Foundation for Democracy (WFD) to engage with female political and civil society leaders on political party regulation and constitutional development.
  4. Support to INGO Conflict Dynamics International to engage with key political groups in the peace process to build trust through an increased joint understanding of options for the transition.
  5. Support to local NGO Sudan Social Development Organisation (SUDO) to prepare Darfuri communities for the Constitutional Conference that has been planned as part of the transition.

What results did the programme deliver? Will they be sustained?
- The programme strengthened community level conflict resolution capacities in Darfur and, to a lesser extent, the Two Areas. Support to the AUHIP resulted in limited progress on the national peace process under former President Bashir, but there was some progress on the Sudan-South Sudan border demarcation processes.
- Support to UNAMID helped enable its role in logistical support to the Juba peace processes. Support to the OHCHR has seen progress towards the establishment of its permanent office in Sudan.
- Other smaller scale projects were initiated late in FY 2019/20 due to the uprising. Almost all were extended past March 2020 and then further extended with the onset of the Covid-19 crisis. As a consequence, the results of these projects were only partial or unclear at the time of this Programme Completion Review.

What lessons have been learned?
- It is important to support CSSF programming with dedicated conflict/stabilisation related policy capacity. The absence of a Conflict Adviser between May 2019 and January 2020 meant that less technical, strategic and policy support was available during this time and fewer monitoring visits were possible.
- Programming seeking to influence national peace processes must acknowledge difficulties and set realistic outcomes.
- The programme provided good Political Access and Influence for HMG to assist its role within the broader efforts of the international community to influence peace building processes in Sudan.
- After the unseating and arrest of the former president, the programme had to adapt to major contextual shifts. It did so to a certain degree by shifting support towards the transition process by initiating a number of pilot initiatives. Although the Results Framework was adjusted, a renewed comprehensive contextual analysis was not undertaken until a cross-HMG workshop in January 2020.
- The programme has aimed to work on supporting peacebuilding/stabilisation processes at both national and sub-national/local levels, based on a theory of change that efforts at both levels were needed. A question remains around the added value of combining local level and national level peace building support.