Annual Review - Summary Sheet

PROGRAMME TITLE: Somalia Stabilisation Programme
Country and Region:	Somalia
IATI Unique ID:	CSSF-03-000028
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD)
Total Budget :	ODA: £8.31m			Non-ODA: £0
Budget this FY	ODA: £2.1m			Non-ODA: £0
Spend this FY	ODA: £2.258m			Non-ODA: £0
Original Programme Start Date: 01/04/2016		Planned End Date: 31/03/2021
Outputs					Score
Government finds favourable conditions for the establishment and continuation of effective district councils and/or formal district administrations.					A
Gender and conflict sensitive approaches to grassroots reconciliation and political negotiations are developed, integrated and transitioned, by the programme, in collaboration with AMISOM (African Union Mission in Somalia), Somali National Security Forces (SNSF), Federal Government of Somalia (FGS) and other stabilisation actors.					A
Community driven activities identified and delivered through inclusive participatory (community, AMISOM, Somali Security Forces, Ministry of Interior, Federal Affairs & Reconciliation (MoIFAR) and Federal Member States (FMS)) processes, supported with a combination of programme funds and assistance of other partners.					A
Overall output score					A
Outcome Assessment: Progress on outcomes has met expectations. The programme has helped the FGS/FMS plan, coordinate and implement gender and conflict sensitive stabilisation efforts in selected districts in South-West and Jubaland States. Expansion to Galmudug and Hirshabelle States has been incorporated into the programme during the last quarter. The programme has contributed to ensuring that AMISOM/SNSF can apply stabilisation approaches and sustain the conditions for inclusive grassroots reconciliation and political negotiations.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A	A	A	A	A	A	A	A
Risk Rating - low/medium/high	H	H	M	M	M	M	Medium	Medium
*output/outcome scores
How has the programme changed during this period? The programme has expanded its early recovery intervention to include newly recovered areas in Lower Shabelle, where it ran a strategic communications pilot project. The programme also did new exploratory work in Galmudug and Hirshabelle.

What support did the UK provide in FY 19/20?
A series of interventions aiming to reduce local drivers of conflict in areas of Somalia recently recovered from al-Shabaab (a-S) control and provide foundations for the local political settlements and stability and working with local and international actors to enhance civil-military coordination and influence Somalia’s overall approach to Early Recovery Stabilisation.

- The Early Recovery Initiatives (ERI) project provides advice and capacity building to the Somali authorities and AMISOM as they plan and conduct stabilisation initiatives in areas recovered from, or contested by, al-Shabaab. It establishes community platforms and dispute resolution mechanisms that help support the re-establishment of the FMS and FGS roles in these areas.
- The Building Confidence in Recovery (BCR) project was part of an ongoing pilot of communications work in local communities, reflecting specific concerns of the population to build support for and confidence in a return to government control in newly recovered areas and in communities still under al-Shabaab control.
- The immediate stabilisation support in newly-recovered areas such as rehabilitation of critical infrastructure or other needs that supports community resilience and reconciliation.
- Provision of institutional support for federal authorities and ministries in Mogadishu in stabilisation policy coordination.
- Assist the Ministry of Defence (MOD) and Somalia National Army Head Quarters (SNA HQ) to manage and direct Somali led teams and deliver capacity-building training relevant to stabilisation, as part of their pre-deployment training.

Key results for FY 19/20:
- ERI mediation and facilitation between communities, local government and security forces improved security and centre-periphery relations in targeted communities.
- The Building Confidence in Recovery (BCR) pilot gathered information directly from the Newly or Recently Recovered Areas (NRRAs) and released content to complement the early recovery programming.
- The programme continued to support UN Stabilisation in its coordination role and in two rounds of the Fragility Index & Maturity Model reports, now covering 24 districts out of the total 32 districts. These are the only available open source resource tracking stabilisation progress on the district level.
- The federal-level MoIFAR and state-level Ministries of Interior maintained ownership and expanded their involvement in stabilisation planning and delivery.
- The SNA has begun to demonstrate buy-in into Gender and Human Rights (GHR) accountability at the leadership level.

Key Lessons
- The immediate needs of communities in early recovery phase are basic and relatively simple, but need to be addressed with urgency to secure support for the government and security actors. There is a growing appetite within the FGS, the FMS and the SNSF to engage with early recovery through community engagement.
- The importance of ensuring the direct involvement of stakeholders in capacity building work i.e. ‘Showing by doing’ to ensure sustainability.
- More work is needed to close the gap between early recovery interventions and long-term stabilisation and development programming.

Summary of Recommendations for FY 20/21
- Continue to integrate support to the Newly Recovered Areas (NRAs) in Lower Shabelle with the rest of the ERI programming. Re-examine the targeted areas and modes of delivery to ensure support to the current and future NRRAs.
- Focus on further embedding the principles of early recovery, including GHR, in institutional structures.
- Take the lead in working with stabilisation partners in establishing the principles of a ‘transitional’ stabilisation phase.
- Ensure that the strategic thinking behind the support to the military campaign in Lower Shabelle is captured in the programme documentation and clarify the relationship between the programme intervention and the formation of district councils in the Results Framework.
- Prioritise Third Party Monitoring (TPM) and structured evidence gathering and data collection from the NRAs and consolidate ERI reporting, with a focus on summary and analytical over narrative reports.