Annual Review - Summary Sheet

PROGRAMME TITLE: South Sudan Conflict Reduction
Country and Region:	South Sudan
IATI Unique ID:	CSSF-03-000029
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget:	ODA: £14.6m			Non-ODA: -
Budget this FY	ODA: £5.02m			Non-ODA: -
Spend this FY	ODA: £4.92m			Non-ODA: -
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
Coordination and coherence: UK engagement supports national, regional and international actors to employ increased coherent messaging and strategies, while enhancing coordination between local peace initiatives and linking them to national level peace process. (27%)					A
Accountability: UK engagement via increased political access and influence / (PAI) strengthens the accountability mechanism of the Revitalised Agreement on the Resolution of the Conflict in the Republic of South Sudan(R-ARCSS) (27%)					A
Inclusivity: Marginalised groups are increasingly involved in resolving conflict through local conflict resolution mechanisms (17%)					B
Capacities: Increased capacities of constituencies, communities and leaders to manage and resolve conflict (25%)					B
Evidence and learning: Conflict / gender sensitive informed and adapted approaches implemented in all CSSF funded activities (4%)					Ao
Overall output score					A
Outcome Assessment: The programme continued to contribute value to HMG’s efforts to maintain and move forward the peace process and a more conducive context for future stability, especially at the national level. But the ‘pre-transition’ political context and the ten-month delay in forming a Government of National Unity (TGoNU) meant progress was slow. The fact that agreement was reached, with HMG playing a leadership role in ensuring this, was crucial. But overall, expected progress in most areas of the three-part outcome was only partially met.
Outcome Score: B			Risk: MEDIUM

Summary of Programme Performance
Year	2015/16	16/17	17/18*		18/19*		19/20*
Programme Score		B	A	B	A	B	A	B
Risk Rating – L/M/H		High	Med	Med	Med-H	Med-H	Med	Med
*output/outcome scores
How has the programme changed during this period?			The most significant change was the drawdown and end of two peacebuilding projects at sub-national level.

What support did the UK provide in FY 19/20?
- Provision of eleven international advisers to two implementation and monitoring bodies supporting the revitalised peace process, under the auspices of Intergovernmental Authority on Development (IGAD): the Joint Monitoring and Evaluation Commission (R-JMEC) and the Ceasefire and Transitional Security Arrangements Monitoring and Verification Mechanism (CTSAMVM).
- Funding two HMG members of staff in Juba and London dedicated to work on the peace process, supporting the UK’s Special Representative for Sudan and South Sudan.
- Support to the South Sudan Council of Churches (SSCC) to implement their Action Plan for Peace (APP) on inter-church peacebuilding and reconciliation at both national and subnational levels.
- Funding two subnational level projects: the Conflict Early Warning and Response System (CEWARS), implemented by Catholic Relief Services (CRS), which alerts authorities to conflicts, supports responses and builds local conflict-management capacities in three sub-national areas; and the Preventing Violence and Building Safer Communities project, implemented by Non-Violent Peace Force (NPF) which focuses on civilian protection and gender-based violence issues in Wau.
Development of a Peacebuilding Opportunities Fund (POF), to provide evidence, analysis and advisory support in four targeted locations and at national level, to identify areas for scaled up peacebuilding opportunities. A separate DFID annual review has been carried out on the POF, which this AR draws on.

Key results for FY 19/20:
- CSSF supported advisors provided expertise and capacity which enabled the R-JMEC and CTSAMVM to support progress to agree a transitional government and to monitor ceasefire violations respectively.
- CSSF-funded staff helped enable the UK to lead coordination of the international response to the peace process, helping to keep pressure on the parties to the agreement at a critical time.
- CSSF funding and support helped enable a high-profile retreat in Rome, where the Pope hosted Government and Opposition leaders, including President Kiir and Riek Machar, who made commitments to peace.
- The funding and enabling of a Wilton Park-facilitated regional conference which helped ensure better coordination and coherence of messaging among regional and international actors at a critical moment in the implementation of the agreement.

Key Lessons
- Advisory Support: UK-funded advisers to the peace process bodies made an important contribution to HMG’s diplomatic efforts on South Sudan. More rigour could be applied in this space in future in gathering evidence to assess how, and how much, these positions provide political influence.
- Subnational Programming: Small-scale, subnational peacebuilding interventions have had some local impact, but the programme has struggled to translate these into more than the sum of their parts. To maximise impact, future subnational programming needs to be larger scale, underpinned with better evidence and be more structured and better coordinated with other HMG and partner effort.
- Staffing and Structures: There is a high level of engagement on individual parts of the programme by policy and advisory staff. This is positive but also brings risks for a relatively small programme in terms overall direction, relative priorities and coordination. This is not made easier by key programme management staff being in Khartoum and Nairobi.

Summary of Recommendations for FY 20/21
Future Direction
Take full advantage of the FCDO merger to develop a single integrated staffing and resource approach to conflict, stability and governance policy and programming in South Sudan, simplifying current structures.
- Start now to develop a successor programme with an adaptive structure and an agreed, higher risk threshold at its heart, which can respond quickly to new opportunities in the transition. Consider how best to prioritise Women, Peace and Security objectives.
- As part of this, reassess where and how UK advisers can bring most value and influence to bear on the transition; develop new national level support, including on security sector reform, the future constitution and human rights.
- Undertake a rapid, light touch policy assessment of UK added value on sub-national peacebuilding, with practical recommendations on future UK focus and resourcing options. Take an early decision on the future of the POF.

Programme Management
Simplify the programme level Results Framework, ensuring all targets remain realistic and contribute to programme outputs and outcomes, using it more actively to assess progress.

Governance and Staffing
- Ambassadors in Khartoum and Juba to consider joint or alternate chairing of the Local Strategy Board (LSB). CSSF leads in Khartoum and Juba to jointly prepare LSB agendas and ensure more policy-focused agendas.
- Cease CSSF funding of the peace process Conflict Adviser in London by the end of FY20/21; maintain CSSF funding for a Juba-based D6/A2 slot, the role to include being SRO for the whole programme; end the current approach of policy/advisory leads acting as project-level SROs. Increase Programme Management capacity in Juba.